## Annual Review Template

Title: SUSTAINABLE URBAN ECONOMIC DEVELOPMENT (SUED) PROGRAMME
Programme Value £ (full life): 70 Million		Review date: September 2021
Programme Code: 204338	AMP start date: August 2016	AMP end date: September 2024

Summary of Programme Performance

Year	2017	2018	2019	2020	2021
Overall Output Score	C	B	A	A	A
Risk Rating	Major	Major	Major	Major	Major

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/16865377.odt
DevTracker Link to results framework:	http://iati.dfid.gov.uk/iati_documents/48845228.xlsx

A. SUMMARY AND OVERVIEW

Description of programme

The Sustainable Urban Economic Development Programme (SUED) aims to support selected counties and municipalities to be better prepared for well managed urbanisation. The programme has prioritised 12 smaller and fast-growing towns in Kenya’s sub-national regions to receive expert advice on: a) resilient urban economic planning; b) investment climate reforms; and c) investment attraction into value chain and infrastructure projects. In addition, the programme supports national-level urban development policies that have impact on municipalities, such as affordable housing strategies.

SUED responds to the fact that Kenya is rapidly urbanising. By 2050, almost half the population is expected to live in urban centres, compared to 28% in 2020. Poorly planned urbanisation is known to result in socio-economic inequalities, inadequate and unaffordable housing, high unemployment rates and vulnerability to climate and environmental shocks. Creating the right conditions now for inclusive and sustainable urbanisation in smaller, fast-growing, and marginalised towns presents an opportunity to achieve more balanced economic growth, reduce urban poverty and create climate-resilient livelihoods. The programme contributes to various pillars of the UK-Kenya Strategic Partnership including mutual prosperity, security & stability, climate change, and sustainable development.

SUED is delivered through a commercial contract with Tetra Tech International Development (Tetra Tech) providing programme management, technical oversight, and coordination functions for a group of specialist firms comprising an urban economic planning firm and investment attraction firms. Other programme components were previously delivered through a strategic partnership with the International Finance Corporation (IFC) of the World Bank Group and a commercial contract with Oxford Policy Management (OPM). These components ended in 2020.

Changes in the operating context

The operating context this year remained very volatile, both internally and externally, owing to the ongoing global COVID-19 pandemic. Externally, programme delivery was affected by the unpredictable cessation of movement and other COVID-19 protocols that the government continued to put in place as the country experienced different waves of the pandemic. This was in addition to deteriorating economic performance in the counties and rising political temperatures as Kenya anticipates general elections in 2022. The programme has continued to adopt to new ways of delivery, including virtual engagement with stakeholders where possible.

Within HMG, the seismic impact of the pandemic on the UK economy has forced the UK government to take tough but necessary decisions and, as announced in 2020, the UK has now moved to a target of spending 0.5% of GNI as Official Development Assistance (ODA) in 2021. Following a thorough review, the FCDO’s programme budget has been allocated in accordance with UK strategic priorities against a challenging financial climate of COVID-19. Throughout the business planning process, the FCDO has strived to ensure that every penny of the ODA spend brings maximum strategic coherence, impact, and value for taxpayers’ money. The move to 0.5% has resulted in changes to this programme, which is being adapted and will continue.

This Annual Review reflects that the programme has had to refocus resources and so will deliver against a new plan with new results targets. As a result, the findings of this Annual Review reflect on a programme in transition.

Summary supporting narrative for the overall score in this review

SUED has met performance expectation for the year (overall output score of A). Whilst some components were not fully met, these were largely due to the impact of budget cuts and changes in approach as needed. The internal business planning process took longer than anticipated, with final budgets confirmed in May 2021, when the SUED logframe targets for the year had already been locked. However, the final allocated budget for the programme was not sufficient to deliver all the components of the milestone targets for the year, as further explained in this report.

SUED has continued with its process-based approach to strengthening the municipalities’ urban economic planning capacity and supporting them to deliver on these plans with targeted investment attraction support. This combination of future planning and identifying specific projects for future investment, underpinned by sound political economy and capacity building elevates SUED’s impact and potential. With the urban economic planning component nearly completed, the programme is entering a crucial phase of bringing in concrete investment that will make the UEPs a reality. Getting the seed fund right is a critical factor for the successful execution of this shift from UEPs to investment attraction. Options for the seed fund are heavily dependent on funding availability which will be confirmed through the imminent Spending Review (SR).

A summary of the programme’s key achievements for the year are set out below:

Innovative approaches to investment attraction – a number of feasibility studies have been completed, an important step in the process of attracting investment. This can seem slow and overly detailed from the municipality’s perspective, but the investment attraction teams have done well to keep momentum and engagement with the towns in this process. Furthermore, given the challenge of the smaller size of financing required for some of the investments at municipal level, the implementing teams are looking at how to potentially package investments to make them more attractive to investors. There are already early signs of success, including attracting additional World Bank financing into a waste management project in Malindi municipality.

Strengthened governance capacity in the municipalities – a key achievement of SUED is that whilst its focus is on generating economic plans with towns and identifying projects, it also supports the strengthening of governance systems at municipal level. The work undertaken in Mandera to support a plan for transferring functions from county to municipal level, and in Eldoret to design new structures for the municipal governance, are some examples that are critical to enabling successful delivery of the economic development plans and investment attraction. These are also vital to the overall sustainability of the programme and future impact.

Integrated Programme Delivery Unit (IPDU) within the State Department of Housing & Urban Development – last year, SUED took on supporting national level presidential priorities on housing and the Nairobi Railway City project. This has been taken forward this year with progress in supporting the state department to identify investors for phase one projects of the Nairobi Railway City project (affordable housing, railway station and government precinct).

Firming up the programme delivery framework (Time Extension, MEL, and Contract Amendment) – this time last year there was a high level of uncertainty on the overall programme delivery framework including timelines, the monitoring, evaluation and learning work strand and with the inclusion of the two additional towns that were still outside the delivery contract. The programme team responded well to the recommendations of the 2020 annual review and have now secured a two-year extension to the programme timelines and a corresponding contract amendment with the lead implementor that now includes the additional towns. The MEL component has been adjusted accordingly and moved within Tetra Tech to respond to the fact that the independent MEL contract was cancelled in 2020 due to budget constraints.

Flexing with the Operating Environment – SUED has maintained the focus on its primary objective of supporting towns and despite challenges in not always being able to support in person, all implementors have demonstrated through delivery of results an ability to adapt and flex, ensuring that momentum is not lost. Further, the programme continued to take advantage of emerging opportunities. This year, SUED allocated a budget of £255,000 to complete work started by BE Beijing on the Isiolo-Mandera road annuity project that will raise private financing for the road, thus opening up the region and creating opportunities and security. BE Beijing could not complete this work given significant changes to budgets, but the project (which will connect two SUED municipalities) will amplify impact of the SUED project overall and deliver significant VfM for the financial commitment by BHC Nairobi.
A summary of the output scores is shown in Table 1:

Output	Summary of achievements	Score
Output 1	Counties and municipalities with strengthened capacity to manage and lead climate-resilient and inclusive urban economic development	A
Output 2	National and county-level business environment reforms reviewed and developed.	A
Output 3	Facilitation of public and private financing of climate resilient infrastructure and value chain projects.	A
Output 4	SUED insights, lessons and evidence produced and disseminated for internal and external audiences	A

Major lessons and recommendations for the year ahead

Key lessons learnt from this year are set out below:

Timelines: SUED is an ambitious programme whose success comes with careful investment of expertise and engagement with stakeholders. This takes time and there has been a challenge managing expectations with municipalities and county governments. The SUED team have ensured that at each stage there is a reemphasising of timelines, the long-term nature of planning, project preparation and moving to investment stage.

Politics: The political context has remained a critical issue for delivery. The challenges with some municipalities highlight the constant management of both expectations, linked to the timelines point above, but also the practicalities of working with counterparts who may have different motivations or objectives and can create blockers to progress. With Kenyan elections due in 2022, the impact of this will be magnified in the coming year.

Investment Attraction process: It is increasingly clear that there are factors outside of the control of the programme that are critical to facilitate investment. Whether this is the capacity of the private sector to be able to respond, or the success of identified projects depending on related value chain investments being led by other entities. The programme is ensuring they engage with these issues, keeping a close working relationship and considering where additional input might help facilitate progress.

Recommendations for the year ahead

Recommendation 1: challenges have arisen with some municipalities this year, in terms of engagement hindering the ability to progress work. BHC Nairobi and SUED implementors to consider principles/framework for deciding whether to continue or withdraw support from a municipality. (By December 2021)

Recommendation 2: the work undertaken by the IPDU consultants on affordable housing will have wider applications and useful knowledge transfer for other HMG posts who are also considering ways of supporting the sector. There are also potential connections with PIDG and CDC. The SRO to share this knowledge and evidence through relevant specialist cadres and utilise the PIDG representative on the Programme Steering Committee. (Continuous)

Recommendation 3: The seed fund will be a useful tool supporting element for delivering investment in the later stages of the programme. The SRO should ensure that an appropriate framework for delivering the seed fund is agreed and operationalised. (By December 2021).

Recommendation 4: It would be useful for the programme to consider lessons from other countries where municipalities have succeeded in grouping investment projects together to attract finance. There are particular examples from South African cities that SUED implementers should explore the possibility of replicating across SUED municipalities. (Continuous).

Recommendation 5: As noted above, the logframe was not updated in line with the most recent business planning and budgeting process. It should be revised accordingly including with results and milestones up to 2024. In doing this, the SUED team should consider existing HMG resources e.g., the Jobs Measurement Framework developed and launched by the Economic Cooperation and Growth department, the Cities and Infrastructure for Growth Myanmar jobs and investment attribution methods and CDC’s most recent revised jobs measurement approach for investment. (By November 2021).

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The SUED business case was anchored on the theory of change that through a holistic combination of urban economic planning, investment climate reforms and investment attraction into value chain and infrastructure projects, the programme will catalyse sustainable urban economic development, transforming urban markets into thriving growth hubs that will serve the rising urban populations. Building an enabling business environment alongside stimulating private sector investment into tangible projects will generate long-term jobs and income growth in the small and growing towns.

Impact statement: Inclusive economic growth and poverty reduction in selected municipalities/counties.

Outcome statement: Increased investment in selected municipalities - including investments in climate-resilient infrastructure or value chain projects.

The programme’s impact and outcome statements have remained the same as per the original business case. However, the assumptions underpinning the effective delivery of the results have been revised over the years as part of programme delivery, emerging evidence, and the changing delivery context. Within this year, there were changes to the theory of change and results framework to reflect a programme that is evolving due to the shifts in the operating context. The main change to the theory of change was the Inclusion of the National-level support through the Nairobi Railway City Project. As indicated in the 2020 annual review, SUED has dedicated an allocation of budget to support the national government in preparing for the implementation of the Nairobi Railway City project - a multi-modal, transit oriented, urban development that incorporates mixed use commercial developments, housing, and intermodal facilities. The project has huge potential to promote and further enhance the global competitiveness of Kenya’s capital city Nairobi, but also to create impact and connectivity to the surrounding urban centres.

The development of major city hubs, creating hub-and-spoke models of economic development, is well understood in urban development. Nairobi provides an important anchor city that generates wider economic benefit for surrounding towns. Furthermore, the support to the railway project and on affordable housing as part of the IPDU work has enabled SUED to make stronger links with national government and in particular the State Department of Housing and Urban Development. This is important as it creates opportunities to raise the awareness of SUED and its work with national level officials and Ministers.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

SUED is on track to meet expected outcomes and impact. The types of projects being supported through the investment attraction process have the ability to generate both job creation and wider benefits to local economies. Furthermore, the plans generated at the start of the process for each municipality lay the framework for wider impact for municipalities as they use these plans to build out longer term ambitions.

The next phase of the programme, adding two more municipalities, and the investment attraction work to link with investors and break ground on projects is on track. The programme should now begin to track performance towards outcome and impact level indicators as it comes into its last three years.

Across the department, FCDO is refining approaches to job creation measurement, including how technical assistance to support investment in infrastructure projects can generate jobs and how to measure attribution for investment mobilised. There are also other technical assistance programmes that have attempted to track results. It would be useful for BHC Nairobi and the SUED team to link up with these programmes and teams to see how they could inform results for this programme.

There could be a challenge to delivering the same level of support and impact for the additional two municipalities as potentially the time allowed for this in the remaining years might be constrained. This could have VfM implications, and the SUED team should consider where they can learn from the previous rounds of support to Group 1 and Group 2 towns to maximise the ability to quickly develop the work with the new towns.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Despite ongoing challenges with the operating environment, uncertainty over budgets and the shape of the pandemic in Kenya, SUED has managed to navigate these issues well. It is committed to delivering support to municipalities as well as looking more broadly at the wider impact the programme can have on national level policies. The next three years will define the results of the entire programme and it is important that issues of sustainability are considered. The programme is highly relevant to the wider portfolio. The SUED programme is a critical vehicle for delivering the UK-Kenya Strategic Partnership, supporting across multiple pillars - mutual prosperity, climate, security, and sustainable development.

## C. DETAILED OUTPUT SCORING

Output Title	Counties and municipalities with strengthened capacity to manage and lead climate-resilient and inclusive urban economic development.
Output number:		1	Output Score:	A
Impact weighting (%):		35%	Weighting revised since last AR?	Yes, upwards from 30% to 35%

Indicator(s)	Milestone(s) for this review	Progress
1.1 Climate smart Urban Economic Plans developed and adopted, demonstrating stakeholder engagement and participatory development	- Climate smart UEPs for 3 municipalities (Group 2) adopted by municipal boards, with evidence of stakeholder engagement and participatory development. / - 3 UEP launches held to publicise the UEPs (Group 2) / - Draft climate smart UEP's for G3 (Eldoret, Kerugoya, Mandera) completed .Diagnostic Report Completed for Lamu Municipality	A – Met Expectations / 2 UEPs adopted. (Kathwana Municipality UEP adoption pending) / 2 UEPs launched. (Kathwana Municipality UEP not launched). / Group 3 draft UEPs completed and one diagnostic report for Lamu completed.
1.2 Level of enhanced capacity of municipalities to develop, implement and manage sustainable urban economic development	Capacity gap assessments report for 10 municipalities submitted to FCDO / - Capacity building interventions completed in: / - Training in Financial Management and Revenue Enhancement and reports submitted to FCDO (10 municipalities) / - Training in Urban Governance conducted (10 municipalities) and reports submitted to FCDO / - Finalised construction of the Covid-19-safe market in Kisii Municipality.	B – Moderately not met Expectations / Capacity assessments completed in December 2020 for 10 municipalities. Only G1 municipalities completed financial management training as capacity building component put on hold due to budget cuts. The urban governance training was also not completed due to cuts and change in approach within the programme. / Construction of COVID stalls complete.
1.3 Level of enhanced capacity of the State Department of Housing and Urban Development to develop and implement national- level policies for resilient and future cities	- Finalised review of the Nairobi Railway City master planning document. / - Complete a PPP Feasibility Study for NRC Phase 1 to determine whether Phase 1 of the project is commercially viable. / - Delivery of a bidders' conference for the NRC master planner.	A – Met Expectations / The reviews of the master plan was completed. / The workplan was changed in agreement with the state department to move straight into tendering process for the phase 1 projects.

Briefly describe the output’s activities and provide supporting narrative for the score.

Overall, this has been a successful year of progress for the SUED programme in building on and further strengthening the work of the Urban Economic Plans (UEPs), targeted capacity building support and the work for the IPDU. All three elements of this output remain on track as per the revised workplan.

Urban Economic Plans
The programme has successfully launched or drafted UEPs across six municipalities and all the plans were adopted except for Kathwana. The latter was due to lack of engagement by county and municipal counterparts, raising the political risks that can emerge, despite robust stakeholder management and consultation.

The UEPs are in-depth, technical documents that also outline the broader ambition for the towns, providing a basis for governors to set out their long-term visions. The quality of these plans, especially the forward-planning to consider climate and spatial issues, is optimal. Furthermore, there is a connection between the UEPs, which are not formally required within the Kenyan planning system, and the formal spatial plans. A number of towns are using one to inform the other and vice versa.

There were some important reflections captured from the towns as part of this annual review on how the programme has supported them. Specific comments included – ‘we have been able to leverage the programme to push for agendas like markets and business incubation and also highlight action on important issues such as revenue raising’. On the longevity and usefulness of the UEPs one municipality from the G1 cohort stated that the UEP was ‘a living document that the municipal board uses to guide development and investment’.

There is also a major opportunity to influence county and national level policy both on how to approach planning and future economic growth in the country. The UEPs potentially offer a blueprint of key economic hubs across the country, where towns are set to urbanise fast or are already growing and turning into cities. This highlights the ability of SUED to affect bottom-up processes for local economic development and translate the work into a wider evidence base and real time planning resource for national government. The extent to which the UEPs can inform future development at local and national level will be key to the wider impact of the programme and future sustainability of HMG’s investment. The next few years provide a critical time period for taking the next steps on this.

Capacity Building
Capacity building was reduced within the programme due to budget cuts. This meant that only the first cohort of municipalities (G1) received capacity building for financial management. Unfortunately, the other municipalities expectations had been raised through the capacity needs assessment and knowledge of the training conducted in the G1 towns. The feedback from all the towns interviewed for this review highlighted the importance of this component and questioned when such training will be given to them. It is positive that the programme has pivoted to support capacity building for investment attraction which will be critical to support delivery of the investment activities – discussed further in output 2.

Given the budget constraints this was the right approach to take, however as discussed in the previous review the BHC SUED team and implementors should consider other options for getting capacity building across other areas into the programme. A potential option emerging is to link up with the new BHC Nairobi Devolution programme which may have capacity to build on the needs assessment work from SUED and provide support. This could be both an opportunity to address the challenge of continued capacity building support and build the links between two programmes working at the devolved level, ensuring coherence across the BHC Nairobi portfolio.

Overall, the capacity assessments were welcomed and one town in particular highlighted how it had impacted their planning and recruitment ‘the capacity assessment has helped us identify future staff recruitment needs and has meant we have focus on getting an investment lead and fast-tracking some recruitment to support us deliver’.

Kisii Covid Market: This was a pilot project that responded to a real time need on how to support livelihoods to continue in the pandemic. SUED’s support on this is complete and the intention had been for the municipality to source funds to scale it, however the municipality has struggled to allocate budget for it. There have been lessons learnt, including the fact that a more thorough scoping at the onset of this intervention would have been useful to ascertain the magnitude of demand. The pilot phase is currently not viable as the demand (about 2500 traders) far outweighs the completed stalls (just over 300). SUED is providing some support to the municipality to identify new sources of funding, but beyond this SUED should draw a line under its support to this project.

Integrated Programme Delivery Unit (IPDU): Over this year the work of the consultants delivering on the national level urban development policies and the Nairobi City Railway project have become more integrated into the programme. There is a clearer rationale and narrative for the IPDU work supporting wider SUED interventions, providing a national level connection with government, in particular the Department of Housing and Urban Development, which is also important for raising the profile of SUED above county level.

The Nairobi City Railway project is of national importance and overseen by central government. The support through SUED for the first phase secured partnerships at the UK-Kenya Africa Investment Summit in January 2021 and is now following through to support identification of investors to implement the first phase of the project which includes affordable housing, the railway station and government precinct. This element of the SUED work has synergies with potential UK investment with opportunities for UK design, engineering, and construction to be involved in the development.

A future challenge for the Railway City will be dealing with the land that has been allocated for the project. There will be need for a strong emphasis on stakeholder engagement to come up with an approach to addressing the various tenures - private landowner, leaseholder and public held land.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

The strength of the UEP analysis and stakeholder engagement is critical to underpinning the identification of priority projects as well as long term vision for the towns. This represents good value for money. The time and technical assistance put in at this stage while significant can reap high returns both for the immediate delivery of the next stage of the programme and the towns longer term ambitions for development.

The importance of capacity building has been highlighted and despite the narrowing in focus on future support it remains a critical part for the programme. It can be relatively low cost to deliver but has a high return for sustainability of the skills and expertise built beyond the lifetime of the programme.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The indicators on measuring the support to IPDU and on covid response (COVID-free market stalls) were added to this output this year. Also, the output weighting was increased from 30% to 35%.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Last year’s review recommended a revision of the entire results framework and logframe - given the COVID-19 context - in order to appropriately adjust milestones targets, while maintaining the overall ambition of the programme. This has been completed including better reflecting the IPDU work in the results. However, there will need to be more work to consider outcome and impact results – this is discussed further under output 4.

Recommendation: challenges have arisen with some municipalities this year, in terms of engagement hindering the ability to progress work. BHC Nairobi and SUED team to consider principles/framework for deciding whether to continue or withdraw support from a municipality.

Recommendation: the work undertaken by the IPDU consultants on affordable housing will have wider applications and useful knowledge transfer for other FCDO posts who are also considering ways of supporting the sector. There are also potential connections with PIDG and CDC. The SRO to work with IPDU consultants to reach out to other FCDO posts to make relevant connections and utilise the PIDG representative on the Programme Steering Committee as well.

Output Title	National and county level business environment reforms reviewed and developed.
Output number:		2	Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR?	Yes, Reduced from 25% to 15% to reflect reduced scope due to the closure of the IFC component.

Indicator(s)	Milestone(s) for this review	Progress
2.1 No. of business environment reforms, including climate related, initiated by SUED that have progressed within a) agreed timeframes and b) implemented by National and County government	- Finalised strategy for SUED’s Business Environment Reform work completed. / - 3 mini competitions for Investment Climate Advisers launched and concluded.	Not scored. / This component was cancelled due to changes in the scope and budget of the programme.
2.2 Level of enhanced capacity in all SUED municipalities to implement and manage business environment reforms	-Completed Capacity Needs Assessment including information of factors prevailing in municipalities to drive BER implementation / - 3 Pre-feasibility workshop held to facilitate understanding of current and potential changes taking place within the municipalities, particularly in the COVID-19 context	A – Met Expectations / Capacity Needs Assessments and 3 pre-feasibility studies for the Group 1 municipalities were completed as of December 2020.

Briefly describe the output’s activities and provide supporting narrative for the score.
Output 2.1 on business environment reforms – was cancelled due to changes in the scope and budget of the programme.

However, output 2.2 has met expectations with pre-feasibility study training for Group 1 towns delivered. Capacity needs assessments were completed to identify gaps in the towns. It will be important to consider how to support the next stage of this output due to the cuts to the wider capacity building element of the programme. Support on investment attraction will now be the main focus for the capacity building work. The towns consulted as part of this review underlined the importance of this. SUED may want to consider how to link the financial management training that had to be paused due to budget cuts with investment attraction training. Understanding how to engage and attract investors, put in place appropriate business environment reforms, and conduct rigorous feasibility assessments are all critical for achieving investment. However, being able to manage that investment and more importantly being able to demonstrate sound financial processes are important to secure finance and to reassure potential investors of the town’s financial capabilities.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

As identified in the previous output, capacity building is key to building long-term sustainability and impact for the programme. Delivering investment ready projects and ultimately agreeing a set of investment deals are underpinned by the municipalities being able to engage with investors confidently and address the business environment challenges. However, the sharp focus on building capacity and business environment reforms around SUED’s investment pipeline has potential to be effective.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
The output weighting was reduced from 25% to 15% to reflect the early closure of the IFC component and the removal of business environment reform work.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Given the increasing significance of supporting Nairobi as an anchor to secondary towns, last year’s review recommended that the programme considers a more sustainable structure for supporting the identified activities rather than the ad hoc approach at that time. Given the uncertainties around budgets, it was not possible to enter a longer-term commitment for this component. Instead, short-term technical assistance was agreed to facilitate this year’s support.

Output Title	Facilitation of public and private financing of climate resilient infrastructure and value chain projects.
Output number:		3	Output Score:	A
Impact weighting (%):		35%	Weighting revised since last AR?	Yes, Increased from 30% to 35%

Indicator(s)	Milestone(s) for this review	Progress
3.1 No. of municipality-based climate resilient infrastructure and value chain projects progressed and finalised.	G1 towns / 9 pre-feasibility reports completed / 3 due diligence reports submitted to FCDO / G2 towns / Project screening and selection report that shortlists projects for pre-feasibility with clear selection criteria submitted to FCDO	A – Met Expectations. / All feasibility and due diligence reports were completed for G1 towns. / Project screening and selection reports for pre-feasibility for G2 towns all completed by July 2021.
3.2 Investment promotion strategies done in conjunction with the municipalities/Counties to broaden municipalities ability to attract investment	2 Investor readiness workshops completed / 1 Investor mapping database completed	A – Met Expectations. / Investor readiness workshops and mapping database were completed this year.
3.3 No. of climate resilient infrastructure and value chain development projects in implementation with sustainable financing models as a result of SUED support	Seed Fund guiding principles document presented to all municipalities. / Finalise TOR for Seed Fund investment committee and intake process	B – Moderately did not meet expectations. / The programme prepared the guiding principles for the seed fund, however more time was needed to think through the operationalisation framework before presenting to the municipalities. (discussed below)

Briefly describe the output’s activities and provide supporting narrative for the score.

Investment Attraction
This component is implemented through the investment attraction specialist KMPG and Open Capital Advisers (OCA). The partners have made strong progress over the last year, despite the challenges in the operating environment, particularly not all team members being able to provide support in person.

Feasibility studies were conducted on the top 3 projects for the first cohort of municipalities (G1). Of the nine projects studies, seven were judged as feasible and moved to the next step of investment attraction – investor outreach and due diligence assessment. It however emerged that the pathways for most projects were complex, sometimes dependant on factors that are outside the direct influence of the programme. These have been discussed with the SUED team and a flexible approach based on the uniqueness of each case has been agreed. There is also a clear recognition of the challenge of the smaller sizes of some of the potential projects, a common issue at sub-national levels. Therefore, the investment attraction teams are considering ways to look at portfolios of investments, perhaps grouping more than one waste management project together for example, to make them more attractive for investors.

During the discussions with towns as part of this review it emerged that some of them are also launching their own investment attraction processes, sharing the UEPs with potential investors to generate interest – one municipality stated that ‘the programme has focused us on attracting investment and we are now reaching out and inviting other investors to meet with us’. This demonstrates the multiplier effect of the investment promotion work outside of the programme.

There are some examples of supporting climate-resilient projects. In Isiolo - a low lying town which experiences major flooding, a project to focus on sustainable urban drainage has been identified. Investing in drainage systems, managing the water sources and storm water management are all critical for building future resilience. To note however this particular project involves resettlement of some community groups, a complicated process even where agreed parameters for how to do this are in place. The SUED team will need to carefully monitor how they support Isiolo to undertake this, what their role is in this and be prepared for potential issues arising and have mitigation actions ready.

Seed Fund Facility
The delay in confirming the details of the seed fund - how or when it will be deployed is a concern. The seed fund facility is a critical element in supporting the later stages of the investment process, especially as the projects move through feasibility to packaging the projects ready for investors. It is well known that reducing the risk on projects is important to attracting investors, especially where towns lack capacity, or ability to demonstrate previous experience managing capital investments. Seed fund support, whether through more targeted technical assistance at the upstream investment stage, or downstream deal support, could be an important factor in the next stage of this programme.

Flexibility has been allowed within the programme to provide some targeted technical assistance for transaction advice and due diligence assessments which has been successful. Whilst this has been effective, the BHC SUED team needs to confirm the operating framework for the fund. Options for this are however heavily dependent on funding availability which will be confirmed through the imminent Spending Review (SR).

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

The programme has considered the importance of gender and inclusion across the components. In particular at the investment attraction stage the implementers have developed and supported towns to consider gender considerations in the projects identified. The approach taken has been to acknowledge there will be gaps at municipal level in experience in gender issues and how to incorporate this into planning and investment considerations. The implementors have taken a sound approach, considered issues of economic empowerment for different groups and equitable access to infrastructure and services, alongside the importance of human capital development. This approach is important in maintaining the equity of the programme.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
The milestone indicators were revised to better articulate the ambition of this output.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

A key lesson learned has been the importance of ensuring a close working relationship between the urban planners and investment attraction specialist so that the latter have a stronger understanding of planning needs and ambition of the municipalities and how projects are initially identified.

Recommendation: The seed fund could be a useful supporting element for delivering investment in the later stages of the programme. The BHC SUED team needs to firm up the operating framework for the fund within 3 months.

Recommendation: It would be useful for the programme to consider learnings from other countries where municipalities have succeeded in grouping investment projects together to attract finance. There are particular examples from South African cities that SUED implementers should explore the possibility of replicating across SUED municipalities.

Output Title	SUED insights, lessons and evidence produced and disseminated for internal and external audiences
Output number:		4	Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1 No. of SUED engagements, knowledge management and learning products produced	Best practice report (1) – “Working with Municipalities to Ensure Local Ownership of Urban Economic Development” / - Annual Newsletter (1) / - Success stories (3) / - How to guide on conducting pre-feasibility studies at municipal level produced by OCA on pre-feasibility stage to be shared with KPMG.- 3 After Action Review Reports developed. / - 2 case studies from selected feasible G1 projects that demonstrate the positive environmental and climate resilience aspects of these projects.	A – Met Expectations. / All knowledge and learning products were completed for the year across best practice, success stories, how to guide and case studies.
4.2 No. of SUED engagements, knowledge management and learning products disseminated with SUED's target audience	Evidence of sharing of knowledge and lessons learnt from programme implementation demonstrated through: / - Annual newsletter, best practice report and success stories (3) published on SUED website. / Engagement meetings: / - Governors meetings (2) / - Private sector (5) / - Public sector (3) / - Consultative Forums (2) / Kisii covid-19 impact study disseminated widely to development partners’	A – Met Expectations. / The range of leaning products were produced and disseminated throughout the year – all were completed by August 2021.

Briefly describe the output’s activities and provide supporting narrative for the score.

Lessons and Knowledge Sharing
Previously, SUED had an independent MEL component, which was however closed in 2020 as part of the budget realignment processes. This created a gap in the programme’s MEL functions. However, SUED has adjusted and responded well by strengthening the internal monitoring and learning capacity of Tetra Tech to take on additional MEL functions.

The learning component of this output has been strong, this is both demonstrated through the products produced but also the facilitated meetings between different implementing partners to learn from each other. Feedback loops become critical in a programme like SUED with groups of towns at different stages and multiple implementing partners. It becomes even more important when much of the work is being delivered remotely.

The dissemination of the Kisii covid-safe market study to other development partners is important given the potential wider application of the design across the country and internationally.

Over the next year, SUED should begin mapping out how to package and communicate learning across the phases of the programme which can be shared with more widely. Whilst the timing of this would likely not be until the final two years, once a full cycle has been completed – where municipalities have been through UEP and investment attraction with investment secured – it is useful to consider how to draw out this learning that has potential to inform policy development at HQ level on investment as well as future programmes.

Monitoring and Results
The approach to monitoring results and thinking creatively about projecting future results has regained momentum, following the upgrade of the Tetra Tech Internal MEL capacity. SUED has looked at future targets though extrapolating from current results given the phased approach to the programme. The team has been able to look at results emerging from Group 1 towns and agree targets that could be carried forward for the final 3 years. The logframe was revised earlier in the year although this now needs to be updated further in line with the country plan.

There remain challenges related to the ability to collect accurate data given restrictions for travelling to towns and constrained budgets limiting the level of more in-depth studies. This will be monitored in the new year as the COVID-19 situation evolves in the country.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

This output is critical for supporting the overarching value for money of the programme. Through lesson learning, feedback, and dissemination of best practice across implementors and components the programme has the ability to drive improved efficiency and improve sustainability of results. Despite the setback with the cut to the MEL contract the results this year show this output continues to deliver VfM, especially given the flexible approach taken to strengthen the internal MEL function within SUED.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Following the closure of the independent MEL component, the internal MEL function of Tetra Tech was strengthened by hiring senior personnel.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Given the decision to close the independent MEL contract, the last review recommended the programme team to consider alternatives to achieving a rigorous monitoring, evaluation and learning in the programme. This has been fully implemented, with the team strengthening the internal MEL function of the lead contractor (Tetra Tech) as described above, while allowing flexibility to commission short-term independent pieces of work as need arises.

Recommendation: As noted above the logframe was not updated in line with the most recent business planning and budgeting process. It should be revised accordingly including with results and milestones out to 2024. Consideration should be given for how to add stretch targets where feasible within the results.

Recommendation: This is a high value programme and communicating results at outcome and impact level will be important over the last three years. The SUED team and SRO to consider how to align to the Jobs Measurement Framework developed and launched by FCDO’s Economic Cooperation and Growth department, the Cities and Infrastructure for Growth Myanmar jobs and investment attribution methods and CDC’s most recent revised jobs measurement approach for investment.

D: RISK

Overview of risk management
SUED is judged as a major risk programme. This year has seen the emergence of new risks due to the changing operating context and future potential political impacts from upcoming elections in 2022. The key risks are set out below:

Politics and the Kenya Elections 2022: The programme team have highlighted the potential risk the upcoming elections pose. As has already been reflected in the lessons learnt from this year, political engagement is key becoming a blocker to making progress. The elections next year could mean changes in governors and therefore a reset process in those municipalities affected. The team are aware of the risks and are putting in place appropriate mitigations such as building strong engagement with technical teams within the municipalities. This will be an ongoing risk that will need close monitoring and strong political economy analysis.

Capacity Building: The challenges of budget constraints create risks around the sustainability of the programme, where municipalities need more foundational support to get the processes right before being able to capitalise on the benefits of the SUED programme. FCDO Kenya and the SUED team recognise this and are putting in place options for how to support broader capacity building for the municipalities.

Seed Fund: As reflected in this review, pinning down the future operation of the Fund and moving it into implementation will be important. There is a risk that the technical support the programme has provided to get projects to investment stage could be undermined if a critical area of support on buying down risk is not in place. This also poses a risk to delivering results.

Change in Team Leader: At the time of this Annual Review the Team Leader for SUED has moved on to a new job. And, whilst the transition has been well managed and a new team leader with relevant skills and experience identified, there is a risk that momentum is lost in relationship management in the transition phase. There are already good mechanisms for working with both the municipalities and with downstream implementing partners which should mitigate some of this risk. The Tetra Tech team and BHC Nairobi will need to work closely to onboard the new Team Leader and set expectations.

SUED has a receptive risk appetite overall (willing to accept the majority of activities carrying a major degree of residual risk). The risks are monitored and managed through the programme delivery plan and the online risk register in the Aid Management Platform (AMP). The team takes an open approach to risk management with risks discussed at the bi-weekly programme catch up meetings between the BHC team and the implementors. Risk escalation is robust, both from the implementers to the BHC team and within the BHC itself. The BHC sub-regional advisers have been instrumental in supporting risk management, through more frequent visits and engagement with SUED counterparts in the regions, as well as providing political intelligence that is useful in understanding the nuances.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency.

SUED continues to demonstrate flexibility in its implementation, adopting to the changing context in a way that minimises risks and takes advantage of emerging opportunities. The programme’s delivery framework has significantly changed from what was envisioned in the business case, particularly over the last two years, in response to the adverse impact of the COVID-19 pandemic. The process of closing the IFC component and the independent MEL contract that was initiated in the previous year due to the impact of COVID-19 and shrinking budgets was finalised within the reporting year. SUED is now solely implemented through the Tetra Tech contract and a downstream network of specialist firms, as set out in diagram 1, below.

The programme delivery framework has been firmed up this year. As per the recommendation of the last annual review report, the programme team sought an approval to extend the programme timelines by 24 months to allow sufficient time for delivery and recover time lost over the COVID-19 Pandemic. This was granted, with the new programme end date now being September 2024. Subsequently, the programme team renegotiated the contract with Tetra Tech, to take into account the changes in timeframe and scope. This has brought much-needed stability to the programme delivery framework, formally includes the two additional towns that were previously still outside the TetraTech contract and provides a viable timeline to implement the programme.

The BHC SUED team has built a good working relationship with Tetra Tech that is based on openness and trust. Progress on programme delivery is monitored through bi-weekly programme catch up meetings between BHC and Tetra Tech; detailed quarterly reports followed by quarterly review meetings; strategic field visits including by the BHC sub-national advisers; and through the Programme Steering Committee that provides strategic insights. Downstream, Tetra Tech holds monthly meetings that bring together all the technical partners, while continuing to engage them on an ongoing basis through the Tetra Tech technical leads. Following the closure of the independent MEL contract, the internal MEL unit at Tetra Tech was strengthened by hiring a senior manager to fully bring in-house the monitoring and learning functions of the programme. This however means that the detailed independent programme evaluation that was included in the original business case will not be undertaken.

Tetra Tech has met expectation as the lead contractor and has shown adequate flexibility and responsiveness in the volatile delivery context. The partner was marked as a good performer in the strategic partnership scorecard review of April 2021.Towards the end of the year, the legacy SUED team leader exited the programme and a new team leader had been identified through a rigorous recruitment process, to join the team from September. Whilst this had the potential risk of disrupting delivery, the process was well managed by Tetra Tech and BHC through speedy recruitment process. The process of onboarding the new team leader should be prioritised.

Financial management of the programme has been satisfactory – meeting 97% of forecast target. Following the business planning process and budget allocation, the programme teams worked together to reorient the programme delivery plan and corresponding budget lines. All payments are made upon satisfactory achievement agreed milestones. Diagram 1 below shows the financial performance against the forecast for the year. The budgets for the new year was agreed as part of the business planning process. SUED will spend a total of £6.4m, mainly allocated to completion of urban economic plans and progressing the investment attraction activities.

Diagram 1: Summary of SUED financial performance

Component	Description	Budget	Spend	Variance	%
204338-102	Management Costs- Tetra Tech	1,116,371	1,116,371	-
204338-103	SEED Flexible Fund		-	-
204338-105	Investment Attraction- KPMG/OCA/ NRC	2,172,721	2,059,657	113,064
204338-106	Urban Economic Plans- Atkins	1,343,696	1,300,350	43,346
204338-107	ICF Trust Fund			-
204338-108	Monitoring and Evaluation	294,014	294,013	1
204338-109	Programme Coordination for depart for Housing and Urban planning	300,000	293,940	6,060
	Total	5,226,802	5,064,331	162,471	97%

Value for Money

SUED has developed a Value for Money matrix to assess and measure VFM performance against specified indicators. The updated report on the VFM indicators is annexed to this report here. The programme implementers report on the VFM indicators on a quarterly basis. The programme is judged to be delivering value for money and has been flexible to change the delivery plan in a way that maximises value for money. Below are examples of the VFM parameters:

Economy
FCDO’s contract with Tetra Tech is fully milestone based with payments made only on completion and FCDO’s verification of milestones. Tetra Tech’s profit margin is capped at 6%; all costs to sub-contractors are on a pass-through basis and Tetra Tech does not charge additional overheads or profits on these. Sub-contractors are procured through competitive bidding processes.

Efficiency
The programme has worked to harmonise implementation approach and sequencing; and leverage each partners’ strengths and experience. For example, Tetra Tech has developed a framework for engaging downstream partners in a more coherent manner; all partners participate in monthly Programme Working Group meetings to identify ongoing implementation synergies. Further, as part of the response to the impact of the COVID-19 pandemic, SUED team has refocused programme delivery to only continue with components that provide maximum value towards achieving the intended outcomes.

Effectiveness
The team has worked closely with the county governments and municipal boards to ensure ownership of the project development and implementation process. This is enhanced by: (1) signing of participation agreements with municipalities to define the responsibilities of each party and the basic conditions for collaboration under SUED 2) building the capacity of the municipal boards to manage SUED projects after the programme ends; (3) official launch of the Urban Economic Plans and (4) institutionalisation of counties’ contribution to SUED through legislation, to maintain programme gains in the face of elections and potential changes in county governments over the life of the programme. Effectiveness will be measured by assessing the progress from output to outcome as defined in the results framework.

Equity
The Programme through the Urban Economic Planning (UEP) process is addressing the key principles of inclusion and climate change mainstreaming, which is evidenced through business surveys, case studies etc. UEP diagnostic phase already underscores the need for proposed projects to be grounded on social inclusive principle, promotion of green and low carbon infrastructure, and minimising environmental impacts. There are early signs of inclusive access to economic opportunities for all. For example, potential projects are scored against, among other criteria, their potential to improve access to employment for youth, women, and people with disabilities. The weighting of project selection criteria is agreed with local stakeholders within each municipality (there is evidence that representation by marginalised groups in the UEP process is targeted).

Diagram 2: SUED delivery chain 2021

Date of last narrative financial report	July 2021	Date of last audited annual statement	30th September 2020 (unqualified opinion with no significant risks identified).

Annual review process
This annual review was conducted by HMG’s Cities and Infrastructure Adviser based in Ghana. It involved a mix of desk review of documents and virtual meetings with stakeholders as listed below. The report was quality assured by the FCDO Kenya’s accountability and results team.

List of Stakeholders engaged through virtual calls
Director – Tetra Tech
Team Leader – Tetra Tech
Thematic Leads for Capacity Building, UEPs and MEL – Tetra Tech
Municipalities – Iten, Eldoret, Kisii, Mandera
Investment Attraction Implementers – OCA & KPMG
Nairobi Railway City and Affordable Housing - IPDU Consultants