## Annual Review Template

Title: Responding to the Nutrition Crisis in Yemen (R2N)
Programme Value £ (full life): £147,276,317.52		Review date: October 2021
Programme Code: 300525	AMP start date: 25 September 2018	AMP end date: 31 March 2022
[note] A cost and time extension for this programme until September 2022 was approved by FCDO ministers but spending approval from HM Treasury (HMT) was given only until the end of the fiscal year, March 2022. A request to authorise spending in the remaining period will be submitted to HMT in early 2022. This review considers the end date as 30 September 2022.

Summary of Programme Performance
Year	2019	2020	2021
Overall Output Score	B	A	A
Risk Rating	Severe	Severe	Severe

DevTracker Link to Business Case:	http://iati.FCDO.gov.uk/iati_documents/36022579.odt
DevTracker Link to results framework:	http://iati.fcdo.gov.uk/iati_documents/57385334.xlsx

The seismic impact of the pandemic on the UK economy has forced the UK government to take tough but necessary decisions, and as announced in 2020, the UK has now moved to a target of spending 0.5% of GNI as Official Development Assistance (ODA) in 2021.
Following a thorough review, the FCDO’s programme budget has been allocated in accordance with UK strategic priorities against a challenging financial climate of Covid.
Throughout the business planning process, the FCDO has strived to ensure that every penny of the ODA spend brings maximum strategic coherence, impact and value for taxpayers’ money.
The move to 0.5% has resulted in changes to this programme, which is being adapted and will continue. This Annual Review reflects that the programme has had to refocus resources and so will deliver against a new plan with new results targets. As a result, the findings of this Annual Review reflect on a programme in transition.
The UK remains a world leader in international development, not only through the impact of these financial allocations but also through the creation of the FCDO, integrating diplomacy and development to deliver greater impact. We will return to our commitment to spend 0.7% of gross national income on ODA when the fiscal situation allows

A. SUMMARY AND OVERVIEW

Description of programme
This is the third and final annual review for the Responding to the Nutrition Crisis in Yemen (R2N) programme, which runs until September 2022, following which a Programme Completion Review will be published. As such, this annual review reflects a programme continuing to function effectively, albeit impacted by Covid-19, and recommendations are focused on potential FCDO programming.

Malnutrition remains one of the major challenges and causes of mortality in Yemen, with increasing numbers of Yemenis affected, particularly women and children. 7.5 million Yemenis, 25% of the entire population, are malnourished. At least 2.25 million children and 1.2 million pregnant or breastfeeding women are acutely malnourished, including nearly 400,000 children under five who are suffering from severe acute malnutrition (SAM).
[note] Yemen Humanitarian Response Plan 2021
As part of the wider UK Government objective to improve nutritional outcomes and health services for women and children in Yemen, under the R2N programme the FCDO agreed to provide up to £142.5 million over 4 years to the United Nations Children’s Fund (UNICEF), and £7 million to the World Bank. The programme is built around a life-cycle approach that aims to address the immediate and underlying causes of undernutrition in Yemen. These include addressing malnutrition, health, water and sanitation needs, while also supporting technical analysis and evidence to inform the humanitarian response in Yemen. Since 2018, this programme has contributed to:
- Treatment of over 784,000 children under 5 for severe acute malnutrition.
- Over 566,000 pregnant women receiving skilled health support while delivering
- Routine immunisations for over 2.5 million children
- Provision of safe drinking water to over 5 million people
FCDO investments have been structured across three areas.
Output 1: Immediate Actions - Critical Nutrition, Health, Water, Sanitation and Hygiene service delivery – provide lifesaving, improved quality nutrition, health, and wash services for affected populations, complemented by a focus on protection for the most vulnerable.
Output 2: Remedial Actions - System strengthening and risk management – maintain and strengthen systems delivering nutrition, health and water and sanitation services at a sub-national level. Improve efficiency and effectiveness of health risk management through improved planning and financing.
Output 3: Increase contextual understanding - Knowledge and evidence generation – address the information and data gaps that exist in Yemen by improving the knowledge and evidence base for the context and supporting analytical products to improve decision making.

Summary supporting narrative for the overall score in this review
This Annual Review primarily covers the period July 2020 to June 2021. The programme overall received an ‘A’ score in this annual review, meaning it generally met the expected level of results and performance. All individual outputs of the programme also met expectations and were scored ‘A’. The outbreak of Covid-19 has been the major challenge to performance, particularly due to further restrictions on community outreach activities by the authorities, which exacerbated an environment where authorities already heavily restricted access. Despite this, targets were achieved or exceeded for most key indicators.
During the reporting period, the second wave of Covid has largely passed and restrictions on activities imposed by the authorities for reasons of public health (such as vaccination campaigns) were removed, allowing programme performance to recover again in several key areas, for example SAM cases examination. We expect that the delays of the remaining unmet targets to be reduced as Covid restrictions continue to subside in Yemen.
The World Bank component of this programme was not assessed as part of this review as activities did not start in the period.

Summary of lessons and recommendations for the year ahead

UNICEF should ensure closer monitoring of defaulters from SAM treatment, including tracking and analysing the principal reasons, and feeding this analysis into mitigation measures.

FCDO TPM (Third Party Monitor) should review the functionality and sustainability of solar water pumping systems, and draw on this learning for future programming.

The number of Therapeutic Feeding Centre (TFCs) and Outpatient Therapeutic Programme (OTPs) supported by UNICEF with functional child-friendly spaces (offering Early Childhood Development services) (indicator 2.2), was stopped due to changing priorities due to Covid-19 and practical challenges. FCDO and UNICEF should agree on future plans for this work.

FCDO and UNICEF should work on increasing monitoring coverage during the existing programme, with particular attention to quality issues and barriers to access. Minimum standards for monitoring type and frequency should be established, with implications for UNICEF support if these are not met, or irregularities are found during monitoring. FDCO should ensure that minimum standards and access to UNICEF TPM findings are an explicit part of any future funding to UNICEF.

Outreach activities of all kinds faced hindrances due to Covid-19. UNICEF should work on developing a clear plan that prioritizes resuming and catching up on these activities as soon as possible.

FCDO should revise output 3 indicators (Evidence is generated by UNICEF to improve understanding of the context and influence the shape of the response in Yemen), to ensure they capture the critical pieces of evidence necessary to understand the nutritional situation in Yemen, specifically including SMART surveys, MICS(Multiple Indicator Cluster Surveys), Nutrition Causal Analysis and the Joint Monitoring Framework. UNICEF should ensure that resources are then prioritised in line with the results of these analyses.

FCDO should ensure indicator 3.4 (NIS review action plan endorsed/validated) adequately captures the implementation of the NIS Action Plan.

FCDO should finalise the due diligence assessment for UNICEF, including a pillar on safeguarding.

UNICEF should improve its beneficiary feedback and grievance redressal mechanisms, including ensuring their Safeguarding Unit is staffed and operational as soon as possible, and that barriers to reporting Sexual Exploitation, Abuse and Harassment (SEAH) are better understood and mitigated.

FCDO should review and discuss with the World Bank whether future FCDO funds for health and nutrition can be spent in a timely and efficient manner before decision are made on delivery channels in a future programme.

FCDO should consider in future programming the advantages and disadvantages of greater earmarking in any continued support to UNICEF.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

This programme is part of a wider UK Government objective to avert famine in Yemen. The above diagram illustrates that with the right financial and technical inputs we will contribute to outputs that address nutrition needs working through health and water and sanitation (WaSH) interventions. The programme aims to strengthen Yemeni systems to ensure that Yemenis have access to life saving interventions leading to an overall improvement in nutrition status among the population. Evidence and learning will continue to be gathered and shared across the interventions to ensure that the best approaches are being taken.
These interventions do not happen in isolation, however, and rely on a portfolio approach with other FCDO investments. This programme complements FCDO programming with other partners including FCDO funded programmes on food security and social protection.
The programme initially targeted 107 high-priority districts considered at heightened risk of famine, as identified jointly by the WASH, Nutrition, Health, and Food Security and Agriculture clusters. As the situation in Yemen is rapidly evolving and uncertain, the programme maintains flexibility to work in any of the 333 districts for emergency response if/when the situation arises. Covid-19 has challenged some assumptions within the theory of change. For example, due to previous restrictions on access and movement, vaccination campaigns and other outreach activities have been suspended in some periods, resulting in the loss of some planned results. In addition, reduced humanitarian funding for Yemen in 2020 and 2021 led to UNICEF not being able to achieve overall targets in some areas. As FCDO funding contributes flexibly to UNICEF’s wider country results, this led to some FCDO outputs not achieving expectations.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Overall, based on the evidence available we believe the program remains on track to achieve the desired effect and results.

The intended overall impact of improving nutritional status across the life course of all vulnerable populations in Yemen is measured through proxy indicators GAM (Global Acute Malnutrition) and stunting rates. There have been plans to measure these and other indicators through nutrition surveys using the Standardised Monitoring and Assessment of Relief and Transitions (SMART) surveys and Multiple Indicator Cluster Survey (MICS) in previous years, but these have largely not been approved by authorities. These surveys now look likely to take place across Yemen in late 2021 and early 2022, which we hope will provide an evidence base to report on the programme impact indicators in 2022. In the absence of reliable data on these indicators for several years, it is hard to judge whether targets are likely to be met, and they may prove optimistic in a deteriorating overall humanitarian context.

The programme outcome indicators focus on the coverage of SAM treatment and the quality of service provision, measured by proxy indicators on stockouts of drugs and therapeutic foods. As reported by UNICEF, these indicators are largely on track to meet expectations. FCDO plans further TPM cross checking of these indicators over the next 12 months.

FCDO remains concerned about UNICEF’s systems for detecting and reporting on issues of Sexual Exploitation, Abuse and Harassment (SEAH). No incidents of possible SEAH have been reported to FCDO during this programme, and UNICEF have not adequately responded to FCDO questions on this issue. FCDO will prioritise engagement with UNICEF on this issue in the year ahead.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
The aims of the programme remain highly relevant in the current context in Yemen. The focus on health, nutrition, water and sanitation is a critical part of preventing famine. UNICEF remains the principal actor in primary healthcare and treatment of SAM in Yemen and has strong relationships with line ministries. Focusing on immediate service delivery while at the same time carrying out long-term strengthening of government-provided services remains appropriate in the context. UNICEF has largely delivered as expected in the year, despite the challenges of Covid-19. We therefore assess that the programme should continue. FCDO will need to assess the effectiveness of future funding to the World Bank, given the delays to implementation of that component.

C. DETAILED OUTPUT SCORING

Output Title	Affected populations in Yemen are provided with life-saving nutrition, health, WASH and protection support
Output number:		1	Output Score:	A
Impact weighting (%):		50%	Weighting revised since last AR?	No

Indicator(s)	Baseline	Milestones for this review	Progress	Results Attribution to FCDO
Nutrition
Indicator 1.1a (cumulative) / # Of children under 5 screened for Severe Acute Malnutrition (SAM)	3,113,421	7,501,682	11,603,493 / (Overachieved but not adjusted for double counting 155%)	30%
Indicator 1.1b (cumulative) / # Of children under 5 with SAM enrolled in management programmes	288,928	814,306	784,116 / (Met expectations 96%)	29%
Indicator 1.1c (reporting period) / % Of under 5 children enrolled in SAM management programmes who default (expressed as an average and range min/max)	14.7%	<15%	9.55% / (Met expectations)	12%
Indicator 1.2 (cumulative) / # of children at school age (10 - 19 years old) receiving weekly iron supplementation as part of anaemia prevention interventions	0	600,000	72,659 / (Substantial underachievement 12%)	100%
Indicator 1.3 (cumulative) / # Of pregnant and lactating women receiving counselling and education on infant and young child feeding (IYCF)	1,530,810	3,552,715	7,216,272 / (Substantial overachievement 203%)	30%
Health
Indicator 1.4 (cumulative) / # Of primary health consultations provided to children under 5, caregivers and pregnant and lactating women through health facilities, outreach services, and mobile health teams	1,090,559	6,500,000	6,767,684 / (Met expectations 104%)	30%
Indicator 1.5 (cumulative) / # of women of reproductive age receiving skilled birth attendance (home/facilities)	35,452	520,000	566,900 / (Minor overachievement 109%)	15%
Indicator 1.6a (reporting period) / % of targeted children who are vaccinated with three doses of DTP/Penta vaccine (Routine vaccination & Integrated Outreach rounds)	82%	1,096,991 (100%)	1,005,399 / (Minor underachievement 91.7%)	25%
Indicator 1.6b (reporting period) / % Of children <5yrs vaccinated during each round of Polio Vaccination campaign (Total target=5,535,816)	89%	9,640,446	8,818,596 / (Minor underachievement 91%)	70%
[note] Target and Milestones are set as 90% of the nutrition caseload, and is subject to revision based on caseload

Indicator 1.7 (cumulative) / # Of healthcare facility staff and community health workers (CHW) trained in Infection Prevention and Control, detection and referral of suspected Covid-19 cases among children, pregnant and breastfeeding women		12,000	10,686 / (Minor underachievement 89%)	13%
Wash
Indicator 1.8 (cumulative) / # of people provided with access to drinking water through UNICEF support to operational and maintenance (O&M) and rehabilitation of public water systems	1,119,791	2,400,000	4,070,128 / (Substantial overachievement 170%)	53%
Indicator 1.9a (cumulative) / # of individuals provided with emergency WASH	668,154	1,939,157	2,844,993 / (Substantial overachievement 147%)	100%
Indicator 1.9b (reporting period) / # of Rapid Response Teams responding to cholera and emergencies	0	300	300 / (Met expectations 100%)	60%
Indicator 1.10 (cumulative) / # of household members who have benefitted from UNICEF hygiene promotion activities, observed practicing handwashing with soap at critical times	0	1,670,000	1,498,742 / (Minor underachievement 90%)	100%
Indicator 1.11 (cumulative) / # people supported through continuity of WASH service		400,000 / (Results July 2020-March 2021)	1,650,000 / (substantial overachievement 413%)	100%
	Indicator closed August 2021 (Covid-19 funding)
Indicator 1.12 (cumulative) / # WASH NFI kit distributed to self-isolated Household		25,000 HH / 200,000 people / (Results July 2020-March 2021)	64,066 HH / 448,462 people / (substantial overachievement 256% / 224%)	100%
	Indicator closed August 2021 (Covid-19 funding)
Health & Nutrition
Indicator 1.13 (cumulative) / # of pregnant women and mothers with new-borns receiving vouchers to cover transportation costs for delivery, postnatal care and medical care in case of complications		3,150 (60%)	0 / (substantial underachievement 0%)	100%
	Indicator closed August 2021
Protection
Indicator 1.14a (cumulative) / # of identified children who receive support through case management/referrals	1,500	1,200	1,000 / (substantial underachievement 83%)	100%
Indicator 1.14b (cumulative) / # of children and caregivers receiving mental health and PSS inside HF and remotely (within HF catchment areas)	125,000	125,000	106,288 / (minor underachievement 85%)	100%

Briefly describe the output’s activities and provide supporting narrative for the score.

This output scores an A, as most critical indicators have met expectations or overachieved. This represents good performance in a context where the Covid-19 pandemic has been a significant and unexpected challenge. The pandemic has affected the provision of health services in general, including the provision of vaccination services through fixed service connection points and awareness raising. During the reporting period, the second wave of Covid has largely passed and restrictions on activities imposed by authorities for health reasons have been removed (e.g., vaccination campaigns), which allowed program performance to pick up again in several key areas, notably SAM admissions and plans to restart iron supplementation.

While SAM admission rates have increased significantly compared to the first half of 2020, we remain concerned that they have not yet returned to pre-Covid levels, and decreased in the second half of the reporting period, despite easing of Covid restrictions and an expansion of the number of treatment centres. While Ramadan may have been a factor in this, UNICEF should monitor this careful and ensure they understand what the barriers may be to seeking treatment.

The areas that showed significant underperformance were iron supplementation (1.2) and the Rapid Response Teams (RRT) (1.9b). The RRT lead the cholera response, they engage communities on malnutrition and hygiene promotion, and distribute hygiene kits. Iron supplementation was suspended in April 2020 as a precaution against Covid-19 but has been reinstated since the beginning of 2021 and UNICEF expect that targets will eventually be met. The number of rapid response teams had to be reduced due to lack of funding and low numbers of cholera cases. Permission from authorities was not given for transport vouchers (1.13), so this activity has been closed and funding moved to other outputs.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

This output continues to deliver VfM through bulk procurement and transportation of supplies such as vaccines, “plumpynut” (brand name for a Ready-to-Use Therapeutic Food) etc to deliver lifesaving support through its health, nutrition, WaSH and protection activities. UNICEF report that in terms of the plumpynut they procure, the unit cost does not exceed the (£37.12) per carton for one child as set out in the business case (current market rate is $48.20 USD). The same has been reported for other VFM indicators set out in the business case for items such as hygiene kits or water tanks where the original costs remain relevant. In the case of consumable hygiene kits the cost is £4.38 which is judged to be reasonable. The agency maintains Long Term Agreements with specific suppliers for standard items which the agency expects to order multiple times over the course of a year. These agreements are typically in place for one year at a time, securing predictable prices and speeding up procurement.
Competitive tendering processes are maintained throughout, but UNICEF also assesses the viability of procuring items in Yemen, to avoid delays with international procurement. The lack of availability of items of acceptable quality within the country nevertheless precludes local procurement in most cases.
In addition, UNICEF has increased the integration of hybrid solar energy systems. While this should provide for more cost-effective and climate-sensitive programming, there are anecdotal reports of such systems not being maintained, and in some cases accessing unsustainable groundwater sources. This is something FCDO and UNICEF should assess more systematically through TPM.
To allow WASH actors to exit from water trucking, UNICEF supports the extension of existing pipelines from the nearest city to the IDP site, allowing for piped water to replace the need for water trucking.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Activity (1.13) # of pregnant women and mothers with new-borns receiving vouchers to cover transportation costs for delivery, postnatal care and medical care in case of complications, has been closed as noted above.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress against last year’s annual review recommendations

#	Recommendation	Update since Annual Review 2020	Status
1	FCDO and UNICEF to review indicator 1.9b (number of Rapid Response Teams responding to cholera and emergencies) by 31 December 2020 to ensure it takes into account case incidence e.g. deployment of Rapid Response Team to X number of suspect cases – otherwise the indicator will always be missed when there is not a large disease outbreak.	UNICEF understood this action to be complete as the target for RRTs was revised from 800 to 300 in early 2021, through multiple discussions with FCDO.	Complete
2	Follow up with UNICEF by 31 December 2020 on issues highlighted by our third party supplier, in respect to beneficiaries being charged registration fees for some health services in some health facilities and visibility/existence of beneficiary feedback and complaints mechanisms. Both these issues have been recurrent themes in a health facilities visited so far.	This remains an issue of discussion between FCDO and UNICEF. Although a common practice in Yemen, we would like further monitoring to have greater assurance that this is not happening systematically in UNICEF-supported centres and activities.	Ongoing
3	Polio vaccination was slightly off-track before the Covid-19 outbreak and was severely curtailed during the outbreak. There is now an outbreak of vaccine-derived Polio in Yemen which needs a massive and swift response. Outreach activities of all kinds have been constrained by Covid-19 and humanitarian access impediments in 2020. These activities must be prioritised for advocacy as soon as possible, with support from FCDO and other donors and other key stakeholders [N.B. progress was being made at the time of finalising this report but needs to be sustained].	Additional Integrated Outreach Rounds were conducted in 2020 and 2021	Complete
4	UNICEF’s learning around adapting activities to Covid-19 should continue to be applied in the long term – both to maintain preparedness for any subsequent waves and to ‘lock in’ the enhanced practices around Infection, Prevention and Control (IPC), triage and disease surveillance. Adequate in-country buffer stocks of Personal Protection Equipment (PPE) must be maintained to protect health workers and service users and to ensure activities can continue.	UNICEF reports improved learning on continuity of essential services during the Covid-19 outbreak, that will be applied going forwards.	Ongoing

Recommendations for Year Ahead

UNICEF should ensure closer monitoring of defaulters from SAM treatment, including tracking and analysing the principal reasons, and feeding this analysis into mitigation measures.

FCDO TPM should review the functionality and sustainability of solar water pumping systems, and draw on this learning for future programming.

Output Title	Nutrition, health and WASH services in Yemen are supported at a local level to be more efficient and effective
Output number:		2	Output Score:	A
Impact weighting (%):		45%	Weighting revised since last AR?	No

Indicator(s)	Baseline	Milestones for this review	Progress	Results Attribution to FCDO
Nutrition
Indicator 2.1 (reporting period) / % of functional health facilities supported by UNICEF that provide SAM management programmes	83%	80%	89% / (Minor overachievement)	15%
Indicator 2.2 (cumulative) / # of Therapeutic Feeding Centre (TFCs) and Outpatient Therapeutic Programme (OTPs) supported by UNICEF with functional child-friendly spaces (offering Early Childhood Development services)	0	230	83 / (Significant underacheivement 36%)	50%
Health
Indicator 2.3 (cumulative) / % of clinics supported by UNICEF offering minimum initial service package (primary health care, reproductive health, sexual and gender-based violence support) (total=4500)	0	56%	56% / (Met expectations)	20%
Indicator 2.4 (cumulative) / % of estimated pregnant women in Yemen that have received at one ante-natal visit by a community health worker	N/A	45%	43% / (Met expectations)	25%
Indicator 2.5 (cumulative) / # of Health Facilities provided with medical, preventive and protective supplies (PPE, IPC supplies, ventilators and related equipment, test kits etc) to continue service delivery with optimum safety from Covid-19 transmission (both for health providers and clients)		4,000 / (Results July 2020-March 2021)	3,643 / (Minor underachievement 91%)	15%
	Indicator closed August 2021 (Covid-19 funding)

Wash
Indicator 2.6 (cumulative) / # of UNICEF supported isolation units /health centres meeting WASH basic IPC standard		30 / (Results July 2020-March 2021)	39 / (Significant overachievement / 130%)	100%
	Indicator closed August 2021 (Covid-19 funding)
Indicator 2.7a (cumulative) / # of water facilities supported by UNICEF that have a risk management plan for improvement of water services	0	4	3 / (Significant underachievement 75%)	100%
Indicator 2.7b (cumulative) / # of people provided with improved water services by water facilities with a risk management plan	0	1,250,000	3,093,498 / (Significant overachievement 247%)	100%

Briefly describe the output’s activities and provide supporting narrative for the score.
This output has scored an A, as most activities met expectations or overachieved. Activities under this output aims at improving the quality of services being offered to children and women of child-bearing age and building stronger systems. Most of the activities including nutrition, health, early childhood development and provision of clean drinking water, are aimed at extending the range of services available to children and women of reproductive age and therefore contribute to mitigating the multiple causes of malnutrition. One of the most important of these is access to clean water. UNICEF ensures there are ‘business continuity plans’ in place to support the resilience of water delivery systems. Essentially these are contingency plans to ensure sustained access to water.

Key indicators on delivery met expectations or overachieved: the percentage of functional health facilities supported by UNICEF that provide SAM management programmes (2.1); the percentage of clinics supported by UNICEF offering minimum initial service package (primary health care, reproductive health, sexual and gender-based violence support) (2.3); the percentage of estimated pregnant women in Yemen that have received at one ante-natal visit by a community health worker. Providing Child Friendly Spaces (2.2) was off track prior to the outbreak of Covid-19, due to difficulties encountered in providing incentives for CHWs (Community Health Workers) and lack of space in facilities. UNICEF has no plans for additional risk management plans for water facilities (2.7a) though more people will be provided with safe water supply through water quality monitoring and Chlorination which represent part of risk management.

In more general terms, FCDO received some anecdotal feedback from several sources (INGOs, other donors, local civil society actors) of quality issues in service provision at some health centres, including beneficiaries having to pay for services provided. In discussion with UNICEF, FCDO assesses that monitoring by UNICEF and Third-Party Monitoring by UNICEF and FCDO can be improved and needs to provide greater assurance on these aspects. FCDO has been discussing with UNICEF and our Third-Party Monitoring contractor Tahseen about increasing coverage over the remainder of the programme and will look to have a significantly increased focus on monitoring in any future support to activities that are implemented through local government systems.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

The system strengthening aspect of the programme is in many ways more challenging than direct service provision, in a context of weak governance and limited developmental focus at the central level. Ultimately, there continues to be a strong case that investment maintaining and strengthening local government capacity to deliver services makes sense and will deliver value for money in the long term for Yemenis through more sustainable, resilient health services that are more able to manage shocks.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

In response to the challenges presented by Covid-19 and UNICEF’s funding situation some milestones under this output reduced over the reporting year:

Output indicator 2.1 (% of functional health facilities supported by UNICEF that provide SAM management programmes) milestone for period Jul. to Dec. 2020 was reduced from 90% to 80% because of the impact of Covid-19 has impacted on the functionality of health facilities.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress against last year’s annual review recommendations

#	Recommendation	Update since Annual Review 2020	Status
1	Extending the coverage of Severe Acute Malnutrition management services to more health facilities is an important objective under the programme, especially at a time when IPC levels are deteriorating, and more children are likely to become severely malnourished. By 31 December 2020 UNICEF and FCDO should review the constraints involved in this objective with a view to increasing the level of ambition for providing malnutrition services and perhaps if appropriate move budget to this component of the programme from another spending area.	19 new centres opened resulted in the extension of the SAM cases coverages.	Complete
2	Although UNICEF has committed itself to a simple action plan, it aims to develop a more rigorous approach to program data - especially the use of data for analysis. The annual review revealed some weaknesses and inconsistencies in the use of data to generate results and interpret data into meaningful results. If data collection is weak, this need strengthening. All data must be treated objectively to ensure rigorous evidence is generated. UNICEF should seriously consider expanding data processing and analytical capacity.	A review of the nutrition information system is on-going. UNICEF have confirmed this recommendation has been implemented.	Ongoing

Key Lessons Learned

FCDO need to continue advocacy and support to the authorities to keep facilities open and operational for non-Covid-19 emergency services, also to facilitate access as it is a continues challenge for the progress of the programme specially in the north.

Recommendations for Year Ahead

Number of Therapeutic Feeding Centre (TFCs) and Outpatient Therapeutic Programme (OTPs) supported by UNICEF with functional child-friendly spaces (offering Early Childhood Development services) (2.2), was stopped due to changing priorities due to Covid-19 and practical challenges. FCDO and UNICEF should agree on future plans for this work.

FCDO and UNICEF should work on increasing monitoring coverage during the existing programme, with particular attention to quality issues and barriers to access. Minimum standards for monitoring type and frequency should be established, with implications for UNICEF support if these are not met, or irregularities are found during monitoring. FDCO should ensure that minimum standards and access to UNICEF TPM findings are an explicit part of any future funding to UNICEF.

Outreach activities of all kinds faced hindrances due to Covid-19. UNICEF should work on developing a clear plan that prioritises resuming and catching up on these activities as soon as possible.

Output Title	Evidence is generated by UNICEF to improve understanding of the context and influence the shape of the response in Yemen
Output number:		3	Output Score:	A
Impact weighting (%):		5%	Weighting revised since last AR?	No

Indicator(s)	Baseline	Milestones for this review	Progress	Results Attribution to FCDO
Indicator 3.1 (cumulative) / # of surveys and assessments conducted by UNICEF funded by FCDO	0	6	6 / (Met expectations 100%)	25%
Indicator 3.2 (cumulative) / # of analysis conducted on how the response efficiency could be improved (e.g. return on investment analysis)	0	8	10 / (Minor overachievement 125%)	100%
Indicator 3.3 (cumulative) / # of risk analysis and preparedness and contingency plans updated and shared with FCDO	0	2 / (Results July 2020-Dec 2020)	2 / (Met expectations 100%)
	Indicator closed August 2021 and replaced with indicator 3.4
Indicator 3.4 / NIS review action plan endorsed/validated	New indicator. Not assessed this reporting year

Briefly describe the output’s activities and provide supporting narrative for the score.
This output has scored an A as all assessed indicators were met or exceeded during the reporting period.
Despite meeting numerical indicators, the Standardized Monitoring and Assessment of Relief and Transitions (SMART) surveys funded under this output are some of the most critical to understanding the nutrition situation in Yemen, and these have still not been able to be implemented due to delays in obtaining permissions from authorities. UNICEF is hopeful that these will take place across all governorates in late 2021 and early 2022. UNICEF is also working towards carrying out the Multiple Indicator Cluster Survey in early 2022. As well as being necessary to understanding the current situation of malnutrition in Yemen, these are also needed to assess the impact indicators of this programme.

In terms of evidence generated during this period: on Covid-19 there were three rounds of a Rapid Assessment in April 2020, July 2020 and March 2021 to assess knowledge, attitudes, risk perception and adoption of Covid-19 prevention practices in Yemen; a rapid assessment on Covid-19 vaccine hesitancy was also conducted in May 2021 targeting the health workers in the South.

Also during the reported period UNICEF conducted analysis which has contributed to the response to Covid-19, and the nutrition crisis. This includes the Risk monitoring framework, Yemen Action Plan, Nutrition Information System (NIS) review. The NIS review was jointly designed with FCDO and carried out by technical experts contracted by FCDO. It aimed to systematically identify factors which affect the collection, analysis, dissemination, and utilization of timely, accurate and representative nutrition information in Yemen. The final report and findings of the Yemen NIS review were validated by stakeholders including Ministry of Public Health and Population (MoPHP) in both Sana’a and Aden. The NIS workplan was drafted to move forward the recommendations the NIS review report and capacitating the MoPHP, GHO and DHO for quality assurance of the information system.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

This output continues to demonstrate VfM by producing analysis to help inform and ensure and effective and efficient response in Yemen.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

FCDO and UNICEF agreed to replace indicator 3.3 with indicator 3.4 representing next steps on the NIS work.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress against last year’s annual review recommendations
#	Recommendation	Update since Annual Review 2020	Status
1	Indicators under output 3 (Knowledge and Evidence Generation) - should undergo further analysis by 31 December 2020 with a view to clarifying and ensuring FCDO are clear on what is being funded and how the products are informing and improving the overall humanitarian response.	Following multiple exchanges with FCDO from Jan-April 2021, UNICEF changed indicator 3.3 to focus on NIS review and follow up.	Complete

Key Lessons Learned
None
Recommendations for Year Ahead
FCDO should revise output 3 indicators to ensure they capture the critical pieces of evidence necessary to understand the nutritional situation in Yemen, specifically including SMART surveys, MICS, Nutrition Causal Analysis and the Joint Monitoring Framework. UNICEF should ensure that resources are then prioritised in line with the results of these analyses.

FCDO should ensure indicator 3.4 adequately captures the implementation of the NIS Action Plan.

D: RISK

Overview of risk management

The ongoing conflict in Yemen has exacerbated pre-existing vulnerabilities and continues to worsen the operating environment. In 2020 Yemen has experienced macroeconomic deterioration, dramatic falls in remittances, increasing costs of key commodity imports and a sharp reduction in humanitarian aid.

This programme was rated major residual risk at the business case approval stage, given the complexity of delivering the programme and contextual risks. The humanitarian context in Yemen remains high risk and since the business case was approved the overall context has deteriorated, increasing delivery, fiduciary and safeguarding risks. UNICEF continues to demonstrate an ability to deliver well under the volatile conditions of conflict however, there has been a lack of reporting from UNICEF on safeguarding and fraud/aid diversion. Given the context and the large number of downstream partners, FCDO remains concerned that systems that exist on paper are not succeeding in identifying and reporting on cases. This has resulted in the residual risk being increased to severe. The programme still operates within FCDO Yemen’s risk appetite across the seven different risk categories (strategy & context, policy & programme delivery, financial & fiduciary, safeguarding, public service delivery & operations, reputational and people). Both UNICEF’s and FCDO’s own risk register provide appropriate mitigations to ensure risks remain within FCDO Yemen’s risk appetite.

FCDO discusses risk as part of regular meetings with UNICEF on at least a quarterly basis. UNICEF share an updated risk register with FCDO on a bi-annual basis.

Main risks to programming

The Covid-19 pandemic affected the overall health service delivery, including delivery of vaccination services through fixed and outreach service delivery points. UNICEF supported the development of a Covid-19 risk mitigation matrix to support continuity of immunisation services, ensuring infection prevention control (IPC) measures in place, such a provision of personal protective equipment (PPE). The global guidance on IPC was contextualised and translated for use during the training of health workers/ vaccinators in Covid-19 context.

A continued concern is the administrative restrictions placed on international aid by the authorities, particularly in areas under Ansar Allah control. These administrative restrictions can cause delays to UNICEF’s programming and also affect key pieces of information that enable FCDO to assess the impact of the programme. It also affects UNICEF’s monitoring and assurance, including their third party monitoring, audits and spot checks. Regular engagement between FCDO and UNICEF helps to ensure that minimum levels of monitoring are being achieved.

Due Diligence

A Central Assurance Assessment was completed for UNICEF in November 2020 which noted Improvements in UNICEF’s systems of governance and control since the last central assessment was completed. FCDO is working on a refreshed due diligence assessment of UNICEF that will also cover UNICEF’s emergency cash programming activities under the Yemen Social Protection programme (YeSP).

Safeguarding

UNICEF have started a safeguarding unit which reports to the Deputy Programme Representative and for which recruitment is ongoing. FCDO will continue to follow up with UNICEF on the progress of this new safeguarding unit. UNICEF do not currently have a grievance redress mechanism operational across their programming, but rely on a mechanism that exists under the World Bank emergency health and nutrition programme. FCDO third party monitoring and a recent ICAI review into safeguarding in Yemen (conducted in July 2021) found that although these grievance mechanisms are in place, they are largely unused.

To date UNICEF have been unable to provide FCDO with the assurance that UNICEF has robust systems in place to detect and report on issues of Sexual Exploitation, Abuse and Harassment (SEAH). No issues of SEAH have been reported to FCDO and a list of questions was shared with UNICEF in September 2020 which has yet to receive a response. FCDO will continue to follow up with UNICEF on these aspects which remain unsatisfactory, through bilateral meetings and the due diligence assessment refresh.

Downstream Partners

Local government health organisations are the main implementing partners for UNICEF, with technical support and oversight from the MoPHP. NGOs also provide services in more remote areas, and accompany local government where humanitarian needs are high, complementing supplies and other assistance provided by UNICEF. UNICEF agreements specify quarterly reporting on use of funds and progress with the programme to UNICEF. If instances of fraud and corruption occur, UNICEF ceases work with that organisation and pursues refunds.

Given the volatile security environment and high risk of fraud and corruption, ensuring adequate scrutiny is more important but also more difficult than usual. With no presence in country, FCDO is reliant on TPM for independent monitoring. While FCDO TPM provides useful insight and has identified a number of issues, oversight would be strengthened by access to UNICEF TPM reports, which FCDO has requested. Unfortunately, UNICEF HQ has for the moment refused to share their TPM reports with FCDO, arguing that these are for internal use only.

Gender & Inclusion

FCDO’s third party monitor, Tahseen, recently completed a gender and inclusion study on some of FCDO’s partners. The report found that UNICEF have comprehensive policies, standards, frameworks and tools in place for Gender Equality, Women’s Empowerment (GEWE) and social inclusion. UNICEF Yemen conducted a gender programmatic review in April 2020 which found UNICEF’s basic reporting on gender and age had been inconsistent. It also found the UNICEF Yemen Monitoring Framework did not consider gender, and recommended including a series of gender-based indicators for health and nutrition, WASH, education, protection, social inclusion, planning and communication for development. While this report and its recommendations are promising, it is unclear the extent to which UNICEF will implement the recommendations.
The FCDO programme team will continue to have discussions on gender & inclusion with UNICEF at quarterly meetings, ensuring to follow up on UNICEF’s progress on the recommendations set out in the gender programmatic review.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and FCDO, on commercial, and financial issues

Year	Spend per year
2018/2019	£35,677,497.75
2019/2020	£34,343,221.67
2020/2021	£52,728,334.10
2021/2022	£17,527,264.00
Total funds disbursed to UNICEF to date:	£140,276,317.52

Exchange rate challenges

On UNICEF’s systems, all budgets reflect costs in US dollars and the UN exchange rate for the past 12 months (which is an average of 580 YER/USD), are used at the time of payment. This reasonably accurately reflects the exchange rate in the north of Yemen (around 600 YER/USD). However, the exchange rate in the south of the country has deteriorated markedly and is currently around 1,500 YER/USD. FCDO has raised this issue with UNICEF for around a year, and UNICEF reported finally implementing a new approach in November 2022 that takes into account local market exchange rates in the South.

Performance of partnership

FCDO appreciates UNICEF’s close engagement and working in partnership. UNICEF’s model of working largely through government entities allows scale but also raises concerns over quality of delivery and reporting, and the sufficiency of monitoring. We want to work together with UNICEF to improve monitoring, assurance and accountability to affected populations. FCDO appreciates closer working with UNICEF recently on areas such as ensuring the transparency and credibility of key SMART surveys, while noting that we expect greater engagement and prioritisation of issues of safeguarding and beneficiary feedback, and greater transparency on UNICEF TPM.

Delivery against planned timeframe

Timeliness of narrative and financial reporting has been adequate and on time. However, in terms of quality and coherency of data there is significant room for improvement. For example, UNICEF’s reporting and presentation of data in relation to the logframe has been incomplete and at times inaccurate.

Monitoring of assets

UNICEF maintains an assets register in a programme called VISION, from which it can trace FCDO funded assets. A physical count is done twice a year (June and December) to ensure asset safeguarding measures are in place and to record functionality conditions

Monitoring

October 2018 – June 2021
number programmatic monitoring visits	211 programme monitoring visits conducted
number micro-assessments	140 Micro Assessments Conducted for IPs
number audits	Audits for 74 IPs are in final stages.
number spot checks	40 Spot Check Conducted and 56 IPs have Spot checks in progress.

The above table notes monitoring conducted by UNICEF throughout the programme. Due to Covid-19, UNICEF have advised that some monitoring visits are still being conducted remotely.

Monitoring activities UNICEF conducts:

- Programme monitoring visits (PMV’s) – undertaken by programme staff or third parties where there are access constraints.
- Project specific TPM – contracted by UNICEF either as a project or donor requirement. FCDO do not fund this type of monitoring so this type of monitoring is not carried out for this programme.
- Financial monitoring – spot checks and audits (either scheduled or special) which focus only on monitoring cash.
FCDO has contracted its own third-party monitoring service with two light-touch reviews and one in-depth review conducted in early 2020 and one in-depth review conducted so far in 2021. We anticipate a further 4 in-depth reviews and six light-touch reports to be completed by March 2022.

World Bank

In October 2020, FCDO provided the World Bank with £7m through their Global Financing Facility (GFF) to contribute towards their Emergency Health and Nutrition Project (EHNP). The EHNP aimed to contribute to the provision of basic health, essential nutrition, water, and sanitation services for the benefit of Yemen and joint funding would allow closer working and synergies between FCDO and the World Bank. Unfortunately, in December 2020, the World Bank informed FCDO that it was not possible to use FCDO funding for EHNP, due to changed World Bank rules around environmental and social safeguards. The World Bank and FCDO agreed to use these funds for a new Yemen Covid-19 Response Project (YCRP). The YCRP aimed to prevent, detect and respond to the threat by Covid-19 (coronavirus) and strengthen national systems for public health preparedness and would be implemented by the World Health Organisation (WHO). However, the Bank have had major delays in the set-up of this project, including through getting Bank Board approval of the YCRP (which was only approved in June 2021) and then setting-up the legal agreement for signature between the Bank and WHO. YCRP funding began to be disbursed in August and so this component will be reviewed as part of the project completion report.

Value for money (VfM)

Economy - Inputs of the appropriate quality at the right price

UNICEF indirect costs are in line with other UN partners. FCDO’s contribution includes an indirect cost recovery charge of 8% (a standard board-approved rate), and on an approved overall budget of £140.2 million this equates to just over £11 million. A further 9% in country management cost (which was reviewed in June 2020 and reduced from 11.7%)) has been applied which covers operations (5%), M&E (1.2%), emergency and field operations (1%), external communications (1%) and security costs (0.8%). In addition, direct staff costs were 6.86% of the total budget.

Efficiency - How well are inputs converted into outputs?

UNICEF, globally is the one largest procurers of basic child vaccines, mosquito nets, nutrition supplies, and other equipment which gives UNICEF leverage in negotiating low prices with suppliers.

UNICEF’s approach of working through Local Governorate Health Offices (GHO) and NGOs continues to ensure a more comprehensive service in Yemen and enables FCDO to access programming throughout the country. Delivery through GHOs makes use of the existing health infrastructure and exercises long term benefits by supporting and strengthening systems resilience. The combined delivery mechanism ensures reach and helps harmonise and manage costs across different geographical areas.

On WASH, UNICEF has entered into a Service Level Agreement (SLA) with World Food Programme (WFP) since Dec 2018 for the procurement and distribution of fuel to 36 Local Water Sanitation Cooperation (LWSC) in 15 Governorates in Yemen. The actual cost of delivered fuel through this mechanism until end of June 2021 is $7.95M compared to estimated market cost of $11.46M to deliver the same amount which resulted at least 31% in terms of efficiency gains ($ 3.5M) for the first 6 months of 2021.

With the current context UNICEF are facing some higher operating costs, particularly in logistics. This can negatively offset against where UNICEF are seeing VfM gains. Overall UNICEF’s nutrition team have noted that overall costs have not significantly increased for the costs of treatment. For example, plumpynut remains below the unit cost of £37.12 per carton for treatment of one child as set out in the business case. The cost per beneficiary of providing a package of child, maternal health and nutrition interventions through the integrated outreach remains within the cost of £7.23 as set out in the business case.

Examples of improving VfM

Commercial - UNICEF spend a lot of money purchasing fuel for generators, making sure their warehouses are functioning well and maintaining temperature for temperature sensitive medical commodities. Although currently funded by another donor, UNICEF are currently working on a project for solarising their warehouses. Money saved from solarisation of these warehouses will be spent on interventions that can add more value in terms of achieving intended outcomes.

Date of last narrative financial report	11 August 2021	Date of last audited annual statement	07 July 2021