## FCDO Logframe
PROJECT NAME |  | UNICEF - Responding to the Nutrition Crisis in Yemen (R2N) - 300525
IMPACT | Sector | Impact Indicator 1 (nutrition) |  | Baseline | Milestone 1 (Oct 2018 - Jun 2019) | Milestone 2 (Jul 2019 - Dec 2019) | Milestone 3 (Jan 2020 - Jun 2020) | Milestone 4 (July 2020-Dec 2020) | Milestone 5 (Jan 2021 - June 2021) | Miestone 6 (July 2021 - Dec 2021) | Target - March 2022
Improved nutrition status among infants, children, adolescents and pregnant women in Yemen through convergent life-saving interventions and improved services |  | % of children U5s wasted (moderate and severe) | Planned | 15% | 13% | 13% | 11.5% | 11.5% | 11.5% | 11.5% | 10%
|  |  | Achieved |  | 12% | 11.9% | 12 | 12% | 12%
Source
SMART surveys results, MICS
|  | Impact Indicator 2 (nutrition) |  | Baseline | Milestone 1 (Oct 2018 - Jun 2019) | Milestone 2 (Jul 2019 - Dec 2019) | Milestone 3 (Jan 2020 - Jun 2020) | Milestone 4 (July 2020-Dec 2020) | Milestone 5 (Jan 2021 - June 2021) | Miestone 6 (July 2021 - Dec 2021) | Target - March 2022
|  | % of children U5s stunted (moderate and severe) | Planned | 46% | 45% | 45% | 44% | 44% | 44% | 44% | 43%
|  |  | Achieved |  | 45% | 45% | 45% | 45% | 45%
Source
SMART surveys results, MICS
OUTCOME | Nutrition | Outcome Indicator 1.a (nutrition) |  | Baseline | Milestone 1 (Oct 2018 - Jun 2019) | Milestone 2 (Jul 2019 - Dec 2019) | Milestone 3 (Jan 2020 - Jun 2020) | Milestone 4 (July 2020-Dec 2020) | Milestone 5 (Jan 2021 - June 2021) | Miestone 6 (July 2021 - Dec 2021) | Target - March 2022 | DFID attribution* | Cumulative or reporting period** | Assumptions
Affected populations in Yemen have access to critical live-saving humanitarian interventions and services are strengthened (with a focus on provision maintenance, risk management and learning) |  | % coverage of SAM treatment against need | Planned | 73% | 85% | 90% | 90% | 90% | 90% | 90% | 95% | 29% | Cumulative | ‒ Districts and health facilities remains accessible ‒ Access to import and transport supplies to the service delivery locations.
|  |  | Achieved |  | 89% | 99% | 101.5% | 98% | 96.29%
Source
CMAM Database from OTPs and Mobile teams, Caseload Estimates of the nutrition cluster
| Nutrition | Outcome Indicator 1.b (nutrition) |  | Baseline | Milestone 1 (Oct 2018 - Jun 2019) | Milestone 2 (Jul 2019 - Dec 2019) | Milestone 3 (Jan 2020 - Jun 2020) | Milestone 4 (July 2020-Dec 2020) | Milestone 5 (Jan 2021 - June 2021) | Miestone 6 (July 2021 - Dec 2021) | Target - March 2022 | DFID attribution* | Cumulative or reporting period**
|  | % of health facilities supported by UNICEF reporting no stock-outs of RUTF | Planned | 92% | 95% | 95% | 98% | 98% | 98% | 98% | 98% | 15% | Reporting period
|  |  | Achieved |  | 92% | 94% | 95% | 95% | 95%
Source
TPM data, NGOs reports to the cluster, Monthly CMAM reports
| Health | Outcome Indicator 2 (health) |  | Baseline | Milestone 1 (Oct 2018 - Jun 2019) | Milestone 2 (Jul 2019 - Dec 2019) | Milestone 3 (Jan 2020 - Jun 2020) | Milestone 4 (July 2020-Dec 2020) | Milestone 5 (Jan 2021 - June 2021) | Miestone 6 (July 2021 - Dec 2021) | Target - March 2022 | DFID attribution* | Cumulative or reporting period**
|  | % of health facilities supported by UNICEF reporting no stock-outs of 4 essential drugs and commodities in the last quarter (ORS, Zinc, Amoxicillin, Penta3 vaccines) | Planned | 62% | 65% | 68% | 71% | 74% | 75% |  | 77% | 20%
|  |  | Achieved |  | 62% | 52% | 68% | 75% | 82% |  |  |  | cumulative
Source
TPM Report from 2000 HFs
| WASH | Outcome Indicator 3 (WASH) |  | Baseline | Milestone 1 (Oct 2018 - Jun 2019) | Milestone 2 (Jul 2019 - Dec 2019) | Milestone 3 (Jan 2020 - Jun 2020) | Milestone 4 (July 2020-Dec 2020) | Milestone 5 (Jan 2021 - June 2021) |  | Target - Sept 2021 | DFID attribution* | Cumulative or reporting period**
|  | # of people benefitting from waste water collected by local councils supported by UNICEF treated and safely disposed | Planned | 1787945 | 1889945 | 2173237 | 2456529 | 2667544 |  |  |  | 100%
|  |  | Achieved |  | 2539249 | 2774607 |  | 2357481 | 2824610 |  |  |  | cumulative
Source
Field monitoring and partner reports (No study was carried out to establish the data including baseline)
| WASH | Outcome Indicator 3 (WASH) |  | Baseline | Milestone 1 (Oct 2018 - Jun 2019) | Milestone 2 (Jul 2019 - Dec 2019) | Milestone 3 (Jan 2020 - Jun 2020) | Milestone 4 (July 2020-Dec 2020) | Milestone 5 (Jan 2021 - June 2021) | Miestone 6 (July 2021 - Dec 2021) | Target - March 2022 | DFID attribution* | Cumulative or reporting period**
|  | Number of people accessing a sufficient quantity of safe water for drinking, cooking and personal hygiene | Planned | 75%: 3,434,343 | 3434343 |  | 80%
|  |  | Achieved | 75%: 5192254 |  |  |  | cumulative
Source
WASH Facilitators, TPM and implementing partners progress and monitoring report
| Protection | Outcome Indicator 4 (protection) |  | Baseline | Milestone 1 (Oct 2018 - Jun 2019) | Milestone 2 (Jul 2019 - Dec 2019) | Milestone 3 (Jan 2020 - Jun 2020) | Milestone 4 (July 2020-Dec 2020) | Milestone 5 (Jan 2021 - June 2021) | Miestone 6 (July 2021 - Dec 2021) | Target - March 2022 | DFID attribution* | Cumulative or reporting period**
|  | % of health facilities supported by UNICEF applying the standard operating procedures (SOPs) for integration of social welfare and psychosocial support into health and nutrition services | Planned | 20% | 20% | 25% | 30% | 30% | 30% | 34% | 35% | 100%
|  |  | Achieved | 33% | 20% | 33% | 34% | 34% | 34%
|  |  |  | 62%: Source |  |  |  | 34%
| Evidence | Outcome Indicator 5 (learning) |  | Baseline | Milestone 1 (Oct 2018 - Jun 2019) | Milestone 2 (Jul 2019 - Dec 2019) | Milestone 3 (Jan 2020 - Jun 2020) | Milestone 4 (July 2020-Dec 2020) | Milestone 5 (Jan 2021 - June 2021) | Miestone 6 (July 2021 - Dec 2021) | Target - March 2022 | DFID attribution* | Cumulative or reporting period**
|  | # of national policies, strategies or plans amended based on new evidence generated by UNICEF | Planned | 0 | 0 | 0 | 5 | 10 | 12 | 14 | 15 | 25%
|  |  | Achieved |  | 1 | 2 | 5 | 10 |  |  |  |  | cumulative
|  |  |  | 62%: Source |  |  |  |  | RISK RATING
|  |  |  | 62%: Progress reports, presentations for review meetings, analytical reports |  |  |  |  | High
OUTPUT 1 | Nutrition | Output Indicator 1.1a (nutrition) |  | Baseline | Milestone 1 (Oct 2018 - Jun 2019) | Milestone 2 (Jul 2019 - Dec 2019) | Milestone 3 (Jan 2020 - Jun 2020) | Milestone 4 (July 2020-Dec 2020) | Milestone 5 (Jan 2021 - June 2021) | Miestone 6 (July 2021 - Dec 2021) | Target - March 2022 | DFID attribution* | Cumulative or reporting period** | Assumption
Affected populations in Yemen are provided with life-saving nutrition, health, WASH and protection support |  | # of children under 5 screened for Severe Acute Malnutrition (SAM) | Planned | 3113421 | 2300000 | 3730015 | 5254412 | 6778809 | 7501682 | 8224554.6667 | 8947427 | 30% |  | ‒ Districts and health facilities remains accessible ‒ Access to import and transport supplies to the service delivery locations. - Nutrition Cluster targets are subject to change, which may require revisions to nutrition milestones and targets
|  |  | Achieved |  | 3059390 | 5224246 | 6818571 | 9224877 | 11603493 |  |  |  | cumulative
Source
CMAM , CHVs & CHWs, MUAC camapaign and Integrated Outreach reports
|  | Output Indicator 1.1b (nutrition) |  | Baseline | Milestone 1 (Oct 2018 - Jun 2019) | Milestone 2 (Jul 2019 - Dec 2019) | Milestone 3 (Jan 2020 - Jun 2020) | Milestone 4 (July 2020-Dec 2020) | Milestone 5 (Jan 2021 - June 2021) | Miestone 6 (July 2021 - Dec 2021) | Target - March 2022 | DFID attribution* | Cumulative or reporting period**
|  | # of children under 5 with SAM enrolled in management programmes*** | Planned | 288928 | 229954 | 390823 | 522538 | 654253 | 814306 | 974359 | 1056790 | 29%
|  |  | Achieved |  | 253192 | 433935 | 530279 | 674416 | 784116 |  |  |  | cumulative
Source
CMAM database of the monthly reports of OTPs in fixed health facilities and mobile tems
|  | Output Indicator 1.1c (nutrition) |  | Baseline | Milestone 1 (Oct 2018 - Jun 2019) | Milestone 2 (Jul 2019 - Dec 2019) | Milestone 3 (Jan 2020 - Jun 2020) | Milestone 4 (July 2020-Dec 2020) | Milestone 5 (Jan 2021 - June 2021) | Miestone 6 (July 2021 - Dec 2021) | Target - March 2022 | DFID attribution* | Cumulative or reporting period**
|  | % of under 5 children enrolled in SAM management programmes who default (expressed as an average and range min/max) | Planned | 14.7% | <15% | <15% | <15% | <15% | <15% | <15% | <15% | 12% | Reporting period
|  |  | Achieved |  | 12% | 12.3% | 11% | 9.5% | 9.6%
Source
CMAM database of the monthly reports of OTPs in fixed health facilities and mobile tems
|  | Output Indicator 1.2 (nutrition) |  | Baseline | Milestone 1 (Oct 2018 - Jun 2019) | Milestone 2 (Jul 2019 - Dec 2019) | Milestone 3 (Jan 2020 - Jun 2020) | Milestone 4 (July 2020-Dec 2020) | Milestone 5 (Jan 2021 - June 2021) | Miestone 6 (July 2021 - Dec 2021) | Target - March 2022 | DFID attribution* | Cumulative or reporting period**
|  | # of children at school age (10 - 19 years old) receiving weekly iron supplementation as part of anaemia prevention interventions | Planned | 0 | 0 | 0 | 300000 | 500000 | 600000 | 800000 | 900000 | 100% | Cumulative
|  |  | Achieved |  | 0 | 0 | 22577 | 61871 | 72659 |  |  |  | cumulative
Monthly reports of Adolescent program from GHOs
|  | Output Indicator 1.3 (nutrition) |  | Baseline | Milestone 1 (Oct 2018 - Jun 2019) | Milestone 2 (Jul 2019 - Dec 2019) | Milestone 3 (Jan 2020 - Jun 2020) | Milestone 4 (July 2020-Dec 2020) | Milestone 5 (Jan 2021 - June 2021) | Miestone 6 (July 2021 - Dec 2021) | Target - March 2022 | DFID attribution* | Cumulative or reporting period**
|  | # of pregnant and lactating women receiving counselling and education on infant and young child feeding (IYCF) | Planned | 1530810 | 834563 | 1591614 | 2371376 | 3151138 | 3552715 | 3954292 | 4355869 | 30% | Cumulative
|  |  | Achieved |  | 1856980 | 3318965 | 4414128 | 6071581 | 7216272
Source
IYCF monthly reports from health facilities, mobile teams, community health volunteers and CHWs and integrated outreach activities
| Health | Output Indicator 1.4 (health) |  | Baseline | Milestone 1 (Oct 2018 - Jun 2019) | Milestone 2 (Jul 2019 - Dec 2019) | Milestone 3 (Jan 2020 - Jun 2020) | Milestone 4 (July 2020-Dec 2020) | Milestone 5 (Jan 2021 - June 2021) | Miestone 6 (July 2021 - Dec 2021) | Target - March 2022 | DFID attribution* | Cumulative or reporting period**
|  | # of primary health consultations provided to children under 5, caregivers and pregnant and lactating women through health facilities, outreach services, and mobile health teams | Planned | 1090559 | 1732991 | 2400000 | 3552632 | 4400000 | 6500000 | 7000000 | 7500000 | 30%
|  |  | Achieved |  | 2201648 | 1836978 | 3645229 | 5379925 | 6767684 |  |  |  | cumulative
Source
monthly reports from health facilities, mobile teams, community health workers and integrated outreach activities
|  | Output Indicator 1.5 (health) |  | Baseline | Milestone 1 (Oct 2018 - Jun 2019) | Milestone 2 (Jul 2019 - Dec 2019) | Milestone 3 (Jan 2020 - Jun 2020) | Milestone 4 (July 2020-Dec 2020) | Milestone 5 (Jan 2021 - June 2021) | Miestone 6 (July 2021 - Dec 2021) | Target - March 2022 | DFID attribution* | Cumulative or reporting period**
|  | # of women of reproductive age receiving skilled birth attendance (home/facilities) | Planned | 35452 | 35452 | 70904 | 195466 | 320028 | 520000 | 720000 | 933916 | 15%
|  |  | Achieved |  | 23753 | 120531 | 279102 | 448395 | 566900 |  |  |  | cumulative
Source
monthly reports from health facilities, mobile teams, community health workers and integrated outreach activities
|  | Output Indicator 1.6a (health) |  | Baseline | Milestone 1 (Oct 2018 - Jun 2019) | Milestone 2 (Jul 2019 - Dec 2019) | Milestone 3 (Jan 2020 - Jun 2020) | Milestone 4 (July 2020-Dec 2020) | Milestone 5 (Jan 2021 - June 2021) | Miestone 6 (July 2021 - Dec 2021) | Target - March 2022 | DFID attribution* | Cumulative or reporting period**
|  | % of targeted children who are vaccinated with three doses of DTP/Penta vaccine (Routine vaccination & Integrated Outreach rounds) | Planned | 82% | 784869 (100%) | 523246 (100%) | 540079 (100%) | 540,079 (100%) | 556,912 (100%) | 556,912 (100%) | 830372 (100%) | 25%
|  |  | Achieved |  | 653,020 (83%) | 545,354 (104%) | 335315 (62%) | 588574 (109%) | 416,825 (75%) |  |  |  | reporting period
Source
Administrative Data MoPHP, monthly reports from health facilities, mobile teams, community health workers and integrated outreach
|  | Output Indicator 1.6b (health) |  | Baseline | Milestone 1 (Oct 2018 - Jun 2019) | Milestone 2 (Jul 2019 - Dec 2019) | Milestone 3 (Jan 2020 - Jun 2020) | Milestone 4 (July 2020-Dec 2020) | Milestone 5 (Jan 2021 - June 2021) | Miestone 6 (July 2021 - Dec 2021) | Target - March 2022 | DFID attribution* | Cumulative or reporting period**
|  | % of children <5yrs vaccinated during each rounds of Polio Vaccination campaign (Total target=5,535,816) | Planned | 89% | 5535816 | 5535816 | 5535816 | 5535816 | 4104630 | 1431186 | 5535816 | 70%
|  |  | Achieved |  | 4,692,335 (85%) | 4,548,829 (82%) | 0 | 5,018,283 (91%) | 3,800,313 (93%) |  |  |  | reporting period
Source
Administrative Data MoPHP, monthly reports from health facilities, mobile teams, community health workers and integrated outreach
|  | Output Indicator 1.7 (health) |  | Baseline | Milestone 1 (Oct 2018 - Jun 2019) | Milestone 2 (Jul 2019 - Dec 2019) | Milestone 3 (Jan 2020 - Jun 2020) | Milestone 4 (July 2020-Dec 2020) | Milestone 5 (Jan 2021 - June 2021) |  | Target - Sept 2021 | DFID attribution* | Cumulative or reporting period**
|  | # of healthcare facility staff and community health workers Orientated in Infection Prevention and Control, detection and referral of suspected COVID-19 cases among children, pregnant and breastfeeding women | Planned | 74%: 12000; 75%: 12000 |  | 12000 | 13%
|  |  | Achieved | 74%: 7244; 75%: 10686 |  |  |  | cumulative
Source
Training Report from FOs
| WASH | Output Indicator 1.8 (WASH) |  | Baseline | Milestone 1 (Oct 2018 - Jun 2019) | Milestone 2 (Jul 2019 - Dec 2019) | Milestone 3 (Jan 2020 - Jun 2020) | Milestone 4 (July 2020-Dec 2020) | Milestone 5 (Jan 2021 - June 2021) | Miestone 6 (July 2021 - Dec 2021) | Target - March 2022 | DFID attribution* | Cumulative or reporting period**
|  | # of people provided with access to drinking water through UNICEF support to operational and maintenance (O&M) and rehabilitation of public water systems | Planned | 1119791 | 1151791 | 1260791 | 1369791 | 1478791 | 2400000 | 2400000 | 2400000 | 53%
|  |  | Achieved |  | 1220034 | 1356886 | 1620932 | 3997447 | 4070128 | 3,927,987 |  |  | cumulative
Source
Field monitoring and partner reports
|  | Output Indicator 1.9a (WASH) |  | Baseline | Milestone 1 (Oct 2018 - Jun 2019) | Milestone 2 (Jul 2019 - Dec 2019) | Milestone 3 (Jan 2020 - Jun 2020) | Milestone 4 (July 2020-Dec 2020) | Milestone 5 (Jan 2021 - June 2021) | Miestone 6 (July 2021 - Dec 2021) | Target - March 2022 | DFID attribution* | Cumulative or reporting period**
|  | # of individuals provided with emergency WASH | Planned | 668154 | 738154 | 895654 | 1053154 | 1702907 | 1939157 | 2062857 | 2344691 | 100%
|  |  | Achieved |  | 1319215 | 1545407 | 1911136 | 2721490 | 2844993 |  |  |  | cumulative
Source
Field monitoring and partner reports
|  | Output Indicator 1.9b (WASH) |  | Baseline | Milestone 1 (Oct 2018 - Jun 2019) | Milestone 2 (Jul 2019 - Dec 2019) | Milestone 3 (Jan 2020 - Jun 2020) | Milestone 4 (July 2020-Dec 2020) | Milestone 5 (Jan 2021 - June 2021) | Miestone 6 (July 2021 - Dec 2021) | Target - March 2022 | DFID attribution* | Cumulative or reporting period**
|  | # of Rapid Response Teams responding to cholera and emergencies | Planned | 0 | 650 | 750 | 800 | 300 | 300 | 300 | 300 | 60%
|  |  | Achieved |  | 750 | 750 | 300 | 0 | 300
Source
|  |  | Field monitoring and partner reports | [9 empty] | reporting period
|  | Output Indicator 1.10 (WASH) |  | Baseline | Milestone 1 (Oct 2018 - Jun 2019) | Milestone 2 (Jul 2019 - Dec 2019) | Milestone 3 (Jan 2020 - Jun 2020) | Milestone 4 (July 2020-Dec 2020) | Milestone 5 (Jan 2021 - June 2021) | Miestone 6 (July 2021 - Dec 2021) | Target - March 2022 | DFID attribution* | Cumulative or reporting period**
|  | # of household members who have benefitted from UNICEF hygiene promotion activities, observed practicing handwashing with soap at critical times | Planned | 0 | 650000 | 800000 | 950000 | 1100000 | 1670000 | 1959616 | 2104424 | 100%
|  |  | Achieved |  | 635322 | 905620 | 1050280 | 1225280 | 1498742 |  |  |  | cumulative
Source
Field monitoring and partner reports; Behaviour monitoring reports
|  | Output Indicator 1.11 (WASH) |  | Baseline | Milestone 1 (Oct 2018 - Jun 2019) | Milestone 2 (Jul 2019 - Dec 2019) | Milestone 3 (Jan 2020 - Jun 2020) | Milestone 4 (July 2020-Dec 2020) | Target - March 2021 | Miestone 6 (July 2021 - Dec 2021) | Target - March 2021 | DFID attribution* | Cumulative or reporting period**
|  | # people supported through continuity of WASH service | Planned | 74%: 400000; 75%: 400000 |  | 400000 | 100%
|  |  | Achieved | 74%: 1650000; 75%: 1650000 |  |  |  | cumulative
Source
Field monitoring, partner reports
|  | Output Indicator 1.12 (WASH) |  | Baseline | Milestone 1 (Oct 2018 - Jun 2019) | Milestone 2 (Jul 2019 - Dec 2019) | Milestone 3 (Jan 2020 - Jun 2020) | Milestone 4 (July 2020-Dec 2020) | Target - March 2021 | Miestone 6 (July 2021 - Dec 2021) | Target - March 2021 | DFID attribution* | Cumulative or reporting period**
|  | # WASH NFI kit distributed to self-isolated Household | Planned | 74%: 25,000 HH/ 200,000 people; 75%: 25,000 HH/ 200,000 people |  | 25,000 HH/ 200,000 people | 100%
|  |  | Achieved | 74%: 21,875HH/ 175,000 people; 75%: 64,066 HH/ 448,462 people
Source
Field monitoring, partner reports
| Health and Nutrition (Social Protection) | Output Indicator 1.13 (H&N) CLOSED |  | Baseline | Milestone 1 (Oct 2018 - Jun 2019) | Milestone 2 (Jul 2019 - Dec 2019) | Milestone 3 (Jan 2020 - Jun 2020) | Milestone 4 (July 2020-Dec 2020) | Milestone 5 (Jan 2021 - June 2021) |  | Target - Sept 2021 | DFID attribution* | Cumulative or reporting period**
|  | # of pregnant women and mothers with newborns receiving vouchers to cover transportation costs for delivery, postnatal care and medical care in case of complications (Target 5,285) | Planned | TBD | 0 | 0 | 0 | 3150 (60%) | 3150 (60%) |  | 3,700 (70%) | 100%
|  |  | Achieved |  | 0 | 0 | 0 | 0 |  |  |  |  | cumulative
Source
Helath Voucher Project MIS, Baseline survey of one pilot district in 2020
IMPACT WEIGHTING (%) | Child Protection | Output Indicator 1.14a (protection) |  | Baseline | Milestone 1 (Oct 2018 - Jun 2019) | Milestone 2 (Jul 2019 - Dec 2019) | Milestone 3 (Jan 2020 - Jun 2020) | Milestone 4 (July 2020-Dec 2020) | Milestone 5 (Jan 2021 - June 2021) | Miestone 6 (July 2021 - Dec 2021) | Target - March 2022 | DFID attribution* | Cumulative or reporting period**
50% |  | # of identified children who receive support through case management/referrals | Planned | 1500 | 500 | 900 | 925 | 1125 | 1200 | 1625 | 1850 | 100%
|  |  | Achieved |  | 744 | 912 | 932 | 946 | 1000 |  |  |  | cumulative
|  |  | Source | [10 empty] | RISK RATING
High
|  | Output Indicator 1.14b (protection) |  | Baseline | Milestone 1 (Oct 2018 - Jun 2019) | Milestone 2 (Jul 2019 - Dec 2019) | Milestone 3 (Jan 2020 - Jun 2020) | Milestone 4 (July 2020-Dec 2020) | Milestone 5 (Jan 2021 - June 2021) | Miestone 6 (July 2021 - Dec 2021) | Target - March 2022 | DFID attribution* | Cumulative or reporting period**
|  | # of children and caregivers receiving mental health and PSS inside HF and remotely (within HF catchment areas) | Planned | 125000 | 47120 | 77120 | 92120 | 112120 | 125000 | 134000 | 138600 | 100% |  |  | 25000000
|  |  | Achieved |  | 47120 | 65555 | 91056 | 94486 | 106288 |  |  |  | cumulative |  | 8333333.3333
|  |  | Source | [11 empty] | 70000000
0.11905
OUTPUT 2 | Nutrition | Output Indicator 2.1 (nutrition) |  | Baseline | Milestone 1 (Oct 2018 - Jun 2019) | Milestone 2 (Jul 2019 - Dec 2019) | Milestone 3 (Jan 2020 - Jun 2020) | Milestone 4 (July 2020-Dec 2020) | Milestone 5 (Jan 2021 - June 2021) | Miestone 6 (July 2021 - Dec 2021) | Target - March 2022 | DFID attribution* | Cumulative or reporting period** | Assumptions
Nutrition, health and WASH services in Yemen are supported at a local level to be more efficient and effective |  | % of functional health facilities supported by UNICEF that provide SAM management programmes | Planned | 83% | 85% | 85% | 90% | 70% | 80% | 90% | 95% | 15% | Reporting period
|  |  | Achieved |  | 89% | 89% | 79% | 84% | 89%
Source
OTPs Status Tracking Reports, Third Party Monitoring Reports
|  | Output Indicator 2.2 (nutrition) |  | Baseline | Milestone 1 (Oct 2018 - Jun 2019) | Milestone 2 (Jul 2019 - Dec 2019) | Milestone 3 (Jan 2020 - Jun 2020) | Milestone 4 (July 2020-Dec 2020) | Milestone 5 (Jan 2021 - June 2021) | Miestone 6 (July 2021 - Dec 2021) | Target - March 2022 | DFID attribution* | Cumulative or reporting period**
|  | # of Therapeutic Feeding Centre (TFCs) and Outpatient Therapeutic Programme (OTPs) supported by UNICEF with functional child-friendly spaces (offering Early Childhood Development services) | Planned | 0 | 120 | 120 | 120 | 200 | 230 | 270 | 300 | 50% | Cumulative
|  |  | Achieved |  | 80 | 80 | 83 | 83 | 83
Source
Program Reports, Third Party Monitoring Reports
| Health | Output Indicator 2.3 (health) |  | Baseline | Milestone 1 (Oct 2018 - Jun 2019) | Milestone 2 (Jul 2019 - Dec 2019) | Milestone 3 (Jan 2020 - Jun 2020) | Milestone 4 (July 2020-Dec 2020) | Milestone 5 (Jan 2021 - June 2021) | Miestone 6 (July 2021 - Dec 2021) | Target - March 2022 | DFID attribution* | Cumulative or reporting period**
|  | % of clinics supported by UNICEF offering minimum initial service package (primary health care, reproductive health, sexual and gender based violence support) (total=4500) | Planned | 0 | 44% | 44% | 56% | 56% | 56% | 56% | 67% | 20%
|  |  | Achieved |  | 44% | 56% | 56% | 56% | 56% |  |  |  | cumulative
Source
|  | Output Indicator 2.4 (health) |  | Baseline | Milestone 1 (Oct 2018 - Jun 2019) | Milestone 2 (Jul 2019 - Dec 2019) | Milestone 3 (Jan 2020 - Jun 2020) | Milestone 4 (July 2020-Dec 2020) | Milestone 5 (Jan 2021 - June 2021) | Miestone 6 (July 2021 - Dec 2021) | Target - March 2022 | DFID attribution* | Cumulative or reporting period**
|  | % of estimated pregnant women in Yemen that have received at one ante-natal visit by a community health worker | Planned | N/A | 10% | 20% | 30% | 40% | 45% | 45% | 50% | 25%
|  |  | Achieved |  | 10% | 20% | 31% | 39% | 43% |  |  |  | cumulative
Source
Administrative Data MoPHP, monthly reports from health facilities,
|  | Output Indicator 2.5 (health) |  | Baseline | Milestone 1 (Oct 2018 - Jun 2019) | Milestone 2 (Jul 2019 - Dec 2019) | Milestone 3 (Jan 2020 - Jun 2020) | Milestone 4 (July 2020-Dec 2020) | Target - March 2021 | Miestone 6 (July 2021 - Dec 2021) | Target - Sept 2021 | DFID attribution* | Cumulative or reporting period**
|  | # of Health Facilities provided with medical, preventive and protective supplies (PPE, IPC supplies, ventilators and related equipment, test kits etc) to continue service delivery with optimum safety from COVID-19 transmission (both for health providers and clients) | Planned | 74%: 4000; 75%: 4000 |  |  | 15%
|  |  | Achieved | 74%: 2157; 75%: 3643 |  |  |  | cumulative
Source
Delivery Report from supply
| WASH | Output Indicator 2.6 (WASH) |  | Baseline | Milestone 1 (Oct 2018 - Jun 2019) | Milestone 2 (Jul 2019 - Dec 2019) | Milestone 3 (Jan 2020 - Jun 2020) | Milestone 4 (July 2020-Dec 2020) | Target - March 2021 | Miestone 6 (July 2021 - Dec 2021) | Target - Sept 2021 | DFID attribution* | Cumulative or reporting period**
|  | # of UNICEF supported isolation units /health centres meeting WASH basic IPC standard | Planned | 74%: 30; 75%: 30 |  |  | 100%
|  |  | Achieved | 74%: 39; 75%: 39 |  |  |  | cumulative
Source
Field monitoring and partner reports
|  | Output Indicator 2.7a (WASH) |  | Baseline | Milestone 1 (Oct 2018 - Jun 2019) | Milestone 2 (Jul 2019 - Dec 2019) | Milestone 3 (Jan 2020 - Jun 2020) | Milestone 4 (July 2020-Dec 2020) | Milestone 5 (Jan 2021 - June 2021) | Miestone 6 (July 2021 - Dec 2021) | Target - March 2022 | DFID attribution* | Cumulative or reporting period**
|  | # of water facilities supported by UNICEF that have a risk management plan for improvement of water services | Planned | 0 | 0 | 1 | 2 | 3 | 4 | 4 | 4 | 100%
|  |  | Achieved |  | 0 | 1 | 3 | 3 | 3 |  |  |  | Cumulative
Source
Field monitoring and partner reports (No study was carried out to establish the data including baseline)
IMPACT WEIGHTING (%) |  | Output Indicator 2.7b (WASH) |  | Baseline | Milestone 1 (Oct 2018 - Jun 2019) | Milestone 2 (Jul 2019 - Dec 2019) | Milestone 3 (Jan 2020 - Jun 2020) | Milestone 4 (July 2020-Dec 2020) | Milestone 5 (Jan 2021 - June 2021) | Miestone 6 (July 2021 - Dec 2021) | Target - March 2022 | DFID attribution* | Cumulative or reporting period**
45% |  | # of people provided with improved water services by water facilities with a risk management plan | Planned | 0 | 0 | 500000 | 850000 | 1100000 | 1250000 | 1400000 | 1500000 | 100%
|  |  | Achieved |  | 0 | 710758 | 929523 | 3093498 | 3093498 |  |  |  | cumulative
|  |  | Source | [10 empty] | RISK RATING
|  |  | Field monitoring and partner reports | [10 empty] | High
OUTPUT 3 | Evidence | Output Indicator 3.1 (learning) |  | Baseline | Milestone 1 (Oct 2018 - Jun 2019) | Milestone 2 (Jul 2019 - Dec 2019) | Milestone 3 (Jan 2020 - Jun 2020) | Milestone 4 (July 2020-Dec 2020) | Milestone 5 (Jan 2021 - June 2021) | Miestone 6 (July 2021 - Dec 2021) | Target - March 2022 | DFID attribution* | Cumulative or reporting period** | Assumption
Evidence is generated by UNICEF to improve understanding of the context and influence the shape of the response in Yemen |  | # of surveys and assessments conducted by UNICEF funded by DFID | Planned | 0 |  | 2 | 2 | 5 | 6 | 7 | 8 | 100% (For SMART surveys) | Cumulative
|  |  | Achieved |  |  | 2 | 2 | 4 | 6
Source
Survey and assessment reports
|  | Output Indicator 3.2 (learning) |  | Baseline | Milestone 1 (Oct 2018 - Jun 2019) | Milestone 2 (Jul 2019 - Dec 2019) | Milestone 3 (Jan 2020 - Jun 2020) | Milestone 4 (July 2020-Dec 2020) | Milestone 5 (Jan 2021 - June 2021) | Miestone 6 (July 2021 - Dec 2021) | Target - March 2022 | DFID attribution* | Cumulative or reporting period**
|  | # of analysis conducted on how the response efficiency could be improved (e.g. return on investment analysis) | Planned | 0 | 0 | 0 | 5 | 5 | 8 | 11 | 15 | 25%
|  |  | Achieved |  |  | 5 | 7 | 9 | 10 |  |  |  | cumulative
Source
Progress reports, presentations for review meetings, analytical reports
IMPACT WEIGHTING (%) |  | Output Indicator 3.3 (learning) |  | Baseline | Milestone 1 (Oct 2018 - Jun 2019) | Milestone 2 (Jul 2019 - Dec 2019) | Milestone 3 (Jan 2020 - Jun 2020) | Milestone 4 (July 2020-Dec 2020) | Milestone 5 (Jan 2021 - June 2021) |  | Target - Sept 2021 | DFID attribution* | Cumulative or reporting period**
5% |  | # of risk analysis and preparedness and contingency plans updated and shared with DFID | Planned | 0 | 0 | 1 | 2 | 2 |  |  | 5 | 100%
|  |  | Achieved | 68%: 1; 71%: 2; 74%: 2 |  |  |  | cumulative
|  |  | Source | [10 empty] | RISK RATING
|  |  |  | 62%: Risk register |  |  |  |  | Low
IMPACT WEIGHTING (%) |  | Output Indicator 3.3 (learning) |  | Baseline | Milestone 1 (Oct 2018 - Jun 2019) | Milestone 2 (Jul 2019 - Dec 2019) | Milestone 3 (Jan 2020 - Jun 2020) | Milestone 4 (July 2020-Dec 2020) | Milestone 5 (Jan 2021 - June 2021) | Miestone 6 (July 2021 - Dec 2021) | Target - March 2022 | DFID attribution* | Cumulative or reporting period**
5% |  | NIS review action plan endorsed/validated | Planned | 62%: 0 |  | 1
Achieved | bar: 62% to 74%
|  |  | Source | [10 empty] | RISK RATING
|  |  |  | 62%: Risk register |  |  |  |  | Low
*DFID attribution refers to the percent of results which can be attributed to DFID funds
** Cumulative results are cumulative for both the milestone and overall target. Reporting period refers to achievement during the milestone period.
*** Target and Milestones are set as 90% of the nutrition caseload, and is subject to revision based on caseload
Note on K93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Integrated Outreach Round 1 was implemented in June. The data is not included in the update, and will be included once compiled.
Note on K98: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The campaign was planned only in 14 Northern governorates
Note on M97: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The denominator will be subject to change based on the update/advice that will be provided by NEPI Taskforce and MoPHP.

## Change frame
Use this change log to record all changes to the logframe over the life of the project.
ID | LOGFRAME SECTION | DETAILS OF CHANGE | AUTHOR | DATE
E.g. | Output 1, Indictor 2 | Indicator amended from 'No of children enrolled in primary schools' to 'Number of children enrolled in UNICEF supported primary schools (disagregated by sex) | Joe Bloggs | 2018-01-01
1 | Outcome indicator 3 (WASH) | Upon discussion with FCDO, the outcome indicator for WASH was not indicative of the WASH programme as a whole. The original indicator number of people benefitting from waste water collected by local councils supported by UNICEF treated and safely disposed has been replaced with number of people accessing a sufficient quantity of safe water for drinking, cooking and personal hygiene. | UNICEF | 01.08.2021
2 | Output Indicator 1.7 (health) | The COVID-19 indicators added for the GBP 10m top up funds received in June 2020 have now been closed, with final reporting as of 31 March 2021 | UNICEF | 01.08.2021
3 | Output Indicator 1.11 (WASH) | The COVID-19 indicators added for the GBP 10m top up funds received in June 2020 have now been closed, with final reporting as of 31 March 2021 | UNICEF | 01.08.2021
4 | Output Indicator 1.12 (WASH) | The COVID-19 indicators added for the GBP 10m top up funds received in June 2020 have now been closed, with final reporting as of 31 March 2021 | UNICEF | 01.08.2021
5 | Output Indicator 2.5 (health) | The COVID-19 indicators added for the GBP 10m top up funds received in June 2020 have now been closed, with final reporting as of 31 March 2021 | UNICEF | 01.08.2021
| Output Indicator 2.6 (WASH) | The COVID-19 indicators added for the GBP 10m top up funds received in June 2020 have now been closed, with final reporting as of 31 March 2022 | UNICEF | 01.08.2021
6 | Output Indicator 1.13 (H&N) CLOSED | has been closed, due to ongoing challenges with the MoPHP in the design of the programme. UNICEF is still exploring options and looking at potentially integrating this programme with other ongoing cash benefit programmes, and will continue discussions with FCDO. | UNICEF | 01.08.2021
7 | Output Indicator 3.3 (learning) | has been closed and replaced with NIS review action plan endorsed/validated. Both UNICEF and FCDO agree that the new indicator will better measure programmatic outcomes, and measure progress against the Nutrition Information System action plan. | UNICEF | 01.08.2021