Business Case

Summary Sheet

Title: Afghanistan Election Support Programme
Programme Summary: / The programme will support upcoming parliamentary and presidential elections in Afghanistan, as well as longer-term electoral and political reform. The UK will fund on-going capacity building to Afghanistan’s Election Management Bodies; operations for 2018 and 2019 elections; civil society and media organisations to improve citizen participation and government accountability; and a programme of reform to the longer-term development of electoral and political processes in Afghanistan. The programme aims to deliver more credible elections and a more inclusive process to inform reform, thereby strengthening electoral systems and increasing political stability. Our support will be delivered through multi-donor mechanisms of support to ensure coordination across the international community, and will be implemented in close collaboration with FCO colleagues at the British Embassy in Kabul. Programme design draws on extensive lessons learnt from past cycles of election support and a cross-HMG policy review of Afghanistan’s electoral and democratic development.
Programme Value: / £24 million		Country/ Region: / Afghanistan
Programme Code:	Start Date: / September 2018	End Date: / August 2021
Overall programme risk rating:	Major
Vault Number:	40997162

Intervention Summary (2 pages max)

Narrative summary of why UK support needed, what the funds will be spent on, where, over what period of time, via whom and what they will deliver: Afghanistan plans to hold two rounds of elections over the next two years. Parliamentary elections are due in 2018, followed by Presidential in 2019. Elections are critical to supporting the country’s democratic systems, but experience from past election rounds highlights the challenges in running fair and transparent elections and the risk of creating political instability.
The Government of Afghanistan has requested support from the international community to plan and deliver upcoming elections. DFID Afghanistan will provide up to £16.5 million to the UN’s Election Support programme (UNESP) to support the Afghan Election Management Bodies deliver elections and build their capacity for future election cycles. This investment will be complemented by an additional contribution of £2.2 million for Civil Society and media organisations to conduct observation activities, hold the Government to account on delivery of elections, and improve participation of all Afghans. UK support is targeted beyond the immediate election cycle and is aimed at supporting reform of electoral and political systems over the next three years. DFID Afghanistan will invest a further £5.3 million in a research-driven project component aimed at identifying key barriers to credible elections and supporting future reforms in these areas.
Does the programme fit with DFID’s strategic architecture? The Programme is in line with the NSC Strategy and Building Stability Framework, which call for support to political systems, including elections, to strengthen democratic systems and enable fairer power structures in fragile contexts such as Afghanistan. Electoral support will also contribute to Strategic Objective 1 under DFID Afghanistan’s Country Strategy supporting ‘peace, security and governance’.
What percentage of DFID’s Single Departmental Plan results target does this programme represent? The programme will not directly deliver SDP results. However, by contributing to a more politically stable state, support to elections will increase the effectiveness of those programmes which do, including the Afghanistan Reconstruction Trust Fund.
Is the programme coherent with the wider international community and partner government response? Has the programme set out a sustainable exit strategy? The largest component of the programme will be delivered through a multi-donor programme fund managed by UNDP. All other members of the international community are committing electoral support through this mechanism. This will ensure close coordination between donors, and enable one voice with which to work alongside the Government on election planning. 2018 and 2019 represent the first Afghan-led election processes, including funding from the central budget. The focus on capacity building and support to election reform is expected to reduce the need for support from the international community in future elections. This will be complemented by learning generated under the programme on future electoral and political reforms. Support to civil society will be provided through an EU-managed programme to limit overlap of donor funding in this area.
Has the programme considered working with HMG Departments and accessing cross-HMG funds? The programme will be delivered in close collaboration with FCO colleagues in the British Embassy Kabul and London. The programme will benefit from frequent updates on the political context and messaging to government will be delivered through diplomatic channels. The FCO and DFID conducted a joint internal review in 2017 to guide HMG’s election policy; and both departments regularly attend coordination meetings in Kabul.
How does the programme relate to other UK aid within the specific sector? Electoral Support will complement wider DFID Afghanistan governance and accountability programming, including investment in parliamentary support, civil service reform, and anti-corruption. Supporting a credible election process accepted by the Afghan population will benefit DFID Afghanistan’s investments across the portfolio of programmes.
Is there sufficient flexibility to learn and adjust to changes in the context? What level of flexibility is there to shift this and future commitments? Using a multi-donor programme fund, will allow for flexibility in the event of changes to the political context or a delay in elections. A programme fund will allow us to track UK funding under each output pillar, target funding to the areas developing quickly and most in need of donor support. It also allows us to closely manage monitoring and distribution of our funds to avoid advance of need issues. 12 months of research and design activities are included before implementing actions related to reform.
Does the proposed level of risk to be taken fit with DFID’s risk appetite for this portfolio? The risk is assessed as Major, largely as a result of the risk of postponed elections, and inability to access insecure areas. HMG has a high risk appetite in Afghanistan due to the challenges of working in a fragile state, and designs programmes to mitigate risk where possible. Continued engagement with all levels of government (in coordination with British Embassy colleagues); and the proposed multi-donor coordination mechanism will mitigate delivery risks related to delays and political intervention. The risk of not supporting elections is judged to be higher than that associated with this investment in strengthening the election system. Fiduciary and operational risks are assessed as low.
Is there a clear communications strategy to reinforce our objectives? The programme will not include UK Aid branding given the political sensitivities of international support to Afghan elections. An embassy-wide communications strategy on elections is being developed which will recognise UK funding.
Has the programme been quality assured? How confident are we that the skills, capability, resources and political will exist to deliver the programme? The programme has been quality assured by the Head of Office, Governance Adviser, and the Programme Design Team. The political will exists in Afghanistan to deliver this programme: the Government has requested support for elections from the international community and approved the UNDP multi-donor programme fund as the most appropriate means for doing so. Ongoing political interventions and interactions with the Afghanistan Government will ensure momentum on political will continues. DFID Afghanistan and United Nations Assistance Mission in Afghanistan (UNAMA) have the resources and capability to deliver the programme.
Does the SRO and team have the capability and resources to deliver this programme? The SRO will be the DFID Afghanistan’s Governance Adviser, supported by an experienced Programme Manager, Commercial and Financial Team, Results lead and Economist. The Political Inclusion and Accountability Team Leader/Deputy Team Leader will oversee delivery, reporting to the Deputy Head of Office.
Strategic Case
Why is it important to support elections in Afghanistan?
Upcoming elections are critical to Afghanistan’s stability
Sustained international support to Afghanistan’s political systems, including elections, features strongly in the UK National Security Council (NSC) strategy under pillar two which demands more robust democratic systems in Afghanistan. As a fundamental feature of democracy, fair elections provide an important means of improving responsiveness by making elected officials accountable to voters. Even in fragile states with weak institutions, regular fair elections can be part of an incremental process of democratic consolidation and provide openings for greater civic engagement in governance.
[note] Michael Callen and James Long, ‘Institutional Corruption and Election Fraud: Evidence from a Field Experiment in Afghanistan’, American Economic Review Vol. 105, No. 1, January 2015
[note] DFID and FCO, ‘How to Note on Electoral Assistance’, 2014
Upcoming parliamentary and presidential elections in Afghanistan, planned for 2018 and 2019, present a critical juncture in the country’s transition to a more stable and self-reliant state.
[note] District and Provincial elections are also due to take place alongside Parliamentary and Presidential elections respectively. Any future election programme will also support these processes if the Government confirms that they are going ahead.
Since the fall of the Taliban in 2001, Afghanistan has held presidential elections in 2004, 2009 and 2014; elections to the lower house of the Afghan parliament (‘Wolesi Jirga’) in 2005 and 2010; and provincial council elections in 2005, 2009 and 2014. District elections have never been held. The term of the current parliament expired in 2015. There is a public expectation that parliamentary elections are held in 2018 and presidential elections by 2019. Additional delays to the elections are likely to further diminish public confidence in the nation’s political institutions, and serve to severely undermine Afghanistan’s fragile democracy. However elections will need to be credible and acceptable to Afghan political actors and to the Afghan public in order to not exacerbate political instability.
[note] Anna Larson, ‘Elections and security in Afghanistan: minimising instability going forward, May 2018
[note] Noah Coburn and Anna Larson, ‘Afghan Views of Government and Elections: Legitimacy Pending’, USIP Special Report 409, July 2017

Challenges of delivering elections in Afghanistan
Experience from past election rounds in Afghanistan highlight the challenges in running fair and transparent elections and the risk of creating political instability. The post-2001 political settlement and current electoral system incentivise the winners to do everything possible to win, and the losers to reject the outcomes. This is exacerbated by inefficient electoral management bodies and institutions.
Over 6.5 million Afghans voted in the 2014 presidential elections, with the largest number of female voters recorded to date. However, inconsistencies in voter turnout and allegations of ballot stuffing resulted in Abdullah Abdullah rejecting the results of the second round run-off, causing a political crisis. This was only resolved by sustained international political interventions, and following a nationwide audit of ballots and mediation by the US, the two candidates agreed to form a National Unity Government (NUG).
Electoral reform targeting fraud was central to the political agreement that underpinned the NUG. Some progress has been made, including a new legal framework for elections, and the appointment of new Supplier 1 members. President Ghani also established a number of coordinating mechanisms for national and international engagement on the electoral process. These reforms showed a marked change in political commitment for credible, transparent, free and fair elections. This shift presented an opportunity to foster wider election reform to allow the Afghan people a voice in the future of their country through democratic process. However without further support to improve the capacity of the Supplier1s, and address some key shortcomings such as the lack of a voter register, future elections risk destabilising Afghanistan further.
[note] UK Government, Afghanistan Joint Analysis of Conflict and Stability (JACS), 2015
The current pressures stem from a need to implement and embed longer-term electoral and political reform, including constituency boundaries, voting systems, greater diversity of candidates, and the election calendar. Current opportunities for fraud and underlying weaknesses in the system continue to reward and strengthen patronage networks in Afghanistan. Without investment in addressing such issues, ‘election crises will remain a permanent fixture of the political horizon of Afghanistan’, likely resulting in renewed calls for international support to election cycles for years to come.
[note] UK JACS 2015
There is a risk that if not perceived to be credible, the fall-out from 2018 and 2019 elections could be more de-stabilising than 2014. Afghanistan has been largely spared significant electoral violence since 2001, but long-standing ethnic tensions are rising and the threat of ‘bringing supporters out onto the streets’ has been previously used by losing candidates.
Concerns also exist on public credibility in elections. This has fallen sharply since the 2014 elections. The 2017 Survey of the Afghan People reported a drop in the proportion of respondents satisfied with the way democracy works from 73% in 2014 to 57% in 2017. Another failed election will further lower confidence, destroying legitimacy in the country’s democratic institutions. This further emphasises the need to ensure the voice of the Afghan people is heard and that the changes brought in and recommended since the 2014 election are fully realised. We have been working with the Supplier 1 to strengthen their public outreach and communications to mitigate these concerns
Nevertheless DFID Afghanistan recognises that the security situation in the country will continue to pose a significant challenge to the delivery of elections in 2018 and 2019. The on-going Taliban insurgency and potentially the increase of Islamic State Khorasan Province (ISKP) activity will restrict access to election officials and observers, and risks disenfranchising certain sections of the population. However, this does not negate the value of efforts to influence credible elections. This is a further step in the progress towards a more democratic Afghanistan. Ultimately, sustainable peace will only be possible if a legitimate and accountable government is in place to negotiate. Given recent tentative steps on peace, this will be more important than ever.

What support is needed now?
The 2018/2019 elections are the first to take place since the 2014 draw-down of international troops from Afghanistan, and the Government is taking a leading role in election planning compared to previous rounds. The Afghan-led election planning continues to require technical support to the election management bodies, security planning and financial contributions towards election operations. As such, the NUG has requested support from the international community in planning and delivering the upcoming elections. It is in the UK’s interest to support this request, which provides an entry point to supporting the wider development of Afghanistan’s institutions and economy, putting it on a path to stability.
Financial Support for 2018 and 2019 election operations: 2018 Parliamentary elections are budgeted at $124 million, with the Government of Afghanistan able to provide $30 million. The Government has requested financial assistance to conduct elections from a group of seven international donors which make up the Election Support Group (US, UK, Germany, EU, Denmark, Norway and Japan). A full breakdown of other donor contributions is included (see annexe 4). Presidential elections in 2019 are expected to cost an additional estimated $90-100 million, with the Government of Afghanistan expected to contribute $30 million.
Technical Assistance to the Supplier 1: A UN team, supported by the UK and six other donor countries, has been working alongside staff in Afghanistan’s Supplier 2 and Supplier 3 since October 2017. In response to the 2014 electoral crisis, new commissioners were recruited to both bodies, who require expert support to plan and deliver elections. Building the capacity of the Supplier1s to independently manage credible elections and engage with stakeholders will increase stakeholder confidence in and participation in the electoral process. Both the Supplier 2 and Supplier 3 require embedded support to plan for and deliver upcoming elections. Particularly with regard to electoral administration, public outreach, procurement, operations, recruitment, legal and procedural advice and dispute resolution case management.
Efforts to limit opportunities for electoral fraud: It is not enough for elections to simply take place. Voters must perceive them to be reasonably credible to result in any legitimate relationship between citizen and state. Using data from 2010 and 2014, Eli Berman et al. found that the fairness of ‘elections affects attitudes of citizens towards their government directly relevant to their willingness to be governed, a contributor to legitimacy.’ Given the risk of elections as a destabilising force in Afghanistan, the quality of elections is even more important.
[note] Eli Berman, Michael Callen, Clark Gibson, James Long, ‘Election Fairness and Government Legitimacy in Afghanistan’, National Bureau of Economic Research Working Paper, March 2014
[note] William Maley and Michael Maley, ‘Appraising Electoral Fraud: Tensions and Complexities’, Conflict, Security and Development 16:6, December 2016
The absence of a credible voter register has been a key shortcoming of previous elections rounds. In 2014, 21 million voter cards were in circulation for an estimated voting population of 12 million people. Analysts have blamed the subsequent discrepancies in ballot papers and inability to check voting figures against a register as a key enabler of past election fraud. A new voter register was included as a key deliverable under the NUG agreement. The Supplier 2 launched voter registration in April 2018, and 8.6 million people have registered to vote (60% of the electorate), including 2.9 million women. The UK provided an initial contribution of £3.6 million to voter registration. These activities are expected to deliver Afghanistan’s first polling-centre based voter list addressing one of the key opportunities for fraud from previous election rounds.
Improved accountability mechanisms: The Supplier 3 is the primary mechanism for managing complaints during and after the electoral cycle. Changes to the electoral law in 2016 also expanded its mandate to take on a more proactive role of identifying, addressing and referring cases of electoral fraud and crimes. The new Supplier 3 commissioners require targeted support to ensure they have the skills and resources to meet their mandate. Civil Society can also play an important role in holding election officials to account. Given the security situation it is unlikely that international observation missions will be able to proactively monitor upcoming elections. Civil society organisations such as Supplier 4 and Supplier 5, have the experience and national networks to undertake domestic observation across the country. Local observers are well placed to use their local knowledge and experience to discern what is going on but they require financial and technical support.
[note] Reporting after the 2014 elections, Maley and Maley identified local observer groups ‘one of the most important accountability mechanism of which use could be made’, ‘Appraising Electoral Fraud’, December 2016
Strengthening public confidence in elections: From the limited available research, there appears to be general public demand for elections. In spite of challenges to date, people continue to see elections as a lever for change and progress in Afghanistan (over 8 million have registered to vote since April). However trust in electoral processes and the parliament are low. Civil Society and the media can play an important role in improving trust ahead of elections (raising awareness and increasing participation) and importantly in the aftermath of elections (keeping the public informed, communicating results, monitoring tensions, and following up on complaints). Civil Society can ensure the voices of marginalised groups are included in election planning (including women and people with disabilities); and hold the government to account on delivering any promised reforms after elections.
[note] Susanne Schmeidl, ‘The contradictions of democracy in Afghanistan: elites, elections and ‘people’s rule’ post-2001’, December 2016; and Anna Larson, ‘Elections and Security in Afghanistan’, May 2018
Longer term electoral and political reform: Challenges in holding elections since 2004, and political debate over the last year in the run up to this year’s elections, demonstrate the urgent need to revisit the form of Afghanistan’s political and electoral systems. Many key decisions regarding these systems were made based on short-term objectives of stabilising the country after 2001. For instance, participants of the 2001 Loya Jirga agreed on a on a single non-transferable voting system, which limits the role of political parties (it does not require candidates to be members of parties). Almost all parties agree that the current system requires reform, but the political stakes today are too high for a national conversation on these issues ahead of elections. Opposition groups frequently raise this and other issues, such as constituency boundaries, population sizes, and the role of political parties. It is unclear whether these represent genuine concerns or political grandstanding but such debates have delayed election preparations.
[note] Nematulla Bizhan, ‘Building legitimacy and state capacity in protracted fragility: The case of Afghanistan’, Commission on State Fragility Growth and Development, 2018
[note] William Byrd, ‘Understanding Afghanistan’s 2014 Presidential Election’, USIP Special Report, April 2015; Andrew Reynolds and John Carey, ‘Fixing Afghanistan’s Electoral System: arguments and options for reform’, AREU, July 2012
Afghanistan is also expected to hold the country’s first round of District elections in 2018. There is currently no law or operational plan in place laying out the roles, responsibilities and financing of this new layer of governance. If District Councils come into being, they will require support. This feeds into a broader debate in Afghanistan on sub-national governance and decentralisation. District Council elections will also enable the government to convene a Constitutional Loya Jirga which could revisit the country’s constitution.
Relationship with the peace process: Upcoming elections pose both a threat and opportunity to on-going efforts at bringing peace to Afghanistan. They are a target for spoilers with the aim of directly undermining government legitimacy. Armed groups have already attacked voter registration sites and continue to issue further threats. But analysts also see possibilities for agreed pauses or de-escalating violence in certain areas if the government follows through on commitments to improve candidate vetting, electoral monitoring and fraud prevention. This is particularly important following the recent ceasefire. Increasing participation in elections (including women) can also galvanise involvement in other political processes including any future peace process. Finally, longer-term government commitment and actions to political reform could provide opportunities for future engagement of the Taliban as a legitimate political actor.
[note] Anna Larson and Alexander Ramsbotham, ‘incremental Peace in Afghanistan’, ACCORD Publication, Conciliation Resources, June 2018

Why should the UK address this need?
The UK remains committed to supporting the long term development of democratic institutions in Afghanistan in line with the NSC strategy. Over the last 16 years, Afghanistan has experienced notable successes; however huge challenges remain with the running of elections. With a long track record in investing in electoral support, the UK is in a strong position to learn from these past experiences and tailor our investment to:
- Promote incremental improvements to the election process to reduce fraud and deliver credible and legitimate elections in 2018/2019.
- Support the government of Afghanistan through this Afghan-led process to avoid a crisis and reversal of successes to date.
- Contribute to the longer term development of Afghanistan’s democratic institutions through election system reform.
In line with DFID’s Building Stability Framework, investing in elections is an opportunity to promote ‘political inclusion and legitimate politics by using aid and non-aid resources to influence the distribution of power in society by responding to windows of change’. Elections are critical opportunities for change, and DFID Afghanistan’s joint approach with the FCO enables the combination of approaches and expertise. DFID’s Building Stability Framework sets out five building blocks that drive long-term stability, including ‘Fairer Power Structures that broaden inclusion, accountability and transparency over time, while managing tensions to prevent violence in the short term’. DFID Afghanistan’s Country Strategy recognises the need for long-term investment to help create the foundations for a more stable and prosperous state. Electoral support will contribute to Strategic Objective 1: ‘Peace, Security and Governance’: ‘aligned with good governance and countering direct threats, we aim to achieve results in free and fair elections.’
We recognise that developing fairer power structures in Afghanistan is a long term agenda which requires continued support. Electoral support will complement wider DFID Afghanistan governance and accountability programming, including investment in parliamentary support, civil service reform, and anti-corruption. Political stability during the election process will benefit DFID Afghanistan’s investments across the portfolio of programmes.
[note] ‘Building Stability Framework’, DFID, 2016
Afghanistan is a focus country for the UK’s National Action Plan on Women Peace and Security, updated in 2018. It commits us to increasing women’s role in public decision making processes and peacebuilding. Strengthening women’s participation in elections will help DFID Afghanistan meet this need.
In 2017, DFID and the FCO undertook a joint policy review to assess the risks associated with upcoming elections in Afghanistan and identify the UK’s response. The review concluded that while elections should be Afghan-led, the UK could and should continue to play a key role, with international partners, in mitigating the risks of political instability and supporting the development of Afghanistan’s democratic institutions (see annexe 6). In spite of obvious aversion to international interference in the outcome of elections, there is strong support amongst Afghans for international community engagement ahead of elections, particularly around building the capacity of the Supplier 2 and supporting election observation.
[note] Anna Larson, ‘Elections and Security in Afghanistan’, and findings of UK Government internal policy review (annexe 4)

Lessons from UK past election support
The UK has supported elections in Afghanistan since 2004. In 2009-11, DFID contributed £7m to the Enhancing Legal and Electoral Capacity for Tomorrow (ELECT) project which focussed on strengthening Supplier 2 capability to manage electoral operations competently and transparently. DFID’s Project Completion Report for ELECT, which incorporated findings from an independent evaluation, rated the project as largely having achieved its objectives.
The UK continued its support into the ELECT II programme and contributed £19.9m for the period 2012 – 2015. This provided support to the Supplier 2 and was delivered through sub-contracts to the UN Office for Project Services (UNOPS) and the International Foundation for Electoral Systems. The Project Completion Review concluded that ELECT II fell short of meeting all of its expectations. While support to the Supplier 2, Supplier 3, Supplier 3 and 2014 presidential elections achieved some success, ultimately the elections results and electoral conduct were challenged. The Supplier 2 and Supplier 3 were not developed as institutions as much had been anticipated, reforms were still needed and vital systems and processes such as a comprehensive voter list was not in place.
[note] ‘ELECT II Project Completion Review’, DFID, January 2016
Callen and Long’s research on the 2010 Parliamentary elections recommended that ‘improving the independence of electoral institutions and ensuring that candidates cannot infiltrate them is necessary to fair elections.’ Following investment in the 2014 elections, the UK and international community produced a number of lessons notes. These concluded that the focus on strengthening the Supplier 2 and Supplier 3 ‘was the right one and should be maintained in the next phase’. However these reviews also noted that more could have been done to support the Supplier 2’s capacity at the sub-provincial level, and donors needed to think about alternative mechanisms for providing comprehensive support to civil society and domestic observers.
[note] Callen and Long, ‘Institutional Corruption and Election Fraud’
[note] British Embassy Kabul, ‘Afghanistan Elections 2014: Lessons Learned’, 2015
[note] BEK, ‘Afghanistan Elections 2014’
DFID has considerable experience supporting civil society organisations (CSOs) in Afghanistan, most recently under the Tawanmandi programme which supported 106 Afghan CSOs over six years. An in depth review of the programme has been carried out to understand how to better support CSOs in Afghanistan. The main lessons from the programme included the need for stronger governance, programme management, tighter thematic focus, promoting coalition working between organisations and reducing the scale and speed of grant making.

What are others doing?
The Government of Afghanistan has invited UNAMA to oversee the delivery of the 2018 and 2019 elections, with the lead operational role being fulfilled by UNDP. UNDP has presented a project document outlining the first 15 months of programming under the UN Electoral Support Programme (UNESP). The primary focus is the delivery of technical assistance to the Supplier1s to deliver credible elections. The overall expected result of the UNESP is greater Afghan ownership of the electoral process, as evidenced by a strengthened legal and institutional framework for elections. Proposed outputs include:
- Administration of credible elections is facilitated by the meeting of key Supplier 2 structural and planning milestones.
- Credible electoral dispute resolution (EDR) is provided by the Supplier 3.
- Polling centre specific voter list for the upcoming elections produced by the Supplier 2.
- The Supplier 2 and Supplier 3 provide credible administration of and electoral dispute resolution for the Wolesi Jirga and District Council elections, respectively.
The UK in collaboration with the rest of the international community has assessed that UNAMA/UNDP is the most representational implementer to undertake elections work in Afghanistan. They have previously worked alongside Supplier 2 and Supplier 3 to deliver reasonably fair elections since 2004. They have also built Afghan capacity to run their own elections such that they progressively reduced the need of international advisers from 500 to 57 between the 2005 and 2014 elections. Finally, there are no other clear agencies or organisations with this experience or expertise.
The UN and Government of Afghanistan propose that the UNESP is the international community’s primary programming vehicle for the upcoming elections. The international community in Afghanistan has supported this decision and is already working closely with the UNESP programme team through weekly elections working group meetings and Ambassador level engagement discussions. The UK has already made an initial contribution to UNESP of £3.6 million to support voter registration. The US is expected to be the largest financial contributor to upcoming elections and has already provided UNDP with $15 million to date to support election reforms between 2015 and 2017. Donor pledging amounts are included in annexe 4. No donors are ring-fencing their funds, instead making pooled commitments across all UNESP activities.
In addition, the US and EU are planning bilateral programmes of support for civil society to monitor elections, raise public awareness and increase the participation of women. DFID Afghanistan is working closely with counterparts in both donor agencies to ensure all activities are complementary.

What will the programme deliver to meet the current need?
A comprehensive three year election support programme with the objective of supporting the Government of Afghanistan through the upcoming election period will lay the foundations for longer term reform. The £24 million three year programme will include three complementary components of support:
- Financial, technical and political contribution to upcoming parliamentary and presidential elections to ensure they are as credible as possible and are a stabilising force in Afghanistan’s development.
- Support to Afghan Civil Society organisations to hold the government to account on the delivery of elections, and ensure the participation of all Afghans.
- A mechanism for researching current areas of potential electoral reform and putting in place a longer term programme of support which goes beyond the current election cycle.
The programme will be jointly delivered by a cross-embassy team of staff from DFID and the FCO. Financial investments need to be accompanied by political influence in order to mitigate any risks of instability.
Expected Impact and Outcome:
[note] See draft logframe (annexe 1)
The UK will provide up to £24 million over three years.
[note] This will cover four financial years: 2017/18; 2018/19; 2019/20; 2020/21
The Impact will be:
Political stability in Afghanistan based upon an increasingly mature and accountable democratic system that respects human rights (NSC objective 2.3)
The Outcome will be:
Strengthened and more robust electoral processes in Afghanistan resulting from increased credibility of the 2018 and 2019 Afghan elections; and an inclusive process to reform electoral and political processes and systems.
The programme will deliver the following Outputs:
- Afghanistan’s Supplier 1 and Supplier 2 provide credible administration of and electoral dispute resolution for the Parliamentary and Presidential elections.
- Afghan CSOs have increased capacities to oversee the electoral process and to inform the Afghan public, women in particular, on their rights and duties as voters and potential candidates.
- Support to longer-term reforms to electoral and political processes in Afghanistan (output statement to be developed end of year 1)..
  [note] Outputs will be further refined in agreement with UNDP, EU and CSO partners
The programme will be delivered through 3 components of support:
Component 1: Support 2018/2019 Elections Operations
Supplier 1: UK support will be centred on the strengthening of the existing Election Supplier 1, Supplier 2, and Supplier 3. This continues the UK investment to date in these bodies, and will draw heavily on the lessons learnt from the last election round. This is in line with support provided by the International Community to the Supplier 1s through UNDP in previous election rounds. In addition, we will work with UNDP to identify and target opportunities for structural reforms within both institutions. Activities will include the development and monitoring of strategic and operational plans for both organisations; capacity building of new staff; completion of the new polling-centre based voter registration programme; and improved complaints and dispute mechanisms.
[note] BEK, ‘Afghanistan Elections 2014’
Operational support to 2018 and 2019 elections: Alongside other ESG donors, the UK will make a financial contribution to election operations, including temporary staff, materials and logistics. This will be provided alongside strategic political support from the UK Ambassador to Afghanistan and the cross-Embassy elections team.
[note] US, EU, Germany, Japan, Norway and Denmark
Component 2: Support to Civil Society
Support to election-focused Civil Society: Civil society groups will play a critical role in monitoring upcoming elections; holding the Election Management Bodies to account; and building public confidence in the election process. DFID Afghanistan has been actively engaged in establishing and supporting the Civil Society Election Coordination Group (CECG) of leading election-focused organisations in Afghanistan. The group holds regular meetings between civil society groups and representatives from the Supplier 1s and ensures coordination across programmes and public messaging. In addition, the programme will provide financial grants to CSOs and media organisations working on elections. The focus will be on supporting election observation; improved citizen awareness and participation, including women and people with disabilities; evidence-based analysis on election processes and reforms; and capacity building of CSOs and media organisations.
Component 3: Longer-term Reform
Longer-term electoral and political reform: it is essential to invest in reforms to existing electoral and political processes if we are to see any long-term improvements in running elections in Afghanistan. Though interventions will likely build off the previous reform efforts of the Special Election Reform Committee (SERC), it is impossible to determine which areas of reform to target until Afghanistan has completed the upcoming election cycle. Political stakes are too high ahead of elections to start a national debate on reform, and experiences over the next 12 months will determine which issues are in most urgent need of reform. The programme will include 12 months of research and design, monitoring experiences over both elections and providing research pieces on key issues commissioned by the British Embassy in Kabul. DFID Afghanistan will design a 2 year programme of support for longer term reform during this period. This will be presented in a programme amendment to the business case in 2019 (no change to the total value of the programme is expected).
A politically informed and adaptive approach
DFID will continue to work together with the FCO in a joint team constituting a one HMG approach to supporting elections. DFID electoral support will be tailored to the political context in Afghanistan and messaging will be delivered through diplomatic channels at the most senior level. Security is critical to the successful delivery of elections. The Supplier 2 will be supported by the Ministry of the Interior and Afghan National Defence and Security forces (ANDSF) to develop security assessments. Security actor co-ordination is also supported by NATO, Resolute Support Headquarters.
The Building Stability Framework recommends five key approaches to be adopted in fragile and conflict-affected countries, included in the programme design:
- Put politics first: election operations and reform are highly political in nature. All programme actions will only be made based on on-going political analysis to understand incentives and entry points for reform. UK elections support in Afghanistan is delivered by a cross embassy team of staff, combining UK diplomatic and political resources with development assistance.
- Think and act beyond the state: the programme requires improved understanding of sub-national perceptions of elections, which will be included as part of the research and design under component 3 (electoral reform). It is important to include neighbouring countries in security planning for elections.
- See stability as an overarching strategy: successful elections which do not destabilise Afghanistan will benefit the wider DFID Afghanistan portfolio of programmes. This is a key priority for both DFID and the rest of the Embassy over the next 2 years.
- Be flexible enough to manage risk and return: The programme builds in 12 months of research and design on longer-term reforms to ensure interventions are best suited to political realities in Afghanistan.
- Put the right people in the right places: the SRO and UK Ambassador attend weekly election planning meetings enabling the opportunity to constantly feed into government-led election planning, monitor risks, and build the best networks with government partners and other donors.
The programme has been designed to be flexible and adaptive to changing circumstances. Political analysis and research during the first 12 months will provide the evidence base for decisions on the future direction of the programme in years 2 and 3. This focus on learning and design based on political developments will improve the likelihood of success, sustainability of reforms, and value for money of UK investment.
What are the risks of supporting elections and how will these be mitigated?
DFID Afghanistan recognises the complexity and risks involved in funding election activities in Afghanistan. Given government delays to date, the limited time remaining before parliamentary elections, and on-going political tensions, there is a strong possibility of elections which are not deemed credible by voters. The security situation, including the recent targeting of voter registration sites, will make the delivery of national elections extremely challenging. This could lead to further delays to elections or disenfranchisement of some parts of the country.
Millions have been invested in Afghan electoral processes to date with limited signs of progress and renewed requests for international support in running elections. Our focus on longer term reforms is aimed at breaking this cycle. Nevertheless some improvements have been made since the first election in 2004, and this election cycle must be viewed as part of a longer political and development process rather than one-off event.
Recent experience of elections in Afghanistan warns of the risk they pose of triggering a political crisis if they are disputed: holding elections within the current political and security context risk undermining, rather than strengthening, democratic institutions in Afghanistan. The Government of Afghanistan however is committed to holding elections over the next two years. UK and international community support to the government’s aim and reforms to the electoral process will support the delivery of fairer and more credible elections for Afghanistan, and contribute to minimising the risk of future crisis.
We acknowledge that processes will not be perfect and recognise the high risk of postponed or failed elections. However, in line with the NSC strategy, the UK remains committed to supporting the long-term improvement of democratic institutions in Afghanistan. A stable government is an essential pre-requisite to the sustainability of DFID Afghanistan’s efforts. A joint political and technical approach to supporting elections will go some way in managing wider political risks. DFID has undertaken extensive analysis alongside the FCO and other donors in Kabul, London and Washington DC to inform the design of our programme of support. A full risk analysis, including mitigating actions, is included in the management case.

Compliance with Gender Equality Act
In Afghanistan there is a continued persistence of gender inequality in political representation, organisational leadership within Supplier 1, and political participation. While acknowledging that progress has been made in relation to female participation in the electoral process, it is also necessary to recognise that there is a sustained need for gender-focused initiatives. Thus the program will focus on the following areas: promoting gender equality within the Supplier 1s through increased employment and promotion of women throughout both institutions, mainstreaming gender throughout the electoral registration process, developing gender disaggregated electoral data, and outreach activities promoting women’s participation as voters. Where possible, results will be disaggregated by sex and disability. Funding to external organisations will also be compliant with the Gender Equality Act.

Terrorism and financing
We assess the risk of programme funding being diverted to terrorists or terrorist organisations as low given the largely technical assistance nature of this program. Moreover UNDP monitoring systems and their experience of Afghanistan allows for confidence for financial probity. All election operation funds will be directly managed by UNDP. UNDP’s internal monitoring, complemented by external audits, specifically looks at any deviation of the funding from its intended purposes. As part of the normal due diligence, DFID reviewed a cross section of external evaluations as well as a selected number of internal audits to verify our confidence in their systems and performance to date in this area. Support to civil society and the future reform programme will be preceded by a due diligence assessment.
Appraisal Case

As set out in the strategic case, the programme will be including three complimentary components of support:
1. Support to 18/19 election operations
2. Civil society promotes electoral processes and accountability
3. Longer term reform to electoral and political systems

Options for supporting election operations and civil society
Successful implementation of elections in Afghanistan is critical not only for political reasons but also it underpins economic activities and economic growth in the country. DFID Afghanistan has identified two credible options for delivering the need set out in the strategic case under components 1 and 2. This is assessed against the baseline of doing nothing. The feasible options considered are as follows:
Option 1: Counter-factual: Do nothing
Option 2: Support election operations through the UN Electoral Support Programme (UNESP); support civil society through the EU managed election support programme.
Option 3: Implement both components through another supplier, following a tender process.

Option 1: Do nothing
Under this option the UK would not provide any immediate support to upcoming elections. ELECT II, only partially met its targets as a result of the political crisis that ensued. In light of this experience, DFID and the FCO conducted a joint internal review of Afghanistan election support in 2017 to assess whether or not the UK should continue investment in upcoming elections and identify approaches. The findings of the review concluded that the planning for parliamentary and presidential elections was underway and these were likely to take place. The rest of the international donor community in Afghanistan has expressed their commitment to support this process. In spite of these commitments, the UN’s election support programme has a shortfall for 2018.
Failing to engage in upcoming elections would constrain the UK’s ability to shape the assistance provided to the election management bodies, and plans for the delivery of elections. Overall, it would limit the UK’s ability to encourage credible and peaceful elections with increased participation from all Afghans, including women and other marginalised groups.
Doing nothing restricts UK opportunities to mitigate against the risk of post-election disputes and violence. It would weaken UK influence among donors and importantly with the Government of Afghanistan. Failing to engage also contradicts commitments in the UK National Security Council (NSC) Strategy for Afghanistan, DFID’s Country Strategy and Self-Reliance through Mutual Accountability Framework (SMAF) commitments, the latter agreed target indicators between the Government of Afghanistan and International Community.
Other donors in Afghanistan (US and the EU) have pledged considerable funding to support domestic election observation and voter education through civil society. However no other donor is focusing on longer term support to civil society beyond the current election period. There is a genuine need for supporting civil society to hold the government to account on any future reform agenda and include the voice of all citizens in this process. Withholding UK support to civil society will result in this post-election civil society work not being taken forward.
This option would have the benefit of saving the UK £18.7 million; however the costs to the UK of not continuing to support elections in Afghanistan outlined above are assessed as far outweighing this benefit. For this reason, “doing nothing” is not considered a feasible option.

Option 2: Support election operations through the UN Electoral Support Programme (UNESP); support civil society through the EU’s election support programme.
Under this option, DFID Afghanistan would provide up to £16.5 million to support the UN Electoral Support Programme (UNESP) through a UNDP multi-donor programme fund. UNESP is responsible for delivering parliamentary and presidential elections alongside the Election Management Bodies and government departments. DFID Afghanistan would also provide €2.5 million (£2.2 million) to civil society organisations supporting national elections activities, through the EU’s election support programme.
In advance of the upcoming parliamentary and presidential elections, UNAMA has been tasked by the government of Afghanistan to design and implement a programme of election support. DFID Afghanistan has inputted into the design of the UNESP programme.
DFID Afghanistan has already made an initial contribution of £3.6 million to voter registration activities under the UNESP programme. As a result of this investment, the Supplier 2 has committed to producing Afghanistan’s first polling centre based voter list for parliamentary, district, provincial and presidential elections. Voter registration is underway with 6.7 million Afghans registered as of June 2018.
UK support going forward would not contribute to specific outputs but be committed to the multi-donor fund alongside contributions from six other Election Support Group (ESG) members. Support will contribute to all planning and operational activities associated with the 2018 and 2019 elections, as well as capacity building to staff within the Supplier 2 and Supplier 3.
UNDP has submitted and operational plan and budget to donors covering the cost of district and parliamentary elections between October 2017 and November 2018. The total cost for this period is $124 million, with an estimated $86 million covered by Government contributions and other donor pledges. The UK will contribute to the remaining gap of $38 million (see annexe 4). UNDP are expected to update the UNESP project document to include the cost of provincial and presidential elections in early 2019. Given the potential of delays to elections, fluctuations in other donor commitments, and the expected increase in the overall budget of UNESP, the size of UK funding could vary based on need (see financial case).
Under this option, DFID would also support civil society organisations working on national election activities by co-funding an existing civil society programme. The EU and US have both committed considerable funding to civil society groups working on elections over the course of 2018 and 2019. With only 10-15 such organisations working in Afghanistan, establishing a third major programme of support would flood the market and confuse funding processes for small organisations with limited capacity.
The US ACEP programme is due to end in 2018, and is planning a new programme focused only on domestic observation for 2019. Neither programmes require further funding so are not options.
The EU is currently procuring a three year programme of support to election-focused civil society organisations. The €2.5 million programme is due to start in November 2019, and will facilitate grants to CSOs and the media covering observation, participation of women, and voter education. The EU has requested the UK to match-fund its contribution which will enable to programme to provide more grants, and continue operations beyond the presidential elections supporting civil society during 2020 and 2021. During this period, civil society will play a critical role in starting a national conversation on future electoral and political reform, and holding government to account to deliver on promises of reform made over the election period.

Option 3: Implement the programme through another supplier, following a tender process
Under option 3, DFID Afghanistan would provide electoral operational support through another supplier that would be identified following a tendering process. A 2012 ICAI review of DFID’s global election support programmes through UNDP, recommended that DFID should ‘actively cultivate alternative delivery channels suitable for implementing electoral support. This means seeking out alternative approaches where feasible, in order to complement and compare with UNDP.’
Other organisations with experience in elections exist in Afghanistan. International organisations including IFES and NDI have previously worked on elections. Afghan organisations such as the Supplier 4 have experience in undertaking domestic election observation. DFID Afghanistan will consider directly financing national CSOs instead of contracting Civil Society funding through the European Union.

Assessing the strength of each feasible option
Each of the two options is appraised in the table against the following criteria:
- Time associated with implementing the option
- Experience and capacity of implementing partner supporting elections
- Relationship between implementing partner and Election Management Bodies
- Costs including DFID Afghanistan staff time
- Level of coordination across donors, government and civil society
- UK involvement in election planning process
- Technical quality
Each option is assigned a number for each criterion: 1 (weak) and 5 (very strong).

Success Criteria	Option 2: Fund UNESP and EU		Option 3: Other Election Support
	Comment	Score	Comment	Score
1. Timing	Election Operations: / UNESP activities are already underway, allowing an efficient mechanism to provide immediate UK support to the on-going election planning process. Due to the potential for UNESP to be expanded to cover 2019 presidential elections, this is an opportunity for the UK to invest in both rounds of elections from an early stage. / Civil Society: / The EU programme is due to start in November 2018. The agreement between the UK will be completed before this time and funding available by this time. The programme will not cover parliamentary elections.	4 / 3	Election Operations: / A competitive tender would take months to complete after which it would likely take a couple of months for the programme to get up and running. Parliamentary elections are due to take place in October 2018. There is therefore not enough time to run a competitive tender and support these elections. / Civil Society: / A competitive tender would take months to complete. It is estimated programme activities would start in December 2019.	1 / 3
2. Experience and capacity	Election Operations: / The UN has run all national elections in Afghanistan since 2001 – it is uniquely qualified to support forthcoming elections. UNDP also has a strong international record of delivering elections. The UNESP programme provides additional oversight from UNAMA to strengthen UN delivery. However, the current proposal only includes a limited number of international technical staff. / Civil Society: / The EU has extensive experience of procuring and managing civil society programmes in Afghanistan. Implementing organisations have yet to be identified.	3 / 3	Election Operations: / No other potential suppliers are known to have the equivalent of UNAMA’s experience in delivering elections in Afghanistan, nor capacity to deliver in the current environment. / Civil Society: / A number of international and national organisations are operating in Afghanistan with the capacity to under civil-society focused activities or manage those that do. These will likely be the same organisations supported under the EU programme.	2 / 3
3. Relationship with Suppier 1s	Election Operations: / UNESP provides coordinated support to the Supplier 1s. UNESP staff are already embedded in the Supplier 1s, however the relationship between the team and Supplier 1 has been mixed to date. / Civil Society: n/a	3	Election Operations: / IFES is the only other organisation that provides explicit support to the Supplier 1s. Their relationship with Supplier 1s is believed to be good but is untested with the current commissioners. / Civil society: n/a	3
4. Costs	Election Operations: / Direct programme costs would be up to £16.5 million over two years. / Civil Society: / Direct programme costs would be €2.5 million (£2.2 million) over three years. Co-funding the EU programme will result in considerable cost savings with regards to staff programme management time.	3 / 4	Election Operations: / Theoretically opening up election support to tender could reduce costs and come up with more innovative approaches through competition, improving value for money. However, we know that the market for elections support in Afghanistan is very weak and credible stand-alone alternatives to UNESP unlikely to exist. Tendering would therefore likely be unsuccessful and would take both staff time and resources to complete. / Civil Society: / A standalone UK programme would likely include the same programme costs (£2-2.5 million). However the cost of staff time involved in running a tender, and the direct programme management of CSOs with limited management capacity over three years will be high.	2 / 2
5. Donor, CSO and Government coordination	Election Operations: / UNESP is a proven mechanism for consolidating funds from the international community to ensure coordinated election support. This significantly reduces transaction costs for the Supplier 1s and Government of Afghanistan. UNESP is the Government of Afghanistan’s vehicle of choice to support elections and an agreement has already been signed between UNAMA and the government. However, the Government of Afghanistan is yet to confirm that the UN will lead planning and delivery of the presidential election in 2019. / Civil Society: / Co-funding the EU programmes allows UK support to be delivered in coordination with another key donor.	4 / 4	Election Operations: / An individual UK programme could usefully complement UN election support, but by creating a separate work stream it would be apart from the main emphasis of government and donor support. We would also lose leverage that we have working with other international donors on the wider election support efforts. / Civil Society: / Only 10-15 CSOs work on elections in Afghanistan. Such a small market risks being overburdened by multiple funding streams.	2 / 2
6. UK influence in elections strategy	Election Operations: / DFIDA has input into the design of UNESP programme to ensure it is in line with our own objectives for election support. Supporting UNESP would continue the UK’s strong influence over how elections are delivered and would ensure the UK retains a seat around the table in top policy discussions. / Civil Society: / DFIDA will be able to recommend action to the EU as part of programme design and implementation but the EU may choose to disregard this input. Sharing programme management responsibilities will free up staff time to focus on policy discussions and external debate on the role of CSOs in elections.	4 / 3	Election Operations: / An individual UK programme would be less influential than coordinated support endorsed by the government and provided through the UN. / Civil Society: / DFIDA will have more autonomy over its own programme than one managed by another donor. Its ability to influence will be greater. Though staff time would likely focus on programme management over inputting into policy or external debate.	2 / 4
7. Technical Quality	Election Operations: / ELECT II only partially met results. Risk that UNAMA will implement similar approaches to previous election rounds which have yet to result in credible and fraud-free elections. President Ghani has been critical of UNDP’s approach to date, and experience from the first six months of UNESP have demonstrated gaps in UNDP and UNAMA’s capacity to politically influence the Supplier 1s to deliver. / Civil Society: / DFIDA has assessed the quality of the EU’s initial programme design and found it to be sound. The EU has taken on board recommendations concerning a focus on longer term activities and will include these in an amended version of the programme if DFIDA confirms co-funding.	3 / 3	Election Operations: / Greater competition could lead to suppliers suggesting potentially more innovative approaches. / Civil Society: / It is expected that a separate UK programme would include the same objectives and target the same potential suppliers as the EU programme.	3 / 3
Total Score	44		32

From the above assessment Option 2 is the preferred approach. However this also highlights certain limitations that may need to be addressed either outside the scope of this programme (civil society support will only begin in November 2018 after parliamentary elections), or through mitigation factors (poor relationship between UNDP and the Government of Afghanistan).

Options for supporting longer term electoral reform
Experiences of parliamentary and presidential elections over the coming year will strongly influence the design of component 3 focusing on support to longer term electoral reform. As a result, this component will be split in two phases:
- Research and design phase: September 2018 to August 2019
- Implementation phase: September 2019 to August 2021
DFID Afghanistan has identified three credible options for delivering the research and design phase. This is assessed against the baseline of doing nothing. The options considered are as follows:
[note] An amendment to the business case will be submitted at the end of the design phase laying out complete plans for the implementation phase, including a full appraisal of delivery options.
Option 1: Do nothing
Option 2: Sub-contract the research and design phase to a third party, following a tender process
Option 3: Sub-contract both the research and design and implementation phases to a third party, following a tender process
Option 4: Direct commissioning of research and design by DFID Afghanistan

Option 1: Do nothing
As set out in the Strategic case, there is a strong need for longer term support to complement investments in individual election cycles. Experience from the last few election rounds in Afghanistan show that the critical entry points for change take place in the immediate aftermath of elections, but international support and accountability has previously dropped off at this stage, failing to take advantage of these opportunities. No other international donors are currently planning post-election reform programmes. All are in agreement that these will be necessary but are only planning to start design programme design after presidential elections. By undertaking research and design alongside elections, DFID Afghanistan will be the only donor ready to support reform efforts as soon as the election period ends. For this reason, ‘doing nothing’ is not considered a viable option.
Option 2: Sub-contract the research and design phase to a third party, following a tender process
Under this option, DFID Afghanistan would undertake a competitive tender to identify a third party to directly manage the research and design phase in preparation of DFID Afghanistan’s future support to electoral or political reform. This could include an international research or development organisation with sufficient experience in electoral systems in fragile states, ideally with a strong background in Afghanistan. Early market research suggests such organisations exist. The primary deliverable will be a high quality project document for the implementation phase of support. Based on these recommendations, delivery options for phase 2 will be re-assessed in an amendment to this business case and a second tender process may be necessary to implement phase 2.
Option 3: Sub-contract both the research and design and implementation phases to a third party, following a tender process
Under this option, DFID Afghanistan would identify a third party from the start with the skills to manage both the research and design and implementation phases of this component. Undertaking just one competitive tender process will likely take longer at the start of the programme but save time and costs in the long run.
Option 4: Direct commissioning of research and design by DFID Afghanistan
The UK government has a number of research and advisory resources available to DFID country programmes, including DFID’s Research and Evidence Division and the Stabilisation Unit. Under this option, DFID Afghanistan will commission individual pieces of work from internal HMG and external experts. This will allow for flexible and direct management of research outputs and the design of the future programme of support.

Assessing the strength of each feasible option
Each of the three options is appraised in the table against the following criteria:
- Cost to DFID Afghanistan of using this option
- DFID Afghanistan staff needed to put in place and manage the option
- Technical quality of research and design
- Flexibility of approach to responding to changes in political context and specific needs of the British Embassy in Kabul
Each option is assigned a number for each criterion: 1 (weak) and 5 (very strong).
Success Criteria	1: Contract design only		2: Contract design and implementation		3. Direct DFID A commissioning
	Comment and score		Comment and score		Comment and score
1. Cost	Higher cost because of potential for two procurement rounds (for each phase) and the additional cost of using a contractor.	2	Potential for cost savings as only requires one procurement round. However still higher costs of using a contractor.	3	Potential cost savings of DFID managing directly, including potential use of HMG resources.	4
2. Staff time	Staff time focused on first two months of programme around procurement of implementing partner. Then potential for light touch management.	3	Staff time focused on procurement, but also necessary to invest more time in designing the framework of the three year programme before going out to tender.	3	High burden on DFID A staff time to identify and contract out analysis, and provide strong oversight / direct design of the next phase of support.	2
3. Technical quality	Initial research determines that there are sufficient research institutions or development organisations with the skills to undertake high quality research and design of the implementation phase. But concern that few international organisations have permanent bases in Afghanistan. Also risk that phase 1 implementing partner designs a phase 2 most suited to their skills, limiting further options.	4	Initial research determines that there are sufficient research institutions or development organisation with the skills to undertake quality, research, analysis, design and implementation. Consortiums can be promoted to capture this breadth of support. Concern that few international organisations have bases today in Afghanistan. Difficult to design even the framework of a 3 yr. intervention ahead of elections.	3	DFID A will oversee the delivery of each research piece and the design of the broader programme. The opportunity to directly commission individual pieces and oversee will ensure products are best suited to the needs of the British Embassy elections team.	4
4. Flexibility	Option to change implementing partners following analysis and design allows for flexibility. E.g.: can move from a research lead to development contractor depending on recommendations	3	Agreeing a three year programme of support before parliamentary elections are completed will limit flexibility.	2	Highly flexible approach which enables the British Embassy Kabul elections team to commission analysis as context and needs change over what is believed will be a very politically changeable 12 months.	4
Total Score	12		11		14

From the above assessment Option 3 is the preferred approach.

Theory of Change of the Preferred Option
The theory of change behind the election support programme is founded on the premise that a strengthened electoral system in Afghanistan will promote stability and economic development by providing the government with the necessary legitimacy and accountability. Supporting the delivery of credible elections in 2018 and 2019; promoting active civil society in this sector; and a commitment to electoral and political reform following elections.
The UN-run election support programme (UNESP) recognises that the key development challenge facing elections in Afghanistan is to provide a sufficient degree of capacity, so that the electoral process allows for confidence amongst the electorate, withstands the intense scrutiny and contestation from political actors that has accompanied every Afghan election since 2004 and inspires the broad acceptance of the election results.
Evidence from international best practice highlights the importance of strengthening Supplier 1 as they are the institutional lead for pre-electoral activities including voter registration, administration of elections and assets, voter outreach as well as managing electoral disputes and fraud. This will be undertaken alongside efforts to build public trust in the election process, thereby increasing participation and the overall legitimacy of the process and result.
The programme will be adaptive to potential changes in the political context in Afghanistan over the next 12 months. Learning from this period will inform the design of future electoral and political reforms. All actions are underpinned by constant political analysis, risk monitoring and interventions by the joint DFID-FCO elections team at the British Embassy team in Kabul. See Theory of Change diagram on p.26. This will be developed further during programme implementation to specify assumptions and evidence underlying these in more detail.

What will the Programme fund and deliver?
DFID Afghanistan will make a contribution of up to £16.5 million over 15 months to UNAMA/UNDP to implement the UNESP to support planning and delivery of upcoming parliamentary and presidential elections in Afghanistan. DFID Afghanistan’s contribution will represent an expected 11% of the multi-donor programme fund for this period. UK funding will contribute to all six outputs under the project document: capacity building of the Supplier 2 and Supplier 3; coordination of civil society; voter registration activities; operations of district and parliamentary elections; and operations of provincial and presidential elections. This will provide the UK with opportunity to input into all planning activities, including the mainstreaming of gender and disability issues which we will prioritise in our engagements. The size of the UK contribution may be less than expected, and could be paid over a longer period of time. This flexibility is necessary because of the risk of elections being delayed, and potential changes to other donor pledges. Details on how DFID Afghanistan will manage such flexibility are detailed in the commercial, financial and management cases.
DFID Afghanistan will make a contribution of €2.5 million (£2.2 million) over three years to the EU’s electoral support programme with the aim of co-funding grants to Afghan civil society and media organisations focused on elections. DFID Afghanistan’s contribution will represent 50% of the programme. The programme will build the capacity of an estimated 30 CSOs over three years; finance critical coordination between CSOs, government, the media and Suppier1s; and fund sub-grants focused on undertaking election observation; holding the government to account on delivering credible elections; and increasing citizen awareness and participation in elections and electoral reform. Sub-grants will particularly target improved participation for marginalised groups, including women and people with disabilities; and CSOs from across the country will be encouraged to apply. Pending agreement with the EU, this could include:
- Requiring all grantees to disaggregate data based on sex and disability, using the Washington Group Questions for the latter;
- Having specific windows on priority thematic areas such as gender, displacement and disability;
- Requiring all grantees to set out a formal strategy for integrating gender equality and disability into their investments;
- Encouraging partnerships or the involvement of marginalised groups in the design of bids and using this as criterion for evaluating the strength of bids.
DFID Afghanistan will invest £5.3 million over three years in designing and implementing an adaptive programme of support to Afghanistan’s future electoral and political reform efforts. This will include one year of research, analysis and design over the coming election cycle to inform interventions expected to begin in September 2019. Initial research will analyse the needs of marginalised groups, with a particular focus on understanding intersectionality and build on previous reports produced by Tawanmandi partners analysing disability inclusion in elections. Key outputs over the first year will include a retrospective analysis of electoral support and debates to date in Afghanistan; comparative reviews of electoral systems in fragile states; reactive analysis to key electoral and constitutional issues as they are debated and tested during the upcoming elections; and the design of a two year programme of support (September 2019 to August 2021).

Pillar 1: Support to 18/19 Election Operations
Pillar 2: Civil Society promotes electoral processes
Pillar 3: Longer-term reform to electoral and political systems
- Improved capacity of Supplier1s
- Polling Centre Based Voter List in place
- Operational plans, materials and staff in place
- Dispute and complaints mechanisms in place and upheld
- Evidence based analysis on electoral processes and performance
- Election observation
- Increased citizen awareness and participation in elections, incl. women
- Improved capacity of CSOs and Media
- Learning and Design of future support
- Government has capacity to deliver reform
- Government held to account to deliver on reform
- Citizen’s voices included in future reform
Increased credibility of 2018 and 2019 elections
Inclusive process to inform reform of the electoral system
Strengthened and robust electoral process in Afghanistan
Political stability in Afghanistan based upon an increasingly mature and accountable democratic system that respects human rights
Delivery Assumptions:
- Voter list sufficiently comprehensive to be useful
- Sufficient political will for elections to take place (Supplier1s, Government, Palace)
- Security Situation permits elections
- Enough public credibility and interest to participate remains
- Public support for female participation
- International donors and partners continue to work to common causes and apply agreed principles.
Other Contributions:
UK Government cross embassy political engagement
Election support from other donors and GoA, coordinated through the UN-led Election Support Group
Other UK DFID and CSSF funded programmes in Afghanistan, notably to the security sector

What are the costs and benefits of the proposed approach?
Costs (as of June 2018) are captured in the table below:
Activities		Donor Currency	GBP
Component 1: Support to 18/19 election operations	Total Election Cost	$314million	£242 million
	Government Contributions	$60 million	£46 million
	Other Donor Contributions	$129 million	£99 million
	DFID Contribution	£16.5 million	£16.5 million
Component 2: Support to civil society	Total Programme Cost	€5 million	£4.4 million
	EU Contribution	€2.5 million	£2.2 million
	DFID Contribution	£2.2 million	£2.2 million
Component 3: Longer term reform to electoral and political systems	DFID Cost	£5.3 million	£5.3 million

Total election costs include both Parliamentary and Presidential elections. The figures under component 1 for total cost, government and other donor contribution are estimates that may vary. For the purpose of this appraisal, the DFID contribution is the maximum proposed value. This may be lowered over time depending on the scale of other donors support to elections and the final budget.
Transparent, fair and free elections are critical elements of democratic systems in countries; however estimating the direct benefits of elections is difficult. Benefits tend to be long-term and very difficult to quantify.
We know from previous elections in Afghanistan, that they can have a de-stabilising and subsequent adverse effect on economic growth. Whether or not results are accepted by parties can determine consumer and investor confidence. Following the political crisis after the 2014 elections, economic growth fell from 9.4% (in the period 2003-2012) to 2.1% (2013-2016). This also timed with the withdrawal of international troops and decline in aid, but it is widely assumed that political uncertainty played an equally important role in this downturn.
In light of the relationship between elections and economic growth, efforts to improve the transparency of elections could have a nil or positive effect on economic growth (supporting the continuation of business as usual or an increase in economic activities). Interventions planned under the programme, including capacity building of the Supplier1s and civil society, are aimed at increasing the effectiveness of elections, reducing the risk of economic uncertainty and potentially contributing to longer-term economic benefits. Economists such as Collier and Hoeffler, argue that efforts to improve the transparency of elections can improve accountability between citizen and state.
[note] Paul Collier and Anke Hoeffler, ‘Do Elections Matter for Economic Performance?’, Centre for the Study of African Economies, August 2012
But no evidence exists of a direct link between elections, or election-focused interventions, with economic growth.
There is more evidence on the link between democratic engagement and growth. Rodrik argues that participatory democracy yields more predictable long-run growth rates, better stability in the short-run and the ability to better handle adverse shocks. Interventions planned under components 2 and 3, supporting civil society and including citizens’ voices in future reform efforts support this aim.
[note] Dani Rodrik ‘Democracies Pay Higher Wages’, The Quarterly Journal of Economics, Volume 114, Issue 3, August 1999
Given limited empirical evidence related to elections, we should prioritise considering the qualitative and political arguments for support included in the preceding pages. However it is possible to tentatively assess potential benefits of the proposed programme aimed at supporting stability on three growth scenarios:
Scenarios	Do Nothing	Intervention
1. Probability of positive effect on growth (5% growth rate) [2009 election]	10%	30%
2. Probability of negative effect on growth (1% growth rate) [2014 election]	80%	50%
3. Probability of no effect on growth (3% growth rate) [World Bank projection]	10%	20%

Expected costs of election disturbances / growth downturn under scenario 2 (discounted at 20%)	-$252 million	-$54 million
Expected value of cost avoided from possible election disturbances (discounted at 20%)		Scenario 1: $108m / Scenario 2: $0m

Based on the assumption that elections will go ahead in 2018 and 2019, we assess the probability of a negative effect on growth at 80%, without support from international partners. We assume that the proposed intervention will lower the risk of this occurrence by 30%, though an economic downturn remains the most likely scenario. The estimated cost of such a downturn would however be decreased from $252 million to $54 million. If the elections result in scenario 3 (no growth), there will be no cost. Whilst if they succeed in leading to scenario 1 (positive growth), there could be a benefit of $108 million. However, it is emphasised that this cost benefit analysis is for illustrative purposes only and serves as supporting analysis. Qualitative and political arguments for the intervention should be given more weight.

What measures can be used to assess Value for Money for the intervention?
The project completion review of the last phase of support to Afghan elections concluded that comparing the average per voter cost between elections is complex, and so comparisons between the per-voter costs of the elections in 2009 and 2014 are difficult to make. UNDP did not break down its budget into categories (such as salaries, infrastructure, operations, etc). In the absence of this information, it is not possible to analyse cost-effectiveness or comment on whether ELECT II represents good economy. But it is believed that the election in Afghanistan is expensive compared to other countries and therefore cost per voter is high. One aim of the programme is to help the government of Afghanistan improve longer term electoral systems which are more cost-effective, requiring a smaller share of international funding for future individual election cycles.
The value for money of the programme will be assessed using DFID’s four ‘E’s model which evaluates economy, efficiency, effectiveness and equity.
Economy: Economy ensures that we are buying inputs of the appropriate quality and at the right price. The above analysis demonstrates that UNESP is the sole mechanism available to provide coordinated multi-donor financial support to election operations. The UN has a good track record globally at delivering elections and a reasonable record in Afghanistan. DFID Afghanistan has undertaking a Due Diligence Assessment (DDA) of UNDP. This provides additional reassurance of UNDP’s capacity and capability to effectively use DFID funding. Any additional controls or safeguards identified will be mitigated and managed to ensure our funds are properly accounted for. DFID will monitor the recommendations from the due diligence quarterly.
The UN administration fee is 8% as agreed in DFID’s Global Framework agreement and is relatively low when benchmarked against other DFID Afghanistan programmes. This will be monitored throughout the programme life. Staff costs constitute a large proportion of the work the UK will support. We have benchmarked these against other programmes in Afghanistan to ensure they are reasonable. Procurement of equipment will be undertaken using UNDPs procurement policy which adheres to international best practice.
Under component 2, the EU administration fee is currently 10%. DFID Afghanistan has asked for this to be waived. If this is not possible, we shall negotiate a potential reduction. This is still the lower end of market rates (8-18% for NGO/private sector management fees).
The unit costs for staff, consultants and procurements will be monitored through regular financial reporting. During the life of the programme, key costs drivers will be monitored regularly for each component (including ratio per component):
1. Election Operations: management costs, UN technical assistance, temporary election staff
2. Support to Civil Society: management costs (including the EU, lead INGO and CSOs); CSO training costs
3. Electoral Reform: to be determined upon programme design
Efficiency: Efficiency looks at how well inputs are converted to outputs. DFID proposes to initially invest up to £16.5 million in UNESP which represents 11% of the total UNESP budget covering parliamentary and presidential elections.
UNESP programme design takes into account all of the recommendations from ELECT II’s Project Completion Report in order to improve efficiency. These include: a) a workplan that complements comprehensive institution building of the Supplier 2 with the actual delivery of elections; b) greater emphasis on robust financial management; c) a phased and flexible programme approach to facilitate tighter management of committed finances; and d) increased flexibility so that problem areas or gaps can be addressed as needed. The DFID Afghanistan programme team will monitor these regularly.
There is also evidence that previous rounds of election support have increased the capacity of Supplier 1s and the ability of national consultants to advise and deliver elections. The ratio of national staff to international staff used in the UNESP programme is higher than ELECT I and ELECT II. This represents an efficiency saving as it means outputs can be delivered at less cost. This will also be be monitored to ensure the efficiency savings are maintained.
The inclusion of DFID’s Project Completion Report’s recommendations and increased use of national staff provides some reassurance that UNESP will be efficient, however DFID will continue to closely monitor results and expenditure. Additionally, we will discuss with UNDP whether it is possible to agree some VfM metrics. Potential indicators include average per capita cost of election staff training sessions and the ratio of local to international consultants.
Effectiveness: Effectiveness considers how well outputs are having the intended effect. Again, important lessons from previous rounds of election support help ensure that activities are more likely to provide longer term sustainable reform measures. For example, UNESP has moved away from election regulations and guidelines to support instead pre-electoral activities such as establishing a voter registration system and list; and capacity building in the Supplier1s. UNAMA will also perform an oversight role to strengthen performance and improve accountability. Each component of the programme will contribute towards the achievement of the intended outcomes determined under the theory of change. The overall programme focus is on the longer term development of Afghanistan’s democratic institutions through election system reform. Support to civil society will focus on capacity building which will be sustained for future elections.
Equity: One objective of the programme is to increase voting participation across the country. Supporting the delivery of credible elections will promote equity within Afghan society by extending political accountability to all citizens, including women and those living in contested areas. Reducing the incidence of fraud will increase the value of individuals’ political voices. Activities in the programme include electoral gender sensitisation training to increase female participation.
A set of meaningful VFM indicators will be agreed within the first six months, which can be reported on accurately and within the required time frame to inform programme management and the future design of component 3 focused on longer-term reforms.
Overall VfM Assessment: The overall analysis presented suggests that UNESP will generate reasonably good VfM for DFID’s investment. However, the investment will not address the higher election costs in Afghanistan or reducing the costs per voter nor will it ensure that the election will not be followed by any crisis. Significant improvements to previous election support have been included in UNESP design to improve the quality and sustainability of results, and budgets will be more tightly controlled. VfM at the lower levels of the results chain are more assured, but given the significant risks faced with holding elections in Afghanistan, the downside risks to achieving the desired outcome and impact are assessed as moderate. We expect that the intervention contribute to marginally more transparent and credible but this may be affected by the factors beyond the control of the intervention. The programme’s focus on longer term reform beyond this immediate election cycle is aimed at improving cost-effectiveness and efficiency in the long run in Afghanistan.

Commercial Case

Component 1: Electoral operation assistance through UNESP
As per the appraisal case, DFID Afghanistan will support electoral operations through the UN’s UNESP programme for which political and supervisory oversight is provided by the UN Assistance Mission in Afghanistan (UNAMA). Project implementation support will be provided by the UNDP Country Office, reporting to the UNAMA Deputy Special Representative for Development/ UN Resident Coordinator/ UNDP Resident Representative through the UNDP Country Director. DFID will provide a contribution of up to £16.5 million to UNESP through a Contribution Agreement which complements DFID’s Global Framework Agreement with UNDP. This commercial case considers the design elements put in place to ensure that VFM is achieved through this choice of supply partner; the capacity and capability of the supply partner to deliver and the mechanisms through which DFID will ensure that outputs are achieved.
Value for Money:
UNDP has demonstrable experience in setting up coordinated donor mechanisms for electoral assistance as well as working with Afghanistan’s Election Management Bodies. Previous projects included ELECT and ELECT II (see Enhancing Legal and Electoral Capacity for Tomorrow (ELECT) from 2006-2011 (ELECT I) and 2012-2015 (ELECT II) as well as the current ‘Support to Afghanistan Electoral Processes’ (Project 205059). The project closure review for ELECT II concluded that: ‘Overall, UNDP has delivered the ELECT II project within budget. Given that ELECT II is not over-spending, and has good financial management procedures it is judged as acceptably efficient in its use of resources.’
This is reinforced by DFID’s multilateral aid effectiveness review published in December 2016, which marks the UNDP “GOOD” i.e. adequate level of compliance in matching with UK development objectives and its organisational strength. In addition, UNDP has been marked as one of the most transparent development organisations in the world according to the Aid Transparency Index produced by the campaign for aid transparency ‘Publish What You Fund’ (published June 2018).
The centrally agreed Indirect Cost Recovery rate will be 8% and DFID Afghanistan will go through the presented budget to negotiate any direct delivery costs that are not in line with the market and context.
UNDP Afghanistan is ultimately responsible for the delivery of UNESP and ensuring value for money is delivered. UNDP is supported in the programme governance by the Project Board which includes the ‘Senior Suppliers’ of which the donors including the UK are members. The Executive also monitors project progress to embed value for money principles. UNDP Afghanistan adheres to the M&E guidelines provided by its HQ and dictated in the Monitoring and Evaluation Booklet (PME). UNDP Afghanistan hires an independent consultancy for project evaluations to ensure impartiality.
Supply Partner Capability:
UNDP Afghanistan is considered one of the largest international non-military missions in the country. It has been involved in various fields including environment, livelihoods, gender, rule of law, governance and health. DFID Afghanistan has over 10 years of experience of working in partnership with UNDP Afghanistan and using the organisation’s services as an implementing partner.
Notwithstanding this track record, UNDP Afghanistan’s overall performance on DFID Afghanistan projects has been varied. The organisation has displayed both strengths and weaknesses which have been picked up by the UNDP Afghanistan Internal Audit report 2015, ICSPA Mid Term Report 2016, Independent Evaluation Report commissioned by the EU 2016 and ICSPA Annual Review Report 2016.
A due diligence assessment was carried out by DFID on the UNDP Afghanistan Country Office in February 2018 to ensure that its systems adhere to all processes, policies and procedures put in place by the UNDP Headquarters. This assessment took into account a variety of evidence including the UNDP ELECT II audit and project completion reports and the UNESP project document. The full report with further detail of track record is available as annexe 7. The report highlights a number of findings for which recommendations have been made in each of the 4 pillars. These will be monitored under the proposed programme.
The acquisition of donor-funded electoral equipment (IT and communications equipment and software) and other expenditures agreed under the UNESP (such as technical assistance) will follow UNDP’s procurement rules and procedures. Supplier 2 personnel will be trained in Afghan public procurement rules, and will also have a basic understanding of procurement concepts and practices in UNDP’s systems.
Funding Mechanisms and commercial agreements:
The commercial vehicle will be a Contribution Agreement between DFID and UNDP, in line with DFID and UNDP’s Global Framework Agreement. This states that an agreed disbursement schedule will be included; that goods and services will be procured in accordance with the UN organisation’s regulations, rules, policies, procedures and directives; that supervision of the project will be carried out by the UN Organisation in accordance with its rules, regulations, policies and procedures. Such procedures as applied at local level have been covered by the due diligence assessment above.
An annual report will be provided in January 2019. We will only issue payments if we are content with activities reported in the report, and if there is a demonstrable need for funds as per the financial report. UNDP are committed to spending funds within the financial years agreed by DFID and are unable to rebalance funds across years without prior permission from DFID Afghanistan. It is not considered that Payment by Results is appropriate for this requirement because of the multi stakeholder and particularly multi-donor nature of the project and the difficulty of attributing specific outputs to individual funding sources.
Financial practices as set out in the UN operating procedures and frameworks will be followed and provisions exists and will be exercised for raising any fraud, bribery or corruption concerns. Procurement practices will follow the UN’s strict procurement policy which is in line with international standards. Once signed, contracts are only paid after work is satisfactorily completed and, in the case of procurement, once the goods are received in the specified place and condition. Payments on large contracts are made in instalments linked to contractual obligations, performance and quality control criteria. In the design of the UNESP, donors have been explicit that they will not endorse or reimburse any procurement procedures that do not meet international standards of practice.
Safeguarding:
UNDP, as the Implementing Partner takes responsibility for ensuring the appropriate safeguards are in place, and are binding on each responsible party, subcontractor and sub-recipient. These safeguards are set out in detail in the UNESP Project Document at Annex 1 and cover safety and security of personnel; misuse of funds, fraud and corruption; rights of audit and investigation; and treatment of gifts, commissions or similar payments. The UNDP project document however does not explicitly cover all the new safeguarding standards which we, as DFID have set out for working with our supply partners. Such organisations must be compliant in all 6 standard areas (on a risk based approach) and this will need to be assessed through an enhanced due diligence exercise.

Component 2: Support to Civil Society through the EU
DFID Afghanistan will provide training and financial assistance to Civil Society Organisations (CSOs) to monitor election planning and delivery, hold the government to account on electoral reforms, and increase the participation of all groups of Afghans. DFID will provide a contribution of £2.2 million (€2.5 million), matching the indicative EU budget for the CSOs grants to the EU through a Transfer Agreement by which The Commission shall manage the Contribution on our behalf. The EU has also set aside an additional €300k for procurement and €400k for Evaluations and Audit. DFID funds will enable a number of priority areas to be addressed as identified by the EU including longer-term electoral reform and will enable a broader range of geographical locations to be covered.
This commercial case considers the design elements to be put in place to ensure that VFM is achieved in working with the CSOs and that these organisations have the capacity and capability to deliver the required outputs and outcomes.
Value for Money:
The financing of external actions is governed by the applicable EU Financial Regulation document, the common rules and procedures for the implementation of the Union’s instruments for financing external action.
The EU Delegation in Afghanistan adheres to the comprehensive procurement/grant award procedures set out in their Practical Guide (PRAG) which is the equivalent of DFID Smart Rules. The PRAG covers contracting procedures applying to all EU external actions funded by the EU and provides users with the comprehensive information necessary to undertake procurement or grant procedures from the very first steps to the award, signature and implementation of contracts. This includes the activities of sub-grantees throughout the supply chain.
DFID, alongside the EU, may be invited to sit on the grantees steering committees as observers. The costs will include the management charges of the NGOs and the resulting activities of the CSOs, including security arrangements. The EU anticipates engaging a third party monitoring organisation with local experts to monitor field activities and advise.
The EU General Conditions Article 4 stipulates an ‘admin cost’ of €250k for contributions up to €5 m, which translates to 10% of proposed DFID contribution in this case. We requested them to explore whether this can be waived and if not, DFID will negotiate should we proceed with this mechanism. There have been past occasions when, in the reverse situation, we have waived our management fees and this will help our negotiating position. Our knowledge of the market indicates that public sector and NGO management fees typically lie in the range 8-15% whilst private sector organisations charge 10-18% of the value of the agreement. 10% is therefore at the lower end of the market rates.
Supply Partner Capability:
DFID Afghanistan has not recently worked directly with the EU as a supply partner but the Multilateral Aid Review in 2016 assessed the European Commission (Development Cooperation Instrument and European Development Fund) as ‘Very Good’ at matching with UK Development Objectives and good in terms of organisational strength.
The project organisation structure, under which up to three NGOs will be selected by the EU to manage the CSOs is explained in the management case. The NGOs will be selected in accordance with the EU procurement guidelines as outlined in the PRAG. The EU has specified a set of eligibility conditions for the participation of CSOs (of which there may be 12-15 managed by each NGO) and set out specific selection and award criteria. Both NGOs and CSOs may be local or international organisations and all are likely to be small or medium sized enterprises (SMEs). The number of CSOs to be managed by each NGO is determined by the EU limit of €60k each.
Funding Mechanisms and commercial agreements:
The commercial vehicle will be a Transfer Agreement between DFID and EU (The Commission) which comprises the Special Conditions particular to this project , together with: Annexe I: Description of the Action, Annexe II: General Conditions and Annexe III, Budget of the Action.
The rights and conditions under which termination is allowed are contained in the General Provisions within the Transfer Agreement.
Payments are made once per year in arrears which means that it is possible to assess progress before making our contribution. EU monies are used in the meantime. It is not considered that Payment by Results is appropriate for this requirement as the supply chain is fragmented, not under our direct control and very susceptible to external conditions and influences. The EU however is specifying a detailed set of expected outputs and activities which is in the process of being ratified by member states.
Safeguarding:
DFID will ensure that due diligence processes are applied, including the latest safeguarding standards at both main grant and sub-grant selection stages.

Component 3: Research and design of future support to electoral reform
A full commercial case for the future programme will be included in the amendment to this business case at the end of Year 1. For the research and design phase during the first 12 months, the SRO will commission pieces of work up to a total of £100,000. These will generate evidence and inform potential electoral reform investment areas. Procurement will be led by an accredited Delegated Procurement Officer in line with procurement rules below the agreed threshold.
## Financial Case

DFID Afghanistan will provide up to £24 million of funding through the upcoming elections period and longer term support for electoral reform. The funding will be split across three components:
1. Election Operations: up to £16.5 million
2. Support to Civil Society: approx. £2.2 million (€2.5 million)
3. Electoral Reform: £5.3 million (£100k in year 1)

Component 1: Electoral operation assistance through UNESP
Funding: DFID will fund UNESP up to £16.5 million through UNDP to facilitate this programme as specified in a Contribution Agreement signed between UNDP and DFID, complementing the DFID/UNDP global framework agreement.
The levels of funding for this programme are available within the DFID Afghanistan resource budget (RDEL). There will be no capital expenditure (CDEL). The overall breakdown, per financial year, is estimated at £6.5m for 2018/19; £10m in 2019/20. Given the external context we acknowledge the figures for 2019/20 may change (but not exceed those quoted above without a formal amendment to the Business case). If elections are delayed, payments may run into 2020/2021.
To date, DFID Afghanistan has provided £3.6m to UNESP to support the upcoming elections. This has been split into two parts with the last payment planned for August 2018. DFID Afghanistan will work with UNESP to ensure all funding has been utilised before making payments associated with this programme. This will ensure compliance with the SMART rules and safeguard taxpayer’s money.
Payments and Reporting: payment in 2018/19 will be made in two tranches of £3 million and £3.5 million. Control measures will be put in place to ensure funds are not transferred in advance of need in line with SMART rules. These measures are likely to include: a clear narrative from UNDP on the need for funds including proof of financial need for registration activities.
Payments will only be authorised once DFID Afghanistan is satisfied UNDP have met the requirements specified in the Contribution Agreement. Reporting will include quarterly monitoring and finance reports describing the activities of the programme and the results achieved and progress against the proposals highlighted in the project document; and detailing levels of expenditure across the multi-donor programme fund. An annual report will be provided in January 2019.
Financial Risk/Fraud: UN institutions and specifically UNDP are long-standing and trusted partners of DFID (see Multilateral Aid Review) with sound controls in place to manage finance and limit opportunities for fraud. UNDP/UNESP will be informed of DFIDs financial/fraud policy and encouraged to attend partner finance/fraud training provided by DFID Afghanistan. DFID Afghanistan partnered with UNDP for every previous round of election support. The PCR for ELECT II (2014 elections) concluded that UNDP’s performance met the expectations of medium fiduciary and partner risk. DFID will continue to work with UNESP programme partners to ensure recommendations from the Due Diligence Assessment is continually updated and action addressed to ensure strengthen throughout the programme.
DFID Afghanistan partnered with UNDP/UNESP to deliver voter registration ahead of elections (programme started in February 2018). DFID Afghanistan also partnered with UNDP to deliver its Social, Demographic and Economic Survey programme (SDES). There have been several financial issues to date where we will seek additional assurances across this programme. The main concern relates to reimbursement of unused funds and the retention of accumulated interest. To mitigate this, we will include specific requirements to address this within the contribution agreement. Other issues include reporting and timing of payments. To safeguard taxpayer’s funds, the lessons learned have been captured and the programme team will engage the DFID Afghanistan finance team and UNDP/UNESP to increase assurance during this programme.

Component 2: Support to Civil Society through the EU
Funding: To deliver the objectives of component 2, DFID will fund £2.2 million (€2.5 million) to the EU across the next three financial years. This is a 50:50 agreement and therefore DFID will be matching the contribution of €2.5 million from the EU. The levels of funding for this project are available in the DFID Afghanistan resource budget (RDEL). It is expected the breakdown of the £2.2 million to be as follows; £1 million in 2019/20; £1 million in 2020/21; and £200,000 in 2021/22. This will be negotiated with the EU as part of the Transfer Agreement.
Payments and Reporting: Expenditure will be captured on a monthly basis in GBP (to mitigate foreign exchange risk), but payments will be made in arrears once DFID Afghanistan is satisfied with the narrative and financial reports provided by the EU. Payment will not be made in advance unless there is a clear justification for doing so. This will be reviewed in year 3 when the €2.5m contribution from the EU has been exhausted.
Financial Risk and Fraud: The EU will be working with two/three partners who will sub-grant to implement the project. To minimise the exposure of DFID funding to fraud, the EU will be informed of DFIDs financial and fraud reporting policies and encouraged to attend partner finance/fraud training provided by DFID Afghanistan. The programme team have been assured of the procurement processes and due diligence assessments of onwards partners made by the EU. DFID will also be involved in the sub-grantee process as an additional assurance measure. The EU has allocated €300k for procurement and €400k for evaluation and audit. DFID will not be contributing towards this but will benefit from the investment.

Component 3: Research and design of future support to electoral reform
Funding: DFID Afghanistan will fund up to £5.3 million towards longer term electoral reform. This will be funded through the DFID Afghanistan resource budget (RDEL). The funding will be delivered across three financial years.The breakdown is expected to be as follow: £100,000 for 2018/19; £2 million in 2019/20; £2 million in 2020/2; and £1.2 million in 2021/22. Full financial arrangements for this component will be included in a future amendment to the Business Case.
Payments and reporting: DFID Afghanistan will directly commission work up to £100k under the research and design phase (year 1). Payments for individual commissions will be made in arrears after completion of the agreed product (report or design of future programme).
Management Case

The SRO for the programme is an A2 Governance Adviser within DFID Afghanistan. An A2L Programme Manager will programme manage the start-up of the programme before handing over to a B1 Programme Manager. Additional support will be in place from our Finance and Commercial, Results Team and Economist. The programme will be overseen by the A2 Team Leader of the Political Inclusion and Accountability Team, and A1 Deputy Head of Office

Component 1: Electoral operation assistance through UNESP
Implementation will be under a UN funding vehicle called a Direct Implementation Modality (DIM). This means UNDP rules and regulations will govern the project implementation including, but not limited to; resource management, procurement, recruitment, audit and evaluation. DIM is justified in this context (as opposed to National Implementation Modality) given existing limited capacity within the Election Management Bodies; lessons learned from the previous UNDP elections support, in particular the support to 2014 elections; and the availability of the Afghanistan government resources to fund some areas of election operations.
Whilst we have conducted a due diligence exercise on UNDP, the project will be reviewed quarterly to consider risk. Regular donor meetings will also allow ongoing assessment on progress in accordance with DFID SMART Rules. DFID, as well as beneficiaries represented by the Supplier 2 and Supplier 3, will be involved in the overall programme governance arrangements. The governance arrangement for the UN funding mechanism is represented at the Project Board as illustrated overleaf.
The UNESP programme will be overseen by the Project Board. This group will be responsible for making by-consensus management decisions for a project when guidance is required including approval of project plans, budgets and revisions. In order to ensure UNDP’s ultimate accountability, the Project Board decisions will be made in accordance to agreed standards that shall ensure best value for money, fairness, integrity, transparency and effective international competition. The project reviews completed by the group will be made at designated decision points during the running of a project (quarterly), or more regularly when tabled by the Project leadership.
Based on the approved Annual Work Plan, the Project Executive may review and approve project workplans when required and will authorise any major deviation from these agreed plans. The Project Board will be the authority that signs off the completion of each plan as well as giving authorisation at the start of the next plan. It will ensure that required resources are committed and will arbitrate on any conflicts within the project and negotiate a solution to any problems between the project and external bodies. In addition, it will approve the appointment and responsibilities of the Project Manager and any delegation of its Project Assurance responsibilities.
Building on the initial start-up contribution provided to UNESP for voter registration, DFID will provide up to £16.5 million through the programme to the multi-donor fund (UNESP). DFID will still remain a permanent member of the project board. DFID’s support and position on the project board will remain beyond elections (until August 2021), or an earlier date if UNESP ends.

Project Organisation Structure
Project Manager
Deputy Chief Electoral Adviser

Electoral Support to IEC

Electoral Support to EEC

Project Operations

Project Board (Governance Mechanism) – Co-Chaired by UNAMA and Supplier 2 or Supplier 3 respectively

Senior Supplier
UNAMA, UNDP and donors (incl. UK)

Executive
UNDP

Senior Beneficiary
Supplier 2, Supplier 3

UNDP CD
Chief Electoral Adviser

Component 2: Support to Civil Society through the EU
Internally within DFID Afghanistan, the management arrangements remain the same with those of the UNESP component. However, this component will be jointly funded with the EU Delegation. The respective donor contributions are anticipated to be approximately £2.2 m each over a 3 year period. DFID will enter into a Transfer Agreement, delegating executive management and decision making to the EU. The latter’s management team will have two operational and two finance officers under the oversight of the EU Delegation’s Head of Cooperation.
The EU will procure two or three main international or established national CSO/NGO grantees, who will sub-grant CSOs up to a limit of circa £55,000 (€60,000). The sub-grants would run for 18-24 months, while main grants would run for 36 months to allow for close out and audit activities. The main grant recipients will be responsible for managing delivery, form steering committees where EU/DFID may be invited once a year as observers. Grant recipients will report on a 6 monthly basis, with the EU producing a 2 page summary to verify correctness, financial reports, progress and any postponed activities.
The EU will produce an annual report. They will also share the Grantees’ six monthly narrative and financial reports with DFID. The latter can comment, but as with other Direct Contribution Agreements (DCAs) we have no executive decision making authority. The EU is planning a mid-term report and an impact evaluation at the end of the project as well as an end of project audit. The mid-term report in particular will be used for performance review and all reports will be used to review policy in this area, to further influence the National Unity Government and encourage collaboration with others.
The EU will have two finance and two operational officers under the EU Delegation’s Head of Cooperation who will manage the project and the supply chain.
Component 3: Research and design of future support to electoral reform
Pieces of work commissioned by the SRO and procured by the DPO will be managed per contract management best practice to ensure adherence to the terms of reference and good VfM. A full management case for the future programme will be included in the amendment to this business case at the end of Year 1.

Monitoring, Evaluation and Learning
Monitoring: UNDP will set up and manage systems and processes to monitor activities alongside the Supplier 2 and Supplier 3. Following recommendations from the ELECT II PCR, the DFID logframe will be aligned with the UNDP logframe. UNDP will report to all donors against logframe indicators on a quarterly basis. UNDP is also responsible for assessing and identifying risks on a quarterly basis that may threaten the achievement of intended results. UNDP will provide the quarterly updated risk log for the programme as an annexe to the quarterly report they share with all donors. DFID will be a member of the UNESP Project Board. The project board will hold regular reviews to assess the performance of the project and review the work plan. The project team will also have regular monthly challenge meetings which will consider risk and will update the delivery plan on a quarterly basis. Regular weekly meetings will also continue between the donor group at working and senior level. Under component 2, the EU anticipates engaging a third party monitoring organisation with local experts to monitor CSO/NGO field activities and report back as well as advise on these. Where possible, results will be disaggregated by sex and disability.
Learning: The Supplier 2, with the support of the UN team, will have the principal technical responsibility for learning and knowledge management of UNESP. The Supplier 2 will support reflective learning during the course of UNESP implementation through a number of different modalities, including: lessons learning exercises, case studies, practice notes and repositories of best practices, and knowledge management and information management systems to continuously document and compile data on UNESP best practice.
Under component 2, the EU plans to undertake a mid-term evaluation of the project to incorporate any learning and aid problem solving. An impact evaluation will also be conducted at the end of the project.
Learning is a key driver for the UK investment under component 3 towards longer-term electoral reform. During the first 12 months research and design phase, the programme will commission multiple research and learning pieces on experiences during Afghan elections and efforts at reform to date. These will be used to design the implementation phase of the programme due to begin in September 2019.

Risk management
The risk level is assessed as High. The table below provides an assessment of the main risks and their mitigation measures. Risks will be managed through the Project Board governance structures. Risk is a standing agenda item at every monthly challenge meeting and is reviewed office wide quarterly. However, updates will be made in line with perceived increase/decrease of risk or when the project board assesses that overall risk has changed.
Risk	Probability	Impact	Mitigation Measures	Residual Risk
Context: deteriorating security impedes delivery of support by UNDP/EU/CSOs	5	5	Security considerations built into operational plans; security management by UNDP, with good business continuity planning contingency in place.	High / Prob: 4 / Imp: 4
Context: deteriorating security impedes monitoring by DFID	5	4	Strong engagement with UNDP/EU allows continued monitoring when movement restricted	Moderate / Prob: 3 / Imp: 3
Context: deteriorating security limits Supplier 1 activities (incl. holding elections)	5	5	Security planning included under the UNESP programme, with regular coordination between the Supplier 2 and RS	High / Prob: 4 / Imp: 5
Context: limited government will over three years to implement reforms	4	4	On-going engagement with government and Supplier 2 (working-level and diplomatic channels).	High / Prob: 4 / Imp: 3
Delivery Risks: election timelines change as a result of political decision making	4	4	On-going engagement with government and Supplier 2 (working-level and diplomatic channels).	High / Prob: 3 / Imp: 4
Delivery Risks: delays as a result of changes to Supplier 1 leadership	4	4	Most activities are limited to operational level and should continue. Engagement with government / Supplier 2.	High / Prob: 3 / Imp: 4
Delivery Risks: Government limits UN role in elections	2	5	UN is committed to improving relationship with the Government	Moderate / Prob: 1 / Imp: 4
Delivery Risks: Supplier 1s are unable to recruit the required staff, particularly women	3	4	Secure buy-in of local leaders and extend deadlines if necessary to recruit	Moderate / Prob: 2 / Imp: 4
Delivery Risks: Limited time to complete voter registration and other election planning activities	5	5	Continued engagement over election timeline and importance of a credible voter registry and strong planning	High / Prob: 4 / Imp: 4
Delivery Risks: Electoral Fraud throughout the process	5	5	Interventions targeting opportunities for fraud are implemented. Donors take a strong line on fraud and crime.	High / Prob: 4 / Imp: 4
Delivery Risks: Political crisis following elections cause delays to further elections or reform efforts	4	5	Constant risk monitoring and contingency planning alongside other Embassies, the Government and Supplier 2	High / Prob: 3 / Imp: 4
Fiduciary Risks: as part of the Programme Fund, DFID funds are misspent	2	4	Regular financial reporting from UNDP/EU and oversight by DFID	Low / Prob: 1 / Imp: 3
Fiduciary Risks: UNDP underspend of resources	4	3	Regular financial reporting and oversight from DFID with agreement to return unspent funds	Moderate / Prob: 3 / Imp: 3
Reputational Risk: DFID perceived as wrongfully interfering in Afghan electoral processes	3	4	Support as member of IC rather than DFID; limit political interference	Moderate / Prob: 2 / Imp: 3
Reputational Risk: DFID scapegoated by Government in the event of delays / fraud	3	4	Support as member of IC rather than DFID; engagement with government	Moderate / Prob: 2 / Imp: 3
Operational Risk: DFID unable to appropriately manage the programme.	1	4	Adequate programme management capacity has been included in the design of the programme.	Low / Prob: 1 / Imp: 3
Operational Risk: EU unable to appropriately manage component 2	1	3	The EU have built in adequate programme management capacity	Low / Prob: 1 / Imp: 2

DFID internal risk
Our risk assessment has also carefully considered DFID Afghanistan internal risks. The key risks highlighted are: i) DFID Afghanistan’s own level of resourcing in managing the workloads within a rotation system ii) Learning curve when staff members move on. Collectively these risks, if realised, would not necessarily affect the headline results but they might weaken oversight and assurance and the degree to which the intervention realises full strategic affect. The Senior Management Team in DFID Afghanistan has discussed these risks and there is significant commitment to mitigating measures including building capacity of SAIC colleagues. Time rotations for UK based staff have been agreed and structured written handovers for new staff will be provided. The SRO is the DFID Afghanistan Governance Adviser, ensuring timely and quality input, monitoring of the Results Framework and links to other programmes and teams.

ANNEXES

1. Draft DFID Afghanistan Election Support Programme Logframe
2. UNESP Project Document, including results framework and costed workplan
3. UNESP Logframe
4. Breakdown of Donor Funding under UNESP
5. EU Action Document for Supporting Elections in Afghanistan
6. NSSIG Paper on internal DFID/FCO review of elections support
7. UNDP Afghanistan Due Diligence Assessment (March 2018)
8. Information note submission to SoS on UK Support to Elections in Afghanistan (May 2018)