Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Support to the Afghanistan Reconstruction Trust Fund
Programme Value: £678m		Review Date: November 2018
Programme Code: 204158	Start Date: Nov 2014	End Date: March 2021

Summary of Programme Performance
Year	2015	2016	2017	2018
Programme Score	B	A	A	A
Risk Rating	Medium	Major	Major	Major

Summary of progress on outputs

Result	Score
Milestones (ARTF Pillar II – Outputs)	A
Operations (ARTF Pillars III and IV – Outputs)	A+
Recurrent Cost Window	A

Summary of progress since last review
1. The Afghanistan Reconstruction Trust Fund (ARTF) is a multi-donor trust fund, established in 2002 and managed by the World Bank (WB) in close collaboration with the Government of the Islamic Republic of Afghanistan (GoIRA). The ARTF helps the government to deliver, and be seen to deliver, increased economic development outcomes and improved basic services for its citizens. See Section A “Introduction and Context” for more detail.
2. This review assesses the overall output performance for this period as an A (met expectations). This is despite a worsening security situation on the ground which has had knock-on effects in programme monitoring and donor staff turnover. Importantly, at the programme level, review and learning mechanisms have remained stable. While a programme of such scope and operating in such a challenging environment will require high levels of monitoring, the ARTF’s new Financing Strategy – entitled Partnership Framework and Financing Programme (PFFP) - has taken into account some of the needs for strengthened monitoring and evaluation, and has taken concrete proposals to address these.
3. It is important to acknowledge that the ARTF portfolio funds a large number of projects and some will perform better than others. What is more important is that the ARTF goes through a continuous process of lesson learning and adapts itself to changes in its operating environment.

Summary of lessons learned since last review
Reporting & Transparency of Information
There has been a step change in the amount and regularity with which information is shared by the World Bank. Monitoring reports, agenda items, and regular consultation with donors when sector teams are in Kabul, have now become commonplace. This goes some way in alleviating some of the concerns raised by external audits on information sharing. In the coming year the World Bank and donors should focus on ensuring that sector level documents (Concept Notes (CN) and Project Appraisal Documents (PADs)) are shared with donor sector leads in a proactive and formalised fashion, allowing for meaningful peer review.

Results, Monitoring, and Evaluation
ARTF Results Scorecard
1. The ARTF Scorecard is now the major tool for tracking progress. The four pillars of the scorecard now allow for a more reasonable assessment of the impact, outcomes, and outputs achieved under the ARTF. Going forward the Scorecard should be further refined to include more realistic annual milestones, thereby facilitating a more structured discussion around progress against expected results. Furthermore, indicators in the scorecard are still presented selectively and it is not possible to identify the causal chains between milestone/output indicators and outcome indicators. Data for the indicators comes from different sources, different time periods and from different methodologies. In some cases, indicators have been revised since the last edition of the scorecard, and not all indicators have baseline or target values making an assessment of progress difficult. Furthermore, in some cases, the target figure is lower than the baseline. This makes it difficult to draw from the scorecard for the annual review (AR). The scorecard is also manually compiled by the WB, is analogue and static, and does not enable more periodic feeding in and review of data into it.
2. At the time of writing the third party monitoring element of the programme is both being scaled-up and in the process of transition. Specifically, there has been: (1) an increase in the number of audits conducted by the Monitoring Agent (MA) - including further physical verification of government workers (over 5,000); and (2) the Supervisory Agent (SA) continues to broaden the scope of their work beyond the verification of physical assets (mainly road infrastructure) to include socio-economic outputs (e.g. beneficiaries of the Citizens’ Charter project); both these processes should allow for better quality data to be available for the ARTF Scorecard. Following discussions from last year, the World Bank has begun sharing all of the MA reports with donors, albeit not always in a consistent or timely manner. SA reports continue to be published on the ARTF website.
3. It is still not clear if the Research and Analysis Programme (RAP) has addressed the paucity of evidence and evaluation products. Of the 17 studies commissioned so far under the RAP since it was established in 2015 it has not been made clear to donors how they contribute to ARTF project design or policy dialogue. Recent changes, including the folding of the RAP into the Advisory Services Implementation Support and Technical Assistance Window (ASIST) should be closely monitored to assess whether this results in a step change in impact.
Reporting
1. The WB does make project level results reporting available on the ARTF website. It also publishes a variety of ARTF documents such as minutes of meetings, explanatory briefs, budget allocation and disbursement data and the reports of the SA. The ARTF website presents an impressive amount of information on the programme. However, the information is updated in a sporadic and sometimes incomplete fashion, and is not always in a user friendly format. Furthermore, much of this data is published without any integration. This needs a considerable investment of time and resources from donors to read through the vast array of documents and contribute their comments or inputs, for example in terms of technical advice on project design, or queries over data reported. There are no online interactive dashboards that make it easier for donors to drill down or up to the level of data they require. The WB does have an online data visualisation tool for ARTF financial disbursement and allocation data but not for project or sector performance data.
2. Donors acknowledge the problems caused by their own staff turnover, which is in turn due to budget constraints and a deteriorating security situation in Afghanistan.
Ownership
1. At the strategic level, GoIRA shows increasing ownership over priorities and donors are lining up their efforts with these. 100% of ARTF programmes are now aligned with GoIRA’s National Priority Programmes (NPPs).
2. GoIRA’s expectations of more operational autonomy in ARTF have continued; whilst there has been progress, for example in Public Financial Management, these expectations are not being met. Furthermore, good progress has been made at the policy and portfolio level to align ARTF priorities with government strategy. However, there is a perception in line ministries that the traditional WB method of establishing Programme Implementation Units (PIUs) within ministries has not resulted in a genuine transfer of capacity to the ministry’s staff and that PIUs have become a parallel entity. The WB have recognised the challenge that multiple PIU’s within ministries pose to government, and are looking to streamline these. However, it is important to be realistic about how much capacity building can occur within project timeframes of a few years, given the baseline capacity of civil servants. A fact that is likely to necessitate slow and incremental capacity building over more radical investments in how the ARTF is implemented.
3. On the donor side, there is recognition of the need to coordinate ARTF and non-ARTF programming and the call to move more assistance from off-budget to on-budget. On the former, donors are keen to align and there is a nascent sector wide approach in the education sector which the UK are supporting Ministry of Finance to pilot. Its establishment and expansion would be a boost to alignment, but must first overcome some donors’ reticence, based on concerns that sector-wide approaches (SwAPs) cannot sufficiently adapt to the Afghan context. On the latter, GoIRA call openly for more on-budget assistance. Whilst some donors state that the impediment to this is concerns over fiduciary risk, corruption, and capacity of GoIRA, it is unclear to what extent the proportion spent on-budget would increase even with these changes.
UK engagement
The UK has played an active role in steering the ARTF through its participation in the governance framework and through other interactions with the WB and donors. It has allocated internal staff time, including technical expertise, to the projects above. However, like other donors, the UK has to balance its resource constraints with the level of engagement it can sustainably commit to.

Summary of recommendations for the next year

1. Operational level coordination: DFIDA should work to ensure the continued engagement of DFIDA advisory staff inputs into the ARTF. In particular the ARTF and DFIDA should explore whether and how DFIDA advisory inputs can inform the design and orientation of ARTF projects to ensure best use of resources across the DFIDA portfolio and the minimisation of duplication of effort.
2. Monitoring & evaluation support: when the new third party monitoring agent begins operation DFIDA should review its mandate and implementation at regular intervals to ensure that both the quality and quantity of monitoring and reports meets expectations and addresses past concerns around the sectoral and geographical scope of results. DFIDA should work closely with the WB team to effectively communicate reporting expectations.
3. Proactive engagement at the operational level: The WB should build on progress reported to date, in terms of operational and technical engagement, and provide opportunities for DFID technical staff to engage with ARTF sectoral and programme leads at the design stage. In particular a protocol agreement should be explored giving DFIDA and other donors opportunity to input into Concept Notes and Project Appraisal Documents in a proportionate manner.
4. ARTF Scorecard: the DFIDA team should support the continued refinement of the Scorecard. In particular the team should support the formalisation of a standard set of indicators to be included in the Scorecard, the setting of realistic annual milestones, and the improvement of data quality (especially supporting the integration of third party monitoring data into the Scorecard). As part of reviewing the indicators chosen for the scorecard, DFIDA should look to engage early with World Bank project teams to ensure that the Project Appraisal Documents (PAD), from which the Scorecard indicators are drawn, set out measures of data that will ultimately accurately reflect outcomes on the ground. The DFIDA ARTF team should also revisit the decision to use the Scorecard as opposed to a logframe, and either reconfirm their position of using the scorecard or revert to a logframe.
5. Capacity building of GoIRA: the WB should continue trying to build up the capacity of the GoIRA as part of the process of service delivery. In particular, it should examine how the scale up of its third party monitoring function could be used to support the capacity of the Afghan audit bodies and evidence based decision-making in line ministries.
6. Risk analysis and planning: given the size of the ARTF in DFIDA’s portfolio, the DFIDA team should use the findings of the Country Development Diagnostic (CDD) exercise to identify ways in which the relative importance of the ARTF could evolve given different scenarios about the operating context’s trajectory.
7. Risk management: the project risk register should be reviewed to make sure that it includes political economy, anti-corruption, and changing conflict dynamics, on a semi-annual basis. The objective of this exercise would be to enhance the ability of the DFIDA team to identify emerging risks at the sector level. Thereby, potentially allowing for the management of any significant risks at the sub-ARTF portfolio level.
8. Supporting the WB cross-cutting team: given DFID’s clear reporting requirements regarding value for money (VfM), results, and monitoring and evaluation, the DFIDA team should offer to provide an introduction to DFID reporting requirements to the WB team. This will ensure that the WB is fully aware of DFID’s specific reporting requirements well in advance of future annual or other reviews.

A. Introduction and Context

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-204158
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-204158/documents

Programme context
1. Afghanistan remains one of the poorest countries in the world and will continue to require substantial financial support for many years. The WB estimates that the gap between government revenues and expenditure will remain above 20% of GDP through to 2025.
2. A severe slow-down in Afghanistan’s economic growth characterized the period between 2012 and 2018. This sharp deceleration can be attributed to the combined effects of the drawdown of international military forces, a sharp fall in associated international spending, reduction of aid, and increasing conflict and political instability. These trends are reflected in the increasing vulnerability of the Afghan population, as widespread deteriorations in welfare are evidenced in the sharp increase in poverty rates to 55 percent in 2017-18 (from 34% in 2007).
3. Violence and conflict continues to affect livelihoods and economic activity. Civilian casualties increased in 2018 and reached unprecedented high levels. At the Brussels Conference on 5 October 2016, donors pledged a further $15.2bn up until 2020, or slightly less than $4bn/year, reflecting a continuation of support at or close to current levels.
4. Afghanistan’s five-year strategic plan, the Afghanistan National Peace and Development Framework (ANPDF) 2017 - 2021, seeks to make the budget the driver for reform, identifying a credible national budget and the ability to improve government performance as the basis for moving from aid dependency to self-reliance.
Outline of the programme
1. As of December 31, 2017, 34 donors have contributed a total of $10.3 billion through the ARTF in support of the Government of Afghanistan’s (GoIRA’s) development objectives. There are currently 18 active donors supporting GoIRA via the ARTF.
2. Historically, the ARTF provided support for the government’s annual operating budget through the Recurrent Cost Window (RCW) and its development budget through the Investment Window (IW). These were complemented by the Research and Analysis Programme (RAP) which carried out research projects to inform IW project design, or wider government policy dialogue. In line with the government’s National Priority Programmes (NPP) as of December 2017, the total disbursements under the ARTF in FY 1396 (2017) stand at $933.65 million, with $457.45m disbursed via the RCW and $476.20m through the IW.
3. The new PFFP (approved in 2018) has seen a number of the External Review of the ARTF proposals incorporated into its functioning. Key elements of these proposals include broadening the use of results based disbursements similar to the incentive based model of the Structural Reforms Scheme in the Incentive Programme of the Recurrent Cost Window to Investment Window operations, with projects setting Disbursement Linked Indicators (DLIs).
  [note] “Taking Charge: Government Ownership in a Complex Context” – available through the ARTF website, www.artf.af
4. UK commitment to the ARTF during 2012-2021 amounts to £678m. This includes a £250m uplift following the approval of a programme extension up to 2021 (previously the UK was committed to funding until 2019). The UK is an active member of the ARTF Strategy Group, which includes representatives of the Ministry of Finance (MoF) as well as other donors and meets roughly on a monthly basis. The Steering Committee is intended to meet quarterly, with Ambassadorial or Heads of Agencies representation. DFID advisory staff also participate in sectoral meetings with their WB and other donor counterparts, and currently co-chair the Gender Working Group.
## B: PERFORMANCE AND CONCLUSIONS

Description of scoring

1. We have used the same methodology as in 2017 to score the programme. This, in turn, is a close approximation to previous scoring methodologies, but full details were not available. In order to aggregate indicators to an overall output score:
  1. Calculate a numeric score for each indicator (progress to date/target);
  2. Remove any ‘outliers’. These may be correct but in a small sample can have a disproportionate effect on the final score. We removed one outlier in Output 1 (M18) which scored above 300% on progress to target;
  3. Exclude any indicators where there is no data from the denominator (i.e. no target);
  4. Calculate a simple numeric average of remaining scores; and,
  5. Convert average score to a grade, using the following ranges.

> 100%	A+
75-100%	A
65-74%	B
< 65%	C

Results

Output 1 – Investment Window Milestones

Total score without outliers (A)	1545
Number of indicators	26
Number of outliers	1
Number of indicators with no target	5
Number of indicators without current data	0
Number of indicators in calculation (B)	20
Average (A/B)	77%
Grade	A

Output 2 – ARTF Operations

Number of indicators	24
Number of outliers	0
Number of indicators with no target	2
Number of indicators without data	0
Number of indicators in calculation (B)	22
Average (A/B)	116%
Grade	A+

Output 3 – Recurrent Cost Window
Number of indicators	7
Number of outliers	0
Number of indicators with no target	0
Number of indicators without data	0
Number of indicators in calculation (B)	7
Average (A/B)	84%
Grade	A

Overall Output Score

This is calculated by the standard DFID methodology on AMP.
Output	Weight (%)	Score
1	35	A (77%)
2	30	A+ (116%)
3	35	A (84%)

Overall score: A (90%)

Alternatives Considered
1. DFID AMP method: The standard way of aggregating outputs to get an overall output. Each letter converted to a fixed number, then aggregated. Produced significantly higher aggregate scores because of the existence of positive outliers.
2. Include outliers: Increased overall score for output 1, from 77% to 88%, remaining at A. Overall score remains at A.
3. Don’t exclude indicators without data from the denominator (i.e. where there is no target, assume progress to target is 0% and include these indicators in the overall calculation): Output one is depressed to a C (62%). Output two remains at A+ with the output score lowered to 107%. Output three remains at A (82%) as all of these indicators have targets. The overall grade awarded would remain at A but be reduced to 83%, Part of our wider recommendations for reporting on the ARTF include strengthening of targets that are set for indicators reported in the World Bank’s ARTF results matric.
Advantages of Method
1. Simplicity – see above, allows comparisons year to year.
2. Follows World Bank reporting structures, allowing DFID access to a depth of data that would not be available if we did not use the ARTF scorecard as the basis for our Annual Review.

Disadvantages of the Method
1. Basic method for calculating indicators is poor: Compares progress to final target rather than where projects should be in a given year. Scores will therefore show low progress to target in the early years of a programme, even if exceeding trajectory to reach target, and will almost inevitably rise each year.
2. No penalty for poor data: Some indicators cannot be scored for valid reasons. However others should be scored but are not because the Bank/Government haven’t provided data or set targets. This should arguably be penalised in the scoring
3. Outliers: Where outliers are not the result of bad data, they represent exceptional outperformance. This shouldn’t be completely discounted
4. Conversion of numbers to grades: The ranges used are based on the ranges used for indicators. At output level this may not be valid. It also doesn’t match the DFID standard ranges for overall output scores, which are less generous.
5. The following caveats about the data used and scoring methodology should be noted: The source of data is the WB’s ARTF Results Scorecard which in turn is based on the ARTF Results Framework. As such the Annual Review assesses a WB managed programme based on data from the WB, not from independent sources. This is because the ARTF is unlike a conventional DFID ‘project’ which has separate contracts for an implementing agency and an independent evaluator. This approach was agreed to in the ARTF Business Case, and allows DFIDA access to a depth of data otherwise unavailable. It is beyond the scope of an Annual Review to verify the data of the ARTF Results Scorecard for each indicator beyond comments on the indicator definitions or highlighting missing or ambiguous data. Note that the World Bank employs third party monitoring to collect and verify a proportion of the data reported in the scorecard. In some cases, this is complemented by individual projects, such as SEHAT, contracting external third party monitors to carry out data collection. See section H (Monitoring and Evaluation) for further information.
6. The ARTF scorecard is a selective presentation of indicators for each sector from the ARTF Results Framework which is updated in the WB’s Implementation Status and Results Reports (ISR) for each project. In the scorecard, the WB presents indicators in two categories: outcomes and milestones. It is not possible from the scorecard alone to trace causality from milestones to outcome. For this the reader has to delve into the individual project level PAD and ISR which has a set of Project Development Objective (PDO) indicators and Intermediate Results indicators.
7. Data for each indicator in the scorecard, which is sourced from the ISRs, may be from different sources, from different time periods and, in some cases, from changed methodologies. The target values for each indicator have also been revised in some cases from the last edition of the scorecard (we have noted where this is the case). It is not possible to comment on how standardised these changes are without a comprehensive data quality assessment exercise.

Annual outcome assessment
1. The ARTF programme level outcome statement, as defined in DFID’s Business Case 2014/15 – 2018/19, is: “GoIRA increasingly capable of managing and delivering essential infrastructure, reforms and basic services, improving access to public services and employment opportunities.”
2. This annual review finds that the ARTF is expected to be on course to achieve this outcome by the end of the programme. It has achieved an overall weighted score of 'A' reflecting that it has met expectations across three programme outputs for this review round.
3. GoIRA has shown improved capacity in managing reforms over the course of the ARTF, and this has been reflected in the triggering of ARTF payments under the Incentive Programme. Recurrent Cost Window disbursements fell between 2016 and 2017, from 469.86 million USD to 457.46 million USD, and this is explained by a combination of a reduction in baseline financing, and a slight reduction in disbursements through the Incentive Programme.
4. The Incentive Programme is comprised of the Operation and Maintenance (O&M) Facility, Revenue Matching Grant, and Structural Benchmark. The revenue matching grant increased substantially between 2016 and 17, reflecting an increase in domestic revenue collection by GoIRA. The overall reduction is comprised of a reduction in the O&M facility component, which nevertheless continues to exceed its target, and a fall in disbursement through the structural benchmarks component.
5. The GoIRA has performed reasonably well against structural reform targets since 2015. The administrator’s report notes that whilst some progress has been made on customs and pension reform this will be insufficient to achieve the benchmarks in 2018, and so funds were not disbursed.
6. It should be noted that this has been achieved despite a deteriorating security situation in Afghanistan. Anti-government forces have increased activity in 2018 and both civilian and Afghan police and armed forces casualty rates have been high this year.
7. Transfer of capacity to line ministries has remained a challenge. ARTF projects are administered by the World Bank through Programme Implementation Units (PIUs). There remains a general perception within GoIRA that PIUs have not facilitated the intended capacity transfer and have instead become parallel entities within ministries. The World Bank is aware of this criticism, and is considering how to address GoIRA concerns and increase capacity in line ministries. However, it is also important to maintain a realistic perspective on how much capacity building can take place given the baseline qualifications of the civil service.

ARTF Financing Strategy
1. The new ARTF financing strategy, the Partnership Framework and Financing Programme, was endorsed by the ARTF Steering Committee in June 2018. Despite the six month delay, both the strategy and the process by which it has been developed have been welcomed by government and donors alike.
2. The new strategy not only secures donor funding until 2020 and agreement on priority sectors in which to spend it, but also introduces a number of key changes to how the ARTF is organised:
  1. ASIST Window
The previous ARTF structure was comprised of three windows: Recurrent Cost Window, Investment Window, and the RAP (Research and Analysis Programme). The new structure maintains the Recurrent Cost and Investment Window, and expands the RAP to become the Advisory Services, Implementation Support and Technical Assistance (ASIST) window, as well as adding the Anti-Corruption and Results Monitoring Action Plan (ACReMAP) window. The strategy recognises that GoIRA has had concerns over the existence of World Bank Project Implementation Units (PIUs) in ministries, and in particular the lack of capacity transfer that has accompanied these. GoIRA and the World Bank are therefore looking to streamline the number of PIU’s in ministries, but recognise that this brings its own challenges. The ASIST window will continue to support research and analysis, but will now also ensure that GoIRA is supported through specialised technical expertise, extending beyond that typically provided by World Bank project teams, and to meet GoIRA demand.
  1. ACReMAP Window
The strategy establishes a new fourth window, the Anti-Corruption and Results Monitoring Action Plan (ACReMAP) window. This window aims to consolidate the management and expand the scope of the existing third party monitoring of the ARTF. In practice, this would mean, for example, a greater number of physical verifications of employees whose salaries are reimbursed under the Recurrent Cost Window, and a greater number of physical site verifications for projects funded under the Investment Window, as well as an increase in the number of projects being monitored.
  1. Expanding the use of results-based financing
In line with GoIRA priorities, the financing strategy strengthens the use of results-based financing, and does so through both the Recurrent Cost window and the Investment Window. On the RCW, benchmarks will be set against both the Afghanistan National Peace and Development Framework (ANPDF) and the Fiscal Performance Improvement Plan (FPIP), thus incentivising reforms linked to both. On the IW, some projects have begun to introduce Disbursement Linked Indicators in order to prioritise reforms. As GoIRA has to fund these prior to receiving the funding, they are primarily focused on policy reforms.
  1. Baseline Funding Fiscal Stability Fund
The ARTF expansion of incentive based financing, in particular under the Recurrent Cost Window, and reduced level of baseline funding, introduces new risks to GoIRA in the form of less predictable funding. This is exacerbated by the volatile environment in which the ARTF is operating. In order to mitigate the risk of substantially reduced support to GoIRA and corresponding impact on Afghanistan’s economy and long-term development, the new strategy introduces a Fiscal Stability Fund (FSF). The FSF is a pool of funding that the government can access in a liquidity crisis caused by external shocks or unexpectedly slow progress against reforms, if certain conditions are met.
  1. Sector Wide Approaches
The strategy recognises the difficulties all stakeholders face in coordinating work across a sector, and notes that programming through the ARTF is typically done at the programme, as opposed to sector, level. The strategy explains the WB intention to support GoIRA in testing sector-wide approaches where appropriate, starting with Agri-business and education. The WB will also look to employ their Multiphase Programmatic Approach (MPA) where possible. This is a sector-wide approach that agrees the financing envelope and objectives for a substantial multi-year programme upfront, but then signs legal agreements for disbursement of funds for each phase subsequent to the former being satisfactorily completed.
Another important innovation of the PFFP is that it formalises the process for scaling up and scaling down ARTF projects based on performance. This should help the WB and the Ministry of Finance (MoF) to achieve better value for money. The DFIDA team should closely monitor whether and how this augmented tool works in practice.

Key findings
1. In agriculture, the outcome indicator for agricultural productivity, in terms of irrigated wheat yield, exceeded its end of project target and is at 2.8 tonnes per hectare. Access to agricultural irrigation services shows progress to a 2020 target of 77%, with 80% of the targeted female population having access to new or improved irrigation and drainage services.
2. In rural development, two outcomes have exceeded their targets – proportion of communities with elected and functioning Supplier 1 and increase in employment (direct or indirect) through project supported Enterprise Groups. Current year estimates by the WB indicate that 96% of communities have functioning SUPPLIER 1s, which is a slight drop from last year’s 98% figure, but remains well above the 80% target, whilst 36% of participating enterprise groups have increased employment by at least 30%, and 59% of the target population obtaining employment through Enterprise Groups are women. The establishment and functioning of SUPPLIER 1s is continuing at a relatively high level despite the transition from the National Solidarity Programme III (NSP III) to the Citizen Charter Afghanistan Project (CCAP). The latter has begun operating as the former has wound down, but CCAP did not necessarily target NSP locations, and so to exceed targets this year shows a quick establishment of SUPPLIER 1s by the CCAP. World Bank indicators also show 66.8 million labour days generated by the implementation of sub-projects under the SUPPLIER 1s.
3. Looking more closely at the Citizens Charter, we see that whilst a large number of SUPPLIER 1s have been established, only 15% of the targeted number are currently able to plan and manage their own development projects, and residents are yet to benefit from sub-projects. This reflects the difficulties that the CCAP project has faced in mobilising resources, which we believe have now been resolved.
4. In infrastructure, 119,392 beneficiaries have new or rehabilitated metered connections to the grid in the target areas under the Afghanistan Power System Development Project. Whilst an increase from last year and representing a 95% progress to the 2017 target of 126,000 that was reported in 2016, the new target of 190,000 reported in 2017 means this figure represents only a 63% progress to target. It is reported that under the NSP an additional 6.2 million individuals benefited from new or rehabilitated metered connections to the grid in the target areas, but no target has been set for this as NSP sub-projects are driven by SUPPLIER 1 demand. 18.8 million people have access to all-season roads within a 500-meter range of their house, an increase from the 13.5 million baseline, but a 12% progress to the 2019 target. In addition, there is no progress report available under the rural development indicator of the proportion of rural population living within 2km of an all-season road.
5. In health, one outcome out of three has substantially exceeded its target. 938,799 births were attended by skilled attendants, exceeding the 566,683 target, and representing a 371% progress to target. PENTA3 coverage among children age 12-23 months in the lowest income quintile also shows strong performance, with 59.6% coverage against a target of 60%. Quality of healthcare, as measured by a balanced scorecard tool, achieved a score of 62 out of 100 against a baseline figure of 55 and a target of 70.
  [note] PENTA3 is the abbreviation used for the third and final dose of the pentavalent vaccine, a combination of five vaccines in one, which protects against diphtheria, tetanus, whooping cough, hepatitis B, and Haemophilus influenza type b (the bacteria that causes meningitis, pneumonia and otitis).
6. In education, two key outcome metrics – enrolment and grade 12 completion rate – have exceeded their targets. In the current year, ARTF has achieved enrolment of 8.9 million students (39% of them girls), and 210,274 students completed grade 12. The percentage of girls completing grade 12 has no target, but has increased to 36% from a baseline of 31%. Average attendance rate has fallen slightly below the baseline of 78% down to 77%, representing a significant decrease from 85% last year.
7. In governance, GoIRA generated Afs 36.25 billion of customs revenue in this year. Whilst this represents a substantial reduction from last year’s Afs 55bn revenue, it represents a 22.5% increase on the 2012 baseline, where the target is a 25 % increase (Afs 36.25 bn). The number of ministries that have completed pay and grading increases, and the increase of the Open Budget Index Score have both exceeded their targets. Progress on percentage of procurement done by line ministries using standalone procurement and ministries that have completed at least two processes in their CBR (Capacity Building for Results plan) remain below target, at 50% and 54% respectively. Stakeholder interviews suggest that this reflects the divergence in capacity across line ministries, which the new financing strategy aims to explicitly address. Three new indicators (Increased development budget execution rate, increased domestic revenue as a percentage of GDP, and effective implementation by budgetary units on the external audit recommendations) have been added, all with targets for 2022 and all baselined in 2017, therefore reporting 0% progress to target currently.

Logframe updates since last review
Instead of a log frame, the ARTF scorecard, which is based on data from the ARTF Results Framework, is used to assess progress. This approach was approved in the Business Case. The scorecard is updated annually by the WB. The latest version used for this review round captures data till December 2017.

## C: DETAILED OUTPUT SCORING

Output Title	Milestones (ARTF Results Scorecard Pillar II)
Output number per LF		1	Output Score	A
Risk:		Major	Impact weighting (%):	35%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Key points

The overall grade for Output 1 (Milestones) is A. A set of output (‘milestone’) indicators were taken from the latest version of the ARTF Results Matrix which was provided by the WB and contains data updated till December 2017. An unweighted average of the progress to target figures for each indicator was calculated to obtain the average output progress score. This score was then converted into a grade according to criteria in Section B, Table 1.
1	Total Milestone Indicators	26
2	Indicators with no current data	0
3	Indicators with no target	5
4	Total Milestone Indicators Counted [1-(2+3)]*	20
5	Average Output Progress Score (unweighted)*	77%
6	Overall Output 1 Grade	A

* Also excludes indicator M18 as outlier
The full set of milestone indicators in the ARTF Results Scorecard are given below in tables for each sector.
Milestone Indicators
[note] Where Baseline and Target values are blank, they reflect the absence of data in the ARTF Results Matrix or where a baseline is marked as zero in the scorecard.

AGRICULTURE
Indicator	Units	Baseline	Target	Current Year Actual	% Progress to target
M1 Area provided with irrigation and drainage services (ha) - IRDP	ha	75,000	215,000	170,026	68%
M1 Area provided with drainage service (ha) - OFWMP	ha	-	59,000	42000	71%
M2 New Orchards (including vineyards) established with at least 70 % survival rate (ha)	ha	-	19,000	22,488	118%
M3 Adoption rate of improved horticulture technology packages (%)	%	-	75	54	72%

The milestone indicator M1 reports separately against the Irrigation Restoration and Development Project (IRDP) and the On Farm Water Management Project (OFWMP) and is hence reported twice in the table above.

RURAL DEVELOPMENT
Indicator	Units	Baseline	Target	Current Year Actual	% Progress to target
M4 Number of sub-project proposals financed	number	-	-	88,586.00	No target
M5 Total amount of block grants disbursed directly to SUPPLIER 1s ($)	USD	-	-	1 560 000 000	No target
M6 Female SUPPLIER 1 members (%)	%	38.00	33.33	32.00	96%
M7 Total amount of savings collected by Savings Groups and village EGs	AFN (millions)	-	-	346.8	No target
M8 Beneficiaries participating in Saving Groups and Enterprise Groups	Number	-	68500	69427	101%
M8 Beneficiaries participating in Saving Groups and Enterprise Groups (% female)	%	-	50	56	112%
M9 Total rural roads rehabilitated and maintained(km) (NSP)	km	-	N/A	12,364	No target
M9 Total rural roads rehabilitated and maintained(km) (ARAP)	km	-	2,550	2,240	89%

1. The WB has not defined targets for several indicators above as it states that they are demand driven and dependent on prioritisation of sub-projects by SUPPLIER 1s.
2. Indicators M4 and M5 fall into this category. Both indicators have remained at the same value as reported in the 2016 ARTF Results Matrix.
3. The progress to target figure for indicator M6, which reflects the proportion of women on Supplier 1, has been calculated ignoring the baseline, which is consistent with the approach used for Output 2, and reflects that the current percentage is close to the target. Note that the target of a third of SUPPLIER 1 members being female is lower than the baseline of 38% measured in 2010. This reflects the challenges in maintaining a high average proportion of women in SUPPLIER 1s as the number of SUPPLIER 1s expands, although this explanation could be noted in the scorecard itself. The figure remains at 32%, as was recorded in the 2016 ARTF Results Framework.
4. The milestone indicator M9 reports separately against the National Solidarity Programme III (NSP) and the Afghanistan Rural Access Project (ARAP) and is hence reported twice in the table above. Concerns cited in the 2016 DFID Annual Review regarding the NSP figure have now been resolved – there had been an earlier error in World Bank reporting of a single sub-project, which was started in metres but captured in km. This has now been resolved.
CITIZENS CHARTER
Indicator	Units	Baseline	Target	Current Year Actual	% Progress to target
M10 Number of communities meeting all minimum service standards	number	-	9,600	0	0%
M11 Percentage of grievances received that are resolved	number	-	70	0	0%
M12 Percentage of SUPPLIER 1 members in rural areas who are women	%	-	35	47	134%

The Citizens Charter was established in 2016, and showed initial success in establishing SUPPLIER 1s, and in ensuring these were gender-balanced; hence the high progress to target score for indicator M12. However, the programme hit a number of political blocks following this initial phase, and so struggled to deliver results beyond the setting up of the SUPPLIER 1s. This explains the 0% progress to target scores for indicators M10 and M11. We understand that these blocks have now been overcome, and recommend taking particular note of indicators M10 and M11 in next year’s ARTF Score Card and DFID Annual Review.
INFRASTRUCTURE
Indicator	Units	Baseline	Target	Current Year Actual	% Progress to target
M13 Distribution lines constructed or rehabilitated under the project	km	-	626	425	68%

HEALTH
Indicator	Units	Baseline	Target	Current Year Actual	% Progress to target
M14 Number of health consultations per person per year	number	1.60	2.00	1.90	75%
M15 Proportion of health facilities staffed with at least one female health worker	%	74.00	86.00	85	92%
M16 proportion of children under five years with severe acute malnutrition who are treated	%	24	55	77	171%

1. The progress to target for indicator M14 was published as 95% in the 2017 annual review. The Current Year Actual has remained at 1.9 health consultations per person per year, as it was last year; however we have adjusted the methodology to take into account the baseline figure provided.
2. Indicator M15 was exceeded last year, with 87% of health facilities staffed with at least one female health worker. This year’s progress to target of 93% reflects the proximity of the current year actual to the target, but it should be noted that this is a small decline from last year.

EDUCATION
Indicator	Units	Baseline	Target	Current Year Actual	% Progress to target
M17 Number of rehabilitated or built additional class rooms at primary level	number	-	No target	8,541.00	N/A
M18 Number of qualified teachers as a result of EQUIP financing	number	37,000	30,000	115,000	311%

1. There is no target listed for indicator M17, number of rehabilitated or built additional classrooms at primary level, in the 2017 ARTF results matrix. The 2016 target in the previous ARTF Results Matrix for the same indicator is 9,148, and using this as a benchmark would put the progress to target for this indicator at 93%.
2. The baseline for indicator M18 is higher than the target, and so the progress to target for this figure has been calculated as a percentage of the baseline as opposed to the target. The progress to target figure for indicator M18 is unusually high because of the large deviation between the baseline and the current year actual figure of teachers. As such a large percentage will skew the overall grading calculations; it has been dropped as an outlier while calculating the overall output score.
3. The total number of beneficiaries, disaggregated by sex, was included as an indicator in last year’s annual review. This data is not included in this year’s ARTF results matrix, and as such we are unable to include it in this year’s annual review. Overall recommendations for the ARTF scorecard can be found in section A, and include consistency of metrics where possible.

GOVERNANCE
Indicator	Units	Baseline	Target	Current Year Actual	% Progress to target
M19 Number of internal/external audits verified as done to international auditing standards	number	4	34	34	100%
M20 Number of Procurement Units of line ministries and provincial offices restructured for stand-alone procurement	number	7	61	52	83%
M21 Improvement in core institutional capacity, represented by a reduction in the number of long-term technical assistants	number	499	250	499	50%
M22 Web-based AFMIS extended to embassies and selected districts, municipalities, and State Owned Enterprises (SOEs). / Rolling out e-Government Procurement in the pilot phase in 3 or more departments.	number	-	300	0	0%
M23 Civil service positions recruited by CBR	number		1500	680	45%

1. The current year actual for indicator M19 at 34 audits is the same figure as last year, and no additional internal/external audits verified as done to international auditing standards have been performed in the past year. Progress to target remains at 100% as the target has not changed, and this is in line with World Bank and donor expectations.
2. Indicators M22 and M23 are new to this scorecard, having not previously been captured.

Observations from annual review monitoring visits
1. The consistency of data available in the ARTF scorecard year on year is variable, for example indicators may change slightly from year to year, or target information may not be available. Further to this, the targets on the scorecard are not all 2017 targets, but vary between indicators as they are the targets for the end of projects, which may be a few years from now. This has two consequences: firstly, progress to target scores are likely to improve year on year; and secondly, projects in their early phases, whose targets are for years ahead, will score poorly even if on or exceeding their expected progress for this phase in the project.
2. On the consistency of data, whilst the security situation and the restrictions this entails continues to worsen, the ARTF Steering Committee recently endorsed the recommendation of an expansion to the third party monitoring programme, which is due to go to tender shortly. We anticipate this will improve the consistency and quality of the data provided in the ARTF results matrix. Further information is available in section H (monitoring and evaluation). On the second, our recommendations include working with the World Bank to strengthen reporting through the scorecard and its results matrix. Further detail is available in section A.

Output Title	Operations (ARTF Results Scorecard Pillars III, IV)
Output number per LF		2	Output Score	A+
Risk:		Major	Impact weighting (%):	30%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Key points

The overall grade for Output 2 (Operations) is A+. A set of output (‘milestone’) indicators were taken from the latest version of the ARTF Results Matrix which was provided by the WB and contains data updated till December 2017. An unweighted average of the progress to target figures for each indicator was calculated to obtain the average output progress score. This score was then converted into a grade according to criteria in Section B, Table 1.
1	Total Indicators	24
2	Indicators with no current data	0
3	Indicators with no target	2
4	Total Indicators Counted [1-(2+3)]	22
5	Average Output Progress Score (unweighted)	116%
6	Overall Output 2 Grade	A+

The full set of indicators from Pillars III and IV in the ARTF Results Scorecard are given below.
Indicators

Indicator	Units	Baseline	Target	2017 Actual	% Progress to target
Pillar III: ARTF Operational Effectiveness/Quality of Portfolio
Number of months between project effectiveness to first disbursement	Months	2	2	2	100%
Active operations rated moderately satisfactory or higher on implementation (%)	%	78.00	75.00	86.00	110%
Disbursed amount in an Afghan Fiscal Year disaggregated for the Investment Window ($mil)	$ m	15.59	250	476.2	190%
Disbursed amount in an Afghan Fiscal Year disaggregated for the Recurrent Cost Window ($mil)	$ m	214	400	310.2	78%
Fiscal Year disbursement of active grants divided by total undisbursed funds in active grants by the beginning of the fiscal year (excluding Recurrent Cost Window) (%)	%	55	24	43	179%
ARTF projects that include gender-specific objectives data with targets (%)	%	32	40	40	100%
ARTF projects that include gender-specific outcome data with targets (%)	%	32	40	68	170%
ARTF projects that include gender-specific output data with targets (%)	%	32	60	55	92%
Percentage of Portfolio fully collecting required gender-disaggregated data	%	38	80	60	75%
Percentage of portfolio projects with Gender Focal Point staff in client project teams	%	71	60	72	120%
Percentage of portfolio projects which include technical assistance on gender issues and gender supervision in implementation support missions	%	63	60	82	137%
Percentage of portfolio projects which have produced gender-related knowledge in completed knowledge products	%	38	50	50	100%
Percentage of projects that incorporate Beneficiary Feedback	%	94	100	95	95%
Facetime with the client counted as total number of days spent on Afghanistan including resident international and national staff and visiting missions (days)	Days	12,000	16,500	27,659	168%
Pillar IV: ARTF Trust Fund Effectiveness
Share of planned financing under the ARTF Incentive Programme that has been earned by the government by the end of the fiscal year (%)	%	100	45	26	58%
Number of implementation support missions with joint partner participation (%)	%	50	66	69	105%
ARTF development aid aligned with current NPPs at the programmatic level (%)	%	-	80	100	125%
Recurrent sources as share of government civilian operating budget (%)	%	48.00	No target set	26	-
Development sources as share of government civilian development budget (%)	%	20.00	No target set	31	-
Increase in the execution rate of the development budget	%	-	59	68	115%
Audits received on time (%)	%	-	75	100	133%
Total ARTF pledges deposited by donors by end of fiscal year (%)	%	86	100	92	92%
Unallocated cash balance at the end of the fiscal year as a proportion of the pipeline for the coming year (%)	%	27	30	33	110%
ARTF contributions preferenced (%)	%	30	50	43	114%

1. For each of the above indicators, the baseline figure has been disregarded in calculating progress to target, as current year actuals represent one year only rather than a cumulative figure. This is in line with the approach taken for indicator M6 in outcome 1. In five cases the target set is lower than the baseline for the indicator; addressing such cases forms part of our recommendation for reviewing the scorecard. Further information is available in Section A.
2. Data for two indicators, percentage of portfolio projects which have produced gender-related knowledge in completed knowledge products, and number of implementation support missions with joint partner participation, are new this year.
3. In two cases, share of planned financing under the ARTF Incentive Programme that has been earned by the government by the end of the fiscal year and ARTF contributions preferenced, the targets reported in 2017 have been reduced from those reported in 2016, from 75% to 45% and from 30% to 50% respectively. Percentage of ARTF contributions preferenced is a ceiling figure, and so the increase to 50% represents a relaxation of the target.
4. The indicator “ARTF projects that include gender-specific objectives/outcomes/outputs data with targets (%)” is a composite indicator for which data is reported with breakups for objectives, outcomes and outputs and is hence represented in separate rows in the table for the purpose of calculation. The baseline figure is not broken up in the same way and has one figure of 32%. It has been assumed that the baseline figure is the same for objectives, outcomes and outputs.
5. For the indicator “Increase in the execution rate of the development budget”, the target is defined as a 5% increase per annum. As the 2016 current actual figure was 71% this is estimated to be a 2017 target of 76%.

Observations from Annual Review Monitoring Visits

ARTF Scorecard

1. Whilst the ARTF Scorecard reflects a substantial volume of data collection, the scorecard itself would benefit from additional attention and changes, in particular on the following areas:
  1. Targets: the process by which targets are set remains opaque. In many cases no baseline is available, although this is to some extent to be expected given the context. There are a handful of cases where targets have been set at levels lower than the baseline.
  2. Milestones: Projects under the ARTF are multi-year projects, whose progress is reported on an annual basis. Each project is therefore reported on multiple times throughout its lifecycle, but only ever against the final year target. Taking any given project that is on track to meet its end of project target some years from now, it will necessarily receive a low progress to target score in the early years, and this will increase year on year, even though performance is stable across years. Including annual milestone targets would allow stakeholders to better track progress on an annual basis.
  3. Indicator choice: The indicators in the scorecard are a subset of those available, are chosen by the World Bank, and there is some variation in them from year to year. The WB chooses the indicators from a set of core sector indicators (allowing for aggregation of results) complemented by project level outcome indicators. Clear communication of this methodology to donors would help increase confidence in this process.  Specifically, further clarity regarding the causal link between milestone / output indicators and outcomes, would allow stakeholders to better assess performance.
  4. Presentation: The Scorecard remains a static instrument, produced on an annual basis and with a, necessarily, limited amount of data included. An online data visualisation tool could update stakeholders more regularly, make available a greater depth of data behind each area, and enable stakeholders to better understand the progress being reported. The World Bank is currently working on a data visualisation tool, which is welcomed.
  5. Pillar one narrative: Pillar One of the scorecard captures country level outcomes for Afghanistan. Whilst the WB is explicit that country level outcomes cannot be solely attributed to the ARTF, they also recognise that the ARTF is a significant contributor in supporting results at the country level. Given the context in which the ARTF is operating, it is possible that country level outcomes will deteriorate year on year, but that the ARTF is simultaneously performing well, as has been the case this year. The narrative around Pillar One of the scorecard could discuss in further detail the external factors contributing to this deterioration, and how the ARTF has continued to bolster country level performance despite the challenging context.
  6. Sex disaggregation: The third party monitor collects a substantial volume of sex-disaggregated data, including through a 21-strong female enumerator force who conduct sex-split interviews with beneficiary communities across Afghanistan. Whilst this data is available to stakeholders through third party monitor reports, incorporating this more consistently into the scorecard reporting would enable stakeholders to better assess the progress of the ARTF with respect to sex outcomes.

ARTF Governance Structure and World Bank engagement
1. The governance structure was established to lend voice to a large group of donors contributing to the ARTF, the WB in its role as fund administrator as well as GoIRA representatives. The structure is well thought out and is designed to be representative of the many stakeholders who have an interest in a large financing mechanism such as the ARTF. The World Bank has brought in additional resource to refresh engagement with stakeholders. This is following a period of sustained deterioration in engagement from all stakeholders with regard to the governance mechanism. There were a number of issues during that period, ranging from the administrator not sending out preparatory documents sufficiently in advance, to decision makers delegating junior staff without authority to take decisions. Stakeholders have consistently praised a step change in the World Bank’s stakeholder engagement as administrator, and the corresponding improvement in engagement from donors. This is a positive and substantial improvement from 2017, and should be recognised as such.
2. The improved engagement in governance structures is accompanied by two areas for further improvement. Firstly, this positive change has been driven by individuals, in particular in the World Bank. Given high turnover in all stakeholder institutions in Afghanistan, it would be useful to institutionalise this change so that turnover does not jeopardise progress to date. Secondly, improved engagement in governance has primarily revolved around the administrator informing stakeholders of the work being done, and seeking decisions where required. To build on this positive change, donors have reported that they would like to be more closely involved in the initial design of projects, in particular those under the Investment Window.
3. Project design is a complex negotiation between the Government and the World Bank, and the WB does bring project design documents to certain ARTF donor groups. However there is substantial variation between projects on how consistently this is done. Often donor views are only sought once the project has progressed considerably toward or beyond board agreement. Where concept notes and PADs (Project Appraisal Documents) are shared at an early stage, donors do not typically coordinate comments, or necessarily provide them in a timely manner. Our recommendation is that the World Bank formalise the sharing of concept notes and PADs prior to their finalisation, giving donors a deadline for providing comments on these, which the WB should then formally respond to. Donors should, where possible, identify interest / expertise groups on thematic areas and coordinate responses.
Staff turnover / capacity
1. The security situation in Afghanistan means that there is high turnover of donor staff, and varying levels of capacity according to the size of missions in Kabul. There was a noticeable draw down following an attack near the Green Zone on 31st May, and not all embassies have been able to rebuild to original capacity. The administrator and some donors have noted that new staff often lack understanding of the ARTF, indicating poor handover practices. This creates barriers to the effectiveness of the governance structures, as donors are not able to engage effectively.
2. In addition to high staff turnover, limited capacity means not all donors can or wish to be heavily involved with the full breadth of ARTF projects. There have been attempts to map donor expertise, and in some sectors (e.g. health) there is effective donor coordination. We recommend that donors make use of their comparative expertise areas, and look for ways to strengthen donor coordination within sectors.
3. World Bank Task Team Leaders are increasingly based in Kabul. Alongside this, when WB missions are visiting Kabul donors are typically briefed by the mission. These are welcome changes, and should be consolidated across all programmes.

Output Title	Recurrent Cost Window
Output number		3	Output Score	A
Risk:		Major	Impact weighting (%):	35%
Risk revised since last Annual Review?		No	Impact weighting % revised since last Annual Review?	No

Key Points
The overall grade for Output 3 (Recurrent Cost Window-RCW) is A. However, the numeric score for the indicator declined slightly as disbursements, especially from the Incentive Programme (IP), fell slightly. Two indicators were taken from Pillars III and IV in the ARTF Results Scorecard which are related to the performance of the IP within the RCW. In addition, five indicators were taken from the 6th Administrator’s Technical Review of the Incentive Programme. These indicators were graded according to the criteria in Section B. Going forward changes to the methodology will have to be made as the Baseline Recurrent Cost Facility will be replaced by a Fiscal Stability Fund.
1	Total Indicators	7
2	Indicators with no current data	0
3	Indicators with no target	0
4	Total Indicators Counted	7
5	Average Output Progress Score (unweighted)	84%
6	Overall Output 3 Grade	A

1. In addition to the indicators in the table below, there is a set of indicators for the IP’s Structural Reform Scheme which are qualitative and tracked through a traffic light system (red, yellow and green) by the WB.
2. There is also an indicator for the Incentive Programme on the operations and management (O&M) Facility which is not graded as it has no target indicator but has shown steady progress. The facility refunds incremental O&M civilian spending above a baseline which moves according to underlying revenue growth. By December, 2017, the GoIRA earned a total of $573.48 million through the IP.
Indicators
Description	Units	Baseline	Target	Current Actual 2018	% Progress to Target
Disbursed amount in an Afghan Fiscal Year disaggregated for the Recurrent Cost Window (% of 2yr average)*	$ m	214	400	310.6	78%
Share of planned financing under the ARTF Incentive Programme that has been earned by the government by the end of the fiscal year (%)*	%	100	45	25	56%
Incentive Programme: Revenue Matching Grant**	Afs billion	-	132.6	160.3	121%
Incentive Programme: Structural Reform Scheme**	Reform areas marked as ”On Track”	-	10	4	40%
National O&M expenditures (Afs mil.) **	Afs m	18	20.6	22.1	107%
National Recurrent Cost expenditures (Afs mil.) **	Afs m	198	290.3	253.5	87%
National Domestic Revenues (Afs mil.) **	Afs m	109.4	157.7	160.3	101%

* Source: Pillars III, IV of ARTF Results Scorecard 2017, baseline figures for 2012
** Source: Incentive Programme 2015-17, Administrator’s Sixth Technical Review, 22 May 2018.
Over the period covered by this review, the RCW had three components – Baseline Recurrent Cost Financing, Ad Hoc Payments and an Incentive Programme (IP). The IP in turn has three sub-components: Revenue Matching Grant Scheme, Structural Reform Scheme and an Operations & Maintenance Facility. The financial allocation profile of RCW as of December 2017 is shown in the chart below. As can be seen in the chart, there has been a slight decline in spending under this facility from last year. This has been driven by the fall in the number of structural benchmarks achieved and a decline in baseline payments that has partially, but not entirely, reversed the significant uplift in disbursements from FY2015-FY2016.

Source: ARTF Scorecard, 2018
The IP is a key driver of the RCW and, despite minor slippage from last year, continues to show good overall progress. The replacement of the Baseline Facility with a Fiscal Stability Fund (where payments will be made based on the GoIRA’s fiscal gap) could result in larger year-on-year variation in disbursements going forward. The table below shows disbursement within the IP which is triggered by GoIRA meeting benchmarks and is hence dependent on GoIRA performance.

Source: Part VI, Table 5, Incentive Programme 2015-17, Administrator’s Sixth Technical Review, 2018

1. GoIRA’s performance in revenue mobilisation has increased by a considerable amount, since 2015, which has triggered greater incentive payments from the ARTF. These payments under the Revenue Matching Grant Scheme has tripled since FY2015 (despite a slight decline this year), an impressive achievement given the deteriorating security conditions in Afghanistan and its effects on the economy.
2. GoIRA has also performed relatively strongly in implementing reform benchmarks under the Structural Benchmark Scheme, though incentive payments under this category have dipped since last year. Under the Structural Reform Scheme, GoIRA commits to meeting benchmarks in ten reform areas ranging from customs to land administration.
3. Of these ten reform areas, GoIRA achieved all ten in FY2015. In FY2016, reforms slowed with the WB assigning a red rating to four reform areas and a yellow to a further four. In FY2017 three reform areas were given a red rating, and three a yellow rating.

Observations from Annual Review Monitoring Visits
1. Stakeholder consultations indicate that the IP within the RCW is considered a relative success and offers validation of an incentive based financing model that can be transferred to address issues in sector specific projects funded under the Investment Window. The relative success of the IP is one of the main reasons behind the decision to replace the Baseline Support Facility with a Fiscal Stability Fund. This Fund will make payments conditional on the existence of fiscal gaps (revenue-planned expenditure). Thereby, introducing a new element of conditionality.
2. Consultations with WB point to the following strengths of the programme:
  1. The IP has a higher quality of entry in the sense that it assesses if a counterpart GoIRA agency is able and willing to achieve reform and if reform is demand driven. Not all ministries in GoIRA have the same capacity and this implies that the IP, by picking stronger actors in the government system who can coalesce around a set of reforms, builds in a greater probability of success.
  2. Accountability in the IP can be clearly enforced as reforms are mostly at legislative and policy level which can be verified (e.g. a particular piece of legislation coming into effect) by both GoIRA and WB with minimal ambiguity. Moreover, the President’s Office has a direct line of sight into the IP as it involves apex GoIRA agencies and senior government staff are reported to have had their performance measured based on the meeting of IP benchmarks. Clear verification norms and unambiguous performance based fund disbursement triggers have set expectations within GoIRA accordingly and there is an awareness that unlike a traditional ‘project’, funds will not be disbursed if targets are not met. The incentive to implement reforms will also be sharpened under the new scheme because delayed implementation will result in a reduced incentive payment (up to 6 months, after which no payment will be made).
3. The progress achieved in the IP has influenced the changes taking place in the new PFFP (2018-2021). Key elements of these reforms including introducing greater conditionality. This entails introducing disbursement linked indicators (DLIs) into the pay-outs of an increasing number of IW projects. Secondly, release of incentive funds under the IP is triggered by mostly legislative and policy reforms that do not require much effort to verify. However, given the centrality of actual implementation in realising the benefits of most structural reforms, ensuring that legislative change results in actual change in practise is important. Given that virtually all legislative changes are linked to reform processes supported under the ARFT’s Investment Window and/or other ongoing WB projects, there is an ability to monitor effective implementation. Specifically, the DFIDA team and DFIDA advisory staff should monitor how and to what extent the achievement of legislative reforms does in fact translate into changes in project implementation. It might also be possible to use the Third Party Monitoring Agent to look at this issue in more detail and track what policy changes derive from legislative reform under the increased mandate of TPM through ACReMAP.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
Economy
1. DFID inputs into ARTF fall into the following three broad categories: Contributions into the ARTF fund in line with its commitments in PFFP (see table below); payment towards a 4% management fee to the WB which is paid by all ARTF donors; and in-house staff time and related expenses on ARTF.
2. It is not possible to take a traditional unit cost or cost benefit approach to analysing Value for Money (VfM) for the ARTF as it is not a conventional project but a pooled financing vehicle where DFID is one of several donors. DFID does not ‘preference’ or earmark its contributions to ARTF and has no direct control over how its contribution is applied to sectors or projects therein. Similarly the WB’s management fee is spent on line items, records of which are not shared with DFID or with other donors. Internally, DFID does not have a system of timesheets which can tag internal staff time or expenses to ARTF. Instead, in its staff appraisals, staff agree with line managers on an allocation of their time to particular projects or activity areas. This is then reviewed qualitatively in each appraisal cycle.
3. The following indicators from Pillars III and IV from the ARTF Results Scorecard are therefore used as proxies for VFM assessment.
Indicator	Units	Baseline	Target	2017 Actual	% Progress to target
Disbursed amount in an Afghan Fiscal Year disaggregated for the Investment Window ($mil)	$ m	15.59	350.00	476.20	136%
Disbursed amount in an Afghan Fiscal Year disaggregated for the Recurrent Cost Window ($mil)	$ m	214.00	400.00	310.60	78%
Fiscal Year disbursement of active grants divided by total undisbursed funds in active grants by the beginning of the fiscal year (exc RCW) (%) Excluding NSP	%	55.00	25.00	43.0	172%
Share of planned financing under the ARTF Incentive Programme that has been earned by the government by the end of the fiscal year (%)	%	100.00	45.00	26.00	58%
Recurrent sources as share of government civilian operating budget (%)	%	48.00	No target set	26.00	-

Source: ARTF Result Scorecard, Pillars III, IV, December 2017
Programme Support Systems
1. On economy, the ARTF is a mechanism to strongly leverage the UK’s contribution as it is a pooled fund and is able to operate at a scale that a stand-alone DFID project(s) would not have been able to. By paying a 4% management fee, DFID is able to call on the services of the WB as administrator who with their experience of global operations can offer good safeguards against fiduciary risk. Also, the WB applies its standard procurement processes to all projects to obtain best value from private sector or non-profit suppliers. These processes have been tested in Bank operations around the globe and are rigorous in the way they apply different procurement methods for different procurement thresholds.
2. In addition, the ARTF has commissioned two third party monitors - a Monitoring Agent (MA) for checking eligibility of transactions in the Recurrent Cost Window and a Supervisory Agent (SA) to check compliance. The scope of projects monitored by both agents will expand in line with the WB’s new financial strategy.
Analytical Capacity
The ARTF has a Research and Analysis Programme (RAP) which promotes lesson learning from ARTF projects based on evidence. Established in 2015 as a result of a recommendation in the external evaluation of the ARTF, the RAP undertakes project specific research as well as sector and thematic studies.
Public Financial Management
The Public Financial Management Reform II (PFM II) project, financed under the Investment Window, has indicators that contribute to VFM. Its mandate is to strengthen the efficiency and effectiveness of Afghanistan’s procurement, treasury, and audit systems.

Indicator	Units	Baseline	Target	2017 Actual	% Progress to target
Improved coverage and quality of internal audit	%	49.00	50.00	30.00	60%
Improved coverage and quality of external audit	%	49.00	75.00	71.03	95%
Number of internal audits done to acceptable standards	number	4	34	138	406%
Number of external audits verified as done to international auditing standards	number	WB grant audits	All WB grant audits and 9 compliance audits	FY15 grant audits completed, FY16 underway, 9 line ministry audits completed

Source: World Bank, PFM II Implementation Status and Results Report (P120427), Sequence 12, 15 May 2017
Efficiency
On efficiency, projects funded by the ARTF are tracked using a set of Intermediate Results and Project Development Objective indicators which are reported on by the WB task team or Project Implementation Unit (or by the line ministry project staff if there is no PIU). Efficiency is affected by a range of factors including capacity issues in line ministries, project level challenges due to changes in operating environment and due to a general worsening of the security situation and fragility of government control in Afghanistan. However, across a range of indicators reported in the latest ARTF Results Matrix across the three outputs, ARTF has scored a grade of A for each of the three outputs suggesting that it is meeting expectations.
Effectiveness
1. ARTF is on track to achieve its overall outcome: “GoIRA increasingly capable of managing and delivering essential infrastructure, reforms and basic services, improving access to public services and employment opportunities.”
2. GoIRA has achieved good progress across a range of outcome indicators. Detail is available under ‘key findings’ in section B (Performance and Conclusions), and in Section C (Detailed Output Scoring). These show relatively strong results given the deteriorating security situation in Afghanistan, and whilst this is likely a contributing factor to a number of the less well performing indicators, projects under the Investment Window should still be subject to close monitoring and evaluation to ensure they are performing effectively, and that the theory of change between inputs / outputs is robustly leading to the desired outcomes.

Complementarity
1. The Investment and Recurrent Cost Windows have continued to complement each other. The success of the Incentive Programme in driving structural reforms across GoIRA and increases in revenue through an incentive payment system should have positive downstream effects on sector specific projects in the Investment Window and on the Afghan economy in general.
2. Conversely, projects in the Investment Window such as the Public Financial Management Reform II (PFM II) and the Capacity Building for Results (CBR) projects support the wider ARTF portfolio by improving public financial management and in aiding the absorption of World Bank Programme Implementation Unit consulting into the Tashkeel or civil service and in improving the capacity of select line ministries and departments.
3. Along with these achievements, there remain areas of improvement in tracking causality from outputs to outcomes and checking attribution. Project indicators for NPP aligned projects on the Investment Window side that the WB uses in its Implementation Status and Results reports are mostly at input and output – not outcome – level. This is also reflected in the ARTF Results Matrix which is based on this data where indicators chosen are weakly related to outcome or impact level indicators and is spread across a large number of projects which are difficult to aggregate at a portfolio level. The Monitoring Agent (MA) reports only on financial transactions and does not report on RCW performance indicators at an outcome or impact level in order to track the broader effectiveness of IP indicator targets.
4. The RAP was established in 2013 with the goal of providing more thematic research and insight into the impact of projects and has been used to fund 17 studies so far. It is not clear if they have contributed any impact analysis that has fed into the ARTF Results Matrix in time for this Annual Review round. As DFID does not preference its contributions to ARTF, it does not directly control the research agenda that the RAP can fund.
Equity
On equity, close alignment to GoIRA programmes and explicit targeting of interventions towards vulnerable and underserved sections of Afghan society ensure that ARTF is not at a substantial risk of funding projects that are not equitable.
VfM performance compared to the original VfM proposition in the business case
1. Given the above, ARTF performs relatively well on economy and efficiency grounds as it can leverage limited resources into a pooled fund which acts as a multiplier. Across the sectors and projects reported in the ARTF Results Matrix, it scores an overall grade of 'A' indicating that the ARTF is meeting expectations.
2. On effectiveness grounds, ARTF has shown progress on several of the outcome level indicators shown in the ARTF Results Matrix by the World Bank. However, the picture on effectiveness is more complex because (a) it is uncertain if Pillar I indicators have improved or worsened, (b) there is a lack of impact evaluation or longitudinal tracking studies on ARTF projects that can measure changes in long run outcome variables based on project interventions and (c) there are projects in the ARTF portfolio which continue to underperform despite measures taken by the WB. Pillar I indicators track the general economic and security conditions in Afghanistan and may be treated a set of exogenous variables that affects ARTF but is not driven by it. The general deterioration in security and its knock-on effects on the economy make simple extrapolations risky based on a limited set of indicators presented in the Results Matrix. While there is a lot of project level data at the input-output level, data on outcomes is more limited as what the WB tracks as Project Development Objective indicators can also be at output level. There is a general lack of impact evaluation or longitudinal tracking studies on ARTF projects and the bulk of available data is based on GoIRA socio-economic surveys whose frequency is not regular and does not always cleanly align with ARTF programming cycles. The new PFFP promises to bring in fundamental changes such as more GoIRA ownership, a programme focus instead of projects focus and a move to bring in more results based financing approaches in Investment Window programmes in various sectors. Whether these changes improve effectiveness will need to be assessed in forthcoming annual review cycles.
Assessment of whether the programme continues to represent value for money
1. While VfM benefits and costs cannot be quantified as ARTF is not a conventional DFID project, the ARTF does remain strong on the economy criteria for DFID and continues to represent value for money. By contributing to a trust fund of the size of ARTF, DFID substantially reduces fiduciary risk and delivery of interventions at a scale and depth that it could not have achieved through its own stand-alone programmes or projects at the level of resources it has committed currently to ARTF.
2. On effectiveness, there are signs that the ARTF has shown progress on outcome level indicators presented in the ARTF Results Matrix but the real picture may be more complex and more difficult to measure in the current data environment and it would not be prudent to make simple extrapolations on effectiveness yet.

Date of last narrative financial report	For DFIDA
Date of last audited annual statement	For DFIDA

E: RISK

Overall risk rating: Major

Overview of programme risk
1. According to the Business case, the overall risk of DFID’s support to the ARTF not achieving its objectives is assessed as medium-to-high and with a high impact. However, mitigation measures are expected to moderate the risks to a satisfactory level.
2. The UK’s independent Fiduciary Risk Assessment (FRA) has been updated in 2017. It found that the overall level of fiduciary risk remained substantial. This was confirmed by the visit of DFID’s Internal Audit Department in 2018.

Areas of improvement or no change include fiduciary risk
The recent FRA concludes that while fiduciary risk remains substantial, it is expected to improve. In addition to the WB’s standard fiduciary risk management processes, the UK has maintained a high profile in donor forums, which help determine the direction of the Trust Fund, and has drawn on in-country expertise to help improve the ARTF’s own operations. For instance, DFID has contributed to the restructuring of the Incentive Programme, commissioned, out of its own funds, the fourth external review of the ARTF, supported the new PFFP and has been supportive of the expansion of the Monitoring Agent (MA) and Supervisory Agent (SA).

Areas of increasing risk include delivery risk
1. 2018 presented an increase in Afghanistan's security challenges. If security conditions worsen, aid falls short, or reforms stall, growth would be lower with attendant effects on unemployment and poverty. Public faith in government has remained at a low level. Forthcoming elections and election-season dynamics also lend uncertainty to the delivery of ARTF.
2. Recent findings of the MA have raised concerns about the lack of universal application of project controls within line ministries, in particular in relation to the certification of recurrent costs. This has led to demands for the expansion of existing third party monitoring services from ARTF partners to ensure controls are being universally applied.
3. There is also uncertainty on the fiscal envelope made available by donors for the ARTF’s new 2018-2020 PFFP. The WB has reported lower donor contributions since last year and if this trend were to continue, delivery models would need to factor in lower resources.
4. DFIDA should review how it can dynamically track risks at a quarterly and sub-ARTF portfolio level in order to identify and contain any emerging risks at the sub-ARTF level.
5. DFIDA should also perform a scenario planning exercise in which it carefully considers how and under what conditions it could scale up or scale down ARTF contributions.
F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
The ARTF at the programme level is running according to the approved timeframe in the Business Case. The publication of the new PFFP was delayed by several months, and not published until June 2018. Existing projects continued to operate during this period, with front-loading of new projects using IDA funds. Where successor projects could not be approved because the PFFP had not been agreed, the previous projects were rolled over, receiving extensions to funding and deadlines, reflecting that these projects were continuing to contribute toward the overall aims of the ARTF. Because the ARTF has been in operation since 2002, these project level adjustments do not affect the overall portfolio and can be rolled over. They are in line with GoIRA’s National Priority Projects, and therefore the extensions are in line with the DFID business case.
Performance of partnership (s)
1. ARTF has been in operation continuously in Afghanistan since 2002, a period of 16 years, which provides strong evidence that partnerships between GoIRA and the international donor community have remained stable and functional. DFID is seen as an active, engaged partner by the WB and other donors. Notably, DFID’s Social Development Adviser currently co-chairs the Gender Working Group, and stakeholders have welcomed the notably increased engagement between World Bank task teams, GoIRA and donors through the Gender Working Group.
2. However, the context in which ARTF operates has put pressure on these partnerships to evolve. A deterioration of security conditions on the ground, coupled with budget constraints on donors, has created high staff turnover and reduced capacity in most international agencies. DFID is generally perceived as having a good depth of expertise and capacity, and as having built this up again quickly following the May 2017 attack. Smaller donors who cannot afford full time staff for ARTF have been affected to a greater extent. In all cases there is high turnover which hampers retention of institutional memory.
3. The ARTF is a large portfolio with a large group of donors and it is often a challenge to accommodate individual demands of such a large group. Often this poses difficulties in the relationships between the WB and donors. The past year has seen substantial improvements in engagement between World Bank and donors, and the next progression from this is earlier and more consistent involvement of donors in project design. This will require changes from the World Bank as well as donors, who should be prepared to dedicate resource to responding effectively and, where appropriate, coordination responses.
4. Changes in political conditions and the passing of time has meant that the ARTF no longer operates in the same set of conditions that it used to 16 years back. There is a strong appetite for change from GoIRA in the way international development programming should operate, in particular desiring a move toward sector wide approaches and a greater proportion of incentive-based financing. The new PFFP responds effectively to these needs, and the ARTF should remain responsive to the changing circumstances.
Asset monitoring and control
1. As the ARTF is a pooled financing platform in the form of a trust fund and not a conventional project, DFID does not directly procure assets required by the numerous projects financed under the ARTF. The WB, in its role as administrator of the fund, manages fiduciary risk and conducts risk assurance activities. These consist of (a) the WB’s standard project monitoring systems, internal and external audits; and (b) third party monitoring in the form of a Monitoring Agent and Supervisory Agent procured by the WB.
2. The Monitoring Agent (MA) conducts compliance checks of financial transactions under the Recurrent Cost Window. The MA contract has been in place since 2003. It takes a sample of transactions from the Afghanistan Financial Management Information System (AFMIS) and checks if these transactions are eligible for ARTF funding. It also conducts physical verification of payroll by randomly picking employee names and visiting them to militate against the risk of ghost employees. In addition to payroll, the MA verifies a sample of Operations & Maintenance (O&M) expenses by checking inventory and asset registers at regional offices to ensure that such purchases are actually delivered to local government offices. The MA provides monthly, quarterly and annual reports to the WB. The WB shares these reports, as well as an executive summary, with ARTF donors. Ineligible transactions are refunded by GoIRA.
3. The Supervisory Agent (SA) conducts physical verification of construction carried out under a sample of seven projects under the Investment Window. The SA contract has been in place since 2012. The SA conducts site visits in almost all provinces in the country where these seven projects run and provides a grading system on a scale of 1-5 based on quality of construction and compliance with a variety of specifications. The SA submits monthly, quarterly and annual reports to the WB which are published on the ARTF website. Detailed monthly reports may be requested from the WB as necessary. The SA also provides an online data mapping tool.
4. The new financing strategy provides for an increased monitoring function through the new Anti-Corruption and Results Monitoring Action Plan (ACReMAP) window. This expands the role of third party monitoring in the ARTF, and will support the costs of conducting periodic in-depth fiduciary reviews of ARTF-financed operations.
5. The Supreme Audit Office of GoIRA also conducts an annual audit of ARTF related transactions.

G: CONDITIONALITY

Update on partnership principles
1. The UK’s development programme in Afghanistan supports the Afghan government’s National Development Strategy. In 2012, the Tokyo Mutual Accountability Framework (TMAF) was adopted, containing sets of commitments by the government to tackle key constraints to development, and by the international community to align aid with the government’s delivery of these plans. This was updated at the Brussels conference in 2016 to the Self-Reliance through Mutual Accountability Framework (SMAF). The TMAF and SMAF cite a 50% target for on-budget support, as well as a target for development partners to align 80% of support with GoIRA’s National Priority Programmes (NPPs), but the SMAF does not include the 50% on-budget target.
2. The PFFP has sought to align even more closely with the Government’s NPPs, and 100% of ARTF financing is now aligned to NPPs. The Investment Window which funds projects in various sectors are tied to the NPPs and are a good example of this. In the Recurrent Cost Window, the Structural Reform Scheme within the Incentive Programme modality provides incentives for reform that address NPPs.
3. During the negotiation of the new financing strategy, the Government was seeking a further move toward incentive based financing. Government stakeholder interviews have indicated that they find this a useful modality through which to incentivise line ministries into action, in particular reform. The modalities for both the Recurrent Cost Window and Investment Window have been revised in order to strengthen conditionality. In the Recurrent Cost Window, baseline funding is being removed, and the intention is to link more of the funding to the incentive programme, where structural benchmarks for government reform need to be achieved in order to release funding. In the Investment Window, the new financing strategy aims to include Disbursement Linked Indicators (DLIs) where appropriate, in order to incentivise government reform.
H: MONITORING & EVALUATION

Evidence and evaluation
1. The current ARTF Results Framework is focused at project level and at the input-output level. Integration of data across multiple projects is weak and it is not possible to ascertain from sector specific indicators the overall impact of the ARTF at a portfolio or programme level. (An integrated system to view ARTF financial data in terms of disbursements and allocations is however available and uses data visualisation tools online.) Feedback from ARTF donors indicate this is a key area of concern as donors find it difficult to assess the performance of the overall ARTF portfolio.
2. The ARTF Scorecard is an attempt to integrate multiple sources of data across sectors from the ARTF Results Framework but it is a work in progress and has yet to address some fundamental limitations (several of which were identified in the previous Annual Review round).
3. There is an insufficient number of impact evaluations or longitudinal studies of programme participants to determine longer term outcomes and impact of the ARTF. The RAP was established presumably with a view to doing this but it is not clear from the studies commissioned so far whether it contributes to the assessment of impact of the ARTF at a portfolio level.
4. The M&E system currently stands on two pillars – (i) M&E data produced by systems at project level which feeds into the WB’s Implementation Status and Results (ISR) reports and (ii) third party monitors (TPM) which currently consists of the Supervisory Agent (for the Investment Window) and the Monitoring Agent (for the Recurring Cost Window). Feedback from donors suggests a lack of clarity on the relevance of the data set out under Pillar I and how the ARTF sits within this broader context. There is also the matter of TPM ‘sprawl’. While the ARTF has commissioned a MA and SA, they are not the only ones as some donors – such as Canada and Germany – have commissioned their own TPMs to monitor their contributions to ARTF as well as to other projects beyond ARTF where they are invested. The ARTF should consider whether and how it can use these additional datasets to improve its own data collection and/or cross-check results.
5. With the worsening security situation which makes it difficult for WB international staff to go to field locations and a corresponding loss of faith in project based monitoring systems, TPM appears to be perceived as a cure all solution at present. However, an effective M&E system will depend on striking a balance in resources invested on both pillars. While short term objectives of fiduciary risk assurance can be met by expanding the scope for TPMs, if this is done at the cost of improving project level M&E systems then one pillar could ‘crowd out’ the other.
6. At the time of writing the overall monitoring facility is in the process of changing with the WB aiming to have a single supplier and/or consortium of suppliers providing both the MA and SA functions in the future. Under the existing system, the MA, which is currently an accounting firm, does mostly paper based compliance checks of a sample of transactions taken from the Afghanistan Financial Management Information System (AFMIS). Given that the proportion of ineligible transactions has increased over time, it should be assessed if the MA’s current paper-based methodology continues to be the most appropriate. Various donors expressed concerns about what they perceived as a low level of physical verification. The SA, on the other hand, have been able to complete regular physical inspections of project sites across the country using local staff and it could be the case that the MA needs to increase its complement of national staff, with such a process beginning through the new joint work between the MA and SA.
7. The SA has received relatively favourable feedback in terms of the granularity and coverage of data. However, it should be noted that GoIRA agencies have not always shown an improvement in addressing deviations from construction specifications reported by the SA in ongoing work, and less so when deviations are identified after work has completed. This seems partly due to lack of funds for line ministries to conduct follow-up corrective actions based on SA reports and partly due to lack of a systematic mechanism to assign responsibility to and track follow up actions.
Monitoring Progress in the Review Period
Other than the Annual Review DFID’s Internal Audit Department conducted an assurance review of the DFIDA portfolio in the summer of 2018. This included a detailed review of the ARTF.