 Programme Completion Review – May 2021

Title: Humanitarian protection for vulnerable refugees and host communities in Jordan
Final Programme Spend £ (full life): £14,876,437)	Review Date:	May 2021
Programme Code: 300537	Start Date: 04/04/2018	End Date: / 31/03/2021

Summary of Programme Performance

Year	2018/2019	2019/2020	2018-2021
Programme Score	A	A+	A+
Residual Risk Exposure Rating	Minor	Moderate	Moderate

DevTracker Link to Business Case (and any addendum):	https://iati.fcdo.gov.uk/iati_documents/35462254.odt
DevTracker Links to all logframes used during programme lifetime:	https://iati.fcdo.gov.uk/iati_documents/45939247.xlsx

A. Summary and Overview

Description of the programme and what it has achieved
The Syrian refugee crisis has placed a significant burden on Jordanian services at a time that the country is facing its own economic and social challenges, compounded by the effects of the COVID-19 pandemic. Syrian refugees and other vulnerable groups (including people lacking documentation, people with disabilities or mental health conditions, female-headed households, and children) can face significant difficulties in accessing the health, protection and other services they require to ensure their rights and wellbeing are protected. The protection programme was part of the FCDO Jordan humanitarian portfolio which also includes multi-purpose cash assistance to the most vulnerable refugees. The combination of delivering both cash assistance and protection services (responding to needs such as lack of civil documentation, children at risk, or people with disabilities) ensures that the most vulnerable are able to cover their basic needs while having access to specialised services. These communities are particularly vulnerable as they do not have regular access to livelihoods opportunities or may have members in their households who are disabled or in need of other services which they are not able to receive. Supporting people to obtain civil documentation, for example, ensures they have a legal status in Jordan and can also support them in accessing public health services.

Through this programme, FCDO provided £14.8m over three years to International Medical Corps (IMC), Norwegian Refugee Council (NRC), and Humanity and Inclusion (HI) to deliver life-changing activities addressing the basic protection needs of 62,167 vulnerable Jordanians and refugees (including Syrians). The services were delivered in a way that promotes sustainability and resilience and which builds the capacity of local actors. Activities took place across different governorates and included:
- Legal counselling and case management (e.g. to enable people to obtain marriage and birth certificates or to resolve employment disputes);
- Health support for people in remote communities including persons with disabilities (PwD) requiring physical rehabilitation, mental health support, and psychosocial services;
- Child protection case management;
- Training for health professionals, community leaders and local NGOs on a wide range of topics including safeguarding and needs assessments; and
- Awareness-raising and advocacy on refugee rights through continuous community outreach and social media campaigns.

This programme was designed through an open call for proposals in 2017, from which these three partners were selected.

While the programme consists of different components, FCDO also worked to strengthen how partners work together holistically across these issues.

A major change in context that affected this programme is the COVID-19 pandemic and associated lockdown measures introduced in Jordan. The impact this had on delivery and how partners adapted is explained in the sections below. Overall, the partners were able to adapt and continue delivery, overachieving on most output indicators resulting in a score of A+. The main reasons for over-achievement were the unanticipated needs in communities (for mental health, legal assistance, child protection, and rehabilitation services) and the enhanced outreach activities which partners undertook in order to reach more vulnerable people.

Major lessons learned, evidence generated and recommendations
The main lessons learned from this programme relate to the sustainability of service delivery in a protracted crisis situation. Early and clear engagement with local service providers and relevant government ministries helped build their capacity and improve overall systems to deliver services both to refugees and Jordanians. This was met with challenges and competing priorities on the Government’s side, particularly with the onset of COVID-19, but close follow-up and building a good relationship across teams has enabled some elements of transition programming to be applied. For example, alongside technical training for the provision of rehabilitation services to people with disabilities (PwDs), HI worked to strengthen government systems on the early detection and early intervention of disabilities in children. In addition, working with local communities as volunteers to raise awareness of services, refer beneficiaries as needed, and in certain cases delivering home-based support was essential to build trust and reach vulnerable families. Activities continue with other donor funding. Details on lessons from each output can be found in section C, as well as specific recommendations.

During implementation, all three partners conducted external evaluations of their interventions, with HI undertaking both a mid-term and final evaluation. These have generated important evidence on the efficiency, sustainability, and effectiveness of this programme. Some recommendations made in these evaluations include scaling up work undertaken with government to harness the strong relationships established under this programme, ensure stronger consultation with beneficiaries at the design stage of the programme, and to focus interventions on areas where agencies can add the most value (e.g. for NRC to focus on complex cases of refugee registration procedures). The evaluations also included technical recommendations which we have discussed with partners and will take into account when designing the new Jordan Protection Programme (JPP).

Summary of high-level recommendations for new programme:
Recommendation	Timeline	Responsible
Scaling up work with government to harness the strong relationships established under this programme	Ongoing, with key discussions to happen during the design and inception phase of the new JPP (July-October 2021)	FCDO along with potential new INGO partners
Ensure stronger consultation with beneficiaries at design stage of programmes	July-September 2021	Potential new partners
Agencies to focus on interventions where they can add the most value	During design of new programme and throughout implementation	Potential new partners and FCDO
Programmes to focus on and prioritise localisation, including building the capacity of local actors	During design of new programme and throughout implementation	FCDO and implementing partners

How this report was conducted
This report was drafted by the FCDO Jordan Humanitarian Adviser with review and comments by the Senior Programme Manager, Monitoring, Evaluation and Statistics Adviser, Economic Policy Officer, and FCDO Jordan Portfolio Manager.

The report relied on partner quarterly reports, field visits (including conversations with beneficiaries), partner quarterly meetings, and evidence from previous Annual Reviews.

Actions following approval of this report
Following the approval of this report, we are expecting partner final reports to be submitted by the end of June 2021 to enable any outstanding payments to be made (previously accrued based on partner forecasting). We are also expecting the publishing of audited financial statements of NRC and HI by the end of June 2021 and IMC’s by March 2022. The team will also archive the programme after all closure tasks are completed.

This PCR will also be published on the Development Tracker and recommendations shared with partners.
## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	£15,000,000	£14,054,404.98 with £822,032.02 to be paid following receipt of final reports
Timeframe	3 years	3 years
Outcomes	Overall outcome: Needs of the most vulnerable met by greater access to expanded and strengthened protection, rehabilitation, and legal services, as well as advocacy efforts to promote policy change	Overall outcome achieved through achievement of outcome indicators (see below)

Overall assessment of programme outcomes, sustainability and VfM
The logframe outcomes were achieved within the programme timeframe and budget, where the outcome indicators and results are outlined below:
- Outcome indicator 1: Percentage of beneficiaries who report exercising their legal rights- achieved results is 98% compared with target of 75%
- Outcome indicator 2: Percentage of beneficiaries who rate the service provided positively- achieved result is 92% compared with target of 85%
- Outcome indicator 3: Percentage of beneficiaries showing improvement in functional independence- achieved result is 85% compared with target of 80%
- Outcome indicator 4: Number of instances where partner recommendations are reflected in targeted policies, decisions, and/or other arenas by the government of Jordan (GoJ) – 27 achieved out of a target of 11
- Outcome indicator 5: Two national early detection/ early intervention (ED/EI) guidelines developed and approved by the Ministry of Health (MoH) and the Ministry of Social Development (MoSD)- achieved one guideline for EI and one clinical pathways guideline for ED.
We assess these results to be sustainable as the interventions were designed with sustainability in mind. In particular, the ability to obtain documents and exercise legal rights, improved functionality as a result of mental health and rehabilitation interventions and strengthened GoJ systems through the development of guidelines for the early detection and intervention of disabilities. It is more difficult to track the sustainability of the other outcome indicators, but they contribute to tracking the quality of service provision (outcome indicator 2) and overall advocacy efforts to promote policy change (outcome indicator 4). The activities relating to these outcomes will be discussed in more detail in section C.
Value for Money (VfM):
In this section, we will look at the cost-effectiveness of the programme as well as equity considerations. Economy and efficiency will be discussed in other sections of the review.

As shown by the results above, the programme has achieved and over-achieved on the outcome indicators, indicating the effectiveness of the programme. Despite challenges faced by partners due to COVID-19 and related movement restrictions in Jordan, they continued to adapt their delivery modalities to ensure programme effectiveness. For example, HI relied on their trained community volunteers to deliver home-based rehabilitation sessions (where they were already trained) and continued to focus on functional independence of people with disabilities. Patients are also provided with exercise tips that they can implement by themselves. IMC worked swiftly to develop remote consultations for mental health and maintained contact with patients who require regular sessions and medication. Moreover, NRC continued with the remote delivery of legal counselling and focused on ways to support people to obtain their legal documentation. While the last year of the programme faced unprecedented challenges, the partners were able to continue the delivery of services and remain effective.

On equity, all throughout the programme period, partners ensured equitable access to services based on vulnerability where services were available to refugees of all nationalities as well as to vulnerable Jordanians. Working through community volunteers and local organisations also enabled partners to have a wider outreach and not limit services to those able to reach their centres. IMC’s partner the Jordan Hashemite Fund for Human Development (JOHUD), for example, ran a mobile medical unit (MMU) to ensure health services (including mental health) reach those in remote areas and living in informal tented settlements (ITSs). The MMU delivered over 12,000 consultations over 3 years. In addition to that, partners provided services equally to men, women, boys, and girls where data was disaggregated by age, sex, and geography and shared with the FCDO (the average percentage of men and boys reached by all 3 partners was 47% to 53% women and girls). Overall, partners sought to leave no one behind and delivered services equitably.
Summarise the programme’s theory of change and results framework, including any changes to outcome indicators.
This programme’s theory of change (ToC) is based on the delivery of specialised protection services to vulnerable households (including support to people with disabilities, child protection, mental health, and legal assistance) whereby improving the protection situation of vulnerable families and individuals will lead to an improvement in their well-being and social participation, and build their resilience towards future shocks. The programme also worked on strengthening the capacity of national systems to respond to the needs of vulnerable groups; contributing to the enhanced well-being of refugees where they can live in safety and dignity. The assumptions that underpin this ToC remained valid throughout implementation; the Government of Jordan (GoJ) granted authorisations for these activities to take place, the security environment remained stable, and refugee populations did not return to Syria in large numbers. There was no new evidence that challenged this ToC; partners continued to deliver on outcomes and impact as planned. As mentioned above, the change in the operating environment due to COVID-19 impacted partners’ ability to deliver services, particularly during strict lockdown periods. However, all three partners were able to adapt by delivering services remotely where possible and applying safety measures for in-person service delivery to ensure vulnerable people are not impacted.

Throughout the programme period, we maintained close contact with partners, downstream partners, and beneficiaries when possible to inform our assessment of the ToC. Due to COVID-19 risks, we did not conduct any field visits in the last year of the programme but met partners remotely on a regular basis, including ad hoc informal discussions to remain engaged and informed about the situation. Moreover, partners continued their regular monitoring which continued to inform delivery. For example, on the outcome related to exercising legal rights, beneficiaries were asked if they were able to obtain the needed legal documentation as a result of NRC interventions and then use those documents for their intended purposes (e.g. enrol in school). IMC and HI’s indicators on functional independence looked at beneficiaries’ ability to perform daily tasks independently (e.g. get dressed) and levels of pain associated with certain disabilities.

The programme used a logframe to track results which only underwent minor changes during the past years. These were changes to target numbers as partners adjusted delivery based on need and resources, and the wording of some output indicators to better reflect the activities that we are measuring. No changes took place in the last year of implementation where the last changes made to the logframe were in December 2019 and captured in detail in last year’s Annual Review.

## C: Detailed Output Assessment

Output Number and Title		Output 1: Training and capacity building of key stakeholders including non-governmental organisation (NGO) staff, GoJ staff, and community leaders
Output Score		A+
Impact weighting (%)	20%	Impact weighting revised since last AR?	No

Output Indicator	Final Logframe Target	Final Result Achieved
1.1 # of national, local authorities, lawyers, jurists, law students and legal aid providers trained on access to justice issues for refugees	200	323 (162%)
1.2 # primary health care providers receive training, for example mhGAP, early detection/ early intervention (ED/EI) and mental health and psychosocial support (MHPSS)	228	416 (182%)
1.3 # of community actors and leaders that are empowered to support protection needs both in community settings and camps to influence service provision	412	483 (117%)
1.4 # of projects assessed and for which inclusion action plans have been developed for implementation	10	9 (90%)
1.5 % of training participants demonstrating an improved knowledge in topics covered	70%	98% (140%)
[note] To support primary healthcare providers in identifying and referring mental health patients
[note] HI’s target is for the number of primary healthcare centres, the number of staff trained in the centres is extracted from the narrative reports

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.
This output combines different activities that were undertaken by all three partners to train and build the capacity of national stakeholders with the aim of strengthening national systems to respond to the protection needs of vulnerable groups.
Partners have overachieved on all indicators except one under this output due to the increased demand for training which partners were able to accommodate. The increased demand is partly due to new staff joining and increased efforts by partners to improve skills and knowledge at national and local institutions. While the modality of delivering training has had to change due to COVID-19 restrictions (moving to a mix of remote and face-to-face interaction) this demonstrates the flexibility of the programme to respond where needed and the importance of these activities. Activities also involved on-the-job coaching (as in the case of the mhGAP training) as well as close follow-up of implementation (as in the development of inclusion action plans). This output focused on making services sustainable and building expertise. The inclusion plans developed under output indicator 1.4 have improved how other agencies design their programmes to ensure that services are inclusive of people with disabilities (PwDs). The plans include training on the use of the Washington Group Questions as well as tailored technical advice on how to interact with and include people with functional limitations in programming.

The result of output indicator 1.5 demonstrates the effectiveness of these activities in improving the knowledge of training participants. It’s difficult to determine the exact reason for over-achievement on indicator 1.5 as it is based on pre and post evaluations of training participants. It does show, however, that these activities are delivering positive results (as evidenced by the result) and can be assumed that it leads to better quality of service delivery.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme
Costs of major inputs remained stable throughout programme implementation. For this output, those mainly consisted of venue rental, transportation costs, and salaries of staff involved in delivering these activities. During the last year of implementation, costs associated with training and capacity building reduced as activities were disrupted due to COVID-19 related restrictions and carried out remotely, while staff salaries remained stable. Cost savings made were in turn redirected towards other programme activities that partners were able to implement. For example, IMC used savings to provide more beneficiaries with child protection and mental health services where needs were also increasing due to school closures and limited movements.
The cost for this output per beneficiary for NRC for example (as measured by NRC) increased from $294 in 2019 to $387 in 2020 due to a fewer number of training beneficiaries targeted in 2020. The efficiency of this output is demonstrated, however, by the ability of those trained to increase outreach of protection activities, including the assessment and referral of cases to the right services. This proved even more important during imposed lockdown measures where HI trained community-based rehabilitation (CBR) volunteers, for example, were still able to operate in their own communities. In addition to that, volunteer costs vary between 10-15 JOD per day where an HI staff member in a lower-grade position requires a salary of around 82 JOD per day.

As for the equity of activities under this output, partners targeted different groups for capacity building and training, including women and PwDs. HI’s CBR volunteers, for example, include PwD where being part of this initiative not only empowers them but enables them to reach other PwDs in their communities as well as work on reducing stigma in communities. Similarly, IMC community groups include men and women from both the refugee and host communities to encourage those more comfortable in discussing their mental health with people they trust.

Lessons learned through this output, and recommendations for future programming
One of the main lessons identified through delivering this output is the important role that community volunteers play in detecting and referring cases for protection services, as well as in increasing the outreach of programmes. During the COVID-19 lockdown in specific, volunteers were one of the only ways in which partners could reach beneficiaries where HI volunteers, for example, advocated with local authorities to allow movement permits for staff in order to deliver vital protection services. Another lesson learned is the link between the delivery of sustainable services (which we are seeking) and the training and capacity building of local service providers including NGOs and government services. The mhGAP training for example provided additional capacity to doctors in primary healthcare centres where they are now able to detect and refer mental health cases, and even treat mild cases. This reduces the need for parallel NGO services in the medium to longer term. Moreover, NRC’s work on training stakeholders on refugees’ access to justice contributes to refugees’ ability to obtain documentation for example or seek legal support.

A recommendation for future programming is to capitalise on the opportunities provided through training and capacity building of national actors in specific, to strengthen government systems and implement sustainable programming, particularly in protracted refugee situations.

Output Number and Title		Output 2: Awareness is raised amongst beneficiaries and other community members on protection issues
Output Score		A
Impact weighting (%)	10%	Impact weighting revised since last AR?	No

Output Indicator	Final Logframe Target	Final Result Achieved
2.1 # of direct beneficiaries and community members who received information	81,002	83,978 (104%)

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.
This output reflects activities undertaken by NRC and HI to raise community awareness of protection issues and available services, mainly around legal information (e.g. how to obtain civil documentation) and services available to people with disabilities. The output has achieved its target despite difficulties faced due to lockdowns and movement restrictions throughout 2020. NRC expanded its outreach by providing information through WhatsApp groups or online sessions, while HI relied on its CBR volunteers.
Information provision remains important where agencies not only use it to raise awareness but to inform communities of available services and establish contact with potential beneficiaries. For example, NRC’s sessions are always followed by inviting people to speak to NRC staff if they require any legal consultations. HI also uses this activity to reduce stigma around PwDs and sensitise the community on factors leading to exclusion and attitudinal barriers preventing PwDs from accessing services and being included in their communities.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme
There were no major changes to input costs for this output in the first two years of implementation. These costs were mainly staff costs of those delivering the information sessions and any associated rental or transportation costs. Over the past year, costs related to delivering this output have reduced, mainly due to agencies moving to remote modalities of communication. For example, the cost per beneficiary for NRC to deliver information reduced from $15/person in 2019 to $10/person in 2020. The increased efficiency enabled NRC to reach more people with important information. The effectiveness of remote delivery of this output is still not clear but NRC teams continue engaging closely with beneficiaries in order to receive feedback and adapt as necessary.

Delivery was equitable as sessions included both men and women (reaching an average of 30% men and 70% women), and where partners worked with local organisations to increase reach to different areas. The higher percentage of women reached is explained by men usually being engaged with work during the hours that sessions take place and where it can be seen as the woman’s role to approach organisations for information. It also had a focus on providing information to PwDs and stressed their inclusion in communities and service delivery.

Lessons learned through this output, and recommendations for future programming
A lesson learned through delivering this output is the importance of community-based organisations (CBOs) and engagement with local volunteers to increase outreach and spread awareness. As INGOs often don’t have the capacity or local presence needed to reach many communities, working with local actors ensures a wider reach. Moreover, COVID-19 lockdowns required changes in delivery modalities where quick action and preparation from partners ensured the continuation of services with minimal disruption.

For future programming, it’s important to keep localisation in mind at the programme design stage, and work closely with local actors to reach communities. It’s also recommended that agencies have contingency plans in place for effective remote delivery, alongside feedback mechanisms to be able to receive and respond to feedback on the new and adapted delivery modalities.

Output Number and Title		Output 3: Research is produced to influence advocacy and policy change
Output Score		A++
Impact weighting (%)	10%	Impact weighting revised since last AR?	No

Output Indicator	Final Logframe Target	Final Result Achieved
3.1 Number of periodic reports and policy briefs produced on barriers to rights for refugees in Jordan	8	18 (225%)

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.
In the last year of the programme, NRC produced an additional 9 products, overachieving on this target. Below is the list of reports and policy briefs produced during the programme’s lifetime:
1. Briefing note on the Pardon Law issued in January 2019, and how it affects the legal issues of refugees
2. Findings and Recommendations on Protecting Work Rights of Refugees in Jordan (shared in the 2019 Brussels Conference)
3. Needs assessment of asylum seekers and refugees coming from countries other than Syria
4. Legalising Labour Work Rights and Conditions for Syrian Refugees in Jordan- done jointly with Tamkeen (a local NGO).
5. Policy brief on legal challenges to return that are faced by Syrian refugees- done jointly with UNHCR.
6. A presentation on legal safety for durable solutions presented at an NRC regional donors’ breakfast in December 2019.
7. Recommendations presented, jointly with Tamkeen, at a learning event held by the Swiss Embassy in Jordan; focusing on how to promote decent working conditions for refugees, migrants, and nationals in Jordan and Lebanon.
8. Briefing note on education pathways, looking at education documentation and equivalence between the Jordanian and Syrian education systems.
9. NRC “Quarterly Legal and Policy Update/Returns” April – June 2020.
10. Briefing Note on “NRC information, counselling, and legal assistance (ICLA) legal safety for return preparedness intervention. Analysis of Syrian refugees’ legal safety related needs and NRC ICLA response in Jordan”, June 2020.
11. Joint UNHCR-NRC Briefing note on Syrian refugees in Jordan originating from Dar’aa views on housing, land, and property (HLP) rights, June 2020.
12. NRC Jordan “2020 – 2021 Return Strategy”.
13. Protection Trends Analysis covering July to August 2020
14. Note on unregistered refugees in Jordan
15. Briefing Note titled “Analysis of legal pathways to register death in Jordan”
16. Briefing Note titled “Legal Pathways to Report Absentee and Missing Persons”
17. Returns “Quarterly Legal and Policy Update October –December 2020”
18. Briefing Note on “Forged and Falsified documents” for the NRC Jordan Office

Some of the products (e.g. numbers 6 and 7) may not strictly fall into the description of this output indicator. Nonetheless they are felt to be relevant because they were live advocacy events focusing on policy recommendations from completed products.

Overall, these reports and briefing notes are important sources of evidence but also tools for shaping the overall response by donors and organisations for refugees in Jordan. The emphasis on work rights is feeding into wider discussions and advocacy to improve work rights, and the work related to returns preparedness is a key part of thinking through durable solutions for Syrian refugees. Additionally, the specific internal briefing notes produced by NRC improve the quality of services provided by setting out pathways for often complex legal processes.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme
As this falls under the ‘advocacy’ component of NRC’s VfM framework, it is very difficult to assess its efficiency and economy. The main costs going into the reports are a combination of consultant fees and staff costs related to data collection and analysis. As each piece of work required a different combination of these and reports are designed for different audiences, it is a complex task to measure the efficiency of advocacy work. However, as NRC has exceeded the target using resources budgeted for at the start of the programme without an increase in costs, then we can determine that this output has performed well in terms of VfM. NRC disseminated these products widely to relevant actors such as other donors and NGOs, and utilised them in its programming (for example reaching out to beneficiaries who can benefit from the Pardon Law to support their legal cases), proving their importance to both build evidence and influence to improve the enabling environment for refugees.

Lessons learned through this output, and recommendations for future programming
A lesson learned through this output is having clear agreement with the partner on the definition of advocacy products at the start of the programme to avoid any confusion. Moreover, based on the recommendation from last year’s Annual Review, it’s recommended to agree on a tool to measure the effectiveness of these products more directly; for example, to capture any policy changes as a result of these reports. We have shared an example of this with NRC from another FCDO programme and will apply it for any similar activities in future programming. This will enable us to better capture the direct effects of advocacy and influencing activities.

Output Number and Title		Output 4: Vulnerable persons receive direct assistance, and have increased access to services
Output Score		A+
Impact weighting (%)	60%	Impact weighting revised since last AR?	No

Output Indicator	Final Logframe Target	Final Result Achieved
4.1 # of direct NRC beneficiaries who received (a) legal counselling and (b) direct legal services	(a) 47,000 / (b) 3,600	(a) 50,845 / (b) 4,499 / (109%)
4.2 # of vulnerable people who received comprehensive rehabilitation services	3,600	4,596 (128%)
4.3 # of IMC beneficiaries receiving specialised mental health (MH) and child protection (CP) case management services at static centres and at mobile medical units (MMUs)	5,456	5,541 (102%)
4.4 # IMC beneficiaries receiving the social assistance protection package for three months	300	300 (100%)
4.5 # of most vulnerable people referred by HI to external services (not provided by HI)	1,791	2,667 (149%)

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.
This output covers the specialised services delivered by partners, either directly or through downstream partners in different areas across Jordan. Activities conducted by NRC include legal counselling services as well as legal representation in courts. These are largely related to supporting refugees in obtaining their legal documentation (marriage and birth certificates for example), as well as dealing with housing, land, and property (HLP) rights, and employment disputes. HI services are related to the provision of rehabilitation services to PwDs; this included physio and occupational therapy, as well as the provision of needed assistive devices like wheelchairs or hearing aids. IMC’s activities focused on the provision of mental health (MH) services through psychiatrists and psychologists, and child protection (CP) case management services where children are assessed and supported through counselling or financial assistance where needed. IMC also worked with a local partner to deliver primary healthcare services to remote areas through MMUs, which were also used to provide MH and CP services.
As demonstrated in the table above, partners exceeded expectations of delivery on this output. The COVID-19 lockdown in Jordan temporarily slowed down service delivery but partners were able to deliver some services remotely where possible (e.g. some counselling and case management) and received permits from the authorities to continue important in-person activities like the physical rehabilitation. For output indicators that significantly over-performed:
- Output indicator 4.2: this was a result of large unexpected needs, particularly in Zaatari and Azraq camps where services were delivered by HI’s downstream partner the Nour Al Hussein Foundation (NHF). The accuracy of results reported by NHF were queried and found to be accurate.
- Output indicator 4.5: similar to the above, more beneficiaries than expected needed referrals to external services not provided by HI or its partners. The outreach efforts and community volunteers also contributed to reaching more people than originally planned.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme
These activities formed the core of the intervention under this programme where the business case (BC) identified key cost drivers for all three partners to be staff costs, procurement of medication or assistive devices, and transfers to downstream partners. As the interventions are staff heavy, staff costs represented an average of 50% of the budget across all three partners. This has remained stable throughout the three years of implementation, and partners were able to retain staff during lockdowns where some activities were able to be performed remotely. Partners have also applied competitive procurement methods and sourced items locally to reduce shipping costs where possible.

The partners have also delivered these activities in an efficient way where they maximised outputs with the available inputs. This was slightly affected by COVID-19, but overall efficiency was maintained throughout the three years of delivery. For example, the cost per beneficiary for NRC’s legal counselling services reduced from $40/person in 2019 to $37/person in 2020. This was partly due to savings made on transportation and NRC enhancing remote counselling services. However, the cost per beneficiary for legal assistance increased from $129/person in 2019 to $284/person in 2020. Where legal assistance services continued last year, they were disrupted by court closures and decisions taken by NRC to limit some services of accompanying beneficiaries to the Ministry of Foreign Affairs for document validation to avoid dealing with fraudulent documents issued by third parties. On a more organisational level, HI’s move to consolidate four offices in Jordan into one building has resulted in savings and efficiencies. For example, the reduction of layers within the support teams and the setup of a shared service for the management of the common building of HI (gathering all entities) where the daily management of the building was managed by different logistics teams from different HI entities, it is now managed by a unique team, which allows time and cost efficiency (1 negotiation of 1 contract with 1 supplier rather than multiple negotiations). This was difficult to quantify but HI offices in Jordan collectively made savings on rent costs, for example, by 86% (this is across all the offices and not only the HI office which was managing this particular programme). On IMC’s activities, the cost per beneficiary for the last year of implementation was £212 compared to £384 in year 2 of the programme. Where this was partly due to less spending due to lockdown measures (savings on transportation for example and reaching more beneficiaries due to remote outreach), it was also a result of other donors contributing to IMC’s support costs.

On equity, all partners targeted men and women equally, and provided culturally sensitive settings when needed. Moreover, the programme specifically targeted the most vulnerable people in communities who are suffering from mental health issues or disabilities. Partner outreach activities though the MMU for example has also ensured reaching those in geographical locations with limited services. The move to some online service delivery has also resulted in partners being able to reach a larger number of people. There are evidently some challenges related to remote modalities in terms of access to smart phones or stable internet connections, in which case face-to-face service delivery was prioritised when that was possible.

Overall, the programme delivered value for money throughout the three years of implementation, while providing quality services to the most vulnerable beneficiaries.

Lessons learned through this output, and recommendations for future programming
A lesson learned through this output is the importance of engagement with local organisations and service providers to contribute to the sustainability of service delivery. For example, NRC worked closely with local organisations to build their institutional capacity to deliver legal counselling services. It went beyond traditional training and invested its resources in on-the-job coaching and strengthening support services like finance and HR. Moreover, both HI and IMC worked with and through government services to deliver their activities. IMC mental health services were delivered inside public primary healthcare centres (PHCs) where it used its presence and relationship with the Ministry of Health (MoH) to better integrate primary health with mental health support. Additionally, HI services were all delivered indirectly by local service providers or MoH hospitals where HI’s role focused on technical advice and training. While not captured in the output results, this delivery modality enabled HI to build its relationship with the MoH and work with it and the Ministry of Social Development (MoSD) on strengthening systems for the early detection and intervention (ED/EI) for children with disabilities.

Recommendations for future programming are to focus on the localisation of service delivery where possible and build in elements of system strengthening to support the sustainability and capacity of government services for both refugees and host communities. In a protracted refugee situation such as Jordan’s, this is especially important as we see a trend in declining humanitarian support but continued commitment in development and supporting the most vulnerable.

D: Risk

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.
The overall risk rating of this programme was moderate where it was increased from minor to moderate following a recommendation from the Internal Audit Department (IAD) after a regular Jordan office review. The change was made in January 2020 and the programme was able to deliver within that risk rating. Over the past year, additional risks and challenges were faced, particularly delivery-related risks as a result of the COVID-19 pandemic. Specifically, there was a risk that partners would not be able to operate as planned and deliver activities as a result of lockdowns or movement restrictions, and that momentum on the work being undertaken with the MoH would be lost due to reduced capacity to engage on issues not related to the pandemic. Both those risks were monitored closely and as lockdowns eased activities gradually returned to normal with some delivered remotely. Additionally, we granted HI a no-cost extension (NCE) to allow them enough time to complete the work with the MoH and MoSD where this activity was due to be completed by September 2020, but was extended until the end of the programme in March 2021. As work progressed the risk ratings for these risks were changed from moderate to minor.

Throughout the lifetime of the programme, no other major risks were faced as the context remained stable and we maintained strong oversight of any fiduciary, safeguarding, and reputational risks. We had regular dialogue with partners on mitigation measures, updated them as necessary, and received quarterly reporting on risks and any changes to them.

Due Diligence assessments (DDAs) were conducted for all partners in 2018/2019, including enhanced DDAs (EDDAs) on safeguarding. Recommendations were shared with partners and followed-up. Moreover, all recommendations from IAD’s 2019 audit were completed and actioned.

E: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation
Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency.
All partner reports were submitted in a timely manner and followed agreed templates and sections to report on. Quarterly narrative reports also included financial reporting, updated logframes (including data disaggregation of age, gender, geography), and updated risk matrices. Partners also provided the FCDO with delivery chain risk maps, highlighting the risks associated with working with their downstream partners and how those are being managed. Following review of the reports, we provided partners with feedback and questions, and held quarterly meetings and field visits to verify reporting and monitor the programme. Unfortunately, due to the COVID-19 pandemic, we were not able to conduct field visits during the last year of implementation but continued to have regular discussions and meetings with partners on all aspects of programme delivery.

As part of the financial reporting, partners provided the FCDO with financial forecasts as well as details of any over or underspending on budget lines. Forecasting has been generally accurate but varied during the last year due to the unexpected impact of COVID-19 where previously budgeted activities (e.g. transport costs) were less than forecasted. All partners confirmed spending the allocated budget amounts by the end of the grants in March 2021 and we await final reports to be received at the end of June to make any accrued outstanding payments.

Throughout implementation, we conducted random asset spot checks during field visits or meetings at partner offices. As we were unable to do physical asset spot checks during the last year, we agreed on virtual checks with partners which were completed over Microsoft Teams. Partner teams joined the calls from different delivery locations and we randomly selected items from the asset registers provided by the partners for them to show us on camera and verify using serial numbers or any pre-identified reference numbers. This was successful although not ideal and we were able to verify and locate all randomly selected assets. For assets with staff working from home (laptops, mobile phones), partners provided us with pictures of those assets by email. All partners requested assets be transferred to them after programme closure to be used in continued activities and to enable them to continue supporting vulnerable communities. Their requests were approved by the Development Director after receiving written confirmation from partners on asset use and disposal as per the SMART Rules (now the Programme Operating Framework).

Overall, our close collaboration with partners and regular formal and informal discussions supported the successful implementation of this programme. Continued and transparent dialogue is key for any programmes going forward to ensure any issues are dealt with swiftly and do no impact service delivery or implementation of important programmes. This proved even more important during lockdown where we were unable to meet partners face-to-face and faced with an uncertain environment were able to receive updates on the situation and feed into our analysis of COVID-19 impact on refugees and vulnerable communities. A recommendation on reporting for future programmes is to introduce the 8+3 harmonised reporting model agreed globally to harmonise reporting and avoid any duplication of time and effort by partners when reporting back to different donors.
[note] https://www.harmonizedreporting.com/

VfM was covered in the sections above where the programme demonstrated value for money throughout implementation.

Programme-level approach to monitoring and evaluation
The overall approach to programme-level monitoring and evaluation was referenced in the above section. In addition to that, all three partners conducted external evaluations of their interventions where we had the chance to review and feed into the terms of reference and comment on inception reports before data collection began. This approach worked well where we were able to focus some elements of the evaluations on the sustainability of programming and to what degree that was achieved through the different approaches taken by partners. Main recommendations and lessons from these evaluations were captured in the output scoring sections and will be used to inform any future protection programming. The evaluations can also be shared with relevant teams working in similar contexts or on similar programming.

Moreover, all partners have operational complaints and feedback mechanisms to receive and respond to feedback from beneficiaries. Most comments received are usually around assistance or waiting time between being assessed and receiving services where partner staff explain processes and improve them to enhance the quality of services provided. Accountability to affected populations (AAP) was incorporated into these mechanisms and community volunteers played an important role in creating trust and linkages between communities and the agencies.

This PCR also formed part of the overall monitoring process of the programme, reflecting on its performance and different aspects of the programme cycle.
Date of last narrative financial report	31/01/2021 / Final report pending to be submitted by 30 June 2021	Date of last audited annual statement	NRC: 31 December 2019 / HI: 31 December 2019 / IMC: 30 June 2020
[note] NRC and HI statements due by the end of June 2021 and IMC by March 2022