 Programme Completion Review – Submitted 23 June 2021

Title: East Africa Research Hub – Strategic Research and Evidence Support to Country Office and Regional Research (SCORE Programme)
Final Programme Spend £ (full life): £11,478,174	Review Date:	25 June 2021
Programme Code: 204570	Start Date: 07 July 2014	End Date: 31 March 2021

Summary of Programme Performance

Year	2014/15	2015/16	2016/17	2017/18	2018/19	2019/20	2020/21
Overall Output Score	A	A	A+	A+	A+	A	A+
Risk Rating	Medium	Minor	Minor	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case (and any addendum):	Business case / Addendum
DevTracker Links to all logframes used during programme lifetime:	Logframe

A. Summary and Overview

Description of the programme and what it has achieved

The East Africa Research Hub Strategic Research and Evidence support to FCDO Country Offices and Regional Research was a seven-year programme (2014/2015 – 2020/21) within FCDO’s Evidence Use and Capability Department, under the Research and Evidence Division (RED). The aim of this programme was to support FCDO country offices in Kenya, Tanzania, Ethiopia, Uganda, Rwanda, Somalia, Sudan and South Sudan to use and commission research to 1) inform how we work, 2) generate a robust evidence base for the region on how to improve the lives of the poor, and 3) build capacity to do and use research in the region.

Output achievements

The programme Logframe was updated in December 2018 to better set out output targets for the final years of the programme, which would be centered on the closure of studies. This amendment was approved by the director of the department. Additional changes were made to the Logframe by the SRO in September 2020 to add output targets for the final year of the programme following a yearlong extension from March 2020 to March 2021.The impact and outcome level targets remained unchanged since inception of the programme.

The overall output targets for the programme were met or exceeded throughout its lifetime, and over the programme’s final year (2020/2021), achievements under individual outputs ranged from ‘Met’ to ‘Substantially Exceeded’.

Output 1 targets met and exceeded expectations for the first time in the programme’s third year (2016/17), after which targets were met or exceeded in each subsequent year after that due to Hub’s dedicated and regular engagement with country offices, ensuring the resource it had on offer was understood and made easily available. In the final year of the programme, Output 1, which focused on activities related to generating high quality country-specific research and evidence products, and carried an impact weighting of 40%, achieved an overall A+ (Moderately Exceeded) score.

With respect to indicator 1.1, the programme completed 6 country-specific studies against a target of 4, moderately exceeding expectation [A+].

With respect to indicator 1.2, the programme published 2 journal articles and 19 other open access research outputs (including study reports, policy briefs, rapid evidence synthesis reports, and 2 blogs) against a target of 2 and 6 respectively, substantially exceeding expectation [A++].

With respect to indicator 1.3, the programme set out to achieve a score of over 90% with regards to the percentage of research projects with a credible and appropriate Research Uptake Strategy and tangible uptake of research evidence (with examples). The programme met expectation [A], achieving 100%.

Output 2 targets have never fallen short of expectation over the lifetime of the SCORE programme. The targets were moderately exceeded in four years and substantially exceeded in one year of the programme’s lifetime. Regionally commissioned studies were consistently well received, with interest and uptake persisting to date. In the final year of the programme, Output 2, which focused on activities related to generating high quality regional evidence products relevant for policy and programming in East Africa, and carried an impact weighting of 50%, achieved an overall A+ (Moderately Exceeded) score.

With respect to indicator 2.1, the programme completed 8 regional research studies against a target of 2, substantially exceeding expectation [A++].

With respect to indicator 2.2, the programme published 3 journal articles and 10 other open access research outputs (including study reports, policy briefs, rapid evidence synthesis reports, and 1 blog) against a target of 2 and 6 respectively, moderately exceeding expectation [A+].

With respect to indicator 2.3, the programme set out to achieve a score of over 90% with regards to the percentage of research projects with a credible and appropriate Research Uptake Strategy and tangible uptake of research evidence (with examples). The programme met expectation [A], achieving 100%.

Output 3 targets also never fell short of expectation, with targets moderately exceeded on two occasions, substantially exceeded in its inception year, and met in four years during the programme’s lifetime. The Hub’s offer of technical assistance, training, and brokering has maintained interest and awareness from country offices, ensuring this output remained with an A to A++ score. In the final year of the programme, Output 3, which focused on training and technical support provided by the Hub to country office and policy teams, and carried an impact weighting of 10%, achieved an overall A (Met) score.

With respect to indicator 3.1, the programme facilitated 6 presentation and/or training sessions to FCDO country offices on research and evidence against a target of 6, meeting expectation [A].

With respect to indicator 3.2, the Hub provided substantive technical support 9 times to FCDO country offices, centrally managed programmes, or cross-UK government, against a target of 8, moderately exceeding expectation [A+].

The SCORE programme has delivered on its output targets owing to effective collaboration between the EARH and the Fund Manager in responding to demand consistently over the lifetime of the programme. The EARH and PwC have worked as one team in every respect, making decisions together, and adapting to change and lessons learned, which has allowed a critical pivot in response to new challenges such as the COVID-19 pandemic. The importance of research and evidence produced being effectively disseminated and communicated to ensure 1) an increased understanding and use of evidence by policymakers, 2) that use of evidence becomes embedded in processes, systems, and institutional working culture, and 3) that knowledge from robust evidence is used directly to inform policy or programming, has been valued and upheld throughout the programme’s lifetime.

Major lessons learned, evidence generated and recommendations

Virtual stakeholder engagement, its benefits, and new opportunities

With the COVID-19 pandemic in full swing in East Africa by around May 2020, many projects were coming to an end, and in-person meetings were no longer possible. The Hub and its suppliers proceeded to engage stakeholders virtually, finalising projects in a timely manner despite this new approach and associated challenges. Virtual events allowed for broader engagement with internal and external colleagues, since there were no additional cost implications or logistical arrangements needed as would be the case for in-person events. A lot of the field work that could not be done due to the COVID-19 pandemic required a move to increased use of electronic survey tools and virtual interviews, which was sufficient to deliver against the Hub’s commitments. Further, savings realised from reduced field work were put towards enhancing research uptake through supporting development of targeted and more visually appealing outputs and reproductions. Virtual engagements also allowed the Hub to conduct country office outreach without travel, providing the department with significant savings. The pandemic provided the programme with new commissioning opportunities, specifically in its final year, with many country offices seeking context specific evidence on COVID-19 and its impacts or mitigating measures. The pandemic created an emergency response situation, therefore the Hub proactively moved to identify research questions that would be of interest to key stakeholders and policymakers in the fight against COVID-19. This response by the Hub was very well received by country offices and our partners .

Cross-organisational partnerships and expertise

When the COVID-19 pandemic hit East African countries, there was increased demand from country offices for high quality research and evidence products related to the pandemic. With this emerging need, evidence requests, and funding were reprioritised within the Fund. Along with this, the EARH engaged with other FCDO departments such as the Africa Regional Department (ARD) and teams within the Research and Evidence Division (RED) in order to more aptly meet the evidence needs from offices – specifically leveraging on work led by the RED Science Cell, ensuring coordination and avoiding the duplication of work already done on COVID epidemiology and modelling. The EARH recommends that future programmes and teams also pursue these kinds of partnerships and flexibilities for efficiency and effectiveness.

Cross-organisational partnerships and expertise were leveraged even before the pandemic, as the EARH jointly planned an outreach visit to FCDO Rwanda alongside a RED Evaluation and Results advisor. This allowed the delivery of a joined-up training on the new evaluation strategy, the DiME programme, and CEDIL’s Evidence Gap Maps offer, significantly increasing impact of delivery to the country office. The EARH recommends that future programmes and teams maintain such good practice and leverage the deep expertise available in other FCDO departments and teams.

Local and regional market capacity building

A reputational risk arose in early 2018 when a local paper criticised the EARH for seemingly awarding contracts to solely international suppliers, and not engaging local/regional suppliers. The EARH and the Fund Manager (PwC) responded to this risk by commissioning an evaluation to better understand the extent of local and regional market engagement with the Fund. At the time only 2 of 23 commissioned studies were led by a local/regional supplier, with issues such as a lack of understanding of Value for Money (VfM) and Terms of Reference requirements, weak partnership profiles to leverage on, and certain research topics not aligning with the pervasive issues and topics in the local and regional context, coming to the fore. The EARH brought in Prof. Charlotte Watts, FCDO’s Chief Scientific Advisor, to lead a local/regional supplier engagement session, aimed at jointly identifying recommendations that could address the challenges local and regional suppliers faced, while building their capacity. A major output from this engagement was the implementation of Early Market Engagement (EME) workshops held before studies were launched. During such events, views and inputs from local and regional suppliers were sought, partnerships were formed, and training on how to successfully bid for studies or increase research uptake, was provided. In addition to this, other key aspects implemented included anonymously sharing highlights from successful bids with unsuccessful bidders in order for them to understand how to improve their bids in future, and revising the Fund’s scoring criteria, with favourable consideration given to proposals with local leadership (whether solely or collaboratively) and good mix of local and international expertise.

Together, these activities presented local and regional suppliers with upfront benefits which brought in greater inclusivity and a better blend of suppliers, with positive impact on the programme’s delivery, resulting in a number of programme targets being surpassed. There was notable participation of local and regional suppliers, moving up from 10% in 2016/2027 to 70% by the end of the programme in 2021. While the EARF was not designed to provide this capacity strengthening function with suppliers, it has resulted in great successes for the programme. For example, local suppliers did not understand the concept of VfM very well. The Fund responded to this by providing examples of VfM that could be used in strengthening a proposal, and this guide note was posted on the Fund’s supplier portal to improve understanding on VfM as an integral part of their bids. The EARH recommends that future programmes and teams scope out their local and regional suppliers to assess their level of expertise and areas that need development so that capacity building can be made available as part of the programme’s delivery, resulting in more inclusion of local and regional suppliers.

Foundation to a new programme

Delivery of the SCORE programme has required consideration of the best approaches to ensure a high quality, efficient, cost-effective, and demand-responsive service for our country offices. Employing a Fund Management model has allowed the EARH to embed expertise including: establishment of an extensive network of suppliers including local/regional experts; knowledge of legal frameworks for procurement in the region; programme, risk and due diligence management; monitoring and learning; robust contextual quality assurance; and, capacity strengthening on communication. This model has allowed specialists within the Hub to focus on technical aspects of delivery. Through the Hub's engagement in the core working group, our learnings are informing establishment of a larger Evidence Fund (EvF) programme, which will combine delivery for several Hubs within a single streamlined platform.

How this report was conducted

This report was conducted by reviewing the performance of the programme over its lifetime and in particular its performance in its concluding year (2020/2021), assessing whether Logframe targets across impact, outcome, and output levels were achieved, collating and capturing these narratively and stipulating key lessons and evidence on what worked and what did not work, along with stating recommendations for any similar future programmes. Specific division of labour and timelines for the completion of each section in the Programme Completion Review (PCR) were outlined. The SCORE programme team provided the narrative for the Theory of Change and Outcome Assessment (Section B), Detailed Output Assessment and Scoring (Section C), Risk (Section D), and Programme Management (Section E). Along with this, an external candidate provided the Summary and Overview (Section A).

Actions following approval of this report

There are no outstanding actions or pieces of work related to this programme and upon completion of this Project Completion Review.

An VfM assessment of FCDO’s demand-responsive research programmes in East Africa and South Asia has been commissioned under the Evidence Fund Programme to understand the extent to which both Hubs have responded to the essential research needs of country offices within the resourcing structures and funding modalities available to the two. This assessment is expected to be finalised by October 2021.
## B: Theory of Change and Outcome Assessment

	Starting Point	Final Result
Budget	£ 9,812,000	£11,478,174 (with additional funds drawn from the Evidence fund)
Timeframe	07 July 2014 to 31 March 2020	07 July 2014 to 31 March 2021
Outcomes	1-New and existing evidence forms part of the debate around country office operational plans, business cases, programmes, policy positions and other decision-making processes. / 2-National and regional policymakers and practitioners’ debate and are more receptive to evidence-based challenge and debate.	Substantially exceeded outcome 1 targets. No change was made to the indicator during the lifetime of the programme. / Moderately exceeded outcome 2 targets. No change was made to the indicator during the lifetime of the programme.

Overall assessment of programme outcomes, sustainability and VfM

The VfM proposition for this programme has remained strong, and final Logframe outcome and impact level targets exceeded or met (respectively) by the final year. This is true even while grappling with the challenges brought on by the COVID-19 pandemic.

The programme complied with the 2014 Gender Equality Act commitments. Consideration was given to improving the beneficial impact on women and girls, and reporting used disaggregated results by sex where appropriate. Specific to our work in governance and prosperity, we have sought to test the hypothesis that increased representation of women in government has a positive influence on human and economic development at both sub-national/county and national levels. We have delivered research on the involvement of Somali women in leadership positions in government and political structures, and explored the representation and influence of women as leaders in Kenya, including women’s political inclusion in Kenya’s devolved political system. These insights and discussions are premised on an understanding that we must ‘leave no one behind’, that is, ending extreme poverty in all its forms and reducing inequalities among individuals and groups. Further details on VfM and gender equality are provided in Section E of this report.

Related to sustainability and supplier equity, a core objective of the SCORE programme was to strengthen research capacity and systems in East Africa. By 2018, it was realised that only two of the 23 commissioned research projects had been awarded to local/regional research organisations (as lead). These local/regional organisations were however participating in one or more consortia across the contracts awarded. This precipitated an evaluation of the local/regional supplier market’s engagement with the Fund. The analysis identified several issues including a lack of understanding of the Terms of Reference, bidding, and budgeting requirements, alongside weak partnership profiles to leverage on. Several recommendations were also put forward on ways we could address these challenges. We have since implemented various strategies including: attending strategic conferences and workshops in the region to raise the profile of the Fund and the SCORE programme; targeted market engagement with local/regional research organisations ahead of launching calls to provide information and respond to their questions as well as provide training on, for example, tips for submitting a winning proposal or enhancing research uptake; providing inclusive supplier feedback by embedding highlights from winning proposals to unsuccessful bidders; and, revising proposal scoring criteria with favourable consideration given to those with local leadership/expertise (solely or collaboratively). A direct consequence of these actions has been a significant increase in the participation of local/regional suppliers, moving up from 10% in 2016/2017 to 70% by programme closure in 2021. Further, the Evidence Fund Programme, which will Fund the work of the Hub moving forward, strongly signals a requirement that any Lead Supplier will need to ensure extensive local/regional supplier market engagement, inclusion, and equitable partnerships.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators.

This programme was designed to enhance the generation and use of evidence by country offices in the region, relying on existing evidence (producing and supporting rapid evidence synthesis products that are high quality) and/or new evidence (commissioning country-specific or regional research studies) to address key research and policy priorities in East Africa. Providing technical assistance, supporting skills and capacity development, and brokering departmental and institutional relationships and partnerships to enhance evidence use, are other key functions of the programme and the hub team. We have valued the importance of research and evidence produced being effectively disseminated and communicated, both internally and externally, to ensure: that there is increased understanding and use of evidence by policymakers; that use of evidence becomes embedded in processes, systems, and institutional working culture; and, that knowledge from robust evidence is used directly to inform policy or programming.

There were no changes in the programme’s theory of change in the past year (or since inception), and the programme has achieved expected outcomes and impact. Assessment of the impact of research is done according to the Evidence into Action framework for valuing the use of evidence that classifies them as:
- Transparent use: Increased understanding and transparent use of (bodies of) evidence by policymakers.
- Embedded use: No direct action is taken as a result of the evidence, but use of evidence becomes embedded in processes, systems and working culture.
- Instrumental use: Knowledge from robust evidence is used directly to inform policy or programme.

To enhance dissemination and research uptake process, we have been implementing an approach that requires our researchers/suppliers to map out their key stakeholders and level of intended engagement and expected impact right at the start of the study, and continually update this document throughout the lifetime of the study. We also reach out to our researchers/suppliers six months after study closure to find out if there have been additional instances of uptake and impact based on their study findings and recommendations. Achievement of the programme outcomes is maximised by allocating available resources towards activities and outputs with the greatest impact. As a result of these actions, we have realised notable outcome and impact level successes in the last year of the programme. The Fund has also recorded beneficiary videos showcasing how selected research findings have impacted programming and policy in the region.

The programme has demonstrated high impact in the region. At outcome level, the programme has several strong examples of uptake of research findings both within FCDO and across the UK government, and by national and international decision-makers. There have been a total of 22 documented examples (against a target of 9 cumulatively by the end of the programme) of uptake of research findings internally, substantially exceeding expectations [one in 2014/15, four in 2016/17, six in 2017/18, two in 2018/19, four in 2019/20, and five in 2020/21]. There have also been a total of 10 documented examples (against a target of 9 cumulatively by the end of the programme) of uptake of research by national and international decision-makers, moderately exceeding expectations [one in 2015/16, two in 2016/17, one in 2017/18, two in 2018/19, two in 2019/20, and two in 2020/21].

Outcome(s)	Milestone(s) for this review	Progress
Uptake of research findings by FCDO advisors in operational plans, business cases, and other decision-making documents.	9 documented examples (cumulative)	Substantially Exceeded Expectation [A++]: 22 documented examples to-date, 5 reported in 2020/21
Uptake of research findings by national and international decision-makers	9 documented examples (cumulative)	Moderately Exceeded Expectation [A+]: 10 documented examples to-date, 2 reported in 2020/21

Outcome-level achievements in 2020/21 on uptake of research findings internally, include:

A technical report by the Learning and Monitoring Programme Somalia (LAMPS) on Covid-19 Effects in FCDO Programmes in Somalia presented results from a deep-dive into the impact of Covid-19 programming and pivots, providing lessons and learning for improvements. Further, technical assistance on monitoring and evaluation provided to programmes and implementing partners allowed for course corrections to achieve planned outputs, results, and outcomes. These are examples of [embedded use of evidence].

A rapid evidence synthesis on Bail conditions in the criminal justice systems in Kenya, Uganda, Rwanda and Tanzania for the Tanzanian office provided a comparative assessment of bail condition provisions in these countries, allowing advisers to identify gaps that they could support in strengthening, an example of [instrumental use of evidence].

A rapid review on Water infrastructure in Fragile and Conflict Affected States for the Somalia office provided practical measures that could be taken to address these vulnerabilities and make water systems in urban and peri-urban areas more resilient, directly supporting development of FCDO Somalia's Urban Resilience Programme, an example of [instrumental use of evidence].

A rapid review on Income-generating activities (IGAs) and climate change vulnerabilities for the Somalia office explored means of adaptation and mitigation of the detrimental effects of extreme climatic events in countering the impact on livelihoods, directly supporting development of FCDO Somalia's Urban Resilience Programme, an example of [instrumental use of evidence].

Our regional Politics of Information and Analysis study team provided a helpdesk service to country office advisers including evidence synthesis and learning support regarding food security and nutrition diagnostics in the context of Covid-19 in humanitarian crises situations. This work directly influenced discussions and programming decisions in several East African countries and beyond (Yemen, Afghanistan, Nigeria, DRC, and the Sahel region), an example of [instrumental use of evidence].

On uptake of research findings by national and international decision-makers, achievements in 2020/21 include:

Results from our study on Understanding the Local and National NGO Sector in South Sudan were disseminated in Juba and separately in London, and deliberated by a wide range of actors from international and national humanitarian organisations/NGOs, UN agencies, think tanks, and donors, allowing them to consider options for localising humanitarian aid during armed conflict, an example of [transparent use of evidence].

Findings from Mortality Studies in Humanitarian Crises in South Sudan, Somalia, and Nigeria are feeding into high level conversations in-country, including plans by the lead humanitarian adviser in FCDO Nigeria to include the findings in discussions between G7 countries and the UN’s Inter-Agency Task Force in Nigeria, on their mutual famine prevention initiatives, an example of [instrumental use of evidence].

At impact level, there have been a total of 8 documented examples of new evidence-informed policy, programmes, or practice in the region as a result of EARH-funded research, against a target of 8 research impact cases cumulatively by 2020/21, meeting expectations [three examples in 2017/18, two in 2018/19, one in 2019/20, and two in 2020/21].

Impact	Milestone(s) for this review	Progress
Number of new evidence-informed policy, programmes and practices in the region informed by EARH funded evidence.	8 research impact cases (cumulatively)	Met expectation [A]: 8 research impact cases to-date, 2 in 2020/21

Impact-level achievements in 2020/21 include:

Community Approaches to Epidemic Management in South Sudan: This study documented how communities have created tried and tested systems and structures to control the spread of epidemics and infectious diseases in the country through management, isolation, and hygiene. Designed as iterative research, incoming data was synthesised, analysed, and discussed on a weekly basis by an FCDO South Sudan-facilitated Reference Group made up of CDC, South Sudan Red Cross, UNICEF, REACH, and ECHO/USAID. Mid-way through the study, the Red Cross used the research findings to adapt their approach to working with communities on the Covid-19 response, an example of instrumental use of evidence].

Serosurveillance Studies of the COVID-19 Epidemic in Kenya: The findings from this work were shared during monthly review meetings hosted by the Ministry of Health National COVID-19 taskforce and Emergency Operations Centre, and directly supported the government’s decisions and response with a view to protect the most vulnerable while keeping Kenyan society running. Further, a team from the Ministry of Health Public Health Emergency Operations Centre, Presidential Policy and Strategy Unit, and Kenyatta National Hospital visited the research leads (October 2020) to discuss the findings and engage in discussions around strengthening collaborations and translating the research. Data from the different workstreams fed into ongoing modelling work nationally to provide more robust predictions of infection and disease spread, and was also linked to data on hospital capacity, access, and population vulnerabilities, to better inform exploration of a range of control measures at county level. These are examples of [instrumental use of evidence].

## C: Detailed Output Assessment

Output 1 Title:	Research and evidence products are generated that are high quality and relevant to country offices in East Africa.
Output Score:	A+
Impact weighting (%):	40	Weighting revised since last AR?	No

Output Indicator	Logframe Target 2020/21	Results Achieved in 2020/21
1.1 Number of country office research products commissioned or completed over the review period.	4 country office research projects completed	Moderately Exceeded Expectation [A+]: 6 completed country-specific studies in 2020/21
1.2 Number of tangible research products, including outputs generated from the K4D helpdesk service (i.e. peer reviewed and published journal articles + number of other published research outputs which comply with our open access policy (e.g. reports and policy briefs). [RED Results Indicator 2.1 and 2.2].	2 published journal articles + at least 6 other published research outputs which comply with our open access policy (e.g. reports and policy briefs).	Substantially Exceeded Expectation [A++]: 2 journal articles + 19 other published open access research outputs (e.g. study reports, policy briefs, rapid evidence synthesis reports, and 2 blogs)
1.3 Percentage of research projects with a credible and appropriate Research Uptake Strategy and tangible uptake of research evidence (with examples) [Note: Score programmes 0,1,2 and the indicator is the number that score 1 or 2/total N. RED Results Indicator 4.1].	Over 90%	Met Expectation [A]: 100%

Output 1 focuses on the activities related to generating high quality country-specific research and evidence products. In the final year of the programme, a key focus for the team was on closure of studies by March 31st.

INDICATOR [1.1]: Number of closed country-specific research projects

We moderately exceeded the requirement for this indicator, with six country-specific research projects completed in 2020/21, against a target of four. Details of the completed studies are:

South Sudan: Understanding the Local and National NGO Sector in South Sudan, a study that investigated the historical, political, social, geographical, and ethnic dynamics influencing NGOs and their operating principles, including how they have developed institutionally.

South Sudan: Community Approaches to Epidemic Management in South Sudan, a study that documented how communities have used indigenous knowledge and structures to control the spread of epidemics and infectious diseases in the country through management, isolation, and hygiene.

Kenya: Serosurveillance Studies of the COVID-19 Epidemic in Kenya, a series of linked seroepidemiological studies to monitor, understand, and inform the COVID-19 response in Kenya by using convenient samples of the population to measure SARS-CoV-2 antibody prevalence.

South Sudan: Livestock Economy in South Sudan, a study that explored the importance of livestock to livelihoods and how this has changed over time; examined the state of livestock markets and how they are evolving; and, explored future prospects for the livestock economy in the country.

South Sudan: Understanding of Youth, Violence and Livelihoods in South Sudan, a study that explored how young people make decisions about pursing violent or conflict-based livelihoods or not; the livelihood options available to young people in South Sudan; and, capacities for peace, sources of trust, association, and influence.

Somalia: Covid-19 Effects on FCDO Programmes, a study commissioned to understand the effects of COVID-19 on FCDO interventions in Somalia, including how partners have used evidence to adapt their monitoring and evaluation systems.

Demand for research support from individual country offices remained high, with formative work funded in support of an innovative approach to estimating cattle herd sizes using satellite images, an approach gaining interest from other countries such as Kenya. Ongoing supports for county-specific research are being through the Evidence Fund programme.

INDICATOR [1.2]: Number of published research outputs

In the past year, 2 academic journal articles and 19 other published research outputs (including 2 blogs) which comply with the open access policy, have been produced against a target of two and six respectively for country specific studies, substantially exceeding expectations. Details of the study outputs and some examples of research uptake are summarised below:

South Sudan: Understanding the Local and National NGO Sector in South Sudan

Study outputs included:
- A research report on Localising humanitarian aid during armed conflict: Learning from the histories and creativity of South Sudanese NGOs
- A policy brief on Localising humanitarian aid during armed conflict: Learning from the histories and creativity of South Sudanese NGOs
- A blog post on What shapes national NGOs and faith-based organisations in South Sudan?

Dissemination/uptake: A dissemination event was held in Juba on 11th March 2020, where the research was presented the findings and learnings, with a representative from the Norwegian Refugee Council acting as chair. This was followed by discussions with participants. The event was well attended by a wide range of actors from international and national NGOs, UN agencies, and donors. A second dissemination event was held at the LSE in London on 23rd January 2020. It was attended by representatives from a number of London-based international humanitarian organisations, think tanks, and donor agencies, allowing them to further deliberate the findings of the report. Both are examples of [transparent use of evidence].

South Sudan: Community Approaches to Epidemic Management in South Sudan

Study outputs included:
- A manuscript on Community epidemic management strategies and Covid-19 in South Sudan
- A mid-point briefing on Community Approaches to Epidemic Management in South Sudan
- A report and summary on Community Approaches to Epidemic Management in South Sudan: Lessons from Local Healthcare Systems in Tackling Covid-19

Dissemination/uptake: This study was disseminated and discussed during the 4th session of the SCORE End-of-Programme virtual event (March 16th and 17th 2021), which drew great participation from FCDO, OGDs, and external experts, with between 80 and 110 attendees for each of the 4 sessions covering open societies and democratic institutions, security and conflict resolution, economic development and prosperity, and Covid-19 and global health security. The sessions were moderated by senior colleagues and thought leaders including Nikolai Hutchinson (senior governance advisor, FCDO); Charlotte Morris (senior conflict advisor, FCDO); Eric Olanya (Uganda Country Director, DIT); and, Chris Lewis (Deputy Chief Scientific Adviser and Head of Profession for Health, FCDO). This is an example of [transparent use of evidence]. The suppliers were also invited to present the study findings at the virtual WHO global consultation on the 31st of March 2021 titled “Community-centred responses to health emergencies: progress, gaps and research priorities”, and example of [transparent use of evidence].

Kenya: Serosurveillance Studies of the COVID-19 Epidemic in Kenya

Study outputs included:
- A manuscript on Seroprevalence of anti–SARS-CoV-2 IgG antibodies in Kenyan blood donors
- A policy brief on a Preliminary report of SARS-CoV-2 antibody prevalence among blood donors in Kenya, June 2020
- A policy brief on the Status of the COVID-19 Pandemic in Kenya: Evidence from serological and clinical surveillance, and predictive modelling, August 2020
- A policy brief on the Status of the COVID-19 pandemic in Kenya: Evidence from national case-based surveillance, serosurveillance and hospital-based clinical surveillance, October 2020
- A policy brief on Seroprevalence of SARS-CoV-2 among truck drivers in Kenya, January 2021

Dissemination/uptake: The findings from this work directly supported the Government of Kenya’s Covid-19 response through engagement with the Ministry of Health National COVID-19 taskforce and Emergency Operations Centre; have fed into ongoing modelling work nationally to provide more robust predictions of infection spread and potential control measures; and, resulted in strengthened collaboration of response initiatives. These are examples of [instrumental use of evidence]. Globally, this study and its findings were a special focus in the WHO Weekly Epidemiological Update on 09th March 2021, an example of [transparent use of evidence], and the findings were further disseminated during the 4th session of the aforementioned SCORE End-of-Programme virtual event, an example of [transparent use of evidence].

South Sudan: Livestock Economy in South-Sudan

Study outputs included:
- Understanding the Livestock Economy in South Sudan: Field study findings
- Understanding the Livestock Economy in South Sudan: Briefing paper
- Strengthening South Sudan’s Livestock Sector: Discussion paper
- Food and nutrition matters: Discussion paper
- South Sudan’s lost decade: Discussion paper

Dissemination/uptake: A webinar on Understanding the Livestock Economy in South Sudan (18th March 2021) was held to disseminate findings on the importance of livestock to livelihoods and the wider economy in South Sudan as well as encourage discussion on the future prospects for the livestock economy, helping inform contemporary investment choices in the livestock sector, an example of [transparent use of evidence].

South Sudan: Understanding of Youth, Violence and Livelihoods in South-Sudan

Study outputs included:
- A research report: South Sudan: Youth, Violence and Livelihoods
- A policy brief on Is there a youth livelihoods crisis in South Sudan
- A blog post on Youth, livelihoods and COVID-19 in South Sudan

Dissemination/uptake: The findings from this work were shared and discussed during the 2nd session of the aforementioned SCORE End-of-Programme virtual event, an example of [transparent use of evidence].

Somalia: Covid-19 Effects on FCDO Programmes

Study outputs included:
A technical report by Learning and Monitoring Programme Somalia (LAMPS) on Covid-19 Effects in FCDO Programmes can be found on Vault, and is intended for internal use only.

Dissemination/uptake: LAMPS delivered two separate streams of work which supported programming in FCDO Somalia. The first was technical assistance, which was provided to programmes and implementing partners who required monitoring and evaluation support for specific tasks or areas of work (such as theory of change or Logframe development), particularly as relates to Covid-19 effects on their programmes and implications on achieving planned outputs, results and outcomes. Secondly, LAMPS provided a two phased deep-dive study looking at the impact of Covid-19 on programming including how, and how effectively programmes had been able to pivot at the beginning of the pandemic. This study provided lessons and learning across the portfolio as well as giving an overview of the impact of Covid-19 on FCDO Somalia programming. Both are examples of [embedded use of evidence].

Knowledge-for-Development evidence synthesis reports: The EARH team receives requests for evidence support from country offices. A number of these requests are addressed by commissioning rapid evidence synthesis through the K4D help-desk service. The EARH team works with country offices to help refine their research questions prior to commissioning, resulting in more useful reviews. In the past year, they included:

For Tanzania: Bail conditions in the criminal justice systems in Kenya, Uganda, Rwanda and Tanzania [7 August 2020]. This rapid literature review found evidence of varied bail conditions in Kenya, Uganda, Rwanda, and Tanzania. The African Charter, which all the states have ratified, supports the right to bail, as do other international instruments. Most of the countries surveyed allow bail, but conditions vary as do practical applications. This rapid review provided the evidence for a comparative assessment of bail condition provisions in East African countries, allowing the Tanzanian office to identify gaps where they should seek to offer support to strengthen, an example of [instrumental use of evidence].

For Somalia: Water infrastructure in Fragile and Conflict Affected States [11 November 2020]. This This rapid review examined evidence on the key vulnerabilities in the water infrastructure system in urban and peri-urban areas in FCAS, providing practical measures, including nature-based solutions, that could be taken to address these vulnerabilities and make water systems in urban and peri-urban areas in FCAS more resilient (particularly to climate change impacts). This was a first research question to provide evidence for the development of FCDO Somalia's Urban Resilience Programme, an example of [instrumental use of evidence].

For Somalia: Income-generating activities (IGAs) and climate change vulnerabilities [01 December 2020]. Climate change has affected a number of IGAs for vulnerable groups, such as low-income urban and peri-urban dwellers, women, youth, and disabled people. This rapid review explored means of adaptation and mitigation of the detrimental effects of extreme climatic events in countering the impact on livelihoods. This was a second research question to provide evidence for the development of FCDO Somalia's Urban Resilience Programme, an example of [instrumental use of evidence].

INDICATOR [1.3]: Research projects with a credible and appropriate Research Uptake Strategy

All country-specific studies are required to have an uptake strategy as part of their deliverables, that is approved by the technical steering panel for each study. As such, performance against this indicator has and consistently meets expectations.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

During its lifetime, the SCORE programme delivered a total of 39 studies, 22 of which were country-specific, and 17 of which had a regional focus. The Fund out-turned a total budget of £ 11,478,174, of which £ 3,201,872 was used to deliver country-specific and £ 7,127,438 for regional studies. A total of £ 1,048,864 was used in management fees and the balance for research support activities including communication and external peer reviewer engagement.

Output 1 targets were moderately not met [B] in 2014-15 and 2015-16, met [A] in 2017-18, and moderately exceeded [A+] in 2016-17, 2018-19, 2019-20, and 2020-21. In the initial years, while relationships with country office teams were being established, it took time before knowledge and awareness of the Hub and its resource and expertise was well understood and taken up. This has since been remedied by dedicated and regular engagement with country offices, including during in-person outreach (or more recently, virtual) visits to individual countries.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

The VfM proposition for this output remained strong, including during the past 2 years, even while grappling with the challenges occasioned by the COVID-19 pandemic. We have ensured that research and evidence products are generated that are of high quality and relevant to country offices in East Africa. Further details on VfM are provided in Section E of this report.

The programme complied with the 2014 Gender Equality Act commitments. Consideration was given to improving the beneficial impact on women and girls, and reporting used disaggregated results by sex where appropriate. Further details on gender equality are provided in Section E of this report.

Lessons learned through this output, and recommendations for future programming

There are two related lessons and recommendations identified in the last year in the course of delivering this output. The first, is around the importance of continuing to leverage on a collaborative approach with teams in RED, ARD, and more recently, Research Analysts, to strengthen our offer of support to country offices in a more rapid/responsive way, and with economic constraints coming to bear. The second, is that when possible, it will be crucial to maintain a good practice of joining up with events or visits scheduled by other teams when planning in-person or virtual country office outreach visits, to maximise on the deep expertise available across RED, the HoPs, and others.

A third lesson and recommendation is that in the implementation of country-specific studies, opportunities exist for big-picture perspectives and synergies between studies and/or with other in-country programmes operating under similar themes. In Juba, we brought together researchers working on our Understanding the Livestock Economy in South Sudan study, with colleagues working on our Youth, Violence and Livelihoods in South Sudan study, as well as the UK Peacebuilding Opportunities Fund, to develop a joint discussion paper on conflict in South Sudan. We also linked researchers working on two separate studies on Localisation and Covid-19 in South Sudan and in Somalia for a joint dissemination on localisation in Africa.

We have continued to share our learnings and recommendations with the larger Evidence and Capability department, and are feeding them into development of the Evidence Fund programme, which will combine delivery across RED’s Regional Hubs moving forward.

Output 2 Title	Regionally specific research and evidence products are generated that are high quality and relevant to programming and policy in East Africa.
Output Score	A+
Impact weighting (%)	50		Impact weighting revised since last AR?		N

Output Indicator		Logframe Target 2020/21		Result Achieved 2020/21
2.1 Number of regional specific research products commissioned or completed and closed over the review period.		2 regional research projects completed		Substantially Exceeded Expectation [A++]: 8 regional research studies completed in 2020/21
2.2 Number of tangible research products, including outputs generated from the K4D helpdesk service (i.e. peer reviewed and published journal articles + number of other published research outputs which comply with our open access policy (e.g. reports and policy briefs). [RED Results Indicator 2.1 and 2.2].		2 published journal articles + at least 6 other published research outputs which comply with our open access policy (e.g. reports and policy briefs).		Moderately Exceeded Expectation [A+]: 3 published journal articles + 16 other published open access research outputs (e.g. study reports, policy briefs, rapid evidence synthesis reports, and 1 blog)
2.3 Percentage of research projects with a credible and appropriate Research Uptake Strategy and tangible uptake of research evidence (with examples) [Note: Score programmes 0,1,2 and the indicator is the number that score 1 or 2/total N. RED Results Indicator 4.1].		Over 90%		Met Expectation [A]: 100%

Output 2 focuses on the activities related to generating high quality regional evidence products relevant for policy and programming in East Africa. For this final year, the target was closure of two regional studies by March 31st.

INDICATOR [2.1]: Number of completed regional research projects

Eight regional research study were completed out of a target of two for this year. Four of these studies fall under the urbanisation theme and represent EARH’s largest research contracts, generating evidence for six countries in East Africa (Kenya, Tanzania, Uganda, Ethiopia, Somalia, and Sudan). Details of all completed and closed studies are:

Spatial Inequality in Times of Urban Transition: Complex Land Markets in Uganda, Tanzania, and Somaliland, a study which aimed to understand how land markets distribute the benefits and burdens of transactions across different social groups and key stakeholders involved, to help design urban policies and build more responsive institutions.

A Systems Approach to Air Pollution in East Africa (Kenya, Uganda, and Ethiopia), a study which brought together leading East African and UK researchers in air pollution, urban planning, economic geography, public health, social sciences, and development studies to provide a framework for improved air quality management in East African cities.

Shelter Provision in East African Cities: Understanding Transformative Politics for Inclusive Cities in Nairobi, Hawassa, and Mogadishu, a study which involved a comparative analysis of systems of shelter provision and a multi-sectoral assessment of systems of land-for-shelter, housing, finance, and basic services.

The Urban Land Nexus and Inclusive Urbanisation in Dar es Salaam, Mwanza, and Khartoum, a study which adopted the urban land nexus approach and political economy concepts to provide entry points for examining urban land in three cities in East Africa.

Key influences in the Horn of Africa from Middle Eastern Gulf States and Turkey, a study whose overarching aim was to examine the underlying dynamics and factors underpinning the increased interest and engagement in the Horn of Africa by several Gulf and Middle Eastern States and non-state actors. It explored the nature of security, economic and socio-cultural interactions between state and non-state actors in the Horn of Africa and the Gulf and Middle Eastern States; what these interactions mean for states in the Horn of Africa; and, the nature and implications of these interactions for the Middle Eastern and Gulf states themselves.

Mortality Studies in Humanitarian Crises in South Sudan, Somalia and Nigeria, a study which aimed to strengthen the evidence base on crisis-attributable mortality in humanitarian settings to inform and improve the quality of responses in humanitarian crises in South Sudan, Somalia, and Nigeria.

The Politics of Information and Analysis, a study that generated context-specific evidence from Kenya and Ethiopia on the key factors that constrain data availability and independent analysis of severe humanitarian emergencies, and identified examples of good practice in tackling these constraints. Synthesised data from this and previous research in similar contexts was packaged into a helpdesk service for FCDO country offices for improved decision making in humanitarian emergencies.

Assessment of Science, Technology, and Innovation (ST&I) Metrics in Africa, a study whose overall objective was to explore the metrics used by different initiatives that monitor ST&I in Africa, to provide an assessment of quality, completeness, and appropriateness. This would then inform the development of a dashboard that can be used to track and monitor the ST&I ecosystem in Africa.

INDICATOR [2.2]: Number of published research outputs

We have had 3 journal articles from one regional study, and 10 research products from five regional studies produced against a target of two and six respectively, moderately exceeding expectations. Details of the study outputs and examples of research uptake are summarised below.

A Systems Approach to Air Pollution in East Africa (Kenya, Uganda, and Ethiopia)

Study outputs included (these are additional to those reported in the last annual review):
- Literature review on Urban mobility, air pollution and Covid-19
- A blog titled A Brave New World: Building Back Better from Covid-19

Dissemination/uptake: Majority of the outputs, dissemination, and uptake activities for this study took place in the previous financial year and are captured in the programme’s 2019/20 Annual Review. A webinar on urban mobility, air pollution and Covid-19, with a data driven discussion of what next was held to contextualise the findings of this work in a pandemic era. There was also media coverage in follow-up to this webinar discussing that bold action is required to build back better post Covid-19.

Shelter Provision in East African Cities: Understanding Transformative Politics for Inclusive Cities in Nairobi, Hawassa, and Mogadishu

Study outputs included (these are additional to those reported in the last annual review):
- A peer-reviewed journal article by Hassan et al., on Understanding shelter from a gender perspective: the case of Hawassa, Ethiopia.
- A peer-reviewed journal article by Mwau and Sverdlik, on High rises and low-quality shelter: rental housing dynamics in Mathare Valley, Nairobi.
- A peer-reviewed journal article by Bonnet et al., on Inclusive shelter provision in Mogadishu.

Dissemination/uptake: Majority of the outputs, dissemination, and uptake activities for this study took place in the previous financial year and are captured in the programme’s 2019/20 Annual Review.

Key influences in the Horn of Africa from Middle Eastern Gulf States and Turkey

Study outputs included:
Research Report: Turkey and the Gulf States in the Horn of Africa: Fluctuating dynamics of engagement, investment and influence
Policy Brief: Securing the near abroad: Gulf and Turkish interests and influence in the Horn of Africa

Dissemination/uptake: The findings from this work were shared and discussed during the 3rd session of the aforementioned SCORE End-of-Programme virtual event. A cross-HMG dissemination event for this study was held on the 25th of March 2021 with attendants spanning the Middle East and Horn of Africa regions, including the Ministry of Defence and external partners (Chemonics) and a separate public dissemination meeting held on 9th June 2021 with a wider external audience [all examples of transparent use of evidence].

Mortality Studies in Humanitarian Crises in South Sudan, Somalia, and Nigeria

Study outputs included:
- A research report on Retrospective estimation of mortality in Somalia, 2014-2018: A statistical analysis
- A Frequently Asked Questions (FAQ) document on Estimates of crisis-attributable mortality in Somalia, 2014-2018
- A policy brief on Weathering the storm: Findings and recommendations from a study of crisis-attributable deaths in Somalia

Dissemination/uptake: This study formed the basis for a deep-dive in a famine learning series hosted by the Humanitarian Head of Profession on understanding mortality in famine-risk contexts in November 2020, an example of [transparent use of evidence]. The lead humanitarian adviser in FCDO Nigeria plans to share the findings during discussions between G7 countries and the UN’s Inter-Agency Task Force in-country, exploring how they can best weave together their mutual famine prevention initiatives. The findings will also be shared with government officials in Nigeria with improved coordination in mind. These are both examples of [instrumental use of evidence].

The Politics of Information and Analysis

Study outputs included:
Seeing in the Dark: Real-Time Monitoring in Humanitarian Crises

Dissemination/uptake: This report was cited by the Humanitarian Head of Profession as “recommended reading for those working on humanitarian diagnostics and a useful companion to the earlier paper refreshing the conceptual framework for broader humanitarian needs analysis” with a planned FCDO discussion with the authors as part of the 2021/22 Humanitarian Learning offer, an example of [transparent use of evidence]. This study was extended as a helpdesk service providing expert country-level advice, evidence synthesis, and learning support regarding food security, nutrition diagnostics, and data collection efforts within the context of the Covid-19 outbreak in major humanitarian crises. This work has informed related FCDO policy and programming prioritisation and engagement in Yemen, South Sudan, Afghanistan, Nigeria, DRC, Somalia, Sudan and the Sahel region, an example of [instrumental use of evidence].

Assessment of Science, Technology, and Innovation (ST&I) Metrics in Africa

Study outputs included:
- A synthesis report on: Science, Technology and Innovation Metrics in Africa
- A policy brief on Assessing Science, Technology, and Innovation Metrics in Africa
- Twelve country briefs summarising a scoreboard of the key indicator performance for each country
- A feasibility study report for establishing a web-based STI indicator dashboard with stakeholder consultation reports for Kenya, Zambia and Nigeria
- A report on In-country assessment of the challenges and opportunities on STI web-based scoreboard

Dissemination/uptake: The team has continued extensive consultation with various partners to identify opportunities for hosting a dashboard/scoreboard including a web mock-up of the findings from feasibility studies. The dashboard is designed to be user friendly and easily accessible, with a core set of comparable indicators that can manipulated in line with user preference, for example, a drop-down menu to sort by country, sector, level of investment, or others. This is an example of [instrumental use of evidence].

INDICATOR [2.3]: Research projects with credible and appropriate Research Uptake Strategy

All regional studies are required to have an uptake strategy as part of their deliverables, that is approved by the technical steering panel for each study. As such, performance against this indicator has consistently met expectations.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

During its lifetime, the SCORE programme delivered a total of 39 studies, 22 of which were country-specific, and 17 of which had a regional focus. The Fund out-turned a total budget of £ 11,478,174, of which £ 3,201,872 was used to deliver country-specific and £ 7,127,438 for regional studies. A total of £ 1,048,864 was used in management fees and the balance for research support activities including communication and external peer reviewer engagement.

Output 2 targets have been met [A] in 2014-15 and 2019-20, and moderately exceeded [A+] in 2016-17, 2017-18, 2018-19, and 2020-21, and substantially exceeded in 2015-16. Regional commission supports have been very well received, from quite early on in the programme’s lifetime, and this interest and uptake has been maintained to date.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

The VfM proposition for this output remained strong over the lifetime of the programme. We have ensured that regionally specific research and evidence products are generated that are of high quality and relevant to programming and policy in East Africa. Further details on VfM are provided in Section E of this report.

The programme complied with the 2014 Gender Equality Act commitments. Consideration was given to improving the beneficial impact on women and girls, and reporting used disaggregated results by sex where appropriate. Further details on gender equality are provided in Section E of this report.

Lessons learned through this output, and recommendations for future programming

Successful implementation of these regional studies was hinged, to a large extent, on engaging with, ownership by, and drawing on the expertise and networks of a large number of stakeholders including advisors, Heads of Profession, desk officers and ex-FCO Research Analysts. Sectoral experts brought their perspectives to bear on research outputs, brought them to the attention of programmes that would benefit from the evidence they provided, and in certain cases, directly utilised them for policy and programme response. With a wider customer base in FCDO, we will continue to engage widely and innovatively across the organisation as part of the implementation of the Evidence Fund to ensure better visibility of the Hubs and alignment with in-country and organisational strategic plans.

On supplier engagement, we identified the need to provide guidance and clarity to suppliers during development of the inception report to ensure feasibility of research implementation and alignment with the study Terms of Reference on scope, methodology, length of reports, study timelines, and targeting recommendations for specific audiences.

Output 3 Title:	Through designing, procuring, and managing research, the East Africa Research Hub supports skills and capacity development of country offices to commission and apply evidence.
Output Score:	A
Impact weighting (%):	10	Weighting revised since last AR?	No

Output Indicator	Logframe Target 2020/21	Results Achieved in 2020/21
3.1 Number of presentations and training sessions to FCDO Country offices on research and evidence.	6	Met Expectation [A]: 6
3.2 Number of instances where the EARH has provided substantive technical support to FCDO country offices, centrally managed programmes, or cross-UK government.	8	Moderately Exceeded Expectation [A+]: 9

Output 3 focuses on the training and technical support provided by the EARH to country office and policy teams. These are activities that do not incur programme spend or involve external implementing/delivery partners, rather, Hub staff time. These requests are varied in nature and ad hoc. It is noteworthy that while the Hub had previously delivered a large proportion of these activities during in-person outreach visits or training sessions, we are now delivering entirely virtual sessions given travel and social restrictions associated with the Covid-19 pandemic.

INDICATOR [3.1]: Number of presentations and training sessions

The Hub delivered a total of six training sessions to country office and policy teams against a target of six. These specifically included:

1. Hosting a Covid-19 modelling round table on approaches, challenges, and support needs for the East Africa region in May 2020;
2. Supporting a famine learning series highlighting a SCORE funded study on the politics of information and analysis in famine risk contexts in September 2020;
3. Delivering a session on how evidence, technology, and innovation can boost delivery impact for the BHC Nairobi during an office-wide learning week in October 2020;
4. Supporting a famine learning series highlighting a SCORE funded study on understanding mortality in famine-risk contexts in November 2020;
5. Delivering a SCORE End-of-Programme virtual event showcasing the thematic and geographical breadth of our commissions, while signalling preparedness to deliver more evidence-informed programmes in priority areas of the Africa Strategy in March 2021; and,
6. Delivering sessions on the Evidence Fund Programme; the Hub's position at post; the Hub's priorities for Carole Mundell; and, strategies for engaging with country offices during a week-long Regional Hubs Conference in May 2021.

INDICATOR [3.2]: Provision of substantive technical input

The Hub delivered a total of nine instances of technical support to country office and policy teams against a target of eight. These specifically included:

1. Supporting the Uganda office to develop a business case for a Strategic Evidence Fund in June 2020;
2. Supporting the Tanzania office with submission of a rapid evidence synthesis on bail conditions in the criminal justice systems in East African countries in August 2020;
3. Supporting the Somalia office with submission of a rapid evidence synthesis on water infrastructure in fragile and conflict affected states in October 2020;
4. Supporting the Somalia office with submission of a rapid evidence synthesis on the impact of climate change on income generating activities for the most vulnerable in November 2020;
5. Reviewing interim and final research reports on qualitative perceptions of the UK-Kenya Strategic Partnership pillar for work within the Kenya office in December 2020 and April 2021;
6. Supporting dissemination of the Understanding the Livestock Economy in South Sudan study with targeted FCDO and external audiences in March 2021;
7. Supporting dissemination of the Key influences in the Horn of Africa from Middle Eastern Gulf States and Turkey study with targeted FCDO and external audiences in March 2021;
8. Supporting dissemination of the Estimating Excess Mortality in Somalia due to COVID-19 using Satellite Imagery study with targeted FCDO and external audiences in April 2021; and,
9. Supporting dissemination of the Understanding the Pandemic Response in South Sudan – Localisation and Covid-19 study with targeted FCDO and external audiences in May 2021.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

Output 3 targets have been met [A] in 2019-20 and 2020-21, moderately exceeded [A+] in 2015-16, 2016-17, 2017-18, and 2018-19, and substantially exceeded in 2014-15. The Hub technical assistance, training, and brokering offer has created awareness and sustained interest from country offices, allowing us to also deliver on outputs successfully 1 and 2 above.

Lessons learned through this output, and recommendations for future programming

Providing technical assistance, training, and brokering departmental and institutional relationships and partnerships were key functions of the programme and the Hub team. Demand from country offices for training and technical support remained high and the Hub provided substantial supports to country offices in the region across a diverse range of areas. A key lesson identified in the last 2 years of delivering this programme was the need to consider opportunities for offering country office virtual support when travel is not an option and/or when the budgeted travel allowance has been exceeded. The Regional Hubs are currently working on a revamped and engaging training offer, particularly since travel to our focus countries may not be possible in the near future.

D: Risk

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.

The EARH has maintained an overarching risk register capturing key high-level portfolio-wide risks, with a risk review conducted biannually. A separate and more programme focused risk register was maintained for the SCORE programme, and was updated regularly with mitigation measures put in place for any risks identified. The residual risk of this programme was within the portfolio risk-appetite for the lifetime of the programme. Overall programme risks were maintained at moderate throughout and during the last year of the programme, with variations in the trajectory of individual risks.

Pre-Covid, an external audit was commissioned for the programme, and it confirmed that funds were used for intended purposes. Nonetheless, areas were identified where more could be done, including instituting requirements for partners around fraud reporting and safeguarding; embedding oversight measures such as the use of virtual spot checks with suppliers; and, phasing of payments and additional assurance measures in contracting templates. Risks associated with internal processes including the ODA reduction, and requirements for exemptions, have caused some delays in delivery.

As with most programmes, the major risk flagged this year was related to Covid-19 pandemic challenges. There were delays in programme delivery and cancellation of activities including in-person dissemination events, severely affected by travel restrictions, and requiring a move to virtual events. Field related activities were also put on hold, with face-to-face surveys replaced by electronic surveys. Additionally, an upsurge in Covid-19 research demand from country offices required a pivoting exercise to accommodate this need, and the team instituted a suite of mitigation strategies including continuous review of partner delivery options, agreeing on flexibility in timing of delivery, and extending or amending contracts, to ensure that the programme was both responsive to country office needs, and could accommodative the challenges of carrying out research during a pandemic. On the flip side, the pandemic provided an opportunity to deliver research that informed our Covid-19 response and contributed to global health research. It also provided opportunities to explore alternative methods of conducting business with savings made from costs related to travel.

During the earlier phase of the programme, a recurring delivery risk was identified around delayed spend. Several factors including timelines for peer review and steering panel feedback on quality of reports/outputs, as well as the unpredictable nature of conducting research in the field, were putting the programme at risk of underspend. A key lesson learned from this is the need for the SRO and programme team to proactively stay in touch with delivery partners and flag quite early on any anticipated delays, which can be captured during forecasting and financial disbursement arrangements, including offering supports to elevate any barriers in the field when possible.

E: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency.

At the onset of programme implementation, a results framework was developed for the EARF programme to assess overall performance of the Fund Manager against a number of Key Performance Indicators (KPIs). The KPIs monitored performance against two main categories: Fund Management (procurement, monitoring and evaluation, reporting) and Stakeholder Engagement (communication and staff resourcing). Over the years, the KPI results have demonstrated that the Fund Manager has continued to achieve targets. The quality of reports/reporting has also improved, remaining consistently strong during the latter half of the programme. This was after consistent feedback to the Fund Management team and the refining of the reporting template.

The overall programme budget as at the end of the financial year for the SCORE programme was £ 10, 803, 900, with spend totalling £ 10,688, 843.07. For the EARF, the total budget was £11,478,174 comprising £10,429,310 research budget and £1,048,864 management fee. Of this amount, £ 950,000 was funded through the evidence fund. The Fund has made payments amounting to £ 11, 454,112 which represents 99.7% of the total budget available for the SCORE programme. The programme procured a total of 39 studies, with the Fund Manager playing the role of ensuring compliance from suppliers with contractual obligations. This included managing relationships with suppliers and providing feedback regarding their performance. During its lifetime, one regional study on ‘Labour Migration in East Africa’ and one country-specific study on ‘Tanzanian Returnees from Somalia’ were terminated prior to finalisation due to supplier performance failures in the case of the former, and non-viability of the work given the prevailing political context in the case of the latter.

SCORE Programme compliance with FCDO commitments

The programme complied with the 2014 Gender Equality Act commitments. Consideration was given to improving the beneficial impact on women and girls and reporting using disaggregated results by sex (where appropriate).

The programme was committed to ensuring that its research (where appropriate), had key performance indicators to assess participation by women, and ensuring that this increased through the life of the programme. This included women as lead and contributing authors, and their role in research uptake. To achieve this, the Fund designed a strategic approach to ensure that gender and other dimensions of social inclusion were captured in its operational and programmatic activities. These were deployed in 3 main ways:

- Promoting a collective and tangible understanding and commitment to gender mainstreaming components by research organisations based in the East Africa Region, and especially those contracted to implement SCORE research projects;
- Capturing gender considerations in Terms of Reference where research suppliers were required to clearly set-out how such considerations would inform research parameters by providing context-specific examples and showcasing how different populations would be affected by the issues identified in the research; and,
- Ensuring that the scoring criteria for studies being commissioned rewarded research suppliers who clearly articulated and justified how gender dimensions had been embedded into the proposed research parameters and methods/robustness of approach, including data collection processes.

The Fund further ensured that issues on gender were monitored through research supplier’s progress reports and reports or policy briefs. Suppliers were expected to provide details about their work on gender, including; gender disaggregated data, gender considerations on research uptake, and gender considerations when contracting local or regional researchers and partner organisations. As a result, research suppliers have become increasingly receptive and aware of what was expected to promote gender equity to achieve development impact in the region. For example, while working on a study to ‘Improve understanding of vulnerability and resilience in Somalia’, the Development Initiative team made deliberate efforts to include/invite gender-focused organisations such as representatives from the Somalia Women’s Studies Centre, to share and validate their research findings and recommendations during a breakfast dissemination meeting held at Panafric Hotel in Nairobi on 18th July 2019.

The Fund has however not attained the desired gender parity in the number of researchers engaged in conflict and fragile contexts. Out of 3 research projects commissioned covering the conflict and security theme, of the local researchers engaged in delivery, only 6% were female. This is partly due to the generally lower number of active researchers or experts on issues to do with peace, conflict, and security that are female. That said, over the years, out of 39 studies commissioned, 11 principal investigators were women and 28 were men. The number of women engaged in leading research has improved significantly due to orienting research suppliers on gender mainstreaming components and understanding how gender dimensions can best be embedded in it.

Since inception, the Fund has delivered Downstream Partner Management through conducting robust due diligence assessments and mapping of downstream partners for all SCORE research projects.

Programme information has been published on the International Aid Transparency Initiative (IATI) platform.

Relevant SCORE programme outputs have been published on the R4D website, complying with FCDO open access policy.

The programme’s Fund Manager, PwC Kenya, has remained in compliance with the Supplier Code of Conduct as set out contractually.

Related to compliance with the new cost and transparency requirements, which requires capturing of profit variance and challenge, and using of Open Book Accounting, PwC Kenya charged 9% as the Fund Management fee, maintaining this even when the contract was cost extended, and this was considered good Value for Money. Research funds were disbursed upon delivery withing milestone-based contract agreements.

Strategic Relationship Management (SRM) scorecard assessments scored PwC Kenya 70 or above in each year, demonstrating good performance on reporting, adherence to schedule, communications with the FCDO programme team, adherence to budget, Value for Money, knowledge and lesson sharing, responsiveness to feedback, and compliance and risk management.

Value for Money (VfM)

The key cost drivers for the Fund are the research and management costs. Research costs of up to 91% constitute researchers’ professional fees, reimbursable costs (flights, accommodation, and subsistence) and external peer reviewers’ fees. The management fee is 9% and covers PwC’s staff costs and overheads. VfM is a function of price, appropriateness, quality, and timeliness of sourcing the input, rather than the lowest possible price for a given input. To this end, in 2018/2019, the programme commissioned a portfolio analysis on VfM and a Benchmarking of Professional Fee Rates to provide a peer to peer comparison; understand gaps in operations; and, recommend improvement measures. In essence, the analysis was to help develop a clear understanding of costs (inputs) and results (outputs and outcomes) in relation to the 4 E’s of VfM – economy, efficiency, effectiveness, and equity. From this information, the programme has set out to comprehensively achieve VfM and has provided annual updates.

VfM Indicator	Examples
Economy / For each contract awarded, the Fund ensured that all professional fees charged were within benchmarked rates. In addition, flights were allowable in economy class and, organisational overheads were not charged to the project.	The Fund Manager terminated the contract of Samuel Hall as a result of non-performance based on a resolution from a Labour Migration steering panel within FCDO in July 2018. The Fund Manager facilitated payment of accrued liabilities to the supplier and negotiated a reduction of the professional fees billable by 15%, thereby reducing the accrued liabilities claimed from £45, 388.66 to £39,022.66. / The programme contracted the ‘Vulnerability and Resilience in Somalia’ and ‘Harmonising Registration in Somalia’ research studies to an international supplier (Development Initiatives), which had very strong regional presence in the region. All the staff (100%) working on the project were from the East Africa region, significantly reducing the logistical costs (travel and accommodation). The reimbursements were below 10% of the total budget as a result of minimum logistics. / The programme hosted an urbanisation conference in November 2019. The initial plan was to hire an event’s organiser to handle all the logistical arrangements. Market engagement estimated that this would cost between £20,000 to £30,000. For cost saving prudence, the programme team took up this task thereby realising this savings. / The Fund Manager terminated the contract of RUSI’s “Tanzanian returnees” study as a result of a mutual decision between FCDO and the supplier following a decision by the government officials engaged to discontinue their support for the study. The Fund Manager facilitated payment of the accrued liabilities to the supplier and negotiated a reduction of the fees billable by 29%, thereby reducing the accrued liabilities claim from £21, 276 to £15,072.
Efficiency / The programme reviewed the processes, people, and technology, and how these inputs interacted to translate into outputs, in a bid to answer the question of “what works best”.	The Fund produced a comprehensive guidance to withholding tax that was issued as part of the procurement pack to ensure suppliers and prospective bidders are aware of their tax obligations. / A ‘stakeholder mapping matrix’ was developed to enable suppliers identify stakeholders during the proposal stage, and this was evaluated and strengthened during the inception period with the aim of enhancing uptake of research outputs by stakeholders and policy makers, including targeting outputs to specific audiences as needed.
Effectiveness / The programme monitored the impact of the outputs and more specifically, how the study products were accessed and adapted by various stakeholders. The activities sought to promote and interrogate: / Accessibility of the products to various stakeholders. / Adaptability of the products for various stakeholders. / Extent that long-term goals in the theory of change were met.	The programme’s stringent risk management and robust quality assurance processes have ensured delivery of quality reports. / The programme revamped its website, to enable easy navigation and promote usability and access to key resources. With closure of Fund, the website will be live for the next 2 years. / The programme engaged 28 peer reviewers, largely based in the region, who provided independent external assessments on research outputs and proposals. / The programme procured the services of communication experts to develop a research uptake strategy that would amplify research and evidence use in the region; to support training delivered during early market engagement events in a bid to build capacity of local and regional suppliers in delivering winning bids and improving uptake/impact; and, to support the end-of-programme event. As a result, these activities have resulted in several successes in research uptake and realised impact. In addition, the process has enhanced research uptake capabilities of research suppliers, particularly among our local and regional partners.
Equity / The programme ensured that there was a fair approach in how it managed its programmes and suppliers.	The Fund ensured fairness and equitable treatment of all suppliers who desired to conduct research by providing all supplier with the same information regarding products or services, needs, and expectations. / The Fund sought improved engagement from local and regional research organisations through market development activities and early market engagement with suppliers in the region. As a result, more local and regional supplier engagement was recorded. / The Fund evaluated and actively sought to improve how it had operationalised the FCDO Gender compliance act within research proposals and among research suppliers who implemented SCORE studies. / The Fund is monitored VfM returns with additional guidance provided to suppliers to ensure that this was a well understood concept. Equity considerations was set out in Terms of References, and suppliers were expected to demonstrate how they planned to or were achieving these considerations related to gender, marginalised communities, religion etc.

Programme-level approach to monitoring and evaluation

Programme progress against its Logframe was monitored through quarterly reports, quarterly team meetings, and annual reviews. To build in objectivity, some annual reviews were conducted by independent assessors, including interviews with country office advisers on the usefulness of the programmes’ supports to them. All final versions of Annual Reviews were peer reviewed and approved. Following recommendations from respective Annual Reviews, the programme Logframe was updated, and a cost extension approved to respond to emerging needs and increasing demand for evidence products from our countries of focus.

Organisational learning was a key goal of the Fund. Over the implementation period, individual components under the Fund delivered a number of high-level outreach events to disseminate findings. Senior officials were willing to attend presentations/disseminations when sector-relevant research products or workshops were conducted. Each component lead was responsible for deciding how this dissemination was best targeted and how best research findings were stored. The SRO was responsible for reminding and signposting teams to appropriate fora for sharing learning and evidence.

Date of last narrative financial report	June 2021	Date of last audited annual statement	July 2020