Annual Review

Title: Stronger Health Partnerships for Stronger Health Systems
Programme Value £ (full life): £30 million		Review Date: 30 January 2019
Programme Code: 205243	Start Date: 30 January 2018	End Date: 31 March 2023

Summary of Programme Performance
Year	2018
Programme Score	B
Risk Rating	Moderate

DevTracker Link to Business Case:	Business Case
DevTracker Link to Log frame:	Logical framework

A. Summary and Overview (1-2 pages)

Description of programme (1/2 page)

The UK will invest up to £30m to support partnerships between UK and developing country health institutions – sharing expertise that helps developing countries build stronger and more resilient health systems, including a better-skilled health workforce. This programme builds on lessons and successes from earlier UK health partnership programmes, including the current DFID-funded Health Partnership Scheme (ends February 2019).

The UK has world-class health expertise. A health partnership, often run by volunteers, ‘links’ a UK health institution (e.g. NHS Trust, academic institution or professional organisation) and a counterpart institution in a developing country (e.g. hospital, local authority, training college, or ministry of health). Partnerships enable sharing of expertise, e.g. through UK volunteers supporting development of improved training curricula or management practices, that helps developing countries build stronger and more resilient health systems, including a better-skilled health workforce. This ultimately contributes to SDG3, ‘ensure healthy lives and promote well-being for all, at all ages’. Partnerships also benefit the UK NHS as volunteers bring back new skills, confidence, and motivation.

To deliver the expected outcome, ‘improved health worker and health service performance for poor and vulnerable populations in selected low and lower-middle income countries’, funds will be spent on:
1. Coherent and strategic partnerships supporting health workforce development and health systems priorities in 8-10 focus countries in Africa and Asia. (Approx. 6-8 ‘large’ grants in each country, c. £250,000-£350,000 per grant).
2. A larger number of smaller grants for innovative partnerships, e.g. new approaches to training in specific skills, in more countries (total of 80-100 grants, c. £25,000-£50,000 each).

Summary supporting narrative for the overall score in this review (1/2 page)

The programme is scored at a B for 2018. While there has been progress on design and procurement, including engagement with a range of stakeholders, issuing the invitation to tender to the market is significantly delayed. This has set the programme behind the timeline set out in the Business Case.

Recommendations for the year ahead (1/2 page)

1. The programme team should work closely with Procurement and Commercial Department colleagues to ensure that there are no further delays in the procurement.
2. DFID will work with the implementing partner during inception to mitigate any risks or issues from the delayed procurement, such as the reduced time for implementation of the programme.
3. The procurement of an evaluation provider should proceed alongside the procurement of the main provider. The programme team should continue to ensure that evidence and lessons from the Health Partnership Scheme are reflected on during mobilisation and implementation of the programme.
## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Design and early market engagement
Output number per LF		N/A	Output Score	B
Impact weighting (%):		25%	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Early market engagement	October 2017	Completed 1 March 2018

Provide supporting narrative for the score

This output has been scored at a B. During the review period, the programme has benefited from a wide range of inputs into its design and sourcing. However, this activity has taken longer than expected and has contributed to the overall delay in the tendering of the programme.

An early market engagement event was organised with interested suppliers on 1 March 2018. Twenty-three suppliers attended, with 26% identified as being Small-Medium Enterprises (SMEs). This resulted in changes to the Terms of Reference to better reflect the balance between programme management and technical and country skills and expertise, the potential areas of health systems that partnerships could address beyond the health workforce, the relationship with DFID country offices, and the role that private sector providers could play in partnerships.

There was also consultation with country health advisers to understand alignment with country programmes and how partnerships can be effective across different contexts. A workshop was held at the DFID Health Professional Advisers Conference on 14 March 2018. This contributed to design considerations for the programme, particularly the larger partnership grants, how approaches will need to differ in different country contexts, and to harness the networks and ideas of diaspora communities for partnership projects. Health advisers unable to attend the workshop were given an opportunity to provide written input and express interest for their country to be considered as a focus for the larger health partnership grants. The list of focal countries will be included in the programme terms of reference.

In February 2018 DFID committed to support the Nursing Now campaign by ring-fencing £5 million of health partnership grant funding for nursing and midwifery development and leadership. Nursing Now is a three-year global campaign that aims to raise the status and profile of nursing. The earmarking of grant funding for partnerships focused on nursing and midwifery will support the campaign’s aim to empower nurses through targeted short-term support and long-term relationship building between UK health professionals and their counterparts in developing countries. This commitment will be reflected in the revised terms of reference and delivered through implementation of the programme.

Lessons identified this year, and recommendations for the year ahead linked to this output
From market engagement and consultation, the following should be considered over the next year:
1. Design of grant calls: grant criteria, particularly for large grants, should ensure that proposed partnership activities are suitable for their context, recognising that different activities and approaches will be required for fragile settings, stable and low-income settings, and lower-middle income settings on a transition pathway.
2. Theory of change: the theory of change should be updated regularly, in consultation with the implementing partners for the programme and evaluation, to reflect evidence generated by the programme and any additional analysis commissioned.
3. Alignment with national priorities and plans: the role and capacity of the implementing partner and DFID country offices in brokering relationships and ensuring alignment with national priorities must be carefully managed during the early and subsequent phases of implementation for the programme to contribute to health systems development.
Output Title	Programme procurement
Output number per LF		N/A	Output Score	B
Impact weighting (%):		75%	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Invitation to tender	November 2017	Delayed – expected Q4 2018/19
Contract award	September 2018	Delayed – expected Q1 2019/20
Independent evaluation procurement	September 2018	Delayed – expected Q1 or Q2 2019/20

Briefly describe the output and provide supporting narrative for the score

This output has been scored at a B due to the delayed procurement of the programme. The Business Case expected that inception activities would take place in Q3 and Q4 of 2018/19. On current timelines, the contract is unlikely to be awarded until Q1 2019/20.

The process to identify the route to market was protracted. Initially expected to be approved in the Summer of 2018, the route was approved in December 2018. This process has resulted in an appropriate route to market being identified, that is intended to maximise bids for the contract and effectively deliver the programme objectives. Work to finalise the terms of reference and tender documentation is underway.

The Business Case set out that further two pieces of scoping and analytical work would be completed as part of the inception phase of the programme. The first was further analysis to summarise factors that make health partnerships successful. The requirement for this will be reassessed following the closure of the Health Partnership Scheme and review of the learning documented from the programme.

The second was an analysis of how to ensure that NHS volunteers with the right skills are ready, able and willing to take part in health partnerships that meet developing countries’ priority needs. Understanding the enabling environment is built into the expectations of the supplier in the programme terms of reference. If a formal supply-side study is required to support implementation activities, this will be commissioned in consultation with the contracted implementing partner during the mobilisation phase.

The evaluation procurement has been delayed so that it coincides with award of the contract for the implementation of the programme. As set out in the Business Case, an independent evaluation will be commissioned from the start of the programme so that baseline, midline and endline data can be collected. The evaluability assessment will be prioritised to ensure that DFID can initiate the procurement of an evaluation at the appropriate time.

Lessons identified this year, and recommendations for the year ahead linked to this output

DFID should be realistic about procurement planning timelines and identify and mitigate risks of delay effectively.

The aim should be for the evaluation provider to be in place to build the evaluation design as the implementing partner is completing inception activities.

The need for further scoping and analytical studies to inform implementation should be discussed with the implementing partner at the start of inception activities and take into account all the evidence and learning generated by the Health Partnership Scheme.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year (1/2 page)

The Theory of Change for future support to health partnerships is presented in the figure below.

There are three interrelated ‘output to outcome’ change pathways.

The Partnership change pathway. Well-targeted, more strategic and coordinated long-term partnerships with synergies with wider health systems strengthening activity can improve health service performance in a more systematic way. In addition, funding and support to smaller partnerships can add value in terms of innovation and proof of concepts to be taken to scale.

The Volunteer and UK Health system change pathway. A stronger approach to UK volunteering will enable more strategic partnerships by better matching the right skills and expertise to national and institutional priorities and contribute to improved health service delivery in developing countries. The pathway also describes the benefits for UK health volunteers and the UK health system through their learning, acquisition of new skills and leadership development opportunities. It is expected that positive experience of UK health workers will encourage more volunteering and contribute to recruitment and retention of health workers in the UK. The volunteer change pathway interacts with the partnership pathway through health partnership projects, recruitment and placement of volunteers.

Host country health system change pathway. Health partnership projects and volunteers contribute to a strengthened health workforce that deliver higher quality health services by enhancing the knowledge, skills, attitudes and behaviour of host country health workers. Partnerships can contribute to health systems strengthening by working to improve infection prevention and control measures, leadership and governance, supply chain management, and health information systems, which should lead to sustainable changes in partnering institutions and the broader health system. Partnerships can contribute to sustainable health systems strengthening by engaging with wider health system actors. For example, identifying opportunities to link in with and support government strategies to address wider health system barriers will be an important part of the more strategic partnerships approach. The interaction between country actions/ownership and the larger, more strategic partnerships should lead to changes in the host country health system.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)

As the programme has not mobilised yet, it is not possible to assess the extent to which it is contributing to the expected outcomes and impact.

Explain major changes to the logframe in the past year (1/2 page)

No major changes have been made to the logframe in the last year.

Describe any planned changes to the logframe as a result of this review (1/2 page)

The logframe will be reviewed with the supplier in the mobilisation phase.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year (1 page)

The expected VfM set out in the Business Case is derived from the use of high quality expert volunteers that provide technical assistance at low cost, the efficiency with which partnerships use their inputs to deliver outputs such as better trained health workers or new procedures and standards, and the effectiveness of health workforce capacity improvements for individuals and institutions. Equity has been a key focus of the final phase of the Health Partnership Scheme. Learning from this and the independent evaluation completed in 2016 will inform grant calls and the design of partnership projects to increase the equity of health partnership activities.

For more detail on the expected VfM from the programme, including proposed measures, please see the Business Case.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)

The VfM case for the programme is judged not to have changed since the approval of the business case.

E: RISK (½ to 1 page)

Overview of programme risk (noting the rating from p.1) and mitigation

The overall risk rating for the programme is moderate, based on experience from the Health Partnership Scheme.

The same risks remain as set out in the Business Case. The risk matrix will be refreshed when an implementing partner is appointed and will be regularly reviewed throughout inception, implementation and closure.

An additional risk identified after the approval of the Business Case is on safeguarding. In addition to the programme potentially having a detrimental impact on a developing country, safeguarding risks to and from UK and LIC/LMIC staff have been added to the programme’s risk matrix. The mitigation for this risk will be for the implementing partner to ensure that institutions taking part in partnership projects have robust safeguarding policies and that they are satisfied that these are implemented to minimise safeguarding risks and respond appropriately when cases arise. This expectation will be set out in the programme’s Terms of Reference.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial, and financial issues (1-2 pages)

The procurement process has taken longer than expected and has been delayed from the timeline set out in the Business Case. This has delayed implementation and has created uncertainty for potential suppliers, with a significant gap between early market engagement and tendering for the programme. DFID has sought to mitigate this through updates and responses on the DFID Supplier Portal but, due to commercial sensitivities, only limited information has been provided.

There have been multiple causes of the procurement delay. Some, such as turnover in DFID staff working on technical and commercial aspects of the procurement process, were unforeseen and challenging to mitigate. Others demonstrate that the relevant design and commercial controls worked, such as review and amendments to improve the programme design and proposed route to market.

A revised timetable has been set for the procurement.

Recommendation

DFID will learn lessons to help realistic timeframes being put in place and prevent delays in future procurement processes.

Date of last narrative financial report(s)	N/A
Date of last audited annual statement (s)	N/A

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring (1/2 page)

Monitoring will start during inception. As stated in the Business Case, it will consist of 1) monitoring of partnerships by the implementing partner; 2) programme monitoring and reporting to DFID, and; 3) an independent evaluation. The independent evaluation will be commissioned from the programme outset to allow for baseline, midline and endline data to be collected.

Evidence (1/2 page)

The programme has not generated any evidence at this stage.

Learning (1/2 page)

Lessons learnt from the design and procurement process will be captured and internally documented following the tender of the programme. Learning from the Health Partnership Scheme, through the independent evaluation (2016) and learning generated from the programme, is and will continue be taken forward in the implementation of the Stronger Health Partnerships for Stronger Health Systems programme.

Progress on recommendations from previous reviews (1/2 page)

N/A.