## Programme Completion Review - 2021

Title: Solar Nigeria Programme (SNP)
Programme Value £ (full life): £66.06 million		Review date: 21/01/2022 to 16/02/2022
Programme Code: 203674	AMP start date: 14/10/2014	AMP end date: 30 November 2021

Summary of Programme Performance
Year	2015	2016	2017	2018	2019	2020	2021
Overall Output Score	A+	A	A	A	A	A	A
Risk Rating	Major	Major	Major	Major	Major	Major	N/A

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/projects/GB-1-203674/documents
DevTracker Link to results framework:	https://devtracker.fcdo.gov.uk/projects/GB-1-203674/documents
DevTracker Link to the 2020 Review Report (which is complementary to this report)	https://iati.fcdo.gov.uk/iati_documents/58487347.odt (internal Teams link here)

A. SUMMARY AND OVERVIEW

Description of programme

The Solar Nigeria Programme was designed and delivered as a pioneering initiative created to champion and accelerate the development of public and private markets for offgrid solar power in Nigeria. The programme included four separate workstreams which were also complementary, namely, the social, the commercial, the consumer and the government workstreams.

The social component, which was implemented by Adam Smith International (ASI), and later by AECOM, funded the installation of solar power systems for public health and education facilities in Lagos, Kaduna and Borno States. It also provided support to ensure sustainability of the systems, including spare parts as well as operations and maintenance training to staff in these facilities.

The commercial workstream, mainly implemented by ASI, alongside a separate advisory technical assistance done through the IFC, was created to develop the market for Commercial and Industrial (C&I) solar power. This component emphasised captive, offgrid power (not grid-connected) and was focused on removing barriers to the flow of commercial finance through the solar value chain, by providing grants and support to capable solar companies.

The consumer (or household) market component also mainly implemented by ASI awarded grants to businesses developing the markets for household solar systems and devices in Nigeria. These grants helped to mitigate risks and offset working capital constraints; and were typically awarded directly to businesses in areas such as the provision of finance to consumers or distributors; as well as to solar home systems companies. There was also a separate IFC component which initially aimed to support the banking sector to invest in consumer solar, but this wasn’t quite viable at the time as the market was not mature enough for the banks to lend.

The Government workstream, also implemented by ASI, provided technical assistance to the Federal Government of Nigeria to support the development of the policy and regulatory regime for offgrid solar energy in Nigeria. This was done mainly through implementing the UK-Nigeria Energy Compact. Support for this workstream was discontinued in 2019 and taken over by the Nigeria government-owned Rural Electrification Agency through the World Bank-funded Nigerian Electrification Project, which was deemed better resourced. There was also additional UKAid technical assistance through centrally managed FCDO interventions such as the Africa Clean Energy (ACE) programme and other donors such as GIZ, US Power Africa and more recently Rockerfeller, Rocky Mountain and AllOn have come in to support.

In addition to these UK-funded workstreams, the programme (in 2017) took on management and oversight of some 37.5 million Euro of EU funds for social solar installations in Borno, Kaduna, Kano and Adamawa States. The EU Delegation to Nigeria, having observed the successes recorded on initial phases of the Solar Nigeria Programme committed these funds to FCDO – for additional solar for health and solar for education in the selected northern states – who then helped to deploy the funds on the EU’s behalf working with AECOM as the delivery partner.

This EU-funded work comprised only social-type installations (i.e. solar installations in public health and education facilities) and did not include any of the market building, market development or regulatory support initiatives that the core UKAid-funded Solar Nigeria Programme covered. While this completion review includes, where relevant, discussions about the EU-funded work, detailed reports on the results and status of the EU-funded work (all of which have also been completed as agreed with the EU) have been provided to the EU Delegation.

This report is closely complementary to the 2020 review report

Originally, the Solar Nigeria Programme was scheduled to end in the year 2020, with a planned end date of 31 December 2020. However, as noted in the 2020 report, the programme was extended by a year (with a revised end date of 30 November 2021), primarily to allow for a robust independent evaluation of the programme – which was delayed largely by Covid-19 disruptions. The programme indeed completed delivery in December 2020, however, the planned third-party evaluation scheduled for 2021 did not occur due to budget constraints. Therefore the 2020 review report (DevTracker link to the 2020 report) remains the most comprehensive backwards look at the programme’s achievements and impacts. This formal PCR nonetheless closes out the programme, expounds on the lessons learned as its major selling point and value add to the 2020 report; and for fresh perspectives, presents recent updates in the offgrid solar industry (not necessarily resulting from direct UKAid activity) as well as progress being made by a number of the programme’s beneficiaries. In addition, we also received a short report from the IFC Trust fund element of the programme, which also fed into the narrative in this review.

Summary supporting narrative for the overall score in this review

Solar Nigeria Programme has scored an ‘A’ overall, as an average of previous years’ scoring and representing the programme’s success demonstrated through programme results in spite of its operating context, and due to the efforts of delivery partners and inhouse DFID/FCDO programme team. Further narrative is detailed below.

Political context

The programme’s operating context has been highly variable. It has varied from opportune, to highly favourable, and even to very difficult and challenging. The exact context at any point in time also quite depended on the component or workstream concerned as well as the specific parts of the country where the workstream was being implemented. Having started in 2014, the social component programme (i.e. the component working on solar installations in schools and hospitals) was favourably received by the government of Lagos state, where installations occurred under very stable operating context and welcoming political environment with high levels of government buy-in, and some counterpart funding. The social component later moved into Kaduna State in northern Nigeria where it was also well received by the Kaduna state government. At this time, the commercial pilot and consumer component were also happening quite undisrupted across many different states (but mostly in main cities with favourable economic climate such as Lagos), and the Office of the Vice President was very open to co-creating a National Solar Plan with the programme. It was a relatively stable period during those early years, and being a new technology there were lots of opportunities to test. On the private sector grant side, the advent of the oil related recession presented a setback in 2016.

Operating context got rather difficult when the programme (especially the social component), wanting to pilot solar power solutions in more difficult environments, ventured into the north-eastern part of the country. It was challenging to do installations in Borno State, especially as the relative peace that was believed to have returned to the north east began to wane as insurgent attacks and kidnaps became more rampant from around 2017. This led to significant delays, several contract amendments and extensions, particularly on the Borno projects, and general frustration of programme objectives. To curtail impacts on programme activity and performance, the EU-funded Borno projects were discontinued as detailed in the 2020 report.

Contractor performance

Regarding contractor performance, delivery capacity across the programme was less complex in the early years, including Crown Agents largely handling procurements and Adam Smith International West Africa focusing on delivery in-country. With both teams being highly capable, and few states to work in (Lagos which was stable and had non-existent security challenges, and later Kaduna), delivery went on smoothly in those years. As the programme expanded to other states up north, such as Kaduna and later Borno, each new state meant a new contract needed to be drafted to ease burdens of internal processes of amending the existing contract. The delivery chain of contracting partners became much more diverse mid-way through the programme, when (due to procurement law and policies) newer components of the programme could no longer be re-contracted to Adam Smith International. AECOM (appointed as the procurement agent under then DFID framework) therefore came into the mix of delivery partners.

The mix of delivery partners meant a greater burden on the FCDO programme team’s operating resources, as two different partners, with different processes, risk thresholds etc., had to be engaged. This became even more complex later on as the programme moved into difficult operating contexts such as Borno state with high levels of insecurity. Both partners, including ASI and AECOM maintained consistent engagement and provided monthly reports throughout the programme. ASI particularly continued to monitor and manage the remaining portfolio of grantee solar companies, also worked promptly to close out asset disposal prior to programme closure.

Both the ASI and AECOM team were faced with exit of key staff who sought longer-term opportunities as the programme entered it later phases. Both teams, however, continued to work hard to deliver regardless of the dwindling staff resources. ASI were particularly flexible in managing the programme and were often able to make reasonable adjustments to beneficiary circumstances (especially the private sector grantees, during periods of poor market conditions and low sales of solar products). AECOM also provided very strong stakeholder management services, and proactively engaged with key state government counterparts by working with their subcontractors Em-One and Nuvo throughout the programme.

As more and more work (especially on the social components) needed to be done in northern Nigeria, the AECOM team also deployed specialist security risk advisory. This was highly useful in project planning and in mitigating risks of working in these places with very challenging security environments. The implications of security advisory were ultimately reflected in AECOM’s later decision to close off work in Borno state (north eastern Nigeria) due to the security risks, which then led to contracting, Em-One, who seemed to have had a greater risk threshold, and which had hitherto been a subcontractor, to deliver the remaining works in Borno state. All through these evolutions of the programme, all UK-funded work continued well (with the exception of solar installations in Borno state), and the grant components were particularly progressing well with ASI managing those grants to consumer as well as commercial and industrial solar companies who were really very enthusiastic about UK support at those early stages of the solar market development when not many other development partners were providing such flexible grants to solar developers.

DFID/FCDO performance

The FCDO SNP programme team maintained oversight on delivery partner activity throughout the programme; engaging partners through periodic reports, meetings, responses to no-objection proposals from delivery partners as well as annual review monitoring exercises which typically included project site visits and meetings with grantees. This programme however did experience a high turn-over of SROs. This stalled progress at multiple times, especially on the EU-funded solar projects which happened later in the programme from around 2017 through 2019. Over the life of the programme (roughly 6 years), at least 5 individuals functioned as the programme’s SRO (owing to movement of FCDO staff across countries, and in some cases, untimely exits of staff much earlier than was planned). These staff changes, coupled with unravelling security challenges in northern Nigeria, where most of the EU-funded projects were based and some of the UK-funded projects were being done, created lots of tension and difficulties on the programme, as new decision makers had to relearn much of the programme, familiarising themselves with context and delivery partners and other stakeholders.

The private sector components (i.e. the grant-making components working with solar companies) continued to work quite well during the moments of security challenges with the social solar, as grantee companies continued to sell solar products not having being constrained to one geographic location, and were also beginning to mobilise some private finance. The implementing partner, ASI, had also chosen quite a good set of solar developers to work with following due diligence and assessments, and following decisions made alongside the FCDO team. Programme activities in these commercial and consumer components were progressing well until Nigeria’s economic recession in 2016 to 2018 which strangled demand, coupled with forex challenges, and later by COVID and further forex shortages from early 2020. Although the pandemic’s effect are still being felt until today, there have been signs of recovery since last year as a number of grantees and solar companies have begun to received new rounds of debt and equity financing (in millions of dollars) from more commercial investors who are optimistic about the trends in Nigeria’s solar market, especially in the commercial and industrial space. Decreasing solar component costs and increasing ongrid energy tariffs (without much increase in reliability) have also made solar a much more attractive option for businesses in particular.
Major lessons learned and recommendations for future programming

Not much programme activity has happened since the last review report (i.e. 2020) and now. Key lessons learned throughout the programme implementation remain the same as outlined in the previous report, although now re-emphasised and expounded upon below, with a number of additional lessons drawn from the IFC-led components (which were not reported in the previous years’ reviews) as well as from reflections on recent industry trends:

Resolve tensions inherent in FCDO ambitions by finding a practical way forward to reconcile FCDO’s desire to deliver at pace (and to spend as forecasted) on the one hand, with the need to patiently wait to ensure beneficiaries (particularly government partners and, in some cases, grantee businesses) fulfil their mutual accountability commitments on the other hand. For example, in many cases, due to the urge to deliver projects quickly and to keep spend moving as forecasted, the programme went forward even though partners/beneficiaries in some states were not fulfilling their commitments to secure project sites or to provide alternatives sites when previously selected sites were no longer safe.

Despite having agreements on operations and maintenance (O&M) and sustainability of solar systems from the start, state governments did not always meet their commitments on O&M sometimes due to claimed budgetary constraints or perhaps due to other priorities. As such, there is a need to continually find ways to retain leverage for governments to keep to those O&M commitments throughout implementation (and in fact, beyond implementation), either by taking decisive ‘pause’ or ‘stop’ actions during delivery of projects in order to encourage beneficiary states to action their commitments, or post-implementation by seeking action through concrete ‘asks’ before new requests for support are attended to.

UKAid programmes with multiple components being implemented by different delivery partners need to be better joined up (or should have less components if such synergies cannot be effectively realised). Following the disconnects observed between the ASI- and IFC-implemented components of this programme, it is clear that there weren’t sufficient communication lines between the activities of both partners, which gave room for little complementarity despite that both were in some cases working with and targeting similar beneficiaries, for example the consumer solar market. FCDO advisers overseeing programmes need to do better in making this happen, as opposed to inadvertently setting delivery partners up to work in silos.

It is always helpful to consider the political state of the operating context before launching a new programme. An election year and a change of government pose risks of a slow start for market transformation programs like this, especially in a developing economy such as Nigeria. While such political economy analysis often do occur during programme design for many FCDO programmes (i.e. prior to programme implementation), the political stability context can often change very quickly, and there isn’t always sufficient allowance or incentive to stop to take stock of the political situation once programme delivery and implementation are set in motion. A solution might be for programmes to set funds aside for political economy analysis or for a central team (such as the Integrated Strategy and Delivery Unit) to commission political analysis prior to, or right after, major political events, providing insights relevant to active programmes in the portfolio, and how such programmes may need to respond.

In stimulating competitive markets for solar, especially where one is non-existent or nascent, it is very important to have clarity of purpose, sequence the progression of activities (i.e. not deal with too many issues at a time), and to focus on attracting capable players into the market before attempting to resolve secondary barriers. For example, under SNP, there was usually the view by many local stakeholders (including government and local solar developers) that the programme needed to be more inclusive of local companies, many of whom were just taking off as start-ups at the time. However, understanding that the goal was to rapidly build a market, helped the programme focus on providers who had the capability to do so (who were sometimes outside of Nigeria), as it takes longer to try and develop organisations that did not have that track record of capability, especially in a nascent market where there were no big examples to demonstrate how success can be achieved. Once initial wins are made by penetrating the market, secondary barriers such as developing other players can then be considered.

The idea of “picking winners” or capable players – i.e. already established companies, or perhaps new companies whose management team showed solid understanding of the market and demonstrated business development acumen – for grant receipts is unpopular. However, it worked quite well in the Solar Nigeria Programme, especially when the programme had consultants with the right skillsets to identify such capable grantees following scoring which was backed by due diligence assessments. The successes demonstrated by these capable players helped attract bigger investments and provided credibility for advocacy to resolve regulatory and governance-related barriers.

In environments with unclear or unpredictable macro-economic and policy contexts, an initiative aimed at building a strong market for solar should aim to be nimble and flexible – especially in its relationship with grantees who might sometimes struggle to achieve milestones due to exogenous factors such as economic recession or access to forex. Nascent markets in pioneer and frontier settings are difficult to predict as things change quickly and dramatically. At several points, the programme needed to be flexible – adapting to changes in the market. These external shocks meant that, at some point, the programme needed to provide some grantees, especially a few local ones, who had not met milestones due to inability to access forex for their products, some more time, once it was clear that the failure was not due to internal management incompetence.

To improve regulatory context, it is important to find key champions in government, who are truly willing to drive change, and support them as this programme did through technical assistance to the office of the former Managing Director of the Lagos State Electricity Board, LSEB (on the Lagos solar projects), who eventually became the Managing Director of the national Rural Electrification Agency and presently the CEO of the UN Sustainable Energy for All. To create sustainable shifts in government towards supporting solar, new programmes need to deliver benefits and real impacts first before asking for policy changes – the more “visible” the impacts and benefits, the better the case that can be made. The Lagos solar projects were implemented in partnership with the LSEB and, comprised over 5 MWp installed capacity in 175 schools and 11 primary health care centres in Lagos State. This was the biggest project of such scale in West Africa at the time and was one with visible impact.

For most pioneer initiatives in a budding sector, donors and development partners often tend to focus on the supply side (as we see in Nigeria’s solar market), however, well designed consumer-focused, demand side interventions aimed at consumer awareness and education (as were done under the consumer solar advisory trust fund of the Solar Nigeria Programme) can be very powerful in complementing supply side efforts.

When working with financial institutions (such as banks and microfinance) to fund and finance a new sector of climate finance such as offgrid solar, there is a need to always manage expectations especially with more established financial institutions. Big and already established players are not always better in terms of embracing and championing new markets. Smaller players can often be more open and flexible. New programmes should therefore be open-minded as they explore which stakeholders to work with, considering what incentives and disincentives exist for such stakeholders to want to take action.

1. Major transformative impacts of UKAid programmes do not always materialise within the timeframe of the programme, and as such it might be important to have a monitoring intervention (ideally a portfolio-level one) which aims to track and evaluate impacts generated by UKAid programmes years after they have closed.
2. The sustainable disposal of solar batteries remains an issue unaddressed by this programme, as batteries have a limited life span. Support for sustainably disposing of the batteries at the end of productive life was not built into the Solar Nigeria Programme, as the programme’s primary focus was on developing the nascent, and in many parts of the country non-existent, market for solar in Nigeria. The solar installations provided as a result of the programme’s support, once handed over, became the property of beneficiary state governments. Products sold in the private markets also were the assets of the individuals or businesses who purchased them. Although the national policy in Nigeria on batteries is evolving, and there are now budding organisations such as the Alliance for Responsible Battery Recycling, the e-waste disposal and management sector in the country is not yet well developed. FCDO’s Manufacturing Africa programme is supporting a UK firm building a market around responsible disposal and recycling of solar batteries and other donors such as GIZ are working in this space. Other development partner initiatives could also consider the significant opportunities in this sector.

Although Nigeria’s offgrid solar sector is gaining traction, the sector still presents considerable opportunities for upskilling and capacity building across various segments of the value chain. The trust fund component of the programme provided training to local solar developers and technicians during the course of programme implementation, which many of these individuals found useful in getting jobs or starting their own solar companies based on surveys. However, there is yet a challenge (possibly among other capacity challenges) of getting credible technical partners that can offer independent verification and quality assurance of solar projects, especially the commercial and industrial projects being financed by banks for example, other financiers, and even under government-led initiatives such as the Energizing the Economy Initiative. Development partners or other future donor programmes may consider opportunities in this area.

Solar power has now clearly established itself as a key part of the Federal Government of Nigeria’s (FGN’s) policy. This is evidenced by the NDC commitments to generate 13GW of solar, the Nigeria Electrification Project (NEP) and, the Solar Power Naija’s 5 million homes solar connections commitment, for example. However, sustained commitment to these initiatives, especially by having the FGN as well as various state governments, commit to actually providing significant public funding into the solar sector (other than simply making commitments and policies), and having the government resolve the remaining market barriers such as import duties on solar, customs clearance challenges, widespread mobile money, amongst others, should be encouraged through ongoing FCDO, and other development partner, advocacy.

International donors and development partners must put up a united front in the advocacy for the solar market. If certain groups of donors continue to fund social sector solar for relatively wealthy states for example or if some donors fail to demand mutual accountability on maintenance and security, or if some are silent about resolving unfavourable market barriers such as import duties on solar products (while still providing funds for solar projects), this weakens the efforts of those who are actively advocating.

Having served as one of the UK’s flagship contributions towards addressing climate change and promoting Nigeria’s clean energy transition, it is important to maintain momentum after Solar Nigeria’s closure, ensuring that the programme’s contributions and lessons are not lost despite the inability to have conducted the planned evaluation in 2021. In late 2020, two brown bag knowledge share sessions were held to share programme’s key lessons. One involved internal climate, private sector and energy infrastructure advisers across FCDO and BEIS, who could learn lessons from the programme to inform new programmes. The other brown bag session convened local and international stakeholders in the energy space to share key achievements and lessons learned and was well received. Advocacy and engagement on outstanding policy constraints such as import duties on solar are being carried forward through centrally managed programmes such as the Africa Clean Energy Technical Assistance Facility (ACE-TAF) and some further support to the sector through Transforming Energy Access (TEA) and Manufacturing Africa. UKNIAF undertook viability studies and mapping of industrial and agriprocessing sites (now merged with ACE TAF sites) for minigrids and solar home systems, AECF has provided some grants and as described elsewhere Manufacturing Africa is also in this space. Also, UK NIAF will provide concessional funds to be blended with a commercial clean energy fund, mobilising institutional capital and encouraging Nigerian pension funds to finance offgrid projects including solar mini-grids through the recently announced £10m UKaid fund which would work through InfraCredit. Finally, the FCDO adviser who worked on Solar Nigeria also contributes to the regular (quarterly) offgrid solar donor/development partners’ meeting and continues to help shape the offgrid solar industry’s efforts as informed by lessons from Solar Nigeria, among others. These efforts should be maintained within the limits of reducing ODA and recognising that other development partners are also active in this space.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summary of the programme’s theory of change, including changes to outcome and impact indicators from the original business case, as well as where and how the programme is on/off track to contribute to the expected outcomes and impact

The Solar Nigeria Programme was designed to promote the uptake of solar energy technology in Nigeria working through both the public and private sectors. Public sector activities included the social and government workstreams, while private sector activities comprised the consumer and commercial workstreams.

The initial business case was crafted to include largely social solar installations (i.e. solar systems in public facilities such as schools and hospitals). The rationale was that by delivering installations which were visible for the public and for government officials to see in public facilities such as hospitals and schools, the programme could demonstrate that solar works, as Nigeria had already had a history of visible and failed solar projects here and there delivered with public funds. For solar to really take hold and be trusted, Nigeria needed big, visible, solar projects to demonstrate its effectiveness. That was the change the programme wanted to see on the social workstream.

Activity therefore started in Lagos, with over 5 MWp of installed capacity in 175 schools and 11 primary health care centres – the biggest scale in West Africa at the time – and was progressively expanded to Kaduna and then through an addendum to the business case, to Borno State to pilot test the efficacy of solar for public health facilities in Borno state which was at that point recovering from conflict but has since relapsed into a worsened situation and the operating context was (and still is) difficult and challenging.

Over 7 MWp of installed capacity has been delivered in public facilities directly by the programme, with state governments such as Lagos and Kaduna committing budget flows to do additional systems (though these don’t appear to have materialised yet as of 2021/early 2022) and in some cases seeking further donor support, as well as attracting other donors such as the EU to invest further 37.5 million Euros, and many government office buildings now naturally opting for solar by themselves as the first choice for sustainable power – a demonstration of significant progress beyond expectation towards the intended outcomes.

Also, as part of the initial business case, this approach of building and installing solar for public health and education facilities (i.e. the social workstream) was complemented concurrently by finding and supporting a champion; a government-focused initiative aimed at empowering a champion within government who could further make a case for solar – one who would drive the public sector and political awareness of solar and encourage policy commitment to its use. This was the change the programme wanted to see happen with the government workstream. Therefore, as the social installations in Lagos commenced in 2015, activity also started on this workstream as well, by providing technical assistance to the Lagos State Electricity Board at the time, whose managing director eventually became an adviser on power to the Office of the Vice President, serving as an embedded adviser for the Solar Nigeria Programme. The adviser later rose to become the head of the nation-wide Rural Electrification Agency (REA) and then CEO of the UN agency, Sustainable Energy for All.

The government workstream activity was eventually expanded over the years to include influencing regulation via the UK-Nigeria Energy Compact (a set of policy commitments and actions which the government of Nigeria needed to take to grow the solar market) signed in 2017 between DFID and the REA, as well as providing support for designing other FGN programmes. Today, as at the time of writing this report, the government-run REA is, by itself, running and implementing a Nigeria Electrification Project (NEP), funded by the World Bank and AfDB with about USD 550 million (modelled after some aspects of the Solar Nigeria Programme), and in 2020, the Federal Government of Nigeria announced, by itself, a commitment to roll out solar power connections for 5 million homes nationwide to be funded with a combination of Nigerian government funds and other external public and private finance – an ambitious initiative demonstrating, again beyond expectation, that the case for solar is clear to the government of Nigeria. The National Development Plan (of 2021 – 2025) also includes a significant commitment to solar electricity to be championed and led by the Rural Electrification Agency. The 2021 Energy Transition Plan for Nigeria signed off at COP 26 also depends on solar – it envisages 7GW of solar a year.

As the initial set of public sector activities progressed as structured in the initial business case, the Solar Nigeria Programme took on lessons from other climes such as in East Africa where the solar market had taken off progressively. It was clear that any large public sector solar programme and public support for solar would need an active industry of private sector solar providers/solar companies who in turn would be ready to support public sector needs. This meant there was a need to build market supply capacity as well, which then led to the inclusion of significant support, through grants and market development insights, to Commercial and Consumer solar system providers, in the Business Case.

These companies would be capable solar providers available to serve public sector needs as well as any burgeoning private sector needs; and would need very large flow of private capital in order to be viable. But the challenge at the time, in 2015, was that the market for solar in Nigeria was practically non-existent – solar was either not known by many Nigerians or not trusted by those who knew it; the market was also considered risky by big international players, and there was almost no serious investor finance coming in. This needed to change; and was what the programme sought to tackle with the private market components i.e. the commercial and the consumer workstreams.

SNP understood from international experience that such nascent markets for distributed solar arose initially from the actions of one or a few very capable solar providers who forge the way. These first movers would possess the capabilities and typically bring their own capital for the initial phases. After they are successful, more solar providers enter; investors and banks are then ready to provide finance into the value chain; and there is more momentum to influence changes in policy and regulation. This was the focus of the consumer and commercial work-streams – to attract highly capable solar providers to drive the market.

It was expected to attract big players who might not otherwise have entered the market, and who could demonstrate viability of commercial industrial and domestic solar, and then drive policy change. These players would be attracted by the programme’s provision of market development insights and making flexible grants to cover the risk of first losses and market penetration challenges and help break barriers of entry compounded by policy. Gradually the case for stronger policy incentives could be made, and with increased activity and penetration of these solar providers, competitive investor funding and large public and private finance and investments in solar could be crowded into the Nigerian market. This was the holistic theory of the change regarding how the private markets fitted with the public sector government/regulatory activities.

Thus far, as the programme closes, each of the programme’s workstreams have either met or surpassed expectations, and have holistically exceeded expectations in contributing to expected outcomes and overall transformative impact in driving “the development and consolidation of Nigeria’s solar market with solar companies operations becoming sustainable and commercially viable and with sustained demand for solar energy from households, business and public institutions” as it set out to do in its business case.

The case for solar in government is already clear, largely supported by the programme’s activities and contributions; and public institutions and facilities are now increasingly opting for solar. Solar power also forms a key part of the Energy Transition Plan and electrification plans in Nigeria’s 2021 – 2025 National Development Plan for providing access to power for many underserved and unserved communities across the country. In the private markets, demand for solar amongst households and businesses has also risen significantly, demonstrated by the sales of, and MWp installed by, grantee solar companies, as well as the uptake of consumer solar products and the demand for solar services through leases of rooftop solar and power purchase agreements provided by the grantee solar companies. Furthermore, new rounds of Series A and Series B investment deals being signed by these grantees (many of whom no longer depend on grants for survival and now attracting capital from deep-pocket investors in commercial terms, as sales increase following successful market expansion drives), also demonstrate the significant progress that the market has made. We are also now seeing foreign investment working capital funds launch in Nigeria for solar e.g. Lions Head fund, the Nithio fund. The financing has even shifted to the capital markets – the first green bond for offgrid solar in Africa was successfully issued in July 2021 (with UK support) by North South Power and again with UK returnable capital support we are seeing a planned low carbon energy fund – pending SEC approval to tap into pension fund and insurance money.

## C. DETAILED OUTPUT SCORING

Output Title	Social (Lagos, Kaduna, Borno): Clean and reliable energy services are provided to public institutions (schools and clinics)
Output number:		Output 1	Output Score:	N/A (as activity ended in 2020)
Impact weighting (%):		50%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for the last review in 2020 when activity ended	Progress (as of 2020 when activity ended)
1.1 Installed capacity in schools as a result of the programme activities (MWp) – Lagos	3.17	3.17
1.2 Installed capacity in clinics/hospitals as a result of the programme activities (MWp)	3.15	3.15
1.3 Number of PV systems in public institutions provided with programme support for which there are O&M plans in place	256	250

Outputs, achievements, challenges and lessons learned

Except for audits and expenditure verification on EU-funded projects, no activity has occurred under this component since the last review in 2020. However, the UKAid-funded 78 KWp Konduga solar installation at the Konduga General Hospital in Borno state which was started by AECOM (alongside other installations in Borno state) but particularly got stalled at about 80% completion due to insecurity, was completed by Em-One just after the last review. It can be recalled that during the last review in 2020, it was reported that owing to AECOM’s stance to discontinue working in Konduga due to the security risks, the installations were re-contracted to Em-One (AECOM’s subcontractor on the Solar Programme) in July/August 2020. While the risk of completion not occurring in late 2020 was still quite high, Em-One found a window of opportunity to complete the installations just before the year ended. The installations now serve the Konduga hospital after having been handed over to the hospital management. As at February 2021 significant numbers of displaced persons are being resettled in Konduga town.

As all installations (including Konduga) planned during the programme across all states had been completed, the social component of the Solar Nigeria Programme also effectively closed in 2020, with no activity throughout 2021. It is worthy to note that the social workstream was primarily aimed at demonstrating the efficacy of solar installations in the public sector by addressing challenges that had been faced by previous attempts to introduce solar energy solutions into the Nigerian public sector. It did this by creating visible solar success stories in schools, clinics and general hospitals serving thousands to hundreds of thousands of people – this has been a success. The Borno installations have taken on a larger significance as the main grid transmission line in the state was repeatedly damaged by insurgents in 2021 despite several repair attempts by the Transmission Company, leaving most of Borno without grid power.

These social installations began with the Solar Nigeria Programme providing solar to 175 secondary schools and 11 primary health care centres (PHCs) in Lagos State in partnership with the Lagos State Electricity Board (LSEB); solar power to 34 primary health care centres (PHCs) in Kaduna State in partnership with the Kaduna Power Supply Company (KAPSCO), a Kaduna State backed company now charged with overseeing the maintenance of the solar systems; as well as in Borno state where the programme has provided solar power access to 8 major hospitals (including the relatively recent Konduga), the Borno State College of Nursing and Midwifery, and two village clusters.

While security risks posed major challenges especially in the northern states, especially Borno and to a lesser extent Kaduna, these installations have demonstrated to the government (both state and federal) and especially the public that solar works. Nigeria’s 2021 – 2025 National Development Plan (NDP) which was released late last year by the Federal Government of Nigeria recognises DFID’s pioneering role in the adoption of solar power and in the progress of Nigeria’s solar sector across states in Nigeria, with the NDP stating that: “the Lagos state government through the Lagos Solar project, a joint investment of Lagos State Electricity Board (LSEB) and the UK Department for International Development (DFID) has installed nearly 5MWp of solar-generated off-grid power for 172 schools and 11 clinics within Lagos State.” The Plan also acknowledges how “an additional 1.5 MWp is being installed at public health clinics in Kaduna State under the Solar Nigeria programme by DFID.”

Following the programme’s success in demonstrating that solar works even for public facilities, several other off-grid schemes with support from other international partners are gaining traction across the country with support and partnership of respective state governments. The EU-funded components of the Solar Nigeria Programme are just one of many examples of where UKaid catalysed other donors to fund solar power in other states across the country, with buy in and support of many state governments.

These social solar installations remain perhaps the most visible result of the Solar Nigeria Programme. Since the programme substantively ended in December 2020, officials from states such as Lagos and Kaduna (and in fact Kano and Adamawa where some EU-funded installations were done) have expressed interest in further support and still continue to do so even now. And it is impressive to see that these states (Lagos and Kaduna) as at 2021 have now incorporated solar and offgrid renewable energy into their electrification plans and policies following some technical assistance from a centrally managed UKAid programme, Africa Clean Energy Technical Assistance Facility (ACE-TAF).

One major challenge however is that despite the openness of states to solar policies and plans (and being pro-renewables in general), aside from solar lighting which has been pursued by some states e.g. Jigawa, there is yet no strong state government financial commitment for large scale solar programmes. This is a challenge as state governments would find it valuable if public financing is channelled into powering public facilities such as schools and clinics with solar, especially considering that the returns on improving public health and education outcomes can be very significant. With solar projects often being some of the lowest of the low hanging fruits for development partners seeking to ramp up their climate portfolio, it can be argued that state governments in Nigeria still tend to retain their expectation that more donors will continue to fund solar projects for public sector facilities – thus disincentivising many state governments, including the relatively rich ones such as Lagos State, from significant large scale public budgeting for electrifying social services with solar power.

This scantness of public funds committed to solar power also creates another challenge. This is the weakness, or in some cases the non-existence, of meaningful maintenance of these solar installations in many of these schools and hospitals. Development partners will need to continue to advocate for increased commitment of public funds to solar electrification as well as maintenance of, and securing, existing donor-funded facilities.

And lastly, there is also a challenge of solar battery waste disposal, as the batteries have a limited life span. While the e-waste disposal and management sector in Nigeria is still quite weak, UKAid programme ACE-TAF supported the Nigerian Federal Ministry of Environment and the National Environmental Standards and Regulatory Enforcement Agency (NESREA) in developing policy and standards for e-waste disposal, including waste from solar products. However, implementation of this policy needs to become more mainstream among solar developers and solar costumers. In this regard, Manufacturing Africa, another UKAid centrally managed programme supported Hinckley, a UK e-waste recycling company in developing recycling solutions for the local Nigerian market.

In 2021, a new development partner donor group (led by US, Canada, and EU) – arguably inspired by the obvious success stories from DFID-funded solar for health projects – was launched focusing on electrifying and improving access to solar in primary health care centres across the country. It is yet unlikely whether private sector investments would be seen in the near future in these social-focused solar sub-sectors, due to the non-profit operating model of these government primary health care centres, and as earlier asserted, it is also somewhat unlikely that substantial amounts of public capital will go into electrifying more clinics with solar especially since significant donor funds and interest continue to go into this area.

Nonetheless, one major win and transformative impact that early initiatives such as the Solar Nigeria Programme have had is that these projects are often close to the heart of communities and ordinary people (who benefit from these schools and clinics) and by implication also often dear to government officials who get praised when these solar systems are implemented in their constituencies. For over 7 years since its launch therefore, the Solar Nigeria Programme has helped many Nigerians, and the government of Nigeria, see the potential of solar, and that in fact, solar works. Even though there may not be any large scale catalytic impact on social solar measurable in monetary terms, the goodwill that the Nigerian solar power sector has achieved through these visible solar projects for health and education facilities are truly unquantifiable.

Output Monitoring and VfM Highlights

From the start until end in 2020, results for this social sector output were tracked through bi-annual field visits either by the ASI team or contracted through M&E specialists. One exception was some of the Borno installations outside Maiduguri where it was not possible for safety reasons to monitor them in 2020. This output delivered value for money in a number of ways. On the economy side, competitive procurement processes were undertaken to acquire key solar equipment for the clinics/schools in Lagos, Kaduna and Borno. The programme also managed to save 50% of the total M&E costs since mid-implementation when it was decided to bring the technical and performance monitoring of Kaduna and Borno in-house to ASI and implement a hybrid solution consisting of external data collection and internal data analysis for Lagos.

Regarding efficiency, each phase of the procurement and delivery process reflected lessons learned and an improvement on the previous phases’ design, resulting in procurement of higher quality equipment at relatively affordable costs, as well as delivery of increasingly higher quality systems which reflected lessons such as load coverage planning amongst other lessons such as O&M trainings effected in later phases in Borno and the rest of the northern states for effectiveness. In addition, most of the installations were delivered in unserved or underserved locations, providing critical healthcare and education services to women and young children respectively, thus improving equity outcomes.
Progress on EU-funded solar installations

In late 2017, the Solar Nigeria Programme mobilised 37.5m Euros from the EU Delegation for additional social installations in public health and education facilities in four states, namely Borno, Kaduna, Adamawa and Kano, as the EU was keen to replicate the progress of DFID’s Solar Nigeria Programme. The EU-funded arrangement used AECOM as the delivery partner and covered 30 million Euros roughly equally allocated between the states of Kaduna (thirteen hospitals), Adamawa (seven hospitals and a college of health technology) and Kano (six schools and six hospitals), as well as 7.5 million Euros for installations in Borno State.

All EU-funded solar installations were completed before December 2020 (except for some installations in Borno where we agreed with the EU to not proceed for safety reasons and another contractor took them over), with a final completion report having been sent to the EU Delegation in June 2021. Selected solar installation project sites across Kaduna, Adamawa and Kano states were also visited by Nigerian government officials from the Federal Ministry of Power and the Federal Ministry of Finance, Budget and National Planning in early October 2020, who confirmed during a steering committee meeting held on Thursday 15th October 2020 that the “standard was very high” compared to other projects the team had visited, and that from civil works, to installation and the connections, “the quality of equipment used is very high.” Cross-cutting activities such as branding, comms and visibility, as well as end-line monitoring and evaluation of these installations have also been completed, and as at the time of writing this report an EU-commissioned expenditure verification is ongoing.

Output Title	Commercial markets: Market for solar energy becomes more robust and solar providers build sustainable businesses, with financial available through the value chain.
Output number:		Output 2	Output Score:	N/A (as activity ended in 2020)
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for the last review in 2020 when activity ended	Progress (as of 2020 when activity ended)
2.1 Installed capacity in the private sector and other institutions as a result of the programme activities (MWp)	5.65	7.16
2.2 Total £ (million) of private investment mobilised by the commercial pilot / £ (million) value of spend by Solar Nigeria Programme on supporting the commercial pilot (Note that additional capital has been mobilised in 2021 but has not been counted)	2.00	6.05
2.3 Total value of lending portfolios developed (£ million) - IFC component	3.80	N/A as this component was terminated

Outputs, achievements, challenges, and lessons learned

All activity on this workstream ended prior to December 2020, since the programme’s contracts with Adam Smith International (ASI), the main implementing partner under this workstream closed in December 2020. Since then, no further work has been done under this workstream and no new funding added to the workstream. This commercial component of the Solar Nigeria Programme was created to develop the market for Commercial and Industrial (C&I) solar power in the country by providing grants and support to capable solar companies.

The grants were focused on captive rather than grid-connected power, and were aimed at removing barriers to the flow of commercial finance through the solar value chain as the use of solar for commercial off-grid energy users were virtually non-existent in Nigeria in 2014 when the programme started. Through those grants which were managed by, disbursed through, and monitored by ASI, the commercial component worked to increase investment into commercial solar by facilitating access to finance for these companies. This was however in addition to a parallel (albeit separate and largely unconnected) advisory trust fund programme implemented by the International Finance Corporation (IFC) to facilitate market development support through Nigerian banks, microfinance banks and capacity building for project developers.

It would be recalled that prior to the closure of the ASI contract in December 2020, the last review reported on a number of achievements recorded throughout the life of the programme, namely, how the Solar Nigeria Programme through this component enabled Nigeria’s first 1 MWp solar system (at Bayero University Kano) and pioneered the market in Nigeria for rooftop solar bundled with vendor finance; directly attracted five leading regional solar developers and financiers into Nigeria through its grants and markets insights; and supported the rapid development of Nigeria’s leading local developer of off-grid commercial solar with grant finance, having provided crucial grant funding to companies including Rubitec, Enerwhere, Rensource, PAHL, CrossBoundary Energy, Cold Hubs, and RP Global, some of whom have gone on to become among the leading providers of solar power under the Federal Government of Nigeria’s World Bank-funded Energizing the Economy Initiative.

While no new funding or activity has been commissioned since 2020 on this programme when the ASI-led contracts were closed, the programme continued to engage with the IFC, who had asked for an extension of the Trust Fund beyond December 2020 – when the Solar Programme was initially due to close – in order to monitor and report results of the Trust Fund’s advisory work. The aforementioned achievements of the commercial and industrial markets component implemented by ASI therefore, cannot be said to have been realised without acknowledging the equally significant support to the industry provided by the Solar Nigeria Programme through the IFC Advisory Trust Fund, some of which are reported in the following paragraphs.

The commercial component of the IFC Advisory Trust Fund included interventions on research and market intelligence, capacity building and training for solar companies, as well as engagement with and capacity building for financial intermediaries such as commercial banks. It achieved the following results over the life of the programme, including:

  1. facilitated joint missions with the World Bank during the design of the Nigeria Electrification Project (NEP), as well as working group meetings with 10 financial institutions and over 30 solar companies in shaping the design of the NEP grant components. NEP is the main project to incentivise solar for energy access (for those without any energy) – paying a results based $50 for any new connection out of World Bank financing.

  1. took over a series of courses developed by the Nigeria Energy Support Programme (NESP) in 2014 for piloting training services for solar developers in Nigeria, but which the NESP had no time to deliver. The IFC project supported the pilot roll out of 3 of the courses relevant to DFID’s Solar Nigeria Program, including the Mini-Grid Design (MGD), Solar PV Installation (SPVI) and the Solar PV Installation Supervision (SPVIS) courses. It also selected two training providers including the National Power Training Institute of Nigeria (NAPTIN), and the Ibrahim Shehu Shema Centre for Renewable Energy Research (ISSCeRER) in training 281 solar technicians and engineers across the country between 2018 and 2019. UKaid grants provided 50% to 75% tuition scholarships, and participant satisfaction rates were as high as 83% to 88%. About 64% of participants agreed in a post-training survey that the training helped them in setting up their own renewable energy businesses.

  1. For financial intermediaries, the project also organized training sessions on solar PV finance and climate finance eligibility for the Bank of Industry (BOI), as well as two local commercial banks including FCMB and Access Bank respectively. Although the BOI disbursed three small loans totalling about $328,000 in 2018 to test the waters in the commercial and industrial solar sector following the Trust Fund’s engagement, it was reported by the IFC that BOI was unable to resolve its collateral policies to expand their program significantly in 2019. The COVID-19 pandemic further slowed down the bank’s ability to finance projects and take up planned market development activities.

  1. For FCMB, some significant results were recorded. During the project team’s first engagement with FCMB in 2019, 60 selected FCMB staff across different credit, operations, client relationship units and four operational regions were trained on climate finance eligibility, including solar projects. Following this, the FCMB team were trained to evaluate over one hundred and seventy loans pipelines, after which the bank lended $65mil in eligible climate loans. Of these climate loans, two were for solar businesses with both loans valued at $2.9m in total. However, engagement was suspended by FCMB in the wake of the COVID-19 pandemic. Although FCMB has remained active in the solar sector e.g. it is collaborating with the Green Capital fund in Nigeria, it is likely that the credit risk assessment of banks’ for the solar sector still remains clouded by the covid pandemic.

A summary of the key results in the IFC-led Solar Nigeria Programme-funded commercial component include:
  1. Nearly $8.2m value of bank loans to solar projects (compared to target of $40-45m)
  2. 20 MW capacity facilitated (compared to the original target of 10-12MW)
  3. 281 technicians trained
  4. 13 professional training courses completed.
  5. 3 FIs supported (compared to the original target of 3 FIs)

The IFC Trust Fund team expressed that while advisory and engagement with banks is good, they also noted that the value of advisory is limited without investment support. This assertion assumed that no other components of the Solar Nigeria Programme provide investment support. Meanwhile, the ASI-implemented commercial component was providing investment support to C&I solar developers and financiers – just not to banks, as the ASI team believed that specialist solar financiers and solar developers themselves were better equipped to deploy the grants than Nigerian commercial banks, who at time, the ASI team (quite reasonably) believed were not ready.

A critical lesson here is that all UKaid programmes with multiple components being implemented by different delivery partners need to be better joined up. As the IFC was providing advisory to FIs for lending to commercial solar companies, ASI’s grants may have been made complementary, and as the ASI team provided grant investments, the IFC advisory and capacity building efforts could have been deliberately made to target some of these grantees for optimum impact. Future programmes need to learn from this.

Also, while Trust Fund engagements demonstrated that training and certification of solar technicians and professional are critical as the training surveys show, commercial banks (throughout the programme’s life) continued to report the challenge of getting credible technical partners that can offer independent verification of commercial and industrial solar installations that they were financing. This appears to be a sector wide issue that fairly persists even today. Although some banks are skilling up, many more commercial banks will need to collaborate with technical specialists with expertise in C&I solar development, or donors could consider for future interventions supporting the development of the verification/audit/consulting services in the solar value chain. Many of the commercial and industrial solar projects developed by C&I companies and being commissioned under the Federal Government of Nigeria’s REA’s Energizing the Economy Initiative also need to be verified for completion and quality assurance. REA continues to express need for capacity building in this area during engagements with them, and this area is one that donors could consider supporting in the near future. The BIES-funded UKAid Partnering for Accelerating Climate Transitions (UK PACT) programme, through its skill shares, might have some potential to lean in.

Although both the ASI-led and IFC-led streams of this commercial and consumer solar component have now both ended, the programme’s grantees continue to thrive. One example is Rensource, a Nigerian-owned company, which had barely only been launched in 2016 (a little over a year after Solar Nigeria kicked off) received UKaid grant funding critical for the company, which was one of the pioneers of C&I in Nigeria; and needed to take high risks to break into the nascent C&I market.

Rensource working with REA, pioneered some of the earliest offgrid electrification projects for markets and business clusters across Nigeria, using the Solar Nigeria Programme’s grants to pilot fairly large-scale solar electrification of big local markets in Lagos, Aba, and Kano. Today, Rensource has attracted far more capital and is perhaps the leading developer of solar for markets in Nigeria having also partaken as a beneficiary in the World Bank, REA-managed Energizing Markets component of the REA programme. Just before the pandemic began, Rensource raised $20 million in a Series A round jointly led by African venture capital fund, CRE Venture Capital and impact investor, the Omidyar Network. The round also saw participation from Inspired Evolution, Proparco, EDPR, I&P, Sin Capital, and Yuzura Honda. Last year, Rensource launched a spin-off Sabi, which aims to platform SMEs in the informal sector. Amongst other things, Sabi could further accelerate the reach of Rensource’s solar as a service business as it reaches more SMEs and informal market sectors across Nigeria. Till date, the markets in Iponri Lagos, and Sabon Gari in Kano continue to be managed and serviced by Rensource, with expansion into other parts of the country.

Others such as CrossBoundary, a regional solar financier which, prior to the programme had mobilised funds for solar in East Africa, could not have entered Nigeria – at least not at the time – without the grants provided to help the company assuage initial risks of loss that could result from entering a new, underdeveloped solar market. Today, CrossBoundary has structured significant solar minigrid deals in the country (including some under the minigrid component of REA’s World Bank-funded Nigeria Electrification Project) and continues to expand its solar services to bluechip Nigerian companies which hitherto were not big on renewable energy. In 2021, CrossBoundary signed a 15-year solar service agreement with Nigerian Breweries for a 663.6 kWp rooftop solar array that will supply 800 MWh of electricity per year to the company. Also last year, in what was a first for a major shopping centre in Nigeria, CrossBoundary alongside Actis UK, inaugurated a 609 kWp hybrid solar power project at the ever-booming Jabi Lake Mall in Abuja, with the UK Deputy High Commissioner and Nigeria’s Minister of State for Power present at the event. The company also continues to provide capacity building on financial modelling to solar developers and financiers in the country.

Overall, awareness of solar energy is growing among Nigerian companies and SMEs, and this continues to be seen in the increasing demand for solar power, which also tend to be met by grantees whom the UK Solar Nigeria Programme had supported through grants when their businesses could have failed during the early years of low demand. Commercial banks are also increasingly showing interest in financing solar. However, there is still a lot of internal reluctance within local commercial banks as they are concerned about risks and pricing. The Central Bank of Nigeria has a lot of work to do here to incentivise and encourage commercial banks to prioritise the solar/renewable energy sector and it has asked our Financial Sector Deepening Programme (FSD Africa) for support in this area. The advent of working capital funds and now even capital market funding (North South Power’s green bond and Infracredit’s Low Carbon Energy Access Fund) are signals of a maturing financial market.
Output Monitoring and VfM Highlights

On this component, the main source for output monitoring throughout the programme was quarterly self-reporting by grantees, which included quantitative results and progress narratives. Such results were largely drawn from grantees’ integrated enterprise reporting systems and are considered reliable. Formal reporting was supported with periodic interviews with key grantees, including interviews of a sample of grantees by the FCDO team during annual reviews. The ASI team also monitored grantees through quarterly monitoring reports submitted by the grantees as well as regular management interviews. This ensured that disbursements were made with minimal challenges and resulted in 97% of disbursements made over the life of the programme.

To achieve value for money, the programme developed and implemented an effective set of due diligence processes for pre-qualifying and awarding grants. Using this approach, SNP ensured that the companies/projects that had the most commercially viable business plans and capability to scale were selected and awarded grants. To promote efficiency, the early delivery of pilots during 2015 and 2016 enabled SNP to gain traction, test assumptions and build learning for scaling up solar interventions in the private sector. Delivery options selected combined a Challenge Fund approach and Output Based Aid / Results Based Aid (RBA) approach.

Output Title	Consumer Markets: The private market for household access to small solar lighting and power systems scales significantly
Output number:		Output 3	Output Score:	N/A (as activity ended in 2020)
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for the last review in 2020 when activity ended	Progress (as of 2020 when activity ended)
3.1 Installed capacity in the private sector as a result of the programme activities (MWp)	18.92	14.53
3.2 Number of small solar lighting or power systems acquired by private consumers as a result of the programme activities	1,373,125	1,111,795
3.3 Volume of private investment mobilised across consumer markets component (£ mil)	100.92	119

Outputs, achievements, challenges, and lessons learned

As with the previously discussed workstreams, activity under this consumer/household workstream also ended prior to December 2020 as the programme’s contracts with Adam Smith International (ASI), the main implementing partner under this workstream closed in December 2020. Therefore, following the last review report in 2020, no further work has been done under this workstream and no new funding added since 2020.

This consumer (or household) market component awarded grants to businesses that were developing the expanding markets for household solar systems and devices in Nigeria. These grants helped to mitigate risks and offset working capital constraints; and were typically awarded to businesses in areas such as the provision of finance to consumers or distributors; as well as to solar home systems companies and solar developers directly.

Prior to the completion of the ASI-implemented, grant-making consumer market component of the programme, more than 5 million Nigerians were provided with access to solar lights and solar power in their homes as a direct result of SNP grants provided to consumer-focused solar companies. Over the life of the programme, 28 grantee companies sold over 1 million solar lamps and solar home systems (SHS) on fully commercial terms. These companies include Lumos, Total Nigeria, D.Light, LAPO, Barefoot, Emel, SolarMate, Ecobank, Wandel, Roncho, Orb Energy, Arnergy, Creeds, Rubycom, Opticom Leasing, SOSAI, Solar Sisters, New Trends, Azuri, Green Light Planet, Oolu, Mobisol, Fenix, Lendable, Zola, Nithio Holdings, M Kopa, and All On.

For most of these grantees – including some of the world-leading consumer solar companies who entered the market as well as the local developers who were only budding at the time – they often acknowledged, through meetings and interactions with programme adviser and during annual review calls, that without the Solar Nigeria Programme’s support through grants to mitigate market entry risks, they would either not have been interested in entering the market or would have failed in those early years. This sounds reasonable considering the existing regulatory challenges at the time, political uncertainties during and around the general elections in 2015 and 2019, and multiple rounds of macro-economic shocks and recession, as well as low consumer demand for solar products driven not only by lack of trust in solar and also by low purchasing power, which was especially exacerbated when covid struck. SNP grants therefore helped lay the foundations for solar in Nigeria, by helping these companies accelerate their plans to scale up. While no further support has been provided to these grantees since the programme substantively ended in 2020, SNP’s foundational support during those early years of the market continues to yield results.

Arnergy, one of the few fully Nigerian-owned solar developers whom the programme took a bet on in its early years (when commercial investor would not, due to bankability concerns), surmounted macro-economic, forex and demand challenges, courtesy of UKaid grants, and is fast maturing as a company. In 2019, the company raised $9m from investors such as Norfund and Electrifi in its Series A funding, and has since grown in product sales and revenue by over five times (now not only serving consumer/household customers but also commercial and industrial customers). As of early 2022, the company is on track to raise $50m from investors in its Series B funding round.

Oolu solar, another grantee with Dakar-based women co-founders, serves the West African market and with a large Nigerian footprint, received grants and market support between 2015 and 2019. As one of the largest growing pay-as-you-go solar companies in the region, Oolu closed a deal of $8.5 million Series B investment from purely private sector impact investors in December 2020.

All-On, one of the earliest grantees, also received grants for household solar financing initiative. Today All-On has grown so much that it now does its own solar financing initiative partnering with many other deep-pocket financiers. Amongst many other sector-building and market development initiatives, recently, All-On, in partnership with USADF and Rockefeller foundation announced 13 wholly Nigerian-owned solar enterprises had won $100,000 each of blended finance including 50% grants and 50% convertible debt. This is not the first of such rounds from the All-On syndicate, and the presence of more wholly Nigerian-owned companies who are investible today compared to when SNP started (albeit a combination of grants and debt) attests to a fast-rising solar market demonstrating fruits from early seeds sown by pioneering initiatives such as the UKaid Solar Nigeria Programme.

Although all of the grants were awarded through, and managed by, ASI, another set of interventions targeting the consumer solar market was also implemented under the Solar Nigeria Programme-funded IFC Advisory Trust Fund. The IFC trust fund did not provide grants to consumer solar market players, but it did provide non-monetary support. A summary of the interventions is presented in the following paragraphs.

The consumer or household solar component of the IFC Advisory Trust Fund was aimed at working with client companies to build and develop markets that would enable access to cleaner and safer off-grid solar energy in Nigeria. Alongside IFC’s Lighting Nigeria, the trust fund engaged with solar home system suppliers and developers, as well as the Standards Organisation of Nigeria (SON) to enable the solar companies adopt the IEC standards (IEC TS 62257-9-5 and IEC TS 62257-9-8) for off-grid lighting products. In essence, this meant that for more than 1,423,686 solar products these companies sold throughout the life of the programme within the country to provide access to clean, modern solar energy services for over 7 million people, these solar products had been quality verified under the Lighting Global/International Electrotechnical Commission (IEC) standards.

The Trust Fund project team also worked with microfinance institutions (MFIs) by taking consumer awareness campaigns to their branches and customer group meetings, thus generating demand for loans for the purchase of solar products. Through this effort, the MFIs disbursed 203,627 loans, surpassing the original target by 42%. Over 80% of the loans went to women. The total value of loans given by the MFIs was over $7.6m, five times the original target, with an estimated 142,368 tons of GHG emissions avoided annually. These MFIs include LAPO, Grooming Centre, NPF MFB, UNAAB MFB, and Forward MFB.

In addition, the project conducted several rounds of consumer education campaigns across 27 states in the country reaching 71.8 million people through above-the-line campaigns and 2.4 million through below-the-line campaigns during the life of the programme. This was a unique value add offered by the consumer component of the trust fund, as no other program was running similar consumer education campaigns at the time. These efforts have likely significantly improved awareness about solar products across the country, and possibly could have had effects on the upward trend in sales recorded by consumer solar companies (including some of the grantees of the ASI-managed components). This may be hard to justify however, as the programme did not proactively set out to draw linkages between the awareness campaigns and whether or not, or how they translated into sales outcomes for solar companies in the country.

To facilitate sales for consumer solar companies, the advisory programme also created a business development intervention focused on facilitating B2B connections to grow the supply chain for sales of solar products, by recruiting and training retailers who then sell solar products to women groups, farmers and cooperatives. By employing Brands Optimal (a specialised retail development agency and later InfiBranches (an agent-banking business), solar products were sold through a network of 20,000 agents, of which over 3800 of these agents across 26 states were provided specialised training on solar products. Trainings continued on virtually even during the Covid pandemic.

In spite of its successes, the trust fund advisory programme was not without challenges. The programme was launched in March 2015, just before the country’s heavily contested general elections which led to a change in government. This led to a slow start of the activities, with many manufacturers and distributors wanting to wait until the new government’s transition plans were clear. The lesson here is that it is always helpful to consider the political state of the operating context before launching a new programme. An election year and a change of government pose risks of a slow start for market transformation programs like this, especially in a developing economy such as Nigeria.

Although the programme was able to work with the aforementioned MFIs, some of them, especially the bigger ones were not immediately able to see the opportunity in the solar market, or were just not willing to take the risk in financing solar lanterns and home systems. Even when they did, their internal bureaucracies and the unwillingness of their staff to take on what they considered additional workload led to slow adoption, while some smaller MFIs were more eager to take the risk. The lesson learned is that there is need to always manage expectations, especially with more established financial institutions, and that big players are not always better in terms of embracing and championing new markets.

A summary of the key results under the IFC-led, SNP-funded consumer component includes the following:
1. Volume of quality verified products sold	1,423,686 (compared to target of 1,212,000)
2. Value of quality verified products sold	$34m
3. Number of consumer loans given by MFIs	203,000 (compared to target of 100,000)
4. Number of consumers loans to women	163,337 (compared to target of 94,819)
5. Number of retailers trained	3,818 (compared to target of 1,279)
6. Number of people reached through CE	74m (compared to target of 25m)

Both the ASI-led, grant making consumer component as well as the IFC advisory trust fund component have so far helped the solar product companies in expanding their reach and in penetrating the market further. They have been pivotal in increasing demand for and sales of consumer solar products, through difficult macro-economic conditions and political contexts, ultimately improving the ability of these companies to attract millions of dollars from serious commercial investors that will continue to enable and sustain growths in Nigeria’s household solar sector. The Federal Government of Nigeria’s World Bank-funded Nigeria Electrification Project (NEP), which at the time was the largest off-grid energy access project anywhere in the world ever funded by the Bank with $75 million allocated to SHS is one indicator of the market’s progress as well as several grantees now successfully raising millions of dollars in Series A and Series B funding.

UKAid programme, Manufacturing Africa, is also now able to support local assembly and manufacturing of solar as demand for solar products rise – including support to Arnergy and other Nigerian developers. The fact that people are now looking to manufacture in the country is another key indicator of the market’s development as are the growth of funds and investments.
Output Monitoring and VfM highlights

Like the commercial workstream, the main source for output monitoring for the consumer workstream has been the quarterly self-reporting by grantees, including numerical results and narrative on progress and issues. The majority of such results were drawn from grantees’ integrated enterprise reporting systems. These were also supported with periodic interviews with key grantees.

To achieve value for money through effective delivery, the prequalification and grant award processes were conducted with robust due diligence in a manner that aimed to provide sufficient rigor and rule out non-capable players early on. It involved a detailed set of criteria which was applied to select pre-qualified companies. Grantees scoring higher were offered higher grants. And continued disbursements were based on meeting pre-agreed market, sales, and/or investment mobilisation milestones. For efficiency, the grant administration process ensured a focus on flexibility in the design of the instruments in order to adapt to the evolving market’s needs complemented by multiple rounds of grant funding, with typically one to two formal rounds occurring each year.

Also, SNP supported the promotion of SHS for low-income earners who tend to pay more per unit of energy and a greater portion of their income on energy than more well-off households do. Access to SHS reduces the unit cost of energy and these savings increase disposable income for small households. This strengthened the equity dimension. Moreover, access to modern energy via small solar has positive benefits for women. Women traditionally spend more time occupied with household duties during hours of darkness such as food preparation, and so gain greater benefit from modern lighting. They are also more isolated and so benefit from greater access to radio and TV bringing information about health care and life opportunities.

Output Title	Government Support: Regulatory and policy barriers to improve the enabling environment for developing the solar market in Nigeria are identified and addressed
Output number:		Output 4	Output Score:	N/A (as activity ended in 2019)
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for the last review in 2019 when activity ended	Progress (as of 2019 when activity ended)
4.1 Supporting documentation to improve the enabling environment of the solar sector is drafted/submitted and agreed. (Mini-grid study, documentation supporting National Solar Plan (NSP) development, Energy compact document).	NSP and Energy Compact Agreed	The Energy Compact was signed by FCDO and the OVP through the Rural Electrification Agency in 2017. / Mini Grid study completed, and National Solar Plan evolved into the Nigeria Electrification Project and 5 million homes connection
4.2 Policy and regulatory changes that would facilitate financing in the solar market and improvement in Solar energy provision are actioned as per the Energy Compact (% of total recommendations)	60%	69% (as at last count in 2019 when this component was discontinued)

Outputs, achievements, challenges, and lessons learned

The government or regulatory component of the Solar Nigeria Programme was also implemented by ASI. This workstream was aimed at providing technical assistance to the Federal Government of Nigeria, working with the Office of the Vice President as well as the Rural Electrification Agency (REA), to support the development of the policy and regulatory regime for offgrid solar energy in Nigeria. These interventions were done primarily by signing a Nigeria-UK Energy Compact, as well as advocacy and engagement efforts to get the Government of Nigeria to action this compact.

As noted in the 2019 and 2020 review reports, support for this component under the programme was discontinued in 2019 and was to be taken over through streams of technical assistance support from other DFID/FCDO-funded programmes such as the Africa Clean Energy Technical Assistance Facility (ACE-TAF). However, over the course of the programme, this workstream through the ASI-led team of SNP-funded advisers provided technical support in drafting the Energy Compact between the UK Government and Nigeria’s REA. The compact set out actions that the Nigerian Government needed to undertake to improve the market conditions for solar in Nigeria and was signed in 2017. The signing of the compact stimulated further cooperation between the UK and Nigerian government on the solar home systems market and committed both parties to a set of actions to support the market. As of 2019, when this component was discontinued, 69% of the action points in the Energy Compact were either well in progress or had been completed.

The team also supported the Federal Government of Nigeria to develop a standardised set of designs and business models for the Government's plans to use solar mini-grids to expand energy access in the rural areas. This Mini Grid Study informed the design of the mini-grid component of the Nigeria Electrification Project (NEP) which was funded by the World Bank. In addition, SNP provided technical assistance in the development of the National Solar Plan (NSP) which has evolved into the more ambitious NEP which is already in implementation, as well as the 5 million homes solar connections commitment which was announced by the Federal Government of Nigeria as part of its 2020 Economic Sustainability Plan following the covid crisis. The 5 million commitment was drawn directly from one of the actions listed in the Energy Compact. Additionally, a large part of the NEP SHS grant design was modelled after SNP.

Although no activity has occurred under this workstream since 2019, broader HMG advocacy on offgrid solar sector regulations has continued ever since, especially concerning customs tariffs and exemption of import duty on solar products, as well as customs efficiency in general for unblocking bottlenecks which solar companies face in shipping components into the country. These issues are usually escalated by the HMG Nigeria team to UK government ministers who then raised them on calls and meetings with high-level Nigerian government officials.

One of the issues which the regulatory component worked on was in nudging the Federal Government of Nigeria to commit significant public funds to the solar market. Some sort of progress happened on this through cross-HMG in Nigeria advocacy since the last review. In 2020, the Federal Government of Nigeria in its Economic Sustainability Plan, announced its 5 Million Homes Solar Connections initiative (now called the Solar Power Naija initiative by the Rural Electrification Agency), a plan to power 5 million homes with solar. Following this announcement, the Central Bank of Nigeria announced a NGN140 billion financing facility that will support private developers to provide solar power through solar home systems and minigrids for the five million households, which means providing electricity for up to 25 million Nigerians. The UK’s NIAF programme supported some firms to apply for this but then the CBN was reported to have disclosed (not formally) that it is not supporting the sector as it is too high risk. This shows that the challenge of getting the Nigerian budget to really support the sector remains, alongside other market barriers such as import duties on solar products.

In 2021, UKAid centrally managed programme, ACE-TAF following engagements with HMG team in Nigeria as well as discussions with solar companies, commissioned an impact assessment study on VAT and import duties on solar products to follow up on the commitment in the Energy Compact where the Nigerian Government committed to remove customs duties on solar. This study, which significantly included findings from talking to Solar Nigeria grantees and other solar companies in Nigeria, found that although the Nigerian government would lose revenues from waiving the import duties, the economy and the country in general would gain significantly much more in the medium to long term if these duties were waived considering the job creation and corporate tax and income tax revenue generation potential that many of these solar businesses could create, as well as the follow on positive economic impacts that would result from non-solar SMEs and businesses that would thrive as a result of improved access to solar-powered electricity. Amongst other findings, the study showed that after 5 years, there would be a 9-fold increase in government revenue if the duties were removed.

Working through HMG advisors, including those who worked on the Solar Nigeria Programme, these findings were shared with top Federal Government of Nigeria officials at the 2021 UK-Nigeria Economic Development Forum as an evidence-backed advocacy tool pushing for better regulatory environment and incentives for the offgrid solar sector. Findings have also been shared with other development partners including donors on both the ongrid and offgrid donor working groups with the goal of sustaining the conversation and advocacy on the removal of import duties on solar products. It is hoped that with continued advocacy, using the kind of findings and insights available from ACE-TAF’s study, the Nigerian government will ultimately take the right steps towards easing import duty burdens on this growing sector.

Apart from import duties other existing regulatory challenges in the offgrid sector which have yet to be resolved – and which may warrant further HMG (or other development partner) support include:

Mobile money: While licenses have now been awarded by the Central Bank of Nigeria to at least four payment service banks (PSBs) following UK advocacy through programmes such as EFINA and FSDA, wider penetration of these PSBs and development of business models is needed to ensure greater viability of solar home system business models. The UK’s FSDA programme is now working on this and is well placed to do so as it has good experience from East Africa where Paygo solar is much more widespread.

5 Million Homes: as stated in the last review report, this FGN initiative probably has an over ambitious goal given nascent mobile money and other issues such as forex and business environment which businesses say are deterring them from coming in at scale. The initiative has received significant donor support in terms of technical assistance but to reach all 5 million homes with solar may require some blended finance or donor money given affordability and repayment concerns with some homes. The promised CBN NGN140m Solar Connections Financing Facility also is yet to go live since it was announced in late 2020. This needs to be resolved if the off-grid solar electrification goals in Nigeria’s National Development Plan (2021-2025) are to be achieved.

Importation clearance: importation procedures are quite complex, and clearance of goods is typically slow and often subject to arbitrary customs demands. In spite of HMG’s attempts to engage with the Nigerian Customs Services in 2021, this still remains an issue. This needs to be resolved and remains a hard nut to crack. It is estimated that customs delays when combined with the VAT and customs duties are over one third of the cost of a solar home system in Nigeria.

Apart from the Africa Clean Energy Technical Assistance Facility, other HMG programmes and advocacy initiatives such as Manufacturing Africa, Transforming Energy Access, as well as some other initiatives by other donors such as GIZ, USAID, and SEforAll and others, continue to influence change and government commitments to actioning outstanding elements of the Energy Compact and the regulatory barriers outlined above. Other HMG activities looking into the near future are likely to be targeted at improving broader business/regulatory environment that will promote local assembly and/or manufacturing of solar products. With sustained engagements such as these, even beyond the Solar Nigeria Programme which has now ended, these efforts will hopefully lead to better policy, regulatory and business environment for Nigeria’s offgrid solar market.

D: RISK

Overview of risk management

Over its lifetime, the Solar Nigeria Programme’s approach to managing risk was based on frequent engagement and communications between the FCDO programme team and the delivery contractors. Through monthly reports shared by delivery partners, a section dedicated to risks typically showed already existing risks and emerging issues which the programme grapples with. These issues were then usually discussed on a phone call between the FCDO team and the delivery partners often leading to resolutions on how to resolve them. More difficult issues were usually escalated to the FCDO Team Leader, who may then escalate to the Development Director.
Overview of programme’s key risks and mitigation

A “major” risk rating was retained throughout the life of the programme from inception till the end. This risk rating was largely influenced by the difficulty of the operating context within which the programme delivered, especially with the solar installations for health and education facilities in northern Nigeria, where security conditions were challenging and unpredictable. These security risks were mitigated mostly through engagement of dedicated security risk services by the delivery partners as well as the FCDO team mandating adequate duty of care down the delivery chain. The programme responded to the security challenge by using both internal FCDO security intelligence as well as the contractors who procured third party security/journey management intelligence services to understand the security situation. This mitigation approach was successful in managing delivery, with the exception of one installation in Konduga in Borno State, which the initial contractor deemed unfeasible to complete given the security risk. This was managed by re-contracting the completion of that installation to another delivery partner who had a higher risk threshold. Other major risks during the programme included the high turn-over of SROs. This was typically managed by ensuring robust onboarding of new advisors and ensuring proper handover notes were prepared and made available by the exiting individual.

There was also a tendency for state governments not to uphold their maintenance and security obligations after installations had been handed over to them. This created potential reputational risks for UKaid given that many of these installations were branded has having received UKaid support. Attempts to mitigate this risk included always advocating during meetings with Governors, Commissioners and Directors in government in beneficiary states about the need to commit funds to maintaining these installations. This kind of advocacy obviously had limitations, considering that once installations had been completed there was usually little leverage left besides continuously having to appeal. It was also usually difficult to try to retain leverage through new programmes working in those states as owners of new programmes often simply wanted to get on with their own programme objectives rather than being held back by “baggage” from previous progammes. The FCDO needs to think through solutions for holding such leverage across its portfolio, for example through its Mutual Accountability Framework in respective states.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
Performance of partners and FCDO, notably on commercial, and financial issues

The Solar Nigeria programme has been in implementation since 2014 and has since leveraged additional EU funding of up to 37.5 million Euros in 2017, working across three different suppliers, with projects spanning Lagos, Kaduna, Kano, Adamawa, and Borno, all under the FCDO team management, as well as private sector grantee markets across the entire country.

2020 was the final implementation year across all contracts, and with the exemption of the IFC trust fund which was extend (with no additional funds) only to allow IFC monitor and report results from the advisory trust fund, all major contracts on the programme including ASI’s and AECOM’s contracts were closed on or before December 2020, hence the following programme management highlights here do not differ particularly from what was reported in the 2020 review report.

Programme delivery was done through three main implementing partners including Adam Smith International (ASI), AECOM and IFC. ASI managed a total of £27.73m, which included £4.26m for social solar installations, £15m for consumer and commercial grant-awarding activities, as well as £8.47m for other technical assistance such as for the government workstream. AECOM managed £7.80m for all UK-funded social solar installations, as well as £36.36m for EU-funded social installations. For both ASI’s and AECOM’s solar installations, Em-One was a downstream delivery subcontractor, and was later directly contracted for the completion of the Konduga solar installation. IFC managed £1.58m for the consumer and commercial advisory trust fund programme. For the IFC component, FCDO oversight could have been much stronger, and the dearth of proper communication lines between the IFC and the inhouse FCDO team especially in the later years of the programme (as SROs changed) on one hand, and between the IFC and the ASI component on the other hand, meant there were little opportunities for cross-component synergies. Although both components separately delivered positive results and good VFM, their results could potentially have been stronger had those exchanges and linkages been encouraged.

On financial performance, the spend rate overall was in line with the budget expectations across service providers where security challenges did not have a direct impact, and they have all spent within allowable variance limits. The main service provider (ASI) operated within a tight TA budget (especially in its last implementation year in 2020) and proactively applied reasonable VfM measures in the management of the available resources.
SNP-ASI TA
	Forecasted Total	Actual Total	Variance	Percentage
Sep-19 to Sep-20	493,768.00	502,368.49	-8,600.49	-1.74
Oct-20 to Dec-20	146,330.00	156,096.59	-9,594.33	-6.56

AECOM also managed its finances through the Covid-19 challenges, as well as through the security situation in the northern states of Adamawa, Kano and Kaduna and Borno States. Although AECOM was unwilling to work in some of the locations in Borno State deemed as very dangerous due to insecurity risks, the company was able, alongside downstream partners Nuvo and Em-One, through proactive stakeholder engagement during the covid pandemic, to impressively surmount interstate movement restrictions, with their staff also willing to meet project deadlines despite the health risks.

SNP Capital Spend – AECOM – UKaid funded
	Forecast	Actual	Variance	Percentage
Sep 2019 – Dec 2020	£11, 313	£11, 313	0	0%

Independent financial audits for suppliers, ASI and AECOM, were conducted under the programme since inception till end of final spend, with the exception of the IFC trust fund for which there was limited visibility of the FCDO programme team until the later years of the programme, and for which no financial audits have been conducted.

All financial audits conducted for ASI and AECOM throughout the programme revealed useful findings which typically improved the performance of each contractor in the subsequent years. All of the audits, including the last one which was done in 2020 for both ASI and AECOM have been successfully completed in line with the FCDO smart rules with no qualified auditor opinions.

The programme maintained an asset register which was typically updated by ASI on a biannual basis and reviewed by FCDO Programme Managers. The team conducted periodic asset verifications to ensure that programme’s assets were being effectively managed and maintained. The last independent audits confirmed that FCDO assets were maintained well and managed according to agreement between the service provider and FCDO. In December 2020, the FCDO team working collaboratively with the implementing partner, ASI, successfully concluded the programme’s assets disposal process in line with FCDO smart rules.
Date of last narrative financial report	July 2020
Date of last audited annual statement	December 2019

Monitoring and Performance of Partnerships

The main avenues for monitoring performance of partnerships over the years on the programme were through reports, periodic calls with partners, and field visits. Field visits were not always feasible, given the security challenges across northern Nigeria and also constrained during the final year (in 2020) by the Covid-19 pandemic lockdowns. In those cases, the FCDO team relied on suppliers’ monitoring data and held virtual beneficiary meetings as part of yearly review process to validate delivery results. However, all goods delivered were verified by FCDO through shipment clearances and invoices, and all completed solar installations were verified and assured through annual review visits to the sites, and in cases such as in remote parts of Borno were visits were impossible due to security constraints, they were verified through photos and reports as well as interactions with beneficiary government organisations who confirmed the delivery of installations alongside hand-over notes between the delivery partners and beneficiary government representatives who signed the hand over notes for each solar project site.

Key partnerships over the life of the programme, included with key beneficiary state governments especially the Lagos State Electricity Board (LSEB) and the Kaduna State Power Supply Company (KAPSCO) who continue to speak very positively about DFID’s/FCDO’s investments in their states. Other key government partnerships include with the Office of the Vice President as well as the Rural Electrification Agency. HMG relationships with the REA continue very smoothly and the organisation remains a good entry point for HMG advocacy and influencing with the Nigerian Government on offgrid solar. Other key partnerships included the EU Delegation who committed 37.5 million Euros to DFID, and continue to engage with FCDO today through development partner working groups on both on- and off-grid solar.
Value for Money
From inception till the end, Value for Money (VfM) was a key part of Solar Nigeria’s operating model. Key to the SNP model for VfM was not simply reducing costs, but ensuring the highest quality inputs at reasonable costs, and maximizing the outputs and impacts from these inputs, while also ensuring compliance with FCDO Supplier Code of Conduct and delivery against contracts’ key performance indicators and terms and conditions. Aspects of the programme, essentially the ASI-implemented components which accounted for the major chunk of the programme, were discussed in the 2020 review report in terms of the 4 Es (economy, efficiency, effectiveness and equity). No further VFM analysis have been done on the programme since then as activity closed in 2020 with no further funding having been provided to partners since 2020. Key VfM highlights and excerpts from the 2020 review are presented in the following paragraphs.

Economy: One of the successes of Solar Nigeria was the programme’s demonstrated ability to attract and retain talented team members in a very challenging operating environment in Nigeria. The SNP model married world class international technical experts with high quality local professionals, building the capacity of the latter while work was ongoing. This represents good value for money while ensuring average unit cost of consultants were kept at a low average consistently over the life of the programme.
	2015	2016	2017	2018	2019	2020
Average Daily Rate (£)	537	513	504	511	524	510
National (or local) Consultants Utilisation (%)	63%	61%	63%	81%	86%	89%

The trend in the above table is evidence of Solar Nigeria’s shift to prioritise the use of local expertise, as the utilisation rate of national consultants increased by 26% between 2015 and 2020. The programme was able to shift to using more national consultants by engaging high-level consultants early in the programme to provide support while also building the capacity of national consultants.

The programme’s delivery model also provided outstanding value for money and cost control, maintaining programme management unit costs below 4% of the overall programme spend. This was achieved by significant efforts made to minimize overhead and PMU costs by benefiting from economies of scale in estate and fleet management, shared security information and experience in finance and administrative management carried out by ASI West Africa Operations. Further costs were reduced by personnel, furniture and office floor space shared with other ASI-implemented FCDO-funded projects. Also, throughout the duration of the programme, the programme ensured additional value to FCDO by reducing grant management fees from 6.5% to 5% with £86,000 ploughed back to fund critical aspects of the programme, for example monitoring and evaluation and communications activities.

Efficiency: In seeking efficiency, the programme worked to maximize both the quality and the quantity of outputs. The programme’s model promoted exceptional VfM through efficiency in the following ways:

Supported only projects with high leverage factors: £15 million deployed by the Lagos State Electricity board for the delivery of operations and maintenance. This is also true of the leverage numbers (i.e. finance mobilised) in the Commercial and Consumer workstreams.

Implemented lessons learned: SNP proactively engaged in pilot programs to catalyse the long-term impacts of the programme. Application of lessons learned from previous programming in Lagos helped to improve efficiency, effectiveness and sustainability in Kaduna and Borno phases. Commercial and Consumer pilots enabled SNP to gain fast traction, test assumptions, and in build learning for scaling up solar interventions in the private sector.

Ensured consistent, high quality outputs linked to the overall strategic goal: SNP established rigorous processes in place to ensure the highest quality outputs. This included adherence to and, in many cases, superseding international standards in procurement of solar systems. Consumer and commercial grant disbursements and grantee performance involved rigorous tracking, where each grantee performance was assessed against a range of indicators through quarterly monitoring reports combined with periodic, and annual review, meetings.

By bulk buying a lot of solar components upfront there were cost savings. The contract model used with AECOM also reduced costs as it, i) worked on a modular system rather than specifying exact technology which could change, and ii) put the risk of changes and delays in terms of price on to the contractor – something which was key with Borno were security risks were significant.

A major challenge however was the administrative burden of the programme due to the contractual complexity and number of contract amendments. This was partly as a result of the prevailing UK rules around ASI at one point but also due to security delays. Although it would be good to avoid this in future, it may be a consequence of Works contracts.

Effectiveness: The efficient approach to delivery completed by an experienced team of professionals on the implementing partner end using an exposure to lessons learned from the international arena to gauge how the market would respond to local dynamics of the complex Nigerian micro-economic environment to identify when and how best to target programme activities, also resulted in good value for money on the effectiveness dimension. The mobilisation of additional 37.5 million Euros from the EU for additional social projects in northern Nigeria on top of UKaid, as well as grantee companies on the commercial end mobilising as much as over 600% of the UK aid grant spent in the pilot phase are all impressive indicators of effectiveness of spend.

Equity: Being a programme aimed at powering the Nigerian economy through an accelerated growth in the solar energy market, this programme naturally served underserved and unserved segments of the Nigerian economy, thus helped to promote inclusiveness and equity. The vast majority of the schools and clinics targeted in Lagos were in rural and peri-urban areas, and most of the installations in northern Nigeria were in rural hinterlands serving a high proportion of economically underprivileged citizens, including a remarkable number of women and school children (in millions) with access to more efficient health care and education services powered by reliable access to solar. The private market components, particularly the consumer/household components were also naturally suited to promoting gender-based and age-based inclusiveness as lighting systems such as solar lamps and small stand-alone solar home systems are particularly helpful for lighting small business such as shops, lighting for doing household chores, and for reading in homes.

Overall, in terms of VfM, this programme has demonstrated significant returns on investment, especially considering its pioneering role in championing the development of Nigeria’s solar market in those early days and years when the market was nascent and struggling. The programme has demonstrated visible successes on solar, and generated good will for the solar sector through conspicuous solar projects in several public schools, clinics and hospitals across Nigeria. Very importantly, these projects and UKaid support have created an unquantifiable legacy as they are acknowledged in Nigeria’s policy documents and key national development plans as very critical donor support towards accelerating Nigeria’s offgrid solar sector. In addition, many of the solar companies whom the programme supported in those early stages, while they struggled through rounds of economic recession and poor sales – when no other donor or financier was there to provide finance due to profitability concerns – continue till today to recount the impacts of UK Solar Nigeria Programme grants in helping them stay afloat in those early days until they could demonstrate the viability of their business models. Today, many of those companies are now raising millions of dollars in Series A and Series B investments for expansion of their businesses and for further penetration of the market – multiple times the initial grant investments of UKaid.
Progress on recommendations from last annual review of the programme

There were three major recommendations from the last review. One was for an independent final evaluation of the programme to be conducted, the other was to successfully complete the Konduga installation, and the final one was to ensure successful close out of the EU-funded work. The Konduga installation was completed in December 2020 (shortly after the 2020 review report was published), and all EU-funded installations as well as cross-cutting M&E, communications and visibility activities have all been completed. However, the independent third-party evaluation, which was planned to happen in 2021, sadly did not take place due to budget limitations. Further, the EU has been conducting a time-consuming and not very practically orientated audit which has been ongoing since January/February 2021.

This review is therefore inevitably unable to incorporate any significant additional findings (against what was envisaged in the 2020 report) since the independent evaluation was not conducted. As such, it is recommended that this report – which in reality reads more like an addendum to the 2020 report, having not much substantially to add to the details in the 2020 report given programme activity virtually ended in 2020 – be considered complementary to, and as much as possible, be used in conjunction with the 2020 review report.