## EBA Logframe
Please refer to the Smart Guide for advice on completing the various fields in the logframe.
Smart Guide
PROJECT TITLE
IMPACT | Impact Indicator 1 |  | Baseline (October 2018) | Milestone 1 (September 2019) | Milestone 2 (September 2020) | Milestone 2 (September 2021) | Target (September 2022)
Increased self-reliance within the Ministry of Education in managing the education sector and delivering quality education services to Ghana's children, including the most vulnerable | Proportion of P4 pupils with proficiency in (i) mathematics (ii) English in NEA - dissagregated by gender, age, location and disability | Planned | Maths: 22% English: 37% | Maths: 24% English: 39% | Maths: 27% English: 42% | Maths: 30% English: 45% | Maths: 33% English: 47%
Achieved
Source
National Education Assessment (NEA) via NaCCA, Education Strategic Plan 2018-2030 indicator reporting
| Impact Indicator 2 |  | Baseline (October 2018) | Milestone 1 (September 2019) | Milestone 2 (September 2020) | Milestone 2 (September 2021) | Target (September 2022)
| Net enrolment rate in (i) primary (ii) Junior High School | Planned | (i) 91.1% (ii) 49.7% (2016/17 data) | (i) 89.3% (ii) 48.5% (2017/18 data) | (i) 87.3% (ii) 48.4% (2018/19 data) | (i) 90% (ii) 90% | (i) 93% (ii) 93%
|  | Achieved |  |  | (i) 87% (ii) 86% (2018/19 data)
Source
EMIS Annual Census, GSS out-of-school child survey, UNICEF multiple indicator cluster survey (MICS), Education Strategic Plan 2018-2030 indicator reporting
| Impact Indicator 3 |  | Baseline (October 2018) | Milestone 1 (September 2019) | Milestone 2 (September 2020) | Milestone 2 (September 2021) | Target (September 2022)
| Proportion / Number of primary-age out-of-school children | Planned | 6.5% | 6% | 5.5% | 5% | 4.5%
Achieved
Source
EMIS Annual School Census, National 2021 Population Census, Ghana National Household Registery (GNHR) survey, GSS out-of-school child survey, UNICEF multiple indicator cluster survey (MICS), School re-entry data, census 2021 reults, EOF oiut-of-school child survey
OUTCOME 1 | Outcome Indicator 1 |  | Baseline (October 2018) | Milestone 1 (September 2019) - PbR Indicator 1.1 (£50,000) | Milestone 2 (September 2020) | Milestone 3 (September 2021) | Target (September 2022) | Assumptions
Ministry of Education owning and implementing reforms and driving delivery across education | Extent of Ministry of Education ownership and implementation of reforms to basic education, including planning, prioritisation, budgeting, performance monitoring and reporting | Planned | ESA, ESP 2018-2030 and medium-term plan 2018-2021 and budget approved by Cabinet. MoE Reform Secretariat launched | Final ESP, medium-term plan, priority reforms and budget published. Reform Secretariat set up and strengthening delivery systems. Government reports annual progress against ESP results framework and priority reforms to development partners and public. | Government reports annual progress against ESP results framework and priority basic education reforms to development partners and public. Government allocates increased budget towards delivery of basic education reforms. Percentage of total annual education budget spent on compensation (staff salaries) decreases, and budget for goods and services increases | Government commits to allocate 20% of total expenditure to education. MoE reports progress against ESP results framework and reforms to DPs and public. Education sector plan 2018-2021 reviewed, and 2022-2025 plan developed. | Government allocates increased budget towards education (progressing to 20% of total expenditure). Government reports annual progress against ESP results framework and reforms to development partners and public. Education sector medium-term plan 2022-2025 published. | Leadership commits to strategic prioritization and clear goals in reforms. National-level capacity development impacts service delivery at local levels. Wider determinants of education outcomes such as macroeconomic context, political commitment, nutrition, sanitation, poverty etc do not worsen
|  | Achieved |  | Final ESP, medium-term plan, priority reforms and budget published and distributed. ESP launched by Minister of Education at the National Education Week (August 2019) | MoE developed Education Sector Progress Report 2019 (but did not report against ESP results FW). MoE reported progress on reforms and C-19 response to stakeholders at NEW 2020. Government spend on education increased from GHS 11 bn in 2019 to GHS 17 bn in 2020 (14-15% of total expenditure). No change in percentage allocated to compensation or G & S
Source
ESP 2018-2030, Cabinet minutes, Annual governement and Ministry of Education budget reports, Roadmaps and monthly progress reports, annual reports against ESP 2018-2030, Joint Sector Reviews, public commitments, annual Education Sector Performance Reports (ESPR), Government, Imani and other stakeholder annual budget analysis
| Outcome Indicator 2 |  | Baseline (October 2018) | Milestone 1 (September 2019) - PbR Indicator 1.2 (£50,000) | Milestone 2 (September 2020) - PbR Indicator 1.3 (£100,000) | Milestone 2 (September 2021) | Target (September 2022)
| % of priority basic education reform Roadmap targets achieved and demonstrating improvements to delivery of education (annual) | Planned | 0 | 70% of 2019 Roadmap Key Performance Indicator targets for 2 priority reforms to basic education achieved | 70% of 2020 Roadmap Key Performance Indicator targets for 2 additional priority reforms to basic education achieved. Demonstrating progress post covid restrictions | 70% of 2021 Roadmap Key Performance Indicator targets for priority reforms to basic education achieved and demonstrating improvements to education indicators | 70% of 6 priority reforms completed, focused on improving learning outcomes in basic education implemented, and demonstrating improvements to education indicators
|  | Achieved |  | NaCCA and NIB together have achieved over 70% of their KPIs in their 2019 Roadmaps | Over 70% of the 2020 Reform Roadmaps KPIs for education reforms achieved. MoE rolled out new KG-P6 curriculum nationwide from Sept 2019, developed new National Learning Assessment framework, increased school inspections, established school registration system, introduced new in-service teacher training timetable, increased percentage of licensed teachers in basic schools, rolled out distance learning via TV, radio and online lessons
Source
Annual government and MoE reporting on progress against ESP 2018-2030 and reform areas, progress towards priority reforms and ESP targets based on Roadmaps and feedback from districts/schools, feedback from students and teachers, media reports
OUTCOME 2 | Outcome Indicator 3 |  | Baseline (October 2018) | Milestone 1 (September 2019) | Milestone 2 (September 2020) | Milestone 3 (September 2021) | Target (September 2022)
Ministry of Education and related agencies able to effectively resource, manage and implement CBE to reach out-of-school girls and boys | Amount of Ministry of Education basic education budget spent on CBE programmes (annual) | Planned | CBE programme funded by DFID. Government commitment to allocate 1% of basic education budget to CBE | Ministry of Education spends £400,000 (GHC 2.48) allocation commitment for CBE implementation in 14 districts (for cycle 6) | Ministry of Education meets its commitment for implementing the CBE programme (for cycle 7) | Government meets commitment to allocate budget to CBE to support out-of-school children through EOF | Improved government financing of CBE, including through CEA. Government meets commitment to spend at least $1.5 million on CBE for out-of-school children through EOF
|  | Achieved |  | MoE spent £400,000 to support the implementation of Cycle 6 | MoE met its commitment to implementing CBE cycle 7 in 17 districts. However, given limited fiscal space, MoE was unable to co-finance CBE at expected levels, outside of salaries for national-level CBE PIU and district-level CBE staff
Source
Annual government & Ministry of Education budget and expenditure reports, budget and expenditure reports from 14 districts implementing CBE, annual government audits, EOF reports
| Outcome Indicator 4 |  | Baseline (2018) | Milestone 1 (2019) | Milestone 2 (2020) | Milestone 3 (2021) | Target (September 2022)
| Effective government strategy for continuation of CBE programmes to support out-of-school children | Planned | Government approved CBE policy in place | CBE policy implemented. Strategy for alternative funding and implementing partners for CBE in place. Government capacity to manage CBE strengthened | Final CBE Policy published and rolled out. Government plan and funding for CBE Cycle 8 (to start Oct 2020) in place. Complementary Education Agency (CEA) established, and capacity developed. Agreements signed between MoE/GES, service providers and social investors under EOF project | Agreements signed between MoE, service providers and social investors to run CBE for out-of-school children through EOF, and implementation started | Increased availability of government-managed CBE programmes for out-of-school girls and boys, and improved government management of CBE implementing partners
|  | Achieved |  | CBE Policy implemented for Cycle 6. Strategy for alternative funding and implementing partners for CBE includes GoG budget allocation and new EOF project starting in 2020. GoG capacity to manage CBE strengthened through NFED collaboration. | Minister of Education approved final CBE Policy 2020 and made this available to non-state actors and DPs interested in EOF. MoE yet to finalise a plan and budget for CBE cycle 8. MoE put a Bill to Parliament to establish Complementary Education Agency (CEA). MoE designed and launched EOF in June 2020, but agreements yet to be signed with providers and investors
Source
EMIS Annual Census, 2020 National Census dataset on out-of-school children, GES reports on CBE implementation in 17 districts, third-party spot-check monitoring of CBE activities/students, research reports on CBE, CBE Policy, CBE PIMs, Ministry of Education budget for out of school children
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (October 2018) | Milestone 1 (September 2019) - PbR Indicator 2.1/2.2/2.3 (£100,000) | Milestone 2 (September 2020) | Milestone 2 (September 2021) | Target (September 2022) | Assumptions
Effective delivery systems in Ministry of Education that enable the implementation of priority education reforms | Number of high-quality Roadmaps for priority education reforms reported on to show implementation progress | Planned | No reform Roadmaps | At least 70% of annual Roadmaps for education reforms are in place with named Reform Owners (approved by Education Minister). Roadmaps define targets, KPIs, activities, timelines, risks and data sources. Roadmaps communicated to stakeholders, and formally reported on monthly. | At least 70% of basic education reform Roadmaps for 2020 are in place with named Reform Owners, collaborating agencies, and district-level overall delivery plan (approved by Education Minister). Reform Roadmaps are used to track and analyse progress on a quarterly basis (activities, targets, timelines, risks). | 2021 basic education reform Roadmaps are in place (adaptated for COVID-19 response) and have delivered at least 70% of KPIs. Roadmaps used to track and analyse progress and delivery on a quarterly basis, including from districts and schools | 2022 basic education reform Roadmaps with clear activities, targets, timelines and risks developed for key reform areas, communicated to stakeholders and used to track and analyse progress on priority basic education reforms. | Committed leadership and resources from MoE towards reform agenda. Reform Secretariat able to manage possible tension with Reform Owners and implementing staff, and maintain Minister's commitment to reform agenda. MoE, GES, agencies and DFID have capacity to oversee, manage and implement programmes. Programme timeframe and context allows trialling innovations and new ways of working. Robust data is available, collected, analysed and monitored to show credible trajectory of progress towards reform targets
|  | Achieved |  | 92% (11 out of 12) key education reform Roadmaps developed and approved by Minister of Education, including KPIs, activities, timelines, ROs, resources, risks and data. Roadmaps reported on quarterly . | 77% of basic education reform Roadmaps for 2020 approved by the Minister of Education, including Reform Owners, objectives, KPIs, activities, timelines, resources, budget and data. Reform roadmaps used to track and analyse progress quarterly
Source
Roadmaps developed for each reform area and reform owner, Education Minister/Chief Director approval of Roadmaps, monthly/quarterly/annual update reports against Roadmaps, data sources and databases for tracking progress towards priority reform areas, district-level accountability plan and delivery chain maps
| Output Indicator 1.2 |  | Baseline (October 2018) | Milestone 1 (September 2019) | Milestone 2 (September 2020) - PbR Indicator 2.4/2.5 (£100,000) | Milestone 2 (September 2021) | Target (September 2022)
| Number of Quarterly Performance Accountability meetings (including ATM) held with Minister of Education to discuss and drive progress of reforms | Planned | 0 ATM meetings | At least 2 ATM meetings chaired by the Minister of Education held to review Roadmaps, progress reports and data on priority basic education reforms, and direct action on issues | At least 4 Performance Accountability meetings (quarterly) chaired by Education Minister held to review Roadmaps, progress reports and data on priority basic education reforms, and direct action on issues. At least 2 technical working group meetings with Focal Persons and two (2) coordination meetings facilitated by the RS at national and district levels | At least 3 Performance Accountability meetings chaired by Education Minister to review delivery against basic education reform Roadmaps, COVID-19 response, data and progress reports, and to direct action on issues. At least 2 meetings with District Education Directors to review delivery at district and school levels | At least 3 Performance Accountability meetings chaired by Education Minister to review Roadmaps, progress reports and data on priority reforms. At least 2 meetings with District Education Directors to review delivery at district and school levels
|  | Achieved |  | 2 ATM meetings held, chaired by Ministers of Education to review progress on reforms. Meetings used to direct action on issues | 3 Performance Accountability meetings and 2 coordination meetings held, chaired by Ministers of Education to review progress on reform initiatives and COVID-19 response. 7 technical working meetings held with technical officers / focal persons.
Source
Performance Accountability meeting agendas and minutes, Monthly/quarterly updated Roadmaps presented at Performance Accountability meetings
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline (October 2018) | Milestone 1 (September 2019) | Milestone 2 (September 2020) | Milestone 2 (September 2021) | Target (September 2022)
30% | Effective data collection and analysis systems for priority basic education education reforms | Planned | EMIS in place | Data collection and analysis plan for Roadmaps in place - defining key indicators, data sources, data collection and analysis tools, staff, monitoring mechanisms, schedule, and gaps for priority basic education reforms. | MoE/GES Comprehensive Data Management system, and district-level accountability and data reporting system in place initiated. RS using robust, timely data on key indicators to analyse and track progress of priority basic education reforms | Comprehensive Data Management system with dashboard being developed, EMIS and MSRC data being linked, platform for data collection and analysis at the school level initiated . | Data collection, analysis and reporting systems established and capacities developed for smart measurement and progress tracking, analytical problem-solving and innovation
|  | Achieved |  | Data for tracking progress on priority reform Roadmaps mapped by RS in Performance Management Framework, based on existing systems and EMIS | NERS is coordinating development of a Comprehensive Data Management System, with a Data Visualisation Dashboard. NERS has used data from a Fidelity of Implementation study, 2 ‘Deep Dive’ exercises, and ROs to track progress of education reforms.
Source
MoE/GES data collection systems, EMIS, UIS
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (October 2018) | Milestone 1 (September 2019) | Milestone 2 (September 2020) | Milestone 2 (September 2021) | Target (September 2022) | Reform Secretariat able to build coalitions and ownership of reforms at all levels. Reform Secretariat able to build incentives throughout the delivery system through appropriate signalling and communication. Technical partners offer good VfM and quality TA. DFID's PbR component for Reform Secretariat incentivises better performance, and not perverse incentives/gaming. MoE and GES have clear strategy and demand for technical assistance. MoE, GES, agencies and DFID have capacity to oversee, manage and implement programmes. Programme timeframe and context allows trialling innovations and new ways of working
Increased capacity of Ministry of Education to monitor, track and implement priority education reforms | Effective Reform Secretariat support for Ministry of Education to track and lead delivery of priority education reforms | Planned | MoE Reform Delivery Framework and Reform Secretariat launched. Reform Secretariat staff job descriptions defined and recruitement conducted | Reform Secretariat staff with the right experience and skills recruited and operational (50% female). RS responsibilities and reporting lines agreed. RS support MoE to (i) develop annual plans (ii) prioritise and coordinate reform activities (iii) monitor and track reform progress (iv) report reform progress to Minister of Education. RS conduct at least 2 'deep dives' to provide MoE/GES with robust insights, data and analysis of blockages and progress on reforms. RS identifies required areas of TA for MoE/GES | Reform Secretariat fully staffed with the right mix of people and operating effectively. RS supports MoE to (i) develop annual plans and COVID-19 response (ii) prioritise and coordinate reform activities (iii) monitor and track reform progress (iv) report reform progress to Education Minister (v) conduct research and analysis of blockages and issues (vi) strengthen ROs capacity (e.g. additional staff, budget) | Reform Secretariat fully staffed with the right mix of people and operating effectively. RS supports MoE to (i) develop annual plans (ii) prioritise and coordinate reform activities (iii) monitor and track reform progress (iv) report reform progress to Minister of Education (v) embed focus on gender and inclusion (vi) disseminate findings of research conducted in 2020 | Reform Secretariat staffed with capable, motivated and effective advisers and analysts, and perceived as helpful by Ministers of Education and Reform Owners. Reform Secretariat helps prioritise and coordinate reform activities, provides MoE/GES with robust insights, data and analysis to show blockages and progress on reforms, and builds MoE/GES capacity for delivery
|  | Achieved |  | Seven key staff (29% female) are in the RS consisiting of forur advisers and three programme /support staff. RS responsibilities and reporting lines developed and agreed. The RS has increased MoE capaicty to (i) Develop annual Reform Roadmaps (ii) Prioritise and coordinate focus on 6 key reforms in 2019. (iii)Monitor and track reforms progress through analysing quarterly reports and data from ROs agaianst Roadmaps . (iv) Report reform progress to Minister of Education, based on data and evidence and leadaction on issues. RS condcuted an initial deep dives in December 2018 and has developed ToRs and plans for another two deep dives (v) RS identified required areas of TA for NaCCA and NIB. | NERS has 9 key staff covering policy, communications, M & E, research, performance monitoring, and programme delivery. NERS has increased MoE capacity to plan for reforms, develop a COVID-19 Education Response, prioritise and coordinate reforms, monitor and track progress through quarterly reports to Ministers of Education, and understand delivery issues
Source
Perception Survey feedback from Reform Owners in MoE/GES, Minister/Deputy Minister of Education, Reform Secretariat staff, development partners. Documentation showing RS coordination/prioritisation of MoE/GES reforms, and TA support/capacity building activities. RS TA plan for MoE/GES. Letters from Minister of Education pre and post 2020 elections about role and need of Reform Secretariat. Media reports. Analysis by independent DFID education adviser
IMPACT WEIGHTING (%) | Output Indicator 2.2 |  | Baseline (October 2018) | Milestone 1 (September 2019) | Milestone 2 (September 2020) | Milestone 2 (September 2021) | Target (September 2022)
30% | Effective MoE use of Technical Assistance to support implementation of Ministry of Education priority education reforms | Planned | 0 | TA plan to support MoE/GES Reform Owners to deliver priority basic education reforms in place, approved by Minister of Education. TA and UK partnerships facilitated by DFID is effectively managed and utilised by the MoE to support reforms | TA and UK partnership support provided via DFID to MoE/GES improves government capacity, knowledge and delivery of priority basic education reforms. TA plan updated to identify additional support needed | TA and UK partnership support provided via FCDO to MoE/GES improves government delivery of basic education reforms. TA plan updated to identify additional support needed | Effective, adaptive and flexible TA and UK partnerships provided to Ministry of Education and Ghana Education Service to support delivery of priority basic education reform areas
|  | Achieved |  | Draft capacity-development and TA strategy developed by RS, which led to Minister of Education approving TA requests to DFID for curriculum and inspection reforms. TA managed by NaCCA and NIB to support reform delivery. Partnership between GPI and RS utilised to strengthen capacity of ROs and agencies to conduct data analysis, management, reporting and deep dives | TA contracted by FCDO has been used by MoE/GES to fill critical competency gaps and progress implementation of curriculum, assessment, inspection and CBE reforms. MoE/GES has requested TA to support on gender in education and workforce reforms
Source
TA strategy and contracts, Perception Survey feedback from MoE/GES Reform Owners, development partners, monthly/quarterly reports from TA supplier, monthly/quarterly reports from MoE, TA contract deliverables, TA ToRs
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (October 2018) | Milestone 1 (September 2019) | Milestone 2 (September 2020) | Target (September 2021) |  | Assumptions
Government of Ghana's capacity to resource, manage, and implement complementary basic education strengthened | Number of out-of-school children supported by MoE/GES to complete CBE programmes (annual) - dissag. by gender, age, location, disability | Planned | MoE/GES supported 20,000 out-of-school children through CBE programmes into formal school in 14 districts | MoE/GES support at least 20,000 out-of-school children through CBE programmes and into formal primary school | MoE/GES support at least 20,000 out-of-school children through CBE programmes to improve literacy, numeracy and life skills | 40,000 additional CBE learners (50% female) in total supported through Government of Ghana and FCDO funds to improve their learning and transition into formal schools |  | Committed leadership and resources from MoE towards CBE. MoE, GES, agencies and FCDO have capacity to oversee, manage and implement programmes. MoE and GES have clear strategy and demand for technical assistance. Technical partners offer good VfM and quality TA. Programme timeframe and context allows trialling innovations and new ways of working
|  | Achieved |  | Total :18,983 (9,088) | MoE/GES supported 21,457 out-of-school children (46% girls) in literacy, numeracy and life skills classes under CBE cycle 7. Cycle 7 extended to Dec 2019 as part of COVID-19 response
Source
MoE/GES quarterly progress reports, DFID monitoring visits to CBE classes, reporting through other implementing partners (e.g. Plan International, World Education Inc), data from research reports, transition to school rate data from CBE focal districts
| Output Indicator 3.2 |  | Baseline (October 2018) | Milestone 1 (September 2019) | Milestone 2 (September 2020) | Target (September 2021)
| Timely and effective MoE/GES planning and implementation of CBE in 14 districts | Planned | Agreed MoE/GES Project Implementation Manual in place for CBE cycle 6. Quarterly CBE Steering Committee Meeting dates planned. | (i) CBE cycle 6 implemented by government in line with agreed PIM (ii) Funding for CBE disbursed to 14 districts in time for cycle 7 start-up (iii) GES conducting monthly CBE data collection, quarterly field visits, and annual learning assessments (iv) Quarterly reporting on CBE to MoE Steering Committee | (i) CBE cycle 7 implemented by government in line with agreed PIM, and adapted for COVID-19 response (ii) Funding for CBE disbursed in time for cycle 8 start-up (iii) GES conducting monthly CBE data collection, quarterly field visits, and annual learning assessments (iv) Quarterly reporting on CBE to MoE Steering Committee | Government able to fulfil key functions for planning, financing, managing, implementing, monitoring and evaluating CBE programmes to support out-of-school children (through MoE/GES, EOF unit and Complementary Education Agency)
|  | Achieved |  | i)CBE cyccl 6 activties implemented in line with PIM. Although some activties were not conducted. (ii) GES conducted cycle 6 data collection and field visits although frequesncy was inconsistent. No learning assessment conducted . (iii) CBE cycle 6 and 7 reported on to MoE Steering Commitee at two meetings held over the past year . iv) Funds for CBE disbursed to 17 districts in time for cycle 7. | MoE/GES implemented CBE cycle 7 in 17 districts in line with PIM and a CBE COVID-19 response plan. GES collected monthly data on CBE from districts and CBE PIU did quarterly monitoring. Annual learning assessment not yet conducted. CBE PIU provided one report to CBE Steering Committee in Dec 2020. GoG funding not yet allocated for cycle 8
Source
Project Implementation Manuals, Quarterly CBE Steering Committee meeting minutes, feedback from target districts and communities, MoE/GES quarterly progress reports on implementation, MoE/GES field visit/monitoring reports, MoE/GES expenditure reports, EOF reports
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline (October 2018) | Milestone 1 (September 2019) | Milestone 2 (September 2020) | Milestone (September 2021) | Target (September 2022)
30% | Effective MoE/GES use of Technical Assistance to support implementation and management of Complementary Basic Education | Planned | CBE Management Unit provided TA to Ghana Education Service | TA plan to support MoE/GES to implement CBE in place. TA support for training, policy, coordination, monitoring, evaluation and alternative financing of CBE programmes procured by DFID is effectively managed and utilised by MoE/GES. | TA provided via DFID to support MoE/GES management of CBE improves government capacity, knowledge, delivery, M & E, budgeting and sustainability planning for CBE. TA plan updated to identify additional support needed | TA provided via FCDO used to help MoE/GES start-up EOF and establish Complementary Education Agency to expand CBE, engage service providers, and secure alternative financing for CBE | MoE/GES uses FCDO-funded TA to support effective implementation and management of CBE, through EOF and the Complementary Education Agency
|  | Achieved |  | TA plan to support MoE/GES to implement CBE in place. MoE/GES used TA to help implement formal school teacher orientation for Cycle 6 transition, conduct Cycle 7 community engagement and training of trainers, develop Cycle 7 PIM, conduct annual review, and prepare and submit 2020 CBE budget to Ministry of Finance | TA team supported MoE/GES to assess capacity to continue managing CBE; develop capacity to do CBE learning assessment; develop M & E framework; develop cycle 7 and CBE COVID-19 response plans; train District Education Offices and Directors on CBE; develop a CBE Sustainability Strategy; engage EOF TA team on future CBE support
Source
TA strategy and contracts with alternative funding partners, feedback from MoE/GES, monthly/quarterly reports from TA supplier, Quarterly progress reports from MoE/GES
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
£1.1 million
INPUTS (HR) | DFID (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline (October 2018) | Milestone 1 (September 2019) | Milestone 2 (September 2020) | Milestone 2 (September 2021) | Target (September 2022) | Assumptions
Strengthened evidence base on impact of CBE pedagogy and trajectory of CBE learners in mainstream education | CBE research being used to improve teaching and learning in CBE programmes | Planned | CBE learner assessments conducted for cycle 1 and cycles 3-5 amd evidence shared with stakeholders | At least 5 examples of previous CBE research being used by MoE/GES to improve teaching and learning outcomes in CBE programmes. Further MoE/GES demand for CBE research identified and defined | Assessment of GES CBE COVID-19 response completed, and used to inform continuity of learning for out of school children | CBE cycle 4 tracker study completed to help shape teaching and learning for out-of-school children and in-school children | CBE cycle 4 tracker studies completed and shared with stakeholders, to help shape teaching and learning for out-of-school children and in-school children (especially girls), including through EOF and GEC STAGE project | MoE and GES have demand for ongoing research into CBE, and use of results to inform implementation and policy-making
|  | Achieved |  | Learner Assessments for CBE Cycles 3, 4 and 5, CBE Pedagogy Report, and CBE Final Evaluation Report findings used to strengthen approaches to teaching and learning in Cycle 6. Further MoE/GES demand for CBE research defined in ToRs | Assessment of MOE/GES CBE COVID-19 response is underway
Source
Research reports, presentations on research findings,minutes/reports from CBE Steering Committee meetings and national/international events, changes to CBE policy and implementation documents/practices
IMPACT WEIGHTING (%) | Output Indicator 4.2 |  | Baseline (October 2018) | Milestone 1 (September 2019) | Milestone 2 (September 2020) | Milestone 2 (September 2021) | Target (September 2022)
10% | CBE research being used to improve out-of-school children's transition to the formal education system | Planned | CBE cycle 4 tracker study completed and evidence shared with stakeholders | At least 5 examples of CBE research being used by MoE/GES to improve transition of CBE learners into formal education | Political Economy Analysis study on CBE completed and shared with stakeholders to inform CBE sustainability strategy, and MoE/GES approach to transition out of school children into formal education | Policy Brief on PEA and CBE COVID-19 assessment shared with stakeholders, to inform approaches to help transition of out-of-school child to formal education (especially girls) | Follow-up Political Economy Analysis on CBE completed and shared with stakeholders, to inform government's strategy to transition out-of-school children to formal education, including through EOF and GEC STAGE project
|  | Achieved |  | CBE Final Evaluation Report; Lesson Learning Paper; Tracer Study; Parental and Learner Choice study; and Qualitative Learner Experiences use to strengthen approaches to learner transition | A Political Economy Analysis study of CBE is underway, with draft shared with the CBE PIU
Source
Research reports, presentations on research findings,minutes/reports from CBE Steering Committee meetings and national/international events, changes to CBE policy and implementation documents/practices, changes to support for CBE graduates in primary school system
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)

## Change frame
Use this change log to record all changes to the logframe over the life of the project.
ID | LOGFRAME SECTION | DETAILS OF CHANGE | AUTHOR | DATE
E.g. | Output 1, Indictor 2 | Indicator amended from 'No of children enrolled in primary schools' to 'Number of children enrolled in UNICEF supported primary schools (disagregated by sex) | Joe Bloggs | 2018-01-01
1 | Output Indicator 1.2 - | Reword from “Number of Accounting to the Minister (ATM) meetings held with Minister of Education to discuss and drive progress of reforms” to “Number of Quarterly Performance Accountability meetings (including ATM) held with Minister of Education to discuss and drive progress of reforms” (reworded to reflect this ) | Grace Wood/Patricia Adu-Twum | 2020-06-23
2 | Outpu Indicator 1.1 | Output 1 - include a measure for having a district-level accountability system in place (Output 1.1 has been updated to reflect this) | Grace Wood/Patricia Adu-Twum | 2020-06-23
3 | Output Indicator 1.2 - | include a measure for technical working group/reform coordination meetings facilitated by the RS at national and district levels (this has been reflected on output 1.2 instead) | Grace Wood/Patricia Adu-Twum | 2020-06-23
4 | Output Indicator 2.1 - | Output 2 - include measure for RS supporting ROs to strengthen capacity (e.g. staff, budget) (This has been reflected on output 2.1 and the RS work on supporting the MoE response to COVID 19 has been included as well) | Grace Wood/Patricia Adu-Twum | 2020-06-23
5 | Output Indicator 3.1 | Output 3.1 - Change to “Number of out-of-school children supported by MoE/GES to complete CBE programmes (annual)” as transition data will only be available later than AR deadline (Reworded to reflect this) | Grace Wood/Patricia Adu-Twum | 2020-06-23
6 | Impact Indicator 3 | Impact Indicator 3 - MoE/GES to develop means of tracking numbers and % of OOSC (This update has not been effected yet- an agreement might be reached during this year’s annual review.) | Grace Wood/Patricia Adu-Twum | 2020-06-23
7 | Impact Indicator 4 (Milestone 2) | Impact Indicator 4 - Move Percentage of total annual education budget spent on compensation (staff salaries) down to the Outcome level (This has been updated completely to rather focus on work done on the CBE policy, the new Complementary Education Agency (CEA) agreements on Education Outcomes Fund etc.) | Grace Wood/Patricia Adu-Twum | 2020-06-23
8
9
10

## PbR
RESULTS BASED AID INDICATORS FOR REFORM SECRETARIAT
Payment Indicator | Success Criteria | Logframe Indicator | Lead officials | 2019-09-30 | Amount
1) Reform Secretariat support delivery of MoE vision and reform agenda for basic education | 1. Education Sector Plan (ESP) 2018-2030, medium-term plan and results framework approved by Cabinet, published, and monitored | Outcome 1 | National Reform Coordinator, Reform Owners | 2019-09-30 | 100000
2. 70% of annual Roadmap Key Performance Indicator (KPIs) targets for reforms to basic education (teacher education, curriculum, assessment, inspection, CBE) achieved
| 3.70% of annual Roadmap KPI targets for reforms to basic education (teacher education, curriculum, assessment, inspection, CBE) achieved | Outcome 2 | National Reform Coordinator, Reform Owners | 2020-09-30 | 100000
2)Reform Secretariat improve MoE monitoring, accountability and delivery systems around reforms to basic education | 1. Standard monthly progress reports developed and used for reporting against results targets for basic education | Output 1.1 | National Reform Coordinator, Reform Owners | 2019-09-30 | 100000
2. Roadmaps for each Reform Owner (setting out priority medium-term reform areas, clear activities, targets, timelines and risks) developed and approved by Reform Steering Committee
3. Monthly TWG meetings held for Reform Owners to review progress, unblock issues, and direct action
| 4. Quarterly robust data analysis tracking progress against basic education results targets and reform Roadmaps reported to the Minister of Education at RSC meetings | Output 1.2 | National Reform Coordinator, Reform Owners | 2020-09-30 | 100000
5. Quarterly RSC decisions based on basic education results progress, and actions taken by Reform Owners to drive better delivery and progress recorded and shared

## Guidance Notes
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from DFID and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR). Ongoing monitoring of progress against outcome milestones should still take place as an assessment of whether you expect to achieve the Outcome by the end of the programme will be included in Annual Reviews.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
Progress against Output milestones and results achieved will be assessed and scored during Annual Reviews and the Project Completion Review.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by DFID and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The DFID share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined - if relevant include indicators which towards the DRF / OP / ICF KPIs / MDGs.
l | Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your SRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
DFID’s Approach to Value for Money (Smart Guide) provides further advice on ensuring VfM.

## revisions
Outcome 2 and its indicators belong to CBE
Output indicator 1.3 | The 2021 milestone should be revised to the current status of the dashboard development process . Dashboard development has just started and cannot be used for robust data collection by september 2021
Output indicator 2.1 | Milestone for 2021 talks about research to be conducted but a decision has been reached to diseminate the 2020 deep dive findings
Output indicator 2,2 | Though some amount of TA has been provided for MOE /GES , the FOCA has not taken off so the current TA may not be enough to lead to improvement in the capacity of MOE
Output 4 | belongs to CBE
outcome indicator 2 | Not clear what what the 2 additional priority reforms refers to since at the moment we have all the six reform owners on board