 Programme Completion Review

Title: Improving Reproductive Maternal and Child Health (RMCH) outcomes in Mozambique
Final Programme Spend £ (full life): £ 39.85 million	Review Date:	February 2022
Programme Code: 205074	Start Date: / November 2016	End Date: November 2021

Summary of Programme Performance

Year	2017	2018	2019	2020	2021-22
Programme Score	A	A	A	A	A
Residual Risk Exposure Rating	Medium	Medium	Medium	Medium	Medium

DevTracker Link to Business Case (and any addendum):	http://iati.dfid.gov.uk/iati_documents/4833405.odt
DevTracker Links to all logframes used during programme lifetime:	https://iati.fcdo.gov.uk/iati_documents/59948581.xlsx

A. Summary and Overview

Description of the programme and what it has achieved

The Reproductive, Maternal, Neonatal, Child and Adolescent Health (RMNCH) programme was approved by the UK government in September 2016. Its aim was to reduce maternal and neonatal mortality by tackling key health system constraints over 5 years, in line with the Mozambican Ministry of Health (MoH)’s draft RMNCH Health Investment Case. It took place during a period when Mozambique was subject to a series of external shocks including from COVID-19, major cyclones and fiscal crisis. These shocks had major economic and social consequences which directly and indirectly impacted the programme as resources within the health sector were re-prioritised. The programme focused on achieving two main outcomes 1) Expanding take up of modern methods of family planning and 2) Getting health facilities accredited as being able to deliver comprehensive emergency obstetric and newborn care. These were achieved through five high levels outputs each targeting different actions required to achieve the outcome: Equip / Respond / Enable / Deliver / Coordinate.

 At its inception in 2016, the programme had three components delivered by different partners:

Component 1 (£23.5m from 2016 to 2021) was delivered by the United Nations Joint Programme (UNJP), comprised of UNICEF, UNFPA and WHO to prepare health facilities to provide a minimum level of basic obstetric and neonatal care. This was achieved through a combination of supply-side interventions and technical assistance. £1.6m of these funds were reprogrammed to respond to cyclone Idai in 2019 and an additional £1.2m was reprogrammed to support the Government’s COVID-19 response plan in 2020.

Component 2 (£5.5m from 2016 to 2021) was implemented by a consortium led by Population Services International (PSI) and focused on piloting approaches to increase family planning uptake among adolescents and women in reproductive age in rural and urban areas of Maputo, Gaza and Nampula provinces.

Component 3 (£0.4m from 2016 to 2021) was used to provide technical assistance (TA) to implementing partners and conduct studies to inform programme objectives and direction over its lifetime. This component was implemented through a range of TA service providers.

In 2018, four more components were added:

Component 4 (£2.9m from 2018 to 2020) funding was invested in the programme ‘Rapariga Biz’ (Busy Girl in Portuguese) led by five-line ministries and aimed to prevent early and forced marriages and unintended pregnancies among adolescent girls and young women. It targeted girls between 10-24 years old with sexual reproductive health interventions including mentoring, community radios, comprehensive sexual education, and adolescent family planning services.
[note] Ministry of Youth and Sports as leader, Ministry of Health, Ministry of Education and Human Development, Ministry of Gender and Social Action and Ministry of Justice

Component 5 (£2.1m from 2018 to 2020) was delivered by WHO to support the MoH to prepare for and respond to emergencies. This component provided technical assistance, training, and equipment on climate- and disease-related disasters which regularly disrupt health service delivery.

Component 6 (£800,000 from 2018 to 2021) was delivered by the non-governmental organization Village Reach to pilot the use of Unmanned Aerial Systems (UAS) for the transportation of tuberculosis (TB), and later COVID-19 samples, in remote and rural areas.

Component 7 (£2.5m – August 2020 to 2021) was delivered through funding to the Global Financing Facility (GFF), a multi-donor trust fund managed by the World Bank (WB). The GFF is a country-led financing mechanism based on performance to eliminate preventable maternal, child and adolescent deaths. The UK added this component to ensure continued support to the health sector, including to manage the direct and indirect effects of COVID-19, whilst awaiting a decision on the UK’s longer-term programming in the sector.

Main achievements

According to UNICEF and WB data, maternal mortality rates decreased from 301 per 100,000 women in 2016 to 289 per 100,000 in 2017 (most recent reported data). The neonatal mortality rate decreased from 30.7 to 28.3 per 1000 births from 2016 to 2020. While the programme was not the only intervention in the sector, the decrease in mortality rates is a good indication that this programme has been positively contributing to the government’s RMNCH objectives. Overall, the programme’s achievements aligned well with the business case outcome which was to strengthen the response and resilience of the health system through the five high level outputs cited above (Equip / Respond / Enable / Deliver / Coordinate). The programme’s main achievements are:

- Improvements in institutional delivery capability (Equip): The equipment provided through the programme was a key driver of increasing institutional delivery: 101 health centres with maternity wards and 41 hospitals with surgical blocks were better equipped as a result of the programme (receiving equipment ranging from delivery kits, prenatal, postnatal, family planning and childcare kits, C-section kits, post abortion kits, gloves, mattress and other lab equipment). Almost two thirds (63%) of the health facilities in target areas are now able to offer basic obstetric and newborn care. Ambulances provided have also helped to support the transport of expectant mothers to health centres.

- Increase in the use of contraceptives (Deliver): The programme reached an additional 620,000 women with modern family planning methods. The training and mentorship programmes have increased the confidence of nurses to use long-acting family planning methods. In 2017 such methods represented less than 5% of all contraceptives used in the country; by 2020 this had increased to 10%. As a result, a number of health centres now provide approximately 50 long-acting methods (such as Intra Uterine Devices) per month (compared to what was often zero/month pre-programme) and the community dialogues promoted have been shown to be a good approach to convince adolescents and young women to adopt family planning methods.
[note] FP 2030 core indicator estimates for Mozambique in the year 2020: https://fp2030.org/mozambique

- The quality of the services related to sexual and reproductive health has also improved as a result of nurse training and mentoring: (Enable) 344 maternal and child health nurses have successfully graduated from training. In addition, the mentorship programme was a success. Conversations with mentors showed that peer to peer mentoring was key in explaining the improvement in the quality of services. Nurses acknowledged the contribution of mentors in their work. This translated into a reduction in death rates amongst babies and mothers (usually linked to lack of knowledge and reactivity) as now all health facilities only allow mothers and babies to go home 24 hours after giving birth.

- Increase of human resources in health (nurses and community health workers (CHWs) and the inclusion of health personnel into the budget) (Coordinate). There has been progress in the numbers of CHWs and nurses trained since the beginning of the programme. 2,397 new CHWs and 344 nurses have graduated from training. The Human Resource Health (HRH) Retention Strategy was also developed as a result of this programme, promoting career progression of health workers and health technicians, reducing the turnover of staff. The midterm review of the HRH plan (2016- 2025) showed progress in the number of trained personnel absorbed into the government health system as civil servants (from 90.4% in 2015 to 94% in 2020).

- As part of the programme, at the request of the government, a public health emergency centre was set up in Maputo to coordinate and manage the national response to disease outbreaks and climate related medical emergencies. An example of its activities was the management of the COVID-19 response in 2020. The center will also be able to undertake the surveillance of other diseases including cholera which is endemic.

Major lessons learned, evidence generated and recommendations

1- A key driver of success of the project was the nature of the collaboration between the three UN agencies that gave the project significant leverage. The UN agencies were able to jointly influence the Government of Mozambique (GoM) at national and provincial level and improve their collective impact by building on each agency’s comparative advantage. WHO led on reforms, UNFPA on procurement of contraceptives and UNICEF on the community health worker programme and sustainability. Joint working examples included the development of strategies for water and sanitation in health facilities and the definition of the minimum package of services for health facilities. The result of this collaboration was a joint UN workplan presented to the MoH for future coordination of activities.

Recommendation: In order to continue progress towards the reduction in maternal and child death rates, UNICEF, WHO and UNFPA should ensure they speak with one voice and continue to collaborate while building on each agency’s comparative advantage and avoid working in silos.

2- Despite the activities delivered through the programme, some health centres visited did not have sufficient access to power, water supply or efficient organisation of basic services. This is mostly due to funding constraints of the sector and lack of alignment between partners when looking at supporting health centers. It is necessary to ensure better organisation/coordination of services within the health centres, e.g., improved WASH services by coordinating with the UK’s WASH programme, linked Sexual and Reproductive Health and Rights and HIV/AIDS services by coordinating with partners supporting HIC services or ensuring the availability of disposable items e.g., gloves, masks, syringes etc. at health centres.

Recommendation: FCDO should take a more integrated and holistic approach to programming and explore possibilities to link programmes across the mission, particularly for the delivery of basic utilities such as electricity and water for health services.

3- The systemic lack of human resources for the health sector is of particular concern. Although there has been progress in the system absorbing the number of newly trained nurses (both through the GFF and this programme), there remains insufficient nurses to deliver quality services, as well as few specialised doctors, due to the sector not receiving sufficient resources from the government budget.

Recommendation: FCDO health programs should systematically include other sector ministries (like the ministry of Finance) to tackle issues that have to do with broader public sector reforms, including financial management and human resources. FCDO should advocate for improved budget credibility in the health sector, as there is often a big difference between initial allocations, revised allocations and actual expenditure. This makes planning difficult for the Ministry of Health, and is compounded by sharp changes between years, and a large amount of off-budget spend.

4- It has been challenging to agree on Value for Money (VfM) indicators for some components of the programme, particularly for the first component working with UN agencies. The FCDO’s approach of measuring VfM is not common with delivery partners such as the UN and the World Bank, who did not systematically assess and track VfM indicators over the programme lifetime.

Recommendation: Programme teams should spend more time ensuring that partners develop value for money metrics as early as possible and systematically assess these throughout programme implementation. In some instances, it might have been useful for partners to hire a health financing professional to help them design the VfM indicators.

5- Impact is often linked to the political buy-in of interventions and the willingness to reform systems which can be difficult or slow to take place. Government policies and approaches also changed over time. As a result, it is difficult to trace with precision how much progress at the impact level can be attributed directly to the programme. Partners, especially the UN, failed to track overall impact as most of their reporting focused on output or activity levels while the GoM reports tend to capture overall progress with little detail on activities.

Recommendation: It is advisable to meet regularly with each partner to not only look at progress and how activities are contributing towards programme outcomes, but to also have more regular reviews of the logframe targets to reflect the link to impacts and track changes in the programme. There is also a need to better analyse the data strengthening and the process of data generation to enable tracking of the link to outcomes and impacts.

6- Some of the medical materials delivered were too specialized or too technologically sophisticated for low resource settings especially where electricity and internet were erratic. Equipment use was often also limited as health professionals were not trained on material use and management.

Recommendation: Before materials are purchased, implementers should carry out an evaluation of the environment in which they are to be used in order to make sure they are fit for purpose. Those using materials should be trained in their use and budget provided for this.

7- Medical equipment, particularly equipment used for Caesarean sections or surgery, wore out easily due to high rotation rates and required replacement which was not factored in the original budget.

Recommendation: The durability of equipment and the budget for maintenance and running costs be considered before purchase so as not to end up with underutilised equipment or equipment that quickly needs replacing.

8- Despite the programme supporting various areas in the sector, recurrent issues as basic equipment/consumables as gloves or services such as the transportation of women to the health centers remains. If not looked at, these issues could undermine the impact of this project.

Recommendation: To ensure sustainability and as we are continuing to fund some activities through the FCDO Mozambique planned demography programme, we should be making sure that the budget includes these items or alternatively press the Government of Mozambique and other partners to provide these complementary goods and services.

9- It is important to note that whilst there has been some progress on reducing neonatal and maternal mortality rates, the programme did not meet all planned targets. When it comes to strengthening the health system the programme succeeded in four areas: i) strengthening service delivery, ii) improving supply of medicines and equipment, iii) strengthening human resources and iv) improving the health information system (through the setup of a public health emergency center). However, less progress was made on governance, leadership and financing of the health system. Yet these three components are vital to the sustainability of improvements in the system in the long-term especially as and if more public finance becomes available.

Recommendation: In the future, it would be important to set more realistic expectations when it comes to health system strengthening at impact /outcome level and have a more concrete plan of action to influence at the policy level involving other sectors such as finance and public administration.

10- Throughout the delivery of the programme, there was resistance from the Ministry of Education to allow the delivery of longer acting family planning methods. This is mainly due to socio cultural factors and norms. This is an ongoing challenge for the GFF and progress for family planning in schools.

Recommendation: Evidence-based advocacy by development partners with sector ministries is needed to promote understanding that family planning is key to the demographic transition.

11- The Rapariga Biz project included interventions to address early marriage and pregnancies, but activities were not sufficiently monitored, leading to difficulties in assessing the impact of different activities. However, the mentoring approach was shown to be effective in delaying unintended pregnancies and preventing early marriage.

Recommendation: For future programming (with or without Rapariga Biz), the monitoring and evaluation system should be streamlined and improved before expanding interventions to understand which intervention is most effective.

How this report was conducted

This programme review was completed by the FCDO health team (two health advisers and a programme manager) and informed by a desk review of existing reports from implementing partners, annual reviews of the project since its start as well as two field visits to Zambezia and Nampula with key partners. Finally, a lesson learnt session with the UNJP team was organised after the closure of the first component. The review team also conducted informant interviews with key stakeholders (nurses, beneficiaries, government officials) during field visits.

Actions following approval of this report

Lessons learnt from this report will be shared externally and used to inform FCDO’s policy engagement with the Government of Mozambique and key partners. Some of these recommendations will be included in a successor programme, the Demographic Transition Programme. Lessons identified in the project completion review will be shared with the partners of the new FCDO programme.

## B: Theory of Change and Outcome Assessment

	Planned	Actual
Budget	£34.4 million	£39.85 million. The increase in budget was to fund the GFF.
Timeframe	2016-2020	2016-2021

Outcome: People equitably access and use quality health services	Outcome indicator	Target	Result achieved
	1-Additional users of modern methods of family planning (i) With FCDO contribution (ii) through the State budget / 2-Health facilities accredited as being able to deliver comprehensive emergency obstetric and newborn care (BEmoNC)	(i) 100,000 / (ii) 173,155 / 70%	(i) 620,107 additional users (ii) 6,400,000 Significantly exceeded expectations / 63% Did not meet expectations
[note] Originally DFID - DFID was merged into FCDO mid 2019.

Overall assessment of programme outcomes, sustainability and VfM

Overall, this programme has achieved positive results against outcome and output targets while being flexible in responding to emergencies and changing contexts such as COVID-19 and annual floods/cyclones.

Outcome indicator 1 looked at reaching more women with modern family planning methods. The original target was far exceeded, with over 6.4 million additional users of modern methods of family planning in Mozambique by the end of the programme, compared to a target of 173,155. This was a result of the funding of contraceptives through the UK, the MoH, the Netherlands, UNFPA (independently of FCDO funding), USAID and more recently, the GFF. FCDO’s funds contributed almost 10% of the results (620,107 users) through the UN Joint Programme, demand generation interventions by PSI and the Rapariga Biz programme.

Outcome indicator 2 is linked to the percentage of health facilities certified with the capacity to deliver basic emergency obstetric and newborn care (BEmoNC). Despite various FCDO-funded interventions (training of nurses, procurement and distribution of medical equipment and commodities and the provision of WASH in health facilities) contributing towards this indicator, the target was not met. Only 63% of the health facilities in the country were accredited against a target of 70%. Some issues that prevented sustained progress on this indicator include delays in recruitment and placement of trained nurses to the health facilities, lack of funding to repair broken equipment and only a third (33%) of the initial target of 100 health facilities benefitting from WASH services due to high standards set by the MoH. This reflects the complexity involved in working to strengthen health service delivery systems which not only depends on the provision of materials and training but also on wider structural changes in the system including more human resources for health positions, a functioning local procurement and financing system.

Sustainability

The programme’s sustained impact can be evaluated:

(1) Directly via the impact of the services delivered
The provision of family planning services has a sustained impact through the resulting decrease in unplanned pregnancies requiring maternal/neonatal care and wider reduction in pregnancies reducing pressure on health services. The programme also enabled the continued provision of maternal, child and neonatal services in areas affected by two cyclones, the COVID-19 pandemic and to some extent the conflict in the north of Mozambique.

(2) Through the strengthening of the health system
The revision of policies, development of management mechanisms and training of health workers through the programme strengthened the health system. Examples include: the introduction of the minimum package of services to be offered by the different types of health facilities throughout the country; the establishment of the emergency operating centre to manage disease outbreaks; the training of 5% (344) of new nurses and 25% (2,397) of new community health workers over the last five years, resulting in increased coverage of health services to an additional 2 million people; innovative approaches such as the mentoring of nurses using local professional associations which will improve the quality of service delivery beyond the lifetime of the programme. These changes are a permanent legacy of the programme.

(3) Through sharing lessons and improving coordination between implementing partners
FCDO worked in close collaboration with its partners to ensure good value for money investments but also to reflect on lessons learnt and how to efficiently address the bottlenecks in the health system. For example, the review of the Rapariga Biz programme has influenced the selection criteria of components within the programme and a more streamlined approach being taken by the UN and partners towards the programme. FCDO also encouraged closer collaboration between the UN and the World Bank in their work on maternal and child health, had regular monitoring sessions to review performance and will make sure the lessons from this programme are shared with partners.

(4) Through programme learning for the next phase of our health funding and policy:
Elements of the RMNCH programme such as family planning will be continued under the new FCDO Demography programme to ensure sustained impact. Most of the interventions under the UN Joint Programme will continue to be supported by the GFF. WHO’s programme to respond to emergencies will continue with funds from Switzerland. Unfortunately, the pilots implemented by PSI on family planning and Village Reach for the drones were not successful in securing funding for a second phase.

Value for money

The programme has contributed to significant numbers of poor people in peri-urban and remote areas with better access to basic health services despite contextual challenges such as the fiscal crisis in the sector since the debt scandal in April 2016 which severely reduced funding for the health sector, cyclones Idai and Kenneth in 2018 and COVID-19 since March 2020.

Effectiveness – The programme’s ability to flex and continue delivering maternal and child health services in target health centres contributed to its effectiveness. However, the flexibility also led to disruptions and not all the outputs came together at the desired time leading to some gaps in delivery. For example, there were instances where health workers only received training on how to use the equipment six months after it arrived. Disruption due to the cyclones and COVID-19 meant that both UN and MoH staff were not able to dedicate as much time as needed to provide technical assistance and embed new protocols to be fully effective. There was also a shortage of funds for maintaining and repairing equipment and ambulances, resulting in some of them laying unused until funds were available.

Equity –A total of 2 million people received access to health services by 2019 through the community health worker programme. This included marginalised groups such as adolescent girls in the two most populous provinces (Nampula and Zambezia). The PSI pilot targeted areas which would otherwise not have had access to family planning. The programme worked in some of the poorest regions of the country such as the north with the poorest populations.

Economy – The main cost drivers that can be directly benchmarked are from the UN Joint Programme such as supplies including family planning commodities and kits used by community health workers (40% of costs), equipment (31% of costs) including the installation of WASH facilities in 33 health centres, and training of community health workers and nurses (17% of costs). The UN used their global supply network to secure commodities at the lowest possible price, taking advantage of economies of scale. All family planning interventions in the programme used the contraceptives procured by UNFPA for which the UK contributed 24% of the budget over the duration of the programme. The contraceptives are procured globally at very low cost as compared to locally purchased contraceptives.

Efficiency -The programme has good examples with which to measure efficiency, but it is hard to judge overall performance of the programme as a whole across all interventions. For example, the unit cost of training a community health worker was £814. The training in Mozambique takes only four months while in Tanzania the training lasts nine months. For the sake of comparison, we can look at the cost of training per month, which is £203 in Mozambique and £238 in Tanzania. Although in both countries the community health workers provide health promotion and basic curative services, the number of services on offer in Tanzania is slightly more than in Mozambique, partially explaining the higher cost in Tanzania. That said delays often reduced efficiency of interventions. There were delays of up to six months in transporting the supplies and equipment due to capacity constraints in the MoH’s supply chain leading UNFPA to contract a procurement specialist in the second year of the programme. WASH facilities had a two-year delay in starting as the Ministry of Health, Ministry of Public Works and the UN agreed on the standards for different types of health facilities. The onset of COVID-19 delayed the procurement of WASH equipment from South Africa. As a result, health centres had WASH facilities installed by September 2020 when the original plan was to have these in place by December 2019. These delays brough additional costs and lowered the impact of the programme.
[note] Value for money indicators for the UN Joint Programme
[note] Tani, Kassimu & Exavery, Amon & Baynes, Colin & Pemba, Senga & Hingora, Ahmed & Manzi, Fatuma & Phillips, James & Kante, Almamy. (2016). Unit cost analysis of training and deploying paid community health workers in three rural districts of Tanzania. BMC health services research. 16. 237. 10.1186/s12913-016-1476-5.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators

The programme’s theory of change was initially built on the outcome of strengthening the capacity and resilience of systems for health in relation to reproductive, maternal and child health. This was then changed in 2018 to “people equitably access and use quality health services” which better captured what the programme was designed to achieve.

The programme’s original theory of change (outlined below) remained broadly consistent throughout implementation despite the rapidly changing external context.

Changes to the theory of change

Although the theory of change was realistic, the assumptions on the context were found to be overly optimistic given the number of external crises that materialised. The fiscal crisis meant that salaries for health workers were not consistent and once trained, nurses were not immediately placed in health facilities due to budget constraints. The constant crises and fragmented nature of partner support meant that it was not easy to drive fundamental reforms. For example, the programme undertook a review of the way the Ministry of Health is structured and recommended some fundamental changes taking into consideration decentralisation that requires more decisions to be made at provincial level and a more streamlined central level. However, these changes have not taken place as the focus has been responding to COVID-19 and maintaining essential services. These external shocks meant that outputs had to be modified regularly.

## C: Detailed Output Assessment

Output 1	Enhanced availability and quality of trained midwifery workforce and improved facility readiness at national level by 2020 (UN Joint Programme)
Output Score	A+
Impact weighting (%)	40		Impact weighting revised since last AR?	No

Output Indicator		Starting Target in 2016	Final Logframe Target	Final Result Achieved
1.1 Number of maternal and child health (MCH) nurses who graduated from training and added (from the programme) in health facilities		320 MCH nurses trained and added	320 MCH nurses trained and added	344 MCH nurses trained and added / Exceeded
1.2 Number of health facilities equipped with:(i) ambulances, and / (ii) emergency obstetric and neonatal care (EmONC) kits, including safe abortion care and life-saving commodities		(i) 51 ambulances (ii) 41 EmONC kits procured	(i) 51 / (ii) 41	(i) 51 ambulances purchased, delivered, and distributed by MoH. (ii) EmONC Kits for 41 health facilities / (iii) 1 truck unit for obstetric and neonatal basic emergency care (iv)1 truck unit for obstetric and neonatal complete emergency care (C-section) (v) contentorized Operatory Theatre (vi) 1 Ambulance boat / Exceeded
1.3 Number of technical health / personnel assigned to the primary health care network		Not applicable	15,566 (An additional 704 MCH Nurses)	16,621 (698 MCH nurses) / Exceeded
1.4 Percentage of district/rural / hospitals that received performance‐ / based allocations (PBA) in accordance / with a minimum of two scorecard / assessments in the previous fiscal year		Not applicable	100% of district /rural hospital identified= 15 Districts and rural hospital	15 hospitals- Achieved

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

Output 1 focused on the readiness of health facilities for maternal and child health service delivery and was measured using four indicators aimed at reinforcing health personnel, their training and mentoring and availability of proper equipment. It was implemented by UNJP and GFF. The number of outputs and weight of the UNJP programme were reduced to accommodate other programmes added in 2018. One indicator related to the construction of the WASH facilities was removed due to delays, and the activities cancelled. However, overall results moderately exceeded targets, resulting in a score of A+.

Indicator 1.1: A total of 344 Maternal and Child Health (MCH) nurses graduated from training and were added to the system. The skills of these MCH were assessed to have improved following their time at the training centre and access to training material. In addition, mentoring of nurses was shown to be beneficial to new nurses despite some of them having to wait up to two years to be placed. Whilst nurses were overwhelmed by their high workload due to insufficient nurses for a growing population, they took their role as mentors seriously, allocating time to ensure they supported the provision of improved quality of service for patients. The challenge remains the low rate of absorption of the nurses by the health system and their slow placement in health centers. Although the target was achieved here, it is still low relative to the need.

Indicator 1.2: The EmONC kits and ambulances were distributed to health facilities according to plan and improved the quality of care for mothers and children. Moreover, in response to the insurgency in northern Mozambique which displaced over a million people and destroyed health facilities, additional materials (two mobile units for obstetric and neonatal care, a mobile operating theatre and an ambulance boat) were distributed. Challenges remain in the maintenance of the material distributed and the rapid wear and tear of these resources from high levels of use. There is a need to include maintenance costs in the budgets of health facilities or create a mechanism to ensure funding from the government of Mozambique. Moreover, the number of ambulances remains too low and creative transport solutions are needed to ensure patients reach heath centers in a timely manner.

Indicator 1.3: This indicator was measured through the GFF and was added to the project in 2020; it is complementary to indicator 1.1. The number of health workers recruited for primary care has increased as more positions were created in the health sector by the ministry of finance. However, challenges remain such as the lack of an absorption strategy for health workers, the inefficient use of the new online HR system SIP which sometimes fails to register new nurses or other health professional in the system.

Indicator 1.4: As with indicator 1.3, this indicator is measured through the GFF programme and assessed performance‐based allocations (PBA) attributed to health centres that performed well on a specific date in the previous year. The indicator was met as all hospitals received an accreditation based on the scorecard system and the services they could or could not deliver. This allowed health centres to operate more autonomously and receive funding directly, a significant innovation in the Mozambican context.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

This output is assessed as delivering good VfM overall.

Economy: The ambulances, EmONC kits and commodities were procured at below market price. As a result, UNFPA had a savings of £740,000 at the end of year two which they were able to reprogramme for the cyclone response in 2019.
Efficiency: More programme results were achieved at the same cost; thus, outputs were achieved in an efficient way. For example, maternal and child health nurses (midwives) were trained at a cost that was 16% less than planned. Savings were also made by adapting the nurses’ mentoring scheme, by bringing on board local mentors rather than having mentors fly in from Maputo.
Effectiveness: Whilst targets were generally met or exceeded, there were challenges in maximising effectiveness under this output. The slow allocation of the nurses to health centres, the inconsistent maintenance of equipment due to budget constraints and lately the lack of funds to purchase commodities for health centres, has meant that where nurses are present, they do not always have the means to deliver quality services, undermining the effectiveness of the output.
Equity: The 344 nurses trained by the programme contributed to 688 (60%) health facilities in the primary care network having at least two active nurses in 2019; this increased to 738 (65%) by 2020. These health centres were located were located in the poorer areas of the country, such as remote districts in Nampula, Niassa and Zambezia provinces.

Lessons learned through this output, and recommendations for future programming

A key lesson learned is that a comprehensive and holistic intervention approach is needed to tackle maternal and child health. When working on health system strengthening, all aspects of the system should be considered including the policy for human resources for health, the decentralization process and the autonomy of health centers.

Programmes should not only buy health materials/equipment but ensure that these are suited to the context, can be maintained and handled properly by health professionals and technicians and consider whether basic supplies are available to use the machines. Despite the efforts to get the health system ready for maternal and neonatal care and get the essential medicines in place, basic disposable items e.g. gloves, syringes etc. were not always available and hindered the effort and VfM of programmes supported by partners.

Output 2	Platform for outreach through the community health worker (CHW) programme strengthened by 2020 (UN Joint Programme
Output Score	B
Impact weighting (%)	25	Impact weighting revised since last AR?	No

Output Indicator	Starting Target in 2020	Final Logframe Target	Final Result Achieved
2.1 Proportion of CHW / (i) working in target districts of total needed / (ii) receiving at least 1 supervision visit per quarter	(i) 75% (ii) 70%	(i) 85% (ii) 100%	(I) 94% (ii) 100% / Exceeded/met
2.2 Proportion of CHW equipped and using UPSCALE mobile platform in (i) Cabo Delgado province (ii) Inhambane province / *NB; the UN changed the focus provinces for roll out of UPSCALE from 2018. Another indicator was added: Total numbers of CHW trained on UPSCALE.	(i) 80% (ii) 60%	(i) 30% (ii) 30% / This target was revised down to 30% as the implementation was very slow	(i)20% (ii) 20% / Not achieved / * A total of 2632 (32%) of the total 8,123 CHW are now trained to use UPSCALE, below national target of 50%

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

Output 2 aimed at strengthening the platform of community health workers who connect the highly dispersed population to the health system and are of extreme importance in a context where human resources for health are scarce. Of the two indicators used to measure performance of this output, one saw the target exceeded, whilst the other target was not achieved. Whilst weighting these indicators equally would give an overall output score of A, both elements are critically important for the CHWs to be operational. We therefore assess that underperformance under indicator 2.2 justifies an overall score of B for this output.

Indicator 2.1: This indicator focused on the expansion of the network of trained CHWs in Mozambique, especially in underserved areas). Very good progress was made. A total of 2,397 new CHWs were trained, of which 53% were female. Whilst good progress has been made in expanding the network of CHWs, there are still some gaps in maximising their effectiveness and strengthening their role in Sexual and Reproductive Health and Rights (SRHR), in particular to support adolescent girls in adopting family planning.

Indicator 2.2: This indicator tracked the development and implementation of a digital job aid platform (UPSCALE) to support CHWs to monitor their patients and improve the quality-of-service delivery. Over the lifetime of the project, the target linked to the use of the online job aid platform UPSCALE was reduced from 70 to 30 percent due to technical issues related to its roll out and use. The platform was initially piloted and then rolled out in Inhambane province, where it reached 20% of the CHW by 2018, with plans to scale up to 60% of CHW by 2020. From 2018, UK funds were used for the rollout in Cabo Delgado province, but this was hampered by the escalation of violent conflict in the province later that year. Plans were made to rollout in the most populous provinces, Nampula and Zambezia, as well as transfer the management of the platform to the Government. However, the rollout was slower than expected due to lack of training on the use of digital tools for community health workers, weak technical support on the management and use of the platform, poor internet connectivity and slow integration of the platform into the health information system due to weak capacity in the government.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

National and international evidence demonstrates that CHWs are a cost-effective way to deliver health services in remote areas. This output has contributed to the expansion of the programme from 3,380 CHW in 2017 to 8,123 CHW in 2020, reducing the proportion of the population without access to health services. The World Bank will be supporting the government to improve the training, supervision, and the supply of CHWs in future.

Economy: The training and deployment of each CHW was competitive, costing £203 in Mozambique compared to £238 in Tanzania. The main cost drivers for the rollout of the UPSCALE platform included hardware/IT related costs (60%), and infrastructure related costs (8%). This is different from the costs in India for example, where most of the cost (61%) was on salaries, 33% on information technology and 6% on infrastructure. It demonstrates the challenges that Mozambique had in finding the right digital tool for the context.
[note] Udita Joshi, John A. Naslund, Aditya Anand, Deepak Tugnawat, Ram Vishwakarma, Anant Bhan, Vikram Patel, Chunling Lu,Assessing costs of developing a digital program for training community health workers to deliver treatment for depression: A case study in rural India,Psychiatry. Research,Volume 307,2022, https://www.sciencedirect.com/science/article/abs/pii/S0165178121005941#!
Efficiency: The number of supervisions visits each CHW received from a nurse increased from one per year to four per year by the third year. CHW experienced a shortage of at least one of the commodities in their kits at least twice a year, due to inefficiencies in the system which were unable to alert when stock was running low and needed to be replenished.
Effectiveness: Whilst good progress has been made in expanding the network of CHW, there are still some gaps in maximising their effectiveness. For instance, a recent evaluation by the World Bank showed that 60% of the CHW do not have the required level of knowledge and access to essential medicines in their kits. The UPSCALE platform can help address this by acting as a job-aid to support CHW to remember their protocols and alert the health centre to replace commodities when needed. 2,632 (32%) of the total 8,123 CHWs are now trained to use UPSCALE, albeit below the national target of 50% by 2020. Unfortunately, while the platform holds a lot of promise, the roll out plan that included the transfer of management from UNICEF to the Government experienced many administrative delays.
Equity: The expansion of the CHW network from 75% to 95% of the target districts has meant that an additional 2.3 million people can now access basic health services and information. Part of this has been ensuring that more women can access services. The programme contributed to increasing female CHW to 53% by 2021, an increase from less than a third in 2016.

Lessons learned through this output, and recommendations for future programming

An evaluation from the World Bank reveals that training of CHWs needs to improve. The recommendation is to have more practical trainings in the future instead of lectures that are less adapted to CHWs’ needs. This will be taken froward by government and the World Bank.

Previous studies on the potential of the UPSCALE platform in the Mozambican context should have included a cost-effective analysis. This would have avoided having to adjust the platform after it had been rolled out to a third of the CHWs. This recommendation should be considered by those financing new IT systems particularly in health.

Output 3	Generating demand for family planning among adolescents
Output Score	A
Impact weighting (%)	20	Impact weighting revised since last AR?	No

Output Indicator	Starting Target	Final Logframe Target	Final Result Achieved
3.1 Additional family planning users in the target areas as a result of FCDO interventions	33,650	33,650	76,664 / Exceeded
3.2 Improved knowledge, capacities and agency for SRHR	1 million girls reached through Rapariga Biz	1 million girls	700,000 girls reached / Not achieved

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

Output 3 looked at piloting approaches to increase family planning uptake among adolescents and women of reproductive age and tackling early marriage and pregnancies amongst the most vulnerable girls using an adaptive approach. This intervention/output was delivered by PSI, targeting adolescents/women of reproductive age. The number of indicators under the demand side output were increased from one to two: one for the PSI project and another for the Rapariga Biz project. The weighting of this output doubled from 15% to 30%.

Indicator 3.1: PSI’s pilot exceeded its target, achieving 76,664 additional users of family planning. The pilot’s inclusive approach to generating demand by reaching families, male partners, and communities made the decision to use contraceptives a broader family/community discussion. 139 community promoters conducted demand creation activities using video testimonials in local languages through door-to-door engagement with adolescents, and in discussions with couples and parents. The demand generated for family planning through this approach was met through 36 nurses based in fixed public health facilities as well as in mobile outreach activities. This has resulted in changing behaviours and norms in communities. The pilot was adapted following the outbreak of COVID-19 (after discussions with local authorities on how to maintain activities, including adding COVID-19) and found creative ways to reach beneficiaries at a distance, for example by sharing phone numbers for clients to call in.

Indicator 3.2: An independent evaluation of the Rapariga Biz programme conducted in 2020 showed that the programme resulted in 40% of girls (700,000) in two provinces being aware of their sexual reproductive health and rights while their communities supported the girls to access services. Despite this being a significant achievement, it did not reach the target of 1 million girls in the two provinces. Several factors led to this: a. the government was not sufficiently engaged with other ministries such as education to support coordination and implementation as well as monitor progress, b. resources could not be reallocated to respond to arising needs in specific services such as school-based services given limited delegation of authority to district level and c. demand outstripped supply in health, education and community development. Despite these challenges the programme was able to contribute to a delay in early marriage and unintended, but the monitoring and evaluation system of the programme was unable to pin down which specific interventions led to this shift in behaviour. FCDO decided to phase out support after undertaking a review that helped the UN agencies, Sweden and Canada streamline activities.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

PSI and FCDO agreed on VfM indicators which were monitored every six months. Overall VfM performance for the pilot was mixed. Whilst PSI’s approach delivered results (exceeding targets despite the challenging context), unit costs were high due to the labour-intensive methods used and exacerbated by COVID.

Economy: International evidence shows that the cost of delivering family planning services for the general population (£5.83) is double (£11.28) the cost for the adolescents. A two-pronged approach of integrated services for the general population and targeted services for adolescents who are excluded from general services is recommended. The cost per adolescent for PSI’s pilots was almost three times the cost of similar services in other low-income countries due to the labour-intensive approach that PSI used - this included 118 health promoters in communities to undertake demand creation activities and referrals to health facilities through dialogues with individuals or small groups, as well as 26 trained nurses in fixed public health facilities and or in mobile outreach sites to meet the demand for services. The one-year delay in transitioning from the inception to the implementation phase did not allow for FCDO to recommend that PSI change their approach as value for money data was only available six months after the implementation phase started. Costs were further affected by the pause of interventions between March and July 2020 due to COVID-19, making it difficult for the pilot to reach as many adolescents as it could and therefore benefit from economies of scale, reducing the cost per adolescent.
[note] Sully EA et al.(2020), Adding It Up: Investing in Sexual and Reproductive Health 2019, New York: Guttmacher Institute, http://www.guttmacher.org/report/adding-it-up-investing-in-sexual-reproductive
[note] PSI (2021) Vale a pena quarterly report: December 2020-February 2021.
Efficiency: The cost per family planning method distributed ranged from £7 in 2018 to £13 in 2020. This was still less than half the £36 that PSI had estimated (transportation costs included). The cost of delivering family planning in schools (£1,800 on average) was also less than planned (£3,500) due to the use of free spaces in schools to deliver family planning services.
Effectiveness: The programme exceeded the target of number of new users. The pilot increased the uptake of long acting family planning methods to 13% on average, significantly higher than the national average of 5% in Mozambique. However, the high cost of the programme has meant that this approach will be difficult to scale up without some adjustments to bring costs down.
Equity: The programme reached young people in excluded areas of Nampula, Gaza and Maputo provinces where there were almost no other family planning services targeted at adolescents.

VfM indictators for the Rapariga Biz programme were monitored separately:

Economy: The large number of girls reached through the mentorship model made it low cost. For example, the average cost per girl in the mentorship cycle was £123.64 (cost for training the girls and the mentors), which is significantly less expensive than the safe space programmes in Zambia costing £390 per girl or in low income countries that range from £39 to £520.
[note] Le Blanc R, Eltahir A, Grabaek S D, Calana A and Bischler J (2020) End of Project Evaluation of the One UN-SRHR for girls and young women in Mozambique – Rapariga Biz Program, 2016-2019,Consultancy firm: Nordic Consulting Group-Denmark. Commissioned by Sida, Embassy f Sweden in Maputo, Mozambique.
[note] Austrian et al. (2016)
[note] Swell-Menon et al. 2012
Efficiency: The individual components such as comprehensive sex education, mentoring, community discussions, economic empowerment, radio programmes and delivery of family planning in health facilities were delivered efficiently. However, the programme could have done more to adjust these interventions to girls and young women in a rural context. For example, there was little research on what the contents of the community discussion should have been to be effective. More could have been done to ensure that the messages in the different interventions were mutually reinforcing rather than stand alone. The school corners where adolescents got sexual reproductive health information and services in school consisted largely of a counseling service, and were not linked to the comprehensive sexual education sessions that teachers offered in the same school.
Effectiveness: An independent evaluation of the programme in 2019 found that although the programme led to a reduction in early marriages and non-intended pregnancies, it was difficult to know which of the numerous interventions caused these changes, making it difficult to replicate the programme in other provinces that may want to focus on fewer interventions. Partners (Sweden and Canada), UN agencies and the government will continue to streamline the programme focusing more on effectiveness. At the moment, sustainability of future progress relies on donor financing.
Equity: The selection criteria targeted girls in secondary school thereby excluding the majority who either have never attended school or dropped out. The programme thereby excluded girls who were of lower socioeconomic status or more vulnerable to early marriage in the target provinces. UNFPA are revising the selection criteria to be more inclusive.

Lessons learned through this output, and recommendations for future programming

Future FCDO and other Donor investments should support integrated delivery of family planning for the general population and targeted interventions for adolescents. We have learned through the PSI and Rapariga Biz projects that the involvement of boys and men is crucial to increase the use of family planning. There is also a significant role to be played by the CHWs in promoting this discussion in communities but also to encourage young women to adopt modern family planning methods.

The government has decided to suspend the delivery of long-acting family planning methods in secondary schools. This affected the activities of PSI and the GFF who were able to adapt quickly and deliver these in various adolescent friendly places outside of schools. There is a need for evidence-based advocacy by development partners with sector ministries to promote understanding that family planning is key to the demographic transition. For example, the Ministry of Education has resisted the delivery of longer acting family planning methods in secondary school despite clear demand.

The Rapariga Biz project needs to streamline and improve its monitoring and evaluation system before expanding interventions to understand which intervention is most effective. That said the mentoring approach was shown to be effective at delaying unintended pregnancies and preventing early marriage.

Output 4	Strengthen the sector's capacity to respond to emergencies
Output Score	A
Impact weighting (%)	10	Impact weighting revised since last AR?	No

Output Indicator	Starting Target	Final Logframe Target	Final Result Achieved
4.1 MoH's ability to prevent and respond to outbreaks is strengthened (through WHO's Emergency Preparedness project)	n/a	Evidence of improved MoH preparedness and response to any disease outbreak in target areas	Guidelines and systems for surveillance and response established. / Achieved
4.2 Institutional support to the MoH to advance the pandemic response to reduce the risk of mothers, newborn and children as well as health workers through the UN Joint Programme	n/a	Institutional support to the health COVID-19 response plan	Technical assistance in case management and surveillance/ readiness of COVID 19 centers and procurement of PCR machine / Achieved

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

Output 4 was delivered through activities to increase the capacity of the Mozambican health system to prepare and respond to emergencies and disasters, including maintaining services for mothers and children at these times. The indicators for Emergency Preparedness were reviewed to focus on the different interventions WHO undertook to support disaster prevention and response in the health sector. Their weight was increased from 5% to 10%. FCDO support allowed the MoH to respond to a polio outbreak in 2019, a measles and cholera outbreak in 2020 and supported three rounds of emergency oral vaccination campaigns in Zambezia. WHO was also supported to improve management of the COVID-19 pandemic. Activities under output 4 ended in 2020.

Indicator 4.1: MoH's ability to prevent and respond to outbreaks is strengthened (through WHO's Emergency Preparedness project). A number of guidance documents have been produced and systems introduced that support improved preparedness and responses. For example, the integrated disease surveillance and response guidelines used for the most common disease outbreaks in the country such as cholera and measles. The programme succeeded in setting up a Public Emergency Operation Center, an electronic early warning system that were used in the response to the cyclones as well as the cholera and measles outbreaks in Sofala and Cabo Delgado provinces in 2019, malaria outbreak in the Northern provinces in 2020 and polio outbreak in Zambezia province in 2020.

Indicator 4.2: Institutional support to the MoH to advance the pandemic response to reduce risks to mothers, newborn and children as well as health workers through the UN Joint Programme.
This indicator was added in 2020 to reflect the funds that were reprogrammed for the COVID-19 response to keep health services active, in particular services to mothers and children, and actions to protect health workers being infected.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme
The programme team struggled to develop value for money indicators with WHO for the emergency response as delivery was rushed in response to COVID-19. The overall assessment of VfM is that this component was good value for money because it enabled the UK to respond to disease outbreaks and emergencies in the sector while allowing for the rest of the programme to continue delivering as planned with little disruption despite the external shocks.

Economy: Equipment and supplies, including the Polymerase Chain Reaction (PCR) machine and scanner for COVID-19, were purchased using the UN’s competitive global supply chain system.
Efficiency: Training of health staff took place in three locations throughout the country to reduce costs and ensure that there was coordination between provinces. Equipment and supplies were delivered quickly as they were often urgently needed in health centres.
Effectiveness: Ironically for a crisis preparedness activity, implementation of the programme was disrupted first by cyclone Idai and then by the COVID-19 pandemic. Despite not achieving everything that the programme set out to do, it has enabled the Government to respond to emergencies. For example, WHO purchased one of the first PCR machines for COVID-19 in March 2020 which has been vital for public covid testing in the country. In terms of effectiveness, the emergency command centre enabled the programme to strengthen the health system’s capacity to respond to emergencies and improve surveillance even after the programme ended.

Lessons learned through this output, and recommendations for future programming

There is a need for the Government of Mozambique to improve emergency preparedness and surveillance. Community systems need to be strengthened to enable better coordination, communication, analysis of data and sharing of data between the provinces and districts and central level. The National Institute of Health will now also set up a new surveillance system to follow the evolution of diseases. Canada will support WHO to gather data and evidence to support national policy decisions on emerging diseases.

Output 5	Strengthen our central support towards innovation through drones for health by September 2020
Output Score	A
Impact weighting (%)	5	Impact weighting revised since last AR?	No

Output Indicator	Starting Target	Final Logframe Target	Final Result Achieved
5.1 Number of test flights conducted for TB samples transportation	In-country 23 UAS (drone)study flights conducted	In-country 23 UAS (drone)study flights conducted	Achieved - 23 flights, transporting 140 COVID-19 samples and 160 TB samples

Indicator 5.1 Number of test flights conducted for TB samples transportation
This output was added in 2019 in response to an additional funding opportunity from FCDO to use innovative technologies (drones) to ensure the continuation of health services and enable services to reach all people/health centers equitably during emergencies. Despite constraints due to the pandemic, and the administrative burden from regulatory authorities to undertake the test flights, all the scheduled flights took place safely and without affecting the quality of the biological samples. COVID-19 samples were also added to the TB samples that were transported. The costs of the operation will need to be studied further once more flights per week can be implemented to build the local capacity for handling and maintaining the drones. These innovations can be a way to address last mile delivery and ensure smoother logistics for lab sample transportation.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

The pilot demonstrated that the transportation of TB samples using drones cost more than the current motorbike transportation system (from 26 times more costly (to one health center, once a week) to 1.3 times more costly (to many health centers, twice a week). It is therefore not feasible to completely replace the current system with a drone delivery network. The cost-effective solution could be to have a combined approach where specific sites are selected for drone delivery with the criteria including difficulty of access by other transportation routes, performance of the current supply chain, disease burden and equity. The pilot therefore provided an additional option available to the government to reach vulnerable groups or remote areas.

Lessons learned through this output, and recommendations for future programming

Innovation could be crucial during pandemics as demonstrated by the use of the programme drones for transportation of COVID-19 samples. A key recommendation for future activities in this area is for any pilots to ensure that there is enough funding to properly test the cost- benefit and sustainability of innovative approaches not just operational issues.

D: Risk

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.

The overall risk rating for the programme remained moderate throughout implementation. The high context risks of the operating environment characterised by the fiscal crisis, Cyclone Idai, COVID-19 restrictions and increasing violence in the North required a number of programme changes. A programme risk register was maintained, covering all six categories of risk, and was reviewed and updated on a regular basis. All implementing partners also maintained component-level risk matrices which were reviewed in partner meetings and updated along with narrative reporting. Due diligence assessments of all implementing partners were also conducted. The main risks identified from the onset of the business case are included in the below table:

Risk	Mitigation	Realisation through programme
A reduction in State expenditure in Health undermines the ability to deliver the programme	Strategic technical support through this programme to ensure that cuts are planned and minimise their effect. / Adaptive approach of the programme to ensure that the programme can help the Ministry of Health to minimise the effect of the cuts (except for salaries).	The effect of the fiscal crisis on the maintenance of equipment and absorption of staff was discussed between the UNJP partners and the MoH with the involvement of FCDO. Although no solution was found, the willingness of the Government to discuss these shows a change from 2016 when there seemed little readiness to admit there was a problem.
UN agencies fail to coordinate undermining programme performance	Ensure first 6 months of programme are used to agree roles and ways of working. / Agree on mechanisms to communicate with Government and partners.	The programme team and UNJP partners discussed programme performance including the risk register every six months, with ad-hoc discussions when relevant. However, given the resource constrained environment these discussions should have taken place at least once every quarter. The UNJP partners do have regular discussions with the MoH on how to minimise risks. The partners were still learning how to use the risk register as a management tool.
Excessive costs of the programme as funding was not channelled directly through Government	Kick-off meetings with UN/Service providers to understand funding flows. / Set and monitor value for money indicators jointly with UN and Service provider.	FCDO trained UN partners on FCDO Value for Money approach and supported its monitoring. The programme also took advantage of economies of scale by working with UN agencies central procurement to secure the lowest available prices where it could when procuring commodities.
Major humanitarian emergency due to climatic shocks and or disease outbreak	Ensure that support for disease preparedness is robust and systemic minimising disruptions to service delivery and making systems more robust. / Support institutional capacity building for disease outbreaks.	Emergencies due to weather events and the COVID-19 pandemic have caused delays in implementation, but programme flexibility allowed RMNCAH partners to put in place strong mitigation actions to get interventions back on track and established mechanisms to respond to emergency situations.

Throughout the programme lifecycle, FCDO and implementing partners had to mitigate and adapt to a wide range of risks that materialised. Many of the major risks were contextual; the first, and one of the more significant to the programme implementation approach, was the fiduciary risk of channelling money through the government due to the debt crisis which led to the decision at the start of the programme to channel funds through the UN (the programme was originally designed to finance government systems directly). This weakened system strengthening efforts as the Government’s systems were not directly supported or used by FCDO. It also meant that the context in which the programme operated was one of constant shortages of budget for operating costs on the government side as a number of donors also stopped budget support. In addition, there were two cyclones in 2019. These impacted on project implementation as government, implementing partners and FCDO human resources redirected their attention to the emergency response reducing time for project implementation and monitoring. Project resources such as consumables from the UN Joint Programme were also redirected to the most affected areas. Finally, the COVID-19 pandemic restrictions and pressures on MoH to divert programme activities to support PPE purchase, testing equipment and other consumables for COVID-19 caused significant disruption. The programme was able to respond in two ways. Firstly, the WHO emergency preparedness project adapted their interventions to provide more advice and equipment to the Government. Secondly, the UN Joint Programme project identified savings to respond to the needs of those affected by cyclones, COVID-19 and the conflict in Cabo Delgado.

Update on Partnership Principles

The programme does not channel any funding directly to Government.

E: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency.

Overall, the programme has delivered against its financial targets. The total value of the programme was £39,850,000. The total budget was reduced by £1,613,427 in 2020, following UK reprioritisation of activities in response to COVID. Therefore, the programme spent £37,348,889 in total, equivalent of 94% of total budget. The main intervention areas was system strengthening interventions through UN Joint Programme and World Bank GFF (Multi-Donor Trust Fund (MDTF) that accounted for 75% of the total budget, and family planning for girls and young women which accounted for 17%.

Component	Component name	Budget	Spend	Spend %	Balance

205074-101	Design Funds	133,859.00	133,859.00	100%	0.00
205074-102	UN Joint Programme - RDEL	19,509,719.00	19,484,318.00	100%	25,401.00
205074-106	UN Joint Programme - CDEL	5,000,000.00	5,000,000.00	100%
	UN Joint Programme - Total	24,509,719.00	24,484,318.00	100%	25,401.00
205074-103	PSI	4,467,560.00	4,295,403.29	96%	172,156.71
205074-104	TA	480,210.54	426,715.47	89%	53,495.07
205074-107	Rapariga Biz	2,895,140.00	2,285,846.00	79%	609,294.00
205074-108	WHO - Emergency Preparedness and Response	2,950,084.46	2,950,084.46	100%	0.00
205074-109	Village Reach - Drone Pilot	300,000.00	272,663.00	91%	27,337.00
205074-110	World Bank - GFF	2,500,000.00	2,500,000.00	100%	0.00
Subtotal		38,236,573.00	37,348,889.22	98%	887,683.78
205074-105	Funds reduced from budget reduction exercise in 2020	1,613,427.00	0		1,613,427.00
Total		39,850,000.00	37,348,889.22	94%	2,501,110.78

FCDO’s working relationship with all implementing partners was collaborative. Implementing partners provided regular quarterly project progress updates and met regularly with FCDO programme leads. In particular:

- The FCDO delivery plan was updated monthly, drawing from regular health cluster meetings, partner meetings for progress reviews, programme strategy, risk management and adjustment of annual work plans.
- UN Joint Programme made some changes in the initial work plan and budget throughout the project lifecycle. The initial changes were made in the inception phase of the project when MoH asked to include consumables vital for effective running of the health system. Additional changes were made to respond to the cyclone Idai where savings in commodities worth a total of $1million (£740,000) were reallocated to support the cyclone response.
- When COVID-19 started there was also a need for both the UN Joint programme and the WHO Emergency project to adjust their budget to respond to needs, including the purchase of personal protection equipment (PPE), consumables, and testing equipment worth almost £800,000. The insecurity in Cabo Delgado also required adjustments to the work plan and budget worth £1 million in the UN Joint Programme to procure an ambulance boat, a mobile operation and an operating theatre unit to respond to the needs of pregnant women.
- FCDO mandatory requirements (including fraud, safeguarding, VfM, branding guidance, etc) were adhered to by all the partners. Implementing partners’ reports of fraud and safeguarding were limited and perhaps lower than expected, given the context and work with girls and young women.
- An audit trail is saved on FCDO’s filing system for all key programmatic and financial decisions.

In the first three years the cost drivers were inputs consisting of equipment (31%), training (17%), and commodities (41%). The programme did well on economy VfM measures as the UN procured equipment via the UN’s global procurement systems and agreements with suppliers leading to competitive costs. Both PSI and the Rapariga Biz programme benefitted from UNFPA’s procurement systems for their family planning commodities. Towards the latter half of the programme the cost drivers shifted to training, supervision, distribution of commodities and service delivery taking advantage of savings when possible. An example is the joint training of nurses and community health workers that led to a 16% reduction in overhead costs for the UN Joint Programme. As mentioned above, the overall fiscal constraints undermined the sustainability and efficiency of interventions as the Government has struggled to take over some of the costs previously undertaken by the UN or NGOs such as the maintenance of equipment, utilities and commodities needed for health centres to deliver quality services.

Quality of financial management

FCDO established financial management processes and procedures that were followed to ensure all disbursements were initiated only after the completion of essential appraisals and approvals. The FCDO team provided guidance on financial management to all delivery partners. Implementing partners’ annual work plans and detailed budgets were agreed and approved by FCDO. These budgets were reviewed and monitored regularly to ensure that they were realistic and cost-effective. As set out in the business case, appropriate funding arrangements, disbursement schedules and reporting and monitoring schedules were established and applied throughout the period of the programme.

Programme-level approach to monitoring and evaluation

Project Monitoring and Field Visits
The FCDO team undertook regular monitoring activities as part of the project agreements including review meetings and field visits which included opportunities to elicit beneficiary feedback. Review meetings with implementing partners were carried out at least quarterly and, in some cases, monthly, to discuss project progress, risk management and VfM. The FCDO team carried out several joint field visits with implementing partners during the lifecycle of the programme. The field visits were important to understand the implementation context, progress, and constraints and to meet beneficiaries and government staff at provincial and district level.

Date of last narrative financial report	PSI June 2021 / Narrative UN Joint Programme June 2021 / Financial UN Joint Programme November 2021 / Village Reach June 2021	Date of last audited annual statement	Village Reach AuditReport - December 2021