 Programme Completion Review

Title: Neglected Tropical Diseases Implementation Research Programme (NIRP) – COUNTDOWN
Final Programme Spend £ (full life): £10,269,873	Review Date:	January 2022
Programme Code: 203089	AMP start date: / 29 July 2013 / Actual start date: / 1 November 2014	AMP end date: / 31 October 2021 / Planned end date: / 31 October 2021

Summary of Programme Performance

Year	2014	2015	2016	2017	2018	2019	2020	2021
Programme Score	A	A	A	A+	A+	A+	A+	A+
Residual Risk Exposure Rating	Minor	Major	Major	Major	Major	Major	Moderate	Moderate

DevTracker Link to Business Case (and any addendum):	https://devtracker.dfid.gov.uk/projects/GB-1-203089/documents
DevTracker Links to all logframes used during programme lifetime:	https://devtracker.dfid.gov.uk/projects/GB-1-203089/documents

A. Summary and Overview

Description of the programme and what it has achieved

The Neglected Tropical Diseases (NTDs) Implementation Research Programme, COUNTDOWN, was a 7-year programme, led by Liverpool School of Tropical Medicine (LSTM) with partners in the 4 operating countries (Ghana, Liberia, Nigeria, and Cameroon) where NTDs are prevalent. The programme focused on delivering high quality evidence on cost effective, scalable, and sustainable solutions necessary to control and eliminate 7 NTDs (trachoma, schistosomiasis, river blindness, elephantiasis, and three soil transmitted helminths) that together have been responsible for 90% of the total global burden of NTDs. The main pillar of Integrated NTD Control Initiatives is delivery of Mass Drug Administration (MDA) to simultaneously treat and control disease.

COUNTDOWN brought together researchers from a range of backgrounds and disciplines, health care providers, policy makers, laboratory scientists, research uptake specialists, Ministries of Health and Non-Government Development Organisations (NGDOs) and presented an opportunity to bridge the knowledge to implementation gap for shared health impact. Across contexts, COUNTDOWN worked proactively and collaboratively with health policy makers and NTD programme implementers at country level to disseminate research findings on an ongoing basis and help ensure that evidence generated has been of maximum benefit to NTD programmes. It also consolidated the narrative of research to policy change in an accessible manner, supporting evidence informed policy at district (state), national and international levels. The programme’s efforts to increase the reach and scale up of NTD treatments was important in helping to accelerate progress towards meeting World Health Organisation (WHO) targets on NTDs.

The programme scored A+ - moderately exceeded expectations – against all output targets. COUNTDOWN’s multidisciplinary implementation research approach and, in particular, the use of social research to co-produce adaptations to NTD programmes has demonstrated how barriers to access can be overcome, strengthen MDA, and support those living with NTDs. This was consistent with original objectives for the programme. COUNTDOWN conducted 20 research projects across the 4 African countries generating new evidence and policy/practice uptake that contributed to the reduction in morbidity, mortality and poverty associated with NTDs in line with the 2020 WHO NTD Roadmap. The programme also developed sustainable research capacity amongst individual stakeholders and at an institutional level. A visual summary of COUNTDOWN activities can be found here

Major lessons learned

- It is important that interventions to combat NTDs (and other public health issues) are acceptable to, and have the trust of, affected communities. COUNTDOWN increased trust amongst those affected by NTDs (predominantly the poorest and most disadvantaged) through participation in, and ownership of, the research; by using a range of dissemination tools and materials that were accessible and understandable to identified target audiences; and by targeted dissemination of resources through relevant groups (religious bodies, professional associations, youth groups etc).
- The value of strengthening the research uptake process through early involvement of stakeholders. COUNTDOWN involved policymakers, practitioners, and other actors throughout the research lifecycle to facilitate and contribute to the use of research evidence. This helped; sensitise stakeholders to the research and ensure acceptability of interventions; ensure gender equity was central to thinking; engage strategic partners outside of the NTD programmes (e.g. disability organisations to help address stigma), and ensure the research was appropriate and relevant to country need and responsive to arising gaps identified.

How this report was conducted

The review was undertaken by members of the health research team drawing on: direct engagement with the programme – regular progress meetings (in person and virtual); on-going e-mails and telephone calls on a range of issues (technical progress, the contract, budgeting and finance, and programme closure); participation and attendance at end of programme webinar (attended by over 150 people from 20 countries), link to recording here; the programme website; and documentation including the business case, programme reports and previous annual reviews.

Actions following approval of this report

Outstanding actions are:
- To finalise agreement on the disposal of assets
- FCDO to receive LSTM financial statements covering the period to 31 October 2021
- FCDO to receive further programme outputs, including peer reviewed publications, as these become available during 2022

## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	£7,012,587	£10,269,873
Timeframe	1 Nov’ 2014 – 31 Oct’ 2019	1 Nov’ 2014 – 31 Oct’ 2021
Outcomes	Outcome Indicator: The improved availability, acceptability, affordability, and accessibility of NTD interventions to individuals and communities.	Outcome Indicators: Improved availability, acceptability, affordability, and accessibility of NTD interventions to individuals and communities; and COUNTDOWN research influences improved consideration of gender, equity, and the most vulnerable in NTD programming

Overall assessment of programme outcomes, sustainability and VfM

COUNTDOWN delivered on time and within budget. In 2019, a 2-year costed extension was agreed to further build on COUNTDOWN’s work and strengthen, solidify, and extend its impact. Progress was hampered during the extension period by COVID-19 restrictions and political instability in Nigeria, whilst FCDO budget constraints in 2020 rendered a planned further extension non-viable. Nevertheless, during this final period, COUNTDOWN revised their plans to best effect and focused on: completing the adjusted projects; ensuring sustainability by embedding findings into the health service through increased training, sharing tools and resources and encouraging findings be reflected in policies where appropriate; and hosting interactive dissemination meetings at local, state, national and international level which were supported by social media activity to promote findings and lessons.

Over the programme lifetime, COUNTDOWN delivered a portfolio of high quality implementation research projects and successfully met the programme outcome (set at the outset) of increasing the effectiveness of NTD programmes, particularly in the 4 operating countries. It is likely that the programme outcomes will be sustainable, particularly in the focal countries and that COUNTDOWN’s dissemination activities will be taken into account at an international level.

The consortium worked proactively and collaboratively across contexts with policy makers and programme implementers to disseminate research findings on an ongoing basis and help ensure that evidence generated was of maximum benefit to NTD programmes. It also consolidated the narrative of research to policy change in an accessible manner, supporting evidence informed policy at district (state), national and international levels. The programme’s efforts to increase the reach and scale up of NTD treatments helped accelerate progress towards meeting World Health Organisation targets on NTDs.

To illustrate:
- Over the 7 programme years, COUNTDOWN worked to combat Female Genital Schistosomiasis (FGS), a condition that previously didn’t appear in national policy/plans. In Nigeria and Liberia COUNTDOWN developed and tested an integrated package of care for FGS, introducing referral systems at all levels of the health system. The interventions improved knowledge and capacity of frontline health workers to be able to manage cases at the primary care level, and reduced inequality in access to healthcare and treatment. Consequently, there was reduced stigmatisation of girls and women affected by FGS, and researchers developed extensive evidence for policy on the management of cases. The FGS training guide for Nigeria can be found here, the FGS trainer manual here and an associated presentation here. The Liberia FGS Intervention manual can be found here. The success of the pilot projects led to national FGS policies being created and adopted in both countries. These were the first projects globally to provide FGS diagnostic and treatment services at primary care level. The work has been showcased at several international meetings (A)STMH, COR NTD) and the tools have been incorporated into other FGS projects.
- Using tools created by COUNTDOWN, e.g. the Standard Operating Procedure (SOP) and PGP, Ogun State in Nigeria has been able to identify and engage more stakeholders (including community leaders, religious leaders and local government) to both increase the acceptance of Mass Administration of Medicines (MAM) and to guide the process. This resulted is a reported 35% increase in MAM coverage across the state.
- COUNTDOWN successfully helped to strengthen health systems through NTD research. The core values and approaches that underpinned COUNTDOWN to ensure that no one is left behind supported health systems strengthening and NTD programme delivery, particularly at primary care level, and led to increased access to services.
- COUNTDOWN’s focus on funding, governance, and donor priorities enabled teams to understand how decisions were made and impacted on the planning and delivery of services and were critical factors in evaluating the scale up and sustainability of interventions.
- COUNTDOWN explored the advantages and disadvantages of integrating health systems and co-implementation of disease programmes. Researching the experiences and views of health workers and community drug distributors - the linch pins of MDA for NTD control and elimination - in terms of motivation, support, their integration into the wider health system etc. made for more informed and responsive policy and programming, aiming to retain a motivated cadre of close to community providers working on NTD control.
- By focusing on gender, equity and rights, COUNTDOWN helped ensure that NTD programming was informed by community voices reflecting socio-economic factors, attitudes and beliefs, barriers to access etc.and took account of NTD related stigma and its impact on service uptake, morbidity management and disability inclusion. Thus, COUNTDOWN was able to move beyond a predominantly biomedical approach to NTD management to address support needs from a holistic perspective, including mental health and wellbeing, and generated new solutions for the integrated management of NTDs.

Investment in the COUNTDOWN programme has represented value for money throughout and is deemed to be cost-effective. The programme has: generated a body of research evidence that is being embedded in NTD programmes in focal countries through the use of tools and/or changes in practice that are influencing expanded access for more effective and equitable programming; produced a range of research products, including consolidated cross country findings, for a diverse range of relevant stakeholders and disseminated these nationally and internationally; and successfully built the sustainable capacity of individuals and partner organisations. Furthermore, equity and inclusion have been at the heart of the programme and have enhanced the value of the outcomes by making NTD programmes more accessible to vulnerable and marginalised people,

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators.

The overall logic of COUNTDOWN’s Theory of Change (depicted below) remained valid throughout and continued to guide programme activities. The outcome level detail was revised in 2019 to better align with objectives for the extension period/the status of the programme at that time. In order to achieve its impact of “Reduced morbidity, mortality and poverty associated with NTDs from application of new evidence for cost-effective scale up of sustained control and targeted elimination in line with the WHO 2020 NTD Roadmap and the 2030 SDGs”, COUNTDOWN research has focused on: improving the availability and accessibility of NTD interventions to individuals and communities; and on influencing improved consideration of gender, equity and the most vulnerable in NTD programming, so that more people can access appropriate interventions and treatments and the effectiveness of NTD programmes is increased.

The programme logframe aligns with the Theory of Change and is the basis of monitoring progress. Milestones and deliverables were most recently reviewed in July 2021 and took account of the impact on the programme of COVID- 19 and FCDO budget constraints.

## C: Detailed Output Assessment

Output Number and Title	1. COUNTDOWN generates research evidence to respond to priority information needs of NTD policy makers and programme managers
Output Score	A+
Impact weighting (%)	60%	Impact weighting revised since last AR?	No

Output Indicator		Final Logframe Target	Final Result Achieved
1.1. Number of approved research projects		i) Design: 0 / ii) Implementation: 0 / iii) Analysis/ Dissemination: 0 / iv) Completed: 21 / Total: 21	Met expectation / i) Design: 0 / ii) Implementation: 0 / iii) Analysis/ Dissemination: 0 / iv) Completed: 21 / Total: 21
1.2. Open access research publications: / Total no. of peer reviewed journal articles: / i) lead or co-author with home institution in LMIC / ii) female lead/co-author / iii) female lead/co-author with home institution in LMIC		Total no. of peer reviewed articles – 47: / i) Lead or co-author with home institution in LMIC: 28 / Ii) Female lead/co-author: 36 / iii) Female lead/co-author with home institution in LMIC: 10	Moderately exceeded expectation / Total no. of peer reviewed articles – 57: / i) Lead or co-author with home institution in LMIC: 37 / Ii) Female lead/co-author: 47 / iii) Female lead/co-author- home institution in LMIC: 12
1.3. Number of cross-country outputs and/or learnings		14 cross-country products that highlight how research exchanges have enabled change in research approaches, knowledge/skills and/or NTD programme design or delivery	Moderately exceeded expectation / Achieved: 16
1.4. Open access knowledge products (presentations, blogs, briefs) produced and disseminated		327 knowledge products, including 18 policy briefs, developed and geographic dissemination mapped, including through website download and page views	Moderately exceeded expectation / Achieved: 373 knowledge products; 20 policy briefs

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

Output moderately exceeded expectations. It is to COUNTDOWN’s credit that all 21 planned high quality research projects were completed by the programme end date, despite earlier inevitable delays on some studies as a result of COVID-19 restrictions.

An additional 12 peer reviewed research publications were produced in the period since the last annual review (June 2021) bringing the total number to 57 exceeding the target of 47. In 2022, there will be a special supplement focusing on co-production and implementation science for attaining NTD roadmap goals that will consist of 10 peer reviewed articles showcasing COUNTDOWN’s research.

There were an additional 3 cross-country outputs/learnings in the final programme period: 2 podcasts on how to effectively/ethically engage communities in research and how participatory research methods can be used to make NTD services more acceptable to vulnerable groups; a webinar attended by over 150 people from 20 countries that focussed on disseminating the latest COUNTDOWN research, with a discussion on how findings and progress made can be understood and applied in the context of the WHO NTD Roadmap 2030 (recording here); and a cross discipline toolkit for participatory research methods used by COUNTDOWN,

19 policy briefs (here) have been produced over COUNTDOWN’s lifetime, the most recent of which focuses on Motivation and Incentive Preferences of Community Drug Distributors and Teachers for MDA for NTDs in Nigeria.

Extensive efforts were made throughout the programme to ensure that research findings were accessible and relevant to non-technical audiences, for example by using photovoice stories, cartoons, radio broadcasts and tv interviews.

COUNTDOWN’s peer reviewed publications, policy briefs, case studies, and blogs can be found at https://countdown.lstmed.ac.uk/publications-resources

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

Delivery of this output has represented value for money throughout the programme period. Most recently, in the face of COVID-19 restrictions, COUNTDOWN planned and organised their work effectively to ensure that all research studies were completed on time, thereby maximising the evidence generated from the research investment. By delivering a range of research outputs (academic publications, policy brief, blogs, photo voice stories etc), to meet the needs of a wide range of stakeholders (academics, policymakers, practitioners, the community), COUNTDOWN have helped to ensure that their research findings reach a wide audience, thus fostering both enhanced value for money and equity.

Key Lessons / Sharing Learning

Key Lessons include:
- Photo booklets (created from a participatory research method that empowers participants to tell their own story) have been effective advocacy tools to highlight issues faced by people with NTDs e.g. stigma, social exclusion
- Involving persons affected by NTDs and care givers as co-researchers throughout the research and design intervention process can improve gender equality, equity and/or the situation of the most vulnerable.

The dissemination and uptake of evidence to inform policy and practice has been a core component of the COUNTDOWN programme. All research outputs will remain available on the COUNTDOWN website beyond the programme end date COUNTDOWN | Calling time on Neglected Tropical Diseases (lstmed.ac.uk). Moreover, throughout the programme period, the FCDO programme team have linked COUNTDOWN with the wider FCDO health cadre and advisers working on NTDs and facilitated workshops on emerging evidence etc. We will continue to look for opportunities to disseminate/feed in COUNTDOWN evidence to support policy and practice within FCDO and beyond.

## C: Detailed Output Assessment

Output Number and Title		2. COUNTDOWN supports incorporation of evidence to improve policies and operational plans and practices for scale-up of NTD control
Output Score		A+
Impact weighting (%)		25%	Impact weighting revised since last AR?	No

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
2.1. Involvement of key stakeholders at national, state and district level in developing linkages, partnerships, across disciplines, sectors and countries to enhance evidence-based NTD policymaking and programming			9 examples of how networks established during COUNTDOWN will be sustained beyond the life of COUNTDOWN to influence change to NTD policy and practice	Moderately exceeded expectation / Achieved: 11
2.2. COUNTDOWN undertakes research uptake and dissemination activities effectively			11 examples of change to NTD policy and practice resulting from COUNTDOWN evidence and research uptake	Met expectation / Achieved: 11

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

Output moderately exceeded expectations. Throughout the programme period, COUNTDOWN has actively and successfully identified and engaged with numerous key partners to support evidence based policy and practice for NTD control. They have successfully helped establish sustainable networks, and strategically supported and strengthened multiple research partnerships, collaborations and networks, to benefit NTD control and health systems strengthening.

To illustrate, COUNTDOWN :
- worked at a strategic level internationally, including participating in several Health Systems Global Thematic working groups: Emerging Voices, Fragile & Conflict Affected Settings, Social Science Approaches, and Community Health Workers;
- actively participated in the WHO Gender, Equity and Rights network, working with donors, partners and researchers towards improving gender responsiveness in NTD programming;
- supported the establishment of Ichords (Improving Community Health Outcomes through Research, Dialogue and Systems Strengthening) Community of Practice, a platform for communication, collaboration and knowledge exchange within social and behavioural science research disciplines to address implementation gaps and current issues facing NTD programmes
- was a founding member of the Genital Schistosomiasis (GS) Network comprising researchers, implementers, WHO, policy makers and communication experts who share information, findings, and progress on male and female GS, to improve diagnosis/treatment/prevention;
- helped strengthen mental health networks in Liberia, engaging with: the Ministry of Health and the Carter Centre, Liberia to strengthen stakeholder connections in country; United for Global Mental Health to strengthen collaborations/support future evidence uptake; and the NGDO NTD Network Disease Management and Disability Inclusion working group, focusing on stigma reduction and mental health;
- supported MDA restart strategies in the context of COVID-19. Recent research, on Community Drug Distributor adherence/understanding of revised MDA guidelines and community perspectives on the safety of the MDA in the COVID-19 context, identified challenges with adherence to new guidance and barriers to implementation. COUNTDOWN was well placed to influence evidence take-up, including with NTD programmes considering restarting MDA, implementing partners, WHO and donors.
- supported early case detection of skin NTDs and the prevention of negative health impacts from delayed diagnosis in Nigeria. Drawing on stakeholder meetings to map current and potential health seeking pathways for persons affected by skin NTDs, COUNTDOWN designed training packages/tools for community/primary health workers to recognise symptoms, provide basic treatment and refer cases on.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

Delivery of this output has represented value for money throughout the programme period. COUNTDOWN has effectively linked with priority stakeholders to maximise dissemination and exert strategic influence on research uptake opportunities, Advancing the gender and equity agendas were central components of the programme.

Key Lessons / Sharing Learning

The following cross-cutting themes were found to be central to aiding research uptake:
Sensitisation of stakeholders - to build awareness and acceptability of research and evidence
- Gender equity - gender shapes access and the level of coverage through interactions at the household. Equity can be mainstreamed into routine NTD programme monitoring, and areas with identified equity issues can be investigated and targeted with tailored programme adaptations. Disaggregating all data can highlight gender differences and is vital to promote a gender balance in all activities.
- Partnerships – it was important to work with groups outside of the NTD programme such as gynaecologists for FGS, and disability organisations on stigma and wellbeing.
- Trust -  involving NTD programme staff and implementers as co-researchers helped COUNTDOWN to develop capacity and ownership and to ensure that research was relevant and appropriate to the needs of the country. Community selection of Community Drug Distributors promoted trust within the community and was a found to facilitate acceptability.
- Responsiveness -  involving community groups to address identified gaps such as using seasonal calendars to highlight optimal timing of MDA or location of MDA delivery improved programme acceptability/effectiveness.
- Community Health systems - participatory approaches strengthened health system capacity and supported research uptake as programme implementation was informed by the perspective of the community and community level health implementers, and so more responsive to their needs and contexts.

FCDO will continue to share evidence, learning, and experience from COUNTDOWN with relevant colleagues in FCDO and with key external stakeholders (through NTD fora and programmes) as opportunities arise. We will take account of learning from COUNTDOWN in the development of any new implementation research programmes.

## C: Detailed Output Assessment

Output Number and Title		3. COUNTDOWN strengthens capacity for evidence-based decision making and planning through learning by doing amongst its staff, associated partners and country-based research communities
Output Score		A+
Impact weighting (%)		15%	Impact weighting revised since last AR?	No

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
3.1. Organisations engaged in COUNTDOWN implementation research have improved capacity			6 examples of sustainable change resulting from capacity strengthening at an institutional environment	Moderately exceeded expectation / Achieved: 7
3.2. Individual stakeholders engaged in COUNTDOWN / implementation research have improved capacity			6 examples of sustainable change resulting from capacity strengthening of individual stakeholders	Moderately exceeded expectation / Achieved:8

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

Output moderately exceeded expectations. Throughout the programme period, COUNTDOWN worked to help institutionalise the production and use of evidence to guide decision making within NTD programmes. To ensure that newly introduced research and research uptake activities would be sustained beyond the life of COUNTDOWN, the Consortium provided capacity-strengthening technical assistance to its staff, associated partners and country-based research communities.

Sustainability was central to the success of COUNTDOWN’s capacity strengthening strategy. The programme supported learning across consortium partnerships in how to identify capacity gaps and develop action plans to fill these gaps, focussing not only on technical, managerial, and financial processes within organisations, but also on the individuals in those organisations. The built-in opportunities for lesson learning and improvement within this approach means that initiatives could be scaled-up and become independently sustainable.

Examples of institutional capacity building and of sustainable change resulting from individual capacity strengthening include:
- Expansion of laboratory and staff to enable expertise in molecular genetics of infectious diseases. This subsequently led to the lab currently supporting diagnostics responses for COVID-19 testing in Ghana.
- Support to create institutional policies and processes such as safeguarding policies and gender awareness: Ghana, Cameroon, Liberia, Nigeria
- Support to strengthen partners’ resource mobilisation systems and broaden their funding base by providing training on grant applications and management
- Building the skills of research teams to lead and manage research projects and to liaise and influence policy: Ghana, Cameroon, Liberia, Nigeria
- Writing workshop series to support a wide range of authors from different disciplines and stages of their research careers: Ghana, Cameroon, Liberia, Nigeria
- Partner participation in a cross-country blog series on the impacts of COVID- 19 on research, healthcare and daily life, strengthened partnerships, provided experience of working across 6 countries and put blog writing training into practice. Blog posts are here

An end of programme mixed method capacity strengthening assessment, undertaken by FHI360, found that over time COUNTDOWN had successfully developed and refined its approach to capacity strengthening by listening to the needs of individuals and teams and adapting accordingly. Individuals had learned effective approaches that they planned to continue to use in their professional lives as learners, teachers, mentors and team leaders. COUNTDOWN was seen as a good model of building strategic partnerships.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

Delivery of this output has represented value for money throughout the programme period. By ensuring that sustainability was central to COUNTDOWN’s capacity building strategy, the programme helped to ensure that investments will support long lasting change and generate significant return in the long term.

Key Lessons

A key lesson from COUNTDOWN’s experience of capacity strengthening activities (particularly during the COVID-19 pandemic) is that it can be cost-effective to undertake capacity strengthening activities remotely rather than face to face. On-line training allows more people to learn at once and at the same cost, and can be just as effective as face to face training for some courses. FCDO will take account of learning from COUNTDOWN in the development of any new implementation research programmes.

D: Risk

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.

COUNTDOWN held its own risk register that was monitored and discussed with FCDO regularly. FCDO managed its own risk register and matrix.

FCDO risk ratings over the final year of the programme are shown below. The overall risk rating was Moderate and the risks were all within FCDO’s risk appetite.

Overview of project risk and mitigation 2020 / 2021
Strategy & Context	Policy & Programme Delivery	Public Service Delivery and Operations	People	Safeguarding	Financial & Fiduciary	Reputation	Overall
Major	Major	Minor	Minor	Moderate	Moderate	Minor	Moderate

Strategy and Context – Major – COUNTDOWN research activities were at risk from political instability and civil unrest in partner countries. This was closely monitored and project activities adapted where possible, for example by avoiding certain geographical areas. There was a heightened risk that research activities would be further delayed/not be able to be completed within the programme period, as a result of COVID-19 related pressure on health systems in Liberia and Nigeria. COUNTDOWN continued to closely monitor the situation and adapted their plans accordingly in consultation with FCDO, and all projects were completed on time.

Policy and Programme Delivery – Major – As the programme closed, the focus was on how to maximise opportunities to disseminate research findings and engage with/influence key stakeholders to advance research uptake. Planned, in person, cross-country events were not possible due to COVID-19 restrictions and, where possible, events were moved online. This limited interaction carried the risk that stakeholder engagement and influence may have been less effective than planned. COUNTDOWN continued to mitigate this risk by disseminating findings widely through a range of communication channels and by carefully planning on-line events to help meet programme objectives.

Public Service Delivery and Operations – Minor - COUNTDOWN were familiar with FCDO requirements and expectations and the programme had a good track record of effective, proportionate contact/relations with FCDO. FCDO continued to engage routinely with COUNTDOWN, closely monitoring performance.

People – Minor – COUNTDOWN developed strong partnerships and a culture of peer support. The programme was highly focussed on inclusion and gender equity and delivered very well on its programme of capacity strengthening.

Safeguarding – Moderate – the risk mainly related to ensuring that COUNTDOWN staff adhered to country guidance in UK, Liberia and Nigeria in relation to COVID-19. Teams were in regular contact and updates shared on an ongoing basis. All partners signed up to COUNTDOWN’s safeguarding policies and principles, designed to reduce the potential for harm arising from research in focus countries. Capacity strengthening activities in this area had been tailored to research projects.

Financial and Fiduciary – Moderate – LSTM has comprehensive financial management procedures and has demonstrated good governance (close monitoring of budgets and reporting) which helped protect FCDO funds from fraud or misuse. There was an ongoing exchange rate risk that was effectively managed through setting rates in advance and adjusting financial plans, and close monitoring.

Reputational – Minor– The research topics were not controversial, and findings were not contentious. LSTM is an experienced research partner with strong governance and ethics and a good understanding of FCDO expectations around standards and appropriate use of funds.

Risks over the programme period

Throughout the programme period, the highest level of risk related to Strategy and Context, as a result of: the impact of the ebola epidemic on the feasibility of undertaking implementation research in Liberia in 2015; the security situation in Nigeria throughout and, at times, in Cameroon; and most recently restrictions related the COVID-19 pandemic. There was a spike in delivery related risks in 2019 as a result of: uncertainty over a contract extension with associated challenges around the recruitment of health economists; MDA delivery challenges; and delays in the peer review of journal articles, and again in 2020/2021 as a result of COVID-19. Other risks remained relatively stable over the programme’s lifetime.

E: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency.

FCDO and LSTM collaborated well over the course of the programme and, over the last year, have been in regular contact, by e-mail, telephone and online meetings to discuss a range of issues, including: technical progress, the impact of COVID-19 on programme activities, the possibility of a contract extension, budget reduction, invoicing and forecasting, and programme closure, including asset disposal.

Due to the impact of COVID-19 and pressure on the global and UK financial economies, a planned extension to the COUNTDOWN programme did not go ahead. All underspend from earlier years was removed and the budget allocation for the period to April to 31 October 2021 was reduced to £750,000. Whilst disappointed, COUNTDOWN was understanding and worked with partners to revisit their workplan and budget. Staff contractual salaries in the UK, Liberia, and Nigeria were retained whilst budgets for travel, field teams, annual partners meetings and international dissemination plans were reduced. COUNTDOWN subsequently hosted multiple virtual meetings with stakeholders to maximise the impact and uptake of their findings.

As the programme drew to a close, the programme management teams in each country met weekly to closely monitor activity and associated spend. This resulted in further revisions to partner allocations to fulfil the objectives set out on the onset of each project: partner spend in Liberia increased to accommodate costs associated with the uptake of FGS interventions whilst the allocation to Sightsavers reduced due to activity constraints related to insecurity, and a reduction in staff costs in the final months

LSTM have been efficient in managing the programme budget and reporting on financial performance throughout. The final programme spend is £10,269,873 against an available budget of £10,270,008. Personnel was the most significant cost for the programme at 57%, with programme costs at 23%, travel at 9%, equipment at 2% and overheads at 9%.

COUNTDOWN has maintained a strong focus on economy and cost containment over the life of the programme and capitalised on opportunities to cost share among other projects when possible. Their conversion of research activities to a high number of concrete outputs (publications, tools, job aids etc) that have been widely shared and taken up, is testimony to COUNTDOWN’s efficiency. The successful leveraging of funds from various sources (including COR-NTD and effect:hope) in support of COUNTDOWN objectives totalled in excess of £143,000 in the last while, and enhanced the overall efficiency of the programme.

LSTM maintained a central record all equipment/programme assets centrally on a quarterly basis.
LSTM and FCDO are currently working to agree asset disposal arrangements.

Programme-level approach to monitoring and evaluation

FCDO have routinely monitored this programme though: regular dialogue with LSTM, including face to face meetings in Liverpool and at FCDO; written reports and exchanges; in person attendance at a consortium partner meeting (plans to attend a second partner meeting were cancelled because of COVID-19 restrictions); several COUNTDOWN presentations to the FCDO health cadre; and COUNTDOWN engagement with other FCDO funded NTD programmes.

Date of last narrative financial report	January 2022	Date of last audited annual statement	25 November 2021