## Annual Review Template

Title: Global partnerships for research on infectious diseases of poverty, sexual and reproductive health and rights, and health policy and systems.
Programme Value £ (full life): £35,000,000		Review date: 24 July 2021
Programme Code: 300343 (101 – 104)	AMP start date: 14 May 2018	AMP end date: 31 March 2023

Summary of Programme Performance
Year	2018	2019	2020	2021	2022	2023
Overall Output Score	A	A	A+
Risk Rating	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-GOV-1-300343/documents
DevTracker Link to results framework:	https://devtracker.dfid.gov.uk/projects/GB-GOV-1-300343/documents

## A. SUMMARY AND OVERVIEW
## [1-1 ½ pages]

Description of programme [1-2 paragraphs]

The Global Partnerships Research Programme (based at WHO) was set up to support the generation of research evidence, the strengthening of research capacity, and the uptake of evidence into policy, across three important topics for the health of vulnerable populations: infectious diseases of poverty, sexual and reproductive health and rights, and health policy and systems.

The Programme is delivered through three global special programmes/partnerships for health research and which are leaders and conveners of the research community in their respective fields. These are supported through core funding by UKAid. They are:
- TDR - The Special Programme for Research and Training in Tropical Diseases
- HRP - The Special Programme of Research, Development and Research Training in Human Reproduction
- AHPSR - The Alliance for Health Policy and Systems Research (the Alliance; until March 2021)
All three partners, although independent in their governance and financing, are hosted by WHO, anchored in the WHO Science Division. TDR and HRP are co-sponsored by relevant UN agencies, including WHO, UNICEF, The World Bank, UNDP and UNFPA. The programme also included a component for collaboration that focussed on the synergies of the three partnerships (which ended in March 2021).

All three partnerships have continued their core work as approved by their respective governance mechanisms including the governing boards on which FCDO is represented.

The seismic impact of the pandemic on the UK economy has forced the UK government to take tough but necessary decisions, and as announced in 2020, the UK has now moved to a target of spending 0.5% of GNI as Official Development Assistance (ODA) in 2021. Following a thorough review, the FCDO’s programme budget has been allocated in accordance with UK strategic priorities against a challenging financial climate of COVID.  Throughout the business planning process, the FCDO has strived to ensure that every penny of the ODA spend brings maximum strategic coherence, impact and value for taxpayers’ money. The move to 0.5% has resulted in changes to this programme, which is being adapted and will continue. This Annual Review reflects that the programme will refocus resources and so will deliver against a more limited set of outputs (1 and 2) and related targets. As a result, this Annual Review reflects on a programme in transition.

The UK remains a world leader in international development, not only through the impact of these financial allocations but also through the creation of the FCDO, integrating diplomacy and development to deliver greater impact. We will return to our commitment to spend 0.7% of gross national income on ODA when the fiscal situation allows.

Summary supporting narrative for the overall score in this review [1-2 paragraphs]

All three partnerships have continued to demonstrate good progress in evidence generation, dissemination, and capacity building in their respective fields, despite the challenges of the COVID-19 pandemic. All programmes have also worked on secondary impact of COVID-19 and therefore complemented other FCDO funded research to mitigate the primary impact of COVID-19.

In the reporting year, TDR has conducted critical and timely research, which complements other research investments by FCDO. TDR’s research include, for instance, implementation research on strategies to mitigate the impact of COVID-19 on TB control efforts in West- and Central Africa. This was only one outcome of the collaboration between the West African- and Central African Regional Networks for TB Control supported by TDR. A generic research package for facilitating the use of all-oral multi-drug resistant TB treatment regimens under operational research conditions is now being used by 23 countries worldwide. TDR has also developed a new guidance framework on a ‘multisectoral approach to the prevention and control of vector borne diseases’ following six commissioned reviews in the Journal of Infectious Diseases. Capacity building is one of TDR’s main outputs, and hundreds of TDR-trained researchers in countries applied their skills to the COVID-19 response effort (a survey found that 60% of TDR trained researchers were involved in COVID-19 research). TDR also developed a customised training course on Good Clinical Practice (GCP) for research teams in all hospitals participating in the WHO "Solidarity" clinical trial for COVID-19 treatments (available on WHO Academy’s COVID-19 mobile learning app). Gender equity advanced with the highest proportions of women amongst TDR grantees and women main authors of TDR publications, and with the launch of the TDR intersectional gender research strategy.

Throughout 2020, HRP continued its ambitious programme of research in sexual and reproductive health. Although some studies experienced COVID-related delays, no planned study was cancelled. HRP has generated a large amount of new evidence. For example, to respond to the significant threat to global health generated by the rise in gonococcal infections (est. 87 million global new gonococcal infections in 2016) and increasing antimicrobial resistance, HRP informed the preferred product characteristics (PPC) for gonococcal vaccines to guide R&D efforts. The results of the HRP-led WHO ACTION-I trial showed that dexamethasone can boost survival of premature babies when given to pregnant women at risk of preterm birth in low-resource settings. HRP rapidly pivoted to evidence needs in response to the evidence needs of addressing SRHR during the COVID-19 pandemic, including the multi-country “Unity Study” investigating maternal, pregnancy and neonatal outcomes for women and neonates infected with the severe acute respiratory syndrome (SARS-CoV-2), and the use of COVID-19 vaccines during pregnancy. In addition, HRP and WHO shared evidence-based guidance on sustaining delivery of essential SRH services during lockdowns, as well as addressing the surge in violence against women experienced globally.

In the reporting year, AHPSR has met or exceeded all milestones for 2020. It has been able to continue its work building the field of health policy and systems research, while also supporting research, evidence synthesis and closer interactions between researchers and policy-makers to contribute to responses to COVID-19 in various low- and middle-income countries. As such, through the Embedded Rapid Review platforms, the Alliance helped ensure COVID-19 responses in India, Georgia, Malaysia and Zimbabwe were informed by relevant evidence. It also published a number of key articles that demonstrate its leadership of health policy and systems research, including a supplement covering innovations in implementation research in low- and middle income countries. Important editorials and commentaries also cover the role of health systems research for climate change and health system reforms towards universal health coverage. The Alliance also continued and expanded its work on capacity building leading to country ownership and leadership of research.

In summary, this Programme has more than achieved its stated aims for this reporting year.

Major lessons and recommendations for the year ahead [1/2 page]

The new ODA spending target will have an impact on expected outputs and outcomes of this programme. For AHPSR, the closure of this component will be of significance given the relatively scarce donor base. We have pointed out to the AHPSR secretariat, WHO as well as to other core donors that the decision was the result of the FCDO internal review as described above and is not to be an indication of its performance. For the remaining components, outputs 1 and 2, the limited resource envelope will require adaptations.

The rebuilding of trust will take time and further personal engagement at various levels in FCDO. FCDO should also seek to influence WHO’s financial commitment to these research partnerships utilising part of the increased UK core voluntary contribution.

We recommend
1. that the FCDO team continues its active participation at the PCC and JCB of HRP and TDR, respectively, including continued participation in the donor subgroup of HRP. Assuming virtual meetings future, we aim for SRO/advisory as well as a programme management participation;
2. regular check-in’s between the FCDO SRO and the HRP and TDR Directors, and facilitate take-up of research findings also by FCDO policy and country teams, where appropriate.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

A summary of the theory of change for this intervention is shown below:

The Global Partnerships Research Programme was set up to follow FCDO’s health research priorities that include infectious diseases; sexual, reproductive, maternal, newborn, child and adolescent health; and health systems strengthening.

The Programme aims to achieve the impact of improved health, in particular that of vulnerable populations including women and girls, through generating new knowledge and enabling translation of evidence into policy and programming. This is achieved through two major outcomes: (i) national and international health policy and programmes being informed by best evidence; and (ii) global partnerships having a more cohesive, coordinated approach to fund, implement and disseminate proven interventions. Driving these objectives, the key outputs of the programme are:
1. High quality health intervention, implementation, and systems research evidence, including synthesis.
2. Enhanced health research and knowledge transfer capacity in low- and middle-income countries (LMICs).
3. Stronger research-policy dialogue, including activities and products that promote the uptake of evidence into policy, and an increase in the capacity of policymakers to demand and use research.

As multilateral partnerships, the three partnerships offer the opportunity to work alongside donors with shared strategic priorities, realising economies of scale to increase the reach and impact of funding. They are leaders and conveners of the research community in their respective fields. All are committed to commissioning and coordinating research studies, synthesising research, promoting the uptake of research into policy and practice, developing methods and tools for research, and building capacity to carry out and to use health research in LMICs. They also occupy a unique position within the UN architecture, hosted by WHO, and, in the cases of TDR and HRP, co-sponsored by other relevant UN agencies. This affords them a particular role in providing evidence to support policy and planning within these agencies. Their global convening power will ensure global dissemination of research findings and uptake into respective recommendations of the relevant agencies as well as domestic policymaking. A critical element also includes capacity building in research methods in their respective areas of expertise.

In the Business Case we described that, in contrast to previous funding phases, this Programme focusses on increasing aligned work between the three partnerships, which will build a more cohesive, coordinated approach to research and capacity building among global partners. In the last Annual Review, we already pointed out, that, while synergies between the partnerships remained important, this occurred independent of the incentives of a separate funding component. It was therefore recommended to roll output 4 into the outputs under each partnership. This would not have a bearing on the overall theory of change but component 4 and respective indicators were no longer required.

In light of the UKAid prioritisation conducted earlier in 2021, it was necessary to consolidate the scope of this Programme further. From FY 2021/22 onwards, the Programme will focus on the support of two partnerships, TDR and HRP, with reduced funding. Both partnerships will continue to include aspects of health systems research, but the stand-alone component for health systems research, delivered through the AHPSR ended with the FY 2020/21 in March 2021. While the theory of change remains valid, overall, the expectations of health systems related impact delivered through AHPSR will need to be adjusted. This will not require a change in the theory of change as impact under this component will still have been realised until March 2021. However, expectations for health systems related indicators will need to be adjusted and output 3 and respective indicators will no longer apply in future years.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

The intended impact of the programme is improved health, in particular of vulnerable populations, including women and girls, through:
- improved sexual and reproductive health and rights
- reduced global burden of infectious diseases of poverty
- improved provision of care through strong and resilient health systems (until FY 2020/21)

While the impact indicators are not intended to be measured on an annual basis, the outputs produced by the three partnerships are contributing towards the achievement of impacts and have already made a difference at country level, and globally, where new policies or guidance have been issued. All three partnerships have influenced global and national level policies and have built research capacity in their respective areas.

All three programmes have fully contributed to the planned outcomes and impact of the programme.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]
The Programme continues to offer a high degree of value for money and excellent outputs including critical knowledge products as global public goods, and increased research capacity in the respective areas of specialty. In addition, all partnerships have pivoted to the need for more knowledge and evidence on COVID-19. The Programme offers high complementary value in the context of FCDO’s health research portfolio, notably because the partnerships under this programme are co-funded by various donors reducing risk and offering higher VfM given economies of scale. The hosting arrangement at WHO, and, in the case of HRP and TDR, the co-sponsorship offer a strong convening power and influencing opportunities.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	TDR supports effective and innovative global health research, strengthens research capacity of disease-affected countries, and promotes the translation of evidence into effective interventions for health improvement.
Output number:		1	Output Score:	A+
Impact weighting (%):		33%	Weighting revised since last AR?	Yes, up from 30%

Indicator(s)	Milestone(s)	Progress
1.1 Number of externally peer-reviewed publications. Please breakdown by: / i. Proportion with first author from DEC institutions / ii. Proportion with female first author / iii. Proportion that are open access	>150 p.a. / i. >67% / ii. 50% / iii. 100%	Met expectations: 214 in 2020 (659 cumulative) / i. 81% / ii. 45% / iii. 93%
1.2 Number and proportion of innovative knowledge, new/improved solutions or implementation strategies developed in response to requests from WHO control programmes and/or disease-endemic countries and engaging disease-endemic country stakeholders	37 cumulative	Moderately exceeded expectations: 46 / (13 new in 2020)
1.3 Evidence demonstrating how FCDO funding has been used to build partnerships/collaborations to improve and strengthen research activities (with partners other than HRP/AHPSR)	Evidence provided	Moderately exceeded expectations through evidence provided on new partnerships as explained below.
1.4 Effective research uptake and dissemination activities.	Achieved & documented	Met expectations (as described in the Annual Report)
1.5 i. Number of DEC institutions and networks demonstrating expanded scope of activities thanks to TDR support, with narrative examples. / ii. Proportion of TDR grants/contracts awarded to institutions or individuals in DECs	i. 6 (cumulative) / ii. 75%	Met expectations: / i. 11 cumulative (6 in 2020), / ii. 71%
1.6 Number of TDR grantees/trainees per year, and proportion demonstrating career progression and/or increased scientific productivity, disaggregated by gender.	450 cumulative	Moderately exceeded expectations: / 630 cumulative

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

The number of publications in the last reporting year (214) and the cumulative number, the percentage of authors from DECs (81% of first authors), the percentage of women first authors (45%) and the proportion of open access publications (93%) underline TDR’s performance in the reporting year (listed in TDR’s results report). Much of the research conducted by TDR researchers led to concrete guidance and tools, such as the implementation research toolkit for the use of digital technology for TB control, a TB costing tool for favouring the integration of a health economics component in implementation research projects, a guidance framework on testing sterile insect technology against the Aedes mosquito.

As per TDR reporting, in 2020, five of the TDR deliverables were used by 44 countries in total, and another four deliverables were used in seven instances by global or regional stakeholders.
TDR also ensured that its capacity building can continue during the COVID-19 pandemic through online / virtual learning and thus developed an innovative online SORT IT virtual platform to enable training in countries to continue during the pandemic.

TDR has also been active in the Data Sharing Working Group of the COVID-19 Clinical Research Coalition, supporting several research projects to investigate how best to support researchers from LMICs to access, use and share COVID-19 data.

In terms of partnerships, five new Social Innovation in Health Initiative (SIHI) hubs (Ghana, Honduras, Indonesia, Nigeria and Rwanda) were established in partnership with institutions in countries, embedding social innovation in their portfolio. Critically, TDR is also active in in the Data Sharing Working Group of the COVID-19 Clinical Research Coalition, to support researchers from LMICs to access, use and share COVID19 data.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

TDR continues to offer a high degree of VfM and has demonstrated its ability to quickly pivot towards urgently needed COVID-19 related research and training. The high proportion of TDR trained researchers that are working on the COVID-19 pandemic right now underlines that TDRs capacity building has a lasting effect far beyond its original remit.
TDR works through various networks both in capacity building and research, making it even more efficient. Its results are used as global public goods and inform the global evidence base.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

There are no changes to this output in the reporting year.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

For the current Financial Year (2021/22), the UK investment was reduced significantly, and TDR will carefully evaluate how to ensure that all committed research and training activities can be completed.

Output Title	HRP supports the creation of new knowledge and synthesis of research evidence, with strengthening of research and technical capacity and of the research-policy dialogue.
Output number:		2	Output Score:	A+
Impact weighting (%):		33%	Weighting revised since last AR?	Yes, up from 30%

Indicator(s)			Milestone(s) for this review	Progress
2.1 Number of externally peer-reviewed publications. Please breakdown by: / a. Implementation and clinical trials / b. Global and regional estimates of reproductive, maternal, and perinatal conditions / c. Systematic reviews / d. Proportion of individuals trained are women / e. Proportion of women among PIs of new and ongoing HRP research projects / f. Lead/co-author whose home institution is in a LMIC			(cumulative milestones a-c) / a) 540 scientific articles published / b) 9 global/regional estimates published / c) 120 systematic reviews published / d) 50% of individuals trained through grants and activities of the HRP Alliance are women / e) 50% of first authors on HRP scientific papers are women / f) 50% of first authors on HRP scientific papers are from LMICs	Moderately exceeded expectations: / a) 562 / b) 18 / c) 40 / d) 59% / e) 62% / f) 51%
2.2 Effective research uptake and dissemination activities. List top 5 activities carried out in the reporting period. Briefly describe the research activity/product and why you think it was important	Evidence of effective uptake and use of HRP outputs by HRP cosponsors and by countries	Met expectations (as indicated in the HRP performance report, sections A,B,C,D,H,I and logframe) / Examples include i. The Medical eligibility criteria for contraceptive use (MEC) 5th edition and derivative products, ii. WHO recommendations on antenatal care for positive pregnancy experience, iii. Safe Abortion: Technical and Policy Guidance for Health Systems. iv. WHO guide to essential practice Comprehensive Cervical Cancer Control v. WHO clinical and policy guidelines for responding to intimate partner violence and sexual violence, vi. WHO Consolidated Guideline on Self‐care Interventions for Health: Sexual and Reproductive / Health and Rights
2.3 Evidence demonstrating how FCDO funding has been used to build partnerships/collaborations to improve and strengthen research activities (with partners other than HRP/AHPSR			75 initiatives conducted internationally with cosponsors and other UN partners / 75 initiatives conducted with cosponsors and other UN partners to support country level	Moderately exceeded expectations: / 75 / 91
2.4 Number of new or updated technical, clinical and policy guidelines issued on sexual and reproductive health			10 new or updated guidelines issued (30 cumulative)	Significantly exceeded expectations: / 20 (44 cumulative)
2.5 Number of research centres strengthened through HRP grants, and narrative examples of successes.			Indicator discontinued in 2020 under the new HRP Theory of Change as approved by the HRP PCC (Board)	Met expectations: Research centres & hubs strengthened (evidence below)
2.6 Number of individuals trained through grants and activities of the HRP Alliance (proportion women)			100 individuals (300 cumulative)	Significantly exceeded expectations / 507 (854 cumulative)

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

HRP generated a large number of publications (219 this year alone, 562 cumulative). Critical examples include the above mentioned HRP-led WHO ACTION-I trial on the impact of dexamethasone on survival of premature babies; a publication in The Lancet Global Health, which shows a worldwide decline in unintended pregnancies since 1990–1994 concurrent to an increase in the proportion of unintended pregnancies ending in abortion. These findings suggest that more women and individuals than ever before have been able to exercise their right to limit or space their pregnancies. New research from the Global Maternal Sepsis Study (GLOSS), a major HRP and WHO initiative, shows that infection has a much larger impact on global maternal mortality and morbidity than previously thought. The results of this important evidence are being included in various policy documents by WHO. Another critical publication showed that substandard and falsified medicines could contribute to the persistence of the high numbers of severe complications and deaths of women caused by postpartum haemorrhage, eclampsia, and sepsis, particularly in low- and middle-income countries.

HRP research also led to various guidelines issued by WHO, demonstrating the well-working interface between research and the uptake for the normative function of WHO. Evidence from HRP research was used to develop the WHO labour care guide. Critically for the global fight against female genital mutilation (FGM), HRP developed modelling that reveals a crippling economic as well as human cost (amounting to US$ 1.4 billion globally per year). For individual countries, these costs can require between 10% and 30% of their entire yearly expenditure on health (see also the FGM Cost Calculator available to countries to estimate their burden). HRP, in collaboration with WHO, UNICEF, UNFPA and PATH, launched a new guide, Digital implementation investment guide (DIIG): integrating digital interventions into health systems, to help ensure that digital health investments are effective, sustainable and equitable, and that they are implemented in a coordinated way and are appropriate for the local context.

In terms of capacity building, the HRP Alliance grew to seven regional hubs offering 13 short courses, training a total of 521 researchers from all six WHO regions, 58% of which were women. Sixty-two publications were published by the seven HRP Alliance hubs in 2020. Importantly, 62% of published papers had a female lead author.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

The proposition in the Business Case towards HRP has been maintained and now expanded to include research on the consequences of the COVID-19 pandemic on Sexual and Reproductive Health and Rights, including maternal, adolescent and child health.
The partnership continues to offer a high degree of value for money through its extensive global network (utilising WHO structures as well as the role of the co-sponsors). Its colocation with the WHO Department of Sexual and Reproductive Health and Research results in a high degree of policy uptake and influence. Its very active Board and STAC ensure independent governance and technical oversight, respectively.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

No changes to the outputs. Indicators have been brought in line with our reporting, so that all indicators can be reported on an annual basis. One indicator (2.5), although fulfilled for this year, will not be reported in future years as per the Board’s decision.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Recommend deleting output 2.5 as per future joint reporting requirements.

For the current Financial Year (2021/22), the UK investment was reduced significantly, and HRP will carefully evaluate whether and where further donor funds can be mobilised and how to ensure that all committed research and training activities can be completed.

Output Title	AHPSR supports the generation and synthesis of new evidence to improve understanding of health systems, contributes to effective uptake of research into policy and practice, and enhances the capacity to do and use research.
Output number:		3	Output Score:	A+
Impact weighting (%):		33%	Weighting revised since last AR?	Yes, up from 30%

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of externally peer-reviewed publications. Please breakdown by: / i. Lead/co-author whose home institution is in a LMIC / ii. Female lead/co-author / iii. Publications that are open access	583 cumulative / i. LMIC lead author 50%, / ii. Female lead author 50%, / iii. Open Access100%	Moderately exceeded expectations: / 630 cumulative / 44% / 58% / 100%
3.2 Evidence demonstrating how FCDO funding has been used to build partnerships/collaborations in order to improve and strengthen research activities (with partners other than HRP/TDR)	45 examples cumulative	Moderately exceeded expectations. / 59 cumulative (21 new partnerships; particularly with other WHO departments and regional offices)
3.3 Effective research uptake and dissemination activities. List top 5 activities carried out in the reporting period. Briefly describe the research activity/product and why you think it was important.	15 examples cumulative	Met expectations 15 cumulative (5 new activities); as per AHPSR 2020 annual report.
3.4 i. Evidence demonstrating how FCDO funding has helped build local capacity and infrastructure / ii. Proportion of partner institutions leading AHPSR funded research that are based in LMICs	i. 30 instances cumulative / ii. 85%	Moderately exceeded expectations / i. 48 cumulative instances (14 new) / ii. 97% (56/58 new grants)
3.5 Number of individuals trained through grants and activities of the Alliance (proportion women)	1953 cumulative / (50% women)	Significantly exceeded expectations (partly due to pivoting towards online training) / 4613 cumulative / 2340 (new) 55% women

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

In 2020, the Alliance supported 18 ongoing projects across 38 countries. Many of these projects focus on embedding research within regional and country structures. It conducted a wide variety of research in health policy and systems and re-programmed some of its work to support the response to COVID-19. For the latter, staff and associates of the Alliance described the research needs and priorities for health systems research in the context of the pandemic. In addition to other publications mentioned in the summary section, the Alliance has also taken forward its work on ‘Learning Health Systems’ and a flagship report on this topic is awaited. The Alliance also co-edited the special themed issue of the WHO Bulletin, ‘Primary Health Care: Realizing the Vision’.

The Alliance also continued and expanded its work on capacity building leading to country ownership and leadership of research. For example, as part of the HIGH-Res initiative to build institutional capacity, the team in Malawi helped to reinvigorate Ministry of Health technical working groups and integrate the review of evidence into their terms of reference. The BIRD project has now established six HPSR fellowship programmes, one in each WHO region.
Additionally, an independent evaluation of the Alliance commenced in November 2019 and a draft report was discussed at the virtual board meeting in June 2020. This report confirmed that the Alliance met, and in various areas overachieved, its set targets. It also identified areas for improvement, including in the governance and management of the Alliance.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

Hosted by WHO and collaborating with and working through its global network, the Alliance offers an unparalleled power of convening and thought leadership in the areas of health policy and systems research. It continues to offer value for money.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

Owing to the ODA prioritisation following the economic downturn in the UK, this output and support to AHPSR will end with FY 2020/21. Other core donors and WHO were made aware that this was independent to the important role and progress of the Alliance. Therefore, this change is not a result of this (or other reviews) but a consequence of the budgetary pressures and prioritisation in the UK.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

The external evaluation of the AHPSR was completed in 2020. This evaluation highlighted the achievements of the Alliance and made a number of critical recommendations, which were taken up by the AHPSR Secretariat, the STAC and Board and influenced the new Strategy. FCDO participated in all Board meetings and as part of subgroups to ensure that recommendations were followed through.

D: RISK [½ to 1 page]

Overview of risk management [1/2 page]

Overall risk rating: The overall risk is currently considered Moderate (last reviewed in March 2021). The risks are within FCDO’s risk appetite.

For the detailed programmes, the overall risk for TDR is considered Moderate, for HRP Moderate and for AHPSR Major.

Strategy & Context	Policy & Programme Delivery	Public Service Delivery and Operations	People	Safeguarding	Financial & Fiduciary	Reputation	Overall
Moderate	Moderate	Moderate	Minor	Moderate	Moderate	Major	Moderate

Strategy and Context – Moderate – Work of all three partnerships includes work in challenging contexts derived from political uncertainty as well as the COVID-19 pandemic. However, we would not consider this risk higher than average, and given the global network, all partnerships are able to pivot or prioritise activities accordingly. For HRP, some of the topics are sensitive with donors and locations of research, however this is mitigated by a broad funding base and the independence of the co-sponsors in the implementation.

Policy and Programme Delivery – Moderate – Research always carries a risk of delays due to ethical and other research protocol approvals. However, the long-standing experience of the partnerships and WHO should be able to mitigate against this risk adequately. A risk continues to arise due to delayed project delivery caused by the ongoing COVID-19 pandemic and ad-hoc mitigation measures, such as lockdowns. This is mitigated by increased virtual working and meetings as well as adapted timescales to allow for COVID-related delays. There is a moderate risk that the reduction in UK/FCDO funding will result in less research and capacity building being possible. This is particularly important for the AHPSR. However, AHPSR was (prior to the FCDO prioritisation exercise) aiming for a broader funding base. If achieved, this will help to compensate for the loss of UK funding. We have also advocated to WHO for using core voluntary funding towards all three partnerships, and the AHPSR in particular.

Public Service Delivery and Operations – Moderate – FCDO staff will need to continue to influence other funders (and WHO) to support the three partnerships. Additionally, the need of engagement is not considered above ‘moderate’. But it would be in FCDO’s interest to maintain positive and constructive relationships with all three partnerships. There would also be benefit from continued engagement with other donors. Therefore, there is a risk of slightly increase engagement from FCDO. However, the reduction from 4 components to 2 will compensate for this.

People – Minor – The partnerships have developed strong partnerships globally and within the WHO as well as research networks. This will allow for mutual support. All partnerships are focussed on gender equity.

Safeguarding – Moderate – There is a risk that the programme is not being able to safeguard vulnerable communities or individuals against harm. This arises from the potential for harm caused by research activities in the research countries. However, WHO has a strong policy on safeguarding and FCDO and WHO have previously discussed this.

Financial and Fiduciary – Moderate – As with any UKAid programme, fraudulent activities, and misuse of funds by individuals and project partners can pose a risk. To mitigate against this, FCDO have carried out a due diligence in advance of the programme and WHO oversees the financial handling of all the partnerships. Annual financial reporting, and interim reports where available, will be reviewed by FCDO. There is, however, a considerable amount of risk for all three partnerships (and the Alliance in particular) resulting from the loss of UK funding. Mitigation through search of other donors has commenced and the broad funding base for TDR and HRP will mean that the programmes this risk is lowered. Overall, we consider this as a ‘moderate’ risk.

Reputational – Major – If any of the above risks materialise there is an associated reputational risk for FCDO. And while this is considered minor, there is a ‘major’ risk resulting from the unexpected reduction in funding to all three programmes and the ending of the FCDO support to the Alliance. Rebuilding of trust – through engagement at all levels at FCDO and the UK Government – appears critical going forward.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency. [max 1 page]

Performance of partnerships

The relationship between FCDO and WHO, through the Programme and individual partnerships, has continued to remain strong, despite the difficult circumstances both sides have faced over the last year. There is regular communication on issues affecting the partnerships, and FCDO is represented on each partnership’s relevant governance board.
All three stand-alone partnerships have exhibited significant progress over the reporting period, and it is no reflection of this performance in that FCDO have been required to realign our funding to these elements of the programme going forward. The decision to cease funding to the Alliance was discussed at length with our WHO partners and agreement has been reached on the revised approach and the decision to re-focus our support to the areas where it can continue to be effective.

Quality of financial management

The programme continues to use WHO financial management practices and procedures and accounts are audited annually by WHO’s Internal Audit Department. This programme also forms part of the annual external independent audit of WHO. WHO has robust policies on Fraud and Corruption, aligned with FCDO requirements as set out in the MoU.

At country level the funds are channelled through central WHO departments to the WHO country office where financial procedures are subject to the same scrutiny and internal audit as at Head Quarters. All three programmes continue to perform well financially. There are minimal fiduciary risks, and all three partnerships have responded and adapted well to the changes which the COVID-19 pandemic posed to their workplans and budgets.

Financial Position

Over the reporting period, FCDO disbursed £3.3m of funding, split between the three main work streams. This funding, provided to the two special programmes: TDR and HRP, and the AHPSR partnership, allowed WHO to achieve a broad range of results which impacted on the lives of people in countries where WHO works.

The financial statements outline the activities undertaken by the three partnerships with the core funding obtained.

TDR emphasized its work with partners to provide strong support to priority areas of the partnership’s work, with an emphasis on implementation research and capacity building, including through digital technologies. Emphasis was also put incorporating intersectional gender analysis into research on infectious diseases of poverty as well as multisectoral approaches to the prevention and control of vector-borne diseases. FCDO funding provided dozens of grants to scientists to address regional priorities and support to regional universities, regional training centres and hundreds of postgraduate students and researchers through the postgraduate training scheme in implementation research, and through short, good practice courses as well as massive open online courses (MOOCs).

HRP benefited from FCDO funding to support its full programme of research and research capacity building activities aimed at strengthening sexual and reproductive health and rights in low-income settings. Their research and evidence provided opportunities to mobilize, improve evidence-based practice, and save lives.

The core funding from FCDO helped AHPSR advance health policy and systems research and strengthen capacities for health policy and systems research in LMICs; and stimulate the demand for using evidence in health systems strengthening. Efforts to stimulate demand for evidence included the Embedding Rapid Reviews in Health Systems Decision-Making platforms (ERA) programme. The platforms played a key role in supporting their respective governments in underpinning elements of their COVID response with evidence.

	HRP	TDR	AHPSR
Date of last narrative financial report(s)	November 2020	November 2020	November 2020
Date of last audited annual statement (s)	May 2021: / Financial statement (who.int)