 Programme Completion Review – September 2020

Title: Strengthening Public Financial Management, Anti-Corruption and Accountability Institutions in Sierra Leone
Final Programme Spend £ (full life): 4,109,329	Review Date:	June 2021
Programme Code: 300254	Start Date: 28/09/2018	End Date: 31st March 2021

Summary of Programme Performance

Year	2019	2020	2021
Programme Score	A	A	A
Residual Risk Exposure Rating	Major	Major	Major

DevTracker Link to Business Case (and any addendum):	http://iati.dfid.gov.uk/iati_documents/39975011.odt
DevTracker Links to all logframes used during programme lifetime:	http://iati.dfid.gov.uk/iati_documents/49041437.xlsx

A. Summary and Overview

Description of the programme and what it has achieved

The Strengthening Public Financial Management, Anti-Corruption and Accountability Institutions in Sierra Leone (PFM+) programme was designed to deliver a more effective executive that can raise, allocate and transparently use public resources to drive inclusive development and deliver services for the people of Sierra Leone. The programme aimed to do this by providing strategic and technical assistance to Government institutions, including the Ministry of Finance, National Revenue Authority, Anti-Corruption Commission, Judiciary and Office of the Chief Minister, to support their reform efforts in relation to public financial management, revenue, anti-corruption and accountability. It also supported a range of civil society organisations (Christian Aid, the Budget Advocacy Network, Centre for Accountability and the Rule of Law, Restless Development, and Institute for Governance Reform) to hold the government to account and gather data against which to independently assess progress.

The programme was split into two Phases. Phase 1 was designed to test reform appetite and lay the building blocks for a scaled-up Phase 2, which would be delivered under a single contract drawing together all elements of the programme. Due to the ODA budget reductions associated with Covid-19 and the UK’s shift from spending 0.7% of GNI on ODA to 0.5% of GNI, a decision was taken in April 2021 to cancel the Phase 2. This cancellation was not a reflection of Phase 1 performance. Given these unexpected circumstances, this PCR considers performance based on Phase 1 targets and their contribution to overall objectives, recognising that without completion of Phase 2, full assessment against the original business case is not possible.

Overall, Phase 1 met expectations. It resulted in significant progress in payroll integrity and control, as well as strengthened budget comprehensiveness and transparency. In the revenue space, the project helped to support a range of NRA management priorities, influencing the design of reforms to improve compliance and taxpayer engagement drawing on lessons from Rwanda and Kenya. By the end of Phase 1, the relationships and institutional structures had been established within the anti-corruption space to support effective engagement on grand scale corruption under Phase 2. Given the positive results achieved under Phase 1, UK Minister of State for Africa approved contintuation of the programme to Phase 2 in October 2019. Alongside this impact, Phase 1 produced valuable lessons, including around the role of civil society, which informed the Phase 2 Terms of Reference. Resolving corporate compliance issues related to the initial procurement process for suppliers under Phase 2 (running from November 2019-July 2020), required a second call for bids and technical evaluations between August 2020 and February 2021. To maintain activity during this period, Phase 1 was granted a £600,000 extension between 30th September 2020 and 31st March 2021. During this time, the programme team’s activity remained focused inwardly on procurement work to mobilise Phase 2 successfully. Therefore, PFM+ not progressing to Phase 2 was due to unforeseen and exceptional funding circumstances created by COVID-19, unrelated to the performance of the programme or expectations on what it could deliver. Whilst the impact of Phase 1 cannot be fully understood in the absence of progression to Phase 2, there are still valuable lessons to be drawn from its implementation, which are relevant for any future programming reengagement in Sierra Leone on the agendas, and given their cross-cutting nature, for interventions across our wider portfolio. They also add to the existing evidence base on the role PFM and AC institutional strengthening can play in addressing upstream governance failures, and subsequent improvements to service delivery and human development outcomes.

Major lessons learned, evidence generated and recommendations

Key lessons from the PFM+ programme are:
- Activity must reflect deep understanding of Sierra Leone’s informal political economy within a highly personalised political system. Delivery must adapt to quickly changing political dynamics within and between institutions, with awareness of interpersonal relationships between stakeholders not represented by official remits or formal structures. The relative political capital of stakeholders should direct entry points for activity, identifying where transactional incentives for reform align with programme objectives. This should be understood as a necessary way of working and built into approaches from the outset, rather than primarily as part of delivery risk mitigation strategies.
- Within this political context, flexible, adaptive, iterative programming where activity is not overly bound to logframe indicators is important to achieve objectives. This requires higher risk appetites and increasing FCDO comfort levels with Technical advisers (TA) being empowered to operate independently with authority over small tactical spend, to capitalise on political openings and navigate blockages. FCDO programme teams should be encouraged to use their judgment in managing space for this, maintaining focus on achieving outputs and outcomes, rather than holding attention at the activity level.
- Priorities should be set jointly with the Government formally, with local priorities taking precedence, and should consider the realities facing both individuals and institutions and the risks involved in reform. Workplans should be developed with commitments on both sides. The level of ambition needs to be realistic given the limited fiscal envelope and limits to GoSL absorptive capacity.
- Reforms must be feasible and recognise the continuing limitations in capacity. The aim is establishing, consolidating and sustaining essential functions, not to try to put systems in place according to non-context specific best practice, which far exceed available institutional and personnel capacity.
  [note] A development trap which Lant Pritchett terms ‘isomorphic mimicry’
- Strong and supportive professional relationships between FCDO, TA and GoSL counterparts, characterised by trust, honesty and collaboration, are essential. These develop through close and sustained personal interaction and are required to deliver sustainable change in institutional working practices. Time in the project work programme should be devoted to building relationships.
- Support should target interdependent and mutually reinforcing efforts to strengthen public financial management, anti-corruption and revenue institutions. Effective joint working requires improving working relationships between institutions in practice, which can otherwise often view each other in competition for political space and resources.
- Processes are needed to build the capacity of Sierra Leonean CSOs across a range of areas including financial management, programme management and technical analysis. This includes strengthening their ability to create coalitions for change around key agendas and develop effective influencing campaigns, which draw on a range of communication channels with Government, the public, and other relevant stakeholders.
- Phased approaches to test and adapt programme activities have advantages. However, in order for interventions to remain strategic (supporting design and delivery of policy change, intended to stimulate and embed sustainable institutional reforms) Phases should sit within a set 5 year programme lifespan. This should assure continuity and therefore stakeholder buy-in, whilst maintaining contractual structures that allow for break clauses to end activity early if required.

How this report was conducted

This report is a deskbased review of the programme, led by the programme SRO with contributions from the lead adviser on anti-corruption. The report draws on partner reporting and conversations with key GoSL stakeholders on a continual basis over the duration of Phase 1. This approach was felt to be proportionate given the level of programme spend and the fact that the programme was closed early as a result of the FY21 ODA reductions, making it politically sensitive to seek detailed stakeholder interviews at a time when FCDO are withdrawing support at short notice across a range of areas. As noted above, the PCR could only focus assessment of programme performance against final logframe targets for Phase 1.

Actions following approval of this report

All immediate actions around programme closure have been completed. All assets under the programme have been disposed of and there are no outstanding financial transactions or partner reports. The only action outstanding prior to programme archiving is to receive and review the audit from Christian Aid Sierra Leone for the year ended 31st March 2021, noting they have already provided a project specific audit. This is expected by December 2021.

With Phase 2 not progressing, the programme team has reconsidered how the UK can continue supporting progress on the PFM and AC agendas. Internally, this has included incorporating TA support to the MoF and NRA into our private sector development programming, and contributing to the PFM agenda with sectoral work under our education interventions. Externally, whilst Phase 2 intended to generate wider support from other donors with a ‘crowding-in’ approach, we have shifted engagement to encourage others to ‘step-up’. This will include influencing design of other donor interventions in the space, to specifically fill gaps left by UK withdrawal. On support to the ACC and ACD, given the absence of other donor activity, we have leant into our development diplomacy offer, including support from other parts of HMG, international NGOs and use of small strategic FCDO funds for targeted capability development. Finally, lessons from Phase 1, on using political influencing to advance development objectives of policy reform and institutional change in Sierra Leone, will be captured and shared across the FCDO office. This will inform new ways of working which fuse our political and governance approaches, and apply this to policy engagement and development interventions across our wider portfolio.

## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	Phase 1: £3.5m / Phase 2: £11.5m / Total: £15m	£4,109,328.88
Timeframe	Phase 1: September 2018 – March 2020. / Phase 2: April 2020 – March 2023	28/09/2018 – 31/03/2021
Outcomes	Stronger public expenditure management, revenue, oversight and anti-corruption institutions resulting in increases in revenue, increasingly effective action on corruption, and improved public financial management.	In the September 2020 Annual Review the programme was on-track against 5 out of 7 outcome targets. It was off-track on revenue as a % of GDP due to Covid-19 impacts and against the implementation of the PFM reform strategy due to poorly functioning governance and monitoring structures around this. / There were no March 2021 outcome level targets in the logframe as the next review was due in September 2021 before the decision in April 2021 to cancel the Phase 2.
[note] Additional spend result of Phase 1 extension, see Section A

Overall assessment of programme outcomes, sustainability and VfM

Given the programme closed early due to the ODA budget reductions, the programme did not achieve the ultimate outcome level objectives in full. However, our assessment is that under Phase 1 the programme has made significant contributions towards these outcomes and was on track to achieve the outcome level results, albeit against an updated counterfactual that accounted for the impacts of Covid-19 on the macro-fiscal position.

Table 1 gives progress against the September 2021 outcome targets achieved by the end of the programme. As can be seen, in most cases there is no data available to assess performance. However, the Business Case set out key measures to assess the effectiveness / value of the programme and it is possible to report against these.
- Improvements in revenue. In 2019 domestic revenue was 14.6% of non-iron ore GDP. Above the IMF target and up from 13.7% in 2018. In 2020 revenue was projected at 15.6% of GDP pre-Covid, however as a result of the economic impacts of Covid and the NRA agreeing to defer tax payments to support the private sector, estimated collections were 13.3%. In 2021, the Government expects revenue to remain steady at 13.4% of non-iron ore GDP.
  [note] All figures taken from the IMF Rapid Credit Facility Report, March 2021, Country Report No. 21/58
- Public Expenditure Management, specifically, improvements in the Open Budget Index score, percent of unqualified audit reports and procurement compliance scores. There has been a slight improvement in the Open Budget Index score (from 38/100 to 39/100) and the Ministry of Finance has prioritised improving this further. In Phase I FCDO has not provided support on audit or procurement.
- Increase in savings and payroll cleaning. In 2020 the project delivered over £100,000 in payroll savings. Over the life of the programme ghost workers have been removed from the payroll and over 99% of employees’ records have been verified with those at NCRA.
- Increase in the number of recovered stolen assets from successful corruption cases, and a reduction in money stolen. As reported in section C, recovery of funds is expected to be slightly lower in 2020 than in 2019, due to a reduction in the backlog of historical cases. As of July 2020 £0.3m had been recovered, compared to approx. £0.9m in 2019 and £0.7m in 2018.

Table 1: Performance against Outcome Indicators
Outcome Indicator		Target September 2021 (Phase 1)	Achievement
1.1	Revenue as a % of non-iron ore GDP	13.5	No data available at time of review
1.2	PEFA, TADAT and Open Budget Index reports [exact timings TBD].	Positive trend on PEFA / TADAT (timing tbc) - NB: targeted TADAT / PEFA indicators to be identified during inception.	No data available at time of review. / Government have indicated plans to conduct a government-led PEFA. This is being discussed with donors.
1.3	Implementation of the PFM Reform Strategy	By September 2021, a new PFM reform strategy has been developed (or is in final draft) and effective governance mechansisms are in place.	The PFM strategy has not yet been reviewed.
1.4	Number of grand corruption cases investigated, and prosecuted by Anti-Corruption Commission, and adjudicated by the Anti-Corruption Court to completion.	25	From June 2019, the ACC has prosecuted 19 corruption cases through the ACD. This has seen 49 public figures and their dependents brought to account for their actions in court, with a total of 20 years prison time being awarded where misappropriated funds identified are not repaid.
1.5	% of Commitment Matrix achieved	70%, including 50% of the High Priority actions	N/A - update of commitment matrix targets was delayed following the September 2020 annual review due to staff time being absorbed by Phase 2 procurement and ODA prioritisation exercise.
[note] Further details on Phase 2 procurement timeline included in Section A

As noted in the original Business Case, PFM+ built on previous FCDO anti-corruption, public financial management and revenue interventions in Sierra Leone. Phase 1 was designed to test approaches and government commitment before proceeding to a scaled up Phase 2. In particular Phase 1 aimed to:
- Test the reform commitment of the new Government, which came to power following the March 2018 elections, and establish relationships with new senior stakeholders.
- Learn lessons about how best to integrate interventions across public financial management, anti-corruption and revenue, using a mix of technical assistance and civil society engagement, in order to build a flexible approach that could take advantage of reform windows, step back from what isn’t working, and deliver greater impact by recognising areas of complementarity across the three thematic areas.
- Test approaches to expand anti-corruption work from interventions focused on societal change, strengthening social attitudes against engaging in corruption and promoting local ownership of accountability agendas to also include building state capacity to tackle grand corruption involving public officials and politically exposed persons. A politically informed, iterative and adaptive approach was essential given this more direct intervention within a highly politicised (and therefore higher risk) space, where strong elite incentives against addressing corruption exist throughout the system across the political spectrum. The Bio administration’s supportive rhetoric for anti-corruption provided a well-timed political opening, which Phase I was able to capitalise on, and ensure this top-down approach to alter elite behaviour was demand driven.
It is our assessment that Phase 1, in addition to delivering progress towards outcome level objectives, also provided effective learning across these three issues, which informed the design of Phase 2. Although Phase 2 will not be going ahead, this learning is still valuable to inform policy dialogue, engagement with other donors and, where relevant, the integration of PFM, revenue and anti-corruption engagement across FCDO SL’s portfolio.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators.

The Theory of Change set out in the Business Case argues that by providing:
- Mentoring to senior/technical leaders on PFM, anti-corruption and accountability reforms
- Ongoing institutional and political economy analysis to guide implementation
- Capability building of PFM institutions in revenue, payroll, procurement and budget credibility
- Capability building of a ‘basket’ of oversight institutions (e.g. Anti-Corruption Commission, Civil Society, Parliament, Audit Service), providing internal checks to the system against corruption
This will lead to:
- Improved revenue generation
- Public expenditure management systems strengthened
- Oversight and anti-corruption institutions strengthened in their abilities to deliver
Taken together, this will lead to a more effective executive that can raise, allocate and transparently use public resources to drive inclusive development, as indicated by:
- Agreement reached with IMF and a credible ECF programme is in place.
- Improved fiscal position of the Government of Sierra Leone.
- Actions taken on petty and grand corruption are increasingly effective.
- Views of ordinary Sierra Leoneans including women, vulnerable and excluded groups are represented in the way PFM, anti-corruption and accountability systems operate.
This theory of change remained valid throughout the programme’s life. The ability to quickly adapt and renegotiate TA workplans, drawing on strong relationships with Government counterparts and combined with technical and political economy insights from the embedded TA, ensured that advisers’ work remained relevant, responding to emerging priorities whilst also maintaining a longer term focus on outcome level deliverables. The major negative external shock from Covid-19 led to the IMF ECF programme being paused and replaced by Rapid Credit Facility arrangements and a deterioration in the Government’s fiscal position. However, the programme adapted well to respond, maintaining reform momentum largely due to the continued presence of most of the technical advisers in country. Where advisers had to leave the country, which was the case for support to the NRA, it was not easy for them to work remotely and momentum slowed. Had the programme continued, it is expected that the success indicators would have remained valid, albeit against an altered counterfactual that took into account the macro-fiscal impacts of Covid-19. Government high-level commitment to reform across the three focal areas remained in place throughout the programme lifetime, although at the detailed level this commitment varied across issues and actors overtime in response to competing demands

The overall output score of an A is a good reflection of achievements at outcome level as well. As described above, there are a number of areas where there is early evidence of outputs feeding through to outcome level results. There have been no changes to outcome and impact indicators since the last Annual Review, which details changes since the Business Case. The theory of change and logframe were due to be reviewed as part of the Phase 2 inception.

## C: Detailed Output Assessment

Output Number and Title	1. Strategic and technical assistance that successfully supports and influences strategic direction of Government reforms, builds GoSL capability and supports delivery of key reforms.
Output Score	A
Impact weighting (%)	60		Impact weighting revised since last AR?	N

Output Indicator		Starting Target	Final Logframe Target (Phase 1)	Final Result Achieved
1.1 # Advisers reporting to GoSL and mutually agreed to be performing satisfactorily at break point		N/A	5	6
1.2 % Advisers' workplans with concrete deliverables (including on capacity building) agreed within 6 weeks of mobilisation		N/A	100% of 5 advisers following end-September extension and all new advisers brought on board after this.	120% / (100% of the 6 advisers workplans)
1.3 % workplans delivered on schedule and with clear evidence of GoSL engagement / buy-in		N/A	85%	88%
1.4 Achievement of workplan milestones and targets		N/A	(Sept 21) PFM+ strategy and 3 thematic approach papers finalised, workplans for the first 12 months finalised (including key delivery milestones for Sept. 2021), and delivery against these workplans is on track.	N/A – this referred to Phase 2, which was not taken forwards.
1.5 Phase II mobilisation		N/A	(Sept 21) Phase II inception phase completed. Supplier has core team in place and has demonstrated ability to mobilise qualified technical assistance beyond this.	N/A – this referred to Phase 2, which was not taken forwards.
[note] Given the flexible and adaptive nature of the programme targets at output level were agreed on an annual basis.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

Public Financial Management

Under Phase 1, work on public financial management focused on payroll control and management and strengthening budget preparation, credibility, oversight and reporting. In addition, technical advisers provided support on a number of ad hoc management priorities, which helped them to secure management trust and buy-in and therefore facilitated progress on the core reform set supported by the programme. The areas of focus reflect priorities to improve public expenditure management and the efficient and effective utilisation of scarce resources. Measures to strengthen controls over expenditure have become even more important in the context of Covid-19, which has placed increased pressure on the Government’s fiscal position. Under Phase 2, the intention was to deepen and expand engagement, including making stronger linkages down into education and health ministries, departments and agencies (MDAs). Where relevant, some of this work will be integrated into FCDO’s human development portfolio in recognition of the underpinning role public financial management plays in service delivery.

Over its lifetime the project has led to a significant improvement in the quality and integrity of payroll data, as well as strengthening control over the public sector wage bill by establishing a dedicated Payroll Quality Assurance Unit and a Payroll Audit team, improving workforce planning, and enhancing the management information available to senior decision makers. The project has benefitted from strong support from the Financial Secretary and the Payroll Budget Unit in the Ministry of Finance, as well as good working relationships with other institutions including the National Civil Registration Authority (NCRA), the National Social Security and Insurance Trust (NASSIT), the Human Resource Management Office (HRMO), the Police Payroll Unit, and the Teaching Service Commission (TSC). As a result of the project:
The Accountant General’s Department is able to monitor the accuracy of the data of 88,300 employees in the payroll system, including tracking changes made by individual data entry operators to build accountability mechanisms. This has led to significant improvements in data completeness and correctness. Over 99% of employees now have correct National Idenditifcation Numbers in the payroll and all employees who are paid into their bank accounts have an accurate BBAN. Dates of birth have been corrected for 17,000 employees, with implications for the calculation of retirement benefits. Approx. £40,000 has been recovered from employees with dual assignments and support to follow up the NCRA payroll verification process has resulted in approx. 1,600 ghost workers being removed from the payroll, with monthly efficiency savings of approx. £200,000 expected. Going forwards, a newly established Payroll Quality Assurance Unit will ensure this work is continued.
- There have been substantial improvements in pension management. Reconciliation of NASSIT contributions, combined with correction of NASSIT numbers within the payroll system, has improved the process of crediting social security contributions to individual accounts. Unreconciled records in 2020 averaging just 5,000 per month compared to an average of 32,000 per month in 2019. £650,000 in unpaid social security contributions, affecting 3,223 employees, were identified through an audit supported by the project. The AGD payroll team is working on clearing the backlog through the IFMIS CSM payroll system. This will ensure that retirement process of these employees is smooth.
- Oversight has been improved through a strengthened policy environment, better reporting to senior stakeholders and the establishment of a dedicated Payroll Audit Team. Regular Payroll Reports have been discussed with the Financial Secretary and the Economic Management Team (EMT), chaired by the President. Following up on issues identified the project developed a Payroll Policy Document to serve as a guide for those administering the GOSL payroll on daily basis and a Teacher Recruitment and Retirement Policy, to strengthen teacher workforce management, critical in the delivery of the Government’s flagship Free Quality School Education programme. The Payroll Audit Team has already had some major successes, for example in identifying the challenges with social security contributions described above. In addition, the Payroll Audit Report for the first half of FY2020 has resulted in recoveries of £70,000 in ineligible payments.
In spite of the significant progress outlined above, there are still issues in payroll control relating mainly to political pressures to expand the civil service workforce and raise wages. In 2019 the payroll was around 48% of domestic revenue, equivalent to 6.9% of GDP, above the IMF target of 6%. This increased in 2020 to 62% of domestic revenue or 8.1% of GDP in part reflecting Covid-19 impacts on GDP and revenue, but also increases in the number of public sector workers and pay rises for certain groups. In 2021 the wage bill is budgeted at 7.4% of GDP or 55% of domestic revenue. In addition to strengthening payroll integrity, proper workforce planning is needed to control the wage bill, ensure human resources are well allocated, and support budget credibility through the avoidance of unplanned recruitments. The Government of Sierra Leone employs over 81,000 workers. Currently over 11,000 workers do not have their positions correctly recorded in the payroll. Under Phase 1 the project begun strengthening data to support workforce planning, including by preparing workforce plans for the police and correctional services and supporting the Teacher Service Commssion. Work around teacher workforce planning will be continued under the FCDO’s education programming.

In addition to work on the payroll, the project has also provided support to strengthen budget preparation, credibility, oversight and reporting. This has led to preparation and online publication of key budget documents including the Enacted Budget and the Citizens’ Budget. Financial reporting has been extended to include subvented agencies and public debt information. Ensuring this data is readily available is an important step in strengthening accountability mechanisms.

The project has also responded well to senior management priorities. For example, on request of the Financial Secretary the project supported the Fiscal Risk Division to prepare a financial analysis report for eight TSA Agencies and sixteen state owned enterprises (SOEs) for the period 2015-2018. This was presented by the Minister in the Presidential Seminar for Commissions/Parastatals/Agencies and SOEs (25th February 2020). The report findings were used as a basis for discussion between the Minister of Finance and these entities on reforms to support solvency. Estimated SOE liabilities at the end of 2018, amounted to approximately Le 1.5 trillion (approx. £115m).

An area the project has been less successful is in strengthening governance and coordination of PFM reforms. A PFM retreat in February 2020 created new momentum around PFM reform monitoring and governance, however this was to some extent lost due to the onset of Covid-19 and related disruptions.

Revenue

Following the 2018 elections there were significant changes to the NRA Senior Management Team (SMT), including a new Commissioner General and Deputy Commissioner General. In addition, the new government highlighted revenue mobilisation as a priority and set ambitious targets to increase the revenue to GDP ratio to 20% by 2023.

Initial support under the programme, which began in late 2018, brought in a former Commissioner General of the Rwandan Revenue Authority to help the new SMT to develop and execute their strategic approach. This included supporting the NRA to engage with major reform initiatives funded by other donors including the introduction of new management systems for customs and domestic taxes (ASYCUDA WORLD and ITAS) and piloting of electronic cash registers. The project adviser sat on the steering committee for these reforms and provided practical advice based on experience of implementing these reforms in other countries. In addition to this, the project has helped to deliver a number of reforms aimed at enhancing compliance and strengthening organsiational functioning. Examples of this include support in cleaning the taxpayer register, review of standard operating procedures for non-tax revenue and customs at border crossings, developing a PAYE data base and reconciliation of tax returns with the taxpayer register and NASSIT Filing of social security contributions, strengthening data analytics capacity in readiness for the new systems, recommending and implementing extended working hours and in-house banking at customs to improve customer service and revenue collection, developing NRA human resourcing policies, and advising on business continuity and recovery plans in response to Covid-19.

Early on the project identified a risk around revenue reforms relating to weaknesses in communications with taxpayers, which could undermine reform implementation and compliance. In response an expert in Taxpayer Services from the Kenyan Revenue Authority was brought on board to support the establishment of a dedicated taxpayer department concentrating on tax education and tax awareness. A Taxpayer Charter was prepared and the project supported a number of dialogues with taxpayers.

In the final quarter work under the project focused on supporting the establishment of a functional Block Management System (BMS). The adviser developed the concept paper, monitoring tool and budgets as well as the Handbook and Training Manual for new staff being taken on to deliver registration and filing services at the block-level. BMS provides a basis for improvements in the way the NRA communicates with its customers in their efforts to increase its tax base and involves the identification and registration of potential taxpayers that have not registered voluntarily. The system will also help achieve a complete and up-to-date taxpayer register that will be used to improve monitoring of tax compliance, filing of tax returns, tax payment and follow-up in order to enhance revenue collection. A proposal for a simplified tax regime was also prepared and submitted to the NRA SMT for consideration. This would ease the burden of compliance for small taxpayers.

Overall, Phase 1 laid some good foundations in the revenue space although overall improvements in revenue-to-GDP were hindered by the economic impacts of Covid-19 and tax deferrals to support the private sector in light of this. Much of the NRAs bandwidth was taken up during Phase 1 with the ITAS, ASYCUDA WORLD and ECR roll-outs. These systems will not deliver increases in revenue unless fully adopted and used effectively. The intention under Phase 2 was to increase support for change management around these new system, as well as building data analytics capacity to strengthen risk profiling using data from the new systems. HMRC have begun supporting this work and the project was designed to flex to complement that support.

Anti-corruption

The ACC is underfunded, understaffed and subject to significant public and senior political pressure, with the Anti-Corruption Commissioner appointed by the President. TA worked with the Commissioner to identify and prioritise capacity needs to support the ACC to improve delivery despite these constraints.

During the programme lifetime there was a strong focus on revising and driving forward the ACC Strategic Plan. By setting a clear vision and objectives, and outlining different departments role within this, the Plan supports coordination across ACC departments, addressing inefficiencies within the institution. The strategic planning exercise helped improve working between the central ACC office based in Freetown and those in the regions, resolving a lack of collaboration which had stalled progress on several investigations. Obstacles to developing cases for prosecution, caused by lack of coordination between the Investigations and Prosecutions departments (such as investigators not providing witness evidence in a timely fashion), were also resolved through the process. Key performance indicators within the Strategic Plan strengthened the Commissioner’s oversight of performance across the ACC’s functions and ability to hold heads to account. Revision of the plans was concluded with a final workshop in November 2020. This approach aimed to embed long-term cultural change within the ACC, for sustainable impact, by establishing a working practice and monitoring mechanism which should be maintained between Commissioners.

Staff retention in the ACC is also challenging, due to a combination of factors including low levels of pay, social pressures of working for the institution (requiring high levels of personal integrity and discretion), and poaching of experienced staff to the private sector. High levels of attrition and loss of institutional knowledge severely undermine the ACC’s ability to exercise its remit. In order to help address this, TA worked with the Commissioner to review recruitment processes and staff retention policies. This included a deeper application and interview process, designed to assess candidates’ long-term motivation for working on the anti-corruption agenda. In March 2021, FCDO Advisors were invited to sit on the interview panel for Prosecutors (a first for the international community in Sierra Leone) and witnessed the approach first-hand, which was judged as well executed. Mechanisms for recognising and rewarding exceptional performance from existing staff were also introduced (such as written commendations), to improve motivation and promote a shared institutional culture and identity. At programme close, it is too early to assess the long-term impact this will have on staff retention, but this cost-free approach is in-line with international best practice and likely to provide a positive (if modest) contribution.

In addition to this strategic level support, TA helped to develop priority functions. The amended Anti-Corruption Act (2019) changed provisions on asset declaration for public officials, increasing the frequency of reporting and putting onus for accurate reporting on individuals. The provision of this data makes an important contribution to identifying the misappropriation of funds, and is useful evidence for any subsequent ACC investigations. However, at the time of the legislative change, the Assets Declarations Unit (ADU) of the ACC was still operating with paper records and lacked capacity to deal with the additional amount of information provided. Addressing this was identified as a strategic priority, and TA flexed existing workplans to respond, introducing data management processes and systems, and training staff on their use. TA also leveraged support from the Financial Intelligence Unit (FIU), given its remit of managing Suspicious Activity Reports from financial institutions, and established closer working relationships between the FIU and ADU. Discrepancies between declared and actual assets have been used as evidence of unexplained wealth in several ACC cases, and evidence provided by the ADU was heavily used by the Commission of Inquiry (CoI) into corruption by the previous APC government. Following government response to the recommendations of the CoI in October 2020, the evidence provided by the ADU has been closely scrutinised as appeals by CoI subjects are heard, and has not been overturned in the Appellant Court to date.

Having contributed to valuable improvements in the ACC’s ability to detect and investigate grand corruption, the programme also focused on addressing capacity issues in the criminal justice sector. A bottleneck for the successful prosecution of political elites is that judges lack the skills and experience to adjudicate complex corruption cases, particularly with the confidence required to apply maximum sentences for offences. The resultant lenient sentencing, and reliance on asset recovery over criminal convictions, fails to disincentivise abuse of public office or alter elite behaviour, and undermines public confidence in the government’s commitment to tackling corruption. To address this, the programme worked with the Chief Justice to establish a specialist Division of the High Court which would only hear corruption cases, and appoint already experienced judges who would receive additional training in sentencing guidelines and international best practices. Establishing the Anti-Corruption Division (ACD) of the High Court was challenging, as the judiciary is already overburdened with a substantial case backlog. TA therefore initially faced significant resistance from the Chief Justice, who was reluctant to stretch resources even thinner against competing priorities (such as sexual offences courts). The programme navigated this by selecting established and well connected TA with pre-existing work in Sierra Leone’s criminal justice sector (on gender based violence). Given their background, TA were able to build instrumental relationships with the Chief Justice overtime and, by drawing on and directing senior FCDO engagement, were able to generate buy-in for the establishment of the ACD. To maintain momentum during Phase 1, ongoing support was provided to establish the functioning of the court, including back-office administrative processes (legal clerks, case file management) and assets (printers, photocopiers). TA also leveraged training offers from external sources, such as the UK Sierra Leone Pro Bono Network (UKSLPBN), to provide judges training on adjudicating corruption cases, sharing best practice from UK High Court judges. Having established this relationship, the UKSLPBN continues to arrange peer-to-peer learning for judges at the ACD as part of their continual professional development, independent of the programme. The most recent training visit of the UKSLPBN took place in February 2021, with further training planned throughout the year.

The design of Phase 2 included the embed of further external TA, to provide mentorship and direct day-to-day support on intelligence, investigations and prosecutions functions within the ACC, and budgetary support to provide consistent training and peer-to-peer mentoring for High Court judges at the ACD. This planned support was welcomed by the AC Commissioner and Chief Justice, and short of the implementation of Phase 2, this is as strong an indication as possible that Phase 1 delivered successfully in generating buy-in for politically sensitive support which would increase institutional impact against grand corruption.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

Value for money of delivery is assessed in previous annual reviews, and an overall assessment of the effectiveness of the programme relative to the business case indicators is given in section B.

The project continued to represent value for money over its final 6 months (Oct 20 – March 21).

Economy: The main cost driver under the project was fees for technical advisers. Out of a total number of 17 consultants on a long and short-term engagements contracted to the project (over its lifespan), OPM provided discounted fee rates on 59% of consultants. Efforts were also made to minimise reimbursable costs with both accommodation and travel coming in under budget.

Efficiency: Investments by FCDO advisers to build relationships with Government institutions and key stakeholders helped to ensure embedded technical advisers were able to integrate quickly. Ensuring partner institutions were involved in identifying their preferred advisory candidates from a rage of CVs also helped to develop ownership of the support. Where possible, Advisers were selected who already had strong working relationships.

Equity: Although there was limited direct link to equity under this output, project advisers were required to be gender-blind in their engagement within MDAs, engaging equally with male and female colleagues.

Lessons learned through this output, and recommendations for future programming

Key lessons learned under this output, and recommendations for future programming are as follows:

Technical advisers need to be based in country and must have the ability to build effective senior level networks as well as technical expertise. Combining Sierra Leonean advisers with excellent local networks, contextual understanding and influence, with international experts can help to achieve this. The ability of technical advisers to build local networks within and across institutions is essential for the success of a programme. TA need to be embedded in institutions full-time for a sustained period in order to develop the networks and trust required to drive meaningful reform. Related to this, it is important to build time into TA workplans for them to respond to management priorities as this helps to develop the relationship over time and opens to door to use non-threatening corporate processes to nudge politically sensitive institutional reforms over time. This relationship building is not easily captured in a logframe and can also be a reason why returns to investments in technical advisers are increasing over time as their networks and access increase.

Trust TA and give them the space to work, exercise judgment and deliver, whilst maintaining strategic level dialogue. A carefully balanced three way dialogue between technical advisers, the FCDO and Government stakeholders is essential to build trust and enable the project to deliver on politically sensitive agendas. The relationship between TA and Government is a priviledged one and advisers ability to deliver was strengthened by a hands off approach by FCDO, which meant work was directed and owned by the GoSL. Balancing this, FCDO met regularly with senior GoSL stakeholders to influence at a strategic level, building on insights gained from programme implementation. The value placed by senior GoSL stakeholders on the programme open the door for dialogue with FCDO. With the unexpected postponement of programming support, the senior level relationships built between FCDO and GoSL during the programme have become of even greater value, and are an unintended benefit of the programme approach.

Ensure that TA build networks beyond their home institutions and with other donor programmes, leveraging synergies and working tangentially where required, to maximise impact. TA leveraged external support and linkages to other parts of GoSL highly effectively. This allowed them to increase their value, and therefore access, to GoSL seniors across the system – demonstrating the importance of TA also being skilled political operators. For example, drawing in Financial Intelligence Unit support to the Asset Declaration Unit in the ACC, or navigating resistance from the Attorney General’s office for the establishment of the ACD, required sensitive political manoeuvring. Using wider networks to draw in support from the UKSLPBN, also allowed the TA to direct resources outside of the programme to deliver objectives, and increase their capital with GoSL seniors. Similarly in the PFM space the ability of TA to work across NASSIT, NCRA, MoF, AGD and others has greatly enhanced impact. On the revenue agenda, engagement between the PFM+ programme and FCDO’s private sector development programme, Invest Salone, helped to strengthen dialogue between the NRA and taxpayers in advance of the 2020 Finance Act.

Output Number and Title	2. Civil society and accountability organisations supported to hold executive to account, including through generating critical data.
Output Score	A
Impact weighting (%)	40		Impact weighting revised since last AR?	N

Output Indicator		Starting Target	Final Logframe Target	Final Result Achieved
2.5 Improvements in domestic civil society capacity (as montored through project M&E tools)		N/A	N/A	N/A – this referred to Phase 2, which was not taken forwards.
2.6 CSO campaigns are able to demonstrate evidence of policy influence or strengthened accountability towards citizens.		N/A	N/A	N/A – this referred to Phase 2, which was not taken forwards.
[note] Given the flexible and adaptive nature of the programme targets at output level were agreed on an annual basis.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

This component was live May 2019 – October 2020. There was therefore only one month of activity following the 2020 Annual Review. During this month the consortium partners (Christian Aid, Restless Development, the Budget Advocacy Network, and the Centre for Accoutnability and Rule of Law) focused on completing the lesson learning report and undertaking further advocacy and influencing based on the various evidence products produced during the project.

The details of this Output’s performance can be found in previous annual reviews, however over its lifetime the Output met expectations. Key achievements include:
- Supporting more transparent and effective revenue mobilisation. By jointly conducting a tax perception survey with the NRA’s Research Department the CSO consortium secured buy-in from the NRA to follow-up on the findings, including through amending their taxpayer education and services offer. In addition, by producing an evidenced based position paper, the consortium managed to effectively engage the Ministry of Finance as it prepared a new tax exemptions and waivers policy, although this is still to be finalised.
- Strengthening oversight of public expenditure. The project produced Audit Scorecards as a basis for advocacy on audit follow-up. As a result, the MoF required all MDAs to submit plans on how they will implement the audit recommendations and audit follow-up has been included as a performance measure in vote controllers’ contracts. Budget credibility reports, designed to increase transparency around actual spending, formed the basis for radio discussions and engagements with parliament. Engagements with parliament around this led to BAN signing a memorandum of understanding (MOU) with the Transparency and Accountability Committee of parliament around continued collaboration. The consortium effectively responded to emerging issues. For example, in spring 2020 BAN engaged the Minister of Information, media and other CSOs to advocate successfully against the proposed Covid-19 Fund constitutional instrument, which exempted the Fund from the PFM Act and the Public Procurement Act. Networks built through the project meant BAN signed an MOU with the Parliamentary Research Department to enhance information sharing and support members of parliament during debates and in scrutinising legislative proposals.
Strengthening oversight and anti-corruption institutions in their abilities to deliver. In partnership with the ACC, the consortium produced a Cost of Corruption and a Corruption Perceptions Report. The ACC supported dissemination of these reports across various media platform. The reports were widely picked up in the media and led to a lively public debate, particularly focused on corruption within parliament (which also generated strong engagement from the Speaker of Parliament). However the absence of a sustained campaign approach around this meant momentum was not maintained and the reports did not generate concrete actions. In addition, the consortium monitored proceedings in the new Anti-Corruption Court to produce recommendations that were discussed with the Chief Justice and ACC Commissioner on how to strengthen court capacity and improve functioning. The strong working relationship with the ACC built over the project lifetime led to the consortium being invited to participate in the ACC-led Covid-19 Transparency Taskforce, which was established to oversee the integrity of the response, for example through joint monitoring visits.
Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

This output delivered good VFM compared to the VFM proposition in the business case. Details are covered in previous annual reviews.

Lessons learned through this output, and recommendations for future programming

Key lessons and recommendations from this output are as follows:
- Early engagement by CSOs with the Government and bringing Government into data collection and analysis can create greater acceptance from the Government of recommendations and increase the likelihood that findings are followed up. However, this needs to be done with caution as there is a risk of cooption or CSOs inadvertently reinforcing elite domination.
- Domestic CSOs in Sierra Leone have a robust understanding of the political economy dynamics and strong networks into Government. This means they have high levels of access to policy makers and are able to get their messages heard. This project aimed to support CSOs to generate the evidence products they would need to inform this engagement and hold Government accountable. There are a number of examples of recommendations from CSOs being adopted by the Government. However, there were some weaknesses in the technical quality of engagement and the issue based approach currently taken by CSOs means there is limited follow-up on actions once initial commitments from Government have been secured. Going forwards, there is a need to strengthen domestic CSOs ability independently to produce (in-house or commissioned) high quality, relevant analysis and to use this as the basis for sustained engagement, through campaign based approaches.

This learning will be integrated into future engagement with civil society across the FCDO SL portfolio and has been shared with the FCDO’s Public Finance and Tax Department.

D: Risk

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.

The risk appetite is summarised in Table 1 and was last reviewed in September 2020. Over the programme lifetime risks there were two instances of risks breaching the risk appetite.

Table 1: Programme Risk Appetite
Risk Category	Risk Appetite
Strategy & Context	Receptive
Policy & Programme Delivery	Receptive
Financial & Fiduciary	Cautious
Safeguarding	Minimal
Reputational	Cautious
Public Service Delivery & Operations	Cautious

Over the course of 2020, operational risks were at the upper end of the risk appetite due to the uncertainties created by the transition from phase 1 to phase 2 (requiring various levels of approval and amendments to agreements). An operational risk that “delays in phase II procurement or delays in the supplier’s ability to mobilise due to Covid-19 travel restrictions, result in a gap in support provided, negatively impacting relationships with GoSL counterparts and creating a loss of momentum in programme delivery” was escalated to the Development Director in May 2020 as it increased to major, breaching the programmes risk appetite. Mitigation approaches included close engagement with PCD on the Phase 2 procurement and dialogue with the Government. The aim was to bring the risk back within appetite by the end of 2020, this was achieved given good progress in the Phase 2 procurement and the extension of the Phase 1 contract up until March 2021 to avoid a major gap in UK support and loss of reform momentum.

In February 2021 fiduciary, delivery and reputational risks breached the programme risk appetite are were escalated to the head of office accordingly. These risks all emerged as a result of the likely early closure of the programme as a result of the ODA budget cuts. They related to potential damage to relationships with the Government and civil society actors as a result of an exit from the PFM, revenue and anti-corruption spaces at short notice, the fact that programme outcomes would not be achieved if the programme closed early and the risk of progress reversals as initiatives established under Phase 1 were supposed to be further embedded and made sustainable under Phase 2. In all cases the risks were exacerbated by not being able to communicate clear and final decisions in a timely manner (given highly complex central processes on overall FCDO ODA prioritisation), which made it more difficult to implement mitigating actions through working with the Government and other donors to restructure internal resources and donor support to fill gaps left by the PFM programme closure. At the time of writing this review, risks have been brought back within appetite through flexing the UK’s broader ODA portfolio to cover any critical gaps and using diplomatic engagement to reassure partner institutions that the UK remains committed to the relationship, albeit without large programmatic support.

All risk mitigations arising from the Due Diligence Assessment of Christian Aid have been implemented. This includes actions from the enhanced due diligence to strengthen safeguarding procedures including training for all staff and mapping of safeguarding services.

Update on Partnership Principles

This programme provided significant amounts of information on anti-corruption and public financial management to inform the Partnership Princilples Assessment, however the PPs were not a formal part of programme monitoring.

E: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency.

The bulk of programme delivery took place under two agreements: a contract with OPM for provision of technical assistance to the Government (total spend: £2,737,000) and an accountable grant agreement with Christian Aid Sierra Leone for CSO consortium engagement on the programme thematic areas (total spend: £991,000). Other significant agreements under the programme include: a contract with BDO for the audit of the Bank of Sierra Leone’s 2018 Financial Accounts; a contract with IGR for the conduct of a public expenditure tracking survey; and a contract with Delivery Associates for the Cabinet Retreat in 2018.

In terms of the contract, OPM delivered well against the KPIs and the terms and conditions laid out in the EACDS Framework agreement. For performance against the Strategic Relationship Management scorecard see previous annual reviews as this has not been refreshed in the last year.

Narrative and Financial Reporting and Financial Management
The quality and timeliness of narrative reporting from both OPM and Christian Aid has been strong during Phase 1. The appointment of a new OPM programme manager in November 2019 dramatically improved partner responsiveness and financial reporting.

Financial management, especially accurate forecasting, was a challenge under the programme, especially over the course of 2020. This was driven by:
- Partner internal procedures and communications. This has particularly been a challenge for the CSO consortium, where Christian Aid have struggled to get timely and accurate information from partners. A more hands on approach from the CASL finance team to working with consortium partners’ finance team has improved the flow of financial information. On the OPM side, there was some confusion around DFID forecasting procedures (a view that overspends were seen more negatively than underspends) that led to consistent under-forecasting until this was clarified by DFID (in June 2020).
- Covid-19 impacts. This resulted in disruption to programme activities and created substantial amounts of uncertainty, including related to mobility restrictions, which created a number of challenges in accurate forecasting March – June. The programme has now adapted to be more resilient to Covid-19 impacts (e.g. improved ability to shift to remote delivery models when required).
- Multiple amendments to agreements and delays in agreeing revised workplans. Due to the need to secure approval for phase 2 and then extend phase 1 support given the Covid-19 delays to Phase 2 procurement, there has been a need to revise agreements and workplans on several occasions. This necessarily creates uncertainty around forecasts and has made it harder for partners to plan effectively.
OPM’s forecasting improved dramatically in the final six months of the project following close working with the FCDO team. In the final 6 months the average variance was 2% compared to 10% in the six months prior.
The only agreement which required the provision of audited financial statements to FCDO SL was the AGA with CASL. Christian Aid have provided an audit report for the whole project and the organisational level audit for FY20. The CASL audit for FY21 will be submitted to FCDO in September 2021, at which point all audit obligations will have been fulfilled.

Assets were well managed by CASL and OPM, with regular updates to asset registers and strong cooperation with DFID teams during asset checks. All assets have now been disposed of in accordance with the Programme Operating Framework rules.

Risk management
Discussions on risk have taken place monthly between partners and DFID, in addition to ad hoc escalation where required. This has given a good shared understanding of the key risks. A recommendation by IAD that we continue to strengthen our risk management procedures, including through better articulating fiduciary and safeguarding risks and strengthening the quality of risk matrices, was due to be taken forwards under Phase 2, however this will not now happen.

The 2020 Internal Audit
The project was selected for a deep dive by IAD in May 2020. A summary of key findings and actions taken in response is included below.

Finding	Actoins Taken
Severe operating risks stemming from the combination of coronavirus impacts, phase two contracting and continuity risks, and the impacts of the UK ODA prioritisation exercise responding to the fall in UK GNI.	We engaged closely with the Procurement and Commercial Department on Phase 2 contracting and had adapted Phase 1 to enable continued delivery in spite of Covid-19 and to minimise gaps with Phase 2. We were on track to launch Phase 2 in April 2021 until ODA budget reductions led to the procurement being paused and then cancelled.
Risks surrounding delivery disruption as the programme moves from Phase 1 to Phase 2.	When Phase 2 was cancelled FCDO staff reached out to all government counterparts to ensure relationships were maintained and the broader portfolio was flexed to address critical gaps in support where possible.
Decision capture under the programme should be strengthened to improve lesson learning and risk management.	A decision log was introduced into the delivery plan.
There is scope to further strengthen programme risk management including through more nuanced assessments of contextual risk by component and better capture of safeguarding risks.	Throughout the final 6 months of the programme the team regularly sought advice from the office risk lead on the framing, rating and escalation of risks as well as holding monthly risk discussions, including with partners.
The logframe could be strengthened to become a more useful tool for performance assessment and management.	A full logframe review was planned during Phase 2 inception.

FCDO’s effectiveness as a partner
The programme was approved for an initial 18-month Phase 1 (September 2018 – March 2020; total budget £3.5m). Following a successful first year of delivery, demonstrated by an A in the 2019 Annual Review, Phase 2 of the programme was approved by Ministers in October 2020. In December 2020 a Business Case Addendum was undertaken ito extend the end date and value of the programme to allow time to procure a Phase 2 supplier and deliver a smooth transition between the two phases. Phase 1 was extended until September 2020 to avoid a loss in momentum prior to the start of Phase 2. Due to delays in the Phase 2 procurement, Phase 1 was further extended to March 2021. FCDO were on track to launch Phase 2 in April 2021 as planned, however this was delayed and eventually cancelled due to the ODA budget reductions.

The dynamics around the move from Phase 1 to Phase 2 created a number of risks within the programme and reduced FCDO’s effectiveness as a partner. This is discussed in more detail in the value for money section below.

Value for money
The 18-month Phase I, anticipated to promote VFM by enabling reform appetite and approaches to be tested, has in reality undermined VFM.

Even prior to Phase 2 being cancelled, there were significant challenges arising from the two-phase design. Technical Advisers under Phase 1 accumulated context specific knowledge and built working relationships, which added value to their work. The move to Phase II, which entailed a new procurement process, risked losing the knowledge and relationships. This is significant as most reforms take longer than 18 months to deliver and embed. The design of Phase II was adapted to take this into account, with the contract initially anticipated to run up until March 2024 with the option to extend for an additional 24 months.

The disruption caused by Covid-19, which impacted supplier markets, DFID budgets and needs on the ground, increased the complexity of managing the transition from Phase 1 to Phase 2. Delays to and the eventual cancellation of the Phase 2 contracting process, required a number of formal amendments to agreements to avoid a major gap between Phase 1 and Phase 2 and ultimately led to a very sudden end to the programme given a decision not to progress to Phase 2, which was only formally approved in April 2021 after the end of the Phase 1 contract.

As noted above, issues around the transition from Phase 1 to Phase 2 were highlighted as a severe risk in the DFID Internal Audit Department review of the programme, which took place in May 2020, and subsequent events bore out this assessment.

The absence of a robust value for money framework and unified results framework for the programme (at a more detailed level than the DFID logframe) has made it challenging to effectively assess the VFM of the programme. This is something that was due to be addressed during Phase 2.

Programme-level approach to monitoring and evaluation

Phase 1 of the programme was monitored predominantly through regular partner meetings and reporting against workplan progress. To verify the information in partner reports and monitor the level of Government commitment to reform, FCDO advisers were in close regular contact with technical advisers and Government counterparts. All reports from the CSO consortium were closely reviewed by FCDO advisers to assess quality and FCDO advisers attended events organised by the CSO consortium. Insights from this monitoring were fed into monthly risk discussions and used to discuss and agree changes to TA and CSO workplans as required. A lesson learning report was carried out by the CSO consortium to capture Phase 1 learning. The lack of unified approach to Phase 1 M&E reflects the interim nature of the Phase 1 programming. Phase 2 was designed to pull together all workstrands under one contract with a fully integrated monitoring and learning approach to inform adaptive and politically informed programming.

Date of last narrative financial report	CSO Consortium: February 2020 / OPM: April 2021	Date of last audited annual statement	CASL Audit for period ending March 2020. / Project specific CASL audit received 13th March 2021