Annual Review - Summary Sheet

Title: Infrastructure and Cities for Economic Development (ICED)
Programme Value: £33,500,000 (of which £8M ICF)		Review Date: 28 April 2017
Programme Code: 204250	Start Date: / March 2015 / (with varying dates for implementing partners)	End Date: March 2020 / (implementation period 5 years, / with shorter periods for individual components and partners)

Summary of Programme Performance
Year	2015/16	2016/17	2017/18	2018/19	2019/20
Programme Score	A	A
Risk Rating	Moderate	Moderate

ICED, is a complex multi-component, multi-partner programme. The programme was set up to respond to the key binding constraints to growth identified in the Inclusive Growth Diagnostics (IGDs) through large programming in the energy, urban and infrastructure sectors. This programme is consistent with DFID’s new Economic Development Strategy (EDS), supporting DFID scale up programming and investment in infrastructure and cities.

There has been good progress, and the programme is on track. The programme comprises the ICED Facility, led by the PWC Alliance, and a number of partners working on aspects of cities and infrastructure in relation to economic development. The ICED Facility is the largest programme component. It has made strong links across DFID and responded quickly to requests. The partners funded under this programme have in the majority achieved their targets. Importantly this year we have seen emerging linkages across the components which are contributing to the overall outcome and impact of the programme.

Summary of progress and lessons learnt to date
- The ICED Facility has worked with 17 DFID Country Offices (COs) and central teams, to provide technical advice to the design of new, and improvements to existing, programmes that support improving the enabling environment for infrastructure, energy and urban development sectors. They have also ensured the mainstreaming of gender and climate issues into these new and existing programmes.
- The fragile and conflict-affected states (FCAS) Facility has been successful in delivering specific FCAS country work and a value f=for money (VfM) study for DFID Somalia on its infrastructure programming. It has proven to be a useful starting point for considering the monitoring and evaluation of infrastructure programming in FCAS countries. The latter will now be built on to adapt into tools and guidance for other COs.
- The Construction Sector Transparency Initiative (CoST) independent Strategic Review was approved by the CoST Board. This Strategic Review confirmed the need for CoST and set out critical ways to scale up activity. These are set out under the review of Output 3. On the basis of this Strategic Review, and CoST’s new Business Plan, DFID make a final decision on funding for the next three years.
- The World Bank (WB) project – Enhancing Economic Performance of African Cities – has seen significant take up of the analysis undertaken by the first two cities under the project- Kampala and Addis Ababa – leading to development of new urban policies. The next phase will see work undertaken in at least two more cities in Africa.
- Cities Alliance (CA) has provided strong stewardship of the Joint Work Programme (JWP) on Equitable Economic Growth in Cities, which is focused on supporting cities to invest in public goods and services. The first set of cities in Uganda and Bangladesh have been identified and partners – United Nations Capital Development Fund (UNCDF) and Building Resources Across Communities (BRAC) University – will be delivering specific research and targeted technical assistance to those cities.
- There are clear links between the sub-components of the programme. For example, the ICED Facility has worked with both the WB and CA on a number of initiatives.

Summary of recommendations from last Annual Review (these have all been completed):
- DFID to have agreed a final version of the first amendment to the ICED overall logframe.
- Separate outputs for each partner in the ICED logframe to ensure progress and attribution of partners work under ICED can be more effectively tracked, including revisions to weightings.
- A standalone output on the Strategic Opportunities Fund (SOF) in the logframe.

Summary of recommendations for this year:
There are a number of relatively minor changes to the logframe indicators across the outputs which are listed under each output in this report. The recommendations set out below are a summary of the substantive recommendations built on lessons learnt during the year.

ICED Facility
- DFID ICED team to share information and learning more frequently across the Growth and Resilience Department (GRD) and DFID on knowledge generated to ensure it is used by advisers in their work.
- Devote more resource to sharing knowledge products externally so that DFID positions on infrastructure and cities can inform a wider audience.
- ICED Facility strengthens its knowledge and learning strategy with a focus on systemising learning and take-up of evidence by DFID and external stakeholders throughout the year, in order to articulate how knowledge and learning is leading to improved outcomes. DFID to agree action plan with ICED Facility to deliver this.
- ICED Facility to focus on sharing knowledge products externally to ensure knowledge and evidence generated through programme design is contributing to DFID programming and reaching to a wider audience
Support on Influencing G20
- Remove funding allocated to working with the G20 to influence its focus on infrastructure in developing countries and raise the voice of Low Income Countries (LICs) within this forum, as no opportunities to support this work has arisen. DFID to consider reallocating funding to existing ICED components.
- Consider a logframe indicator to track success of the GIH secondment.
CoST
- Build more CoST partnerships in DFID partner countries.
- CoST to keep DFID appraised of progress on the Infrastructure Transparency Initiative (ITI) and the suggested second country for testing.
- DFID and CoST to agree more realistic milestone targets for the year ahead - whilst most of the indicators were met it is clear that some milestones were not achievable.
World Bank
- The new DFID Cities and Infrastructure for Growth (CIG) Regional Adviser in Uganda to draw out programme synergies with the WB Uganda team.
- DFID and WB to meet to consider possible future collaboration after the final two cities are supported.

Cities Alliance
DFID to ensure the work of this programme in Uganda is linked in with the CIG programme, given the secondary cities focus of both programmes.
SOF
DFID to actively consider new opportunities for support in the non-energy infrastructure sector.
Value for Money and Risk
- Focus on measuring effectiveness of ICED Facility – scale up the of the Facility’s focus on driving a change in programme design and knowledge across urban and infrastructure programming. This should include a more challenging customer feedback score between 8.5-9, and more in-depth questions to COs on take up of learning from the Facility’s scoping and design work packages. This could also include assessing feedback from COs earlier in the lifetime of the work packages.
- GRD Commercial Adviser and Senior Responsible Officer (SRO) to continue working with the ICED Facility on quarterly VfM action plans.
- DFID and the ICED Facility should add to their regular performance reviews a monthly check on the pipeline of projects and the overall shape of the budget. This will enable DFID to put particular work packages on hold to ensure the core Facility work is prioritised
- Update risk matrix across all partners to reflect the need to link with the new CIG programme and manage risks of duplication of effort appropriately.
A. Introduction and Context (1 page)

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-204250 / Specific link to BC http://iati.dfid.gov.uk/iati_documents/4961485.odt
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-204250/documents/ / Specific link to logframe

Outline of the programme
DFID is providing £33.5 million to the Infrastructure and Cities for Economic Development (ICED) programme over five years (60 months), from April 2015 to March 2020.

This project supports DFID and our development partners through:
- Improving the enabling environment for sustainable, inclusive growth-enhancing infrastructure service delivery in DFID focus countries; and,
- Harnessing the benefits of cities for sustainable economic growth and poverty reduction in DFID focus countries.
Some of this work is delivered by assisting DFID COs to scale up bilateral programming; other work is focused on international influencing and delivery of global public goods.

The expected impact is: An improved enabling environment for infrastructure service delivery and better managed and governed cities as drivers of inclusive economic growth in DFID focus countries

The expected outcome is: DFID scales up, enhances coordination and improves the quality of its country/regional/central-level support for an improved enabling environment for infrastructure and planning for cities (including in our most fragile and conflict-affected states).

This will be achieved through the following outputs and partners:

At the country level:
Outputs 1, 2 & 4 - The ICED Facility includes PWC, Adam Smith International, Engineers Against Poverty, the International Institute for Environment & Development, Social Development Direct, MDY Legal and ARUP. To deliver the EDS, DFID needs more high quality infrastructure and cities programmes at country level. This Facility provides support to DFID COs and central/regional departments to develop new, and improve existing, infrastructure enabling environment and city economic development programming.

At the global level:
- Output 3 - Scale up and enhance the impact of CoST activities to reduce corruption and increase value for money in public sector funded construction projects;
- Output 5 - Support a WB’s Enhancing Economic Performance of African Cities programme - to support economic growth in 4 cities in Africa.
- Output 6 - Shape the strategic priorities of the CA and develop and operationalise its Economic Growth programming.

In addition, the programme contains a Strategic Opportunities Fund (SOF) – Output 7 - to enable additional high priority activities that support this programme’s objectives. The use of the SOF is agreed with the ICED SRO and in charge. and approved by the GRD Head of Department.
The above components are designed to be complementary.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
Each partner contributing to the objectives of ICED have their own outcome level indicators and are all making progress towards these. The ICED Facility has been able to deliver specific policy briefings or knowledge products that have contributed to international debates on women’s economic empowerment and the UN Habitat III process. The Facility has been successful in delivering specific FCAS country work and a VfM study for DFID Somalia on its infrastructure programming. The latter will now be built on to adapt into tools and guidance for other COs. There is one outcome level indicator for the % of business cases (BC) the Facility designs which implement programmes with gender, climate and political economy mainstreamed in them. However it is too early to tell whether this will follow through into implementation as these programmes are yet to be procured and begin work on the ground. The indicator timing will therefore be revised to later years of the programme.

A key measure of whether the Facility is moving towards generating better urban and infrastructure programming is how it is contributing to improving programme design, and knowledge and learning across DFID. This requires a strengthened feedback mechanism from country offices and DFID teams to ascertain how DFID is using learning and evidence generated by the Facility and feeding this into policy and programming design. There needs to also be a focus on how the Facility is influencing external stakeholders through its technical assistance and knowledge products. This will be an area of specific focus for DFID and the Facility for the coming year.

CA, WB and CoST are all moving towards delivery of their expected outcome indicators. In particular in reference to the outcome indicator assigned to the CA, the City Level Partnerships have been formed and endorsements secured from the cities it is working with on the initial institutional enabling environment reports it has completed. These reports will form the basis of in-depth fact-based, policy support to improve equitable access to select public goods in the cityover the next year. CoST are making progress to ensuring that the Infrastructure Transparency Index (ITI) is applied across a range of countries, including in DFID countries, facilitating improved governance of infrastructure. This will be assessed in the fourth year of the programme once the ITI has been tested and approved this year (it is currently being tested in Honduras).

These individual components collectively move the ICED programme forward in achieving an improved enabling environment for economic growth in infrastructure and urban development. They tackle city level constraints to urban development, address transparency in the infrastructure sector and provide dedicated technical expertise to DFID programme design in these sectors. The strong complementarity across the programme components reflects both working between partners on a bilateral basis –the CA working with the ICED Facility on the review of the Future Cities Africa programme – and joint working across the CA, WB and ICED Facility to deliver DFID priorities on urban economic development at high level forums such as Habitat III.

This cross-working has been very effective, leveraging each partner’s expertise and networks in country to improve delivery of outputs and quality of advice provided to both DFID and partner governments. For example in the scoping of potential interventions in urban development in Uganda, the ICED Facility drew on CA expertise and existing work in country, including having a CA expert take part in the scoping work, to present options for future interventions to DFID.

Overall output score and description:
Output 1:	A (impact weighting 30%)
Output 2:	A + (impact weighting 20%)
Output 3:	A (impact weighting 20%)
Output 4:	A+ (impact weighting 15%)
Output 5:	A (impact weighting 5%)
Output 6:	A (impact weighting 5%)
Output 7:	A (impact weighting 5%)

The overall programme score is A.

Across all partners funded through ICED there has been consistent performance contributing to an overall score of an A. As noted above good links have been made across the programme components. Partners understand each other’s programmes and how they each contribute to the overall ICED objectives. The ICED programme needs to continue to capitalise on the opportunities that have arisen to work collaboratively, in order to help amplify DFID’s focus on supporting enabling environment interventions in cities and infrastructure.

Key actions
Please see recommendations on summary sheet

Has the logframe been updated since the last review?
Yes. The logframe was fully updated after the last annual review to include additional outputs to reflect all the partners in the programme.

## C: DETAILED OUTPUT SCORING

Output Title	ICED Facility - High quality TA provided by ICED to DFID teams (country office, regional and central) to facilitate the delivery of new and improved existing programmes, initiatives and partnerships
Output number per LF		1	Output Score	A
Risk:		Moderate	Impact weighting (%):	30%
Risk revised since last AR?		No	Impact weighting revised since last AR?	Yes

Indicator(s)	Milestones	Progress
1.1a Number of active TA substantive interventions (SI) supporting DFID teams to design new programmes, initiatives, partnerships. / A. Number of Pre-scoping (PS) reports drafted / B. Number of Scoping (S) reports drafted C. Number of Business Cases (BC) drafted	Year 2: PS:14 / S: 8 / BC: 5 / Total: 27	Exceeded - / PS: 10 / S: 15 / BC: 5 / Total: 30 / ICED has met its milestones for delivering BC and programme scoping support. ICED has supported the SPEED, Asia Regional DevCap Facility, Cities & Infrastructure for Growth, Rural Electrification in Sierra Leone (off-grid) and Increasing Access to Electricity in Sierra Leone (on-grid) business cases. The average quality score for this work is 7.5 out of 10.
1.1b Number of active TA substantive interventions (SI) supporting DFID teams to redesign/extend existing programmes, initiatives, partnerships. / A. Number of Pre-scoping (PS) reports drafted / B. Number of Scoping (S) reports drafted C. Number of Business Cases (BC) drafted	Year 2: / PS: 2 / S: 1 / Total: 3	Met - / PS: 2 / S: 1 / Total: 3
1.2 The level of satisfaction of ICED clients (country, regional and central team) with service/inputs provided by ICED.	Year 2: / Average of 7/10 or more	Exceeded – Average score of 7.8 / Overall the ICED Facility has received positive feedback on its support to COs and central teams.
1.3 % of active TA substantive interventions to DFID teams (country, regional, central) with mainstreaming of A) Gender & Social Inclusion (GESI), B) Climate Change & Environment (CC&E) and C) Political Economy Analysis (PEA) integrated.	Year 2: / GESI: 100% CC&E: 50% PEA: 50%	Exceeded - / GESI: 100% / CC&E: 100% / PEA: 100% / Mainstreaming gender, climate and political economy analysis across the programmes ICED scoped and or/designed has been a key part of the ICED approach. The Facility has performed extremely well in committing to, and working with DFID advisers to do this.

Key Points

The Facility has reached out effectively to the country network and to regional and central teams to build relationships and present a consistent and strong offer of technical support on cities and infrastructure programming. ICED provided support to 17 COs in one year, across Africa and Asia, with further demand from other COs processed and prioritised during the same period, developing a pipeline of CO work.

The Facility has been able to adapt and flex support to CO and central teams’ demand when needed. This has included mobilising at relatively short notice to provide in country support to teams and responding to central team’s demands for support on knowledge and evidence reviews.

This first full year has confirmed significant demand at central, regional and CO levels as indicated above. However this demand has not been solely in designing new programmes as was originally anticipated. With higher levels of new spend on economic development being delivered through central teams, demand from COs has also included support to existing programmes. This has included supporting COs to improve mainstreaming gender, inclusion and climate across their existing cities or infrastructure programmes.

The ICED Facility has a specific FCAS ‘window’ to focus on delivery in FCAS countries. Demand has been strong. ICED has supported DFID Somalia, Sierra Leone, OPTs, Lebanon and Jordan in identifying opportunities to promote stability and economic development, create jobs and support refugee populations.

Through the client surveys and DFID’s advisers direct feedback to the DFID team overseeing ICED, we have received valuable information on strengths and areas for improvement of the Facility model. Areas for improvement have included shortening the ToRs, being clearer on the ICED offer to COs, and drawing in analytical expertise earlier on. This was highlighted, for example, by the DFID Zimbabwe office who gave strong positive feedback on the Facility’s work to review urbanisation trends in Zimbabwe but highlighted that having stronger statistical and analytical expertise brought in from the outset could have improved the initial drafts of the report.

Overall the ICED Facility has received positive feedback on the work packages its delivered and its approach to working with DFID advisers. In particular we have had good feedback on ICED’s ability to deliver under tight timelines, quality of insights and flexible approach to redrafting reports as programme concepts have evolved. As part of the overall effectiveness of the Facility it is recommended that there is a review of the existing client satisfaction questionnaire and scoring to raise the ambition on improving policy and programme design. This is expanded on, with an accompanying recommendation, under the effectiveness element of the value for money section on page 24 of this review.

A strength of the ICED Facility has been its focus on mainstreaming gender and social inclusion into all programming it supports. This approach to mainstreaming has been delivered in different ways – through direct inputs to BC design, running sessions at cadre conferences, inputs to the High Level Panel on Economic Empowerment and a cross cutting project with DFID-Uganda to consider social safeguards in their infrastructure and economic development programming.

Summary of responses to issues raised in previous annual reviews
None

Recommendations
DFID ICED team to share information and learning more frequently across the Growth and Resilience Department (GRD) and DFID on knowledge generated to ensure it is used by advisers in their work.

Logframe amendments:
- Amend Indicator 1.1 (a) to Number of active TA substantive interventions (SI) supporting DFID teams to scope new or redesign existing, programmes, initiatives, partnerships. This is to recognise that the distinction between pre-scoping and scoping is difficult to define and demand over the year has fallen mainly into the scoping or design categories.
- Delete Indicator 1.1 (b) ICED support to DFID teams in the redesign/extend of existing programmes as this is now incorporated as part of the revised 1.1 (a) indicator above.
- Replace Indicator 1.1 (b) above with Number of Business Cases (BC) supported by ICED This is to highlight BC as a standalone output given the importance of delivering BCs by the Facility as this represents the delivery of new programmes.

Output Title	ICED Facility - High quality TA provided by ICED to DFID teams (country/regional/central) to facilitate increased access to ICF funding
Output number per LF		2	Output Score	A+
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting revised since last AR?	Yes

Indicator(s)	Milestones	Progress
2.1 % of ICED-supported business cases facilitated to access ICF funding, actually accessing ICF funding	Year 2: 50%	Exceeded - 100% / ICED has ensured that all business cases prepared by ICED have been subject to thorough CC&E appraisal promotion of ICF-relevant indicators and themes where appropriate particularly where these provide programming opportunities and enhance the socio-economic narrative.
2.2 % of ICED-supported programmes that are accessing ICF funding, reporting on ICF KPIs.	Year 2: 100%	Met – 100% / All three of the business cases for which logframes have been developed have incorporated one or more climate relevant indicators. In most cases, these have also been fully aligned with the ICF.
2.3 % of total spend directly from ICF in relation to the total £ value of DFID Business Cases, approved partnerships or investments in infrastructure/urban development	Year 2: 12.5%	Exceeded – 47% / In terms of ICF funding eligibility, of the three full business cases prepared by ICED that have reached funding approval, all have been recognised as fully or partially ICF-relevant (i.e. they have some element of budget classified as ICF-eligible). Of the total budget associated with these business cases, 47% of total funds have been classified as ICF.

Key Points
To some extent we would expect most cities and infrastructure programming to have an ICF spend within them, given the importance of supporting low carbon and resilient approaches to infrastructure.
However as part of the ICED programme DFID commissioned the Facility to focus on ensuring ICF funding is integrated where appropriate into all the BCs they design with COs. Over the year this has improved as the Facility has developed its ICED CC&E mainstreaming strategy.

The Facility has ensured that all business cases have been subject to thorough CC&E appraisal, including a ‘do no harm’ risk assessment, promotion of ICF-relevant indicators and themes where appropriate particularly where these provide programming opportunities and enhance the socio-economic narrative. Four of the five ICED-prepared business cases have a full or partial focus on scaling investment in renewables or energy efficiency (Sierra Leone off-grid; SPEED) or facilitating improved access to clean energy (Sierra Leone on-grid, CIG).

Summary of responses to issues raised in previous annual reviews
None
Recommendations
Amend Indicator 2.1 to ‘2.1 of ICED supported business cases that are ICF compliant’, as ICF funding is now mainstreamed across DFID funding this re-wording better indicates how BCs need to demonstrate their programme’s applicability for drawing down ICF funds.

Output Title	CoST: CoST creates a more transparent enabling environment for publicly procured infrastructure by establishing effective government systems to publish project information through the implementation of a scaled-up business plan
Output number per LF		3	Output Score	A
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
3.1 A high quality, Strategic Review of CoST's approach and Business Model has been carried out by independent consultant(s) and approved by the CoST Board and an Advisory Panel that includes representation from funders/governments, industry, civil society and developing countries that are implementing CoST.	Year 2: / Strategic review completed & approved by 30 June 2016	Met – whilst the review was completed slightly later than the summer it met DFID’s expectations of a thorough and independent review. This review had fed into the new Business Plan for CoST which has been approved by the CoST Board.
3.2 CoST has developed a revised Business Plan reflecting a more ambitious and clearer vision of what success will look like, supported by a robust theory of change showing how	Year 2: New Business Plan completed & approved by 18 months after MoU signing	Met – A business plan has been submitted to DFID for approval for the next phase of funding. The decision on final approval is pending DFID internal discussions.
3.3 Strong indications that CoST will secure significant funding from other sources in addition to DFID to implement the plan, i.e. statements of commitment from donors or other funders.	Year 2: Letters / e-mails setting out funding intent on the part of at least one other funder by June 2016; with further indications of additional funding sources by March 2017	Not met – it was agreed with CoST that this was an unrealistic milestone given they needed to complete a Strategic Review to reset their strategy and activities. It was therefore unlikely that funders would commit to supporting CoST when such a fundamental review of the programme was being undertaken. For the year ahead we expect CoST to be able to secure commitments, in particular with DFID support in place for the next 3 years.
3.4 Number of Formal Disclosure Requirements (FDRs) imposing a formal/legal obligation on PEs to disclose information.	Year 2: 6	Not met – 5. CoST expects to reach five FDR’s by the end of April 2017 with Malawi and Costa Rica anticipated to pass legislation shortly. This output is one of the more challenging to achieve as it requires Government and often the legislator to approve the Formal Disclosure Requirement.
3.5 Number of projects that are (a) subject to disclosure in the Infrastructure Data Standard format and (b) subject to the CoST assurance process. (see footnote)	Year 2: / (a) 4,400 (b) 240	Met - (a) 6,987 – exceeded (b) 221 – partially met. / CoST’s assurance process is designed to improve the usefulness of disclosed data of public interest to stakeholders. The types of information disclosed have included cost and time overruns in construction projects.
3.6 Number of government staff that has received training on the Infrastructure Data Standard.	Year 2: / 725	Exceeded – 1018 / Training government staff on the Infrastructure Data Standard helps to build the capacity of government to disclose more data on their investment in public infrastructure.
3.7 Launch of the Infrastructure Transparency Index (ITI)	Year 2: / ITI tested in two countries	Partially met – 1 country achieved ITI testing. The ITI is running behind schedule, with testing only carried out in Honduras. The ITI consists of a series of indices designed to measure and report changes in the level of transparency in public infrastructure investment over time in a national setting. It is important to test the index and get this right before rolling out to another country. / Once the index is finalised, CoST are confident they will meet subsequent year targets

Key Points
CoST directly addresses the challenges of mismanagement, corruption and inefficiency in public infrastructure by working with government, industry and civil society to promote greater transparency and accountability. DFID supports CoST as addressing these challenges is critical to improving the enabling environment for infrastructure and urban development that ICED is trying to address. Greater transparency and accountability helps to inform and empower citizens, enabling them to hold decision-makers to account. Informed citizens and responsive public institutions are mutually reinforcing and help drive reforms that reduce mismanagement, inefficiency, corruption and the risks posed to the public from poor quality infrastructure. CoST’s approach has the potential to contribute to governance and public management reforms, reduce waste, create a more competitive environment for business and deliver better value of money for investors and tax-payers.

As part of DFID’s funding conditions CoST needed to undertake an independent review of their activities and, based on this, agree a business plan with DFID. This review outlined five key recommendations that CoST should take forward:
•	More clearly articulate our vision and mission
•	Consider if the ‘CoST’ name is still appropriate
•	Revise the delivery model to increase CoST's global footprint and impact
•	Encourage uptake through better online tools, standards and other resources
•	Build on success of strategic partnerships

The recommendations have been taken forward into a new Business Plan covering the period from mid-2017 to mid-2020. The Business Plan proposes that the Strategic Review recommendations are taken forward as follows:
•	Strengthen the CoST brand with a new vision, mission and theory of change that clearly articulates outcomes and impacts
•	Enhance the delivery model by i) scaling up the amount of data that is disclosed, validated and interpreted by our existing programmes and ii) establish new programmes through a more flexible approach to membership of CoST.
•	Develop tools and standards and promote voluntary uptake beyond CoST ‘members’
•	Persuade international and regional organisations to promote and adopt CoST tools and standards by strengthening existing and building new strategic partnerships

DFID is largely satisfied with the approach set out in the business plan to deliver the above. However a decision on DFID’s funding to CoST for the next three years is yet to be taken. The Business Plan will be reviewed and a final decision taken in the next month. If DFID agrees to the next three years of funding, it will be important that CoST and its activities are better communicated within DFID – in particular with COs.

CoST is currently operating in the following DFID countries: Afghanistan, Ethiopia, Malawi, Tanzania and Uganda. The CoST team have had various levels of engagement with the DFID COs. CoST is also exploring interest in the following DFID countries: Nepal, Caribbean, India and Pakistan. A key recommendation for next year, if DFID continues funding, will be for CoST to actively pursue more engagement with DFID priority countries. DFID Cities Adviser and Infrastructure Head of Profession (HoP) will help facilitate engagement with DFID COs where appropriate.

The ICED Facility has worked closely with CoST over the year and is currently collaborating on a workshop event for DFID on transparency in infrastructure delivery. There are clear benefits to CoST working under the same umbrella programme as the ICED Facility. This includes joining up with ICED scoping missions when in the same country to meet with the COs and also attending DFID professional development conferences (PDC) to promote the work of CoST. CoST ran a session at the Infrastructure, Health and Climate & Environment PDC which enables them to reach out to advisers who have an interest in seeing their countries sign up to CoST.

Summary of responses to issues raised in previous annual reviews
In the last review it was recommended that indicator 3.5 needed to be refined to fully reflect the level of projects being supported. This was done as part of the logframe revision.

Recommendations
- CoST to focus on targeting DFID partner countries to build CoST partnerships with in the next year.
- CoST to keep DFID appraised of progress on the ITI and the suggested second country for testing, to ensure that this component gets back on track.
- DFID and CoST to agree more realistic milestone targets for the year ahead - whilst most of the indicators were met it is clear that some milestones were not achievable.

Output Title	ICED Facility: Knowledge management, research and policy influencing mechanisms in place to improve the basis for international dialogue and action on the infrastructure enabling environment and cities that drive sustainable, inclusive growth
Output number per LF	4		Output Score		A+
Risk:	Moderate		Impact weighting (%):		15%
Risk revised since last AR?	No		Impact weighting revised since last AR?		Yes

Indicator(s)		Milestone(s)		Progress
4.1 Number of quality assured knowledge products delivered.		Year 2: / 5		Exceeded – 10 / The breadth of ICED knowledge and learning interventions include high quality roundtables and workshops supporting DFID to explore policy priorities with stakeholders. These roundtables have covered energy, smart cities, urban finance and engagement at Habitat III.
4.2 Number of knowledge products (KP) delivered related to the promotion of low carbon development and/or climate resilience in the context of cities and infrastructure.		Year 2: / 1		Met – 1
4.3 Number of policy briefings (PB) and positioning papers (PP) approved (by type, separating out those related to climate relevant mainstreaming for infrastructure provision and urban development - tracked off-logframe).		Year 2: / PB: 10 PP: 2		Exceeded – / PB: 10 / PP: 3 / Whilst this has been a milestone that has been exceeded it has been difficult to distinguish between policy papers and briefings. Instead it wouldn’t be useful to set out an agreed number of briefing papers that the Facility can deliver for DFID in response to demand.
4.4 Approval of design methodologies related to Gender & Social Inclusion (GESI), Climate Change & Environment (CC&E) and Political Economy Analysis (PEA).		Year 2: / All methodologies tested via ICED support to DFID teams and refined		Met - CC&E strategy finalised following extensive consultation with DFID. PEA framework developed and approved
4.5 Channel created for LICs to feed into the G20 dialogue for infrastructure (Currently in development and it may be redefined)		Year 2: / Key issues for LICs in G20 agenda identified and disseminated and a policy briefing provided for DFID's input into UK G20 delegation		Met - Comments to DFID on background papers for G20 with focus on LIC perspectives. However there have been limited opportunities for the Facility to work with DFID on responding to G20 opportunities. This is more within DFID’s core remit to deliver on and it has been agreed that the ICED Facility has less of a role in delivering this element of the ICED programme.

Key Points
The ICED programme has a strong knowledge and learning component which is critical to the overall success of the Facility. The past year has been focused on refining how ICED can share learning in a useful way that enables DFID’ advisers to take up the learning from both ICED design in county and wider policy and international influencing work. This has led to a new knowledge and learning strategy that the Facility will implement in the coming year.

Knowledge products have resulted from: a) thematic roundtables designed to catalyse industry/donor dialogue on a key theme such as the construction sector and climate smart infrastructure; b) international influencing or policy engagement opportunities where knowledge products have informed or framed dialogue, such as the products developed around DFID’s Habitat III engagement; c) insightful evidence generated through ICED work packages, with a wide range of products derived from the intensive demand for support in the energy sector; and d) new thinking around programming modalities for DFID such as the evidence reviews and roundtables on Smart Cities and Urban Community Finance.

There have been two particular highlights under this component:

- ICED delivery on behalf of UK of a Networking Event at Habitat III on growth in secondary cities. This was a well received event, with a focus on ensuring there were a high calibre panel discussion and an interactive session with the Major of Jinja, Uganda. This was an excellent vehicle for UK to influence the debates on urban economic development in secondary cities.
- Engagement with the UN High Level Panel (HLP) on Women’s Economic Empowerment which resulted in a published paper - Infrastructure: A Game-Changer for Women’s Economic Empowerment – which fed into the HLP Working Group.

Whilst the Facility has completed a number of knowledge products, there is a need to ensure they are being used, and that a target audience is identified. Furthermore, for Year 3 the Facility should devote more resources to sharing these externally.

As the Facility enters its second year there needs to be stronger focus on systematising the learning coming out of scoping and detailed design activities. For genuine change in DFID programme design to happen the Facility needs to be able to demonstrate how learning and evidence it is generating is being taken up and used, both within DFID and externally. The Facility has developed a new knowledge and learning strategy with a specific focus on how learning happens. This strategy needs to now be actioned with a move away from a focus on the production of high quality knowledge products to the use of those products. The next year will need to develop a more systematic approach to document how knowledge and learning, generated through ICED, is leading towards better outcomes in programme and policy design.

A specific component on G20 under the overarching ICED programme was focused to supporting low income countries (LICs) voice in discussions on infrastructure with the G20. However over the last year it has become clear that this isn’t a viable area for DFID to engage. No opportunities have arisen that could utilise the funding available under ICED to support LICs in the G20 forum.

Part of this G20 component also provides support to the DFID secondee to the Global Infrastructure Hub (GIH). The GIH was established by the G20 (in 2014) to help increase the flow and quality of infrastructure investment opportunities in both G20 and non-G20 countries. The UK is one of the larger funders of the GIH.

DFID’s secondee to the GIH focuses on supporting development of tools and guidance on PPPs and also inputs into new GIH knowledge learning platform. The latter in particular has scope to link with the ICED Facility’s knowledge objectives and conversations have already begun between the GIH and the Facility on this. The DFID ICED team keep in regular contact with the secondee and DFID’s Head of Profession for Infrastructure provides a link between the ICED programme and the GIH. It would be useful for the year ahead to consider a relevant logframe indicator to track the success of the secondment to GIH and links to the ICED programme.

It is recommended that, whilst support to the GIH secondment will remain under this component, the remaining funding for this component to support LICs will be removed from the programme.

Summary of responses to issues raised in previous annual reviews
None

Recommendations
- ICED Facility strengthens its knowledge and learning strategy with a focus on systemising learning and take up of evidence by DFID and external stakeholders throughout the year, in order to articulate how knowledge and learning is leading to improved outcomes. DFID to agree action plan with ICED Facility to deliver this.
- ICED Facility to focus on sharing knowledge products externally to ensure knowledge and evidence generated through programme design is contributing to DFID programming and reaching to a wider audience.
- Remove funding allocated to working with the G20 to influence its focus on infrastructure in developing countries and raise the voice of Low Income Countries (LICs) within this forum, as no opportunities to support this work has arisen. DFID to consider reallocating funding to existing ICED components.
- Consider a logframe indicator to track success of the GIH secondment.

Logframe amendments:
- Remove indicator 4.2 as a standalone indictor on low carbon/resilience knowledge product as a separate indicator is not warranted. Instead fold indicator 4.2 into 4.1.
- Replace 4.2 above with ‘Number of active learning sessions lead by ICED (i.e. Events, Roundtables etc.)’. Year 2 has demonstrated that ICED are able to jointly host and lead external sessions with DFID and external stakeholders to facilitate global dialogues and inform DFID programme design.
- Delete 4.3 due to difficulty in getting a clear definition of policy papers and policy briefings.
- Delete 4.4 – this was a process indicator to approve design of mainstreaming methodologies, for gender, climate and political economy. This was achieved and the indicator is no longer needed.
- Remove the indicator 4.5 on ICED Facility support on G20 (see above)
- Switch round output 3 and 4 to enable a more consistent logframe, with ICED Facility outputs fitting together.

Output Title	World Bank: Improved analytics and diagnostics, planning of economic reforms and institutional and skills development in cities.
Output number per LF		5	Output Score	A
Risk:		Moderate	Impact weighting (%):	5%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
5.1 Number of knowledge products or tools produced and approved/implemented to support improved information and knowledge in high priority areas for City Governments to enhance economic development	Year 2: / 4	Met – a number of research and analysis reports were undertaken to underpin advice to city governments. These include: for Addis Ababa, qualitative analysis of firm level constraints and value chain analysis; and for Kampala, qualitative analysis of firm level constraints, quantitative business survey analysis of informal firms and informal sector survey analysis. In both cases the research and analysis delivered have been done in consultation with city authorities and to meet specific demands. In particular the firm level analysis of informal firms and the informal sector has been critical to understanding a much under-reported sector within which the majority of the poor work.
5.2 Number of client cities planning specific policy reforms or investment projects as a result of the assistance.	Year 2: / 2	Met – Although the project has only been working for a year it has already mobilised cities to begin making policy decisions based on the analysis. In Kampala the government has committed to creating a team to support the development of a city strategy, involving all surrounding stakeholders. In Addis Ababa, the city government has been responsive to land reform and improving businesses support through an improved government one-stop shop.
5.3 A) Number of workshops, trainings and knowledge exchange fora organized with client City Government staff; B) % of participants ‘rating as " very satisfied" or "satisfied"	Year 2: / A) 4 B) >80%	Met – Kampala – 90% satisfaction ; Addis – 89%
5.4 Proportion of client City Government stakeholders rating the support provided by the project as very good or excellent on a four point scale	Year 2: 0 (N/A yet)	Too early to assess – this will be assessed in Year 3.

Key Points
This project aims to support African cities enhance their economic growth and job creation performance. It supports city governments in Africa in two areas - 1) economic analyses that fill knowledge gaps that policymaker’s face, 2) institutional support and capacity development to strengthen their ability to plan and implement relevant reforms. The first two cities the project is working with are Kampala and Addis Ababa. This is funded solely by DFID as a pilot approach to supporting targeted cities to improve their competiveness.

The project has successfully implemented a range of workshops, trainings and knowledge exchanges with city government staff across the two cities. Specifically, executive training on City Competitiveness was provided to staff in Addis Ababa and Kampala city governments. This has also been complemented with a number of high level meetings and briefings on emerging findings from the research studies undertaken.

Upcoming priorities for the project will be to assist city governments implement findings and recommendations from Kampala and Addis Ababa reports into city government strategies. This will be critical for the success of this programme, moving from analysis to implementation.

The Kampala City Council Authority (KCCA) has already begun mobilising resources to support some of the recommendations coming out of the WB’s analysis.

It will be important for the Kampala project to link in with the Cities and Infrastructure for Growth (CIG) programme in country. Conversations have already begun on the synergies between the WB project and the potential interventions CIG will undertake. DFID’s CIG Regional Adviser in Kampala is co-chair with the WB of the urban donor group in country. This will help to strengthen the links and cross-working.

A second key area for the next year will be the development of new projects in new cities. There is strong progress on identifying the next set of cities with work underway with Doula and Yaoundé. Currently a workshop with local government stakeholders in Lagos-Ibadan is scheduled for May.

This programme has linked with Research and Evidence Division’s (RED) Growth Research Team’s support to the WB and Oxford University spatial economic development research that culminated in the well received WB African Cities report (2017). RED and GRD have liaised closely on the two projects to maximised synergies and in particular provide a joint view on the operation of the WB Urban Development Trust Fund that this project is funded through.

The WB project has also linked with the Cities Alliance programme and the ICED Facility. In particular all three were able to contribute their perspectives on urban economic development to the DFID panel discussion at Habitat III that the ICED Facility led on.

Summary of responses to issues raised in previous annual reviews
None
Recommendations
- WB Uganda team and DFID’s CIG Regional Adviser to ensure strong links between this project and CIG.
- DFID and WB to meet to consider possible future collaboration after the final two cities are supported.

Logframe amendments:
Increase satisfaction scoring for indicator 5.3 from 80% to 90% to keep the milestone realistic but challenging.

Output Title	Cities Alliance: Knowledge management, research and policy influencing mechanisms to improve the basis for international dialogue and action on the infrastructure enabling environment and cities
Output number per LF		6	Output Score	A
Risk:		Moderate	Impact weighting (%):	5%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
6.1 Number of global advocacy campaign events on Equitable Economic Growth in cities has raised awareness on the relationship between public goods and equitable economic growth	Year 2: / 2	Met - CA have really demonstrated their convening power and strong partners enabling a range of advocacy and outreach interventions. In particular there were two major global dialogues in 2016: the annual meeting 2016 in London (UK) and a side event at the Habitat III conference in Quito (Ecuador). Both dialogues have been evaluated and documented in two knowledge products. Based on the recognition of the Joint Work Programme (JWP) as a global contributor to a dialogue on economic growth in cities, CA was also asked to contribute to the OECD Inclusive Growth in Cities Campaign, and produced / three additional deliverables in the reporting period.
6.2 Number of peer reviewed global knowledge products are being produced per year addressing the relationship between urbanisation, inequality and growth in cities	Year 2: / 1	Met - Based on a theme identified through extensive consultation with JWP members, / partners a knowledge product was delivered exploring the link between gendered / access to public goods and services and equitable economic growth in cities. The discussion paper was peer reviewed and finalised. / Additional knowledge products have been produced including a Toolkit on how to foster Equitable Economic Growth in Cities.
6.3 Number of completed, peer reviewed Institutional Enabling Environment Reports (IEER) for JWP Countries-Cities (Bangladesh, Nigeria, Uganda, Ghana and Kenya)	Year 2: / 4	Met – 4 reports completed for Mbale (Uganda), Gulu (Uganda), Sylhet (Bangladesh) and Narayanganj (Bangladesh). The reports provide an analysis of the institutional environment of cities. They reveal constraints in all cities that impact on the capacity to deliver public goods and services, resulting in limited services to formal and informal businesses. The constraints include functional fragmentation, financial constraints and limited capacity to manage population growth, land and public space. The city-level engagement provided the foundation for the Institutional Enabling Environment Reports (IEERs) and the continued city campaigns. These were peer reviewed by international experts, endorsed by, and received strong support from, the local governments and their respective multi-stakeholder fora as well as from development partners in both Uganda and Bangladesh.
6.4 Number of peer reviewed city level assessment reports and policy briefs on how to foster equitable economic growth in JWP campaign cities delivered	Year 2: / 0	To be assessed in Year 3
6.5 Cities Alliance membership increases by 2 members per year (annual)	Year 2: / 4	Met - Commonwealth Local Government Forum (CLGF) and ICLEI - Local / Governments for Sustainability became members of the CA.

The key objective of the Joint Work Programme (JWP) on Equitable Economic Growth is to enable local governments in partner countries to deliver public goods and services, which are accessible and responsive to the needs of all people and businesses in cities. By achieving this objective during the programme period, the Cities Alliance Partnership is striving towards being able to provide concrete advice, references, tools and partnerships to mayors, especially of secondary cities, to steer equitable economic growth in their municipalities.

CA has led this programme in its first year, conducting in depth missions to Uganda and Bangladesh to identify secondary cities and partner institutions. In Uganda UNCDF will be delivering some elements of this work and in Bangladesh BRAC University have been contracted. As part of this process the CA applies rigorous standards to their downstream partners. The findings from the institutional enabling environment reports for each selected city provide valuable insights on the policy space that local givernments operate. It is expected that wider dissemination, in particular with those who will deliver the CIG programme in Uganda would be beneficial.

More broadly this component represents DFID’s wider engagement with CA. DFID joined the Management Board of CA in April 2016 with senior level DFID representation. This has enabled DFID to input into the strategic direction of CA and contribute to its longer term ambitions. DFID has engaged with the CA’s JWP on Habitat III which has helped DFID influence the outcome document for Habitat II and work more collaboratively across donors, civil society and development institutions.

Summary of responses to issues raised in previous annual reviews
None

Recommendations
DFID to ensure the work of this programme in Uganda is linked in with the CIG programme, given the secondary cities focus of both programmes.

Logframe amendments:
- Indicator 6.2: Amendment of milestones in outer years - the JWP plan to produce two additional knowledge products, to be delivered in year 4 and year 5 respectively, increasing the cumulated total deliverables to 7.
- Indicator 6.3: Moving the delivery of four IEERs from year 3 to year 4, reducing the cumulated target for year 3 to 6 deliverables. The two IEERs to be produced for cities in Nigeria are moved to year 4 to reflect portfolio and political economy review findings pointing to year 4 as the most appropriate and feasible time for engagement.
- Indicator 6.4: correct the year 3 target to 4 deliverables.
- Indicator 6.4: Moving the delivery of two Local Assessment Reports (LARs) and two policy briefs from year 4 to year 5, reducing the cumulated target for year 4 to 12, as a result of moving the engagement in Nigeria.

Output Title	Strategic Opportunities Fund (SOF) : Support the utilization of the SOF
Output number per LF		7	Output Score	A
Risk:		Moderate	Impact weighting (%):	5%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
7.1 £ value and number of sub-sector projects approved by SOF	Year 2: / 2 proposed opportunities - one in the energy sector - supported; total value around £1.1m	Met: The next phase of the WRI World Resources Report on Cities is being supported and a piece of research on energy systems through Chatham House.
7.2 £ value and number of projects approved by SOF that have achieved their intended outcome as defined by DFID (on a case by case basis)	Year 2: 2 opportunities completed and associated outcomes achieved; total value £700k	Met: The first phase of WRI WRR on cities was successfully completed. The first stage of the UN Habitat State of African Cities report was also completed.

Key points:
There are three projects currently being funded through the SOF:
- A contribution to the UN Habitat and African Development Bank sponsored State of African Cities Report 2017 with a focus on supporting research on FDI flows to African cities
- A contribution to the next World Resources Initiative’s World Resources Report on Cities – Towards a more Equal City
- Chatham House research on Extractives in Development: Implications for Power and Infrastructure Planning in a carbon-constrained world

The SOF was set up to support emerging opportunities across, urban, energy and infrastructure issues. To date this has mainly meant supporting research and strategic reports that directly contribute to the global level aims of the ICED programme.

In particular the WRI report, ‘Towards a More Equal City’, has been successfully promoted, picking up media coverage in the US and UK. The focus of the report on how to provide basic services within cities as a means to promoting wider productivity has close links with the Cities Alliance JWP. These two have linked up through the launch of the report and continued dialogue between CA and WRI.

DFID needs to continue actively seeking opportunities that clearly contribute to ICED’s objectives. The projects funded so far under the SOF have been either urban or energy focused. DFID should consider if there are broader infrastructure focused opportunities under ICED objectives that warrant funding.

Recommendations
DFID to actively consider new opportunities - in particular on non-energy infrastructure.
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

VfM performance compared to the original VfM proposition in the business case
The programme operates based on the VFM proposition in the BC, and in particular for the ICED Facility a process is in place to report against the BC proposition on a regular basis. This is set out below.

Key cost drivers and performance
The ICED Facility provides specialised technical assistance to DFID, primarily DFID COs. The Facility works by developing specific work packages (WP) with COs to deliver a piece of scoping or design work. These are reviewed first by the CO and then the budget and number of days are signed off by the DFID SRO. This provides two levels of check, both on the content of the work to be undertaken and the costings.

Consulting time accounts for 96% of the Facility’s total spend – with the remaining 4 % being allocated to travel and expenses. The two key cost drivers are consultant daily rates (fees) and number of consulting days (input unit). These two categories have been managed through benchmarking in particular across the individual WPs and combining small WPs, where possible, to promote economies of scope. For the benchmarking The benchmarking is at three levels : overall facility VfM; work- package costs and efficiency; and individual fee rates.

For the CA, the major cost driver of the JWP during this reporting period has been the programme implementation and oversight. These costs are subject to UNOPS staffing or procurement processes – including competitive / market tested pay and grading and competitive procurement processes.

For CoST a key cost driver is in country set up of the CoST partner. Partners are identified through strong due diligence to identify relevant partners who have expertise and local networks to save time and costs on setting up wholly new organisations in country.

Partner actions to maximise VfM
The below captures key actions across partners delivering the ICED programme to ensure VfM:

Economy
- At the operational level, the Facility provides DFID with full transparency over inputs at the WP level through detailed ToRs describing proposed resources against scope, and monthly budget management and reporting. This process allows for regular scrutiny and visibility of inputs.
- The Facility has demonstrated economies of scope through combining work across multiple WPs into one in-country engagement. Furthermore ICED has been employing lower-cost local consultants where possible. For instance, in the Tanzania water security scoping study work package, ICED employed a local consultant as the water resource management and governance expert. This saves costs in terms of the fee rates for a local expert compared to an international expert and in travel expenses.
- The Facility has achieved economies of scale, particularly through larger WPs. ICED has improved the ratio of technical consultancy to overall total consultancy days on larger packages.
- The Facility utilise its in country networks and partners to maximise efficiency gains on staff and travel costs.
- CoST achieves economy by using open competitive bidding on high value service contracts such as for the Strategic Review and publishing operational procedures to provide standardised guidelines for managing travel expenses and procurement for the international and national programmes across the CoST network.
- To reduce costs the JWP ensures the reduction of unit costs through setting up a Consultants Retainer Pool through the UNOPs system and applying competitive procurement processes for global as well as local products.
- The CA has sought to contract local entities in the focus countries Uganda and Bangladesh to reduce costs.
- The WB employs local expertise and their in-country teams where appropriate. They also draw on high quality PhD level researchers to contribute to delivery of analysis reports. This is done to save on the high cost of international consultants delivering the work but without comprising the quality.

Efficiency
- The ICED Facility was set up in its current form because of the expected efficiency it would bring from being a centralised programme operating at the CO level, with the ability to provide flexible support to meet a variety of needs in a timely manner. The Facility has achieved this by establishing systems and processes that have resulted in effective team mobilisation, financial effectiveness, and timely and quality delivery of outputs.
- The Facility tracks the financial effectiveness of WPs, quantifying the value of cumulative savings / overruns and their causes. In total, there was a £38,000 underspend across all packages (or 2% of the total approved WP budget).
- CoST utilises digital solutions to maximise the efficient running of the programme. Email, instant messaging and web-based meetings are regularly used to communicate and convene meetings with national programmes, strategic partners and the CoST Board. Where physical meetings or workshops are required, we have designed them to serve several purposes.
- CA have sought efficiency gains by using existing contracted staff with relevant expertise in order to save both recruitment and on-boarding time.
- CA have also leveraged the in country networks and presence of partners in the JWP group to deliver particular aspects of the JWP objectives. This has ensured efficient use of the expertise and resource available to the JWP.

Effectiveness
The core remit of the Facility is to support the design of new and better programmes for DFID in the areas of infrastructure and cities. The effectiveness of ICED will ultimately be judged by the future successes of these initiatives in contributing to inclusive growth in DFID’s priority countries. The progress of the ICED Facility towards achieving this outcome and impact level is evidenced mainly through the results achieved against the logframe, the effectiveness of the programmes that have received ICED support, and the leverage achieved with other ICED Programme partners.

In terms of the Facility’s effectiveness to deliver good programme design, the contract includes a performance-related element where 10% of fees are at risk based on ‘customer satisfaction’ scores provided by users, and the meeting of KPIs. These are both quarterly and annual KPIs. This payment by results method is working effectively with all outputs scoring above 7.

At present it is too early to ascertain more broadly the overarching effectiveness of the new programming designed by ICED and its impact on a step change in DFID programming in the urban and infrastructure sectors, given the time needed for programmes to start implementing on the ground. However, we would expect to be able to comment on this in the coming year and for the ICED Facility to be able to provide an overview of DFID’s portfolio across new programming in these sectors.

The feedback from country offices on the Facility’s technical assistance to programme design is crucial in being able to comment on the above. Therefore, whilst the current KPI scoring is satisfactory, this needs to become more ambitious. This will calibrate the Facility to focus on ensuring there is improved knowledge and programme design within the infrastructure and urban portfolio. It is recommended that the KPIs are reviewed with a particular focus on pushing the customer feedback to an 8.5-9 score. To accompany this there should be a reassessment of the questionnaires used to gather the feedback from country offices. This would be in order to include specific questions on how learning from scoping and design work is being taken up, and how advisers will design policy and programming differently in the future. This will also enable DFID to more robustly assess how innovative ideas on mainstreaming issues such as climate and inclusion are being taken up by advisers. This is ambitious, but warranted given that the overarching outcome of the ICED programme to see a scale up in DFID’s urban and infrastructure portfolio focused on economic growth.

CoST drives effectiveness forward using a result based approach. This is principally through the funding of the CoST national programmes where applicants must meet certain criteria to be eligible for funding, meeting a set of agreed targets to be able to receive the next tranche of the approved grant. CoST is also considering institutionalising transparency within government systems. This means that if a national programme achieves their objective on transparency and this has been integrated into government systems, there is the option of folding the programme. This can deliver clear effectiveness where the ultimate aim of CoST is delivered through assimilating objectives of transparency into existing government systems no longer requiring CoST support.

The effectiveness of the CA and WB projects will largely be assessed towards the end of the project lifetime when a proper assessment of each city worked with under both programmes can be taken. This is in order to track take up of the analysis and policy recommendations provided. For the WB we can already see that some policy interventions have been implemented but whether these will lead to concrete legislative and policy changes that improve city development will take longer to determine.

A strong demonstration of the effectiveness of the programme overall is the complementarity that has been achieved between the different partners under ICED. The ability to leverage on the ground interventions and networks across the ICED partners shows both, the overall coherence of the programme, and the effectiveness of individual projects working together to contribute to the objectives of ICED.

Assessment of whether the programme continues to represent value for money
This original business case proposition on VfM continues to be valid. The ICED Facility, being the largest component of the programme, represents a key area of focus for DFID in driving VfM. The ICED Facility track performance against the VfM indicators set out in the BC on a quarterly basis. The ICED Facility have also established a VfM tracker with associated indicators) to track the delivery of both qualitative and quantitative At present the ICED Facility approach to tracking and measuring VfM is good but there are areas for improvement – in particular tracking WP sizes and monitoring management and quality assurance days assigned to WPs.

A key point to consider for the overall efficiency of the Facility is the number of WPs and the rate at which the Facility is spending the budget. This number of WPs and spend each year is correlated to the level of demand from COs and DFID teams. However DFID needs to work with the ICED Facility to consider prioritisation of WPs, consolidating WPs where possible.

DFID will need to continue to conduct quarterly VfM assessments. The GRD commercial adviser and the SRO will work with ICED Facility on this.

Quality of financial management
The demand led nature of the ICED Facility means that accurate forecasting is more difficult than a less responsive programme. An increase in demand towards the end of the financial year and a requirement for more in-depth support on scoping studies for CIG has led the Facility to exceed its initial year forecast. Overall the Facility has given the DFID team timely information about changes to its spending forecasts.

Financial management under the CA JWP has been handled efficiently by the CA, and is scrutinised as part of the CA’s wider financial management processes. There is a contribution payment made each year. This was reassessed as the CA did not require funding at the pre-agreed date (January 2017). Therefore from April 2017 the payment scheduled will move to April for the coming year and subsequent years.

CoST provides quarterly updates on their funding disbursements as part of the request for the next tranche of funding. These are reviewed by DFID and any discrepancies or queries referred back to the CoST secretariat. Any queries have been expedited quickly by CoST. CoST has also provided future forecasts for the year ahead to support DFID with accurate forecasting.

The process for supporting the GIH secondment was more complicated than had been anticipated given the need to liaise with an organisation (the GIH) who have not had a funding agreement with DFID before. This created considerable more work for the ICED programme manager than anticipated. An important lesson learnt here is to fully set out the processes for funding secondments, taking time to discuss this with the other party and ensuring sufficient programme management time to facilitate this.

The Urban Multi-Donor Trust Fund (MDTF) through which we provide funding to the WB project has satisfactory financial management processes in place.

Recommendations
- Focus on measuring effectiveness of ICED Facility – scale up the of the Facility’s focus on driving a change in programme design and knowledge across urban and infrastructure programming. This should include a more challenging customer feedback score between 8.5-9, and more in-depth questions to COs on take up of learning from the Facility’s scoping and design work packages. This could also include assessing feedback from COs earlier in the lifetime of the work packages.
- GRD Commercial Adviser and Senior Responsible Officer (SRO) to continue working with the ICED Facility on quarterly VfM action plans.
- DFID and the ICED Facility should add to their regular performance reviews, a monthly check on the pipeline of projects and the overall shape of the budget. This will enable DFID to put work packages on hold to ensure the core Facility work is prioritised
- GRD Commercial Adviser and Senior Responsible Officer (SRO) to continue working with the ICED Facility on quarterly VfM action plans.

E: RISK (½ page)

Overall risk rating: Moderate
The overall implementation risk of ICED continues to be moderate.

Overview of programme risk given the progress so far:

Across other partners risks are managed through individual reporting mechanisms and regular updates with lead advisers. Risks for each partner are set out below:

The ICED Facility monitors risks through the quarterly reports to DFID. For the Facility a key risk is a lack of demand from COs and DFID teams for the scoping, design or redesign of new programmes. To mitigate this the Facility has worked to make connections with most DFID COs and to mobilise teams to respond to requests quickly. In this was they are able to demonstrate quick responses to DFID COs and build trust in their ability to deliver. DFID also has a key role to play in connecting DFID COs to the Facility and identifying opportunities for support from COs that the Facility can support. Another key risk on DFID’s side that advisers should approve WPs from the Facility sufficiently quickly to enable them to respond to demand. This has been managed through sharing approvals for WPs between relevant DFID advisers. A way to mitigate this risk has been to develop a ToRs tracker that the Facility and DFID review bi-weekly to ensure both parties are on top of approvals and WPs.

In particular for the Facility the issue of conflict of interest is managed on a case by case basis especially given ICED’ role in the design and pre-scoping studies for large new programmes such as CIG. The ICED Facility has managed this process effectively setting out clear conflict of interest procedures which have been robustly applied. The Facility is acutely aware of the potential conflicts, and where they anticipate these they are quick to alert DFID and work with DFID to resolve these.

For the CA JWP the Management Board recommended that the JWP establish a Risk Management Strategy which is reported against to CA Director on a bimonthly basis. A key risk for the JWP is the lack of local government engagement in the objectives of the JWP leading to no take up of the analysis and policy recommendations made. This is being actively mitigated by deploying suppliers in country with longstanding relationships with city governments and through CA leveraging their reputation to gain traction with city governments.

For CoST key risks have been set out in the new Business Plan and for DFID there are three key risks:
- A lack of sign up and buy-in by country governments. This is being mitigated by the CoST secretariat focusing efforts on countries that have shown emerging interest.
- Inability to attract additional funding. This will be a large focus for Year 3 for CoST. DFID is also supporting efforts with bilateral conversations with current funders to continue support.
- Misuse of funds by CoST national programmes (the host organisations that host CoST national programmes in country) - Grant agreements between the CoST Secretariat, Host Organisation and Management Steering Group (MSG) establish how grant funding should be used. It also includes their Anti-Corruption and Bribery Policy. CoST also requires MSGs to provide a financial report on a quarterly basis as part of the grant agreement and undertake due diligence checks on each host organisation

For the WB the main risk is that the analysis and studies undertaken for each city government is not translated into policy changes and ignored by the local governments. The critical way this is mitigated is by ensuring strong buy-in to the project with each city. In particular working with the city government to identify the right studies to undertake which fit with the government’s existing areas of interest and current policy priorities. Furthermore the WB in scoping out future cities to work with under the project has invested time in pre-meetings and scoping missions to each city to ensure groundwork is done to gain commitment from the outset.

There is an overarching risk across the ICED programme that DFID’s relative lack of experience of engaging with city-level governments in partner countries prevents scaling up of urban development interventions and the take up of evidence from these partners. This is being actively mitigated through working with a strong network of partners who hold valuable urban development expertise and can advise DFID on how best to engage with city governments.

A new risk for the coming year will be how effectively the overall ICED programme engages with the new CIG programme. Given the cross-over in sectoral and to some extent geographic focus of the two programmes there is a risk of duplication of effort. This is both in terms of the on the ground assistance delivered and in knowledge generation. The ICED and CIG SROs will work together to ensure that relevant links are made – there are a number of recommendations in this AR that respond to this.

Outstanding actions from risk assessment
Update risk matrix across all partners to reflect the need to link with the new CIG programme and manage risks of duplication of effort appropriately.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
The programme is currently on track for all deliverables against the agreed work plan and logframe.

Performance of partnership (s)
The partnerships will all suppliers under the programme have been consolidated over this last year and
are working well.

The partnerships for CoST, WB and CA have also been cultivated over the last year, with regular check
ins and feedback with DFID. The SRO for ICED takes an overall oversight of all partners and components,
but in particular for CoST DFID’s Head of Profession for Infrastructure has led the relationship. The HoP
and SRO have regular catch ups on the programme.

Asset monitoring and control
The programme does not acquire any assets. Any IT software developed is open access, open source, and will constitute a global public good.

G: CONDITIONALITY
Update on partnership principles (if relevant) - Not applicable.
H: MONITORING & EVALUATION

Evidence and evaluation
There is provision for DFID to commission an independent review of the ICED Facility at the end of year 2 before the mid-point of the programme to enable feedback on the Facility. This will allow for an assessment of where the Facility is working well, allow for corrective action, and re-design of priorities within the Facility where required.

Given the nature of the ICED Facility interventions, providing support to COs and support to strategic priorities and international influencing, the approach to continual evaluation and monitoring of expected results places a stronger emphasis on learning. This learning needs to be able to inform program direction and feedback into programme design. This approach requires the ICED team to regularly engage in reflections on what they have learned so far and review the delivery of individual WPs. At present this is being done partly through quarterly learning lessons which is opened up to relevant DFID advisers who have used the Facility.

The CA seeks continual feedback and ongoing evaluation of its interventions under the JWP. Feedback from beneficiaries and target audiences are collected, analysed and considered in the design of follow-up activities. For the upcoming year the CA plan to conduct a survey with the members of the JWP as well as with the chosen cities in Uganda and Bangladesh to assess progress and evaluate the process undertaken so far. This will be able to inform the approach taken in the next set of cities chosen by the JWP.

CoST undertook at strategic evaluative review of its activities and operations as part of DFID’s conditions for future funding – this will be published by CoST shortly. Therefore another evaluation is not planned. However DFID and CoST will work together to agree additional review points to assess progress on the recommendations of the strategic review in line with the proposed actions set out in their new Business Plan.

The WB’s project is funded through the Urban MDTF. There was a recent evaluation of the MDTF that delivered positive feedback on its overall operation and the synergies that have been created between the different urban development projects funded under it. The specific project under ICED is evaluated through customer feedback and satisfaction. There needs to be further evaluation of the assumptions underpinning the project – in particular that city governments take up recommendations from the analysis produced – as the WB begins work with the next set of city governments. This will be discussed with the WB as the next year of work begins.

Monitoring progress throughout the review period
Meetings have taken place with all DFID partners under ICED on a regular basis to clarify questions and agree on forward work plans.

In the case of the ICED Facility, the team and DFID have met on a weekly basis for the first year of the programme to discuss progress in CO engagement, and to clarify any outstanding specific issues.

The ICED Facility and the DFID team have agreed a new work package tracker (as mentioned in the VfM section) which can provide a good overview of all past and current WPs and links to whether a relevant knowledge product will be produced from the WP. Going forward this will be a useful way to monitor the overall number of WPs being approved and to monitor the spread of these across the cities, energy and infrastructure sectors.

The work funded with CA is monitored through close involvement in the programme from DFID’s Cities Adviser. DFID chairs this work programme and has regular discussions with Cities Alliance. DFID sits on the Management Board of CA which enables strategic oversight of their activities. Ongoing monitoring for the CA is undertaken through a bi-monthly highlight report to the Cities Alliance Director and a bi-monthly update to the Cities Alliance Management board/DFID.

CoST progress is monitored through the DFID attendance at Board meetings in an observer capacity, regular meetings between CoST and the DFID Head of Profession for Infrastructure and quarterly progress reporting. These reports are reviewed and approved by the HoP and ICED SRO.
DFID has regular review discussions with the WB to monitor progress. Of particular importance for the year ahead is the need to monitor how the WB project works with the Kampala City Authority and how DFID’s new CIG programme will work with the city.