Project Completion Review - Top Sheet

This Top Sheet captures the headlines on the programmes performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	28/06/16

Title: Strengthening Knowledge and Tools for Climate Change Adaptation
Programme Code: 202948	Start Date April 2012	End Date: March 2016
If programme was closed >1 month early please describe in a few words why.

Summary of Programme Performance

Year	12/13	13/14	14/15
Programme Score	A	B	A
Risk Rating	Low	Low	Low

Financial Position

Original Programme Value	£1,188,934 / Quest number of business case 3245846
Extensions/ amendments	Extension of project to March 2016 and £500,000 extra funds on 14.08.14 / Quest doc 5488083
Log-frame revisions (with dates)	March 2014 / July 2014 / March 2015
Total programme spend	£1,668,686.34

Follow up actions required following closure
Development tracker shows a small error. This is due to errors in Alito. These errors are being addressed.

A. Introduction and Context (1 page)

DevTracker Link Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-202948/documents/
DevTracker Link Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-202948/documents/

Outline of programme and what it has achieved
The programme aims to improve knowledge on best practice in climate change adaptation. The programme supports adaptation knowledge and tools to maximise the effectiveness of the UK’s International Climate Finance (ICF) on climate change adaptation/climate resilience by building evidence for what works and providing programming guidance. The programme also supports work to improve coordination and coherence on adaptation across the global resilience/adaptation community. There have been 30 sub projects under this programme. Examples include the development of guidelines and tools on adaptation programming, covering monitoring and evaluation, the economics of climate programmes and improving value for money (VFM). Country studies have directly fed into business case development, helped kick-start international risk financing work (for example, through the Africa Risk Capacity programme), helped to build international consensus and south-south learning on adaptation planning, and informed programming (OECD).

The direct results expected from this knowledge programme are:

- International investments in climate change adaptation (including from the UK) are of a higher quality and carry lower levels of risk as a result of strengthened tools, knowledge about adaptation, and international coordination;
- Better knowledge around what constitutes best practice in adaptation;
- Better international coherence and coordination around climate change adaptation; Project management ‘tools of the trade’ are fine-tuned to support the effective delivery of ICF spending on adaptation; and
- Delivery on DFID’s Policy Division’s Core Offer to make relevant Adaptation knowledge easily available.
A review of this programme was a central part of the preparation for the Monitoring Evaluation and Learning work[1]. This review concluded that while a systematic review of the impact of the knowledge funds would be complex and costly, feedback and annual reviews cites evidence of the products of the Adaptation Knowledge and Tools fund being particularly influential.
[1] Review of Three DFID Internal Knowledge Funds, ICF – MEL Revised Draft 21 April 2016. Carl Jackson (Westhill Knowledge) for IMC Worldwide
The way the funds are set up – being able to respond quickly to gaps in knowledge, to prepare a DFID programme or to be able to bring evidence and influence to bear at the right place and at the right time has been critical to success. The fund for example was able to respond to the needs of the Energy Africa campaign quickly and help produce a plan of action. Work in Tanzania directly influenced and improved the evolution of business cases.

The strong and consistent feedback is that this project was effective in building knowledge, providing advice to support country office actions or providing notice/ information about DFID’s work on adaptation and placing evidence before the international community.
 However, the fragmented nature of the funds – whereby individual actions funded by the project are managed by advisers from across DFID has been a drawback. Systematic monitoring of the results of the fund has been difficult, with the knowledge products spread out across the organisation and not all having copies filed in the project folder. The programme also had a number of SROs through its lifetime and had to compete for attention during the stretching time for the Climate and Environment Department in the run up to the 2015 UNFCCC meeting in Paris.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Overall Outcome Assessment

A

The review done in preparation for CED’s current monitoring and evaluation work and previous annual reviews provides overwhelmingly positive feedback from both inside and outside DFID on the projects funded by this programme and cites evidence of their use. The information has been specifically cited as directing at least 7 DFID activities (target 10). It is more than reasonable to assume there have been more. Further examples include that the OECD workshops sponsored by the programme has already led to sharing of information and collaboration between countries and the OECD has also improved its learning and dissemination techniques with this programme’s support. The World Bank’s “Shockwaves” report has been downloaded over 49,000 times since it was published early in 2016. This places it in the top few percent of World Bank reports.[2] The programme’s products provided knowledge and tools in a consolidated form as part of Policy Divisions’ core offer.
[2] https://www.washingtonpost.com/news/wonk/wp/2014/05/08/the-solutions-to-all-our-problems-may-be-buried-in-pdfs-that-nobody-reads/ Only 13 percent of World Bank reports had seen more than 250 downloads in their lifetimes.

It is worth mentioning that to provide robust evidence of the outcome - i.e. That international investments in climate change action are of a higher quality would require extensive research, and even then results would probably still be contentious. Some of the indicators of this are cited in the logframe – their use in business cases and international citation of the products are easier to assess, but to do this with any rigour would need significant research. This would have been a disproportionate effort given the overall value of the programme.

A full list of projects funded under this programme is at Annex A.

Output Score and Description

Output 1 Score A Improved knowledge around what constitutes best practice in adaptation including on social protection, local accountability, on private sector engagement.

The output produced 9 products (target 10). Not achieving the target of 10 was an artefact of insufficient funds to cover demand rather than a lack of quality proposals. The previous annual reviews have assessed the products as highly relevant to knowledge on adaptation with evidence that they have been influential externally on the development of the Green Climate Fund, and on UNFCCC thinking. Over the last year products have been influential especially on thinking about hydropower, ideas on managing the impacts of climate change on poverty and providing a systematic review of the link between energy access and adaptation.

One project that did not perform to expectations was the one on gender, which required a reduction in the ambition of the project and a change of consultants. Payment was withheld until the original products had been improved. The final products were improved by being more targeted to the audience. They supported the production of at least one business case as well as a range of case studies and an overview paper.

Output 2 Score A Better international coherence and coordination of climate change adaptation including adaptation monitoring and evaluation, frameworks, and communities of practice around adaptation.

This year further development of the value for money work has led to direct influence over country programmes. A contribution to OECD work has helped south-south learning on adaptation as well as helped OECD to hone their climate change communication strategy. More generally, the project has had significant impact internationally - in adaptation principles for the UNFCCC, on monitoring and evaluation for the GCF and the climate investment funds (CIFs) to name a few. DFID’s commitment to evidence and learning has also meant it has been sought out to work with the Global Resilience partnership and its associated community of practice on measuring resilience. Learning materials on resilience and adaptation have been produced that have been shared with the UN, civil society, the World Bank and the CGIAR system as well as across DFID, and been well received, with plans to make them the centrepiece of an international community of practice.

Output 3 Score B ‘Tools of the trade’ to support the effective delivery of ICF spending on adaptation including on value for money, low regret options, guidance on cost benefit appraisals, and decision tools on uncertainty.

The score of B for this output is in part an artefact of how the projects have been classified. Arguably the development of the VFM work reported under output 2 should count here - as it uses and develops earlier work on tools. Other knowledge products also provided ideas on best practice and advice on action but have not been reported under this output. Feedback on the tools produced has been extremely positive, but in the latter stages the work on tools was reduced as the take up of tools was very low, or had limited audiences . The focus changed to raising awareness of the links between climate change and development.

Lessons and how these have been shared

The lessons from individual outputs have all had planned dissemination and communication plans associated with them.

There are clear lessons from the programme as a whole;

- Ability to respond quickly to questions helped to build the early ICF portfolio. Small knowledge funds that can respond quickly to plug gaps in knowledge, produce learning or planning tools or facilitate international dialogue are very useful and can represent very high value for money.
- High transaction costs of contract management at a time when resources are scarce: That managing the funding process is time consuming – the future monitoring and evaluation and learning programme ( Compass ) will combine and manage three small knowledge funds into one to help reduce the burden on DFID staff .
- Robust monitoring and evaluation results on each sub project is essential in gauging the value for money and benefit of this kind of programme. The dispersion of leadership of the actions under this project, and the frequent changes of lead adviser/ Senior Responsible (Programme) Officer (SRO) made gathering evidence and coming to a view on overall value for money more difficult. For future knowledge programmes, a monitoring and evaluation plan should be developed when the programme is designed to enable DFID to understand the extent to which it is responsive to the needs of stakeholders and outcomes of the investment.

The lessons above came out strongly in this review and in studies of this and other knowledge funds undertaken to prepare future monitoring and evaluation work.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Better knowledge around what constitutes best practice in adaptation including on social protection, local accountability, on private sector engagement.
Output number per LF		1	Output Score	A
Risk:		Minor	Impact weighting (%):	34
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of demand led knowledge products completed	20 examples	3 reported in previous reviews +6 last year of the project. =9 Total
Evidence of influence on DFID programming	10 examples	5+2=7
Evidence of influence on the international system	3 examples	3+2=5

Key Points
 The first number above is the aggregate from previous reviews and the second number the number in the last year of the programme. Work over the last year of the project is set out below.

Aries Component	Supplier	Description	Contract Value	Spend	start/end date
202948-126	EFO-World Bank	Study to improve evidence on the impacts of climate change on poverty WB Shockwaves report (2016)	£200,000	£200,000	Aug 14-Jun 15
202948-128*	Vivid Economics/ODI	Understanding Patterns of Climate Economic Development	£104,045	£124,854	Jan15- Nov15
202948-129*	Coffey International	Enhancing Capacity to deliver on Gender	£128,866	£123,712	Dec 14-Jan 16
202948-130*	HTSPE	Literature Review on Energy Access and Adaptation to Climate Change	£25,415	£30,498	Jan 15-June 15
202948-131	Climate Policy Initiative	Private Finance	£65,000	£65,000	Jun 2015-Oct 2015
202948-134	WWF	Strengthening the development impact of Hydropower	£71,000	£40,000	Nov 15-Mar 16

The assessment of evidence of influence is conservative and where specific examples are available. The fact that the project came up short on its milestones on numbers of projects was due to constraints on funds rather than demand with some projects having to be turned away. The milestone had been increased from 10 to 20 in a logframe revision in March 2015 which was unrealistic, but the logframe was not re revised. The value of the programmes offsets the fact that it missed the original milestone by 1 project.

The work was strongly demand led, for example with country case studies in the Vivid Economics work being able to respond to the needs for programme planning in DFID country programmes. The review of knowledge funds for future monitoring and evaluation work noted that the programme funds have had extensive influence and enabling power for the production of DFID business cases. The recording of examples of influence is patchy but products have been widely read and disseminated. Some products influenced the recent Bilateral Aid Review bids (that set our DFID’s future spending plans by country offices) e.g. Tanzania, Nepal, Rwanda, Zambia, Malawi, and highlighted challenges of integration of climate spend.

Evidence for influence over the international system is hard to prove, and would take a bespoke study, tracking the results of all the sub projects. Anecdotes from this year do support the notion that products have been influential – for example the hydropower work featured in the Economist blog[3] and the World Bank work Shock Waves Report (2016) has been actively disseminated by the Bank and has been downloaded over 49,000 times.
[3] http://www.eiuperspectives.economist.com/energy/myanmar-poised-lead-smart-hydropower-planning

One sub project that has not gone so well is the collection of work on Gender due to low quality of work produced by the consultants. This was mainly due to the fact that the work was not focused on the right audiences, and poor understanding of both DFID/DEFRA and DECC needs. This required close management and constant revision of products with DFID, which had some influence but did not fulfil early expectations.

Taking the project as a whole, the reviews over the last two years scored this output as A+ and A. Continued strong performance in the final year merits the rating of A overall.

Summary of responses to issues raised in previous annual reviews (where relevant)
The previous review noted that it was important to make sure that products responded to need and interest. This has been the case, with all activities commissioned this year having a clear set of end users defined in response to work undertaken with Saatchi on Understanding Audiences and promoting learning.

Recommendations for future programmes

See section B

Output Title	Better international coherence and coordination of climate change adaptation including adaptation monitoring and evaluation, frameworks, and communities of practice around adaptation.
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	33
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of products/processes supported on M&E	5	5 reported in previous reviews +2 in last year of the project. =7 Total (Rwanda support to national process, Nepal DFID programme planning. Tanzania programme planning, Braced M and E system, Climate Services for Africa programme
Positive ICAI evaluation of the ICF and particularly of UK adaptation programming.	ICAI comments positive	ICAI report Green/Amber
Evidence of influence on International M&E systems for adaptation	5	9 NAP Global Network; EGA; Community Based Adaptation annual conference; Input into CDKN ,GCF, CIF, OECD, UNFCCC, Community of practice under the GRP

Key Points
Aries Component	Supplier	Description	Contract Value	Spend	start/end date
202948-127*	HTSPE	Low Regrets Phase II	£124,055	£147,619	Sept 14-Oct 15
202948-135	OECD	Structured consultations and country workshops to set out knowledge and policy gaps	£17,326	£17,326	Nov 15-Mar 16

The two outputs above were produced during this year. They are further development and application of the value for money framework, concentrating on its application to country programmes and business cases and with evidence of the framework being used in Tanzania, Nepal, Rwanda, Tanzania and for Regional Africa programmes. Work with the OECD contributed to a project that brought together countries to discuss adaptation so far has resulted in commitments from Colombian authorities to move concerns for adaptation centre stage, and facilitated South-South learning. OECD will report on this work more fully at the Marrakesh Conference of Parties (COP). DFID has also assisted OECD to learn from our work on learning – with Saatchi providing advice and direction on modifying the style of the OECD’s communication to lead to greater impact.

More widely, previous annual reviews have pointed to significant engagement on international issues, with DFID having influence - driven at least in part by the tools provided by this project. Most recently the enthusiasm for DFID’s involvement of the Global Resilience Partnership and the Rockefeller led community of practice has been explicitly because DFID is regarded as a thought leader on adaptation and resilience.

Summary of responses to issues raised in previous annual reviews (where relevant)

Previous annual reviews have underlined the importance of DFID staff engaging internationally. This took centre stage towards the end of this programme - particularly in the run up to the UNFCCC meeting in Paris. The last review also recommended that the new monitoring, evaluation and learning strategy had a more specific plan for sharing information more effectively. This has been addressed by recognising the way our key audiences learn and share information and the 10 learning principles which have put connections and understanding audiences and change at the heart of our work. The review also recommended that learning materials be made more readily accessible to DFID staff. The materials produced under this programme are now part of an interactive learning resource and active community of practice that includes DFID as well as other key organisations and practitioners on adaptation and resilience.

Recommendations for future programmes

See section B

Output Title	‘Tools of the trade’ to support the effective delivery of ICF spending on adaptation including on value for money, low regret options, guidance on cost benefit appraisals, and decision tools on uncertainty.
Output number per LF		3	Output Score	B
Risk:		Low	Impact weighting (%):	33
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of products	10	2+1=3
Uptake of business cases, and appraisals using Adaptation guidance.	No milestone in logframe	6 +
Visible replication of UK practices and guidance.	5	GCF results framework for adaptation includes indicators similar or exact to those developed based on knowledge pieces and international coherence events (donor event – DFID/USAID/GIZ; Adaptation Partnership M&E event) and reports (OECD examination of national approaches to M&E) and Energy work identified 14 Energy Africa Countries.

Key Points

Aries Component	Supplier	Description	Contract Value	Spend	start/end date
202948-133	ODI	Energy Africa campaign evidence and consultation	£25,000	£25,000	Jul 15-Nov 15

This year the work on energy was instrumental is setting up the energy Africa Campaign that currently works with 14 countries. One country has already signed a formal compact and several more are expected to sign shortly.

Counting what counts as a ‘tool of the trade’ as opposed to a knowledge product and the fact that knowledge products are used to inform DFID processes means that counting the products relevant to the ‘tools’ work is problematic. Arguably the VFM stage 2 work which provided support and information to country programmes could be counted here - as indeed can the international interest shown in DFID’s take on adaptation and resilience that continues to be influential. The use of the adaptation guidance being in business cases has not been systematically collected.

This output is scored a ‘B’ largely as an artefact of the way the logframe has been put together and the fact that the monitoring of the impact of the knowledge products has not been rigorous.

Summary of responses to issues raised in previous annual reviews (where relevant)
The previous review noted that feedback on the tools was extremely positive from a few people who used the tools. However , at the time there was a shift in DFID thinking and knowledge of the blockages of integration of climate change into development planning , the shift was from the “supply push” of tools to a more nuanced understanding of the socio and political changes needed to engage partners and country offices .The focus shifted from production of tools by CED/DFID ( which tended to sit on the internet underutilised ) to the use of dialogue and systems and processes to engage staff, especially non-technical staff. This way of learning has been specifically taken up in the new monitoring evaluation and learning contract and pioneering new learning and a community of practice in DFID.

Recommendations for future programmes.
See Section B

## VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
The main costs are the researchers to produce the products. Each contract was negotiated separately and the VFM for each contract assessed against similar contracts. Where one contractor underperformed, payment was withheld until products had been improved.

Internally, this programme has required significant project management to set up and administer a number of small contracts. This work was spread out as lead advisers produced proposals and negotiated TORs.

There was limited incentive for commissioners of work to ensure that they reported back on results for overall programme management, which has made information management and review of the programme difficult. This was compounded by the changeover of staff responsible for the project, which has had a number of lead advisers/SROs and quality assurers over its lifetime. The management of it suffered in the run up to the Paris UNFCCC meeting as key staff needed to devote time to getting a good deal from the Conference of the Parties.

VFM performance compared to the original VFM proposition in the business case
As has been mentioned in previous reviews, the very significant VFM in this programme is that it meant that there did not have to be a myriad of small business cases produced for knowledge work. VFM was also maintained through competitive bidding wherever possible to deliver the work.

Assessment of whether the programme represented value for money
This programme represented value for money in two ways:

1. The alternative to this project would be to do a bespoke business case for each action under this project – which would have taken up significantly more staff time.
2. The other alternative would be to not do the knowledge work at all. While the project has not invested in a systematic piece of research to determine impact (this would be disproportionately expensive), evidence that has been gathered and feedback has noted that the products and activities have been highly influential.

Quality of financial management during programme

The last annual report reflected a miscalculation that that the funds would not be utilised by the planned 10 milestone examples (which were then revised to 20). In fact, effective programme development and the shape of demand within new projects resulted in all funds being used to cover 9 projects. The financial management of the programme has kept up with spending across disparate activities well.

The small underspend was due to budget being held back to cover projects that actually came in under budget but financial procedures making it difficult to rebudget these funds in subsequent years.

Date of last narrative financial report	Various
Date of last audited annual statement	N/A

E: RISK (½ page)

Quality of risk management over the life of the programme

The risk management was split across the individual projects. The risk of fraud was low as contract amounts were small and principally paid for people’s time. Quality control was robust – when one projects' products were sub-standard, payment was withheld until they were improved.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
The products delivered well against the timescale set with the exception of the work on Gender which required extra time and effort to ensure delivery

Performance of partnership (s)
N/A

Asset disposal and value obtained by DFID
N/A
G: CONDITIONALITY (½ page)

Partnership principles assessment
N/A

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
This programme addressed key aspects of the ICF Adaptation Theory of Change especially gaps in evidence/tools are one of the constraints discouraging action. The activities directly support the ICF’s aim for delivery of outputs that enable developing, piloting and supporting scaled up innovative and low regrets adaptation programmes including incentives for macro-level climate resilient growth. By generating new decision making tools on uncertainty, and developing VFM and low regrets options this programme enhances the likelihood of change occurring.

Preparation for the ICF’s wider Monitoring Evaluation and Learning work has concurred that this programme has had significant impact, but there has not been a systematic review of the impact of all the projects. Given the spread of projects - in time, geography and subject, such an undertaking would be complex and it was judged not to represent good value for money given the strong feedback supporting the usefulness of the outputs from the project.

Monitoring progress throughout the programme
Advisers were asked to provide feedback on the usefulness of the projects. Responses were all positive but were not systematic.

There is scope for DFID to be more systematic in collecting learning about the impact of its knowledge and learning products. This lesson has now been applied and a more systematic approach to collecting learning on impact is a strong feature of the ICF’s major new Monitoring and Evaluation and Learning workstream