## Logframe
PROJECT NAME | Support to Flood Recovery in Serbia, and Bosnia and Herzegovina
IMPACT | Impact Indicator 1 |  | Baseline | Milestone Mar | Milestone June | Milestone Sep | Target Feb 2016
The possible effect of future flooding on the population protected by programme funded flood defences is lessened. | % of the target population protected by improved flood defences in Serbia (in Lazarevac municipality) and BiH priority localities. | Planned | 0 | 0 | 50 | 90 | 100%
Achieved
Formal documentation of partner local governments.
UNOPS and UNDP quarterly reporting; HMG monitoring and evaluation
| Impact Indicator 2 |  | Baseline | Milestone Mar | Milestone June | Milestone Sep | Target Feb 2016
| % of project funded flood defenses in the Lazarevac municipality and in the BiH priority localities assessed as 1) offering better than pre-flood levels of protection and 2) capable of withstanding a flood of similar size without any significant effect on the protected population. | Planned | 0 | 0 | 30 | 80 | 100%
Achieved
Project technical documentation and reports; technical supervision reports of partner local governments.
UNOPS and UNDP quarterly reporting; HMG monitoring and evaluation
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone Mar | Milestone June | Milestone Sep | Target Feb 2015 | Assumptions
The flood defences and sanitation infrastructure in Serbia and BiH are improved. | % of flood defence measures in Lazarevac municipality (Serbia) completed. | Planned | 0 | 0 | 50 | 90 | 100& | Programme design and implementation completed succesfully. Outputs are of sufficent scale and quality to ensure a positive outcomes and impact.
Achieved
Source
UNOPS and UNDP quarterly reporting
| Outcome Indicator 2 |  | Baseline | Milestone Mar | Milestone June | Milestone Sep | Target Feb 2016
| % of flood risk mitigation measures in BiH priority localities completed. | Planned | 0 | 20 | 60 | 80 | 100%
Achieved
Project technical documentation and reports; technical supervision reports of partner local governments.
UNOPS and UNDP quarterly reporting
| Outcome Indicator 3 |  | Baseline | Milestone Mar | Milestone June | Milestone Sep | Target Feb 2016
| % of target population in BiH priority localities who have had their public sanitation services restored to at least pre-flood standards. | Planned | 0 | 15 | 60 | 80 | 100%
Achieved
Project technical documentation and reports; technical supervision reports of partner local governments.
UNOPS and UNDP quarterly reporting
RISK RATING
Low
INPUTS (£) | DFID (£) |  | Govt (£) |  | Other (£) | Total (£) | DFID SHARE (%)
| £2 million |  | N/A |  | N/A | N/A | 100%
INPUTS (HR) | DFID (FTEs)
0.2 FTE
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone Mar | Milestone June | Milestone Sep | Target Feb 2016 | Assumption
Flood defences in Serbia are repaired. | Number of projects to fortify riverbeds and banks that are assessed as being on track against their delivery milestones and plans. 4 rivers, Kolubara, Lukavica, Pestan and Turija | Planned | 0 | 0 | 2 | 3 | 4 | Programme design and implementation completed succesfully.
Achieved
Source
UNOPS quarterly reporting
| Output Indicator 1.2 : Capacity is built within municiple authorities, Ministry of Interior and Belgrade Waters. | Planned | 0 | 0 | 1 | 2 | 3 | Programme design and implementation completed succesfully.
Achieved
Source
UNOPS quarterly reporting : [{1} - Skills Needs Assessment Completed, {2} - Draft Plan for Flood Prevention available and under review, {3}- 20 people trained in Ministries and Action Plan for Flood Prevention (with Lessons) Adopted.]
IMPACT WEIGHTING (%)
49% | [7 empty] | RISK RATING
Low
INPUTS (£) | DFID (£) |  | Govt (£) |  | Other (£) | Total (£) | DFID SHARE (%)
| TBC |  | N/A |  | N/A | N/A | 100%
DFID (FTEs)
INPUTS (HR) | 0.05
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone Mar | Milestone June | Milestone Sep | Target Feb 2016 | Assumptions
Flood defences in BiH are repaired. | Number of de-silting and cleaning of wastewater pipe projects that are assessed as being on track against their delivery milestones and plans. | Planned | 0 | 10 | 10 | 10 | 10 | Programme design and implementation completed succesfully. Procurement of services and works completed on time.
Achieved
UNDP reports, procurement and technical documentation related to the projects. Official documentation of partner local governments.
UNDP quarterly reporting
| Output Indicator 2.2 |  | Baseline | Milestone Mar | Milestone June | Milestone Sep | Target Feb 2016 | Assumptions
| Number of wastewater (be it reconstruction, upgrades, desilting and cleaning) infrastructure projects assessed as being on track against its delivery milestones and plan. | Planned | 0 | 10 | 10 | 10 | 10 | Programme design and implementation completed succesfully. Procurement of services and works completed on time.
Achieved
UNDP reports, procurement and technical documentation related to the projects. Official documentation of partner local governments.
UNDP quarterly reporting
| Output Indicator 2.3 |  | Baseline | Milestone Mar | Milestone June | Milestone Sep | Target Feb 2016 | Assumptions
| Number of river dredging and cleaning projects are assessed as being on track against their delivery milestones and plans. | Planned | 0 | 5 | 5 | 5 | 5 | Programme design and implementation completed succesfully. Procurement of services and works completed on time.
Achieved
UNDP reports, procurement and technical documentation related to the projects. Official documentation of partner local governments.
UNDP quarterly reporting
IMPACT WEIGHTING (%)
51%
RISK RATING
Low
INPUTS (£) | 180000 |  | Govt (£) |  | Other (£) | Total (£) | DFID SHARE (%)
|  |  | N/A |  | N/A | N/A | 100%
INPUTS (HR) | DFID (FTEs)
0.02

## Results Chain
Support to Flood Recovery in Serbia, and Bosnia and Herzegovina
OUTPUTS |  |  | OUTCOME | IMPACT
1 | Flood defences in Serbia are repaired. | 49% | The flood defences and sanitation infrastructure in Serbia and BiH are improved. | The possible effect of future flooding on the population protected by programme funded flood defences is lessened.
2 | Flood defences in BiH are repaired. | 51%
3 | 0 | #REF!
4 | #REF! | 10%

## Logframe Summary
Support to Flood Recovery in Serbia, and Bosnia and Herzegovina
Results Chain |  |  | Indicators | Baseline | Target Feb 2016 | Source
IMPACT | The possible effect of future flooding on the population protected by programme funded flood defences is lessened. |  | % of the target population protected by improved flood defences in Serbia (in Lazarevac municipality) and BiH priority localities. | 0 | 100% | UNOPS and UNDP quarterly reporting; HMG monitoring and evaluation
|  |  | % of project funded flood defenses in the Lazarevac municipality and in the BiH priority localities assessed as 1) offering better than pre-flood levels of protection and 2) capable of withstanding a flood of similar size without any significant effect on the protected population. | 0 | 100% | UNOPS and UNDP quarterly reporting; HMG monitoring and evaluation
OUTCOME | The flood defences and sanitation infrastructure in Serbia and BiH are improved. |  | % of the target population protected by improved flood defences in Serbia (in Lazarevac municipality) and BiH priority localities. | 0 | 100& | UNOPS and UNDP quarterly reporting
|  |  | % of flood risk mitigation measures in BiH priority localities completed. | 0 | 100% | UNOPS and UNDP quarterly reporting
|  |  | % of target population in BiH priority localities who have had their public sanitation services restored to at least pre-flood standards. | 0 | 100% | UNOPS and UNDP quarterly reporting
OUTPUTS | Flood defences in Serbia are repaired. | 49% | Number of de-silting and cleaning of wastewater pipe projects that are assessed as being on track against their delivery milestones and plans. | 0 | 10 | UNDP quarterly reporting
|  |  | % of flood risk mitigation measures in BiH priority localities completed. | 0 | 10 | UNOPS quarterly reporting : [{1} - Skills Needs Assessment Completed, {2} - Draft Plan for Flood Prevention available and under review, {3}- 20 people trained in Ministries and Action Plan for Flood Prevention (with Lessons) Adopted.]
|  |  |  | #REF! | #REF! | #REF!
| Flood defences in BiH are repaired. | 51% | Output Indicator 1.2 : Capacity is built within municiple authorities, Ministry of Interior and Belgrade Waters. | 0 | 10 | UNDP quarterly reporting
|  |  | Number of wastewater (be it reconstruction, upgrades, desilting and cleaning) infrastructure projects assessed as being on track against its delivery milestones and plan. | 0 | 10 | UNDP quarterly reporting
|  |  | Number of river dredging and cleaning projects are assessed as being on track against their delivery milestones and plans. | 0 | 5 | UNDP quarterly reporting
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
| 0 | #REF! | #REF! | 0 | 10 | UNDP quarterly reporting
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | 100% | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!