Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Political Settlements Research Programme (PSRP)
Programme Value: £4,366,612		Review Date: March 2016
Programme Code: 204326	Start Date: 01/04/2014	End Date: 30/03/2019

Summary of Programme Performance
Year	2015	2016	2017
Programme Score	A	A	A+
Risk Rating	Medium	Moderate	Moderate

Summary of progress and lessons learnt since last review

The Political Settlements Research Programme (PSRP) has met or exceeded its milestones during its second year. The University of Edinburgh (UoE) led consortium is in high demand from the international conflict policy community, particularly with the UN. PSRP has performed well on three key areas:
- Comparative case study research (e.g. Nepal, Afghanistan, Nigeria and Ethiopia)
- Completion of the political settlements database (due to go live on the website later this year).
- Policy engagement with HMG, the UN, and partners, to inform peace talks on Columbia, Yemen, Libya and Syria This has included expertise provided to UN mediators working on Yemen and constitutional provisions included in the Columbia peace agreement.
Key examples of policy influence so far include:
- Policy support to the drafting of the World Bank Development Report 2017, UN Conflict Prevention agenda, the development of DFID’s Building Stability Framework, and the DFID/ODI-hosted Wilton Park Conference on Re-thinking Conflict, State building and Fragility.
- Further policy work for UNWomen, building on PSRP’s contribution to the United Nation’s 15-year review of UNSC resolution 1325, on women, peace and security, in PSRP’s first year.
PSRP has met or exceeded all log-frame indicators for 2017. Over the final 2 years of the programme, PSRP will focus on impact, and policy relevance, of research rather than number of products. This includes further research on four policy themes prioritised by a UK cross-government group (including Stabilisation Unit, Foreign Office Research Analysts and DFID Policy leads): power and territory sharing, sub-national arrangements, design and implementation of peace processes and security guarantees and justice provisions. Research will also continue on the central focus of the research programme “how to support “inclusive” political settlements”. This will also be integral to the new policy themes. Gender analysis is also a core theme of PSRP’s research and policy work.

Follow-up on 2013-14 recommendations:
PSRP has acted on the recommendations which included reviewing the Duty of Care policy; and Digital Strategy. See Annex 1 for detailed actions taken.

Summary of recommendations for the next year:
As part of this Annual Review (AR) period, PSRP has focussed resources and research to meet high demand from UK officials, and partners working on complex conflicts. The main recommendations from this AR are:
Deepen engagement with DFID/FCO Country teams- PSRP to:
1. Provide comparative analysis and advice to support at least 2 additional UK country teams working on current peace processes (assess by feedback from DFID/FCO teams at next AR).
2. Increase engagement with DFID country teams on case-study research (Nepal, Nigeria, Ethiopia, DRC, and Afghanistan) to improve relevance and uptake (to be assessed from feedback on ACCORD publications at next AR).
1. Provide thematic research on 4 priority policy topics PSRP to deliver a report on each of 4 priority policy topics (peace process design and implementation, sub-national arrangements, power/resource sharing, security guarantees and justice provisions). (by Dec 2018).
2. Revise logframe indicators for uptake PSRP to update logframe impact indicators in light of re-focussed programme; and website related audience indicators for Output 2. Although PSRP met or exceeded the log frame output indicators for research publications, we assess these to be sufficiently stretching. The proposed revisions to the log frame will focus on quality and relevance of PSRP publications in line with the new policy areas agreed with PSRP during this annual review. Revised indicators should include uptake meetings to be held in London every 6 months to improve engagement with Whitehall policy and country teams (by Aug 2017).

A. Introduction and Context

DevTracker Link to Business Case:	4429922
DevTracker Link to Log frame:	5350670

Outline of the programme
DFID is providing £4.4m over four years (2015-19) to fund research into how donors can shape political settlements - the rules that regulate the access of elites to resources and power – to reduce poverty and the risk of conflict[1]. The research programme, in an area which has many evidence gaps, will inform the content, choice and targeting of interventions on political settlements by donors, diplomats, and defence actors, especially in fragile and conflict-affected states (FCAS). The research will lead to more effective interventions that address conflict risks and promote pro-poor institutions.
[1] How power is organized in a society and the rules that regulate how elites work together is termed the ‘political settlement’. Additional characteristics of political settlements include a) a broad reflection of the underlying distribution of power between different social groups; b) that they are not static or single events, but continuous bargaining processes over these rules between different elite and non-elite groups; c) that they are expressed through formal and informal institutions which constrain and shape the underlying bargaining processes; and d) exist both at the state and the sub-state level.
The Political Settlements Research Programme (PSRP) has been running for 2 years, including a six-month inception period (to Sept 2015). This is the second AR.
This programme focusses on three broad themes:
1. How different types of political settlement emerge, and which actors, institutions, resources, and practices shape them;
2. How political settlements can be improved by internally-driven initiatives, including the impact of gender-inclusive processes and rule of law institutions; and
3. How, and with what interventions, external actors can change political settlements.
The research is explicitly comparative (that is, it seeks insights by understanding examples and the differences between them). The programme uses a mix of qualitative and quantitative methods, with substantial field work. Currently, research is focussed on Afghanistan, the Democratic Republic of Congo (DRC); East Timor; Ethiopia (Ogaden); Liberia; Nepal; Nigeria; Philippines; Sierra Leone; and Somalia, with comparison with less fragile settings: Colombia and Northern Ireland.
Following a competitive procurement process, the University of Edinburgh was selected to lead the consortium and implement the programme. PSRP complements existing RED research programmes, notably the Effective States for Inclusive Development Consortium (ESID), the Justice and Security Research Consortium (JSRP), and the Secure Livelihoods Research Consortium (SLRC).

## B: PERFORMANCE AND CONCLUSIONS
Annual outcome assessment
The Political Settlements Research Programme (PSRP) has met or exceeded all output indicators. This progress is beginning to translate into tangible outcomes:
UK Policy influence:
- UK Conflict Policy: Edinburgh University has provided substantive input to UK conflict policy for example through their engagement on sequencing of peace agreements and constitutional processes with FCO Research analysts. PSRP research also shaped the themes on conflict-resolution processes and fair power structures, informing DFID’s ‘Building Stability’ Framework.
- UK Country Policy; PSRP has provided flexible advice to senior officials working on peace processes during times of crisis - a service for which there is growing demand. PSRP advised the FCO on precedents for transitional constitutional arrangements to inform the Vienna Process on Syria. This advice made “a major contribution to shaping the UK approach to this matter” according to a senior UK official.
- PSRP has also trialled sessions with country teams (Syria and Yemen) to help review their support to peace processes, drawing on comparative evidence. Positive feedback from these early engagements has enabled PSRP to build more targeted sessions with the teams in June. We will review feedback on these in next year’s AR. These sessions will also be extended to other teams in 2017.

International Policy influence:
- Multilateral Policy: A PSRP recommendation was featured in the Global High Level Report which fed into the new 2015 UNSC Resolution on women, peace and security. Following this recommendation, the German Government provided $5 m to support training and policy advice to women in Middle East peace processes over the next five years
- Operational support: In collaboration with International IDEA, PSRP provided the UN with, advice, data analysis and research papers to inform negotiations in Yemen. International IDEA credits PSRP’s contribution with helping make important progress in the talks[2]
  [2] Negotiations regarding the constitutional process remain confidential.
Influencing peace processes: PSRP was approached by parties to the Colombian peace negotiations and UK officials to advise on the legal enforceability and constitutionality of any resulting peace accord. The advice, informed by PSRP research, resulted in constitutional protections being written into the final peace agreement. Although these were not endorsed by the referendum vote, PSRP’s advice helped overcome a strategic stalemate during negotiations, and achieve an important milestone in the peace process. Two major national newspapers in Columbia (El Espectador[3] and El Tiempo[4]) cited PSRP research in support of an Agreement and the research was referenced during an interview conducted with the main political magazine (Semana[5]). PSRP was also referenced by the Colombian peace mediator when presenting the Agreement to the Constitutional Court[6].
[3] http://www.elespectador.com/opinion/lex-pacificatoria
[4] http://www.eltiempo.com/politica/proceso-de-paz/acuerdos-del-proceso-de-paz/16590732
[5] http://www.semana.com/nacion/articulo/derecho-en-procesos-de-paz-habla-christine-bell/474441
[6] HYPERLINK "http://es.presidencia.gov.co/noticia/160526-Intervencion-del-Jefe-de-la-Delegacion-del-Gobierno-Humberto-de-la-Calle-en-la-Corte-Constitucional" Intervención del Jefe de la Delegación del Gobierno, Humberto de la Calle, en la Corte Constitucional, Presidencia de la República (Colom., May 26, 2016).
Overall output score and description: A+ (Output and performance exceeds expectations)

Key lessons and actions
1. Country case study research and analysis needs to be tailored to teams working under intense pressure in contexts where there are sensitivities about sharing analysis that could be seen to influence negotiation outcomes.
Action: Provide comparative analysis and advice to support at least 2 additional UK country teams working on current peace processes (recommendation 1a above).
More detailed case study research is being undertaken in contexts where peace processes, and cycles of conflict, have evolved over 20-30 years and where wider lessons are easier to determine (e.g. Nepal, Nigeria, Afghanistan, DRC). The bulk of the case study research was undertaken this year.
Action:	Increase engagement with DFID country teams on case-study research (Nepal, Nigeria, Ethiopia, DRC, and Afghanistan) to improve relevance and uptake (to be assessed from feedback on ACCORD publications at next AR). (Recommendation 1b above)
2. Comparative thematic analysis: emerging peace processes: Demand for PSRP advice and research has been highest among those working directly on peace and/or constitutional processes, often in contexts where peace negotiations are less than 5 years old. PSRP has tailored research uptake to take account of policy interests.
PSRP’s 2016 Sequencing report made the case for aligning peace agreements and constitutional processes and for situating shorter term mechanisms in a longer term process suited to protracted conflicts. This approach (drawing together analysis from the database, with case studies and wider literature) generated significant uptake among policy and country teams. A X-Whitehall group of officials identified other common themes which could generate similar operationally relevant findings across contexts.
Action: PSRP to deliver a report on each of 4 priority policy topics (peace process design and implementation, sub-national arrangements, power/resource sharing, security guarantees and justice provisions). (by Dec 2018). (recommendation 2 above).
3. Revising impact indicators for uptake: Demand for research on political settlements is variable, and subject to fluctuating conflict cycles and international attention. Ongoing peace and political processes can take 20 years or more to reach conclusion. PSRP’s work to inform ongoing processes may therefore be best reviewed through feedback from those involved in the process rather than concrete signs of progress in contexts where an end to conflict may be some way off (e.g. Syria, Yemen). PSRP’s work on Columbia, demonstrates the value that research can provide when the political conditions for a positive milestone emerge. While we would expect these outcomes to contribute towards reduced discrimination, fragility, deaths in conflict, and violent homicide rates (PSRP programme impact indicators), it is clear that the current indicators are too ambitious in terms of direct attribution and measurability.
Action: PSRP to update logframe impact indicators in light of re-focussed programme; and website related audience indicators for Output 2 (recommendation 3 above).
Has the logframe been updated since the last review?
Substantial logframe revisions were made over the last year. Further revisions at impact level will be made by August 2017.

## C: DETAILED OUTPUT SCORING

Output Title	Research products
Output number per LF		1	Output Score	A+
Risk:		Moderate	Impact weighting (%):	60%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1 Peer reviewed academic articles, reaching high standards of international excellence	6 articles / essays published in journals / outlets and 1 monograph, all with peer-review	Exceeded / PSRP has produced 13 peer-reviewed journal articles or book chapters (see annex 3)[7] / While the envisioned monograph is yet be completed (delay of project 5.4), two special journal issues are currently in print and will be published in March 2017 (‘Global Constitutionalism’) and May 2017 (‘Journal of International Development’).[8]
1.2 New datasets capable of supporting ongoing research	Peace Agreement Access Tool's data collection on women and international norms and violence against women projects has begun.	Achieved / The Peace Agreements Database (PA-X) coding is 90% complete. PSRP has provided a demonstration of the database to DFID and FCO staff. Completion date is by end March 2017. / A database including all agreements that refer to UNSCR 1325 is already online and fully functional. / Work on the Amnesty database has begun and will be complete by the end of December 2017.
1.3 Range of research products	1 special edition of ‘Accord’ magazine, 10 briefing papers, 5 research reports and 10 blogs completed and freely available online	Exceeded / PSRP has delivered 14 briefing papers, 16 research reports, and 47 blog entries[9]. / The ACCORD publication on Nepal was published in March 2017. Further publications on Nigeria and Nepal were also published in 2016/7.
[7] Journal publications are green open access (entered in repository with full text of ‘author’s last version uploaded open access online)
[8] All journal publications are independently peer reviewed
[9] All PSRP non-journal publications are gold open access

Key Points
2016 – 2017 has been a productive year for PSRP with all databases near completion and publication targets exceeded. Several outputs have achieved significant policy impact (see section B).
Based on the experience gained so far, and consultation with users of PSRP research, particularly in HMG, PSRP should refine the scope of future research to focus on the types of output most likely to have impact.
Summary of responses to issues raised in previous annual reviews (where relevant)
Logframe was revised. Outputs brought into line with AR cycle.
Recommendations
PSRP will refine the scope of the research to focus on those areas where there are substantive emerging findings and where this overlaps with UK policy interests, as per recommendation 2 above. The refocus will also be reflected in PSRP’s website themes (by Dec 2017).

## C: DETAILED OUTPUT SCORING

Output Title	Uptake and engagement
Output number per LF		2	Output Score	A+
Risk:		Moderate	Impact weighting (%):	40%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Output Indicator 2.1: Cumulative number of workshops, briefings and engagement events involving PSRP and key stakeholders in which PSRP research is discussed substantively	At least 5 workshops; at least 5 other stakeholder engagement events (cumulative)	Exceeded. / PSRP has organised 21 events (12 during the reporting period) including workshops, seminars, conferences, stakeholder engagement forums, and 4 summer schools. / This included three events to inform the country case studies, on Ethiopia, Afghanistan and Nigeria. DFID/FCO staff attended and have provided feedback on draft reports. These follow similar events on Nepal and DRC in Year 1. / Other events informed the development of the PSRP databases to improve compatibility with other international datasets and helped to develop tools for measuring political processes. / PSRP is in high demand within international conflict policy circles. They contributed to events, with the UN in New York and with Carnegie and USIP in Washington. / The event co-organised with International IDEA led to PSRP support for the UN mediation team on Yemen.
2.2 PSRP Research taken up and referenced elsewhere (cumulative totals)	2 peer-reviewed articles cite PSRP work	Exceeded / PSRP work has been cited by 5 peer-reviewed journal articles not authored by PSRP or affiliated researchers: / Bell, ‘What we talk about when we talk about’, cited in: Abdulai, Abdul‐Gafaru. "Rethinking Spatial Inequality in Development: The Primacy of Power Relations." Journal of International Development (2016). / Pospisil/Kühn, ‘The Resilient State’, Third World Quarterly, cited in: Wagner, Wolfgang, and Rosanne Anholt. "Resilience as the EU Global Strategy’s new leitmotif: pragmatic, problematic or promising?." Contemporary security policy 37.3 (2016): 414-430. / Ni Aolain, ‘The “war on terror” and extremism’, International Affairs, cited in: Basu, Soumita, and Catia C. Confortini. "Weakest “P” in the 1325 Pod? Realizing Conflict Prevention through Security Council Resolution 1325." International Studies Perspectives (2016): ekw004. / Vogel/Musamba, ‘Recycling Rebels’, Briefing Paper, cited in: Richards, Joanne. "Implementing DDR in Settings of Ongoing Conflict: The Organization and Fragmentation of Armed Groups in the Democratic Republic of Congo (DRC)." Stability: International Journal of Security and Development 5.1 (2016). / Hagmann, Stabilisation in Somalia Report, cited in: Woolner, Christina J. "Education and extraversion: naming, valuing and contesting ‘modern’and ‘indigenous’ knowledge in post-war Somaliland." Journal of Eastern African Studies (2016): 1-21.
2.3 Policy decisions or processes where there is credible evidence of substantial influence by PSRP work (cumulative totals)	2 decisions in South; / 2 decisions in North	Achieved (see section B for details). / Germany / UN / Middle East / Decision: increased funding to gender and power sharing training and policy advice / Evidence: Feedback from UN. / UK / Syria / Libya: / Decision: a model for the transitional constitutional arrangements in Syria / Evidence: testimony of senior UK official. / UK/ Colombia: / Decision: the inclusion of constitutional protections in the peace accords. / Evidence: Colombian press articles and court records, testimony of FCO official. / UK / UN / Yemen: / Decision: which potential solutions, and how to frame these, to obstacles to the constitutional negotiation process. / Evidence: Testimony from International IDEA and UN representatives.

Key Points
PSRP has met or exceeded all output 2 targets. High quality research outputs (as measured by indicator 2.2) clearly underpin high level consultation (see section B for details).
Workshops, briefings, and engagement events this year have focussed on deepening the substance of the research. In years 3 and 4 we expect PSRP events to demonstrate clearer links to policy audiences and policy influence.
Limited data from PSRP’s website and social media activity makes it difficult to fully assess uptake of publications.
Summary of responses to issues raised in previous annual reviews (where relevant)
Outputs were substantially revised immediately after last AR.
Recommendations
Action: Recommendation 3 above outlines that PSRP will revise indicators to reflect the refocused activities and improved uptake plans by August 2017. PSRP should report cumulative data on website hits/downloads to show annual year-on-year change and also clarify how policy influence emerges from uptake events in quarterly reports (by AR 2018).
PSRP will also plan HMG uptake events in London every 6 months to ensure ongoing contributions to DFID/HMG policy and country teams. This builds on PSRP input to the DFID Conflict Advisers annual Professional Development Conference, and workshops with country teams over the last year. DFID and PSRP will also consider additional opportunities to improve uptake within UK government by AR 2018. This could include; a session for regional heads of mission conferences, Conflict Security and Stability Fund events or other policy discussions. These actions will be reviewed again in the AR 2018.
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE
Key cost drivers and performance
This is a milestone based contract. Expenses are paid on a quarterly basis in arrears based on actual costs. DFID retains 5% of each payment, the retained amount is then issued the following quarter providing all performance criteria have been met. Full details of key cost drivers are set out in section 4 of the contract.
VfM performance compared to the original VfM proposition in the business case, and assessment of whether the programme continues to represent value for money
Indicator category	Indicator	Performance / Best practices
Economy	Cost saving measures	Reduced travel costs by prioritising high impact events and using skype for planning with in-country partners. / Reduced printing costs, through online dissemination and in-house editing.
	Best practices in procurement	Meets fair trade and living wage requirements in line with UoE procurement guidelines. / Benchmarks southern researcher payments.
	Financial oversight	Robust financial systems at UoE include, copy receipts for all invoices submitted by partners, with internal and external auditing in place for the Consortium.
	Financial risk management	Adoption of a risk management strategy, according to DFID policies and risk management
Efficiency	Project management strategies	‘Basecamp’ virtual technology used for continuous communication between consortium members; / Benchmarking of project output/partner commitments.
	Increase quality/quantity of output	Internal peer review process for each project output / External peer review for all reports, including in-country review; / University-independent peer review of academic outputs / Contractual commitments delivered with additional outputs.
Effectiveness	Demonstrate ability to attract further funding	Additional funding from British Academy, UN Women and ESRC has accelerated and multiplied the programme’s core work e.g. UN Women grant on women and peace processes will produce eight country-specific briefs and topic guides, particularly on women’s inclusion and the implementation of UNSCR 1325 in Syria, Yemen, and the MENA region. The briefing papers relate to the PSRP core content of negotiating inclusion in fragile political settlements.
	Promote academic impact	8 articles in top academic journals, a further number of publications in edited volumes and other academic outlets; / substantial use of popular open access platforms, in particular SSRN, Academia and ResearchGate; / Active participation at leading international conferences, including the organisation of sections (EISA 2015, DSA 2016) or panels (ISA 2017, BISA 2016); / High profile reports, often in partnership with international organisations such as UN Women and International IDEA; / Launch events of reports at international key locations (such as Carnegie Endowment for International Peace, UN Headquarter); / Reception at ISA – largest international studies conference with over 5000 participants.
	Promote research uptake	Prior engagement with key stakeholders before finalising research design (questions and research design revised to reflect key stakeholder input) and prior to publication; / Hard copy circulated to key stakeholders with key publications (particularly non-academic); / Translations of reports to other languages (French, German).
	Establish research partnerships	Established key strategic partnerships with International IDEA, DLP Birmingham, ODI, LSE, Berghof Foundation, SOAS, The Graduate Institute Geneva.
Equity	Involvement of Southern Researchers	All in-country research joint with southern partners, including joint design, implementation and co-authoring research.
	Consider social inclusion	Explicit research focus on inclusion – in country partners ensures representation of different social, economic, political and gender groups. This has included indigenous women in Colombia, and gender and sexual minorities in Nepal; / Public events ensure disabled access; / Publications are designed (in terms of font and print) to comply with good practice for people with disabilities such as dyslexia; / A range of means of engagement are used to suit audience – publications, power point, online audio and video.
	Promote professional development of project staff	Management approach includes staff annual reviews and takes account of staff’ interests and career progression, / Promotes opportunities for southern based researchers by including named participants in the research and co-authors.

Quality of Financial Management
The overall variance for the year 16/17 year was 3%. This is a marked improvement over the 15% variance recorded in last year’s AR. Invoicing is robust and of good quality. All relevant supporting paperwork has been provided. This contract operates with a 5% retention each quarter, with the retention paid out the next quarter subject to key performance indicators being met. To date, no funds have been withheld.
The 1st quarter expenditure of 2016/17 was 97% of that originally forecast (£353,915). Quarter 2 was 93% (£386,598) of original forecast and quarter 3 was 99% (£387,152) of forecast with a final quarter forecast of £353,910. Expenditure in this quarter (Q08) was 115% of that forecasted in the latest budget revision. This spend recovers the slight underspends seen earlier in the financial year. Cumulatively, expenditure is 101% of that forecast for the full financial year with all work programmes progressing well. This represents a spend profile of 33% of the overall budget. The forecast expenditures for the following years are £1,177,381 (year 3: 2017-2018) and £870,099 (year 4: 2018-2019).
A full breakdown of expenditure can be found in Annex 2 page 39-43 of Political Settlements Annual Report.

F/Y Spend 16/17
£	Q1 (Mar- May)	Q2 (Jun-Aug)	Q3 (Sep-Nov)	Q4 (Dec-Feb)	Total
Forecast	353,915	386,598	387,152	359,910	1,481,575
Actual	341,821	358,067	383,771	406,709	1,490,368
Variance	(12,094)	(28,531)	(3,381)	52,799	8,793
% spend	97%	93%	99%	115%	101%

Date of last narrative financial report	Quest No 5707918
Date of last audited annual statement	N/A as a contract

E: RISK

Overall risk rating: Moderate
Overview of programme risk
The programme was originally assessed as Medium Risk using DFID’s earlier 3 category scale. PSRP members and organisations have continued to implement the risk management activities agreed in the original tender, to ensure that levels of risk in the programme remain at an acceptably low level. PSRP has focused risk assessment/management around four risk categories, two of them related to the outputs set out in the Logframe, the other two relating to internal factors – governance and management of the programme – and to the external environment. A summary is in annex 2.
The detailed risk assessment is shown in table 9 page 31-34 of PSRP annual report.
Following the recommendation in last year’s AR, PSRP reviewed Duty of Care procedures in all sites of ongoing field research. Systems put in place by partners were found to be reliable and compliant with University of Edinburgh oversight and DFID policy. PSRP has pursued a proactive approach to duty of care procedures by developing ‘Guidelines on Security, Risk and Ethics’ which were endorsed by all partners. Guidelines extend beyond contractual commitments, and requirements to inform the University of Edinburgh of risks, to include risk mitigation measures. These are attached as annex four of PSRP annual report (page 66) Quest No 5707918.
In the review, the two partners with significant fieldwork, Conciliation Resources (CR) and The Rift Valley Institute (RVI), demonstrated good and conflict-specific practices and systems. RVI has good local systems in DRC where conflict risks are particularly high. Their risk mitigation, staff safety and emergency response policies are tailored to high conflict contexts. PSRP has also worked with Edinburgh University lawyers to review partnership contractual obligations given the research in high risk contexts. This review confirmed that the legal responsibilities of all consortium partners are clear and well managed.
The main geographical areas of risk are DRC, Ogaden/Ethiopia (where the major part of field research has already been successfully conducted) and Afghanistan. Research work underway in these areas is closely monitored and allowed sufficient flexibility to take account of changes to the security situation.
PSRP’s revised Duty Of Care and risk management procedures are appropriate to implement the work.
Downstream partners: PSRP has provided full detail of the 5 downstream partners and respective funding flows to DFID. PSRP reports on activities and publications by partner and clearly identifies transactions to partners in budget and expenditure reports. DFID officials have met with all downstream partners at least once this year to discuss progress against activities.
Outstanding actions from risk assessment	None
F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
The project is on track against the planned timeframe.
Performance of partnership (s)
DFID is represented on the Consortium Advisory Group (CAG), which met for a full day on 01/03/2017. Regular telephone meetings are held between DFID and the UoE. Work plans, objectives, performance measures and budgets have been shared and openly discussed with DFID, all to DFID’s satisfaction.
Asset monitoring and control
There are no physical assets associated with this project.

G: CONDITIONALITY

Update on partnership principles (if relevant) Not relevant.
H: MONITORING & EVALUATION

Evidence and evaluation
PSRP completed its inception report in September 2015. The report was approved by DFID as a basis for further work.
Monitoring progress throughout the review period
DFID and the PSRP Director have formal meetings quarterly to discuss and monitor overall progress and communicate at least monthly and more frequently where required. PSRP submitted their Annual review and quarterly reports.in a timely manner. Quarterly reports are detailed and rigorous for a programme of this size.
This annual review was carried out during February and March 2017 by a team of DFID and Stabilisation Unit staff including an A1 Conflict Advisor, an A2 Governance Adviser, and a B2 Project Manager.
The DFID review team conducted a desk-based review of key documents, including a detailed report of the programme’s performance over the review period submitted by the partners, and reviewing key research and communication outputs. Meetings were held with PSRP, FCO, Stabilisation Unit, and DFID officials to ensure the research is meeting UK government interests. PSRP also received feedback on the research and policy engagement during participation at the annual DFID conflict advisers’ professional development event. A project review meeting was held in Edinburgh on 10/02/2017, the Consortium Advisory Group met on 01/03/2017, and a further meeting held between the AR team and PSRP in March 2017. The Annual Review report was shared with PSRP in March 2017. Recommendations will be followed up at subsequent project meetings.
ANNEX 1: Follow up on 2015/16 AR recommendations

1. The logframe for this programme will need to be revised in particular to reflect new research engagement outputs. This will require a new set of output measures relating to research uptake and stakeholder engagement, and synchronising milestones with future Annual Reviews. (ACTION: DFID to propose new draft by end March 2016; new logframe agreed with PSRP by end June 2016).
Completed: logframe was revised in April 2016. Further revisions, notably at impact level, are planned for the 2016/17 period.
2. The relationship between the PSRP digital strategy and DFID’s new digital policy needs to be clarified. (ACTION: PSRP and DFID, to be concluded by end June 2016).
- Completed: PSRP now use an organizational communications platform called ‘basecamp’ which acts as a central hub for communications between disparate consortium partners and a way to keep track of various outputs and important events. Experience thus far suggests a marked improvement.
    - PSRP have also set up a list-server email communications system that helps them keep in regular contact with external partners.
    - The PSRP Website is being redesigned following internal and external review of accessibility. This involves thematic summary pages and a comprehensive and user-friendly publications database. This database to be linked into a new blog feature highlighting key policy takeaways of all publications (To be complete by end of March)
    - PSRP to begin monitoring website and social media usage data to evaluate effectiveness of changes. (baseline data gathered by 17/02/2017)
3. Edinburgh to test Duty of Care arrangements and ensure they are operating appropriately at all levels within PSRP. PSRP to examine best practice from similar research consortiums e.g. SLRC and JSRP (ACTION: PSRP to review Duty of Care Arrangements by April 2016, subject to conditions in the field).
Completed: PSRP undertook a full review of duty of care and safety and security procedures. Although they were found to be sufficient, the process still proved to be an opportunity for cross-programme lesson learning and a legal review of contractual obligations between parties was undertaken. Shortcomings identified during the 2015/16 AR process were found to be an exception. Nonetheless, procedures have been tightened up and awareness of them amongst partners increased which should mitigate future risk.

ANNEX 2: Summary of risk matrix / Risk Category
Output 1 – High quality, relevant, timely and reliable research products on political settlements
Risk Category	Probability	Impact		Management/mitigation
Unstable working environment Medium High Some risk in Nigeria and to a certain extent Nepal, also highly relevant for case study work in DRC, Afghanistan and Ethiopia. Duty of Care in place and tested.
Research fails to provide applicable evidence-base to inform policy Low High Inter-programme learning a priority. Participation at DFID conflict cadre conference aimed at assuring relevance and responsiveness. / Research fails to achieve high/ international quality standards Low Medium Internal peer review mechanism is in place; In-programme research assessment against Research Excellence Framework quality standards.
Non-level playing fields between resources and attention given to work streams Medium Low Regular monitoring at programme level to summarise achievement and ensure relevant balance between work streams. RVI continued involvement in internal and external research uptake events.
Overall risk assessment of risk category 1: LOW
Output 2: Enhanced research impact/capacity, particularly in Global South
Limited interest/willingness for gender equity, policy engagement and research uptake	Medium		High		Continued involvement with United Nations and World Bank. Risk is still low purchase of ‘political settlements’ concept outside of the UK.
Research does not have any impact on potential users	Medium		High		Considerable in-country engagement to ensure uptake (using the ‘practice lab’ approach)
Research does not have any discernible impact on policy makers	Low		High		Research uptake strategy in place and working, international uptake is good. Research is increasingly being utilised by key stakeholders.
Capacity building challenges with recruited Southern researchers	Medium		Medium		Skype used where attendance not possible. Continued exchange with Southern-based researchers actively pursued

Overall risk assessment of risk category 2: MEDIUM
Risk Category 3: Risks related to programme governance and management
Significant delay in project implementation	Medium	Medium			Programme management increases output monitoring. Reporting density lowered, reporting quality increased. Amber-rated projects closely followed.
Fraud such as misuse of programme funds	Low	Medium			Regular quarterly financial reporting, detailed monitoring, requirements to set-up traceable expenditure systems ensuring compliance with the Bribery Act
Underperformance by any sub-contractor and/or breakdown of relationship between University of Edinburgh and any of its sub-contractors	Low	High			Regular dialogue with sub-contracted parties, regular reporting and detailed monitoring against set milestone targets. Red-Amber-Green traffic light system is working well.
Inability to retain key programme personnel	Low	Medium			Level of involvement by all partners and key persons remains high
Changing priorities from DFID and/or other donors active in this research area	Low	High			Monitoring plans in place; regular discussion with DFID and other donors; Proactive engagement with DFID is key programme task.
Non-compliance with legislation, e.g. Companies Act, Taxes Acts, Health & Safety Act, Bribery Act	Low	High			External Audits; Staff training; Advice from central University of Edinburgh resources if needed; close management of PSRP by UoE structures
Overall risk assessment of risk category 3: LOW
Risk Category 4: External environment
Ongoing violent conflict and physical safety concerns for researchers	Medium		Medium	Particularly DRC and Afghanistan. Duty of care procedures in place, programme partners have processes of ethical approval, which also concerns safety issues. close monitoring in place.
Direct impact of natural disasters on research, dissemination	Low		Medium	Traffic light system management to address
Unfavourable political environment hampers field research, dissemination	High		Medium	Dissemination activities closely monitored. Management structures of all partners do security assessments before publications, events and research meetings.
Climate change and policy engagement	Low		Low	Climate change could shift policy-maker priorities towards managing associated climate crises. Hold regular discussion with DFID and other key stakeholders to keep abreast of any significant policy change
Environmental risks arising from the research	Low		Low	Work closely with the Department of Sustainability and Social Responsibility. Communication is done electronically, travel and how to minimise environmental impact part of regular reporting.

Overall risk assessment of risk category 4: MEDIUM

ANNEX 3: PSRP publications

Name	Type		Remark
Project 1.1 – Conceptualising Project
Pospisil, ‘UN Review Processes: Politics and international state- and peacebuilding’, PSRP Briefing Paper 09		Briefing
PSRP/GJA Summer School, ‘Inclusive Political Settlements: the Theory and Practice of Transforming Conflict’, 20-22 June 2016, University of Edinburgh		Summer School
Bell, 2016, ‘International Law, the Scottish Independence Debate and Political Settlement in the UK’, in the forthcoming A. McHarg, T. Mullen, A. Page, and N. Walker (eds.), The Scottish Independence Referendum: Constitutional and Political Implications, Oxford: Oxford University Press.		Article	Additional output
Bell, 2016, ‘Political Settlement and the New Logic of Hybrid Self-determination’, in the forthcoming H. Patrick Glenn and Lionel Smith (ed.), Law and the New Logics’, Cambridge: Cambridge University Press.		Article
Project 2.2 – Armed Actors and Public Authority
Verweijen: ‘A Microcosm of Militarization: Conflict, governance and armed mobilization in Uvira, South Kivu’	Report
Vogel & Musamba, ‘Recycling Rebels? Demobilization in the Congo’, PSRP Briefing Paper 11	Briefing		Additional output
Vlassenroot, Mudinga, Hoffmann: ‘Contesting Authority: Armed Rebellion and Military Fragmentation in Walikale and Kalehe, North and South Kivu.	Report
Cuvelier, Bashwira: ‘Women, Conflict and Public Authority in the Congo’, PSRP Briefing Paper 13/RVI Usalama Project Briefing	Briefing		Additional output
Seminar ‘Electoral Dynamics in the DRC: Socio-Economic and Security Dimensions’, RVI in cooperation with the Egmont Institute, Brussels, 7 June 2016	Workshop		Additional output
Verweijen: ‘Stable Instability: Political Settlements and Armed Groups in the Congo’, PSRP Report/Usalama Project Report	Report
Mathys, Vlassenroot: ‘ “It’s not all about the land”: Land disputes and conflict in the eastern Congo’, PSRP Briefing Paper 14/RVI Usalama Project Briefing	Briefing
De Vries, Hugo, 2016, ‘The Ebb and Flow of Stabilization in the Congo’, PSRP Briefing Paper 08.	Briefing
Project 3.1 – Peace Processes, Bargaining, Inclusion and Political Settlements
Jamar, ‘Escalating Conflict in Burundi: The Challenges of Overcoming Radicalisation’, PSRP Briefing Paper 10	Briefing
Bell & Pospisil: ‘Negotiating Inclusion: The Space of the Formalised Political Unsettlement’, Journal of International Development (forthcoming)	Article
Bell and Zulueta-Fülscher: ‘Sequencing Peace Agreements and Constitutions in the Political Settlements Process’, PSRP Report/IDEA Policy Paper No 13	Report
Bell: ‘Symposium on the Colombian Peace Talks and International Law: Lex Pacificatoria Colombiana: Colombia’s Peace Accord in Comparative Perspective’, AJIL Unbound (November 2016)	Article
Bell: ‘The Fabric of Transitional Justice: Binding Local and Global Political Settlements’, forthcoming in Bell (ed.), ‘Transitional Justice’ (Routledge, 2017); available as SSRN Edinburgh School of Law Research Paper No 22	Article
Bell: ‘Bargaining on Constitutions: Political Settlements and Constitutional State-building’, in Global Constitutionalism (forthcoming, 2017), special issue on political settlements, now available together with four additional papers as SSRN Edinburgh School of Law Research Paper No 23 (2016).	Article, edited volume
Edinburgh Dialogue on Post-Conflict Constitution Building in cooperation with International IDEA, ‘Sub-state constitutions in fragile and conflict-affected settings;, 9-10 December, Edinburgh	Workshop
O’Rourke: ‘Gendering Political Settlements: Challenges and Opportunities’, Journal of International Development (forthcoming)	Journal
Project 4.1 – Conceptualising Gender
Witt & Balfe: ‘Civil Society, Conflict Transformation and Peace Building: A Christian Aid Ireland Learning Paper’, PSRP Working Paper No 4	Working Paper
Ní Aoláin: ‘Gendering the Law of Occupation’, PSRP Working Paper No 5	Working Paper
Brown & Ní Aoláin: ‘Through the Looking Glass: Transitional Justice Futures through the Lens of Nationalism, Feminism and Transformative Change’, International Journal of Transitional Justice (9:2015), 127-149	Journal		Additional output
Hawthorne-Steele, Moreland & Rooney: ‘Transforming Communities through Academic Activism: An Emancipatory, Praxis-led Approach’, Studies in Social Justice, 9:2	Journal		Additional output
Ní Aoláin: ‘The War on Terror and Extremism: Assessing the Relevance of the Women, Peace and Security Agenda’, International Affairs, 92:2, 275-291	Journal		Additional output
Rooney: Grassroots Transitional Justice Training Manual	Training Manual
Ní Aoláin: ‘The Relationship of Political Settlement Analysis to Peacebuilding from a Feminist Perspective’, Peacebuilding, 4:2, 151-165	Journal
TJI Summer School on Transitional Justice: ‘Women and Political Settlements: International, Regional and Local Approaches to Peacemaking’, 27 June to 1 July 2016, Ulster University Belfast	Summer School
‘Toward a Framework of Transitional Justice in Israel/Palestine’, Summary Lessons Paper from Workshop with Zochot, Christian Aid and TJI, PSRP Working Paper No 6	Working Paper
Valji, ‘Security Council resolution 2242 (2015) on Women, Peace and Security: Summary of critical elements and progress’, PSRP Briefing Paper 06	Briefing
Project 4.6 – Gender and Violence
Ní Aoláin & McWilliams: ‘Moving Slowly to Regulate and Recognize: Human Rights Meets Intimate Partner Sexual Violence’, TJI Research Paper No 16-10.	Article
Project 5.1 – Nepal
Neelankantan, Ramsbotham, Thapa: ‘Peace, Power and inclusive change in Nepal: Political Settlements in Practice’, PSRP Report/ACCORD Spotlight	Report		Overlap with project 1.2
Project 5.6 – Stabilisation
Gardner & El-Bushra: ‘The impact of war on Somali men and its effects on the family, women and children’, PSRP Briefing Paper 12/2016	Briefing		Additional output
Hagmann: ‘Stabilization, Extraversion and Political Settlements in Somalia’	Report
Project 6.1 – Conceptualising Transformation
PSRP Roundtable at the BISA conference – ‘Peace and Justice: Measuring Success?’, chaired by Jan Pospisil, contributors C. Bell (PSRP), Tobias Kelly (SPS Edinburgh), Jonathan Joseph (Sheffield), Edinburgh, 15 June 2016	Conference
Workshop ‘Local, Regional and International Perspectives on Political Settlement and Transition’, TJI in cooperation with Oñati International Institute, 14-15 July 2016, Oñati	Conference
Zulueta-Fülscher, Bell et al: ‘Constitution-Building in Political Settlement Processes: The Quest for Inclusion’, Discussion Report, June 2016	Report		Additional output
Peace agreement database roundtable in Edinburgh, 3-8 December 2016, University of Edinburgh	Workshop		Planned for Q9, overlap with project 6.2
Project 6.2 – Measuring Transformation
PSRP Workshop, ‘Political settlements in fragile and conflict-affected states: measuring governance trajectories’, organised by ISS, University of Denver, 31 May to 1 June 2016	Workshop		Overlap with project 6.1