## Sheet1
PROJECT NAME | School of Oriental and African Studies (SOAS) Research: Fair Trade, Employment and Poverty Reduction
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 (August 2010) | Milestone 2 (August 2012) | Target (August 2013)
Poverty reduction policies, company decisions and certification standards are shaped by high quality evidence of the impact of agricultural produce certification on poverty | Evidence of the impact of certification schemes on rural poverty and wage employment disseminated to stakeholders (donors, certification bodies, business) | Planned
Achieved
Source
| Impact Indicator 2 |  | Baseline | Milestone 1 | Milestone 2012 | Target (August 2013)
Planned
Achieved
Source
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 (August 2010) | Milestone 2 (August 2012) | Target (August 2013) | Assumptions
Relevant stakeholders have a better understanding of comparative benefits and disadvantages (especially for women) - from a labour market and poverty reduction perspective - between special certification and non-certified production | Degree of willingness of relevant stakeholders to use evidence in their decisions | Planned |  |  |  | 4 examples of companies, certification bodies, Government and donors indicating their intention to adapt policy, programming or organisational arrangements as a result of this research
Achieved
Source
| Outcome Indicator 2 |  | Baseline | Milestone 1 (August 2010) | Milestone 2 (August 2012) | Target (August 2013)
Planned
Achieved
Source
Primary case study data (quantitative and qualitative), national representative data (e.g. Demographic and Health Surveys and Living Standards Measurement Surveys)
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 692958 |  | 0 | 0 | 607475 | 100%
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (2009) | Milestone 1 (August 2010) | Milestone 2 (August 2012) | Target (August 2013) | Assumption
Appropriate research methodology to assess effectiveness of certification schemes on poverty reduction among women and men is available | Degree of access Research Team have to existing knowledge on poverty and certification | Planned |  | Research Team complete broad review of literature | Research Team update broad review of literature | Positive peer review of literature on methodology as part of final report
Achieved
Source
| Output Indicator 1.2 |  | Baseline (2009) | Milestone 1 (August 2010) | Milestone 2 (August 2012) | Target (August 2013)
| Extent of progress with developing fieldwork methodology | Planned |  | Fieldwork methodology for research in Ethiopia compiled | Fieldwork methodology for research in Uganda compiled | Positive review of field report as part of final report
Achieved
Source
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline (2009) | Milestone 1 (August 2010) | Milestone 2 (August 2012) | Target (August 2013)
25% |  | Planned
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | n/a |  |  |  |  | Low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
158381
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (2010) | Milestone 1 (August 2010) | Milestone 2 (August 2012) | Target (August 2013) | Assumptions
Longitudinal assessment completed of the comparative benefits and disadvantages (especially for women) - from a labour market and poverty reduction perspective - between special certification schemes and non-certified production | Extent of progress of data collection | Planned |  | Research Team create Ethiopia sex disaggregated data set | Research Team create Uganda sex disaggregated data set and compile main data set | Research Team complete sex disaggregated data set with methodological and technical notes (public availability subject to reasonable embargo) | There is continued political stability in Ethiopia following the death of President Meles Zenawi in August 2012
Achieved
Source
| Output Indicator 2.2 |  | Baseline (2010) | Milestone 1 (August 2010) | Milestone 2 (August 2012) | Target (August 2013)
| Degree of relevance of research findings to the research question | Planned |  | Research Team agree draft research findings internally | Research Team agree research findings to test publically | Peer validation of research findings through academic conferences and workshops
Achieved
Source
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline | Milestone 1 (August 2010) | Milestone 2 (August 2012) | Target (August 2013)
60% |  | Planned
Achieved
|  | Source |  |  |  |  | RISK RATING
Low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 493578 |  | 0 | 0 | 493578 | 100%
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (2009) | Milestone 1 (August 2010) | Milestone 2 (March 2013) | Target (August 2013) | Assumptions
Research results and policy messages disseminated to donors, certification bodies and business | Degree of accessibility and quality of research findings to decision makers | Planned |  | Research Team develop Dissemination Strategy | Advisory Group/Steering Committee to comment on dissemination strategy | Research Team implement Dissemination Strategy
Achieved
Source
| Output Indicator 3.2 |  | Baseline (2009) | Milestone 1 (August 2010) | Milestone 2 (August 2012) | Target (August 2013)
Planned
Achieved
Source
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline (2009) | Milestone 1 (August 2010) | Milestone 2 (August 2012) | Target (August 2013)
15% |  | Planned
Achieved
|  | Source |  |  |  |  | RISK RATING
Low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 41000 |  | 0 | 0 | 41000 | 100%
INPUTS (HR) | DFID (FTEs)