Business Case
Summary Sheet

Title: The Caribbean Development Bank’s (CDB) Special Development Fund (SDF 9) for 2017 – 2020
Project Purpose: To contribute to economic and social development in the Caribbean’s poorest countries through CDB investments in core sectors that contribute to the progress of the Caribbean Sustainable Development Goals (SDGs): transport, education, water and sanitation, agriculture, climate change/environment and inclusiveness – leave no one behind, jobs and prosperity.
Programme Value: Up to £18 million, including up to £4.5 million as a performance based tranche to be triggered in 2020 based on positive progress (Performance Agreement with CDB)		Country/ Region: Caribbean
Project Code: 204675	Start Date: January 2017	End Date: 31 December 2020
Overall programme risk rating:	Moderate
Quest Number:	5451862

Intervention Summary

What support will the UK provide? As part of delivering on the UK’s Caribbean priorities on growth, stability and prosperity, DFID will contribute up to £18 million (including up to £4.5 million performance based tranche for 2020) towards the replenishment of the Special Development Fund 9 (SDF 9 for 2017-2020). The SDF is the Caribbean Development Bank’s (CDB) concessional mechanism (soft loans below market rates, grants and technical assistance) supporting the most vulnerable and poorest people in the Caribbean region.

How will the intervention be delivered, who will the funding go to and for what? The SDF supports projects with a focus on basic social infrastructure such as roads and electricity, vocational training centres and schools, agriculture and climate change resilience (e.g. flood and hurricane protection) as well as support to poverty reduction through its Basic Needs Trust Fund (BNTF), which has focus on local vulnerable communities and gender equality.

Regional member countries with an income per capita of less $10,000[1] receive country allocations based on a formula that takes account of needs and performance. Countries with an income per capita above $10,000[2] can only benefit from regional projects. Funds are lent at 1% with the maturities dependant on the income of the country. SDF has grant funding “set asides” for Haiti ($45 m), the Basic Needs Trust Fund (BNTF $45 m), disaster responses ($3 m) and regional collaboration ($4 m).
[1] ODA eligible; grants and soft loans: Haiti (grants only) Belize, Dominica, Grenada, Guyana, Jamaica, St. Lucia, St. Vincent and the Grenadines and Suriname.
[2] Non-ODA: Anguilla, Antigua and Barbuda, Bahamas, Barbados, British Virgin Islands, Cayman Islands, St. Kitts and Nevis, Trinidad and Tobago, Turks and Caicos Islands.

The CDB is responsible for policies relating to the SDF and overseeing project design and delivery with the beneficiary countries responsible for project design and delivery. The CDB also manages the Bank’s ordinary lending (Ordinary Capital Resources - OCR, which is provided at near market rates) and a number of trust funds.
Why is UK support required? The Caribbean region is struggling with slow growth and high vulnerabilities to economic and natural shocks. Although poverty has gone done, the modest improvements from 24% to 21% for overall poverty and from 12% to 11% for indigence (excluding Haiti) reveals little change in close to a decade. Growth has been held back by high levels of public debt, driven by unsustainable public spending and falling competiveness. There is a very significant infrastructure gap in the Caribbean, estimated at £3.5 billion by the CDB. Aging, inefficient, inadequate, broken or missing infrastructure due, for example to natural disasters, is a major constraint to doing business. Social investments to poor communities also limit inclusiveness. The governments in the region recognise the need for action, but lack the financial and human resources to implement the reforms needed to stabilise their economies and to promote economic growth. Most of the CDB member states, including some of the poorest such as St Vincent, Suriname, Dominica, St Lucia, have limited access to grants and concessional financing available to very poor countries through the World Bank (WB), the Inter-American Development Bank (IDB)[3] or the European Union (EU – European Investment Bank - EIB).
[3] IDB only has country programmes in Haiti, Bahamas, Barbados, Guyana, Jamaica, Suriname and Trinidad and Tobago.

Why channel support through the CDB? The CDB’s strongest comparative advantage is that it the only MDB, other than the EIB, which is active in the smallest and most vulnerable island states in the Caribbean, focusing on climate smart infrastructure and education. CDB has also developed expertise in disaster preparedness and disaster relief. The SDF, with its focus on the poorest borrowing countries and vulnerable communities, complements DFID’s bilateral programme in areas such as infrastructure, economic management, climate change and community resilience at a scale that would require a much larger DFID bilateral staffing presence to deliver.

The Bank is contributing to the UK National Security Council vision of long-term economic stability in the Caribbean as well as the UK Aid Strategy on prosperity through promoting inclusive economic growth by investing in poor and vulnerable communities, small businesses, an enabling environment for private sector development and trade; and resilience to disasters and climate change. As part of HMG’s re-engagement with the Caribbean, DFID is also using CDB to implement infrastructure projects (roads, bridges and ports), in particular the £300 million UK Caribbean Infrastructure Fund (UK CIF). DFID’s development support through the CDB, including the SDF and UK CIF benefits both the Caribbean, by promoting growth and stability, and UK interests through increased investment and export opportunities when the economies and trade grow. DFID uses CDB to deliver on the UK’s development objectives in the Caribbean and is part of a longer-term objective to change from aid to investments and trade.

What are the expected results? The CDB is expected to deliver both direct development results through the SDF 9 and internal reforms agreed as part of the SDF replenishment negotiations. These reforms, if implemented as planned, will strengthen its efficiency and effectiveness leading to improved performance during the SDF 9 period and beyond. The Bank has outlined the expected development outputs and results offer for the SDF 9 period 2017-2020[4]. Examples include: 222 km of roads built or upgraded, 198,900 students benefiting from improved educational facilities and provision, 285 small businesses benefiting from credit, 248,768 beneficiaries of community citizen security interventions and 18,400 households with access to improved sanitation and water supplies (Refer to page 12 for further details on results). As our core contribution is at least £13.5 m, with an additional £4.5 m linked to performance, our attribution would be around 7.5% of the expected results.
[4] Source: Replenishment of the Resources of the Special Development Fund Unified (SDF 9) Resolution and Report of Contributors, draft May 2016.

How will we determine whether the expected results have been achieved? As part of the SDF 9 replenishment, CDB and contributors revised the results framework covering 2017 – 2020, which includes both expected development results and indicators on operational and institutional efficiency. We use a selection of these indicators and the expected results from the framework, reflecting UK priorities, in our SDF 9 Logframe. There will be annual SDF 9 meetings and a Mid-Term Review (MTR) of the SDF 9 with a meeting convened halfway into the four-year SDF period which will provide the opportunity for donors to take stock of progress made and challenges facing CDB and the SDF and revise the programme if needed. (Refer to monitoring section page 46 and attached logframe).

What is the value for money assessment of the SDF 9? UK support to the CDB is a significant part of the UK’s engagement in the region. Our support to the SDF not only contributes, albeit on a small scale, to the Caribbean Sustainable Development Goals, it also is a factor in the UK’s wider relations with the region, particularly the smaller, poorer countries that have limited access to other MDBs and are benefitting from the CIF.

The SDF has been assessed in various reviews[5] as relevant and responsive to the needs in the Caribbean. CDB’s performance and capability are below those of most DFID-supported multilateral organisations. CDB was assessed as satisfactory by the 2011 Multilateral Aid Review and whilst making some progress since then, was assessed in the 2016 Multilateral Development Review (2016 MDR) as satisfactory against UK objectives but weak on organisational strengths, with the biggest gaps being in value for money, programme efficiency and particularly in transparency (not yet a member of IATI). The most recent SDF and capital subscription projects failed to fully achieve their planned outputs.
[5] For example: the 2016 independent Multi-Cycle Evaluation of SDF 6 – 7 for 2005 -2012, SDF 8 MTR 2015 and CDB’s 2016 Haiti Evaluation.

The UK has pushed hard over the last few years for CDB to improve its performance. The Bank has strengthened its internal structures and on staffing and the direction of travel is positive, but it is too early to see any substantial improvement in operational delivery. This is partly the result of weak capacity in the region, where national governments, civil society and the private sector have financial and human resource constraints.

DFID’s SDF 9 Delivery Plan for the up to £18 million contribution includes further details how we engage with the Bank on its under-performance, including slow delivery, low disbursements and lack of progress in priority areas such as regional collaboration and private sector development. Ministers also decided to include a performance related tranche (up to $4.5 m), with the last year’s DFID payment (1/4 of pledge) being subject to CDB improving its performance and joins the International Aid Transparency Initiative (IATI) during the SDF 9.

What are the key risks to the success of the SDF 9? A major external risk is the continued weak capacity at country level to implement projects. The Bank has an institutional action plan to improve its performance and mitigate the delivery and operational risks and we will monitor its progress closely. We assess that there are moderate residual risks that slow delivery and weak monitoring of programmes could lead to reduced development outcomes (Further details on risks are provided on page 37).

Strategic Case

A: Context - Slow growth, vulnerability and poverty remain challenges

The Caribbean countries, most of them small island states, share a number of characteristics that pose special development challenges. The region still struggles with high vulnerability to economic shocks and to natural disasters, as exemplified in the devastation caused by tropical storm “Erika” in Dominica in 2015, and climate change. The region’s growth and development is also held back by high communication, energy and transportation costs, and disproportionately expensive public administration and infrastructure due to the small populations. The small island developing states depend heavily on tourism, struggle to diversify their productive sectors and have little to no opportunity to create economies of scale.

The long-term trends were exacerbated by the 2008 financial crisis and ensuing global economic slowdown which has affected the region as demand for tourism (the primary foreign exchange earner) fell dramatically. Tourism arrivals across the region have started to recover since 2014, but new investment and employment creation in the sector is limited. Unemployment, poverty and crime are causes of concern, particularly with regard to the youth. Over the last five years, regional growth has been either negative (2009-2011) or marginally positive (2012-2015) - well below rates seen in other middle income countries. Being small and open economies, most Caribbean states are highly dependent on imports while having a narrow and undiversified export base rendered uncompetitive by low productivity, high input costs and a regulatory framework that inhibits private sector development.

There is a very significant infrastructure gap in the Caribbean, estimated at £3.5bn by the Caribbean Development Bank. Years of under-investment in infrastructure are holding back the Caribbean’s ability to compete in global markets, reduce poverty and promote sustainable growth. Aging, inefficient, inadequate or missing infrastructure is a major constraint to doing business, resulting in lower productivity and growth. This has direct impacts on competitiveness, particularly in key industries such as tourism and agriculture which typically provide employment opportunities for women and low skilled workers. The lack of investment in climate resilient infrastructure means that when natural disasters occur, existing infrastructure struggles to cope, particularly with the effects of hurricanes. The infrastructure gap harms the ability of countries to grow in the short term and prosper in the longer term, but also places them at greater risk when natural disasters occur and prolongs the time it takes for an economy to recover.

Table 1: Debt/GDP Ratios in the Caribbean

The governments in the region also struggle with high levels of debt and constraints in public expenditure. The Caribbean is one of the most highly indebted regions of the world[6] and still struggling from the 2008 financial crisis. As noted in the table above, countries such as Barbados, Jamaica, Grenada and others are struggling with high debt/GDP ratios.
[6] In 2015, the Economic Commission for Latin America and the Caribbean (ECLAC) reported that in 2013, five Caribbean countries were among the twenty most indebted countries in the world. The debt to GDP ratio for the eight territories of the Eastern Caribbean Currency Union (ECCU) stands at an average of 89%.

As a result of slow growth, the high costs of doing business, fiscal constraints and high debt burdens, the Caribbean region did not meet its poverty reduction target by 2015 and vulnerability remains an issue. However, it did make some progress. Aggregated Caribbean data for the period 2006 to 2014 shows a decline in the proportion of the population in poverty based on income from 54% to 44% (including Haiti) and from 24% to 21% (excluding Haiti). For the same period, there was also a decline in the proportion of the Caribbean population below the indigence line (measured as food poverty) from 41% to 22% (including Haiti) compared with 12% to 11% (excluding Haiti). The movement from 24% to 21% for overall poverty and from 12% to 11% for indigence (excluding Haiti) reveals little change in close to a decade.[7]
[7] Poverty data reported in Caribbean Development Bank Country Poverty Assessments, except for Jamaica.

Table 2: Poverty and Human Development

As noted in table 2 above, the situation was more positive for the non-income human development poverty reduction indicators of the MDGs. For example, enrollment rates at the primary school level continued to improve in 2015, reaching around 90% for both female and male enrolment although they are still just below the 2015 target values of 95%.

CDB’s response to the Caribbean development challenges
CDB focuses on infrastructure, climate change resilience, education and support to communities in response the regional challenges described above on inclusive growth and poverty reduction. CDB’s strategy for the period 2015 - 2019 responds to the development challenges in the Caribbean as illustrated in the following diagram (Diagram 1):

The Bank mainly covers the English-speaking Commonwealth countries and UK Overseas Territories, most of them smaller island states, but has a growing engagement in Haiti, the poorest and most vulnerable country in the region. In Haiti, the Bank works closely with other institutions such as the World Bank, IDB and the UN agencies with a focus on education and productive agriculture, and it focuses on two areas where it has strong sector experience: support to education and community based infrastructure.
The Bank is an important source of development finance and technical assistance in the region. As an indigenous regional institution, the Bank is viewed by regional partners as a close and valuable development partner. The CDB provides around 16% of all concessional lending to the whole region. The table below gives an illustration below shows official ODA spend for 2012 - 2013 to some of the West Indies countries, including Jamaica, which together with Haiti receives the major share of official ODA to the Caribbean.
The Bank is a major source of concessional financing for some of the Caribbean countries and UK Overseas Territories. CDB’s focus in supporting achievement of the SDGs is on infrastructure, industry and education (over $500 million of cumulative loans), with more modest engagement in agriculture and climate change resilience (over $250 million) as well as more direct contributions to poverty elimination through its Basic Needs Trust Fund (BNTF) and gender equality.

Graph 1: Top 10 West Indies Donors 2012-2013

TOP 10 WEST INDIES DONORS 2012-2013
(ODA spend in US$ millions
* ODA spend 2012-2013, based on the of the Top 10 Donors compiling of the following countries : Antigua and Barbuda, Belize, Dominica, Jamaica, Granada, Saint Lucia, St Vincent and the Grenadines, Suriname. It does not include Haiti, which receives substantial aid due to fragility status and the earthquake in 2010.

Graph 2 below presents data on the country allocations of CDB funding (broken down by Gross ODA loans and grants) for the previous three years of available data. It is clear that there is a degree of prioritisation within the region and Haiti received by far the largest amount of grants and received the second highest level of funding in total behind Jamaica.

In addition, Saint Lucia and Belize receive a large amount of funding, despite their very small populations, due to their higher poverty. The large grant element to Haiti is consistent with DFID’s commitment to FCAS, as it is the only FCAS in the region.

Graph 2- 2012-2014 financing by type
Source: OECD DAC

B: Why is the UK supporting CDB?

UK policies and programme engagement with CDB

CDB’s role in the region is aligned with the UK’s ODA Strategy particularly the Global Prosperity objective through its investment in infrastructure (such as transport, energy), agriculture and industry. CDB also contributes to helping the most vulnerable through its support for education, resilience, and in crisis response through support for projects such as sea defences and flood protection. CDB is part of the UK’s development objectives to the Caribbean region, which has the following priorities:

- Supporting economic growth through private sector development to create business and job opportunities and increase exports to regional and global markets;
- Working with Caribbean countries to reduce violent and organised crime and to create safer communities;
- Improving the region’s ability to deal with and recover from the impacts of climate change and natural disasters.

DFID’s support to the Bank and SDF contributes to DFID’s Business Plan through CDB actions to achieve the SDGs, enhance wealth creation and strengthen tackling climate change and gender equality (improve the lives of girls and women). DFID’s support to the CDB SDF is in line with the UK’s Gender Equity Act. DFID has considered the impact of the SDF on gender equality, which includes a mixture of project that has expected moderate to limited impact on gender equality for infrastructure programmes and in some cases significant impact for, often smaller, projects targeted directly to women and girls through the SDF community support. The section on gender below sets out our analysis and outlines the areas where we will continue to push CDB to sharpen their focus and impact (Refer to gender section 23).
Our CDB shareholding role (10% shareholder) and responsibilities are also in line with UK’s guidelines on “Overseas Security and Justice” and the Public Sector Equality Act, as the Bank has policies and procedures that follow international best practice and obligations in respect of race, disability and gender. We use the CDB Board to voice concerns about human rights, alleged discrimination, social and economic inclusion and environmental concerns as part of the broader social and environmental safeguards for programmes and projects over the full project cycles.

CDB recognises the obligations of its member countries under various United Nations Security Council Resolutions to take measures to prevent the financing of terrorism. The Bank undertakes to use reasonable efforts, consistent with its Charter and policies, including those pertaining to combating the financing of terrorism, to ensure that funds provided under any arrangement are used for their intended purposes and are not diverted to the financing of terrorism. Nor are they used directly or indirectly, to provide support to individuals or entities associated with terrorism. This is in line with the other MDBs and we use our role at the CDB Board to scrutinise the Bank and ensure accountability and transparency. CDB has strengthened its audit and integrity functions over the last couple of years. DFID has done a Central Assurance Assessment of the CDB (2015), but we have not specifically assessed its specific procedures on financing of terrorism.

In September 2015, the UK Prime Minister announced the creation of a new £300 million UK Caribbean Infrastructure Fund (CIF) which collaborates with CDB in support of infrastructure in the Caribbean such as roads, bridges and ports to help drive economic growth and development across the region. This substantial new grant funding for the period 2016 – 2020 will make CDB a more important development partner for the UK in the Caribbean and for the region generally over the coming years. As CDB has capacity constraints, DFID is providing additional technical capacity as part of the CIF and DFID has four staff currently seconded into the Bank to support on implementation and supervision. The CIF focusses only on physical infrastructure and it uses the Bank’s normal processes, systems and structures for its implementation. The main reason for the CIF was to assist the Caribbean to invest in needed infrastructure that would not be feasible to implement due to fiscal and budgetary constraints in the targeted ODA eligible countries.

SDF results for the period 2013 – 2016

In early 2013, DFID pledged £36 million for the current SDF 8 for 2013 – 2016. The amount included a £6 million performance tranche on results management. DFID only provided half of the tranche as CDB did not meet all the criteria, which meant that the total UK contribution became £33 million. As demonstrated in the table below, which provides some examples, CDB (including the SDF) delivered a wide range of development outputs for the period 2013– 2016:
Table 3: CDB/SDF results 2013 - 2016

However, CDB continues to have capacity constraints. In the Multilateral Aid Review (2016 MAR), it was noted that CDB had started to build up a results culture and improved on gender, climate change and resilience, but it needed to make further progress on these and to give more attention to programme delivery especially in complex and fragile situations such as Haiti. The Bank also needs to demonstrate better value for money in programming and in institutional efficiency. The main outcome from the MAR is that the Bank now needs to focus on programme delivery as it struggles to complete projects within expected time-frames, which has cost implications and delay the expected development outcomes.

The Bank has not achieved its targets on regional integration and private sector programming, which was part of DFID’s Performance Improvement Plan (PIP) for CDB during 2013 – 2015. The DFID PIP 2013-2015 noted that CDB had improved its lending volumes over the period, but the Bank still struggled with disbursements due to slow delivery. As a result, the Bank did not meet all of the PIP targets. This was also was noted in our annual reviews as DFID has scored the ongoing SDF 8 (2013 - 2016) as “B – Outputs moderately not met” for three years in a row and the PCR for the GCI (General Capital Increase project) scored the project as a “C – Outputs substantially not met”. Slow delivery leads to slow disbursements and more costly projects as many projects need to be extended, typically two or three years on top of the normal five-six year plans. Our assessment is that the Bank is on the right trajectory in regards to improvements, but still likely to continue to struggle with capacity and performance over the coming years if it does not focus its programming. We will work with the Bank to consider further options to focus its programming and strengthen capacity to deliver. As noted in the risk section (page 37) we assess the residual risk after mitigations for development outcomes for the SDF 9 not to be met as moderate.

C: Impact and outcomes we expect to achieve
The Special Development Fund (SDF) offers loans with long maturities and grace periods and low interest rates (below market rates). All members of the Bank, including the UK, are required to contribute to SDF. However, the actual amount is voluntary but there are expectations for larger non-regionals such as Canada, the UK, Germany and Italy to retain their shares of the total volume for each cycle.
During each SDF cycle negotiations, contributors and the Bank agree on the priorities and issues to address. Over the years, we have pushed for a stronger emphasis on poverty reduction directed at the poor and low-income groups. In recent cycles, we have also urged the SDF to give significant support to themes such as environmental sustainability and advancing the climate change agenda and building capacity and enhancing governance in beneficiary countries. We have also strongly encouraged the Bank to improve on regional cooperation and integration and enhancing the Bank’s development effectiveness. This is now part of the Bank’s focus, albeit not yet demonstrated in real increases in programming.
The total volume of the currently ongoing SDF 8 is $348 million (with 206 m as contributions) for 2013 – 2016. During the SDF 9 replenishment, CDB suggested scenarios that included substantial increases for the SDF 9 up to $431 million. The UK, Canada and Germany strongly pushed back, noting that the low performance of the Bank, and the fact that the exchange rates for the Sterling, Euro and the Canadian Dollar have gone down substantially compared to the US$,. CDB therefore revised the volume during the replenishment. The Bank has agreed a total budget of $355 million. The agreed SDF 9 contributions would represent a decrease from just under $240 million to around $167 million for the period 2017 – 2020.
The Special Development Fund 9 Themes and Priorities
Contributors agreed that the SDF 9 priorities and objectives operational programme should take account of the findings of the Mid-Term Review (MTR) of SDF 8 and the Multi-cycle Evaluation of SDF 6 and 7. We approved the following themes for the SDF 9 replenishment:

- Supporting the achievement of SDG targets relevant to the Caribbean and specific to SDGs on poverty, food security, economic growth, climate change, education, energy and water and sanitation;
- Building resilience and promoting environmental sustainability; and
- Promoting regional cooperation and support for regional public goods (RPGs).

These themes will be supported by the cross-cutting areas of gender equality, good governance, (in full alignment with SDGs 5 and 16, respectively) and, as in SDF 8, environmental sustainability. As part of the SDF 9 replenishment process, CDB, the UK and other contributors agreed to resource the SDF 9 programme at a level that is consistent with the ambitions of the 2030 International Development Agenda (SDGs) with a focus on:

Continued support for community level infrastructure, poverty reduction and promoting equality and good governance, through additional funding for an enhanced Basic Needs Trust Fund (BNTF) programme from SDF 9 ($45m); Education and human development is the largest component, with substantial support also going to regional collaboration and coordination and basic services such as water and sanitation for vulnerable local communities.

Continuing targeted support for Haiti ($45 million), in close cooperation with development partners, with particular emphasis on education (44%), community-driven development 27%), disaster mitigating and resilience (26%).

Continuing support for disaster response, mitigation and rehabilitation, and for environmental sustainability, environmental risk management, adaptation to climate change and sustainable energy;

Spurring agriculture and rural development as means for creating rural employment, promoting food security and reversing environmental degradation;

Enhancement of the enabling environment for private sector growth through the development and effective implementation of a programme of support for creative industries, promotion of competitiveness, and training interventions for small and medium-size private enterprises; and

Support for regional integration, regional public goods and regional solutions to economic and social constraints.

SDF 9 expected programme results and outputs 2017 - 2020

The table below includes all expected results (outcomes in DFID’s Logframe) from programming in across the period 2017-2020. These results are the aggregated outputs from projects planned for completion and reporting on in the Bank’s Development Effectiveness Reviews over the SDF period.
For DFID’s SDF 9 Business Case Logframe, we use selected indicators based on the UK’s priorities from the Bank’s larger results framework. Key areas include inclusive growth, gender and climate change. We also measure outputs in key infrastructure sectors such as transport and energy plus the Bank’s overall efficiency in operations and administration (Refer to 33 for the economic appraisal of the expected results).

Table 4: SDF 9 expected results for 2017 - 2020[8]
[8] Source: Replenishment of the resources of the Special Development Fund Unified (SDF 9) Resolution and Report of Contributors on SDF 9
Indicators	Targets: expected results 2017 - 2020
Economic and social infrastructure development
1. Transport: Primary, secondary and other roads built or upgraded (Km)	222
2. Transport: Beneficiaries of road projects (number)	120,000
- of whom female	63,000
3. Sea defences/ landslip protection/ urban drainage (Km)	8
4. Water: Installed water capacity (cubic metres/day)	128,630
5. Water: Supply lines installed or upgraded (length of network in Km)	950
6. Water: Households with access to improved sanitation and water supply (number)	18,400
7. Communities: Beneficiaries of community infrastructure construction/ enhancement projects (number 0 % female)	125,780
Agriculture and rural development
8. Agriculture: stakeholders trained in improved production technology (number - % female)	2,600
9. Land improved through irrigation, drainage and/or flood management (hectares)	2,900
Education and Training
10. Classrooms and educational support facilities built or upgraded according minimum standards (number), of which	1,299
11. Teachers and principals trained/certified (number)	9,286
12. Students benefiting from improved physical classroom conditions or enhanced teacher competence, or access to loan financing (number plus % female)	198,900
Citizen security
13. Beneficiaries of community based citizen security interventions	248,768
14. Beneficiaries of youth at risk interventions (number - % female)	31,085
Environmental sustainability (climate change resilience, environmental management and disaster risk management)
15. Energy: Conventional or renewable power generation capacity installed (MW)	14
- of which renewable (MW)	8.5
16. Sustainable energy policy/legal/regulatory or capacity deficits addressed (number)	8
17. Energy savings as a result of EE/RE interventions (GWh)	15.9
18. Transmission or distribution lines installed or upgraded (length in Km)	130
19. Communities with improved capacity to address Climate Change and DRM (number)	8
20. National sector policies, strategies, plans or tools developed or implemented to improve capacity for climate resilience, conservation, rehabilitation or environmental management	16
Private sector operations and development
21.Value of credit made available to the private sector ($mn) (disaggregated by sector)	43
22. MSMEs benefiting from credit (number - % female)	280
23. Beneficiaries of mortgage programmes (number - % female)	194
25. Beneficiaries of TA interventions targeted at MSMEs	6,075
- of whom female beneficiaries	3,622
Governance and accountability
26. Financial institutions with enhanced capacity for credit delivery, business planning, or sustainability (number)	5
27. Economic management systems upgraded and public sector investment programmes supported (including budget, treasury, accounting, debt, revenue, and procurement)	10
28. Stakeholders trained in results focused Project Cycle Management or Public Policy Analysis and Management (number)	1,500
29. Systems/processes/instruments supporting evidence-based policymaking and MfDR strengthened (number)	7
30. Business climate and competitiveness enhancement projects implemented (number)	3
31. BMCs with increased capacity to undertake Public Private Partnership arrangements (number)	12
Regional cooperation and integration
32. RPGs created or strengthened (e.g. statistical capacity, quality standards, procurement, and debt relief) (number)	8
33. Certification or accreditation systems supporting the free regional movement of goods and persons, created, strengthened, or expanded (number)	6

SDF's total investment plans for 2017 – 2020

Contributors agreed on an overall programme level for SDF 9 of $355 million to be financed from internally generated resources within SDF of $132.4 million, agreed contributions of $166.6mn, and an allocation from the Bank’s OCR net income of $15 million, with an unallocated structural gap of around $41mn.

The total programme level for the agreed scenario includes 33.5% grants, earmarked for Haiti ($45 m), community support ($40 million to BNTF) regional public goods, disaster management and disaster responses and climate change initiatives. Apart from Haiti and community support, the grants are often blended with lending in most cases to respond to the assessed needs of the country and will be channeled through national governments, community organisations and privates sector.

The indicative programming allocations to achieve the SDF 9 priorities and objectives are set out in the table below.

Table 5 : Indicative programming for the SDF 9; 2017 – 2020
SDF 9 CORE THEMES ($ 000)	Grants		Loans	Total		%

BNTF 9	*40,000	-			40,000	11.3
Haiti	*45,000	-			45,000	12.7
Institutional Strengthening and / Education/Training	*12,000 / -	8,000 / 60,000			20,000 / 60,000	5.6 / 16.9
Governance and Capacity Building	6,000				6,000	1.7
Agriculture and Rural Development	*3,000	30,000			33,000	9.3
Technical Assistance to Enabling Environment (Creative Industries and Competitiveness)	*3,000	-			3,000	0.8
Social and Economic Infrastructure	-	55,000			55,000	15.5
Sub-total	109,000	153,000			262,000	62.5
Building Resilience, Environmental Sustainability and Climate Change
Water and Sanitation	-	46,000		46,000		12.9
Environmental Sustainability, Climate change and SE	*3,000	12,000		15,000		4.2
Disaster Response	*3,000	-		3,000		0.8
Natural Disaster Mitigation and Rehabilitation	-	*20,000		20,000		5.6
Sub-total	6,000	78,000		84,000		23.5
RCI and RPGs
RPGs and Regional Solutions	*4,000		5,000	9,000		2.5
Sub-total	4,000		5,000	9,000		2.5
TOTAL PROGRAMME LEVEL	119,000		236,000	355,000		100.0
Percentage of grants	-		-	32.7%		-
* Set-aside allocations

D: Theory of Change

Evidence used to prepare the appraisal, including the theory of change and options

The SDF 9 Business Case draws from evidence from evaluations and reviews, mainly the 2016 SDF Multi-Cycle Evaluation (SDF6-7), the 2015 SDF 8 MTR, various CDB country, thematic and impact evaluations, the SDF 9 Contributors Report, DFID’s Annual Reviews of the SDF 8 and the 2016 MDR (Multilateral Development Review of the CDB, including the SDF replenishment). We assess that evidence is limited, with adequate quality and based on CDB’s internal reviews from its operational departments and from its independent evaluation department (IED), which validates all reviews and commissions evaluations. The evidence base is the same for the three appraisal options as they focus on the volume of the UK contribution as other options on priorities and ways of delivering have been agreed by DFID Ministers through the six-month replenishment process.

Assumptions for the Theory of Change

Our theory of change (see diagram 2 below) is based on two interlinked assumptions:

- CDB, albeit small, is a sufficiently relevant, responsive, reliable and effective development partner that achieves reasonable development results in Caribbean as evidenced by internal reviews and independent evaluations (e.g. 2016 Multi-Cycle Evaluation of SDF 6-7),
- Our contribution will contribute to further economic growth, poverty growth and a reduction in vulnerability in fragile and distressed countries and allow us to influence the Bank’s priorities and performance.

The theory of change for providing resources to CDB for the SDF 9 replenishment builds on the relevance, effectiveness and efficiency of CDB’s strategy and operations. CDB plans to maintain its concessional assistance over the SDF 9 period to support the regional member countries in addressing their development challenges and helping them make progress on the SDGs. Another assumption is that the SDF 9 replenishment will respond to (i) the need for concessional assistance to address development challenges in the region, and (ii) CDB’s effectiveness in assisting countries to address these challenges.

The theory of change sets out the steps by which the process should take place. It is depicted diagrammatically below, and is built on the following linkages:

- DFID’s inputs: of finance and policy engagement during the negotiations and throughout implementation, centred around the policy issues described above, will translate into an output of an SDF that works more efficiently and effective,
- A more effective SDF – the output, is in turn able to deliver improved results in the Caribbean – the outcomes.
- Finally, the outcome of improved SDF results contributes to the desired impact of achieving the Caribbean SDGs.

The assumptions in this theory of change are based on and tested against the evidence presented in this Business Case. However, we do not have any independent assessment on the assumption of DFID’s influence and we would rely on e.g. the Independent Commission for Aid Impact (ICAI) evaluating this as they did for the Asian Development Bank in 2012[9].
[9] ICAI: “The Effectiveness of DFID’s Engagement with the Asian Development Bank”; 2012

Diagram 2: DFID’s Theory of Change for the SDF 9

Input
Outputs
Key Assumptions
- Financial contribution
- Policy engagement during negotiations and delivery
- Other development partners provide resources
- Clients continue to engage positively with SDF projects and demand remains high
- Reform led from HQ in Barbados has an impact on ways of working in-country and at HQ
- Reforms are relevant, and do improve the Bank’s ability to deliver results through speedier and more effective project processes
- Projects are resilient to risks arising in country
CDB organisational and operational outputs e.g.

Around $350 m of concessional funding to SDF countries including $45m to Haiti

CDB joins International Aid Transparency Initiative (IATI)

Eradicate poverty and achieve the Caribbean Sustainable Development Goals
- The Bank is capable of having a sustained impact on the sectors and policy areas it programmes in
- There is the political will and capacity in partner countries to ensure bank projects have a sustained impact
- The UK is successful in influencing the shape of SDF 9
- The Bank implements and monitors the agreed organisational and operational changes

Impact
Outcome
SDF resources delivering material impact in partner countries as outlined in the results framework: e.g.
- 120,000 beneficiaries from road projects,
- 198,000 students benefiting from improved facilities,
- 950 km of water supply lines built

For inputs to translate to outputs

The UK is successful in influencing the shape of the SDF 9

There are no external reviews of DFID’s engagement with the CDB. However, the ICAI review “How DFID works with multilateral agencies to achieve impact”, found that DFID has significant influence in the multilateral system and has succeeded in focussing agencies on key global challenges, such as gender, promoting reform and improving results, as well as promoting impact and value for money. However, it recommended DFID focus less on how and more on what the agencies delivered, working with others to achieve this. We will depend on ICAI or other external agencies to do an assessment of how effective we influence CDB in the SDF 9 as we would need independent evaluator. However, we will, in collaboration with DFID’s Caribbean office, assess the UK’s influence and relationships in the Caribbean in light of the substantial reduction to inform future SDF replenishments and bilateral funding such as the £300 million UK CIF.

However, the UK had a strong role in shaping the SDF 9 in pressing the CDB to provide an evaluation of the SDF (Multi-Cycle Evaluation 2016 of the SDF 6-7 for 2005-2012) plus an evaluation of its Haiti programme. Evidence from both were used during the SDF 9 replenishment. As the SDF 9 Replenishment took place over the period March 2015 – December 2016, IFID (International Financial Institutions Department) sought Ministerial steers three times. DFID's SoS and MoS agreed with IFID recommendations prior to the first SDF 9 replenishment meeting in March 2016, the rationale for the UK’s continued engagement in the SDF for 2017 – 2020. Our priority objectives for the replenishment were; “leave no one behind – inclusive growth through infrastructure and business”, “gender – women and girls”, “improved disaster and crisis responses”, “climate smart development” and “improved project readiness and delivery– especially in fragile countries”. Ministers decided on the substantial reduction (from £33 m for SDF 8 to up to £18 m for SDF 9) in November 2016 and CDB was informed prior to the CDB Board meeting in December 2016. We will use CDB’s revised results framework to measure the progress in these areas and on the Bank’s operational and organisational efficiency.

CDB implements the agreed organisational changes

Our theory of change is based on the assumption that CDB has sufficient capacity to deliver its targets and improve its organisational efficiency. As weak capacity has been a concern over the last few years, we consider this a key area for the Bank to focus on to ensure efficient delivery of the development outcomes for the SDF 9. The UK, with support from Canada and Germany, therefore used the replenishment to encourage the Bank strongly to focus its efforts on enhancing capacity to develop and implement SDF 9 priorities and programmes. As a result, the SDF 9 Contributors Report now includes an action plan to improve the Bank’s efficiency.

Our assessment is that the Bank has made some progress on internal reforms over the last couple of years, albeit slower than expected. For example, it has implemented a series of reforms to enhance corporate governance and oversight. CDB has also strengthened policies, strategies and guidelines, right-sized its structures and staffing, and streamlined its business processes, including procurement. We used the SDF 9 to push the Bank to pay further attention to the agreed reforms and continue to ensure that the reforms are value adding and that there is the right balance between reforms and cost given the constraints of the Bank’s policy to keep the admin budget within zero real increases (only allowing for inflation).

However, it is still too early to see a sufficient improvement in speed of delivery although the Bank has improved on project readiness, which includes faster procurement and mobilisation of contractors prior to starting a project. As the table 5 below indicates, more than 60% of all projects are extended due to slow implementation (on average more than three years extensions), leading to higher transactions costs for mainly the recipient country. In addition, only one-third of all completed projects over the period 2014 - 2015 had a project completion report (PCR). The UK therefore has quality delivery as our main priority for the SDF.

Table 5: CDB operational performance

The 2016 independent Multi-Cycle Evaluation of the SDF 6 and 7 included the following comments on CDB’s efficiency in regards to programme delays and weak supervision:

Box 1 below includes the key actions to improve efficiency that we pushed the Bank on during the SDF 9 replenishment. They are now part of the action plan for reforms that is included in the SDF 9 Contributors Report.

Key elements being taken to boost operational efficiency and strengthen country engagement

Internal Cycle Speed: Inception to Completion
- Enhancing the project cycle by improving quality at entry, supervision and gleaning appropriate lessons through timely completion of Project Completion Reports.

Supervision Presence
- Engaged experienced consultants in countries which exhibited acute implementation challenges to augment the supervision effort of Bank staff thereby supporting project delivery.

Disbursement Performance
- Identification of single points of contact with respect to disbursement management by BMCs. During 2016, the Projects Department has identified disbursement champions within each operating unit with direct responsibility for all aspects of the claims process. The group of disbursement champions will have a direct reporting line to the Office of the Director of the Projects.

In-Country Capacity
- Strengthening in-country capacity particularly around project cycle management training. The training unit within the Bank has recently completed the stakeholder consultation process within seven BMCs and is currently in the process of developing the project cycle management curriculum which is being tailored to address the peculiar gaps within each country’s project development and delivery process.

Knowledge Presence/Visibility
- On the internal front, by installing an Electronic Display Board to track project implementation performance, and externally, through the development and presentation of various Knowledge Products including climate resilience related tools and having a deeper participation and presence in Communities of Practice.

In the specific case of BNTF various assessments of its performance have made recommendations for improving the efficiency and effectiveness of the programme including measures for improving commitment and disbursement rates. In response, the Bank commissioned a comprehensive review of the Governance Structure and agreed with the SDF 9 contributors the following actions:

- Expand the pillars of support to include supporting productive livelihoods with assets, skills and knowledge products, entrepreneurial development, market information;
- Widen the categories of eligible beneficiaries to include individuals, small work groups, civil society groups, and cooperatives;
- Enhance effectiveness and efficiency of operations in CDB and in participating countries, by simplifying procedures and due diligence frameworks; increasing authorisation limits; and establishing a BNTF forum to disseminate internal best/good practice; and,
- Mobilise additional resources through partnerships and expand channels of delivery

Our assessment is that the Bank will need some time to demonstrate further improvements for the whole SDF. We do not expect any quick improvement in regards to the Bank’s operational performance, based on our experience from the DFID-CDB Performance Improvement Plan (PIP) for 2013-2015 and the fact that the SDF 8 has scored B as expected outputs were not met over the years 2013, 2014 and 2015. We therefore assess that there is a moderate risk after mitigating factors are taken into account that the SDF 9 outputs will not be achieved in full during 2017-2020 (See Risk Section for further details).

For outputs to translate to outcomes and sustainable impact

The SDFs efficiency, relevance, effectiveness

The independent 2016 Multi-Cycle Evaluation of the SDF 6 – 7 (2005 - 2012) found that the SDF operations were relevant to the needs of the country (BMC – borrowing member countries) and beneficiaries and performed reasonably effective; as shown in these paragraphs:

However, the evaluation found that the SDF struggled with issues such as project delays and weak supervision, which made the Bank less efficient in achieving the expected sustainable development outcomes. These overall findings are similar to other reviews such as the SDF 8 MTR in 2015 and the Bank’s annual Development Effectiveness Reports. The independent 2016 Multi-Cycle Evaluation of the SDF 6 and 7 highlighted the following positive sides to the SDF as assessed over a longer period (2005 – 2012):

The following sections highlights key sectors for the SDF 9, including infrastructure, support to communities (BNTF), private sector, gender and areas such as regional integration, transparency, fraud and anti-corruption and uses examples with evidence of results as part of our theory of change.

Why is inclusive growth through infrastructure important for the Caribbean?

All CDB borrowing countries suffer from a significant infrastructure deficit, which needs to be tackled if they are to improve the prospects for increasing growth, job creation and reducing the negative impact on citizens’ quality of life. Our theory of change is based on the assumption that increased infrastructure investments will contribute to growth; initially through direct creation of jobs and economic activities, and in the long-term infrastructure by improving the conditions for businesses and beneficiary communities and enhance productivity. We also assume that CDB will use its established safeguard processes to avoid negative effects from the investments.

There is a lack of independent evidence on CBD and infrastructure apart from the SDF 8 MTR and the Multi-Cycle Evaluation of the SDF 6-7 (2016). The Bank reports on mixed progress on its infrastructure projects. For example, for the current SDF 8 (2013 - 2016), CDB is likely to exceed substantially on roads built or upgraded (400 km) as roads constructed were much more than originally programmed, some related to reconstruction and rehabilitation of roads after natural disasters, which could not have been planned. The Bank is on track to meet the number of beneficiaries of road projects (570,000) and households with access to sanitation and water supply (20,000). However, it is unlikely that the Bank will reach the land irrigation target and the communities with improved capacity to address climate change and disaster risk management target. The Bank do finalise all infrastructure projects although some are substantially delayed due to factors outside CDB’s direct control.

The 2015 SDF 8 MTR reported on CDB’s support to local infrastructures, mainly community buildings:

Promoting inclusion

CDB’s focus for the SDF is on inclusiveness across infrastructure, education and other sectors. As noted in DFID’s 2016 MAR, CDB has policies and guidelines in line with best practice among MDBs on social and economic inclusion, where the main inclusion policy is on gender.

However, the challenge is to implement the policies as the Bank has limited capacity and relatively small programming compared to other MDBs. The Bank has very small levels of programming in citizen security, targeting youth and vulnerable local communities to crime. The SDF, through the BNTF, regularly collects data and monitors excluded or marginalised groups and communities, particularly in rural areas, including indigenous groups. CDB is currently considering how to make the BNTF work more inclusive, including capacity strengthening of some of the smaller partners that the Bank works through at the local level on issues such as vocational training and support to vulnerable communities.

The Bank does not have a specific vision or strategy on the broader “leaving no one behind” agenda and the Bank’s results framework does not currently identify any specific groups other than men and women. The independent SDF Mid-Term Review in 2015 found that within the Bank’s programming gender tends to interact with other dimensions of prejudice, including ethnic and class dimensions. The review recommended that the Bank be more demanding with the gender marker when mainstreaming gender and consider the interactions of other dimensions of prejudice with gender, including ethnicity and class dimensions.

The SDF 8 MTR found that the community based poverty reduction focused BNTF had been relevant, but not efficient as it was too slow to approve and deliver projects. The MTR noted:

The UK, Canada and Germany strongly supported the suggested reforms of the BNTF during the MTR and we used the SDF 9 replenishment to push the Bank to restructure the BNTF to make it more efficient and effective. Those plans are now part of the SDF 9 action plan.

Private sector development

CDB works across its programmes and the SDF with private sector development. However, there is a lack of independent evaluations of what they have achieved apart from project reviews and SDF MTRs. The Bank and its regional members face many challenges as they aim to expand the contribution of the private sector to sustainable growth and development. CDB is mainly focusing on supporting an enabling business environment and it does very little on direct support to businesses.

As noted in the table below, the Caribbean countries, despite most of them having middle-income status, score relatively low on business environment and ease of doing business compared globally.

Table 6: Ease of Doing Business; Ranking

DFID has encouraged the Bank to redouble its efforts and to use innovative approaches for enhancing the contribution of the private sector and in particular medium and small sized enterprises (MSMEs). The role of the Bank’s Caribbean Technological Consultancy Services (CTCS) network in strengthening MSMEs is a key one, but we have requested the Bank to adopt further measures for improving the efficiency and effectiveness of this programme. CDB’s Private Sector Policy and Strategy are currently being revised to allow for risk-based assessment and appropriate pricing of private sector loans, as well as to provide a platform for portfolio diversification.

We have pushed the Bank to put further emphasis on initiatives focused on enhancing the institutional and policy environment for encouraging private sector growth, building competitiveness, promoting creative industries, innovation and entrepreneurship, through reform of legal, regulatory and institutional infrastructure and the use of technology. Insufficient investment in innovation contributes to the large productivity gaps of medium and small sized enterprises and constrains the enterprises in responding to market opportunities that can unlock technology-driven projects.

The Bank has pointed out, based on their project reviews, that the principal factors constraining medium and small sized businesses investment in innovation and firm upgrade include the inability to recoup research and development costs; and limited access to finance due to asymmetric information associated with financing technological investments. We support the Bank’s suggestion that SDF allocates resources to foster a culture of innovation, including technical support for education and training, research and development, and the identification of appropriate financing instruments to support new technologies.

The box below includes an example of support to Jamaica to improve competition and private sector growth.

Box 2: Example of support to business climate in Jamaica

The private sector is also a major contributor to the economic empowerment of women in the region. We support the Bank’s plans to improve access to finance for women as well supporting female MSMEs in the value chain is therefore critical in private sector development. The following section provides further information on what the SDF 9 will support on gender and leaving no one behind.

Gender: focus on women and girls - ensuring that no one is left behind

This section on gender provides evidence and examples of gender related projects including outlining the areas where we will continue to push the CDB to improve further their focus and impact. As mentioned above, IFID has carefully considered the impact of this new funding on gender equality to ensure it is in line with the UK’s Gender Equity Act. We assess that CDB overall is expected to provide moderate to limited gender outcomes as the fund includes a broad variety of different projects in sectors such as energy, climate change, transport, water and sanitation, finance, governance and education. Gender is one of the main themes for the SDF, especially the BNTF (Basic Needs Trust Fund) and all interventions include gender considerations in design, delivery and monitoring.

As noted in the SDF 9 Contributors Report (2016 draft), Caribbean countries have been moving toward compliance with the United Nations’ Convention on the Elimination on Discrimination Against Women (CEDAW). However, across the Caribbean region, gender gaps persist in the areas of access to economic opportunities, borne out by the data on women’s participation in the labour markets, access to physical endowments, and in participation in decision-making at the highest political levels. A key rationale for addressing gender equality (SDG 5) as a cross-cutting area in the Bank’s programming is because of the link between gender inequality and poverty in both rural and urban contexts.

Our assumption is that CDB’s work on gender and inclusion will contribute to improvements in equality in the Caribbean where all citizens and communities benefit from growth and poverty reduction. DFID and others welcomed the Bank’s recognition, in the planning for SDF 9, of the importance of mainstreaming gender and of its role as a driver of growth and a critical contributor to economic efficiency and effectiveness. Given the persistent gender inequalities and the continuing institutional weakness of national gender machineries, contributors endorsed the Bank’s commitment to follow a multitrack strategy by mainstreaming gender into all of its programmes, projects and strategies, in particular its social and economic infrastructure interventions, and by designing and implementing gender-specific initiatives.

The Bank’s work on gender has increased over the last few years, which includes training of staff in operations on gender analysis, the roll out of a gender analysis toolkit and gender marker and the integration of gender into the Energy Sector Policy and Strategy. The Bank is also providing regional training on gender, including gender mainstreaming in Caribbean Trade Policies. The Bank’s Scorecard sets targets and monitors data on sex and gender at both outcome and activity level. Since 2013, it has reported for example on the number of girls benefiting from education projects and women benefiting from roads, credit and community infrastructure programmes. For example, in 2014, there were over 30,000 female beneficiaries of road projects, 75 beneficiaries of rural enterprise credit programmes and over 83,000 from community infrastructure interventions.

The Bank has positioned itself well in regional policy dialogue on gender in relation to the review of the Beijing Platform for Action and the MDGs and in defining regional gender priorities of the SDGs. It has achieved this through regional partnerships with national and regional development agencies, including the CARICOM Secretariat and UN system agencies. Initiatives to enhance this policy dialogue include for example addressing gender stereotyping of girls in the education sector; women’s advancement in the ICT sector; women’s voice and agency in the water sector; and occupational segregation in the labour market - with a focus on the construction sector.

CDB has improved its gender work in project preparations. The proportion of loans with some gender benefit increased from 32% in 2013 to 55% in 2014. Although positive progress, the independent 2015 SDF 8 Mid-Term Review recommended that the Bank should continue strengthen the gender marker in projects (classification of gender aspects in project), complete country gender assessments for all remaining borrowing countries, focus its grants on selected priorities and be more visible publically as a gender advocate. Based on the SDF 8 MTR, we pushed the Bank to go further in mainstreaming gender, linking gender to the ethnicity and class dimensions in a more meaningful way in its sector projects (gender marker) and in identifying and acting on a set of specific gender equality priorities, which would lead to more concrete and significant results on the ground. The UK has been a strong supporter of this work during Board, annual meetings and the recent SDF 9 replenishment.

During the SDF 9 replenishment, the UK requested the Bank to include work on prevention and elimination of gender-based violence. The Bank and contributors agreed that the SDF 9 will support this through awareness building, behaviour change and security measures, in particular psychosocial support programmes, life skills training, relevant citizen security interventions and through gender-sensitisation training of contractors in infrastructure projects, gender-responsive projects in disaster situations, and through the provision of better data on the prevalence of gender-based violence.

Fragile and Conflict Affected Situations (FCAS) - Haiti

Haiti is the Bank’s largest regional member country with a population estimated at about 11 million. Haiti is the poorest of the Banks borrowing member countries. It is also the most unequal country in the Americas, with a Gini coefficient in 2013 of 59.2, and an income equality rank of 168 out of 187 countries. Its gender equality rank at 132nd in the world is similarly poor. Haiti has large development deficits, very high levels of poverty; lack of basic infrastructure, significant security problems and weak institutions. It has also suffered a history of devastating natural disasters, and is still recovering from the 2010 earthquake. Reducing poverty in Haiti will require large resources and a long-term commitment. Haiti currently is the only fragile state among the Bank’s regional member countries. There is a huge demand for international support and CDB is contributing to fill some of those gaps in education, agriculture and resilience. CDB’s role, albeit small, and added value compared to IDB, WB and others is mainly its technical expertise in the core areas but they do struggle with the culture and language barriers.

The SDF 8 Mid-Term Review in 2015 concluded that CDB had worked effectively with the World Bank and the Inter-American Development Bank (IDA) to deliver $70 million SDF funding to Haiti over the past seven years. Over that period, CDB had gained experience on which it could build and should consider moving in part towards a direct programming model, a strategy that would require CDB to increase its internal capability to work in Haiti. As noted in the independent 2016 Haiti Evaluation, the Bank is aware of the challenges of working in fragile states and complex environments such as Haiti. CDB faces the challenges of the limited capacity, coherence and political commitment of some partner governments, and there are a limited number of contractors able to deliver to Bank standards.

Climate change and vulnerability to disasters

Building resilience to climate change and natural disaster events, and promoting environmental sustainability, are primary themes as well as, cross-cutting areas for SDF 9. During the replenishment, contributors and the Bank agreed that climate change and natural hazard events threaten to unravel much of the development gains of the Caribbean region. As demonstrated in the graph below, the economic losses due to disaster are high in the Caribbean.

As noted in the SDF 9 Contributors Report, the World Bank estimates that between 2001- 2010, economic losses due to natural hazards in the OECS countries were $870 million in 2000 Real USD terms. Regional losses from Hurricane Ivan in 2004 totalled over $6 billion. In Grenada and Cayman Islands, losses were close to 200% of the national annual Gross Domestic Product (GDP). More recently, in August 2015, Dominica suffered the effects of Tropical Storm Erika, which caused severe infrastructural damage, estimated at $483 million, equivalent to approximately 90% of Dominica’s GDP.

Global records indicate that climate-related disaster risk is increasing. The Caribbean region will continue to be among those most adversely affected and greatly challenged to cope with the anticipated shocks to the social, economic and natural environmental systems due to the impacts of climate change.

Graph 3: Estimated damage and loss due to natural disasters (CDB DER 2015)

CDB’s independent evaluation of the SDF 6 (2004 - 2008) and SDF 7 (2009-2012) noted that the SDF funds were used effectively for rehabilitation following natural disasters such as storms and hurricanes. The evaluation mentioned the following examples:

The independent review “2015 MfDR”, based on the Multilateral Organisation Performance Assessment Network (MOPAN) methodology, rated CDB “strong” on environmental issues as it is a priority area for CDB. This priority is reflected in recent country strategy papers and the Strategic Plan 2015-2019, which includes a related cross-cutting priority – environmental sustainability, climate change resilience and disaster risk management strategies. The Bank has an Environmental Sustainability Unit whose functions include ensuring that environmental safeguards are applied in all operations. The review noted good documentation on environmental and social safeguard procedures; a climate resilience strategy; an energy strategy; and a disaster management strategy and operational guidelines.

Over the last few years, the Bank has sought to integrate environmental sustainability into its operations across all sectors through interventions targeted at climate change adaptation and disaster risk reduction, environmental awareness, capacity development and improved environmental governance and management at both national and regional levels. All CDB projects are required to be screened through a climate resilience lens. All infrastructure projects are required to be climate-proofed and opportunities sought for the use of renewable energy in the region. Over 8% of the Bank’s portfolio has been invested in projects that deal directly and primarily with environmental sustainability and disaster risk reduction but there is a growing number of projects that include climate smarting in the design. However, no independent assessment has so far been undertaken of the robustness of these requirements.

In late 2014, the Bank approved a new Energy Strategy and Policy, which has a strong focus on renewable energy. Examples of climate-smart activities include the use of solar photovoltaic systems (PV) to supply renewable energy in schools, and in community and health centres in areas that have no connection to the national grids. The BNTF, which addresses basic infrastructure, is using PV systems to provide water to poor remote communities. The Bank has also installed a new PV system in its headquarters in Barbados, which reduces its energy costs and works as a demonstration project for other institutions. The Bank has Adaptation Fund accreditation and is expecting to Green Climate Fund (GCF) accreditation in October 2016. The Bank also has secured access to concessional funds for renewable energy generation through the negotiation of Sustainable Energy Facility, which is dedicated financing from a consortium including IDB, the Clean Technology Fund; and GEF. Another concessional funding mechanism – Sustainable Energy for the Eastern Caribbean - funded by the EU Caribbean Investment Facility, DFID and CDB - is in the process of operationalisation.

CDB’s contribution to tackling Climate Change is reflected in its results framework and scorecard at the outcome level in terms of energy savings and clean power capacity installed as well as building capacity for disaster risk management and for climate resilience more generally. It also tracks the proportion of financing supporting environmental sustainability and climate change. Whilst in recent years, the proportion has exceeded the Bank’s 10-15% target, this has been set at an unambitious level, not least compared to other MDBs as over 21% (and increasing over the coming years) of the WB investments goes to climate change and 18% for ADB.

We assess that the Bank has a reasonable climate change policy framework and the policy commitment and ambition of the Bank is clear. However, it has not yet realised the level of lending in promoting climate-smart development. We used the SDF 9 to encourage the Bank strongly to increase its investments in climate change. The Bank also provides support to disaster preparedness such as infrastructure, community resilience to disasters and climate change and disaster relief and it provides financial support to recovery and rehabilitation of physical infrastructure. The UK pushed for the SDF 9 to continue support disaster response, mitigation and rehabilitation and for environmental sustainability, environmental risk management and adaptation to climate change.

Regional integration

The Caribbean region is facing challenges that require joint actions across the region. Notable among these are natural disaster warning and response, air and water pollution, watershed management on shared islands, knowledge goods and regional transportation of goods and people. The Bank supports regional policies and programmes albeit in a more limited way than expected and with some political constraints. Whilst only 3% of financial support in 2015 went to regional projects, CDB has supported regional cooperation in other ways. This included playing a key role, with the IMF and World Bank Group, during the resolution of the crisis in the banking and financial sector in the OECS (Organisation of Eastern Caribbean States) sub-region. CDB also lead on improving regulatory and institutional environments in the region to promote Public – Private Partnerships (PPPs) through the roll-out of the PPP Regional Support Mechanism and active dialogue with regional members on their capacity-building needs.

Examples of regional knowledge sharing and policy influence include the Bank’s key role during the OECS financial sector crisis, with CDB in a task force with IMF and WB, and leading on regional education planning. CDB is collaborating on a partial credit guarantee scheme in the OECS and with the IDB and WB to promote private equity and venture capital-enhancing activities in the Caribbean. CDB has a particularly significant role in the OECS where it is the largest provider of official finance. The IDB channels resources to the OECS through CDB. One example is the 20 million Global Loan in 2013/14, and the immediate response grant to Dominica after Tropical Storm Erika.

As noted in the independent Stakeholders’ Review in 2014, CDB has a comparative advantage through its strong regional knowledge and the ability to work closely with smaller island states where the WB and IDB do not have programmes, and a special grant allocation to Haiti as part of the SDF. As noted in the review, stakeholders appreciate its regional engagement which allow it to support capacity building during project implementation stages, particularly where existing capacity is very low in risky or complex environments, for example Haiti. Stakeholders appreciated the professional competence of the staff (although only two thirds believe that staff have the necessary skills to a high degree rather than a modest degree) and the regional knowledge, credibility and empathy of the staff. Stakeholders also appreciated the Bank’s experience in small island development, ability in project appraisal, financial strength and conservatism, and expertise in small infrastructure and in education. However, as in other evaluations, various stakeholders noted the continuing issue of slow implementation.

Over the last two years intensified its research-related knowledge products. This has included publications on:
- ‘Making Air Transport Work Better for the Caribbean’ (2015)
- ‘The Youth are the Future’ (2015)
- ‘Imperative of Youth Employment for Sustainable Development in the Caribbean’ (2015)
- Public Private Partnerships: Building on Early Lessons’, (2014)
- ‘New Paradigm for Caribbean Development: Transitioning to a Green Economy’ (2014)
- ‘Public Sector Debt in the Caribbean: An Agenda for Reduction and Sustainability’ (2013).

These publications have served to help shape public policy and reduce policy errors in the Caribbean. Beyond these regional public goods, the Bank has played a role in helping to inform the strategic direction of the Caribbean Regional Technical Assistance Centre (CARTAC) as a steering committee member and has also played a role in the Caribbean Growth Forum in collaboration with WB and IDB.

In conclusion, over the last few years we have pushed for the Bank to increase its work and spending on regional integration but it has not led to a major increase in its programming due to lack of demand for larger projects from the countries in the region. Instead, the Bank has focused on smaller technical assistance and research. We used the SDF 9 replenishment to continue our push for CDB to invest in more large-scale regional integration projects apart from research and knowledge sharing. We will continue to push the Bank on this issue as it is one its main mandates as stated in the Bank’s Charter.

Transparency – the International Aid Transparency Initiative (IATI)

Transparency is a UK priority for all the multilateral organisations DFID support. CDB has improved its openness over the last few years, but there is scope for further improvements. The Caribbean Development Bank’s Information Disclosure Policy (IDP) was approved in 2011 and it governs the Bank’s disclosure of information. The IDP demonstrates the Bank’s commitment to undertake its operational activities with transparency and accountability and to increase information flows on development activities to its stakeholders and key business partners. Publicly disclosed information is currently being posted on the Bank’s corporate website. The IDP includes provisions for a two-stage appeals mechanism with time-bound responses to review and render decisions in cases where members of the public consider that the Bank has violated IDP by denying their request for information.

The IDP also provides a framework within which the wide range of information collected and generated about its activities and projects in support of development programming can be disclosed. In line with current international best practices on information disclosure, the policy is based on a presumption of disclosure of any information in CDB’s possession that is not on the list of exceptions. Information will be made accessible to the widest external audiences possible to increase public exposure and broaden stakeholder understanding of CDB’s activities. The “2015 MfDR” review noted that there has been a “significant and noticeable improvement” in CDB’s disclosure, as seen from the increase in documents available on the Bank’s website. However, it also noted that more documents (e.g. audits and evaluations, and project appraisal reports for projects under implementation) should be uploaded, the search engine needs work, and the GIS has the potential to be enhanced.

Whilst the Bank’s adoption of this policy brings it closer in line with the larger regional development banks in terms of intent, the Bank is not yet a member of the International Aid Transparency Initiative (IATI). The UK has been in discussions with CDB on this over the last year. DFID used the SDF 9 replenishment, with Canadian support, to push CDB strongly to join the IATI standards on transparency as part of DFID’s policy for all multilateral organisations we fund to be part of IATI. The Bank has agreed to join, but it requested some time to fully sign up to IATI. We have agreed that this will happen during the SDF 9 period.
## Appraisal Case
A: What are the feasible options that address the need set out in the strategic case and follow the theory of change?

DFID’s bilateral MDB replenishments are different from the way we prepare for bilateral projects and the Business Case is therefore also different. Replenishments discussions take place over a six to nine months’ period with typically three meetings where the contributors and the banks discuss the overall objectives, priorities, expected results, monitoring and other related issues.

For the SDF 9, this took place during the period March 2016 to October 2016 and DFID with Ministers providing their steer at three different times: March 2015, May 2016 and September 2016. DFID’s representative used these steers to push for the UK’s objectives and priorities, which were then reflected in the outcome of the replenishments as outlined in the final SDF 9 Contributors Report, which is the formal record of the negotiations. As a result, this leaves little scope for further considerations in regards to objectives, priorities, mechanisms and expected results of feasible options and pros and cons apart from the final steer on the UK’s actual contribution to the SDF 9. The SDF replenishment negotiations were completed, apart from the UK’s pledge, at the final meeting of donors in October 2016, with donors pledging a specific amount . The SDF 9 Donors Report and Resolution (including details of donor’s burden shares) will be adopted in early 2017, reflecting the final UK pledge which affects the final SDF 9 volume.

There are two sets of options: first, what level of contribution should the UK and second, whether part of it should be subject to a performance or results tranche.

UK Contribution

The counterfactual option – do nothing (zero contribution)

All CDB shareholders are required to contribute to the SDF. For the UK to not provide any financial support to the SDF 9 would be difficult politically as the Caribbean matters for the broader UK foreign policies and CDB is a key agency in the region, working closely with DFID and other agencies for a long time, including co-financing. For the UK to not provide any funding would be seen as an extremely strong signal about our lack of confidence in CDB and in the Caribbean. The zero option would also be seen as a first step for the UK to leave the Bank which would have major implications for the future of the Bank and would have substantial wider repercussions for our standing and influence in the region, affect the delivery of the £300 m UK CIF and undermine HMG’s wider policy of strategic re-engagement with the Caribbean. It is likely that credit rating agencies such as the Standard & Poor’s and Moody’s would make a re-assessment of CDB, which could lead to a lower rating and in the longer run higher costs of borrowing for the Bank and its regional members.

It would also sit uncomfortably with the UK’s bilateral decision in December 2015, following PM Cameron’s announcement for additional support to the Caribbean in September 2015, for substantial funding via CDB for the UK CIF (£300 million in grants for 2016 - 2020). The UK CIF will use the CDB as the lead agency to invest in physical infrastructure to the poorest countries in the region, acknowledging the weak capacity and therefore including additional technical assistance and DFID secondment to the Bank.

We therefore did not consider it a feasible option to withdraw totally from the SDF (do nothing – the counterfactual) as this would have sent an extremely strong negative and contradictory signal to the Bank, other contributors and to the region as a whole as the UK has been an important contributor to the SDF since inception.

Identification of the Preferred Option

The options explored in this business case, which all include a performance tranche for 2020 (up to 1/4 of amount) based on performance improvements and for CDB to join IATI, are:

- Option 1: £36 million, which is the same amount as pledged for the last SDF and on par with the other main donor, Canada (21% burden share);
- Option 2: £30 million, which would be a 17% reduction (which would minimise the risk of Canada cutting, leading to a smaller SDF 9), to signal our concerns about CDB’s slow delivery, whilst recognising the capacity constraints in the region and thereby managing the risk to our standing in the region;
- Option 3: £27 million, which would be a 25% reduction to strongly flag our concerns on performance with a moderate risk that Canada and others might reduce their expected pledge levels, leading to a smaller SDF 9 budget;
- Option 4: £18 million, a 50% reduction as a very strong signal in response to poor performance and our lack of confidence in the Bank’s ability to improve that would most likely affect our influencing and standing in the Caribbean (This is the option that DFID Ministers decided on).

OPTION 1: Maintain £36 million contribution
The UK, Canada and Germany have already used the replenishment negotiations to convince CDB senior management that we would not consider any increases to the SDF during the next cycle. We rejected CDBs scenarios that included substantial increases and requested the Bank to consider a more modest volume bearing in mind the Bank’s overall weak capacity, performance and progress on institutional changes and the external circumstances in regards to the current exchange rates for the British sterling, the Canadian dollar and the Euro compared to the US dollar. All three currencies have weakened over the last year, which means that even flat nominal contributions in the three currencies would represent a real reduction by at least 10% in US$ terms (exchange rate set already as six month average up to June 2016). The Bank accepted this and decided to take the currency risk as their estimation of the contributions is fixed. Option 1 suggests that DFID retains the flat nominal £36 million as in real terms it represent a slight reduction of around 10% due to exchange rate changes from the SDF 8 which reflects our concerns about the Bank’s weak performance.

OPTION 2: A decrease to £30 million
A reduction by 16% compared to Option 1 would only reduce the full $349 million SDF 9 by around $10 million. The main purpose would be to send a stronger signal to the CDB and other shareholders that we are concerned about the Bank’s performance. Options 2 suggests that the UK remains the second largest contributor, albeit at a lower burden share. Our burden share would fall to around 17%.

OPTION 3: A decrease to £27 million.
A reduction by 25% would send a strong signal about our concerns on performance. Depending on what others might do, our burden share would be between 15 - 16%. Canada might be uncomfortable to have a gap of more than 5% between them and us, which could mean some slight reduction in the overall SDF budget.

OPTION 4: A decrease by 50% to £18 million
A 50% reduction of the UK’s contribution from £36 million to £18 million (approx. $25 million) represents around 10% of the contributions for the SDF 9. However, such a cut could probably lead other donors to cut their contribution because of concerns about relative burden share (e.g. Canada) and the possible impact of a lower overall replenishment size on those donors who pledge in terms of a given burden share. A substantial reduction would have implications for planned investments over the coming years and beyond as projects typically need between five to seven years to be completed. A reduction would also have more long-term effects as lending would be reduced which would also reduce the Bank’s reflows into future SDF cycles. This would send a very strong negative signal that the UK is dissatisfied with CDB’s performance. Other might also cut. As a result, the SDF 9 would be substantially smaller and our burden share may fall below 12%.

In summary, CDB’s weak performance and low scoring in the 2016 MAR warrant a cut in the UK contribution. Option 1 could be seen as a weak response with a greater cut needed to ensure the credibility of the MAR. To provide no contribution would undoubtedly have very significant negative implications that would outweigh any additional benefits to DFID from taking a very hard position.

In deciding between the Options 2 to 4, a balance has to be taken between the strength of the performance message that Ministers want to send, and the extent of impact on relations with CDB and the significance of CDB to our wider relations in the Caribbean that DFID-Caribbean’s parallel submission considers in more detail. We judge that a cut of up to 25% may not have a significant knock-on effect on other donor’ contributions or credit rating agency assessments and therefore would limit the impact on wider UK interests. A cut of 50% would clearly have significant knock-on effects that could materially affect our wider interests.

Table 6- pros and cons of the feasible options
	Positives	Drawbacks
Option 1: £36 m, flat nominal	Represents the level of commitment desired by CDB from the UK and would enable them to provide the level of support desired to the region / Would complement the more substantial UK commitment to the CIF. / Would send a signal that the Caribbean matters and that the UK continues to support CDB in its role, despite weak performance. / It would match the Canadian contribution and burden share which historically is at par (around 20%).	There have been performance issues with CDB in recent years. / Maintaining the current level of support might send the message that DFID’s funding is not contingent on progress.
Option 2: £30 m, 17% reduction	This would send a signal that the mixed performance record of CDB and their lack of reform has consequences in terms of UK funding. / Despite this the SDF would still have enough resources to continue the bulk of its work and support as it would not have any substantial consequences to the total SDF 9 volume (around $370 million)	Would appear strange given the size of the recent commitment to £300 UK CIF and would need careful communications. / However, we assess that a 17% reduction would not result in any other donor cutting.
Option 3: £27 m, 25% reduction	This would send a strong signal about our concerns on performance with the moderate risk that Canada and others might cut their contributions.	Depending on what others might do, our burden share would be between 15 - 16%.
Option 4: £18 m, 50% reduction	Would send a very strong message to CDB regarding DFID’s expectations in terms of performance.	DFID might come under political and media criticism for the inconsistency of providing £300 million to CIF and then cutting SDF core contributions to the poorest and most vulnerable communities only months later. The cut would affect the UK’s standing among the regional member countries, especially the Commonwealth and OTs. / Other donors might substantially reduce contributions, leading to reducing the organisation’s ability to operate in the region. / Haiti receives the largest proportion of grant funding of all countries and much of the support goes to commonwealth countries that are important for UK policy more broadly.

Results and performance based tranche

During the replenishment process, we considered possible ways to use a part of the SDF 9 contribution as a more specific results or performance incentive based on progress on implementing internal reforms. For the SDF 9, we therefore pushed early on with the other non-regionals for clear expected results and stronger and a more specific action plan to improve the Bank’s slow delivery. Other donors such as Canada and Germany are fully behind the need to improve delivery further and we will work together to make that happen over the coming period.

However, DFID Ministers wanted to send a strong signal that we expect effective delivery and for all multilateral organisations to be part of the International Aid Transparency Initiative (IATI).
Ministers therefore decided to make part of the UK’s contribution conditional on the CDB achieving its expected outputs and reforms and especially its commitment to join the International Aid Transparency Initiative (IATI) in line with other multilateral banks, such as the WB, AfDB, AsDB, EBRD and IDB and which follow their standards on aid transparency.

After consultations and discussions with CDB in October 2016, Ministers decided in November 2016 to link part of the UK’s payment to the SDF 9 (£4.5 m out of a total of £18 m) to overall progress in regards to speed of delivery and for CDB to join IATI. This will be monitored in a DFID – CDB Performance Agreement, which will include expected targets for 2019, which would trigger the final SDF 9 payment in 2020.

B: Economic appraisal of the preferred option
Financial outcome
The estimated contributions to SDF 9 (excluding internal CDB re-flows from past loans) are presented below in Table 7 (indicative amounts as not yet confirmed by all donors). The exchange rates below are fixed by the Bank based on an agreed methodology (six-month average before end of June 2016).
Based on the Bank’s suggested flat nominal contribution of $51.6 (£36 million) for the UK towards the $246.6 million total “contribution sharing basis” finance available for SDF 9 (including donor contributions, the structural gap and CDB’s transfer of OCR resources), the UK Burden share is equivalent to 21%. The share calculated on this basis is the one reported by the Bank as the UK’s contribution to SDF 9.
A contribution down to $40 million (£30 million) towards the $246.6 million total “contribution sharing basis” finance available for SDF 9, would mean that the UK Burden share would be 16.2%. A 16-17%% reduction from the UK would mean that the total volume would go down by $10 million to around $369 million, not considering the possibility that Canada and other non-regionals might reduce as well.

Based on a 50% decreased contribution of around $26 million (£18 million), the UK burden would be around 10%. Negotiations on the new SDF 9 (2017-2020), concluded in December 2016 when the UK pledged. The SDF 9 replenishment negotiations will result in agreement on operational targets and funding levels for the period 2017 - 2020.

The UK’s contribution is £18m (Options 4). The UK would provide the second largest contribution with a burden share of between 7.5 and 10% , with Canada providing $52 million, which would be equivalent of around 25% burden share.

Table 7: SDF 9; Contributors and relative share and amounts

16 CDN$1.3307=US$1 - Average daily exchange rate for 6-month period ending June 30, 2016
17 GBP1 =US$1.4339 - Average daily exchange rate for 6-month period ending June 30, 2016
18 Euro1=US$1.1164 - Average daily exchange rate for 6-month period June 30, 2016

Economic analysis

Due to the nature of the funding as a core funding to a regional development bank, which will in turn leverage this funding to provide grants and subsidised loans to Caribbean countries, a monetised benefit-cost analysis is not appropriate. This is due to three key reasons:

1. projects for the SDF 9th replenishment have not been finalised and the small number of projects funded means any estimation is likely to be inaccurate
2. the fact that the primary design choice relates to scale of the UK’s core contribution and
3. the significant objectives pursued by the UK in the replenishment, and the level of influence the UK achieves in the CDB and more broadly from its contribution are un-monetisable.

Costs and benefits of each option

The benefits, drawbacks and monetary costs of each option are set out in table 6 above. This considers, in a qualitative way, the results achieved, VfM and political considerations of each option. It is difficult to know what the effect of a change in the UK’s contribution, as one of the largest donors, on other contributors might be and the CDB is unable to provide unit costs of the projects it finances; therefore the economic appraisal will focus on a qualitative (and relative) assessment of the feasible options.

What follows is an outline of the costs associated with each option presented; high-level results achieved through the SDF 9 financing over the next four years[10] and DFID’s attributed share under each option and an assessment of the likely level of influence that each option might bring before concluding as to the preferred option.
[10] This will serve as an indication of results directly from SDF9, as projects funded through this round are only anticipated to be completed by 2024

Value for money of the SDF 9 (operational effectiveness)

Although the question as to the size of DFID’s commitment to SDF 9 is a matter of judgement, it still remains to make the case for why the SDF 9 as a whole is worth supporting from a VfM perspective using the limited information available. This suggests, as set out below, that projects supported through DFID’s contribution will represent VfM, and sufficient assurance can be obtained through CDB’s project appraisal process.

VfM of CDB’s anticipated results

Table 8 below provides a breakdown of anticipated results for the next three years, assuming the bank’s proposed financing scenario is achieved, as well as achieved results in the preceding three. What is striking about these numbers is the variation in achieved and forecast. This is largely due to the results achieved in any one year being attributable to a small number of projects; as the type of project that is completed in any one year changes, so do the results. This is illustrated by graph below which sets out the number of projects reaching completion in each year and their value.

When considering what might be achieved with SDF 9 financing, for which this BC is considering, the small number of annual projects means that any extrapolation would be highly tenuous and almost certainly wrong. That said, we note the significant results achieved in the period 2013-2016 in the context of the Caribbean (such as almost half a million benefiting from community infrastructure) and substantial results anticipated 2017-2020 (including almost a quarter of a million benefiting from community based citizen security) showing a strong level of commitment.
Table 8- CDB results (achieved and forecasted)	Achieved	Projected	% Increase
	2013-2016	2017-2020
Economic and social infrastructure development
1. Transport: Primary, secondary and other roads built or upgraded (Km)	435	222	-49%
2. Transport: Beneficiaries of road projects (number)	385,801	120,000	-69%
- of whom female	192,800	63,000	-67%
3. Sea defences/ landslip protection/ urban drainage (Km)	20	8	-60%
4. Water: Installed water capacity (cubic metres/day)	17,079	128,630	653%
- Urban	n.a.	73,842
- Rural	n.a.	54,788
5. Water: Supply lines installed or upgraded (length of network in Km)	1,057	950	-10%
- Urban	19	898	4626%
- Rural	1,038	52	-95%
6. Water: Households with access to improved sanitation and water supply (no.)	14,721	18,400	25%
- Urban	500	11,040	2108%
- Rural	14,221	7,360	-48%
7. Communities: Beneficiaries of community infrastructure construction/ enhancement projects 1 (number)	469,746	125,780	-73%
- of whom female beneficiaries	233,467	n.s.
Agriculture and rural development
8. Agriculture: stakeholders trained in improved production technology (no.)	3,570	2,600	-27%
- of whom female	n.a.	n.s.
9. Land improved through irrigation, drainage and/or flood management (hectares)	992	2,900	192%
Education and Training
10. Classrooms and educational support facilities built or upgraded according minimum standards (number), of which	585	1,299	122%
(a) ECD	n.a.	n.s.
(b) Primary	n.a.	n.s.
(c) Secondary and post-secondary/tertiary	n.a.	n.s.
11. Teachers and principals trained/certified (number)	4,830	9,286	92%
(a) ECD (total/female)	n.a.	n.s.
(b) Primary (total/female)	n.a.	n.s.
(c) Secondary and post-secondary/tertiary (total/female)	n.a.	n.s.
12. Students benefiting from improved physical classroom conditions or enhanced teacher competence, or access to loan financing (number)	124,950	198,900	59%
- of whom female	n.a.	n.s.
Citizen Security
13. Beneficiaries of community based citizen security interventions (number)	832	248,768	29800%

Graph 4- number and value of CDB projects by year

VfM of CDB’s footprint

CDB’s country and sectorial allocations are outlined in the Strategic Case (page 14). This aligns with a number of UK priorities in the region and DFID will continue to push for further improvement. For example, OECD DAC data shows that Haiti received the most amount of grant funding in recent years, which is aligned with DFID’s allocation model of countries with an inability to self-finance poverty reduction. As well as providing Saint Lucia and Belize with large amounts of funding, despite their very small populations, due to their higher poverty rates. In terms of sectors, CDB allocate a large amount to social and economic infrastructure. This is crucial for prosperity and economic development in the region.

Measuring the economic returns of CDB projects

It is not possible to calculate systematically an economic rate of return or cost-benefit ratio for the SDF9 as a whole. However, the CDB does have a robust approach to considering the economic returns to individual projects[11]. This includes requiring at least a 12% economic rate of return ex ante and systematic measuring of returns ex post:
[11] Operational Policies And Procedures Manual (2014), Volume 2: Identification, Preparation And Appraisal, CDB

“In instances where the project is expected to generate benefits that cannot be measured in monetary terms, the NPV or EIRR cannot be calculated. In such instances, the economic analysis must (i) clearly define and justify the project objectives, reviewing broader sectoral or economy-wide programmes to ensure that the objectives have been appropriately chosen; and (ii) use least-cost analysis to demonstrate that it is the most efficient way of attaining the stated objectives.”

Overall VfM Statement on the SDF expected results

The limited analysis possible suggests that the SDF represents VfM in addressing the development needs of the region, particularly in promoting economic development and resilience in the smaller and poorer members where other MDBs do not operate and given the limited capacity of DFID to manage projects directly.

C: Risks and opportunities for SDF 9 implementation

In its operations, the Bank faces different kinds of risks, including financial, operational, organisational and reputational risks. DFID’s 2016 MAR assessed the Bank as having good internal risk processes.
As part of the rollout of central due diligence assessments of the multilateral organisations, CDB was assessed in March 2015 (DFID’s Central Assurance Assessment of the CDB). It highlighted that appropriate governance structures and controls are in place at a central institutional level to ensure effective oversight and management of funds from donors, including trust funds. Standard quality assurance, audit, fiduciary control and procurement processes are also in place. The review concluded that the CDB clearly demonstrated its drive to align itself with multilateral development bank best practice in organisational effectiveness - including through seeking membership of communities of practice - while recognising the need to adopt an approach which is proportionate to its relatively small size.
Over the last two years, the Bank has improved its audit, risk management, evaluation and integrity and compliance functions. The biggest internal barrier to effective changes was previously staff capacity constraints and the difficulties in recruiting albeit with lower vacancy rates (down from 25% in 2013 to 8% in 2015).
 The Board of the Bank is regularly discussing the appropriate level of “risk appetite” across its programming and organisational risks as a way to find out which level of risks shareholders would consider appropriate. This is important given the relatively small size of the Bank’s operations, with a major share of lending going to a few large borrowers with the majority of them experiencing fiscal constraints and slow economic growth.
The Bank manages operational risk with the support of best practice recommended methodologies such as industry standard Risk Control Self Assessments and the use of operational risk registers. These efforts are complemented by enhanced monitoring; effective segregation of duties, frequent staff training, education and awareness. The Bank’s operational risk programme also places a strong emphasis on threats relating to its developmental mandate; fraud; business disruption; information and information technology.
CDB uses Credit Risk Monitoring especially of large exposures. The Board discusses risks for all new projects and regularly monitors progress. Examples include Board discussions on the use of policy-based lending, including factors such as the involvement of other actors such as IMF when countries are in fiscal distress (e.g. Jamaica). The Board also discusses risk assessments in CSPs and the appropriate level of risk appetite, including the application of risk limits and other risk elements in the portfolio and for the institution as a whole.
Internal and external audits meet international standards. The “2015 MfDR” review rated CDB as strong in regards to financial audits as the Bank has generally good audit procedures, robust financial oversight mechanisms and provides externally audited annual accounts. The Audit and Post-Evaluation Committee, of which the UK (DFID) is currently a member, assists the Board of Directors in discharging its responsibility on the provision of assurance on the adequacy of internal controls. The mandate of this committee has recently been expanded to include the integrity, compliance and accountability functions, and in October 2015 the Board approved this, including renaming it as the Oversight and Assurance Committee.
DFID assesses the overall risk rating for the SDF 9 as moderate taking account of the Bank’s risk management processes. A detailed consideration of each of individual elements is set out in the table below: external context, delivery, safeguards, operational, fiduciary and reputational. The most significant residual risk after mitigating actions is that the reforms to improve the speed of project implementation may not be fully achieved and delivery of results will slip. DFID-Caribbean will closely monitor the Bank’s action plan to improve its performance.

Table 9: Risk; probability, impact and mitigation
Risk Categories	Risk level; probability and loss in outcomes if this occurs despite mitigation	Mitigating actions and residual risks
External Context	Minor to Moderate: Some probability of risk of economic and financial problems in the Caribbean due to global economic circumstances. We would expect a modest loss in outcomes if this occurs for the whole SDF 9 programme over the four year cycle as CDB would focus on counter-cyclical assistance and other donors and IMF would provide support. However, if there were a major global crisis, the SDF would make limited difference. Financial resources will have to come from other sources.	CDB financial plans and contingencies in place to support countries during fiscal stress and high debt in case of economic slowdown. / DFID should engage with CDB and partners to discuss financing, including possible capital increases. Major residual risk that SDF funding, as limited and earmarked, will not be sufficient to absorb all risk.
Delivery of outcomes	Moderate: some probability that delivery of outputs will be affected as partner capacity can be weak and if CDB continues to be slow to implement its internal reform despite our push for improvement. Slowdown in internal processes will have an impact on quantity and quality of delivery and impact. / CDB now has a more focused plan to improve speed and quality of project delivery and cost efficiency, which are captured in the results framework.	We expect slow progress. DFID to continue to raise with the Bank and push for more progress in line with Bank’s defined plans. / DFID will monitor processes through the Board and SDF 9 monitoring, including the MTR.
Safeguards	Minor: low probability of risk materialising for the whole CDB with limited loss. There is a risk that safeguards might be breached in specific projects. However overall the Bank has reasonable processes in place to detect and handle these, through adequate safeguards policy and systems.	CDB has adequate processes given their small size. The UK uses its Board position to raise any issues that cause concern. Residual risks are dealt with on a case by case basis.
Operational	Minor: low probability of large scale operational risks materialising and impacting CDB’s whole operations and outcomes due to the Bank’s diversification across a number of countries and sectors, including within the SDF. At project level, the risk is moderate and linked to weak capacity at both CDB and country partner levels. We engage with CDB on the policies, structures and processes that it has in place to manage its operations effectively, in line with international best practice for MDBs. We assess that CDB needs to strengthen its operations in Haiti and we are pushing for that to happen (we are not convinced it needs a stand-alone country mission).	DFID will engage formally and informally with CDB, through different channels. / We have used the SDF 9 replenishment to push for further strengthening its Haiti operations, which stand to receive substantial support from the SDF 9($45 million).
Fiduciary	Minor/moderate: low probability for the whole CDB and with limited loss in outcomes or resources. Whilst fraud could happen in some specific cases the strength of CDB systems will constrain the extent and enhance the chances of recovery of resources. These processes are documented in DFID’s Central Assurance Assessment from 2015.	Residual risks remain despite CDB systems in place, including the new unit for integrity and accountability, which has set up whistle-blowing and other compliance mechanisms. DFID will raise concerns as appropriate.
Reputational	Minor: low probability of risk and limited impact. There is a reputational risk for both the Bank and the UK as a shareholder; e.g. programmes being high jacked for political gain; embroiled in a large scale corruption scandal and fraud cases; or mismanagement at or programme level. CDB has reasonable systems, structures and processes in place for operations and admin, but residual risks remain that could cause reputational damage especially as CDB does not have a strong track-record on communicating on issues that could potentially lead to reputational damage.	Some residual risk remains despite Bank systems in place to mitigate those risks. In our experience it is important to have an active Board that scrutinises projects on a regular basis. DFID plays an active part of Board discussions and engages at country level as appropriate. We will also discuss with CDB how it could improve its communications to the public and the shareholders.

The following matrix graph shows our assessment of the residual risk and return - that the expected returns in regards to development outcomes and institutional improvements within the Bank are satisfactory – important outcomes with reasonable development returns - and the overall residual risk for the whole SDF is moderate probability that the expected results will not be met or close to being met with some potential loss over the full SDF 9 four year cycle.

Graph 5: Risk Return Matrix

RETURN / RISK	Modest	Solid	High	Very High
Minor
Moderate	CDB
Major
Severe

Commercial Case, including value for money on admin budget

A: Value for money through procurement

As noted in the independent CDB Stakeholders Perception Review from 2014, the CDB is valued as a regional bank. In the smaller borrowing countries, the CDB offers a range of support from technical assistance to loans in several sectors, and capacity-building support. It also provides the bigger regional countries with support that complements that which they receive from other MDBs. In the 2014 independent review of stakeholders’ perceptions of the Bank, feedback was mainly positive, however stakeholders noted some negative factors on competitiveness in regards to delivery of the CDB compared to larger institutions such as the WB and IDB. These included speed and flexibility, delegation of decision and approval authorities to professional staff, incentives for staff to achieve objectives, innovation and entrepreneurship, loan cost in the current competitive environment and CDB’s lack of permanent in-country presence.

As noted in the DFID 2015 Central Assurance Assessment (CAA), CDB has reasonable procurement policies in place. However, a DFID commercial adviser visited CDB in early 2016 and raised concerns about the capacity within the procurement team which is now considered by CDB and DFID Caribbean office. DFID Caribbean is now following up on that issue as it also affects the £300 million UK CIF. As with other MDBs, responsibility for procurement management rests with the recipient of CDB financing with the Bank providing oversight to ensure that procurement is carried out in accordance with the Bank’s procurement guidelines and the terms of the relevant financing agreement between the recipient and CDB.

CDB’s approach to procurement is to ensure open and fair competition in all its tenders, so that it procures high quality goods and services at the lowest cost. It requires procurement of goods and services through international competitive bidding, with limited exceptions, similar to those used traditionally by the World Bank and other MDBs. CDB, as part of its commitment to international aid effectiveness (Accra, Busan commitments). It supports the upgrading of public procurement systems in its borrowing countries. CDB procurement review processes and oversight are adequate to ensure compliance with guidance as assessed in the DFID’s CAA and through the preparations for the UK CIF in 2015.

The scale of UK CIF will represent an opportunity for CDB to increase its capacity. This will ultimately influence the Bank’s ability to manage complex transactions, engage with wider markets and potentially attract new suppliers. For example, in July 2016 Department for International Trade conducted series of events in the UK to highlight the opportunities and processes associated with the Fund. The strategic case noted that we will advocate CDB to increase transparency during this SDF period. This represents a good opportunity to increase information available for businesses, for example accurate procurement pipelines.

During the SDF 9, we will look for opportunities to understand further CDB’s commercial and procurement processes and capabilities. If through this we identify any weaknesses or gaps, we will work closely with the Bank to lobby for any reforms to increase efficiencies. A particular area that we might explore is the scope for collaboration with other financial institutions in the region.

B: Value for Money on CDB as an institution (admin efficiency)

Value for money includes three components: economy, efficiency and effectiveness. (Refer to VfM statement on the SDF expected results on 37). The 2016 MAR noted that the administration budget, where staffing costs; salaries and travel, are the main cost drivers, are initially prepared in nominal terms and then recalculated in real terms to reflect zero real growth. The Bank undertakes annual staff compensation surveys, with the average uplift from the survey used as the deflator for staff costs for the coming year. CDB’s results framework includes indicators, benchmarks and targets on administrative efficiency such as administrative expenses compared to disbursements and approvals, vacancy rates, ratio between operational, front line staff and administrative/back office plus gender ratios.

The Bank’s past performance shows overall control of the administrative budget but more specific evidence is lacking. Although the budget policy allows the Bank to remain within the zero real growth scenarios, it does not adequately respond to the need for the Bank to demonstrate cost efficiency gains and the use of incentives for management and staff to seek value for money within its staffing costs and other administration costs. This could include new ways of working, changes in staffing responsibilities, including reductions in back office/support staff and use of new technology to drive down costs and improve productivity.
On the admin cost side, CDB has a long record of zero real growth budgets and relatively lower salaries compared to other regional development banks. As noted in the table below, CDB is reasonably efficient with other financial institutions of similar size in regards to admin expenses compared to active portfolio, with the caveat that the ways of working also plays an important part when comparing admin costs to active portfolios. The SDF is more staff intensive due to its focus on smaller community based projects and ways of working (e.g. monitoring small activities) which means the admin expenses are higher than the Bank’s ordinary lending (OCR). In addition, the admin costs compared to outstanding portfolio has increased for both the OCR (1.0% in 2011 to 1.4% in 2015) and the SDF (2.8% in 2011 to 3.3% in 2015).

Table 10: CDB compared to other small financial institutions on admin costs/loans ratio
Institutions	Admin costs	Loans/Equity outstanding	% Admin to loans	Currency	Year
Inter-American Investment Corporation	49,261,000	954,000,000	5.2%	USD	2015
Central American Bank for Economic Integration	38,000,000	5,200,000,000	0.7%	USD	2015
Black Sea Trade and Development Bank	18,447,000	1,100,000,000	1.7%	EURO	2015
North American Development Bank	8,567,000	1.185,514,000	0.7%	USD	2014
CDB – OCR	14,000,000	992,500,000	1.4%	USD	2015
CDB – SDF	17,900,000	546,000,000	3.3%	USD	2015

Sources: Annual Reports, 2014-2015, financial sections

We used the SDF 9 negotiations (February – October 2016) to push for improvements on reporting on value for money in the results framework and ensure that its administrative budget remains within the agreed level and that the Bank’s programming demonstrates better how it seeks value for money through all the business processes, including design, procurement, implementation and monitoring/evaluation.

We will continue to measure the Bank’s organisational and operational efficiency through the results framework, which is analysed in the Bank’s annual Development Effectiveness Reports.
## Financial Case

A. What are the costs, how are they profiled and how will you ensure accurate forecasting?

The UK will provide up to £18 million, with £4.5 million of that set aside for a performance related tranche to be paid in 2020, to SDF 9 over the period 2017-2020. The Bank laid out the terms of payment in the SDF 9 resolution and requests payments in equal amounts in each calendar year of the replenishment. It is anticipated that the contribution will be paid in four equal annual instalments in financial years 2017/18, 2018/19, 2019/20 and 2020/21 (last year linked to performance assessment.

The UK will make its contribution in the form of Promissory Notes (PNs) over the four years of SDF 9. The replenishment negotiations agreed a series of deadlines for issuing the PNs and the four year SDF 9 period is when the Bank commits the resources. The UK’s pledge to SDF 9 is subject to UK Parliamentary approval and a signed agreement between the Bank and DFID (the Instrument of Contribution – signed by the Director Value for Money) to make the contribution. The timing of the first UK PN payment is thus influenced by the timing of the decision by Parliament and agreement of the Instrument of Contribution. PN payments in subsequent years will generally be made in equal amounts to the first payment and paid in the same month as the first payment was made. However, flexibility may be built in to our agreement with the Bank in order to vary this pattern across the replenishment period in consultation with the Bank, should the need arise.

Forecasts for the PN deposits will be entered on ARIES Forecaster at the start of each financial year and monitored closely throughout the year against ARIES project components 204675-101 to 204675-104. DFID works closely with the Bank to ensure timely receipt of the calls for funds and with FCPD and the Bank of England to ensure that Promissory Notes are signed and deposited in line with forecasts. The encashment payments (draw downs on the PNs) will be forecasted on FCPD’s monthly large cash payment spreadsheet for the appropriate month.

B. How will it be funded?

The funds will come from DFID’s programme capital budget and are included in the scenarios being put forward to Ministers for 2017/18 -2019/20 fiscal CDEL.

C. How funds will be paid out?

Parliament needs to approve a Statutory Instrument for the UK’s contribution to SDF 9. The UK will then deposit PNs for the grant contribution over the four years of the SDF period. As PNs are treated as an irrevocable commitment, they are scored to DFID’s resource budget as soon as they are deposited.

The PNs making up the UK’s contribution of between £13.5 – 18 million will be encashed based on a standard schedule. This schedule is based on the projected disbursement pattern for SDF 9. A standard weighted encashment schedule for SDF 9 donor contributions was agreed by donors during the SDF 9 negotiations and is laid out in the SDF 9 Resolution. The encashment schedule is based on the Bank's historical disbursement profiles weighted by the expected composition of the SDF 9 programme or such other drawdown arrangements as may be determined by the Board of Directors. The fixed encashment schedule is communicated to the Bank by each Contributor at the time of the deposit of an Instrument of Contribution.

In order to ensure that an appropriate level of cash is available for project disbursements, the Bank maintains an active presence in international money markets to help manage liquidity, including moving assets into liquid assets as appropriate. The CDB has a liquidity policy but this only relates to the Bank's Ordinary Capital Resources and the Bank is providing a transfer from the OCR to the SDF. In other CDB funds, including the SDF, the bank are principally concerned that liquidity is sufficient to meet disbursements as there would be no debt associated with them. Payments are made within the 4 years of the replenishment window and the replenishment amount itself is based on a pipeline of projects that have been identified to be funded during the 4 years of the replenishment. The encashment schedule is derived from estimates of the disbursement profile of the projects to be funded and also takes into account the liquidity requirements of the Fund. Each loan or grant has a project implementation plan and a disbursement schedule agreed that is appropriate to the project. Payments are made according to the disbursement schedule.

Our experience from previous replenishments shows that the bank only makes requests for encashment in line with the agreed encashment schedule (i.e. there is no deviation from the payment dates agreed) and therefore payments are not in advance of need.

D. What is the assessment of financial risk and fraud?

The following section includes brief descriptions of the Bank’s main processes on financial risks and fraud; which includes key due diligence aspects such as risk management, audits, anticorruption – integrity and the prevention of fraud.

Risk ratings

The Bank first received AAA ratings from the major ratings agencies in early 1990 (Moody’s) and 2003 (S&P). The downgrading of the Bank’s credit rating by two ratings agencies in 2012 was a major concern. In response, the Bank focused on improving its risk management in 2013 with the implementation of a comprehensive enterprise-wide risk framework and recruitment of professional risk officers. These actions and other positive changes led to the removal of the “negative outlook” on CDB’s credit rating by Moody’s in late 2013 and by Standard & Poor’s in May 2014 (from AA/negative to AA/stable). Standard & Poor’s assesses the Bank as having a "strong" business profile and a "very strong" financial profile. The Bank has strengthened its risk management over the last year and now has a comprehensive risk management function in place appropriate to its size. This was seen by the rating agencies as a key aspect to improve its credit rating.

Audit processes

Internal and external audits meet international standards. The “2015 MfDR” review rated CDB as strong in regards to financial audits as the Bank has generally good audit procedures, robust financial oversight mechanisms and provides externally audited annual accounts. The Audit and Post-Evaluation Committee, of which the UK (DFID) is currently a member, assists the Board of Directors in discharging its responsibility on the provision of assurance on the adequacy of internal controls. The mandate of this committee has recently been expanded to include the integrity, compliance and accountability functions, and in October 2015 the Board approved this, including renaming it as the Oversight and Assurance Committee.

External financial audits are performed across the CDB for SDF resources, OCR, and Other Special Funds (OSF). The performance of financial audits across the organisation at the CDB was rated very strong in the MfDR 2012. The MfDR 2015 found that CDB had made further improvements in its internal financial audit processes. Financial audits at the regional, country or project-level were rated “adequate” as internal project audits had been performed at a slow rate and there was no specification that audits should be carried out using international standards or national audit systems and procedures, only that the “CDB shall maintain accounts in accordance with generally accepted accounting principles.” The 2015 Audit Plan indicates that there will be stronger reliance on the work of Internal Audit, which suggests good progress in CDB’s strengthening of that function.

Anticorruption, integrity and the prevention of fraud

Corruption is a key risk in the Caribbean. A major factor is selecting the CDB as a partner is the ability to utilise its well established systems to help reduce the risks of fraud and corruption taking place. This is especially important given that DFID has a limited presence in many of the countries that will be beneficiaries of SDF funding. As a regional partner, the CDB has the comparative advantage of its strong local knowledge and the ability to work closely with its borrowing member countries. Its “hands on” approach allows it to support capacity building during project implementation stages, particularly in risky or complex environments. The CDB is building up its ability to detect and manage fraud as part of its new Strategic Framework for Integrity, Accountability and Compliance, approved in May 2015, which includes a whistle-blowing mechanism and a new independent office for Integrity, Accountability and Compliance (ICA).

The CDB has a multi-year Country Strategy Paper, for each borrowing country, and has been improving the quality and regularity of these strategies. While preparing the Country Strategy Paper, sector assessments and diagnostic work are undertaken to understand the capacity of each borrowing member government. The capacity assessments include the recipient government’s legislation and systems regarding fraud, bribery and corruption. All CDB’s financing arrangements are managed under the standard policies and procedures of the CDB. These include, for example, anti-corruption, counter fraud measures, risk assessment and management procedures and systems. Multiple informal structures for donors also exist to manage risks of delivery for their programmes. This allows for robust and systematic checks and balances on programme governance[12].
[12] The CDB’s Code of Conduct (2009) and Guidelines for Procurement (2000 and 2005) include anti-fraud and anti-corruption rules, including clear roles and responsibilities for concerned staff and departments and mechanisms for prevention and complaints.

The Bank has not reported on any fraud detected and acted upon, but the new whistleblowing policy and overall framework for integrity, compliance and accountability provide the basis for strengthening the systems to do so, including a whistle-blowing function. ICA’s work, which started in late 2015, will enhance the integrity of the Bank’s internal systems and external operations. Among other things, ICA will be able to detect (including through a new whistle blower system currently being implemented), prevent, investigate, and recommend and enforce sanctions on entities for violations related to fraud and corruption. One of ICA’s strategic pillars is collaboration with other development partners on best practices and regional bodies including regional organizations like the Caribbean Financial Action Task Force on issues related to regional anti-money laundering terrorist financing compliance and ‘de-risking’ by correspondent banks due to money laundering concerns.

DFID Central Assurance Assessment

In August 2015, DFID completed a Central Assurance Assessment and Due Diligence of the Caribbean Development Bank. This assessment concluded that:

CDB is a reputable international financial institution with well-established governance and control financial systems in place in line with international best practice. Significant risks from poor capacity to manage DFID funds are therefore low; and

the CDB has been facing internal and external challenges (eg staffing), but has embarked on a concerted effort to address these with the result that the CDB has demonstrated improved performance in several operational and institutional areas, including meeting or exceeding lending and disbursement targets and reinvigorating several of its core internal functions through a significant reduction in vacancy rates for professional staff, important improvements in its governance, and a strong effort to embed a results culture in all teams.

E. How expenditure will be monitored, reported, and accounted for?

Expenditure will be reported in DFID’s annual accounts and are reflected in DFID’s Statement of Financial Position (balance sheet). Resource spend will be recognised at the time each PN is deposited. The value of PNs deposited, but not yet encashed, is also required to be reported as a liability on DFID’s Statement of Financial Position. This will be captured and reported by DFID’s Financial Accounting team, who maintain a record of all PNs deposited and encashed with the Bank of England. Finally, under International Accounting Standard 37 Provisions, Contingent Liabilities and Contingent Assets DFID is required to report within a note to their accounts any contingent liabilities. These will include the level of PNs guaranteed under the Instrument of Contribution but not yet deposited. This detail is again maintained by the Financial Accounting team within their PN database and will be reported as part of DFID’s annual report and accounts.

The Bank is also responsible for ensuring that Fund contributions, including those from the UK, are committed and mobilised appropriately and are in line with the implementation plan for the replenishment. Performance information feeds into the Annual Development Effectiveness Review under organisational and operational effectiveness. Data on replenishment commitments and disbursements is also published as a financial annex to the Bank’s Annual Report. SDF accounts are subject to an annual external audit by an intentionally respected firm of auditors. These reports are made public in the Bank’s Annual Report. The DFID CDB policy lead, with support from the Regional Development Bank team Programme Support Officer, and the UK representatives at the CDB, will be responsible for monitoring the expenditure related to this contribution using the Bank’s financial reports and audits.

Management Case

A: CDB and the UK: voice and influencing

The UK engages with the Bank at the following levels; through the Board of Governors, the Board of Directors (non-resident single-seat UK Executive Director is Head of DFID Caribbean), through direct contacts from London (IFID and DFID Policy Leads) and at the country level, especially in developing countries where DFID and the Bank have co-funded programmes. The Secretary of State is the UK Governor on the CDB Board of Governors and the Minister of State is the Alternate Governor. Our formal board interventions along with our access to staff and management, together with the SDF, the depth of our co-financing and the strength of country level relations, all serve to reinforce our influence. In most instances, it is a combination of levels of contact that supports our objectives and achieves influence. Critically, DFID is seen as challenging the Bank and importantly as willing to help develop solutions. The SDF 9 will not require additional management or resources to manage it. DFID London (IFID) has the equivalent of approximately 0.7 full-time staff members working on the institutional and reform agendas.

The regional nature of the Bank means that Caribbean countries always carry the dominant vote. Policies and programmes that come to the Board are rarely opposed by the Board. It is not sufficient therefore to convince Bank management of our arguments; we also need to convince other Board members. Clear evidence based feedback which is objective carries significant weight in influencing the management of the Bank. Consistency of our message through time, irrespective of changes to personnel, has been especially helpful. As a major shareholder, we also invest significant time in understanding the details of priority Bank decisions (e.g. staff remuneration packages) that influence its overall performance and client focus.

B: Monitoring and evaluation

UK’s engagement with CDB: IFID manages the UK’s engagement with the CDB through a Delivery Plan, which articulates the UK’s priorities for the CDB in general and the SDF. It includes what we want to achieve, means of influence, managing risks and identifying partners and blockers. The Delivery Plan, which is an internal IFID document, is reviewed annually after each annual review. Following poor results in Annual Reviews of both our contributions to the SDF and the CDB’s GCI, In 2013, DFID and the Bank agreed on a Performance Improvement Plan (PIP) for 2014 – 2015, which included the main operational/programmatic and organisational targets from the Bank’s results framework that reflected the UK’s priorities for the Bank. In the PIP, the following six indicators related to results management: improved direction for results, stronger country focus on results, stronger monitoring of results, improved accessibility of results and performance information, increased results with gender focus and stronger links between aid management and performance (linking budgetary allocations and disbursements to results).
Although the Bank improved in some areas during the PIP period, e.g. in regards to lending levels and how it integrates results management within the organisation, there are still weaknesses in its programming. Examples of areas to improve are a need for more investments to private sector development and regional integration and better project monitoring and reporting and improvements in speed and quality of delivery, which would lead to increased disbursements. During negotiations for SDF 9, donors collectively set out detailed activities and/or milestones for implementation. The Contributors’ Report, which outlines in detail the major initiatives to be undertaken over the course of the replenishment period, is produced and disseminated at the end of the negotiation process. Also built into the SDF replenishment process is a midterm review. Halfway into the 4-year SDF period, there will be a mid-term meeting to provide the opportunity for donors to take stock of progress made and challenges facing CDB and SDF.
CDB’s monitoring and evaluations: CDB has adopted a results management approach to improve the planning, monitoring, and evaluation of all its operations in an effort to achieve and sustain intended development results. CDB also launched its Development Effectiveness Review series, which assesses progress at a number of levels including operational and institutional effectiveness. CDB uses a results framework (RMF) that includes expected results in regards to priority indicators and milestones. The RMF was reviewed and updated as part of the 2015 process of developing the new Strategic Plan for 2020.
The Bank will report on the expected results through its RMF on an annual basis. For SDF 9, Contributors and the Bank agreed that the Corporate RMF 2015-2019 will be used to track SDF 9 results as RMFs indicators are the same since most projects are financed by a blend of SDF and OCR resources. The Bank has ensured that the Corporate RMF captures SDF 9 strategic themes and programme areas by including SDF specific indicators in the Corporate RMF, as required. In terms of reporting, the SDF Annual Report will refer to CDB’s Annual Development Effectiveness Review for reporting on results. The revised RMF will track implementation performance of the SDF 9 at four levels: regional outcomes, CDB contribution to outcomes, CDB operational efficiency and organizational efficiency.

CDB has an independent evaluation department (IED) which provides regular project, thematic and country assessments. The IED evaluates project and country programme performance as part programming and of its revisions of country strategies and the findings and lessons learned inform the consultations for each new country strategy. The independent 2016 evaluation of the SDF 6-7 (2005-2012) found that the Bank had weak monitoring and evaluation systems and processes. The Bank responded by strengthening the evaluation unit in regards to staffing and budget resources, Given IED’s limited capacity, the UK used the SDF 9 replenishment to agree that it would focus on evaluations that can contribute to the strategic direction for the Bank and make it more effective in delivery. That includes a stronger focus on sector and thematic evaluations and less project specific reviews.

DFID’s SDF 9 Logframe: The indicators in the Logframe for the UK contribution draw from the Bank’s RMF, reflecting elements that are DFID priorities. See annex for DFID’s SDF 9 logframe.
We will not include an indicator on our own effectiveness in influencing the Bank. Instead we will rely on possible ICAI evaluations covering CDB issues. However, we will continue to assess and consult on our engagement with CDB with DFID colleagues in the Caribbean office, especially in relation to the UK CIF over the coming years. DFID’s logframe has the following major indicators:

Impact: What development progress has been made in the Caribbean? Examples of indicators include that we include in DFID’s logframe; poverty, children in school, roads, electricity rates, water and sanitation and other socio-economic targets for the Caribbean.
Outcome: How well is CDB contributing to development in Caribbean (development outcomes). Examples of indicators include: Teachers trained in primary and secondary education (number-cumulative), Student benefiting from improved classrooms, enhanced teacher competence and access to student loan financing (number cumulative), Primary, secondary and other roads built or upgraded (km - cumulative), Beneficiaries of road projects (number; male and female tbd),
Output 1: Is CDB, as an organisation, managing itself efficiently in regards to human resources and gender? Examples of indicators are: Percentage of budgeted professional staff in operations departments, Ratio of professional staff to support staff, Representation of women in management positions, and, Vacancy rate at management and professional levels,
Output 2: Is CDB efficient in its use of admin resources? Administrative expenses per US$ million as % of loan project approvals (3 year average) (%), Projects at risk, average time taken from approval to first disbursements (months).
Output 3: Is the CDB managing its operations effectively? Examples of indicators are: Percentage of concessional resources allocated according to performance-based allocation system (%), Portfolio performance rating for implementation (% Satisfactory), Percentage of projects completed in past two years with Project Completion Reports (%). We have also included the indicator on project extensions as project delays are a major challenge for the Bank causing inefficiencies across the operations.
Output 4: Does the CDB have a strategic focus? Approved projects with gender-specific or gender mainstreamed rating, approvals supporting environmental, renewable energy/energy efficiency and climate change, approvals supporting regional collaboration.

DFID will do Annual Reviews of the SDF 9 over the period 2017 – 2020, based on updated results figures from the Bank’s annual Development Effectiveness Review and a Project Completion Review in 2021.

End of Business Case

Flag A: IFID’s Risk Register for the Special Development Fund (SDF) 9

Department	IFID
Programme name / ARIES number	SDF 9
Name person completing form	Bo Sundstrom
Grade / Job title	A2; Head of the Regional Development Banks Team, IFID
Measuring residual risk
How would you assess or measure the residual risk (minor, moderate, major, severe)?
We have reviewed all DFID’s categories of risks and included a table in the SDF 9 Business Case outlining the risks, mitigation, probability, impact and residual risks that needs to be monitored in our day to day relationships with the CDB.
What were those residual risk factors?
Slow project readiness and delivery leading to low disbursement rates, cost overruns, lower value for money and late achievement of development outcomes.
Why did you choose that risk assessment?
We used CDB’s own reporting on risks plus our own Central Assurance Assessment for the Bank as a whole.
Measuring planned development return
How would you assess or measure the planned development return (modest, solid, high, very high)?
Modest, as assessed in the Risk Section of the SDF 9 Business Case
How would you describe or articulate the expected returns?
As described in the SDF9 Business Case; using the Bank’s assessment of expected results and negotiated volumes and mechanisms for the period 2017 – 2020.
Why did you choose that return assessment?
We have to use the Bank’s results framework which includes expected results for the SDF 9 for the agreed period.
The risk-return tool
Anything else to note?

Flag B: DFID Smart Guide

Smart Guide
The Business Case
- Sets out the case for a programme, adapted to suit the context
- Explains very clearly what the programme will do within what timeframe and is explicit about the risks and uncertainties and how they will be managed
- Records an understanding for DFID, our partners and intended beneficiaries about what we are planning to do and the results we expect to achieve
- Allows DFID to report to the UK public on what we are doing with taxpayers’ funds

The Business Case is structured around the Treasury 5-case model. Within this broad framework the design should be adapted to suit different contexts and investment types. The content is indicative, not prescriptive and teams are encouraged to use judgement in making a logical argument to make the case in a way that suits the individual investment. There is also a set of questions in the Smart Rules that design teams should consider during the process. This is not a checklist and only the questions relevant to the context should be answered.

Teams should refer to the considerations below as a guide to writing the business case

Intervention Summary (2 Pages)
A succinct and unambiguous description of what the project will do. The summary sets out the problem the programme will address, what it will do and what the money will be spent on. It sets out the expected results in the context of the Operational Plan and DFID’s wider priorities and a summary of risks. The accompanying submission should set out any sensitive information that supports the case (e.g. risk tolerances and escalation measures)
Strategic Case
This section makes the case for DFID intervention by setting out the overarching context and the problem to be addressed. It should be clear what the programme will do and how with evidence. It should link to – but not repeat – the Operational Plan with a clear illustration of how the programme contributes to DFID global and portfolio priorities of poverty reduction.
Appraisal Case
The Appraisal Case explores how we will address the need in the Strategic Case in a way that optimises value for money. It appraises genuinely feasible options for achieving the objectives, including high level commercial choices , with a summary of the quality of evidence. The appraisal considers delivery mechanisms including capability and capacity, costs and benefits, risks and likelihood of success. It concludes with a preferred option.
Commercial Case
This section provides more detail on implementation and how value for money will be achieved. It sets out the procurement approach and requirements, proposed funding instrument and how the choice of instrument will be used to ensure vfm. It considers the market place response to this intervention with an explanation of how supplier performance would be managed. It sets out the procurement policies, capabilities and systems of the third party entity to ensure we get vfm.
Financial Case
This section sets out issues of affordability and the sources of funding. It includes a high level budget which does not impair VfM in procurement exercises for individual contracts. It sets out how funds will be disbursed and how expenditure will be monitored, reported and accounted. It highlights the evidence underpinning a judgement that funds will be used for the intended purposes.
Management Case
This section focuses on governance and management arrangements and the ability to deliver. It sets out the management implications for the business unit/ level of effort with realistic timings for mobilisation and start up. It outlines out the expected roles and responsibilities, including DFID’s own resourcing strategies (SRO, project team etc). / It sets out how it will respond to changes in context and the key elements of the Delivery Plan, key milestones and decision points where we can course correct. It includes a clear illustration of the risks, tolerances and approach to escalating problems and issues as well as exit and possible closure scenarios.