Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Supporting Economic Transformation
Programme Value: £4.467m		Review Date: December 2016
Programme Code:	Start Date: 18/11/14	End Date: 31/7/2018

Summary of Programme Performance
Year	2015	2016
Programme Score	A+	A
Risk Rating	Medium	Moderate

Summary of progress and lessons learnt since last review

The SET programme continues to make good progress. Although SET has scored an ‘A’ this year, it was on the borderline of an ‘A+’, as we are now expecting a higher standard and a higher level of performance. This is reflective of SET moving from the the inception phase to full project implementation and overall, DFID is pleased with performance. To date, it has collaborated with 8 DFID country offices (double the expectation), 2 DFID central departments and 5 partner governments. Major achievements include extensive support to the Government of Tanzania in the development of its second Five Year Development Plan, for which SET has been asked to continue its work. Feedback from DFID country offices about the relevance and quality of SET’s work was positive. Continued support in Nigeria, for example, has helped the DFID office to interact with the new Nigerian government (e.g. through a launch event of SET’s Economic Transformation paper in May 2016). SET has also influenced DFID centrally managed programmes, including its support to DFID’s business case for Invest Africa through scoping studies in Kenya, Uganda, Tanzania and Rwanda.

SET is actively engaging the private sector. Highlights include their participation in the development of Tanzania’s Five Year Development Plan and a roundtable on Kenyan Manufacturing with the Kenyan Ministry of Industry. There is scope for further improvement and over the coming year, SET needs to implement an engagement strategy to strengthen engagement between government and the private sector. As for DFID, they need to review what SET’s engagement with the private sector can realistically achieve over the remainder of the project.

Strong communication networks have been built with development partners, external research bodies and eminent economists, such as Dani Rodrik. There are good examples given on the uptake on SET products, which over-achieved the milestone target for this year. There is also an increase in downloads from the SET website. While good progress on communications has been made, awareness among DFID staff on the SET data portal was low and both SET’s communications strategy and data portal strategy need refreshed.

The quality of reports has significantly improved during the last year. Reports are well edited, have clear policy implication and a logical structure. Going forward, there is still scope to further improve reports, through making information clearer and better tailored to a target audience (e.g. government ministers, to ensure key messages are easily accessible). There is also demand in DFID for shorter policy briefs giving key high-level messages on economic transformation. .

Summary of recommendations for the next year

        Reporting

SET Project Director to sign-off on DFID’s reporting guidance and send it to DFID Senior Responsible Officer, from January 2017.

SET better tailor key message to government ministers, by April 2017.

SET’s products include policy briefs with key takeaway messages for DFID staff on economic transformation, by April 2017.

Private Sector Engagement

SET produces a 2 page strategic action plan on engaging the private sector for DFID approval by April 2017.

SET and DFID better monitor and measure the programmes influence on the private (and what has changed as a result) by April 2017.

Communications

- SET submit a revised Communications Strategy and Data Portal Strategy for agreement by April 2017.
- A logframe indicator monitoring the implementation of the Communications Strategy is introduced by April 2017
General
- DFID and SET check the risk of duplication before proceeding with any new work .
- SET provides the average cost per output in future years, to better assess value for money by the next DFID annual review.
- All project milestones should be reviewed, to make sure they are stretching by April 2017.

.

A. Introduction and Context

DevTracker Link to Business Case:	204254
DevTracker Link to Log frame:	204254

The Supporting Economic Transformation project (SET) is a 4 year Accountable Grant, to support DFID and development partners respond on economic transformation. It brings together country level policy and advisory work, high quality policy analysis, support to DFID growth diagnostics, knowledge and learning management and communications on economic transformation.

It has three interdependent outputs:
(a)	Policy advice to DFID, governments and other development partners
•	Support to DFID country offices and central departments with analysis to inform policy and programme work
•	Analysis to help understand potential patterns of transformation and how to orient policies and programmes to unlock this potential;
•	Support to country governments on strategies to accelerate economic transformation
•	In-depth and comparative analyses focused on specific issues proposed by DFID and other partners
•	Periodic anchor papers on major economic transformation issues

(b)	Promoting economic data for transformation including a portal to sources of data bases on economic transformation; and

(c)	A communication component to promote evidence from the programme and important policy issues on the quality of growth processes.

Economic transformation is essential for creating jobs and raising incomes in developing countries on an adequate scale. At present only (16%) of work in DFID countries is in waged employment in modern, productive sectors. The bulk of people work in unproductive or subsistence work in rural and urban areas. Changing this picture significantly even by 2030 would require accelerated economic transformation. There are opportunities for significant improvements in patterns of inclusive growth if resources were to reallocate between sectors and to higher value techniques in existing sectors.

This intervention is intended to help bridge the gap between DFID’s aspirations on transformation, and the practical actions needed to achieve change. Analyses under SET will inform policy dialogue with partner governments, help shape economic development portfolios and contribute to new growth and poverty diagnostics by DFID and those undertaken by governments and other donors.

SDGs have now been agreed with a strong transformation focus: Goal 8 includes ‘Achieve higher levels of economic productivity through diversification, technological upgrading and innovation, including through a focus on high-value added and labour-intensive sectors; and Goal 9 concerns about industrialisation, manufacturing, firm growth and high value agriculture. African governments were especially keen on Goal 9, which shows the relevance of the objectives of this programme.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment
Outcome Title	DFID , governments and other development partners design and implement economic development investments to foster structural economic transformation in order to give rise to stronger, more inclusive growth and poverty reduction in the long term.

Indicators	Milestone (2015)	Progress

1.1 Number of DFID country portfolios influenced by SET research and advice, in design or delivery	4 by October 2016	4 portfolios influenced- Met expectations / DFID Kenya / SET’s work on Kenya as a services hub influenced the undertaking of DFID Kenya’s Internal Growth Diagnostic (IGD), which influenced their wider project portfolio. SET’s work also helped DFID Kenya think about the way services can promote economic transformation. / DFID Burma / As a result of SET’s report, DFID Burma has begun to think about how best to gear its project portfolio to respond to China’s influence on economic transformation in country. / DFID Tanzania / SET’s ongoing work with the Tanzanian Planning Commission has involved DFID Tanzania throughout. SET’s coordination of the interaction between DFID and the government has helped DFID design and deliver new economic development programmes. / DFID Nigeria / SET’s work was informative for DFID Nigeria’s thinking on growth and economic transformation and has fed into the second phase of DFID Nigeria’s country diagnostic
1.2 Number of DFID centrally managed programmes influenced by SET research and advice.	2 by October 2016	5 centrally managed programmes – over double the expectation - Substantially exceeded expectations. / DFID Trade Policy Unit (TPU) (2 cases) / Trade briefing (see previous AR) / The Economic Adviser commented that the Trade in Services Paper, developed with TPU, would be useful to inform policy and programming work. / DFID Growth & Resilience Dept (3 cases) / SET developed the export-based manufacturing paper (and corresponding requested policy summary) which was well received. / SET’s provided support to building the business case for Invest Africa (in Kenya, Uganda, Tanzania and Rwanda) and was a direct influence on the decision-making process / SET responded to a request to assess the extent to which economic transformation is prioritised by the World Bank in its individual country strategies. SET’s work in this area is influencing DFID’s agenda with the World Bank.
1.3 Number of other donors, governments or multilateral agencies adopting policy or programming choices through SET programme influence.	1 case by October 2016	1 Case - Met expectations / Government of Tanzania / The Five Year Development Plan II (FYPD) contains recommendations that were proposed in the SET background paper. One example of uptake is a major section on monitoring and evaluation, a specific suggestion from the SET team. This is a clear example of policy influence.

Outcome Title	2. Better coordination between private sector/ business and government on economic transformation.

2.1 (i) Policy processes being changed by private sector participation / (ii) Private sector firms/associations operations/plans changed by interaction with the SET programme		3 case by October 2016	Moderately did not meet expectations. / Showing that a (i) policy process and (ii) private sector plans have changed is extremely difficult for a relatively short programme. DFID and SET should review whether the ambition is too high and clarify what success looks like. / However, SET has multiple cases of (i) supporting policy processes by engaging private sector participation, and (ii) private sector firms/associations interacting with the SET programme.
Outcome Title	Better global knowledge on how policies can support growth by accelerating economic transformation

3.1 SET programme demonstrates it is a centre for knowledge on economic transformation by the global community (NGOs, think tanks, academia).	2 cases by October 2016	Multiple cases – Exceeded expectations / SET research has been referred to in research bulletins (e.g. the European Centre for Development Policy Management and the Donor Committee for Enterprise Development) and featured prominently in the International Trade Centre’s quarterly magazine. / It has built several partnerships with international research and development organisations, including with the World Bank, IMF, ACET and undertaken work with international bodies (e.g.UNECA, New Climate Economy). / SET’s contribution to global expertise in the area of economic transformation has also been demonstrated in the facilitation by SET of a high-level debate in Development Policy Review by economist Morten Jerven and others. / However, SET’s Anchor Paper on Economic Transformation, setting out its approach to economic transformation, is still to be formally launched and it is not yet evident that SET has demonstrated that it is a ‘centre’ for knowledge on economic transformation.

Overall Outcome score and description

A – met expectations. Good progress has been made influencing DFID portfolios and government thinking. The programme is on track to meet this target. SET is engaging well with the private sector, but the ambition appears too high and this needs to be reviewed in early 2017. SET is building good partnerships with the global community and we look forward to seeing what impact its Approach Paper on economic transformation will have, when it is launched in early 2017

Key lessons
As we move into the third year of the programme, we need to start gathering stronger evidence about the changes that SET has brought about to DFID’s thinking and what DFID it is doing differently.
DFID’s expectations that SET’s engagement with the private sector is going to change government policies and private sector plans looks over-ambitious within the project timeframe and on a relatively modest budget. We need to be clear on the kind of change or influence we are expecting and agree what success would look like.

SET has developed good networks to raise awareness about economic transformation, but its communication strategy needs updating and should include indicators to demonstrate that SET is ‘a centre for knowledge on economic transformation’.
DFID has a modest budget to evaluate the programme and over the coming year, one should be commissioned to measure project impact and ensure that DFID’s expectations are well grounded.

Key actions

DFID to commission a small evaluation under the existing programme budget, to evaluate the impact SET has made and what DFID does differently, as a result of this project. The evaluation should be commissioned by June 2017.
-	DFID/SET to start tracking a sample of work for evidence of policy influence/change, by June 2017.

-	DFID to review its expectations on SET’s engagement with the private sector and ensure that it is achievable within the project timeframe, by April 2017.

-	SET’s revised communications strategy needs to include plans for how it becomes a centre for knowledge on economic transformation. This should be agreed by April 2017.

Has the logframe been updated since the last review?

Yes.

•	Key performance indicators were linked to output indicators, in order to measure quality.

•	A new output on private sector engagement was introduced and weighted at 20%.

•	Policy advice to DFID and governments, which had previously been combined, was disaggregated into two separate outputs, to ensure that we did not lose sight of either. Each was weighted at 25%.

## C: DETAILED OUTPUT SCORING

Output Title	Policy advice to DFID.
Output number per LF		1	Output Score	A+
Risk:		Moderate	Impact weighting (%):	25%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
1.1 DFID country offices and central departments policies and programmes supported by SET research outputs, including support with growth diagnostics;	4 country offices by October 2016 / 2 central departments by October 2016	Substantially exceeded expectations- 8 Country offices double the expectation. / DFID Nigeria (economic transformation pathways for Nigeria) / DFID Tanzania (FYDP II and DFID’s economic development programme) / DFID Kenya (services for economic transformation) DFID Burma (Chinese investors) / DFID China (relocating manufacturing) / DFID Rwanda (scoping mission) / DFID Occupied Palestinian States (Internal Growth Diagnostics) / DFID Uganda (Internal Growth Diagnostics) / 2 Central Departments / DFID Trade Policy Unit (Trade in Services paper) / DFID Growth and Resilience Dept (Manufacturing, Invest Africa, World Bank Jobs
1.2 In-depth and comparative analyses focused on specific issues proposed by DFID and other partners.	2 comparative analyses by October 2016 / …	Substantially exceeded expectations - / 19 analyses undertaken more than 9 times the expectation. / Anchor paper / Gender and Economic Transformation (ET) / Trade policy and ET / Economic Transformation Lessons from Large Developing Countries / Baseline on ET / The role of services in ET (applied Kenya) / Gender and ET in Tanzania / Manufacturing in Africa (ACET) / Trade Facilitation in Africa (ACET) / Public-private collaboration (ACET) / Developing Export-Based Manufacturing in Sub-Saharan Africa / 4x Jobs Africa (Rwanda, Uganda, Kenya and Tanzania) / World Bank / Trade in services and ET / Africa’s New Climate Economy (with New Climate Economy) / UNECA

Key Points

The milestone targets for support to DFID have been substantially exceeded, but the fit with DFID’s needs could be improved. While feedback received about the quality and relevance of SET’s work was generally positive, we also received comments that reports could be more focused and easier to glean useful information. There is also demand from DFID advisers for shorter high level policy documents that highlight key messages on economic transformation.

SET has strong country networks and a clear focus. It might benefit from an independent challenge function to contest established views, perhaps by inviting people from outside their network of experts to join review teams (e.g. IGC).

Country offices and central departments also identified possible duplication with other projects (e.g. Trade Mark East Africa) as a risk.

The DFID business model for the programme is working well, although some DFID country offices suggested Growth and Resilience Department clarify their responsibilities for managing the programme.

Summary of responses to issues raised in previous annual reviews

SET responded well to issues raised in the previous annual review. All activities now have a sponsoring DFID country office/department that agrees the TORs, team etc. The DFID business model is working well.

An improvement in project reports was confirmed during interviews with DFID colleagues. SET is following DFID guidance on reporting, which needs to be signed-off by the SET Project Director, to give assurance that best practice has been followed.

Recommendations
1.	SET’s products include policy briefs with key takeaway messages for DFID staff on economic transformation, by April 2017.
2.	SET uses more experts outside of its own network (e.g. IGC, where they are in country), to provide a challenge function to their approach and findings, by April 2017.
3.	DFID and SET check the risk of duplication before proceeding with any new work .

SET Project Director to sign-off the reporting guidance and send to DFID Senior Responsible Officer, from January 2017.

## C: DETAILED OUTPUT SCORING

Output Title	Policy advice to governments and other development partners
Output number per LF		2	Output Score	A+
Risk:		Moderate	Impact weighting (%):	25%
Risk revised since last AR?			Impact weighting % revised since last AR?

2.1 Support to country governments on strategies to accelerate economic transformation.	3 country governments by October 2016.	Moderately exceeded expectations - 5 country governments, nearly double expectations. / Government of Tanzania (2 cases) / Government of Rwanda / Previously (see AR 2015): / Zanzibar Planning Commission / Nepal Parliamentary Committee on Water Resources / Kenya Vision 2030 Delivery Secretariat

Key Points

This year, SET has supported two additional governments and is assessed as moderately exceeding expectations. It provided extensive support to the Government of Tanzania (GoT) through the Tanzanian Planning Commission (POPC) in the development of its second Five Year Development Plan (FYDP II) for 2016-2021. SET received strong feedback from the POPC and DFID Tanzania on quality of the support. The final version of the FYDP II contains recommendations that were proposed in the SET background paper. One strong example of uptake is that the Plan contains a major section on monitoring and evaluation, a specific suggestion from the SET team.

SET has been asked to continue working with the GoT over the coming months to support the implementation of the FYDP II. SET’s might consider how it can better target the government audience, (e.g. an easy to read summary version of main points for Ministers).

A scoping report for Rwanda was finalised in July 2016. It confirmed four topics that are high priorities for both the Government of Rwanda (GoR) and DFID Rwanda. The scoping report received positive feedback from the GoR. In September SET members brought together DFID Rwanda and the GoR for a meeting which provided the authorisation for SET to proceed with its proposed work-plan.

Summary of responses to issues raised in previous annual reviews (where relevant)
SET has responded well to previous recommendations. DFID country offices have oversight of all SET’s activities in country ( TORs, team etc.).

Recommendations
SET better target and message key government ministers, by April 2017.

## C: DETAILED OUTPUT SCORING

Output Title	Private sector and business engaged on the role of economic transformation in policy dialogue.
Output number per LF		3	Output Score	A
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		New Indicator	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
(i) Policy processes in which private sector participate. / (ii) Private sector firm’s/ associations operations/plans interacting with the SET programme.	3 processes by October 2016 / 3 interactions by October 2016	Substanitally exceeded / 5 processes – nearly double expectations / Development of Tanzania’s FYDP II (drafting 6 Oct 2015) / Development of Tanzania’s FYDP II (implementation strategy 27 Oct 2016) / Launch of Nigeria paper (31 May 2015) / Roundtable event on Kenyan manufacturing, August 2016 / Kenya services workshop (28 April 2015) (See AR 2015 for detail) / 6 interactions – double expectations / Kenya (roundtable event on Kenyan manufacturing, including Kenyan Association of Manufacturers) / Rwanda (firms, chamber heads interviewed about export manufacturing prospects) / China and Burma (Investors in Burma) / Uganda (Jobs Africa) / Kenya (services workshop in 2015) / Nigeria (NESG at launch of Nigeria paper in 2015)

Key Points
While SET has substantially exceeded each of the milestones, it is difficult to measure the quality of engagement with the private sector and there is a lack of strategic approach. Therefore, SET is assessed as meeting expectations.
While activities might have raised government’s awareness about the importance of engaging the private sector, evidence of any resulting changes is limited. DFID and SET need to consider how to better monitor the impact of the private sector.

Summary of responses to issues raised in previous annual reviews (where relevant)

This is a new output.

Recommendations

SET produces a 2 page strategic action plan on engaging the private sector for DFID approval by April 2017.

SET and DFID better monitor and measure the programmes influence on the private sector by February 2017 and what has changed as a result, by April 2017.

## C: DETAILED OUTPUT SCORING

Output Title	Data portal to promote better use of economic data in analysis on economic transformation in policy dialogue.
Output number per LF		4	Output Score	B
Risk:		Moderate	Impact weighting (%):	15%
Risk revised since last AR?			Impact weighting % revised since last AR?

Indicator(s)	Milestones	Progress
Quality of portal	Survey of DFID country offices in SET focus countries reveals 70% have knowledge of data portal.	Substantially did not meet expectations. / Over 10 DFID economic and private sector development advisers responded to the survey. Only one was aware of the portal.

Key Points

While awareness of the data portal in DFID is low, it does contain good data for analysing economic transformation, in select countries, which is regularly updated. Therefore, it is a failure to communicate the availability of the data portal by DFID and SET, rather than a quality issue.
More focus needs to be put on reviving the portal over the coming year and the DFID Technical Committee meeting in early 2017 would be a good opportunity. DFID agreed to put work on the portal on hold until the implementation phase was approved in July 2017, but DFID and SET have not discussed it since.

Summary of responses to issues raised in previous annual reviews (where relevant)

None

Recommendations

SET to submit a revised Data Portal Strategy for agreement by April 2017.

## C: DETAILED OUTPUT SCORING

Output Title	Implementation of a communication strategy including events to promote understanding of economic transformation.
Output number per LF		5	Output Score	A+
Risk:		Moderate	Impact weighting (%):	15%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?

Indicator(s)	Milestones	Progress
Results of multi-event assessment tool show good responses from participants	7 out of 10 people surveyed rated the event as 'good' and higher	Substantially exceeded expectations / 100% of SET events have been rated as good or excellent. / Feedback examples are shared in impact log of quarterly reports.
Uptake of SET products (including anchor papers, themed papers, comparative analyses) by the global community, including via the media	2 Cases	Substantially exceeded expectations / Almost 40 cases of SET outputs mentioned in the media. / 4 cases of SET outputs featuring in external organisations’ newsletters/promotional material. / Improved traction on social media, e.g. the services / Kenya paper was retweeted by Dani Rodrik and 20+ others.

Key Points

Although SET has performed well against milestones, it hasn’t responded to the recommendations of the last annual review. Therefore, it is assessed as moderately exceeding expectations. DFID agreed that the communications strategy would be put on hold until the inception phase was approved in July 2016. However, DFID and SET have not discussed the strategy since.

SET products have achieved a high level of uptake and there is an over-achievement of the milestone. DFID need to make it more stretching for the next annual review.

Downloads from the SET website have increased significantly in the past year, and there have been visitors from over 100 countries, including developing countries in Sub-Saharan Africa, and South Asia.

Summary of responses to issues raised in previous annual reviews (where relevant)

The next draft of the communications strategy was to consider how to develop the website further, implement a public relations strategy and finalise key messages for the programme. This needs to be done by SET and DFID as a priority.

Recommendations

SET submit a revised Communications Strategy for agreement by April 2017.

A logframe indicator monitoring the implementation of the communications strategy is introduced by April 2017

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance

The table below shows a breakdown of the costs for the SET programme for the past year.
	FY15-16 Q3	FY15-16 Q4	FY16-17 Q1	FY16-17 Q2
0 Core costs	31,500.00	31,500.00	31,500.00	39,000.00
1 Policy Advice and Research Support	144,549.90	240,330.00	200,982.72	251,565.70
2 SET Portal website	4,001.20	2,704.00	15,252.16	9,855.52
3 Networking / Public Affairs	20,118.10	13,383.26	21,788.89	21,794.13
Total	200,169.20	287,917.26	269,523.77	322,215.35

Total spend to end of FY 2016-17 Q2: £1,079,825.58. Costs have been driven by increased demand for policy advice and research support from DFID offices, DFID HQ and government partners.

Assessment of whether the programme continues to represent value for money

The programme continues to provide value for money, although we need to better track the average cost of SET outputs over the coming year to allow us to compare them with the benchmarks set out in the tender.
The value for money of the programme is monitored by focusing on a set of unit costs (economy), assessing the quality and adequacy of teams and their delivery of outputs (efficiency) and whether the outputs together provide valuable new insights and analysis that have traction with policy makers, donors and researchers (effectiveness).

Economy

Flights are economy class and there are modest accommodation and subsistence limits. This was confirmed by spot checks on travel to Nigeria and Rwanda.

Fees are benchmark against rates agreed in the business case and offer good value for money.
Efficiency

95 outputs were produced in Year 2

Output type	Number of outputs
Policy brief	7
In-depth /comparative analysis sector/thematic analysis	12
Full policy report/note/Working Paper	15
Blog/opinion piece	12
Other (written) output	24
Public event	6
Other event e.g. workshop/roundtable	8
(ODI participation in) external events to disseminate policy findings	11

The total spend to produce 95 outputs is lower than the average costs outlined in the DFID business case below (approximately 18% less, minus management costs). However, SET did not have information on cost per output for year 2. We recommend that SET provides the cost per output in future years, so we can assess value for money more clearly by measuring actual costs against the benchmark rates SET provided for DFID’s business case (see table below).

Benchmark rates for comparing costs of outputs under SET
Output type	Average cost
Policy brief	£4,774
Indepth /comparative analysis sector/thematic analysis	£20,764
Full policy report/note/Working Paper	£34,661
Case study	£34,613
Blog/opinion piece	£680
Other (written) output	£11,208
Public event	£3,044
Other event e.g. workshop/roundtable	£5,656
(ODI participation in) external events to disseminate policy findings	£1,357

The programme has demonstrated efficiency by making use of synergies between data portal development, country work and advice. For example:

- Export-based manufacturing paper – SET produced extensive data work whilst writing their paper, which was made publicly available on data portal.
- New Climate Economy (NCE) – SET data was used extensively for the joint paper with NCE on climate change and economic transformation.

Effectiveness

It is still early days to see impact, although there have been some early signs (e.g. their work with the government of Tanzania). However, DFID and SET need to start tracking selected pieces of work over the remainder of the project, for evidence of the changes that this programme is bringing.

Quality of financial management

Best value for money is discussed with DFID during monthly programme management meetings.

The quality of financial reporting has been satisfactory and there have been no major issues to date. The invoice for quarter July –September 2016 did have an underspend of some £15,000 for the data portal, to which DFID were not alerted until the invoice was submitted. This resulted in a variance of more than 5% on SET’s forecast. SET should ensure they keep within this target and send updates to DFID when significant changes are likely.

Date of last narrative financial report	19 October 2016
Date of last audited annual statement	31 October 2016

E: RISK

Overall risk rating: Moderate

Overview of programme risk

The main risks to this programme are identified as follows:

Quality of SET’s reports does not meet DFID expectations (moderate risk/ major impact)

DFID and SET have worked hard to manage this risk. Feedback on reports produced this year has been good and we will continue to seek improvements.
SET’s policy advice and analysis is not aligned or implemented by DFID country offices and partner governments. (moderate risk/ major impact)

A Project Advisory Committee and Management Committee is being set-up in to guide strategy and work-plans. They will meet in early 2017. DFID needs to establish a system to liaise with DFID country offices, in order to ensure SET’s work is meeting their needs.

Project fails to effectively engage with the Private Sector (major risk/ moderate impact).

DFID and SET need to agree a private sector engagement strategy and be realistic about what this project can achieve within the timeframe (and how to measure it).

SET fails to become a ‘centre of knowledge’ for economic transformation

A revised SET communications and data portal strategy needs to be developed, agreed and monitored.

SET duplicates existing products (moderate risk/ moderate impact).

DFID and SET will scope existing work, before new work is commissioned.

Outstanding actions from risk assessment

The communication strategy was to be finalised and put into practice when the implementation phase started.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe

SET is on track to deliver outputs and meet milestones within agreed timeframes, with the exception of the data porta, for which a strategy will need to be agreed and implemented.

Given the high demand for SET services, work-plans will need to be agreed every six-months, to ensure SET is meeting key demands. Work-plans will be agreed by the DFID Technical Committee, consisting of representatives from a broad cross-section of DFID departments and country offices.

Performance of partnership

SET has been very receptive to DFID’s feedback and continues to make good progress. It has a strong pipeline of projects and the partnership with DFID is working well.

SET delivers against six-monthly work-plans, agreed with the DFID management team, setting-out the key project activities and deliverables.

The inception phase was formally agreed in July 2017, after a good performance over the previous six months. Feedback on the quality of final reports delivered to DFID was positive and SET is demonstrating that it is using a broad range of technical experts.

Asset monitoring and control

There are no DFID assets held by this project.

G: CONDITIONALITY

Update on partnership principles (if relevant)

Not relevant.

H: MONITORING & EVALUATION

Evidence and evaluation

The Business Case includes a budget for an evaluation, which should be implemented by June 2017, to assess impact. DFID and SET should also select work to continually track for evidence of longer-term impact.

Monitoring progress throughout the review period

SET and DFID meet monthly to monitor progress against the six-monthly workplan, discuss any issues and agree going forward. Narrative and financial reports are submitted to DFID quarterly. Progress is reviewed by requesting feedback from 1) DFID offices by GRD; 2) SET seeking feedback continually from stakeholders.

## Smart Guide

## The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.
## The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.
The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessmen
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience? / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process