Programme completion review

Title: Strengthening Ethiopia’s Adaptive Safety Net (SEASN)
Final programme spend: £40,750,464.44	Review date:	21/4/2022
Programme Code: 300683	Start date: 4/11/2020	End Date: 3/2/2022

#### Summary of programme performance
Year	2022
Programme Score	A
Residual Risk Exposure Rating	Moderate

DevTracker Link to Business Case (and any addendum):	Not available
DevTracker Links to all logframes used during programme lifetime:	Not available

A. Summary and overview

#### Description of the programme and what it has achieved
SEASN was approved by Ministers in September 2020 via an emergency humanitarian funding submission, which requires that a full business case is later submitted for Ministerial approval in due course. At the time of receiving the emergency approval, it was envisaged in the draft SEASN business case that the programme would run until 2026. However, by the time that the business case was finalised in October 2021, the context had changed significantly in Ethiopia due to the conflict and growing humanitarian needs. A decision was therefore taken to end SEASN earlier than originally planned, in February 2022. Future UK support to the safety net in Ethiopia will be channelled through a more flexible humanitarian and development programme, that can adapt better to needs on the ground. This is therefore the only FCDO review of SEASN that has taken place, and covers the period from November 2020 to February 2022.

In a short period the SEASN programme contributed to providing predictable cash and/or food transfers to 8 million extremely poor people in chronically food insecure woredas (districts) in rural Ethiopia, delivered through the Government of Ethiopia’s (GoE) Productive Safety Net Programme (PSNP) and temporarily through World Food Programme blanket food distributions in northern Ethiopia when government systems were not functioning, primiarly in the whole of Tigray but also temporarily in parts of Amhara and Afar. Beneficiaries for PSNP are selected through a community-based targeting process. Households with able-bodied adult members are asked to work on community public works in exchange for their transfers. Public works projects include activities such as rehabilitation of land, tree planting, watershed management and the rehabilitation of low volume roads, as prioritised by the community. Women are exempt from public works during the second and third trimesters of pregnancy and two years postpartum. Labour-constrained households and people with disabilities receive unconditional transfers (PDS) and are linked with complementary social services where possible. The safety net also provides livelihoods support in the form of skills training, business planning, savings promotion, credit facilitation and employment linkages.

SEASN has performed moderately well but the operating context has been challenging due to a series of shocks that have occurred during the past two years, most notably the Covid-19 pandemic and its residual impacts, climate change induced droughts, and the impacts of the conflict in northern Ethiopia. More broadly, Ethiopia has also been beset by macroeconomic challenges, including a shortage of foreign currency and severe inflation. A further challenge has been a shortage of donor financing due to political factors and competing humanitarian demands, which has decreased the overall funding envelope available to the GoE to spend on PSNP. Whilst core transfers have been delivered to the majority of beneficiaries throughout this period, except those in conflict affected areas, these contextual factors have significantly disrupted planned delivery. The GoE have shown good levels of flexibility to adapt to the challenges posed.

The PSNP programme, now in it’s 17th year of operating, remains ambitious and complex. It has embarked upon a number of significant changes in the past year as it transitioned from Phase 4 to Phase 5, including a full re-targeting of beneficiary recipients in 2021/22 using multi-criteria poverty indicators for the first time rather than focusing on chronic food insecurity. In some woredas this has led to a significant shift in beneficiaries, whilst in other woredas recipients have stayed largely the same. Whilst there is limited evidence at this stage of people ‘graduating’ from the safety net based on rising prosperity, this retargeting exercise demonstrates that the programme is adaptive to federal level guidance. In parallel, the transition has also seen the programme launch an expansion to 70 new woredas, in addition to the existing 403 woredas, based on the prevalence of extreme poverty in those areas, which should help to improve food security in more parts of Ethiopia.

The programme scored an A overall, with strong performance in terms of the core responsibility to make timely transfers to people in need but mixed performance against remaining output indicators, though it should be noted that PSNP was designed for a more stable environment and was delivered within a highly challenging operating context. UK funding and policy engagement has helped to ensure that core transfers for PSNP beneficiaries have been prioritised, whilst other components such as livelihoods interventions have been delayed until budget and external conditions allow their resumption. Partner coordination and collaboration across this multi-donor programme has been strong including joint governance arrangements and knowledge sharing.

The following targets were changed during the life of the programme:

Following a request from the Government of Ethiopia in March 2020 the programme also agreed to provide blanket food distributions to conflict-affected populations in northern Ethiopia. Performance against this additional, short term, component has been strong despite the challenging context with a total of 885,617 people supported (48% women) against a target of 364,666 (50% women).
#### Major lessons learned, evidence generated and recommendations
Major lessons learnt include:
- PSNP beneficiaries could better cope with the adverse impacts of Covid-19 on food security: Independent survey data collected by the International Food Policy Research Institute (IFPRI) in 2020/21 demonstrated that PSNP beneficiaries were significantly less likely to have suffered from food insecurity than non-PSNP beneficiaries. The likelihood of becoming food insecure increased by only 2.4% for PSNP households and the duration of the food gap increased by only 0.13 months, compared to 11.7% and 0.47 months respectively for non-PSNP households. The protective role of PSNP is greater for poorer households and those living in remote areas. PSNP households were also less likely to reduce expenditures on health and education by 7.7% and were less likely to reduce expenditures on agricultural inputs by 13%. By contrast, mothers’ and children’s diets changed little, despite some changes in the composition of diets, with consumption of animal source foods declining significantly.
  [note] COVID-19 and food security in Ethiopia: Do social protection programs protect? | IFPRI : International Food Policy Research Institute
- But PSNP is unable to cover all of those identified as in need by communities: Whilst there was a good understanding amongst PSNP community food security taskforces of how to target the poorest of the poor, PSNP caseloads were only able to reach less than 10-25% of those identified by these community leaders as being extremely poor. A full retargeting exercise was completed in most PSNP woredas before the end of 2021, and it was evident that there was a significant change in beneficiaries, but coverage rates were highly constrained by increasing rates of deprivation in rural areas identified by community leaders, whilst PSNP budget shortfalls meant that expanding caseloads was not possible.
- ‘Primacy of cash principle’ must be reinforced to cope with financing gap: The Ethiopian Financial Year (EFY) 2014 workplan running from July 2021 to June 2022 identified a finance gap of more than 25% of the total PSNP budget. Whilst cash and food transfers have largely been protected in prioritisation discussions, public works and livelihoods activities were severely disrupted. As a result we had to reinforce to government, the primacy of cash principle to ensure beneficiaries are not penalised for not participating in public works and transfer continue to flow in a timely manner to those in need.
- Severity of drought impacts increases strain on PSNP infrastructure: A lack of water supply, for both WASH and agriculture, had a varying but overall severe impact on food security in parts of Ethiopia during 2021/22, particularly Oromia, Somali region and Southern Nations, Nationalities, and People's Region (SNNPR). Some level of resilience was provided by previously implemented community public works projects, such as pond building, watershed management and land rehabilitation from over-grazing, but they were not designed to cope with the severity of drought that parts of Ethiopia have experienced. Inter-sectoral coordination between Ministries at the federal and regional level should improve to tackle drought induced vulnerability and there is a need for other government sector programmes to invest in the WASH infrastructure required to help communities cope with what is now consistently low rainfall.
- Shock responsive PSNP could work more evidence based and more timely: The intention at the start of SEASN was for the government led humanitarian food response for transitory food insecure beneficiaries to be delivered through PSNP systems in PSNP woredas, rather than through a separate parallel system. This would entail institutional consolidation of the Food Security Coordination Department within the Ministry of Agriculture and the Ethiopia Disaster Risk Management Commission (EDRMC, formerly National Disaster Risk Management Commission) (within the Ministry of Peace). This has not materialized and subsequent work to harmonise early warning systems and pre financed response plans has been severely delayed. Although technical work to agree on shock responsive protocols has been finalized, the system is still not as evidence based, harmonized and timely as originally envisioned, which resulted in delays to the 2021/22 drought response in Somali Region and SNNPR.
- PSNP reforms are challenging to introduce in a fragile, conflict affected environment: 2020/21 saw the transition to a new five year phase of PSNP at the same time as conflict spread across northern Ethiopia. This conflict caused significant damage to PSNP systems and impacted on government bandwidth, technical capacity and the frequency by which they could engage in strategic decision making. Subsequent delays to major programme redesign processes, such as the transfer of beneficiaries to e-payments, the development of the electronic household registry and the development of PSNP linkages to social services, ensued. Some level of flexibility was provided by PSNP Development Partners (DPs), including the World Bank in terms of compliance with Performance Based Conditions to release funding, but future redesign processes should better consider existing government capacity to implement desired changes. Capacity constraints were also eased somewhat by the presence of 24 technical specialists embedded across different parts of Government, but funded by the PSNP multi-donor trust fund.
- Conflict responsive risk mitigations have been developed: During the course of SEASN a model has been developed to monitor and mitigate risk in conflict affected areas. This includes better live information flows on the status of PSNP systems in conflict zones, agreement on the need for independent post distribution monitoring to trace the flow of funding and additional independent spot checks to monitor compliance with programme standards (framed in the Programme Implementation Manual (PIM). Whilst difficult to agree with government initially, this model should now be applied consistently across PSNP conflict areas.
- Independent evaluation revealed design issues: In 2021 the endline evaluation of PSNP4 was finalised and presented to government. This revealed significant challenges with beneficiary levels of awareness of their entitlements, the availability of grievance redress mechanisms (GRM) for PSNP beneficiaries and the effectiveness of livelihoods interventions. These issues are being addressed through programme adaptations but only after prolonged policy discussions. Future independent evaluations, and indeed wider research of PSNP, should work more closely with government to clearly communicate policy implications of research findings and to align this process with the policy cycle.
Recommendations include:
If the UK provides future funding to social assistance in Ethiopia, it should work with relevant stakeholders to prioritise the following recommendations.

- Apply a new model to manage risk in conflict affected areas: SEASN has responded to contextual challenges and changes that could be described as unprecedented, which although significantly impacted on the timeliness of some payments, provided a model for the future management of PSNP risks in conflict affected areas and the transfer of responsibility to third party actors in non-federal-government controlled areas. The programme team should harness this learning to enhance risk preparedness and mitigations for PSNP in the future, and decision making processes on when to transfer resources to humanitarian actors.
- Monitor regional variations in programme quality standards: Variation in programme implementation and adherence to standards set by the federal government should be closely monitored through the independent spot checks of the PSNP system that are funded by the World Bank and audit measures implemented by federal government. This is especially important as the political economy in Ethiopia is fluid, causing implications at the regional level in terms of adminstrators willingness and ability to follow the rules and guidance developed by the federal government.
- Build a stronger working relationship with federal government: During 2021/22 the UK acted as the Chair of the PSNP Donor Working Group for six months, which provided the opportunity for regular engagement with the Ministry of Agriculture on a range of strategic implementation issues. Following the end of the Chair period the UK should identify further opportunities to continue to work closely with the GoE on social protection and build a mutual understanding around PSNP priorities that help to tackle food insecurity, including shock responsiveness, risk management and technical capacity building.
- Reduce the focus on additional components in future phases of PSNP if finance pressures continue: The core focus of PSNP is to provide timely, predictable, adequate and well targeted social assistance to the extreme poor and chronically food insecure people in rural parts of Ethiopia. If financing pressures continue in future years and contextual risks increase that threaten the viability of this core focus, the UK should seek to reduce the investment in components that act in addition to cash and food transfers, such as livelihoods interventions, public works capital investments and linkages to social services.
- Champion inclusion across PSNP: The UK should to seek to better facilitate gender and disability inclusion, in line with UK obligations under the Public Sector Equality Duty (PSED). At a minimum, this should include monitoring the increased risks of gender based violence in Ethiopia and influencing a response to research in this area planned by Unicef in 2022. We should also use our embedded adviser within the World Bank to ensure the use of the Washington short set of questions on disability to capture accurate and inclusive information and then tailor provisions, such as improving understanding of how many people with disabilities in a community are able to access permanent direct support through PSNP.
- Communicate UK impact on food insecurity in Ethiopia: PSNP plays a vital role in improving food security for the extreme poor in remote rural areas of Ethiopia. These impacts should be more visible to a UK audience and the role of UK funding in this process should be better understood to an Ethiopian audience through case studies that trace the impact of UK investments.
#### How this report was conducted
This report was conducted by 1 x Social Development Adviser from the Human Capital Development Team (HCDT), 1 x Human Capital Policy Adviser from HCDT with oversight from 1 x Social Development Adviser from the Resilience and Humanitarian Team (RHT) and 1 x Team Leader from RHT. To inform the visit the full review team of four people joined representatives from the World Bank and Government of Ethiopia to complete field visits to inform the review. Two team members (1 HCDT, 1 RHT) visited Sidama and SNNPR, one team member visited Dire Dawa (HCDT) and two team members visited Jijiga (1 HCDT, 1 RHT), which involved meetings with regional government, focus group discussions with community leaders and beneficiaries, and observations of public works sites. Meetings were also conducted between British Embassy Addis Ababa and the World Bank.
#### Actions following approval of this report
Following approval and finalisation of this report the programme team should ensure timely and full closure of the programme on the Aid Management Platform and ensure that lessons learnt are suitably shared with PSNP partners, the FCDO and the wider social protection community. A narrative and communications strategy should also be compiled, including case studies. The SEASN team should continue to work on outstanding recommendations with the Government of Ethiopia, the World Bank and other stakeholders.

## B: Theory of change and outcome assessment

	Starting point	Final result
Budget	£45,000,000	£40,750,464.44
Timeframe	The programme was originally approved as a humanitarian emergency response in September 2020. All funding was disbursed before the end of the 2020/21 financial year.	The programme started on 04 November 2020 - and ended on 03 February 2022
Outcomes	Enhanced resilience to shocks of extreme poor and vulnerable rural households in PSNP woredas
	Number of new woredas in which PSNP systems have been established and are being used for core PSNP payments	70 against target of 70 / Source: MIS, Quarterly and Annual Progress Reports
	Average number of months that PSNP households report experiencing food shortages in the past 12 months (disaggregated by male and female headed households)	Independent impact evaluation evidence, with data collected from November 2019 to November 2020, indicates that PSNP households experienced lower food shortages than comparable non PSNP households, but it is too early to indicate results beyond this point. / PSNP beneficiaries experienced 1.7 months food gap for the year between July 2019 to August 2020 compared to 2.1 for non PSNP beneficiaries. / Source: Independent impact evaluation endline survey (IFPRI 2020)
	Percentage of client households reporting use of harmful coping strategies (disaggregated by male and female headed households)	Independent impact evaluation evidence, with data collected from November 2019 to November 2020 suggests that PSNP households were less likely to reduce expenditure on health, education and agricultural inputs than non PSNP households, but it is too early to indicate results beyond this point. / PSNP households were less likely to reduce expenditures on health and education by 7.7 percentage points and were less likely to reduce expenditures on agricultural inputs (fertilizer, seeds and livestock) by 13 percentage points. / Source: Independent impact evaluation endline survey (IFPRI 2020)

#### Overall assessment of programme outcomes, sustainability and VfM
Progress towards outcomes
PSNP has expanded it’s operations to 70 new woredas, in addition to the 403 established woredas, although readiness and capacity of PSNP systems and staff capacity varies across these areas. The evidence that is available also suggests that PSNP has enhanced levels of resilience to shocks of the extreme poor and vulnerable households. Although this suggests that SEASN outcomes have successfully been met, the endline impact evaluation of PSNP4, uses data collected in 2020, and no outcome level data is yet available beyond this point to monitor performance during the SEASN implementation period. The data that is available indicates that PSNP reduced the period by which beneficiary households experience food shortages, and the number of beneficiaries using negative coping strategies to deal with food insecurity. During SEASN implementation the majority of PSNP beneficiaries have received timely and critical transfers (65%) that have protected people’s welfare and the government of Ethiopia are also maintaining their own financial contributions to PSNP, which is predicted to stand at 18% of the total budget for the Ethiopian Financial Year 2015, which ends in July 2022.
[note] PSNP endline impact evaluation, IFPRI 2022

Despite strong progress towards overall outcomes, PSNP operations have been severely constrained by the conflict in northern Ethiopia. Prior to the conflict PSNP was operational in 55 of Tigray’s 94 woredas in all zones except the Western Zone and had a caseload of 1,010,752 people of which about 562,000 (56%) were women. However, in late 2020, PSNP clients were reached through emergency blanket food distributions, where no distinction was made between PSNP clients, humanitarian assistance clients and other food insecure households. Since June 2021, PSNP has not been operational in Tigray and responsibility for reaching people in need has been handed over to the World Food Programme, who have been severely constrained by access limitations. In Amhara and Afar regions, where PSNP has a caseload of 1,890,985 and 562,080 beneficiaries respectively, PSNP services have also been severely disrupted. At time of the December 2021 Government and donor Joint Review of Implementation Standards (JRIS), 21 of the 34 PSNP Woredas in Afar and 51 of the 70 PSNP woredas in Amhara were affected by conflict and related displacements.

Value for Money
PSNP is cost-effective, providing good value for money. Clearly, however, not all components performed as hoped. PSNP social transfers have proved effective in alleviating poverty and preventing food security crises and asset losses, and the public works component has built community assets which help to improve climate resilience. Yet nutrition-sensitive features have not so far been sufficient to curb malnutrition, and livelihood interventions appear unlikely to set households on a sustainable path of asset accumulation so that they graduate out of poverty. On both of these fronts, balancing more investment in the complementary rural services that would appear to be a prerequisite for further progress, against increasing coverage rates and transfer values annually to cope with local food inflation will be a key decision point for the GoE and PSNP donors in terms of overall programme effectiveness. Financing pressures will continue to make this decision more challenging.
[note] White, P. (2020) Ethiopia’s Productive Safety Net Programme, Phase 4, 2015/16 – 2019/20: Value for money assessment, DFID Ethiopia

Theory of Change
The overarching theory of change will link the safety net that pays the right amount to the right people at the right time and increased resilience to shocks at household and community level for the poorest, most food insecure people in Ethiopia. The productive public works component of the programme also supports further resilience -building at community level and addresses the productiveness of agricultural land on which beneficiary communities rely. A detailed theory of change can be found in Annex A.

## C: Detailed output assessment

Output number and title	Output 1: Timely and adequate transfers received by eligible core caseload of PSNP clients
Output score	A
Impact weighting (%)	75		Impact weighting revised since last AR?	No

Output indicator		Starting baseline	Final logframe target	Final result achieved
1.1 Number of core rural PSNP program clients (disaggregated by male (M) and female (F))		7.9 million (M: 3.768m / F: 4,132m)	7.9 million (M: 3.768m / F: 4,132m)	Moderately unmet: 6.8 million
1.2 Percentage of payments made to core clients according to the program’s performance standards for timeliness		T:55	T: 60	Moderately exceeded: 65%
1.3 Number of core client households receiving their transfers in electronic accounts		1.037m	1.1m	Met: 1,210,058
1.4 Percentage of female clients who own and operate electronic accounts (Percentage)		0	46	Met: 46% everage (49% in Amhara, 46% in SNNPR, and 43% in Oromia)

Output 1.1 PSNP has a permanent caseload of 8 million beneficiaries but due to the conflict in Tigray, more than 1 million of these beneficiaries were not reached through PSNP systems from June 2021 onwards. Blanket food distributions were provided between December 2020 and June 2021, but then PSNP ceased to operate in Tigray. However, these beneficiaries remain part of the PSNP caseload and will be included in the operating budget in the event that access to the region improves.

Output 1.2 The programme target (60%) for the timeliness of transfers has been met during the period between April to June 2021, and the period between July to September 2021. The average timeliness was 65% of transfers reaching beneficiaries within 30 days of the month following the public works participation for all woredas and 69% for woredas when taking into consideration those conflict affected areas.

Output 1.3 Just over 1.2m core client households received their transfers in electronic accounts by the end of December 2021, exceeding against a target of 1.1m. In some regions including SNNP and Sidama, there was a smooth transition of E-payment from the microfinance institution (Omo Micro Finance Institution) to the Commercial Bank of Ethiopia in which 100% timeliness was ensured in transfer of payments for the region and woredas. However, multiple payments scheduled for September, October and November in other areas were delayed and paid with December payments. As such, the data in the above table does not adequately capture the delays that were experienced by some clients (with significant negative impacts on clients).

Output 1.4 46% of female clients operate and own their electronic accounts, meeting the target of 46%. The availability of regional data is helpful and ensures that regional disparities are made clear – 49% of female clients exceeding the target in Amhara, compared to 43% of clients which does not meet the target in Oromia. If performance against this target continues to be lower in Oromia the programme might consider a more focused targeting on this indicator in Oromia, drawing on lessons from regions where the target is being met or exceeded.

#### Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme
Dissaggregated data against indicator 1.1 and the gender specific indicator 1.4 allows equity to be tracked but more data is required to assess performance for other protected characteristics such as people with disabilities. It is also noted that a new PSNP pilot is being conducted in 2022 to target transfers at female household members, to review any gendered differences in consumption patterns. There are major opportunities for the use of e-payments to improve efficiency of the transfer process and to reduce beneficiary transaction related costs, but we do not yet have data in this area. We know that PSNP transfers have a strong multiplier effect, with local communities benefiting from enhanced resilience and improved productivity. An FCDO assessment in 2020 indicated that PSNP and pulic works bring in $2.08 for every $1.00 invested. This analysis also suggested that benefits of $2.25 (highlands) and $2.88 (lowlands) ensure for each $1.00 transfers in terms of prevented losses from climate induced shocks. Howeber, inflationary pressures are testing the effectiveness of PSNP transfers, given increases in food prices, so the market value and benefits of core transfers will need to be adjusted in the future.
#### Lessons learned through this output, and recommendations for future programming
Apply a new model to manage risk in conflict affected areas: SEASN has responded to contextual challenges and changes that could be described as unprecedented, which although significantly impacted on the timeliness of some payments, has provided a model for the future management of PSNP risks in conflict affected areas. This includes lesson learning on when to transfer responsibility to third party actors in non-federal-government controlled areas, how to conduct post-distribution monitoring to trace the flow of funding and how to provide guidance to conflict affected regions and woredas on risk mitigation. The programme team should harness this learning to enhance risk preparedness and mitigations for PSNP in the future, and decision making processes on when to transfer resources to humanitarian actors.

Reduce the focus on additional components in future phases of PSNP if finance pressures continue: The core focus of PSNP should be to provide timely, predictable, adequate and well targeted social assistance to the extreme poor and chronically food insecure people in rural parts of Ethiopia. If financing pressures continue in future years and contextual risks increase that threaten the viability of this core focus, the UK should seek to reduce the investment in components that act in addition to cash and food transfers, such as livelihoods interventions, public works capital investments and linkages to social services.
#### Sources
* PSNP Donor CoordinationTeam (DCT) annual report 2021
* Joint Review and Implementation Support (JRIS) mission Feb 2022
* FCDO SEASN AR, 2021

Output number and title		Output 2: Shock-responsive transfers received by eligible clients when needed
Output score		A+
Impact weighting (%)		5%	Impact weighting revised since last AR?	NA

Output indicator	Starting baseline		Final logframe target	Final result achieved
2.1 Number of person months of assistance provided	5.7mil		No target set as based on needs identified in-year	Met: 4,008,691
2.2 Preparation and adoption of a geographic expansion and caseload allocation plan	No plan prepared		Plan prepared and adopted	Met: Geographic expansion and caseload reallocation plan has been prepared and adopted and communicated for all concerned parties. Targeting ongoing in most regions.
2.3 Key shock responsive systems established and operational	Not operational		Scalability manual prepared and adopted	Moderately unmet: Manual prepared and adopted, but early warning dashboard and drought response assistance plan submitted in December has substantial quality issues and requires further amendment.
2.4 Number of women, men, boys and girls receiving WFP food assistance in northern Ethiopia, disaggregated by beneficiary category (age, gender and disability).	Number of women, men, boys and girls receiving food assistance, disaggregated by beneficiary category (age, gender and disability)		364,666	Substantially exceeded: 885,617* / (460,520 Male and 425,096 Female) / Disaggregated data is not available for disability and age / Source: Counterpart Post- Distribution Report, WFP Post Distribution Monitoring and beneficiary contact monitoring.
2.5 Quantity of WFP food commodities distributed in northern Ethiopia as a percentage of the planned total. / Wheat: 5,470 mt / Pulses: 547 mt / Vegetable oil: 165 mt	Quantity of food commodities distributed as a percentage of the planned total. / Wheat: 5,470 mt / Pulses: 547 mt / Vegetable oil: 165 mt		100%	Exceeded: More than 100% of planned commodities were distributed, exceeding original targets for wheat and pulses, but not for vegetable oil. / Wheat: 6,273.84mt / Pulses: 865.65mt; / Vegetable oil: 116.77

Overall system level progress on shock responsive transfers has been minimal and frustratingly slow. Although assistance was eventually provided at scale, both for the shock response and humanitarian distribution in northern Ethiopia, early warning systems enhancement, evidence based needs identification and timely transfers have not materialised as originally envisaged.

Output 2.1. PSNP distributed food to more than 4 million targeted Humanitarian Food Assistance (HFA) beneficiaries through the 3rd, 4th and 5th rounds of distribution between May 2020 and December 2021. This is broken down as 1st and 2nd round combined 1,170,570 people, 3rd round 891,843 people, 4th round 891,843 people, 5th round 1,054,435 people, which is a total of 4,008,691 (person months). Each round is a month. However, the timeliness of these transfers has not been assessed as part of this review, but delays in allocation were experienced due to the absence of an effective early warning system and response plan.

Output 2.2. Geographic expansion of the programme has been completed, with 70 new PSNP woredas now operating, although challenges have been observed in terms of overall PSNP coverage due to the ongoing conflict in many parts of the country which has impacted delivery in 127 PSNP woredas, and limited capacity of newly established regions including Sidama and South-Western Region to deliver timely transfers in newly expanded woredas that lack administrative capacity.

Output 2.3. The Early Response Plan (ERP) document, which triggered the release of the World Bank’s (WB’s) Contingent Emergency Response Component (CERC) financing for shock response amounting nearly $50 million was submitted by Food Security Coordination Directorate (FSCD) in December 2021. FSCD also developed and approved a revised shock response operational manual which released $1.5m by complying with a WB Performance Based Condition. Further to this, two additional PBCs, the Early Warning dashboard and the Drought Response Assistance Plan were submitted, though significant quality gaps remain when assessed against fulfilling the PBC terms and conditions. This means that resource allocation has not been as evidence based, nor as timely, as it could be. It should also be noted that planned institutional consolidation between the National Disaster Risk Management Commission (NDRMC) and FSCD did not take place, which has hampered the efficiency of the humanitarian food assistance response in PSNP woredas.

Output 2.4. Within this output, progress against the FCDO-supported World Food Programme (WFP) component should also be reported. This additional component was set up following a GoE request in March 2021 to provide additional support to conflict-affected regions and is part of a humanitarian relief activity designed principally to meet the immediate food security needs of conflict-affected people, PSNP beneficiaries and IDPs. The component planned to deliver in-kind food to food-insecure beneficiaries under the Humanitarian Response Plan (HRP) and PSNP clients, in conflict-affected areas in the north of Ethiopia. Almost 365,000 beneficiaries were targeted for assistance in 24 Woredas. Following road blockages on the way to Tigray and increased need in the neighbouring regions, WFP expanded this assistance to also support Woredas in Zones 2 and 4 from Afar and North Gondar in Amhara. WFP worked with tier two partners Samaritans Purse, Food for the Hungry and World Vision to deliver general food distributions in the target locations. 822,410 beneficiaries were reached across 38 Woredas in 9 months. Of these, 652,134 were in Tigray across 24 Woredas, 124,716 were in Amhara across 6 Woredas and 45,560 were in Afar across 8 Woredas. Disaggregated data was available for gender (48% of beneciaries receiving food assistance female) but does not appear to be available on age and disability.

Output 2.5. WFP distributions were 100% food, rather than cash, due to the lack of market functionality in conflict affected areas. Of the food procured, it should be noted that additional food was procured and distributed compared to that originally envisaged but 101.85MT (1.3%) were reported by WFP as losses incurred during transport and storage due to adverse weather conditions and elongated storage periods. The latter were inevitably caused by delays in distribution due to the security situation.
#### Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme
Substantial effectiveness gains could be made with a functional early warning system that assesses food insecurity risks and a financed response plan that allocates resources according to levels of need through the shock responsive PSNP. The existing system relies on a time consuming negotiation process between federal and regional government which delays disbursements and the effectiveness of targeting resources to those most in need.

Although the WFP component led to a significant amount of food wastage, this component was delivering within a difficult and changeable context. The delivery of food distributions in Tigray were affected by road closures, insecurity and lack of fuel which undermined effectiveness as in some areas distributions were not possible and efficiency as the process to deliver this in-kind support became even more complex. The decision was taken to repurpose some of this food aid to neigbouring regions of Amhara and Afar to maintain efficiency and effectiveness and to respond to growing needs there and ensure that access constraints did not lead to more food spoilage
#### Lessons learned through this output, and recommendations for future programming
Managing timely commodity distributions and losses: While some of the issues related to commodity losses were not fully under control of WFP at times, especially relating to security reasons, WFP continues to proactively monitor and address challenges to avoid such losses. Customs clearance issues with deliveries were further escalated and controls were established to avoid further such scenarios resulting in losses, such as more appropriate storage conditions at borders.

Shock response technical assistance: Given the technical issues with the existing shock response early warning system and financing for PSNP, we have recommended that the UK funded Building Resilience in Ethiopia programme invests in an evidence synthesis review of alternative early warning systems for the GoE, to underpin future improvements that need to be made for PSNP. This process needs to be fully owned by GoE.

Internal displacement: This PCR notes the large number of conflict induced Internally Displaced Persons (IDPs), some of which are displaced PSNP or non PSNP households, that have been hosted in PSNP woredas of Afar and Amhara regions during the past year. Whilst a large majority of these IDPs are in critical need of food assistance, delivering food assistance through the PSNP’s shock response mechanisms has not taken place and IDPs have instead been covered by humanitarian actors. Although PSNP beneficiaries can reclaim any transfers in their home communities if they return within 12 months, and are eligible in new communities after two years, new guidance should address this issue by highlighting what provisions would need to be made to support displaced PSNP beneficiaries whilst they are temporarily away from their home communities (e.g. portable client cards and electronic transfers).

Sources
*DCT annual report 2021
*FCDO AR, 2021
*WFP component progress report, 2022

Output Number and Title	Output 3: Public Works implementation and management
Output Score	B
Impact weighting (%)	5%	Impact weighting revised since last AR?	NA

Output indicator	Starting baseline	Final logframe target	Final result achieved
3.1 Total area of land (hectares) treated through area enclosures, rangeland management, soil and water conservation, forage and forestry activities	0	400,000	Moderately unmet: Up to December 2021, 312,008 hectares treated.
3.2 Percentage of public works planned following the GoE’s national watershed/rangeland guideline (disaggregated by highlands (HL) and lowlands (LL))	T: 82 / HL: 92 / LL: 62	T: 85 / HL: 90 / LL: 80	Moderately umet: 78% / HL: 89 / LL: 33
3.3 Percentage of public works screened in accordance with Environmental and Social Management Framework (ESMF) (disaggregated by highlands (HL) and lowlands (LL))	T: 76 / HL: 91 / LL: 61	T: 86 (82 in BC) / HL: 97 (95 in BC) / LL: 75 (68 in BC)	Substantially not met: No data available due to delayed Public Works annual review
3.4 Percentage of pregnant women participating in PW transitioning to temporary direct support before or at 4 months	35	35	Substantially not met: No data available due to delayed Public Works annual review

Output 3.1 Public Works activities are selected on the basis of their ability to address community level vulnerability to drought. Projects consist of soil and water conservation measures, nurseries and forestry projects, road construction and maintenance and social infrastructure projects. Progress was made during the implementation period, with a total of 312,008 hectares treated, but this was disrupted due to Covid, the conflict and budget shortages. Of these 312,008 hectares, about 17,608 hectares of land has been treated with different soil and water conservation activities and 406,109 Person Day (PD) was utilized. About 2,218,768 PD have been used in this quarter and 20,605 hectares of land was planted with different forestry, agro-forestry and forage tree, shrubs and grass species. These climate projects have provided resilience to communities in southern Ethiopia coping with the impact of drought.

Output 3.2 The Public Works Coordination Unit (PWCU) has been provided with technical support, which has helped to ensure that guidelines were disseminated and followed. Despite this, the 78% of plans following the guidelines falls below the 85% target set. Further evidence is required to understand why lowland pastoral regions lag so far behind highlands regions on this indicator.

Output 3.3 Unfortunately no data is yet available on the compliance of public works projects with the ESMF under the screening process, due to delays in data collection. However, a new database of existing public works projects was developed and finalised, which allowed the collection of extensive M&E data from 7 regions. Geographic Information System/Global Positioning System (GIS/GPS) techniques were used for the watershed document revision and new watershed study, with five new watersheds studied and 650 existing watershed plans revised. Two rounds of both ESMF and GIS Training of Trainers (TOT) training has been given to regional Public Work (PW) staffs, and two regions (Oromia & Afar) have cascaded the ESMF training to woreda level staff.

Output 3.4 The current phase of PSNP makes provisions to remove the conditionality for pregnant women to participate in Public Works projects after 4 months of pregnancy and until 24 months post partum. No data is currently available to assess the implementation of this policy due to delays in data collection but informal data collected during an FCDO field mission suggests that the policy is being enforced by community leaders. As with output 3.4 the Public Works annual review has not been completed due to capacity constraints within the Ministry of Agriculture.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme
It is difficult to assess the value for money of this output due to the implementation challenges caused by a budget shortfalls. Whilst previous reviews have highlighted the positive climate related impacts of PSNP public works projects, and the potential of nutrition focused public works projects, the delays in implementation due to a lack of an approved capital budget for Public Works, the weak functioning of the Public Works Technical Committee and the need to revise Public Works activities to respond to post-conflict risks in Amhara and Afar, mean that there is an evidence gap in this area.

Lessons learned through this output, and recommendations for future programming
Strengthen monitoring and evaluation: there are substantial data gaps for public works projects, which should be addressed through improved regular public works monitoring at the federal level. This should include an in depth case study on why lowlands regions lag so far behind highlands regions on public works implementation.

Recommunicate primacy of cash principle: Given the public works budgetary challenges, which are likely to continue in future years, it is important that the woreda level adminstrators do not withhold transfers on the basis of beneficiaries not participating in public works projects that have been delayed. During the PSNP field mission in February 2022, this had to be reinforced to regional adminstrators. Federal government should continue to communicate this principle to the regions.

Respond to conflict impacts: Amhara and Afar regional adminstrators should undertake an assessment of the extent of damage to PSNP public works infrastructure, taking into account the ESMF requirements, and propose appropriate options, either as business as usual, exemption from PW implementation, or redirecting the PW towards rehabilitation of infrastructure and post-conflict community reconcilation. In conflict affected areas there should be a full assessment of unexploded ordnance prior to resumption of public works activities.

Sources
*DCT annual report 2021
*JRIS Feb 2022
*FCDO AR, 2021

Output Number and Title		Output 4: Linkages to available social services facilitated for core PSNP clients with emphasis on Permanent Direct Support (PDS) and Temporary Direct Support (TDS)
Output Score		B
Impact weighting (%)		5	Impact weighting revised since last AR?		N/A

Output indicator	Starting baseline		Final logframe target	Final result achieved
4.1 Percentage of TDS and PDS HHs who have accessed social services available locally, disaggregated by Temporary Direct Support beneficiaries and Permanent Direct Support beneficiaries	TDS: 35 / PDS: 42		TDS: 37 / PDS: 50	Substantially unmet: Data not yet available due to inter ministerial M&E system gaps (responsibility for this output sits between health, education and agriculture).
4.2 Number of children aged 1-5 years enrolled in child-care centres	0		12 childcare centres established	Moderately unmet: 45 ‘pilot centres’ established but discontinued due to conflict

Output 4.1 The current phase of PSNP places more of a focus on ensuring that PSNP beneficiaries can better access other local social services in their area, such as health services, safe childcare and nutritional advice. In order to facilitate these links a number of accomplishments have been achieved during the reporting period as outlined below but the reporting data has not been submitted by the government because of delays to joint ministry reporting systems being established by Ministries of Health, Education and Agriculture.
- Social Development Unit (SDU) has been established in FSCD that will be responsible to coordinate overall social development, linkages to available social services (LASS), Grievance Redress Mechanism (GRM) and nutrition issues.
- LASS Technical Committee established. The ToR for LASS TC has been adopted in a way that brings together senior officials from the Ministry of Health (MoH) and Ministry of Women and Social Affairs (MoWSA), with FSCD coordinating. This structure is now being replicated at regional and local level.
- Guidance for Nutrition Champions selection and operation has been developed. The guidance for nutrition champions has been developed by the LASS TC members and endorsed by the Technical Committee (TC). For the Guidance defines the objectives, scope of work, work relationship, and selection criteria for PSNP Nutrition Champions.

Output 4.2 It has been reported that women spend 8 times more time providing direct care to young children in Ethiopia than men, restricting women’s access to the labour. Childcare has been demonstrated to increase mothers’ labour supply and income. Recognizing the differential burden of childcare responsibilities, the PSNP piloted community-based childcare centers (CBCCs), which were run by public work participants with the goal of providing a fun, safe, caring, and stimulating environment for young children 1-5 years old, fostering the sensory-motor, cognitive, language, and socioemotional skills development of children, and developing and promoting good caregiving practices. A pilot was launched in Amhara, with 45 centres operational, providing child care to around 800 children, 411 of which were girls. As part of this scheme more than 1000 childcare workers received training, with materials developed by government. The childcare centers were managed and run by community facilitators and childcare workers selected from the community and the PSNP public work clients. Due to the conflict in northern Ethiopia, the intervention has been suspended, which meant there was no time to assess the impact of this scheme. However, an independent survey finds high levels of community buy in and the scheme should be resumed if and when the context stabilises.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme
Linking PSNP clients to available social services delivers additional benefits to PSNP clients with low additional investment which delivers a number of local economic benefits. The economy inputs of this intervention are merely the linking process itself delivered by MOLSA and supported by the World Bank, but the results to be delivered are significant, boosting equity for beneficiaries that are affected by multiple disadvantage criteria and supporting increased efficiency for support received by beneficiaries under PSNP / SEASN if they are receiving twofold support through this programme. Whilst progress has been mixed, the approach of this indicator demonstrates a good understanding of and commitment to good VfM.

Lessons learned through this output, and recommendations for future programming
New institutional linkages take time to establish. A Tripartite Memorandum of Understanding between the three government ministries involved in social service delivery (Health, Education and Agriculture) was finalized and endorsed at TC level but has still not been signed due to the recent restructuring among key government ministries, including the former Ministry of Labor and Social Affairs (MoLSA), which necessitated revisions. However, these delays suggest that the inter-departmental work remains complex and time consuming to establish.

PSNP childcare pilot should resume when conditions allow. From the small window of implementation of the child care pilot we can see that the findings from an independent baseline survey are indicative of the high demand for and economic potential of childcare centers. The finance gap on PSNP means that it will be challenging to resume this pilot, even if conditions stabilise, so alternative donor financing should be sought to restart implementation.

Sources
*DCT annual report 2021
*JRIS Feb 2022
*FCDO AR, 2021

Output Number and Title		Output 5: Tailored livelihood options accessed by eligible PSNP clients
Output Score		C
Impact weighting (%)		5	Impact weighting revised since last AR?		N/A

Output indicator	Starting baseline		Final logframe target	Final result achieved
5.1 Number of eligible clients receiving livelihood grant (total (T), off-farm (OF), female (F), youth (Y))	T: 0 / OF: 0 / F: 0 / Y: 0		T: 36,740 / OF: 18,370 / F: 18,370 / Y: 15,431	Substantially not met: many activities delayed

Ouput 5.1 The livelihoods component of PSNP5 was re-designed to focus on a targeted number of households, providing them with more intensive support and a timebound graduation approach. Despite some encouraging work to redesign interventions at the federal level and prepare for roll out, implementation has been severely disrupted by Covid-19 and budget restrictions. As a result no grants were disbursed during the reporting period but some progress was made in terms of preparations.

During the reporting period FSCD conducted awareness raising sessions with regions on preparatory activities and the livelihoods operational manual; allocated caseloads to 181 woredas; identified 14 ‘big push plus’ (higher quality, more tailored and increased value of support to fewer and better-targeted clients) woredas; profiled households in those woredas; developed new technical guidance for the big push plus interventions; and established a new Livelihoods Technical Committee at both the federal and regional level. This means that when financing becomes available for grant distribution and training, interventions should be able to start within a quick timeframe.

Clearly, the context has provided challenges to get this output up and running. The finance gap, conflict, covid and broader economic situation in Ethiopia mean ‘graduation’ as the desired outcome of the livelihoods interventions will be difficult to achieve, even if funding becomes available. This is especially the case for off farm pathways, with formal employment opportunities becoming more limited in Ethiopia due to the impact of Covid and macroeconomic challenges, and have yet to return to pre-pandemic levels. Some delays were within the control of government though, such as the placement of local development agents to support livelihoods interventions and delays signing memorandum of understanding amongst the regional implementing agencies.
#### Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme
Given that no livelihoods grants were disbursed and training did not take place, it is difficult to assess the effectiveness of this output. An independent evaluation of Phase 4 of PSNP demonstrates that livelihoods interventions delivered through PSNP increased beneficiary household level asset ownership but had a limited impact on food security, income generation and wellbeing. This led to substantial design amendments for PSNP 5, which have yet to be tested due to implementation delays.
#### Lessons learned through this output, and recommendations for future programming
Challenges of graduation from social assistance enhanced in fragile, conflict affected areas – graduation interventions for the extreme poor are challenging in stable conditions due to the wide range of factors that inhibit households from exiting conditions of poverty. This challenge becomes enhanced in fragile conditions as economic opportunities decrease and donor financing for livelihoods interventions becomes more constrained. In this context the right decision was made to protect core PSNP transfers at the expense of delaying the rollout of livelihoods interventions. When conditions allow this output should be resumed and closely monitored to assess impact.
#### Sources
*DCT annual report 2021
*JRIS Feb 2022
*FCDO AR, 2021
*Phase 4 IFPRI evaluation of PSNP

Output Number and Title	Output 6: PSNP management and capacity enhanced
Output Score	C
Impact weighting (%)	5	Impact weighting revised since last AR?		NA

Output indicator	Starting baseline	Final logframe target	Final result achieved
6.1 Number of woredas using MIS for key program functions	0	250	Moderately unmet: MIS is not consistently functioning yet at woreda level.
6.2 Number of client households with complete information in the registry	0	0	No target set within this time period and data collection for the registry has not yet started.
6.3 Percentage of payment recipients for whom client card has been issued	0	0	No target set due to mass re-targeting of PSNP
6.4 Percentage of woredas submitting monthly commodity flow and utilisation reports to regions and federal using the CMPM templates	92	92	Substantially unmet: 20 out of 129 woredas submitting CMPM data.

Output 6.1 The rollout of the Management Information System (MIS) has been delayed due to procurement and contract management issues in the transition from Phase 4 to 5 of PSNP, which undermined the timely completion of core system development workstreams, but notable progress was made in terms of overall system design and delivering associated training. World Bank experts have provided quality assurance support to MIS developers and training to more than 45 government officials to ensure that the design meets operational standards but the system is yet to be rolled out at the woreda level. 50 pilot woredas have been selected from three regions (Oromia, Amhara and SNNPR) for initial rollout, 150 woredas have also been connected to data and internet services through the Woreda Net; and further connectivity expansion work is underway in 11 additional woredas.

Output 6.2 There were also delays in the rollout of the household registry because of contractual issues with service providers that were due to collect data during 2020/21, but who experienced delays due to Covid. Subsequently the terms and conditions of these contracts had to be renegotiated which meant that the initial phase of data collection could not be completed before the end of December 2021, as per the original schedule.

Output 6.3 A full retargeting exercise was conducted in 2021 meaning that PSNP 5 beneficiaries were not issued with new client cards during this reporting period. The World Bank, in coordination with the government, also led a review process during January and February 2022 to assess the costs and benefits of issuing a standardised version of the PSNP client card, using a more durable material, which would generate economies of scale and could lead to an improved response for displaced PSNP beneficiaries to continue to access benefits in new regions in the future.

Output 6.4 The Ethiopian Disaster Risk Management Commission (EDRMC) and newly established Commodity Management Coordination Office (CMCO) have submitted timely quarterly commodity flow and utilisation reports to PSNP donors, including balances and distribution status. Whilst this has enabled the UK and other donors to monitor levels of commodities at the regional level, we have not been provided with monthly updates that provide woreda level figures. Instead the World Bank rely on a separate specifically conducted assessment as regions have failed to report the exact number of user woredas. This shows that the level of CMPM template usage is insufficient, indicating weak systems and a lack of capacity at the woreda level.

#### Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme
The value for money of this output has been compromised by the contracting of external agencies to deliver services for the GoE. There appears to be a weakness in external market capacity to deliver complex systems improvements related to MIS and the digitisation of other data sources, which is made more challenging due to the lack of digital infrastructure in remote rural areas. The expansion of electrification in Ethiopia and predicted enhancements in internet connectivity anticipated over the next 2-3 years should present major efficiency gain opportunities for core PSNP systems in terms of information management, that could then be used to improve programme effectiveness in a number of areas.
#### Lessons learned through this output, and recommendations for future programming
Technical capacity and bandwidth within GoE should be monitored – during Phase 4 of PSNP donors funded a technical capacity building facility, which employed 24 specialists in a range of different roles to support core government staff in complex technical areas, such as procurement, shock responsiveness, MIS and social development. This facility comes to a conclusion in 2022 and a long term solution that protects, builds and ultimately transfers to government capacity is yet to be identified. The UK should engage with GoE to identify short term capacity support options and a long term plan for staffing capabilities to be fully funded by GoE.
#### Sources
*DCT annual report 2021
*JRIS Feb 2022
*FCDO AR, 2021

D: Risk

#### Overall risk rating:
The overall risk rating of the programme upon approval of funding disbursement was considered as moderate. Upon completion of this review this rating has been upgraded to major as a result of changes in the context in Ethiopia. Importantly, many of the risk mitigation activities within the programme are well-established from previous phases of PSNP safety net programming. The programme benefits from an established governance architecture, a new risk mitigation strategy (agreed during the December 2021 JRIS) and good financial management by GoE, but the combination of Covid-19 limiting the monitoring and supervision of PSNP implementation, the conflict impacting on PSNP implementation, and a lack of donor financing to ensure all components of PSNP are fully financed, has increased the overall risk. A number of risks are worth highlighting:

Programming in conflict affected areas: during the course of this programme period conflict and inter-communal unrest has materialised in Tigray, Amhara, Afar on a large scale and within other regions on a small scale. This had a varying degree of impact on PSNP implementation. In Tigray it has effectively ended the operation of the safety net in that area, and required humanitarian agencies to take on the distribution of emergency food aid. In Amhara and Afar the situation has been fluid and regional adminstrations have remained functional, but a significant number of woredas have experienced significant damages and disruptions to PSNP implementation.

Conflict induced trauma and gender based violence: Evidence has shown that the risk of gender-based violence (GBV), and in particular intimate partner violence (IPV) and sexual exploitation and abuse (SEA), are very likely to have increased in the north of Ethiopia due to the conflict and may have increased across the south of Ethiopia due to the prolonged drought and economic crisis. In this context, women’s participation in the programme could exacerbate household tensions and would accordingly require sensitisation for male members of the household to the benefits of women’s participation for the entire household. An additional focus should be placed on preventing gender based violence in the Public Works and LASS components.

Severity of drought induced shocks: southern Ethiopia has experienced a prolonged drought, which has significantly increased the risk of food insecurity across parts of Somali region, SNNPR and Oromia, causing widespread displacement and leading to localised conflicts. Shock responsiveness financing has been released in response to this risk, but much work remains in consolidating work on early warning systems and scalability triggers to ensure that a timely and adequate amount of funding is released.

Commodity management risks decrease: Continued concern from development partners over the consecutive qualified audit reports led to several instances in which the Donor Working Group stated that Development Partner finance could not be used to purchase commodities until recommendations from audit reports had been addressed satisfactorily. Additionally, a legally binding covenant between the WB and GoE required substantial institutional consolidation between EDRMC and MoA regarding the management of commodities for the programme. This has led overall to an improved and more transparent approach by GoE to this aspect of the programme with the creation of a new Commodity Management Coordination Office.

Because of the changes in context, we have used our role as a PSNP donor to establish three additional assurance mechanisms to mitigate some of the emerging risks referred to above. These measures have all been agreed with the Government of Ethiopia, but remain at different stages of development and finalisation, as outlined below:

Traffic light assessment – the aim of this assessment is to ensure a shared understanding between the GoE and Development Partners on the status of PSNP implementation structures, human and physical resources and access in Tigray, Amhara and Afar regions. We have agreed a framework with GoE to provide data on an ongoing basis to ascertain which areas of Amhara and Afar are proceeding with implementation For green areas PSNP will continue as normal, for amber areas PSNP can continue once minimum requirements are met and monitoring is in place and for red areas PSNP should be temporarily suspended until access returns. An initial assessment has been provided by the government, which now needs verification to check if the minimum structures and PSNP systems are (re)established and the cost of damages.

Post distribution monitoring in conflict affected regions – the regular PSNP monitoring mechanisms such as the Kebele grievance redress process, the vertical monitoring lines through the food security and finance structures, and other reporting has been disrupted in those amber rated woredas. To mitigate this we proposed to GoE temporary post distribution monitoring in order to:
  1. Better understand the status, scale and progress of the food and cash distribution (both in terms of timeliness, quantity, and quality of operations).
  2. Highlight the functionality of PSNP related structures and systems in conflict affected woredas of Amhara and Afar regions.
  3. Identify challenges, shortcomings and opportunities in a timely manner so corrective actions can be taken for continuous improvement.
  4. Better safeguard against any unintended risks on the affected population during or after distribution by integrating beneficiary feedback into the implementation process.

National Independent Spot checks – The primary objective of this measure is to provide regular and timely external feedback to the Government of Ethiopia and DPs on key programme implementation performance against standards laid out in the original PIM. The purpose of the spot-checks is not to show impacts or changes over time by revisiting the same woredas, rather to show regional patterns on programme implementation to inform corrective actions. Depending on emerging issues, questions to be included in the spot-check may be revised during each round while maintaining a similar scope in terms of number of issues and woredas to be visited. Hence, the spot-checks will be designed and implemented in an agile manner ensuring suitability of the exercise to the stage the programme is in and the issues it faces. Each round, conducted annually, will sample 65 PSNP woredas spread over all regions. This has been agreed with the GoE and the procurement has started to find a provider and commence with an inception study.

Some additional risk mitigations that have been discussed with government, but not agreed by the time of this review, include:
- Identify and prioritize the most urgent capacity needs that need to be supported and replenished to ensure a minimum level of PSNP resumption in areas that were highly affected by the conflict (but now under Government control) and identify resources to fund these.
- Depending on how much time it will take to put in place the minimum level of capacity and structures in post conflict areas, agree with DPs and other implementing partners on how to reach PSNP clients in the interim.
- Revisit the social service linkages approach and guidelines with more emphasis on protection issues. Work with humanitarian protection cluster partners and women affairs sector to map out GBV referral mechanisms and provide the necessary support to GBV service providing institutions.
- Re-think grievance redress approach in post-conflict setting, for example independent/outsourced complaints mechanism through NGOs
- Track displacement status in PSNP woredas (displacement into the woreda and outside the woreda). In PSNP woredas where there has been large outflow of residents, put in place extra support to ensure that returning PSNP clients are able to access their missed transfers and are able to be supported in settling back.
- Re-think the feasibility and role of public works in post-conflict rehabilitation while still meeting safeguarding requirements. This means considering public works projects that are not normally under the PSNP plans but that may be a priority for communities that are rehabilitating their lives.
- Revisit the social service linkages approach with more emphasis on rebuilding demand for services (for example children in PSNP households that left school because of the conflict, linkages to available emergency related social services for example nutrition treatments).

Update on Partnership Principles
A programme level partnership principles assessment was conducted in November 2020, and January 2022 for SEASN. On the basis of the evidence assessed, we judged that, for PSNP specifically, GoE demonstrated credible commitment to PP1 (poverty reduction), 2 (respecting human rights and international obligations), 3 (financial management, accountability, corruption and the misuse of funds) and 4 (domestic accountability) but the current operating environment in Ethiopia and broader concerns around the approach of the Government to certain elements of these principles outside of the PSNP space, means that GoE commitment to these pricniples need to be regularly reviewed. For PSNP GoE’s commitment to achieving results for the poorest is demonstrated in growing levels of financial contributions to the safety nets, with an ongoing commitment to an increasing trajectory of domestic finance to the rural safety net. GoE has also committed to an annual streamlined reassessment of transfer value based on Central Statistical Agency inflation data. Safeguards have been maintained in the programme to mitigate against political manipulation of targeting or use of PSNP transfers as an incentive to induce compliance with GoE programmes and/or policy direction. Overall, there was good evidence at the time of funding dispursements of a credible commitment of GoE across the PPs and that aligned non budget support financial aid remained an appropriate mechanism to deliver results in poverty reduction and to strengthen systems to build resilience through the PSNP.
#### Annual Statement of Progress
Current level of fiduciary risk and direction of travel since last ASP	Moderate / Increasing
Specific assessment of corruption risk and direction of travel since last ASP	Moderate / Stable

A Fiduciary Risk Assessment (FRA) of the rural safety net was conducted in March 2020 and the overall conclusion was that fiduciary risk associated with PSNP was ‘moderate’. A light touch review of the key findings of this FRA was conducted in February 2022 and found that fiduciary risk was moderate but increasing in some specific areas.

Summary of fiduciary risk management processes in PSNP

All Channel 1 financing, including UK funding disbursed through SEASN, went to a designated PSNP account in the Ministry of Finance. For PSNP, funding from other Development Partners (DPs) also reaches this same account, although the majority is channelled through a multi donor World Bank Trust Fund. Resources then flow from the designated account to Government entities responsible for using the financing for activities to achieve the project/programme development objective. Also, at all levels, separate local currency accounts are opened specifically for project purposes. This is then transferred to the regional finance Bureaus, woreda finance offices, and the federal level implementers based on the annual work plan and budget upon the request of the Food Security Coordination Directorate (FSCD).

Financial assessment is carried out for all projects which use country systems. For PSNP-5, the World Bank conducts financial management (FM) assessment in line with the World Bank’s Policy and Directives on Investment Project Financing (IPF) requirements. The FM assessment focused on review of the World Bank’s FM implementation support mission reports, Interim Financial Reports (IFRs), Audit Reports, and discussions with the Ministry of Finance (MoF), FSCD and DPs to review the existence of adequate FM arrangements within the project. Experiences from the previous phases were also examined. The assessment concluded that the FM arrangements provide reasonable assurance that project funds will be used for the intended purposes. Implementation support missions reassess the risk of the projects and provide rating on the performance of the FM systems which are reported to management regularly.

Annual work plans and budgets are prepared by Ministry of Agriculture Food Security Coordination Directorate and reviewed and cleared by the Development Partners. During the review, DPs ensure that the operational budgets are consistent with eligible expenditures for the project. The budget is then included in the government budget, after going through the government system, and approved by the parliament.

At the federal level, the projects use the existing government accounting systems (either IFMIS or IBEX accounting software), and at the regional and woreda levels IBEX is used. According to the latest Interim Financial Report , out of 403 PSNP woredas (excluding the 55 woredas of Tigray), 323 woredas are using IBEX.

All operations have appointed finance management staff responsible for the whole project. Under PSNP there are 492 accountants and 425 cashiers at all levels excluding Tigray region (according to the last report there were 38 Accountants and 62 cashiers). This number varies slightly from quarter to quarter due to turnover until replaced. However, the overall staffing level meets the minimum human resource requirement to implement and deliver financial management activities to the necessary standard.

Disbursements by the Bank to designated accounts are based on the cash forecasts included in the quarterly IFRs. The disbursement considers the approved plan, forecast expenditure and resources available. Quarterly IFRs are consolidated by MoF and submitted to the Bank. These statements show the amounts received, expenditure per component and category as well as unused resources.

For disbursements for PSNP5 verification of results is carried out before funds are released.

Interim Financial Reports are submitted within 60 days of the end of the reporting quarter. The IFR format and content was agreed with MoF during negotiation of the project. Once the IFR is submitted to the World Bank and Donor Chair, DCT circulates to all DPs the IFR and a draft a review letter on the behalf DPs. World Bank provides quality assurance to the IFR review letter and the current Donor Chair signs and issues the letter to MoF. The review letter includes clearances of advances and expenditure documentation, comments and recommendations on: budget utilization, disbursements and financing status, outstanding balances, staffing and accounting, cash management, and any in accuracies.

PSNP is subjected to financial audit. As part of the annual financial audit, an interim audit is also conducted once per year. The annual financial audit report is due within sixty days of the end of the fiscal year and the interim audit is due within ninety days of the end of the semester. The audit is carried out by the Office of the Federal Auditor General (OFAG), or a qualified auditor nominated by OFAG and acceptable to the World Bank. The audit covers all project implementing entities. All projects are required to prepare action plans to rectify the audit report findings and to submit the status of the action plans.

For food resources, an independent commodity audit is undertaken annually. This builds upon the quarterly Commodity Flow and Utilization report that the Government prepares and submits to Development Partners. This is reviewed by the Donor Coordination Team.

As part of implementation of support of the project, World Bank carries out financial management (FM) supervision every six months. Currently, the FM supervision is being conducted for the period from July 2021-December 2021. The supervision mission reviews areas of budgeting, accounting, internal control, funds flow, financial reporting and external audit.

Bank staff also monitor procurement activities based on level of risk. Procurement monitoring measures include (i) post procurement review (PPR) where samples of those contracts which are not subject to prior review by the Bank are post reviewed to ensure compliance with the agreed procedure, which could further be enhanced by increase of the sample size; (ii) use of Independent Procurement Audit: in addition to the standard prior and post review procedures, where necessary and feasible, independent procurement audits are used for ensuring such compliance; (iii) mandatory use of the procurement planning, tracking, and monitoring tool (STEP); (e) close monitoring of contract management; (f) beneficial ownership disclosure in high value high risk contracts.

If misuse of funds is detected, the Bank has several remedies that serve as a deterrent. The most common handling of a misuse of funds is to declare such expenditures as ineligible, which requires the Government to revert the same amount to the Bank.

However, there remain a number of on-going issues:

- The finance gap has led to the suspension of core components on PSNP, due to a lack of planned disbursements from donors materialising.
- The use of manual paper based systems used for reporting purposes has heightened issues in those woredas that were affected by conflict. A number of woredas, to be confirmed, have experienced destruction to beneficiary lists, computers and other reports due to the conflict. It remains a priority for the Donor Working Group to roll out the MIS and electronic household registry over the next year.
- Consistent challenges remain in relation to those identified in 2020 in relation to commodity audits, although since then some progress has been made to improve commodity procurement through the establishment of a new joint EDRMC and MoA food procurement office, though it remains too early to assess the impact of this change.
- Examples of internal control lapses and weaknesses which appear to be minor but, when combined with less than optimum internal audit arrangements throughout government, and left unaddressed, could undermine the programme. These could be addressed through an Fiduciary Management Improvement Plan (FMIP);
- The high turnover of PSNP contract staff, particularly at sub-national level.

E: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

#### Quality of financial management and delivery against planned timeframe
Date of last narrative financial report	May 2021	Date of last audited annual statement	April 2021

#### Financial Performance
The overall FCDO programme budget was £45,000,000 of which £ 40,750,464.84 has been spent. Around 81% of the budget was transferred to GoE as direct financial aid, whilst due to the ongoing conflict, 8% was transferred to WFP as an alternative delivery arrangement to reach beneficiaries in Tigray, while the remaining portion was used to contribute to the World Bank Donor Coordination Team, who play a vital role in providing programme oversight and technical support to the government. A full breakdown is provided below.

#### Financial expenditure
Component	Budget	Forecast	Spend
Cash and food transfers to chronically food insecure households (financial aid)	Programme delivery	£8,400,000.00	£8,400,000.00
Public works infrastructure programming (financial aid)	ICF	£28,000,000.00	£28,000,000.00
World Bank coordination & research component	Programme delivery	£750,000.00	£750,000.00
Multilateral food response funding	Programme delivery	£3,600,000.00	£3,600,000.00
SEASN design budget	Programme delivery	£464.44	£464.44
Total		£40,750,464.44	£40,750,464.44

#### Performance of partnership
Overall the programme management performance of FCDO, the Government of Ethiopia, the World Bank and the World Food Programme has been broadly effective. Programme governance structures, including the PSNP Donor Working Group, which meets on a fortnightly basis and PSNP Technical Committees, which meet on a monthly basis, have functioned as designed. The multi-donor arrangement has been particularly efficient, with the UK working alongside 10 other PSNP donors to improve aid effectiveness and reduce the administrative burden on GoE. It should be noted though that GoE bandwidth to engage in strategic decision making processes and reform initiatives, such as shock responsive systems development, has been limited by multiple shocks in Ethiopia, which has caused delays in delivery of key results and results reporting.

Regular (6-monthly) JRIS missions have provided ample opportunity to evaluate and re-direct the operation of the programme. The regularity of JRIS missions has also helped GoE to provide up-to-date narrative reporting based on programme performance data, and allowed in depth analysis of operational challenges alongside both federal and regional programme officials. However, quarterly Director level Coordination Managament Committee meetings have not taken place, which has hampered progress on inter-departmental issues, such as effective collaboration on the linkages to social services component.

The World Bank Donor Coordination Team has provided expert support on key programme issues such as procurement, financial management and capacity development, working closely with technical advisers within the GoE. A new Donor Coordinator has been extremely effective at improving communication between donors, and between donors and the government. However, a number of challenging contracts, such as the evaluation, MIS, capacity building facility and household registry have faced procurement challenges, in terms of compliance with World Bank regulations and the quality of outputs produced, which should be monitored in the future.

Improvements in performance on key financial management indicators (accuracy of budgets, reduction in budget revisions and improved audit performance) have been seen from GoE, and additional support from the Donor Co-ordination Team has led to 6 years of unqualified financial audits for the programme. The programme Fiduciary Risk Assessment Annual Statements of Progress note these year on year improvements, in particular in low capacity regions such as Somali and Afar.

FCDO has been a key development partner and bilateral PSNP financial aid donor, acting as the Donor Chair between October 2021 and April 2022. The UK contribution through SEASN helped to ensure positive policy influence in a number of key areas, such as risk management, operating in conflict affected areas, addressing the financing gap and prioritising shock responsiveness.
#### Programme-level approach to monitoring and evaluation
PSNP is a heavily scrutinised and highly researched programme, with a wide range of evaluations investigating performance and impact since it’s establishment in 2005. This has shown PSNP to be an effective mechanism for improving food security amongst the extreme poor. In SEASN a new endline impact evaluation of PSNP was finalised, which demonstrated a number of critical issues requiring attention of the GoE for Phase 5, including beneficiary awareness of rights, functionality of grievance redress mechanisms and awareness of the primacy of cash principle amongst administrative staff.

GoE has also established a comprehensive system for monitoring of the PSNP which comprises (1) regular programme monitoring based in administrative data including beneficiary caselaoad, timeliness of payments, implementation of PW and progress indicators for livelihoods pathways; (2) quarterly financial reports on donor disbursements; (3) spot checks to assess compliance with programme implementation manual, conducted quarterly in a rotating sample of woredas; (4) periodic performance assessments examining key aspects of the programme (PW, livelihoods, grievance review mechanism) and other technical studies and reviews to assess performance and draw out learning; (5) annual financial, commodity and procurement audits;

Routine monitoring, however, has been weak due to continued reliance on paper-based systems and lack of adequate verification mechanisms (World Bank SEASN PAD 2021). The process of collating information for this PCR has brought to light the need for greater alignment of these different sources of evidence with indicators in the PSNP log frame. For some indicators, data is inconsistent or unavailable. It was anticipated that for SEASN, the rollout and use of the MIS will ease the burden of routine data collection and analysis and enable a shift to more real-time monitoring, but this has not materialised.

This system has been complemented by strategic level reviews conducted 6 monthly by the Joint Review and Implementation Support Mission (JRIS). These are led by GoE with participation from donors and DCT. Field missions have been suspended due to Covid but should resume in 2022, which will add value to the process.

#### Annex A: Theory of Change