## Annual Review Template

Title: Building Resilience Through Asset Creation and Enhancement II – South Sudan (ICF Programme)
Programme Value £ (full life): £54,6m		Review date: 04th July 2022
Programme Code: [AMP ID# 204888]	AMP start date: 04/09/2015	AMP end date: 30/09/2023

Summary of Programme Performance
Year	2016	2017	2018	2019	2020	2021
Overall Output Score	B	A	A	A	A	A
Risk Rating	Severe	Severe	Major	Major	Major	Major

DevTracker Link to Business Case:	Business Case and Addendum
DevTracker Link to results framework:

SUMMARY AND OVERVIEW

Description of programme

Building Resilience through Asset Creation and Enhancement (BRACE II) is the Foreign, Commonwealth & Development Office (FCDO) South Sudan’s flagship resilience and international climate finance project, aiming to increase the capacity of vulnerable households to cope with climate shocks and stresses, improve their food security and build better community relationships. The programme, originally due to end in March 2021, was extended until 2023 to maintain delivery of resilience building work during a period of global uncertainty, and to bridge the transition to a standalone multi-year humanitarian and resilience programme.

BRACE II has two delivery components and an independent monitoring and evaluation component. Component I began in 2015 and is delivered by the World Food Programme (WFP) and the Food and Agriculture Organization (FAO) in partnership in all counties of Northern Bahr el Ghazal (NBeG) and Twic County of Warrap state. Component II began in 2018 and is delivered by an NGO consortium led by World Vision (WVA) and implemented in Aweil North in NBeG; Gogrial West in Warrap state and Magwi in Eastern Equatoria state.
[note] FAO and WFP work with five cooperating partners: Norwegian Refugee Council (NRC) in Warrap and Concern Worldwide (CWW), Joint Aid Management (JAM), Action Against Hunger (ACF), World Vision (WV) in NBEG, while World Vision-led consortium consists of two national NGOs: Smile Again Africa Development Organisation (SAADO) and Support for Peace and Education Development Programme (SPDP).

The programme has four main objectives:

- Address immediate food insecurity and basic needs (provision of conditional cash assistance).
- Improve longer-term food security (support for agro-pastoral production).
- Increase capacity to absorb, anticipate and adapt to climate variability and extremes (support climate change adaptation).
- Improve community relationships and social cohesion.

BRACE II was designed to target areas of South Sudan that are highly food insecure but more stable than other parts of the country. BRACE II builds on a successful three-year pilot project, BRACE I, and was set up with two delivery modalities, one through the UN and one through an NGO-led consortium to enable FCDO South Sudan to compare approaches.
Context update

The seismic impact of the Covid-19 pandemic on the UK economy has forced the UK government to take tough but necessary decisions, and as announced in 2020, the UK moved to spending 0.5% of GNI as Official Development Assistance (ODA) in 2021. The UK have committed to review and confirm each year whether a return to 0.7% of gross national income is possible.

The move to 0.5% has resulted in changes to this programme, which is being adapted and will continue. This Annual Review reflects that the programme has had to refocus resources, already delivering against a new plan with new results targets. As a result, the findings of this Annual Review reflect on a programme in transition.

In South Sudan, three years of consecutive flooding with an increase in conflict-related violence, eroded coping mechanisms and exacerbated vulnerability. In 2021, a combination of excessive seasonal rains and overflow of the Nile river, Sudd wetlands, the Lol and Sobat rivers resulted in widespread flooding that have affected more than 835,000 people, particularly in Jonglei and Unity states, followed by Upper Nile and Northern Bahr el Ghazal states. FAO reported a 4.7% loss in cereal production compared to 2020, and devasting effects on livestock-based livelihoods with small ruminants recording the highest losses, more than 10 million livestock heads affected, threefold increase in livestock diseases and limited availability of forage. In Northern Bahr el Ghazal and Warrap states where BRACE II is implemented, flood-induced losses have been significant, with Aweil South and Aweil West counties, and Gogrial West, and Twic most affected.
[note] South Sudan Flooding Situation Report No. 3: Inter-Cluster Coordination Group - As of 14 December 2021 - South Sudan | ReliefWeb
[note] CFSAM 2021, unpublished.
[note] FAO flood impact report, 2021 SP5 Project profile template August 2019 (fao.org)

In 2021, South Sudan implemented several forex reforms aiming at reversing the trend of depreciation of the South Sudanese Pound (SSP). In July 2021, the Central Bank of South Sudan started to auction dollars on the foreign exchange market and commercial banks.

This has improved the appreciation of the SSP and narrowed down the gap between the parallel market, and official exchange rates that, together with a relative stability of commodity prices over the year, has translated into improved beneficiaries’ purchasing power. Despite cash transfers having mitigated the impact of shocks and stresses for some, humanitarian assistance has still been required over the year for the majority of the population. Flooding, coupled with the ongoing insecurity and population displacement have worsened food insecurity, resulting in 7.74m people (63% of the population) projected to experience high acute food insecurity corresponding to Integrated Phase Classification (IPC) Phase 3+ between April and July 2022. The Integrated Food Security Phase Classification (IPC) is an internationally recognised standard that provides decision-makers with a rigorous, evidence- and consensus-based analysis of food insecurity and acute malnutrition situation in a country to inform emergency responses as well as medium- and long-term policy and programming. It differentiates between different levels of severity of acute food insecurity (1) Minimal/None, (2) Stressed, (3) Crisis, (4) Emergency, (5) Catastrophe/Famine with each of these phases having important and distinct implications for where and how best to intervene as shown in the table below. In South Sudan the current IPC analysis shows approximately half a million more people in IPC3+ than at the last IPC analysis conducted in December 2020.
[note] This corresponds to the lean season, the period between planting and harvesting when job opportunities are scarce and food stocks deplete, resulting in higher risks for families to become food insecure.

Table 1: Acute Food Insecurity Scale classification developed by The Integrated Food Security Phase Classification (IPC).

Considering BRACE II implementation areas specifically, all counties are classified as IPC Phase 4 (Emergency) over the coming lean season (April to July 2022) with the exception of Aweil Centre in NBeG and Magwi in Eastern Equatoria, which are projected to be in IPC Phase 3. While food security has deteriorated in Twic compared to 2021, there were positive improvements in Aweil South due to a scale-up in humanitarian assistance.

County	IPC Classification, April-July 2022	IPC Classification, April-July 2021
Magwi	Phase 3	Phase 3
Gogrial west	Phase 4	Phase 4
Twic	Phase 4	Phase 3
Aweil East	Phase 4	Phase 4
Aweil North	Phase 4	Phase 4
Aweil Centre	Phase 3	Phase 3
Aweil South	Phase 4	Phase 4, with pockets of Phase 5
Aweil West	Phase 4	Phase 4

Summary supporting narrative for the overall score in this review
The overall score in this Annual Review is A; ‘Outputs Met Expectation’.

This review covers the period between January and December 2021 where the UK disbursed a total of £7,500,000 to partners. In 2021, direct cash transfers to beneficiaries represented 58% on average (£2,378,250) for the two components compared to 65% in 2020. This means the proportion of cash directly received by beneficiaries for every £1 disbursed in 2021 is 58p, which is lower compared to 65p for last year.

Despite challenges deriving from insecurity, climate shocks and uncertainty over budget, partners have been able to reach over 21,000 vulnerable households in highly food insecure counties with cash-based transfers (CBT) and skills development, maintaining a good value for money despite reduced budget. CBT have allowed participants to engage in community assets development that have in turned improved their ability to manage and bounce back from climate shocks and adapt to climate change.

This Annual Review has been undertaken by the FCDO South Sudan livelihoods advisor (SRO), together with the programme manager and the programme officer. The draft was shared with cross-cutting advisers across the FCDO office for inputs and with BRACE II partners for fact checking. The report is the result of a desk-based review of partners’ quarterly reports, annual reports, partners’ M&E data, Third Party Monitoring (TPM) factsheets and partners’ interviews.

Output Scoring Calculator

A++	138% and above	Outputs substantially exceeded expectation.
A+	113% - 137%	Outputs moderately exceeded expectation
A	88% - 112%	Outputs met expectation.
B	63% - 87%	Outputs moderately did not meet expectations.
C	Under 62%	Outputs substantially did not meet expectations.

Update on recommendations from last year:

Most of the key recommendations from last year have been acted upon. This includes programmatic updates such as updating logframes, reviewing value for money indicators, documenting lessons and advancing the BRACE II evaluation agenda. Details of these are in the relevant sessions of this report. The following is an update on other recommendations formulated last year:

- In 2021 the British Embassy in Juba (BEJ) initiated the development of a cross Embassy resilience strategy which articulates links between resilience and peacebuilding programming, therefore strengthening social cohesion outcomes across the BEJ portfolio. In addition, the FCDO are engaging with the Conflict Sensitivity Resource Facility (CSRF) to provide technical assistance to the Partnership for Resilience and Recovery (PFRR) to operationalise the humanitarian – development - peace nexus in South Sudan.
  [note] The CSRF is a joint donor initiative funded by UK, Switzerland, Canada and the Netherlands, initiated in 2016; it supports the use of conflict sensitivity in donor strategies, policy decisions and programmes in South Sudan.
  [note] The PfRR is of group of donors, UN Agencies and NGOs started in 2018; brings the UN’s “New Way of Working” together with the support of multiple donors and non-governmental partners in a commitment that shifts the focus from “meeting needs” to “reducing needs, risks, and vulnerability”. It is now being revamped to operationalise the HDP nexus in South Sudan.
- Evidence of work carried out by partners including alternative livelihoods options in predominately pastoral communities are being collected to inform the future humanitarian and resilience programme starting in March 2023 and captured in the above-mentioned strategy.
Due to several FCDO budget uncertainties including reductions and belated confirmation of funds that have limited forward planning and adjustments in current implementation, some recommendations formulated last years were not acted upon, such as the review of the theory of change that was put on hold.

Budget constraints have not allowed the team to strengthen the gender and inclusion outcomes of the programme, especially protection against Gender-based Violence (GBV). These recommendations will be considered whenever additional resources are available. Despite the inability to include new components addressing GBV due to reduced resources, partners have been able to report progress on recommendations provided in the WFP 2019 Rapid Gender Assessment.
Main lessons from this year:

Due to connectivity issues, access and limited ownership of mobile phones, and literacy levels, use of mobile money is still a challenge in South Sudan. While this is increasingly used, it is not yet the preferred method used by beneficiaries. Partners are exploring the use of mobile money and continuing discussions within the South Sudan Inter-Agency Cash Working Group (CWG) on how to increase access and use of mobile payments. The UK has funded a centrally managed programme on the use of digital technology in Protection of Civilian and Internally Displaced Persons (IDP) sites. Teams in London and Juba are working together to share lessons.

Monitoring data from both components shows that the highest achievements in terms of asset construction and maintenance, have been in counties which have largely been unaffected by floods. While this is a positive achievement of the programme, it does not show how assets built through the programme have supported communities to mitigate risks from excessive flooding. The BRACE II evaluation to be undertaken in 2022 will investigate how communal assets have strengthened resilience of those counties most affected by floods.

A partners’ learning event has highlighted the need to review the cash-based transfer approach which is currently the same across counties and does not consider needs based on context specificity. This should include a review of transfer values (also in view of seasonality), distribution dates and timelines, as well as whether a county-specific response/approach should be tested.
Major recommendations for the year ahead

Given the disproportionate contributions of the two components across all outputs over the years, the FCDO team should review the equal weighting of the two components in the log frame. A proportionate weight would give a more accurate picture of the programme's overall performance. However, given the programme is in its final year of implementation, this could represent a challenge for consistency of the approach used. It is recommended that the programme team assesses implications of a significative adjustment of weighting of the two components across all outputs based on confirmed overall funds for 2022/2023.

During the partners’ learning event at the end of 2021, questions and discussions about balancing emergency, resilience as well as market development activities in BRACE II counties were prominent. BRACE II learning represents an opportunity to advance the operationalisation of the humanitarian - development- peace nexus in the country. Future resilience building interventions in more stable parts of the country should be informed by findings from the upcoming evaluation of BRACE II as well as learning from previous Third-Party Monitoring (TPM) and partners.

Lack of TPM from April 2021 onwards due to reduced budget and overall inability of the FCDO team to carry out field visits due to security restrictions that do not allow travel in remote rural areas of the country, significantly limited the situational awareness of the FCDO team, and also its function as quality assurer. Working to facilitate field visits to address these constraints is a priority given the importance of observations, direct communication with downstream partners and as part of overall monitoring the work of partners.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

BRACE II was designed in 2015 to respond to both the immediate food insecurity needs that were exacerbated by the crisis in 2014, and to improve the resilience of South Sudanese individuals and communities to climate shocks. Since then, multiple violent conflicts, a deteriorating economy, unprecedented flooding, and the social and economic effects of the COVID-19 pandemic, have resulted in a dire humanitarian situation. In 2022, 63% of the population is projected to be severely food insecure (IPC3+), a 7% increase from last year.

Although the BRACE II theory of change has evolved over the life of the programme, its causal impact pathway did not fundamentally change. The latest theory of change is shown below.

Figure 1: BRACE II theory of change draft for revision in 2020.

BRACE II uses a ‘Cash for Assets’ approach in which vulnerable households receive assistance in the form of cash or food transfers, under the condition that they work on the creation or rehabilitation of ‘assets’, such as anti-flooding dykes, clearing new farm land, creating water ponds, etc. This approach has multiple benefits. The food assistance immediately addresses food insecurity, while the creation or rehabilitation of assets reduces the risks and impacts of climate shocks and improve beneficiaries’ ability to produce food. Complementary activities are also implemented to improve agricultural productivity, including access to better agronomic practices and increased skills and awareness on key areas. Furthermore, communities decide together which assets they would like to create or improve and then work together to deliver this, helping to build community cohesion.

A mid-term evaluation, completed in 2019, recommended revising the theory of change based on clear, measurable interpretations of terms such as resilience, climate risk, climate resilience, vulnerability, food insecurity, and climate related causes of food insecurity. It also recommended an examination of the existing assumptions as key livelihoods drivers have changed, along with revisiting impact indicators to better reflect actual pathways to resilience and ones more likely to reflect the value addition of BRACE II outcomes.

In the last two years of the programme, 2020 and 2021, the overall budget uncertainty has made planning and adjustments difficult in both short and the long term, therefore these recommendations formulated in 2019 were not actioned. Budget continuity is essential in resilience programming, and it is strongly recommended that this requirement is factored in future resilience interventions to deliver better value for money and sustainability.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Regular monitoring of partners does not include collection of data towards all outcome level indicators as indicated in the results framework. The available data is presented below to show progress while a final evaluation planned for 2022 will provide a full assessment against all indicators.

Impact: The period under review has been characterised by a context of worsening food insecurity in the country overall as a result of third year of excessive flooding and increase in subnational and localized violence compared to 2020. UN partners’ reporting data also tells us that compared to the baseline (2016), the prevalence of moderately and severely food insecure households in counties where BRACE II is implemented, decreased considerably from 92% to 38% at the end of 2021 (WFP), with increased stability and better market being the main reasons behind this significant improvement.

Impact level information measured by the FAO Resilience Index Measurement and Analysis (RIMA), indicates a significant deterioration from the previous year:

	Resilience Capacity Index
	2017	2018	2019*	2020	2021
Aweil Centre	26.23	31.48	23.39	39	28.63
Aweil East	34.68	37.19	29.02	34.6	24.67
Aweil North	32.82	42.96	31.10	31.3	27.31
Aweil South	23.42	29.61	30.47	30.9	31.66
Aweil West	31.83	31.90	42.05	40.9	30.96
Twic	30.31	33.21	38.66	35.9	28.90
Magwi		32.01	29.04	na	39.29

Figure 2: Resilience Capacity Index (higher number=more resilient).
* 2019 figures are not comparable to previous years due to a change in method but can be compared to 2020 results.

The information presented in Figure 2 is based on data collected at household level, through the FAO RIMA approach that is used to calculate the Resilience Capacity Index (RCI). The RCI measures a household’s capacity to withstand stresses and shocks and it is constructed based on the four pillars of resilience - assets, social safety nets, adaptive capacity, and access to basic services. Latest data show a deterioration in resilience indicators in BRACE II areas between 2019 and 2021 which is confirmed by the worsening of negative coping strategies such as selling productive assets or reduced frequency of meals adopted by households and reduced access to basic services, compounded with climate shocks.

Final Outcome (FO): Improved food security and better community relationships
FO1: prevalence of poor and borderline food consumption, disaggregated by sex of household head (Food Consumption group)
During the review period both components were able to provide information against final outcome indicator 1. The Food Consumption Score (FCS) is a composite indicator measuring dietary diversity, food frequency and nutritional importance of the food consumed over the one-week period prior to data collection. If poor and borderline food consumption scores reduce, it means that more households have acceptable food consumption characterized by more diverse foods, more nutritious foods and more frequent consumption of these foods. In 2021 both components show an improvement in household food consumption.
The survey conducted under Component II shows that there was an improvement since 2019 in the food consumption score in BRACE II areas: 4.93% of respondents, compared to 6.10% in 2020 reported that their food consumption was poor. The magnitude of this progress is outstanding if compared to 51% in 2018. However, given significant donor-funded interventions have been implemented in BRACE II areas since 2018, this can be partly but not solely attributed to BRACE II.
The prevalence of poor and borderline consumption surveyed in BRACE II areas under Component I, shows that compared to the same period in 2020, poor and borderline food consumption has reduced amongst BRACE II households; in other words, more households in 2021 have acceptable food consumption.

Poor and borderline food consumption in BRACE II areas
Baseline		2019		2020		2021
Component I (2016)	Component II (2018)	C1	C2	C1	C2	C1	C2
93%	51%	32.6%	29.6%	62.3%	6.1% (only poor)	47%	4.93%%

Figure 3: Prevalence of Poor and borderline food consumption

FO2: Diet diversity score of targeted households, disaggregated by sex of household head (HDDS)
The dietary diversity of households (DDS) represents a households’ ability to access a variety of foods and nutrient adequacy. In 2021 under Component I, compared to the same period in 2020, the DDS has slightly decreased with a household consuming food from about three food groups on average (from 3.8 in 2020 to 3.30 in 2021). The reduction is more significant if disaggregated for female headed households; in 2020 female headed households consumed about four groups on average and in 2021 only three groups, while this reduction is minimal for male headed households.

While the HDDS does not account for intrahousehold difference in access to different foods, especially for micronutrient adequacy of the diet of women of reproductive age and children under 5 years, it is important to understand what the drivers for this reduction are, as this is the second year that HDDS decreases. As the indicator often reflects socio-economic status of the household and their ability to buy different foods, possible reasons include delayed cash transfers distributions, due to belated confirmation of funds, compared to 2020 and effects of limited access to markets and high food prices in 2020, but also recurrent climate shocks. Further analysis under Component I will be made during the analysis of the Round 1 Post Distribution Monitoring (PDM) data.

FO3: Proportion of targeted households implementing crisis and emergency strategies, disaggregated by sex of household head (Livelihoods Coping Strategy Index)
The Livelihoods Coping Strategy Index (LCSI) measures the extent to which households need to utilise coping strategies to manage a shortage of food. Crisis/emergency consumption for example, include households sending children to live elsewhere, or rationing food by cutting portion size or the number of meals or selling off assets. Compared to 2020 the livelihoods coping strategy index has shown an increase from last year, from 29% to 34%. This means that households are adopting slightly more negative coping strategies, such as selling assets, changing cultivation practices or shifting to less preferred economic activities. However, there is a notable difference in the coping strategies employed by male headed households than female households, with 34% of female headed households employing crisis and emergency strategies compared to 42% of male headed households. In other words, female headed households have had to adopt fewer crisis/emergency strategies, which are often irreversible, as they have found other ways to cope with food shortages.

Intermediary Outcome (IO) 6: Increase in incomes at household level
Given the reliance on agriculture as the primary source of livelihoods and food security for more than 80% of the South Sudanese population, annual cereal production and consumptions are used here as proxy for increase in incomes in BRACE II counties. However, for a more accurate analysis, this needs to be interpreted with project monitoring data regarding use of cash by beneficiaries.
Data from the FAO 2021 post-harvest assessment shows that using an average annual cereal consumption requirement of 130kg per person or a daily dietary energy requirement of 2100 kcal per person, the harvests obtained from the FAO-provisioned seed were projected to be sufficient to cover about five months of food consumption needs for each household comprising six members. This is an estimated 5.3% decrease in the quantity of harvests produced through FAO crop support between 2020 and 2021.
[note] The 2021 Post Harvest Assessment (PHA) was conducted between November and December 2021 and involved household interviews with 2 767 farming households including FAO Emergency Livelihoods Response Programme beneficiaries from 36 counties across 10 States of South Sudan. Therefore, it is used here as proxy for FAO’s distributions but cannot be directly attributed to UK funds. For a more accurate analysis, this needs to be interpreted with project monitoring data from BRACE II areas.
IO7: Increase in cereal production at household level, disaggregated by increase in production and cultivated area [Metric Tonnes (MT)]
UN data from the 2021 FAO/WFP Crop and Food Security Assessment Mission (CFSAM) reported that the 2021 net cereal production in the traditional smallholder sector is estimated at about 839,500 tonnes, 4% below the 2020 output and well below the pre-conflict levels. CFSAM also reported that the overall cereal production deficit in 2022 is estimated at around 541 000 tonnes. This is about 16% above the deficit estimated for 2021 which means that, due to insecurity and impact of climate shocks, households will have less food from their harvest, therefore confirming the worsening of food security level projected by the IPC analysis for 2022.
[note] The annual FAO/WFP Crop and Food Security Assessment Mission (CFSAM) was conducted from 7 to 17 December 2021 to estimate the cereal production in South Sudan during 2021 and assess the overall food security situation in the country. This is used as proxy for BRACE II areas but cannot be directly attributed to UK funds.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

BRACE II continues to perform well, with the last four ARs scoring an A – Outputs Met Expectation. The programme is a key part of FCDO South Sudan’s strategy of balancing emergency humanitarian support with interventions that build self-reliance, where access and security allow.

BRACE II aims to break the cycle of reliance on humanitarian assistance by targeting areas with households facing extreme food shortages and acute malnutrition, who are dependent on food assistance. Providing regular and predictable cash transfers allows South Sudanese households to meet their food needs while also improving their ability to plan ahead and invest in basic services essential for resilience in the long-term, such as health and education. Giving people cash, costs a lot less than providing the equivalent value of food, previous annual reviews reported that WFP costs associated with distributing food reached up to 300% of its value. In parallel, BRACE II supports conditional asset transfers that provide a unique opportunity to reduce disaster and climate-related risks.

The UK’s 2022 International Development Strategy cements the UK’s commitments around preparedness and resilience. The UK’s 2017 Humanitarian Reform Policy also clearly indicates that UK £1 invested in preparedness saves on average more than UK £2 in humanitarian aid and can increase the speed of responses by two weeks.

BRACE II is a key part of the British Embassy Juba’s Country Plan. The programme is in its final year of implementation; findings from the planned final evaluation will support partners implementing cash for work interventions in South Sudan, including the World Bank in more stable areas of the country.

## C. DETAILED OUTPUT SCORING

Output Title	Food insecure targeted households’ access to labour-based safety nets (cash/food-based transfer)
Output number:		1	Output Score:	A
Impact weighting (%):		35%	Weighting revised since last AR?	No

Indicator(s)	Milestone for this review: WFP/FAO	Progress: WFP/FAO	Milestone for this review: WVA	Progress: WVA	Indicator Score / (equally weighted)
Number of women, men, boys and girls receiving cash/food transfers, disaggregated by sex and types of transfer / [Accepted variance of 10%]	92,910 beneficiaries	92,910 beneficiaries / F (54%): 50,171 / M (46%): 42,739 / 100%	36,000 / beneficiaries	36,000 / Beneficiaries plus 6400HH reached with one-off distribution / 100%	100%
Total amount of cash transferred to targeted beneficiaries (USD) / [Accepted variance of 10%]	$1,520,668.00	$1,519,169.50	$1,374,000.00	$1,374,000.00 plus 288,000 $ distributed as emergency response / 100%	100%
Partner Score	WFP/FAO Score (equally weighted)	A / 100%	WVA Score (equally weighted)	A / 100%	A / 100%

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 1 is about reaching vulnerable households with conditional cash-based transfers (CBT). This year, BRACE II reached a total of 124,786 individuals (nearly 21,000 households) of which at least 50% were female.
[note] An estimate of six beneficiaries per household is used across by both delivery components.

CBT are intended to be provided during the Lean season (April-October), to meet the opportunity cost of households participating in asset creation, rehabilitation of “assets” such as anti-flooding dykes, opening new or reclaiming farmland and water ponds and training activities throughout the year. However, due to FCDO budget discontinuity and late confirmation of funds, BRACE II partners were not able to make six consecutive transfers. Under Component I, partners made six transfers from May/June until Jan 2022. Under Component II (WVA) partners made four transfers from May 2021 to Dec 2021, one in Feb 2022 as part of regular conditional distribution in all BRACE II areas and a one-off distribution with unconditional cash transfers in NbeG and Warrap to 6400 HH severely affected by floods as emergency support. For continuity in capturing results, these are reported in this review period.

Compared to previous years, under both components, CBT were unrestricted which means that if households are unable to complete outputs for reasons beyond their control, such as due to flooding, the cash transfers were still provided with participants expected to complete the assets during the dry season. For example, under Component II, the work on the community assets was not completed by the end of December 2021 but it was completed by February 2022. The delays to CBT were raised as a concern by beneficiaries as there were significant deviation from the timelines in previous years. Funding constraints have been communicated to beneficiaries, state and community authorities by partners to avid tension and manage risks.

In 2021, the WFP-led Component maintained its cash transfer value of $40.50 per month ($2.70 per day of work) per six months, while WVA-led Component decreased its value from $49 to $45 (with the transfer in May still being $49), increasingly aligning the two values and what ultimately beneficiaries receive in SSP.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

Under the review period, equity and effectiveness showed mixed progress.

BRACE II targets households vulnerable to food insecurity and climate shocks in targeted counties who are able to participate in labour-based activities. This is based on the assumption that the most vulnerable in these areas are supported through other organisations (e.g., WFP, UNICEF and other partners’ emergency responses). The criteria for being included in the projects are defined by partners together with communities targeted. For example, in areas served by Component II, complementary funding from the Swiss Development Cooperation (SDC) allowed WVA to support households that were labour constrained with unconditional cash transfers, which has also likely strengthened social cohesion in communities. SDC is currently undertaking an evaluation, which will also provide insights on this complementarity between the two modalities, conditional and unconditional, targeting different groups of the community.

Under Component I, partners ensured that at distribution points pregnant women, the elderly and people with specific needs were served first to reduce their waiting time. Partners aimed to serve these population groups within 30 minutes after the conclusion of pre-distribution messaging.

During the review period, BRACE II had a percentage of female beneficiaries above 52% (54% under Component I and 50% under Component II). Monitoring Data from Component I report that the number of female vs male heads of household in the project varies slightly by partner, though the majority of households are headed by females. On average, about 65.4% of BRACE II households are headed by females. This is in line with population characteristics in the state where nearly 70 percent of households are headed by female, reflecting the loss of lives of men during the conflict, or male family members who moved due to their involvement in the armed forces. In addition, Post Distribution Monitoring (PDM) from August 2021 for Component II showed indeed that 16% of household members have some form of disability, however 6% experience/have a severe form of disability that impairs a household member’s capacity to actively engage in labour intensive or productive activity.

Progress on effectiveness has been limited. An indicator of effectiveness of cash transfers is timeliness of distribution. Due to budget uncertainties, there has been delays in distributions compared to the original schedule that is designed to overlap with the lean season, and also not all six transfers could be completed. Delays in distributions affected beneficiaries’ ability to plan ahead which is key to protect livelihoods from the adoption of negative coping strategies. Observations under Component I suggest that households have resorted to borrowing money or commodities from traders/neighbours. Depending on the inflation rate this can negatively affect them when they pay back the loan/money/food.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes to any of the indicators. However, the approach to CBT taken was adapted to become unrestricted to seasons, allowing more flexibility to farmers to work on assets when climatic conditions create challenges.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

One of the recommendations from last year’s AR was to pilot an approach where conditionality of transfers can vary based on needs of agricultural seasons e.g., to allow households to hire additional labour for land clearance. Due to uncertainty of funds this could not be piloted in 2021, however it has been agreed in both components and piloted in Feb/March 2022 to support beneficiaries before prices peak and to enable them to hire causal labourers to work on farm. Results of this will be reflected in the next AR.

Partners under the two components have worked to align values of transfer to ensure a similar amount that beneficiaries receive in SSP. The Cash Working group continues to engage with partners to face the challenge of diminishing beneficiaries’ purchasing power. In 2021 the two rounds of PDM carried out by WFP showed that beneficiaries are starting to recover from the effects of the pandemic. Commodity prices have been mostly stable in BRACE II areas compared to the previous year which have supported beneficiaries in addressing the challenges of volatile markets for essential imported products such as sugar, soap and oil.
Lessons learned this year

Gender: Recommendations from the WFP 2019 Food assistance For Assets (FFA) Rapid Gender Assessment were applied to BRACE II operational areas to the extent possible under both components.

- Partners have in both components instituted concrete measures to enhance women’s attendance in Community-based Participatory planning (CBPP) meetings. Going beyond just women’s attendance, partners are trying to increase the number of CBPP female facilitators.
- To ensure inclusiveness of the selection process and improve understanding of beneficiaries about prioritisation criteria and targeting processes, partners under Component I have shifted approach and now communicate prioritisation criteria publicly in a general assembly within the boma. This has generally increased understanding of the targeting process and prioritisation criteria.
  [note] A boma is a lowest-level administrative division, below payams, in South Sudan.
Impact of CBT on Intimate Partner Violence and GBV: World Vision has carried out a study (unpublished yet) in BRACE II areas to assess the impact of cash transfers on intimate partner violence (IPV) and gender-based violence (GBV). Preliminary results show that there is no increase in IPV and GBV as a result of cash transfers, however a deeper understanding of how the programme has affected community and household dynamic/relations between men and women need to be sought with through a qualitative discussion. Also, more information is needed on how the programme is supporting and monitoring the disclosure of GBV, given there is no direct reference to referral pathways in place.

WFP Food Assistance for Assets evaluation: The decentralized evaluation was commissioned by the WFP South Sudan Country Office and covers the FFA project for the period from 2016 to 2019. Due to COVID-related delays in the field work, results were only published in mid-2021. Results related to this output confirmed that the provision of food assistance to food insecure and vulnerable people is highly relevant and produces immediate advantages to food security and nutrition by filling food gaps and supporting asset creation. FFA was found to be effective in reaching almost all of its programme targets and improving household food security, agricultural productivity, incomes and community cohesion (although disputes between crop farmers and pastoralists were reported), and reducing the extent to which households had to use negative consumption-based coping strategies. FFA was also found to be efficient through the large scale of the project and by the increasing use of the cash modality rather than food. Areas to consider for further thinking are related to the duration of support in relation to the degree of vulnerability of beneficiaries, as greatest gains have been found to be in the first two years in areas where vulnerability is lower.

Returnees: Stakeholders in Magwi had raised the challenge that returnees face when coming back to their communities after being displaced by conflict or flooding, due to lack of resources to start over. Alignment between FCDO and SDC funds and programming approach under Component II has proved useful to support the humanitarian need of 967 returnee HHs through unconditional cash distributions.

Learning from partners’ day in 2021 includes:

- The CBT approach should be reviewed by partners to include a review of transfer values (also in view of seasonality), distribution dates and timelines, as well as whether a county-specific response/approach should be tested.
- The use of online reporting software has strengthened post-distribution monitoring, resulting in more effective, timely and accurate reporting. Using SCOPE, WFP’s beneficiary and transfer management platform has helped improve payment related issues, avoiding duplication of transfers.
Recommendation for the year ahead

- Given the disproportionate contributions of the two components across all outputs over the years, the FCDO team should review the equal weighting of the two components in the log frame. A proportionate weight would give a more accurate picture of the programme's overall performance. However, given the programme is in its final year of implementation this could represent a challenge for consistency of the approach used. It is recommended that the programme team assess implications of a significative adjustment of weighting of the two components across all outputs based on confirmed overall funds for 2022/2023.
- It is important that the programme isn’t introducing harmful new dynamics for the women and men of the programme. Depending on resources available, the programme could consider whether to introduce an approach that address and changes harmful and restrictive gender norms, so that this programme has more of a gender transformational approach.
- Depending on resources available, following the WFP decentralized evaluation of FFA it would be good to consider under both components:
  - the introduction of an ‘exit package’ when beneficiaries leave the project. This could take the form of a voucher for the purchase of equipment, materials or training that would contribute to improving the former participants’ livelihoods at an individual or community level, and would help contribute towards a more consistent level of resilience
  - the flexibility of the period of enrolment in the project, based on vulnerability criteria. This would allow beneficiaries in more food secure/less vulnerable areas to exit after two years if they can achieve a satisfactory level of resilience, and conversely those in less food secure/more vulnerable areas would be able to stay involved for up to four years if necessary.

Output Title	Community and household assets that enhance resilience to food insecurity and climate variability and extremes are improved or created.
Output number:		2	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone for this review: WFP/FAO	Progress: WFP/ FAO	Milestone for this review: WVA	Progress: WVA	Indicator Score / (equally weighted)
2.1 % of achievement in assets built, restored and maintained / [Accepted variance of 10%]	90%	88% of annual target	100%	96% / (115 out of 120)	92% / A
2.2 % of asset that are still used and/or maintained +12 months after their construction, disaggregated by types of assets	85%	117% of annual target	100% / 388 (Total # of assets expected to be +12 months by the end of 2021) / 203 created in 2018 plus 65 created by November 2019, and 103 created in 2020 and 17 created 2021	93.5% (363 assets have been used for more than a year / out of 388 total created). The 17 community assets created this quarter have not been in use for more than a year.	105% / A
2.3 # of households having access to improved seeds, tools, equipment [Accepted variance of 10%]	15,485 HH | DSR 2021: 9,500 HH | Total: 24,985 HH	62% / MSR 2021: 15,485 HH (F: 10,274 | M: 5,210)	6000	100% / (6000 achieved)	81% / B
Partner Score	WFP/FAO Score (equally weighted)	89% / A	WVA Score (equally weighted)	96,5% / A	92% / A

Briefly describe the output’s activities, and provide supporting narrative for the score.

This output is about community and household assets that beneficiaries build, restore or maintain as a condition for receiving cash transfers. Payments are intended to enable beneficiaries to immediately respond to their food needs during the lean season while they are participating in labour intensive activities. In the long term also improving their resilience to climate shocks and stresses. In 2021 progress under this output has been overall good, but limited with respect to access to improved seeds, tools and equipment.

In both components, most communal asset creation activities showed progress in 2021 despite flooding affecting delivery in some areas. In NbeG due to flooding and stagnant water during the last quarter of 2021, it was not possible to fully achieve what was planned for the year under Indicator I. However, participants and community leaders have agreed to continue the work in the dry season that has not taken place due to climate conditions.

Indicator 2 showed a significant progress under both components, meaning that on average all assets have been in use for more than a year.

In BRACE II areas, partners have been distributing seeds, tools and equipment to farmers to support adoption of new agronomic practices, and work on household assets and block farms. Under Component II distributions include dry season kitchen gardening kits, these include tools such as treadle pumps, watering canes, wheel barrows and vegetable seeds (eggplant, carrots, cabbage, tomatoes) etc. Under Component I delays in funding decisions have trickled down to activities implementation, resulting in households not being able to receive vegetable and fishing kits as part of the 2021/2022 dry season response which is shown in limited progress under indicator 2.3.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

One of the indicators used to show the effectiveness of the interventions is the timeliness of distribution, as for example seeds need to be distributed before the planting season, and tools are needed for the asset work before constructions start. PDM data from WFP showed that beneficiaries complained about late receipt of tools for community work. This was due to supply chain constraints, and WFP is considering outsourcing tool procurement to partners to mitigate future delays.

PDM data from FAO (October 2021) reported that over a two-thirds (63.6%) of people were satisfied with the timeliness of distribution while a third (34.7%) reported that seeds were distributed late. In BRACE II areas, the majority of the households who were dissatisfied with the timing of the seeds distribution were in Warrap (66.9%PDM data also reports on satisfaction with the composition or type of crop seeds. Overall, more than 80% of beneficiaries were satisfied with the composition of the kit. However, Warrap reports the third highest dissatisfaction rate, with 19% of beneficiaries not happy with the distribution.

One of the indicators used to show effectiveness of asset work is how many assets are still functional to date. Data from Component II showed that 199 out of 203 created in 2018 and 61 out of 65 HH assets created in 2019 are still functional. The assessment carried out by WFP’s Community Infrastructure Engineer in 2021 in 11 bomas in FFA areas, including those covered by the BRACE II programme, show that all assets were functioning, maintained and in use, though level of maintenance varied depending on the site. Results show that generally, there was a higher level of maintenance and functionality in NBEG sites compared to Warrap, though notably the sites in Warrap had been more affected by recent flooding.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress on recommendations from the previous AR

Under Component I:
- Recommendations from previous reviews identified the need to improve access to water for irrigation and to manage water resources. WFP has included irrigation equipment and processing machines (budget lines included for downstream delivery partners) in 2022/2023 planning. The effect of this will only be visible in the next review period.
- A recommendation from 2019 to strengthen dispute resolution/ peacebuilding mechanisms and link community planning processes to local governance structures and development plans was addressed this year. WFP field office in Warrap has carried out a study to assess the effects on peacebuilding of FFA activities. The case study shows potential of FFA activities; this has informed FCDO thinking on resilience building in both the conflict prevention and the new humanitarian and resilience BC.
Under Component II:
- In Magwi, Aweil and Gogrial the adoption of sweet potatoes as a climate smart response to flooding has been positively taken by the communities. In Gogrial the farmers are also using raised bed as a way of mitigating against flood. Sorghum, groundnuts and cowpeas are some of the nutrition-dense crops farmers are growing. They are both drought tolerant and are of high nutritional value.
- Farmers are able to preserve and store their own seed for the next season especially sorghum and groundnuts. BRACE II has been supporting with seed only for the first month, with the farmers providing their own seed in the next season. For the current group of beneficiaries, cohort D, WVA piloted a new system of early cash transfer to support the farmers procuring seed locally. An assessment is planned in 2022.
Lessons learned this year

- WFP Food Assistance for Assets (FFA) evaluation: the FFA evaluation carried out in 2020 showed that maintenance of assets built under the programme is still a problem as neither local government nor beneficiaries have the resources to manage the maintenance, particularly of large infrastructures such as roads and dykes.
- WFP rapid gender assessment undertaken in 2019 raised issues of work norms that needed to be designed according to specific needs of groups. WFP has followed up to make sure that women are not overburdened. Also, WFP is working regionally to look at gender transformative work norms with the University of Nairobi; the recommendations and guidance from this collaboration may inform programmatic adjustments from 2022.
- Timely provision of inputs/kits is key to ensure that farmers can engage in production at the right time: the need for early input distribution and crop diversification was raised as feedback from farmers under Component I together with the provision of sufficient asset creation tools. Also, identification of the block farms prior to the building of control dykes was raised as challenge to be addressed.
Recommendation for the year ahead:

Monitoring data from both components show that the highest achievements in terms of asset construction and maintenance have been in counties which have largely been unaffected by floods. While this is a positive achievement of the programme, it does not show how assets built through the programme have supported communities to mitigate risks from excessive flooding. Quality and scale of assets and their long-term effect in withholding high levels of water, remain a key challenge within the programme. Partners have agreed to evaluate asset design to improve the capacity of assets in controlling excess floods. In addition, the BRACE II evaluation, expected to be finalised in the second half of 2023, will investigate how communal assets have strengthened resilience of those counties most affected by floods.

In its final year of implementation, partners together with the FCDO need to explore solutions to support the maintenance of assets. Roads and dykes need significant level of equipment, knowledge and skills to be maintained that unlikely beneficiaries/communities can provide. Partners should consider including options in the BRACE II exit strategy.

Partners should monitor the uptake of seeds from previous harvests and to what extent farmers are multiplying seeds as a proxy for the development of a local input supply market and less reliance on seeds distribution. A breakdown of farmers who have preserved seeds from previous harvests could be possibly included (recommendation from previous year not actioned).
Output Title	Skills and knowledge for resilience are improved
Output number:		3	Output Score:	A
Impact weighting (%):		25%	Weighting revised since last AR?	No

Indicator(s)	Milestone for this review: WFP/FAO	Progress: WFP/FAO	Milestone for this review: WVA	Progress: WVA	Indicator Score / (equally weighted)
# of people trained on improved and climate-sensitive agricultural practices [Accepted variance of 10%]	19,485 (MSR: 15,485; DSR 4,000)	MSR 2021: 15,485 HH / (F: 10,274 | M: 5,210) / 79%	6000	6000 / 100%	A / 89,5%
# of people trained for improved nutrition practices (disaggregated by sex) [Accepted variance of 10%]	15,485 / (F: 8,362 | M: 7,123)	17,845 / (F: 11,671 | M: 6,174) / 115%	1565	3739 / 239%	A+
# of people trained on conflict mitigation in targeted communities [Accepted variance of 10%]	920	920 / 100%	576	576 / 100%	A
Number of dispute resolution / resource management structures set up (or improved)	92	92 / 100%	36	36 / 100%	A
Partner Score	WFP/FAO Score (equally weighted)	A	WVA Score (equally weighted)	A++	A
[note] Through BRACE II, the UK contributes to two nation-wide distribution campaigns that the FAO carries out: the main season response (MSR) and the dry season response (DSR).

Briefly describe the output’s activities, and provide supporting narrative for the score.

Output 3 is about improving households’ skills and knowledge, a critical part of the BRACE II package to build resilience to climate shocks and stresses; robust progress has been made in reaching the targets set for 2021.

Training on improved agricultural production such as sunken beds, mulching, application of animal manure, as well as the introduction of short maturing vegetables has been conducted under both components through demonstration plots. Under Component I, additional training on improved water and soil management, integrated pest management, nutrition education, and fisheries trainings will be conducted as part of the dry season response, therefore in the first quarter of 2022, thus reported in the next reporting period.

The overall training target under Component II exceeded in terms of numbers due to additional beneficiaries from previous cohorts reached as refresher trainer on nutrition.

FAO, under Component I has sustained the radio programming that was launched in 2020 in collaboration with Eye Radio, national  independent radio broadcaster of news, information & entertainment in South Sudan and the South Sudan Department of Meteorology. FAO has procured additional 100 solar powered radios to be distributed to listener groups across project locations and will provide access to all local FM radio frequencies, including Akolyam, Radio Miraya, Weer bei FM and Eye Radio. In order to assess the effectiveness of activities disseminating climate information to farmers under this output, the FCDO has commissioned FAO to undertake a study that will provide information on the availability, delivery and application of climate information services in selected counties in South Sudan. Findings of the study are described in the section dedicated to learning below.

On nutrition, all partners provided key health and basic nutrition messages at distribution points. Under Component II, PDM report from August 2021 revealed improved nutrition practices (81.7%), with an increase of 3.7% from August 2020 PDM (78%). The respondents reported eating at least five to eight different food types on a weekly basis. More stable commodity prices have contributed to this improvement. Under Component II, nutrition training was re-started this year (after pausing last year due to Covid-19 social distancing requirements), through cooking demonstrations, under the assumption that lead farmers would share information with and guide other BRACE II beneficiaries within and outside households, and through awareness raising at distribution points. Topics included child feeding and exclusive breastfeeding, nutrition sensitive agriculture to improve dietary diversity and prevent malnutrition, and basic norms on hygiene. While through focus group discussions participants seems to have increased their knowledge about diet diversity, PDM results from 2021 show that diet diversity score decreased from 2020, from 3.80 to 3.30, especially for female headed household.

Targets for the number of dispute resolutions and training on conflict mediation were met by both components. In BRACE II, Project Management Committees (PMC) are established in each boma. Their role is key to improve accountability as they function as a channel to facilitate communication between partners and communities. PMC are trained and supported in resolving project related disputes or conflicts. Common issues that committees are successful in resolving are those related to land access, ownership and use.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

In terms of effectiveness, output 3 contributes to the increase of incomes at household level (IO6) and increase in cereal production at HH level (IO7), for which VfM is currently being tracked through quality and timeliness of trainings received.

Given the lack of TPM, there is limited evidence on effectiveness of trainings. PDM results from FAO under the Dry Season Response show that 57% of the households reported to have received awareness or training on the utilization of the fishing kits. PDM from Component I note that 68.3%of respondents could decrease their post-harvest losses before versus after post-harvest handling training. Additional results from the post-harvest assessment produced by FAO in Nov. 2021 showed that the majority of crop kit beneficiaries considered the delivery of inputs as having been timely, while the quality was considered satisfactory. At least 68% of the farmers who responded practiced crop-rotation, 30% practiced minimum/zero tillage and at least 20%practice mulching and cover cropping. Additionally, less than 15% of farmers practice manure application, Integrated Production and Pest Management (IPPM), erosion control/infiltration barriers, rainwater harvesting, varietal selection and record-keeping.

PDM results from Component II shows that 71% of project farmers use at least two or more techniques acquired as part of BRACE II agricultural trainings, a finding of significance in ensuring increased production while maintaining regenerative environment.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Lessons learned this year

- Learning from partners gathered in July 2021 showed there is need to strengthen adaptive agriculture trainings, allowing for learning curriculum to be more flexible depending on seasonal needs. In addition, trainings on climate downscaling have enhanced skills of project staff to better support beneficiaries.
- Market development and post-harvest losses and storage trainings were identified by partners as preferred topics by many beneficiaries. Partners could expand these topics to more FFA beneficiaries, but not at detriment of core climate sensitive agriculture techniques.
- The FCDO has commissioned a study by FAO to get a better understanding of the production, dissemination, and distribution of seasonal climate information to communities in South Sudan. The report’s findings that will be included in the next review period, are informing the development of FCDO’s proposed new humanitarian and resilience programme and will be used to improve FAO’s work to disseminate climate information to farmers for improved productivity and disaster risk management.

Recommendations for the year ahead

The gap between training and level of understanding/uptake has been flagged again as an area that needs to be addressed. Previous TPM showed that there is still a gap in uptake of even basic practices (row planting, mulching or over cropping, minimum tillage) as they are still reported to have a low adoption rate. This was confirmed during a focus group discussion in a field visit in NbeG and in Warrap during partners’ meeting. Given the lack of TPM, the FCDO together with partners need to improve the collection of evidence of effectiveness of training in learning and uptake, disaggregated by gender and age. Given this recommendation has not been actioned since last year’s recommendations, it needs to be prioritised in the design of interventions for FY 2022/2023

Output Title	BRACE II management is adaptive and informed by the M&E and feedback mechanism
Output number:		4	Output Score:	B
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone for this review: WFP/FAO	Progress: WFP/ FAO	Milestone for this review: WVA	Progress: WVA	Indicator Score / (equally weighted)
1. Partners' community feedback mechanisms established at the distribution sites	100	100 / 100%	36	36 / 100%	A
2. Proportion of people who know where to complain/provide feedback	95%	55%	95%	89,6%	B / 72%
3. # of Monitoring & Evaluation & Learning products produced by the M&E component	NA	2 PDM, plus one for WFP in 2022 / 100%	3 / (Market survey and 2 PDM)	2 / (The final PDM is scheduled for the 2nd week of February 2022 after the recent distribution) / 66%	B / 83%
Partner Score	WFP/FAO (equally weighted)	A	WVA (equally weighted)	A	85% / B

Output 4 is about the way BRACE II is monitored by partners, and how the programme management is able to adapt to a changing context and remain relevant to beneficiaries.

Feedback mechanisms in BRACE II include:
Community feedback committees that collect and refer issues to project management committees.
1. Feedback desks at distribution points that receive complaints from participants and non-participants, which are shared with project management committee members and/ or partner.
2. A WFP free hotline to receive feedback.
3. Community monthly and quarterly meetings.
4. Feedback through field staff.

In 2021 under both components, there has been a decrease in the proportion of people who know where to complain/provide feedback. As showed by Indicator 2 only 55% of beneficiaries served by Component I know where to complain/provide feedback, which is a significant reduction from last year. Partners have reported problems with help desks which did not function as planned. Consequently, partners have provided training on record and management of complaints and in addition, WFP protection teams plan to monitor partners and PMCs’ training to ensure the effective use of the helpdesks in 2022. Under Component II, data from the August 2021 PDM survey adduce that 89.6% of the respondents know how and where to complain and give feedback. Majority, 83% preferred to feedback via the help desk, 62% prefer using phone calls or messaging and 15% prefer the suggestion box. Awareness about the mechanism continues to happen with the help of Boma Project Management Committees.

Under Component II, one PDM was conducted in 2021, the second is planned for Feb. 2022. All 36-feedback committees were registered and trained. Key thematic areas covered in the trainings were: 1. Sexual Exploitation and Abuse 2. Fraud and Corruption 3. Child Protection and 4. Roles and responsibilities of the committees and how to report or provide feedback to the implementing partners. Under Component I, the target for Indicator 3 was not set for 2021 and this will be adjusted for 2022 consistently with previous years. Nonetheless, partners have produced two post purchasing monitoring reports; a PDM report for the FAO’s Emergency Livelihood Response Programme (ELRP) for the Main Season Response (MSR), and a WFP PDM, plus an additional study which is planned for the first quarter of 2022.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

We don’t report against this output in the current VfM matrix, but generally effectiveness of the activities under this output can be reviewed by looking at the feedback mechanism and how well partners responded and integrated such feedback in programme delivery.

Under Component I, WFP has planned to engage with protection teams to place more emphasis on training partners and PMCs to ensure effective use of the helpdesks in 2022.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress on recommendations from the previous AR

Recommendations from last year were not acted upon and are included in the recommendations for the year ahead.

Lessons

Partners have organized a learning event in July 2021. Key lessons are documented under each output.
For the next review period two studies are planned:

- FAO is undertaking a study to get a better understanding of the production, dissemination, and distribution of seasonal climate information to communities in South Sudan.
- Recommendations from 2019 Annual Review recommended early transfers to give households the option of buying food during the early months of the year when food commodity prices are low. The recommendation builds off one of the findings of the Mid-Term Evaluation which indicated that one of the barriers to households expanding production beyond 1-2 feddan was due to labour constraints, given that key agricultural processes are achieved through manual labour. As a result of these recommendations, WFP has piloted an advance cash transfer in Feb. and planned a post distribution monitoring assessment to assess how the cash is used and the level of investment in farming activities and other household expenditure. Findings will be presented in the next review period.
  [note] One Feddan is equal to 0.42 Hectare. It is the land area measurement unit commonly used in South Sudan.
Recommendations for the year ahead
- All partners should consult with male and female beneficiaries of the projects to identify any barriers to feedback being provided through existing mechanisms and redouble efforts to communicate ways for people to provide feedback during the start of transfers in 2022.
- In 2022 partners to demonstrate how they have made adaptations to programme plans based on learning and feedback mechanisms.
- Partners to update results framework and logframe for 2022.

D: RISK

Overview of risk management

The BRACE II business case was approved with a Severe risk rating with the operating environment and climate disasters, conflict and insecurity being the highest risks. The overall risk was revised to Major in 2018 and continues to be assessed as Major. The levels of risk for these risk categories are assessed as being within the British Embassy Juba’s risk appetite as summarised in the table below.

All BRACE II partners continue to actively manage risks which is demonstrated by them continually updating risk registers on a quarterly basis and apprising the FCDO project team to significant changes in risks and any new risks that emerge. There have also been regular management discussions on risks between partners and the project team during quarterly meetings or as and when required when an urgent risk issue needs to be discussed. For example, there has been a need to have discussions on appropriate mitigation measures to manage risks associated with incidences of violence in or around project implementation areas to ensure staff safety until conditions improve to allow project activities to resume.

The most significant risks which have been actively managed for BRACE II during 2021 are summarised below:

S/N	Risk Category	Risk Appetite	Risk description	Mitigation measures taken during the period of review	Residual Risk
1	Strategy & Context	Eager	Insecurity and threats of insecurity were experienced in some parts of BRACE II project implementation areas in Warrap State, and Magwi County of Eastern Equatoria State. Some BRACE II locations were affected due to access constraints and reduced ability of FCDO and partner staffs to monitor effectively. FCDO had to cancel two field monitoring missions to Magwi and Twic Counties respectively. This also meant that the programme team lost an opportunity to conduct programme asset inventory verification in the two locations.	Partners have worked with state governments, local authorities and community leaders to resolve some of the issues that created tensions. In Magwi County of Eastern Equatoria State, the local leaders, county authorities and state government are engaging the cattle herder's community to avert further conflict with the farming indigenous communities. / BRACE II implementing partners World Vision continue working with the United Nations Department for Safety and Security (UNDSS) and local authorities to monitor insecurity.	Receptive
	Strategy & Context	Eager	Climatic shocks such as flooding was experienced in parts of BRACE II project implementation areas along the Lol River basin from Aweil South and Aweil North Counties in Northern Bahr El Ghazal and Twic County of Warrap States. This has reduced the ability to maintain some community assets such as roads.	4 dykes were constructed in Aweil through the conditional cash transfer arrangement which ensured year-round connectivity between villages and within bomas and also access to services. In addition, FAO in collaboration with Eye Radio and the South Sudan Department of Meteorology, through funding from FCDO also continue to air a radio programme “Ziraa Tanna”, meaning “Our Farm” in Juba Arabic. The programme provides farmers with weather updates and guidance on proper management of agriculture, livestock and fisheries in South Sudan. FAO also partners with local radio stations including Akol Yam in Aweil and Mayardit FM in Turalei (Twic County) to adapt the weekly content to the local Dinka language.	Cautious
	Strategy & Context	Eager	The risk of soaring Covid-19 infection rate did not materialise. Overall, there has been a slight increase in the number of infections in South Sudan from quarter 2 from 12,823 to 16,909 with the rate of mortality has remaining constant at 137.	Preventive measures continued to be put in place at project sites by partners to minimize chances of infection to the beneficiaries.	Cautious
3	Financial & Fiduciary	Receptive	Risk of looting before and during cash payment process affects provision of entitlements to participating households	Registration of households in SCOPE and annual review of data entered in SCOPE database prevents fraud. / Regular monitoring of security situation and risks during transfers prevent incidences. / WFP and FAO representatives are present at all cash distributions points. / WFP has contracted financial services providers (FSP) and shifts risk to them as the cash are insured.	Cautious
4	Safeguarding	Receptive	Safeguarding has been identified as a major potential risk in BRACE II programme. However, no safeguarding related case was reported during the review period.	FCDO updated the safeguarding and fraud letters and issued them to all partners in August 2021 making clear FCDO’s expectations of safeguarding prevention and reporting. / World Vision, FAO and WFP continues to create awareness among beneficiaries on their rights to ensure accountability. New Boma project management committees (BPMCs) and Help Desks officers are trained to ensure beneficiaries are aware of their rights and communities on the use of the toll-free number and suggestion boxes for raising complaints on physical, sexual, and emotional abuse (PSEA) during the distributions and cash for assets (CFA). / FCDO continue to be vigilant and monitor reports for such cases	Cautious
5	Reputational	Cautious	Insufficient Budget for cash transfers, ITFs, Training and extension support leads to pipeline breaks or reduced service delivery to targeted households	Despite earlier reduction in budget to £4.5m for 2021/22, FCDO managed to secure additional £3m ICF funding that prevented the partners failing to roll out the required cash transfers to mitigate against the long lean season. WFP was able to complete 6 cash transfers while WVA completed 5 out of six.	Cautious

Recommendations

FCDO to engage WFP in country to review the financial reporting arrangement in the framework arrangement (2015) and the contribution arrangement to ensure that the earlier wavier to report on cash transfers value and related costs are revised and FCDO funds are earmarked for BRACE II and in line with FCDO financial reporting standards.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency.

Reporting

All partners have provided timely and quality progress reports throughout the year. Where there have been minor delays, partners have sought extension requests before the due date. Where FCDO have requested supplementary information or minor points of clarification, partners have been quick to respond. BRACE II contributes to WFP’s larger FFA project which is multi-donor funded and therefore, WFP only provides cash transfer value reporting, since that is the only budget component which WFP’s financial system tracks against individual donor contributions.

Financial position and performance

Due to delays in FCDO approving its country budget allocations in 2021/22, a bridge funding arrangement was out in place for BRACE II partners FAO, WFP and WVA for the period of April – June 2021 to avoid stalling of project activities. The full year budget of £4.5m represented a 44% reduction from 2020. However, an additional £3m International Climate Finance funding uplift was granted in November 2021 to allow partners to provide an additional two rounds of cash transfers during Q4. Jan – March 2022 which increased the full year budget to £7.5m.

The table below shows the financial position of BRACE II as of 31March 2022 and financial performance during the period of the review. It demonstrates overall the programme has utilised 98% of its approved £7.5m budget compared to 100% in 2020/21 FY when the budget was £8,018,686. In addition, WFP has also spent an additional £15,000 of the original M&E allocation in 2021/22 on a post distribution monitoring (PDM) study that monitors the effects of a cash transfer that was distributed in Q4 before the start of the lean season. World Vision has spent 93.33% of its budget during the 2021/22 FY.

Due to ODA cuts only £4.6m shall be programmed up to March 2023. Subject to ministerial approval, British Embassy Juba plans to integrate resilience programming into a new humanitarian and resilience programme, which will start in 2023. A decision will be made before the end of this calendar year whether to close BRACE II programme in March 2023 - seven months earlier than envisaged – or if there are delays in design of the new programme, to continue with implementation during the 23/24 UK financial year.

	All figures in £’s		Period of review
BRACE II partner	Approved programme budget 2015 - 2023	Expenditure to 31st March 2021	Budget for 21/22 FY	Expenditure for 21/22	21/22 % Utilisation	Balance remaining
FAO	11,402,123.47	8,106,144	1,608,175	1,608,175	100	3,295,979
WFP	28,513,340.53	23,407,444	3,752,408	3,767,408	100	5,105,897
WVA	13,800,000.00	10,869,705	2,124,417	1,982,752	93	2,788,630
M&E	884,536	623,020	15,000	0	0	261,516
Total	54,600,000.00	43,006,313	7,500,000	7,358,335	98	11,452,022

FCDO tracks WFP spend through their value for money biannual report, covering what is spent on cash transfers, non-project attributable costs (NPAC) and other admin costs. Their reporting is based on a reporting framework agreed at HQs level, which does not provide the option for the local FCDO team to request more detailed/additional information. FAO doesn’t present financial forecast in FCDO format, but nonetheless the quarterly financial report allows FCDO to track spent accurately.

World Vision struggles with providing accurate quarterly forecasts, where variances to actual expenditure can be as high as 10%. These variances are primarily due to exchange rate fluctuations, delays in capturing expenditure on their systems as well as the occasional delayed activity or over budgeting. These challenges in forecasting resulted in this component underspending by £142k during the 21/22 FY. FCDO and World Vision are currently in discussion to agree on practical steps which can be taken to reduce these forecasting variances.

Value for money (VFM) consideration

The original BRACE II Business Case states that value for money would be tracked by looking at key costs, such as the cost of delivering cash transfers, and that a comparison of the two delivery modalities (component I delivered by a UN partnership and Component II delivered by an NGO-led consortium) would give additional indication of the model delivering the best value for money.

Economy: Key costs and savings

Component I: UN partnership delivery

For component I (see the table below), direct and indirect support cost constitute 10% (£216,137.00) which is 1% reduction from the 2020 figure of 11% (US$675.543), and implementation cost was 21% (£433,418) – 8% increase from 2020. For FAO, the major cost drivers in 2021 were the contracts which include letters of agreement which FAO signs with NGOs and CSOs for implementation of a significant proportion of the activities at the local/community level and other frontline services (45%), procurement of seeds and tools (13%), staff cost (11%), and M&E (7%) which made up the bulk of FAO’s spend. Overall, the proportion of funds allocated to cash transfers in 2021, £1,090,936 (52%), was lower than in 2020 which was 63%).

Cost Category	Amount programmed GBP	%
Cash Based Transfer (CBT) Value	GBP 1,090,936	52
CBT Transfer Cost	GBP 348,991	17
Implementation Cost	GBP 433,418	21
Direct Support Cost (DSC)	GBP 88,609.	04
Indirect Support Cost (ISC)	GBP 127,528	06
Total	GBP 2,089,482	100%

Component II: NGO consortium delivery

For component II (led by World Vision), the main cost drivers have marginally increased compared to last year’s review – which are cash transfers; agriculture; and transportation and field expenses. Overall, cash-based transfers still account for the most spend at 65%, a 2% reduction from last year, while agriculture has increased by 2%. The table below shows a comparison of WVA’s main cost categories over the three years between 2021, 2020 and 2019.

WVA’s Cost Category (GBP)	2021	%	2020	%	2019	%
Cash Based Transfer (CBT) Value	1,287,314	65%	1,822,595	67%	1,725,534	55%
Agriculture and Transportation	202,994	10%	223,186	8%	528,807	17%
Field Cost (Transport, logistics, staffing, M&E, Capital)	362,731	18%	493,660	18%	655,413	21%
Indirect Support Cost (DSC) – NPAC	129,713	7%	177,761	7%	203,683	7%
Total	1,982,752	100%	£2,717,202	100%	£3,113,437	100%

Efficiency:

In 2021, direct cash transfers to beneficiaries represented 58% on average (£2,378,250) for the two components compared to 65% in 2020. This means the proportion of cash directly received by beneficiaries for every £1 disbursed in 2021 is 58p which is lower compared to 65p for last year.

The figure is reached by calculating overall cash disbursed to beneficiaries, divided by the overall amount disbursed to the partner.

The impact of the budget reduction on BRACE II translated into a reduction from £8m to £4.5m in 2021, however the project received an additional £3m funding in Q4 which offset the potential loss from the original allocation. However, given that the direct, indirect and implementation cost across all the partners FAO, WFP and WVA remained largely the same in 2020 and 2021, it can be reasonably concluded that the full impact of the budget cut will affect the amounts allocated for direct cash transfers, agriculture and training if other cost levels are maintained. Nevertheless, further analysis of the impact of the budget cut will be conducted in 2022.

Direct Support cost %		2021	2020
Field Cost (Transport, logistics, staffing, M&E, Capital)
	WFP	25%	24%
	WVA	18%	18%

Exchange rate

South Sudan’s exchange rate reform in 2021 and a relative stability of commodity prices have improved beneficiaries’ purchasing power. The transfer value when converted to SSP has provided significantly more to households compared to 2020 which has enabled them to buy more, particularly in the last few months when commodity prices remained fairly stable and in comparison, to 2020. The below table shows average exchange of the US dollar to the South Sudan Pound over the two review periods.

	Average Exchange rate for cash transfers for US$1 to South Sudan Pounds (SSP)
S/N	Component I (FAO/WFP)	Component II (WVA)
2020	SSP 195	SSP 172
2021	SSP 253	SSP 391

The official UN exchange rate was relatively lower than the official exchange rate, therefore, WFP negotiated to reimburse the financial service provider a slightly higher rate as reflected above. World Vision on the other hand, also had a negotiated rate slightly above the official exchange rate for SSP, but lower than the parallel market rate. It can be concluded that beneficiaries in 2021 received more in local currency than in 2020 with a better purchasing power due to relative stable prices and exchange rate.

Cost per beneficiary

The cost per beneficiary this year was examined, and it is compared to previous years in the table below. Results indicate that the cost per beneficiary for Component I has been fairly higher than Component II until 2021 where it is lower compared to Component II which increased from £47 in 2020 to £55 in 2021.

Cost per beneficiary per year estimates	Component I	Component II	Programme Estimates
2017 Annual Review	£53		£53
2018 Annual Review	£53	£46	£49
2019 Annual Review	£58	£43	£52
2020 Annual Review	£52	£47	£50
2021 Annual Review	£52	£55	£53

Overall, the cost per beneficiary for Component II increased from £47 in 2020 to £55 in 2021. This can be attributed to the number of beneficiaries reached this year which was less than in previous years due to discontinuity of funds that the partners have received and did not allow to add another cohort as planned.

As stated in other ARs, while it is important to track how cost per beneficiary varies across the years to be able to monitor the cost of interventions, it cannot be used as a metric for value for money unless compared to a benchmarked cost per beneficiary, for a similar package of interventions in South Sudan. Based on latest data, Component II seems to provide the best value for money regarding cost per beneficiary compared to Component I, however it is being left for the planned evaluation to assess thoroughly and compare the other dimensions.

Component III: Monitoring and Evaluation

Due to ODA budget reductions, the contract for the third-party monitoring (TPM) was not extended onto 2021. A successful process should lead to a contracting a TPM partner in 2022, subject to budget availability. In addition, due to FCDO security restrictions there was no project sites visited by FCDO during the period under review. The FCDO team in Juba is aware of this constraint and possible alternatives are now being considered. A final programme evaluation is planned for 2022.

Annual Financial Statement

World Vision Australia’s annual financial statement for the period ending 30th September 2021 gave unqualified audit opinion of their financial statement. FCDO funds cannot be identified within the income statement nor the table showing World Vision Australia’s disbursement to World Vision South Sudan. Consequently, the audit report does not meet the FCDO’s audit requirement standards. This annual review recommends that World Vision Australia is requested to revise the annual audited accounts statement for 2021 and extract BRACE II specific information. This will greatly enhance the assurance that the organisation has spent UK taxpayers’ money on its intended purpose.

The UN BRACE II implementing partners WFP and FAO conduct regular annual audits of their finances at corporate level. These audited financial statements do not identify FCDO’s funding to BRACE II. The external auditor who conducted WFP’s audit provided an unqualified audit opinion of WFP’s financial statement for the period ending 31st December 2021. The audit report confirms that WFP has continued to implement the audit recommendation made in 2017 to extend the roll-out of SCOPE biometric registration system for implementing cash transfers. The proportion of cash-based transfers covered by SCOPE increased from 59.8% in 2020 to 70% in 2021 globally. In South Sudan the coverage also increased by 30% in 2021 reaching a total of 1,407,251 beneficiaries. The registered beneficiaries through SCOPE in South Sudan increased from 3.1m in 2020 to 4.3m in 2021. This is commendable for WFP and the BRACE II project as the rightly registered beneficiaries benefits from the project and duplication is avoided.
[note] Annual Country Report | World Food Programme (wfp.org)

FAO South Sudan does not conduct BRACE II project specific annual audits. However, it does conduct regular corporate audit of the FAO in South Sudan. The audit provides sufficient assurance that FCDO funds are being used for the intended purposes.

Asset Management

Of the three BRACE II project implementing partners; it is only World Vision that keeps and shares an annual asset inventory list with FCDO. The latest WVA asset inventory list shared with FCDO for 2021 has no new updates from the last one submitted in 2019. Physical asset checks were not conducted in 2021 due to inability of FCDO staffs to visit project locations because of security concerns. WFP and FAO have not procured assets using FCDO funds. Therefore, for this review period, there are no submissions on assets from the two partners.

Date of last narrative financial report	FAO/WFP: Received on 23/02/2022 covering the period 01/01/2021-31/12/2021. WFP does not provide BRACE II project specific financial report. They only track cash transfers and therefore, financial status of the project is tracked through the bi-annual VFM report. This creates visibility challenges of WFP finances. FCDO recommends meeting with WFP to discuss and improve the reporting. FAO does provide a clear financial report. / WVA: Received on 22/02/2022 covering the period 01/10/2021-31/12/2021. WVA financial report is easy to interpret and of high quality .
Date of last audited annual statement	WFP: received on 23/05/2022 covering the period 01/01/2021 to 31/12/2022. / FAO: N/A / WVA: Received on covering the period 01/10/2020 to 30 September 2021