 Programme Completion Review (PCR)

Title: Punjab Education Sector Programme (PESP) II
Final Programme Spend £ (full life): £430million	Review Date:	April 2022
Programme Code: 202697	Start Date: Jan 2013	End Date: March 2022

Summary of Programme Performance

Year	Year	2013-14	2014-15	2015-16	2016-17	2017-18	2018-19	2019-20	2020-21	2022 / (PCR)
Programme Score	Overall Output Score	A	A	A	A	A	A	A	A	A
Residual Risk Exposure Rating	Risk Rating	Medium	Medium	Medium	Medium	Moderate	Moderate	Major	Major	Major

DevTracker Link to Business Case (and any addendum):	http://devtracker.dfid.gov.uk/projects/GB-1-202697/documents/
DevTracker Links to all logframes used during programme lifetime:	http://devtracker.dfid.gov.uk/projects/GB-1-202697/documents/

## A: Summary and Overview

Description of the programme and what it has achieved

The Punjab Education Sector Programme II (PESP II) aimed to support the Government of Punjab (GoPb) to reform and transform delivery of education in Punjab, providing equitable access to better quality education across the province. It supported a range of innovative interventions with the government, private sector and civil society organisations (CSOs), with specific focus on eleven low performing districts in South Punjab. PESP II was extended to run for a total of 9 years, and at £430 million is the UK’s largest bilateral education programme. Resultantly, it is a large and complex programme which has been adapted over its lifetime to respond to changing contexts and opportunities, with lessons learned informing adaptations to the activities and logframe.

The original PESP II Business Case was for up to £350.3 million for six years (2012/13-2017/18). This Business Case was extended four times, to a new total of £437.1 million to 2022/23. Extensions included:
- Cost extension in 2015 to provide £70 million additional sector budget support (SBS) to support the Punjab Chief Minister’s Reform Roadmap.
- Time extension to March 2021 to utilize unspent funds aligning the programme with the Pakistan’s Country Development Diagnostic and Business Plan.
- Cost and time extension to July 2021 to provide £6 million to allow more time to complete and handover safe classrooms to the Government of Punjab.
- Cost and time extension to March 2022 to provide £10.6 m to enable continued support to the Ministerial priority area of girls’ education and support the GoPb to respond to COVID-19 shocks to the education sector.

Throughout its lifetime, PESP II had eight key interventions, some of which changed substantially during implementation. A summary of these components is set out below.

#	Component	Date	Aim	Partner
1	Sector Budget Support (SBS)	2012-2022	Providing funds to the GoPb to improve access to education and improve quality in public schools.	GoPb – through the School Education Department (SED) and allied institutions (including Quaid-e-Azam Academy for Educational Development (QAED), Punjab Curriculum and Textbook Board (PCTB), Punjab Examination Commission (PEC) and the Programme Monitoring and Implementation Unit (PMIU)).
2	School Construction and Rehabilitation Programme (SCRP)	2012-2022	Focusing on improving learning environments across the province.	2014 - 2021: IMC Worldwide / 2019 - 2022: GoPb / 2019 - 2021: The Citizen’s Foundation (TCF)
3	Financial Support to the Punjab Education Foundation (PEF) through targeted Financial Aid (FA)	2012-2019	Expanding the capacity of the PEF to build capacity and quality of Punjab’s growing low-cost private sector, through an Education Voucher Scheme (EVS), New Schools Programme (NSP), and Foundation Assisted Schools (FAS) programme.	PEF
4	Access to Finance component	2012-2014	Credit guarantee scheme focused on expanding low-cost private schools in / under-served areas.	This was dropped in 2014 following a study concluding that the evidence base for the intervention was weak. This was replaced with targeted support to PEF to expand education provision to underserved areas.
5	Tackling Social Exclusion	2012-2022	Tackling social exclusion and inequality by: / Providing targeted support through civil society organizations (CSOs) and PEF to stimulate demand for education and expand education provision to underserved areas / Including children with disabilities in mainstream schools and support to special education institutions / Scholarships for girls to encourage better transition and completion of secondary education	2015-2019 PEF / 2015- 2019 GoPb Special Education Department (SpED) / 2013-2022 Punjab Education Endowment Fund (PEEF)
6	Technical Assistance (TA)	2012-2022	To underpin delivery of all other components	2014-2018: McKinsey, and Adam Smith International. / 2014 - 2018: World Bank through External Financed Outputs (EFOs) to provide TA to SED / 2018– 2020: Cambridge Education. / 2020-2022: Institute of Social and Policy Sciences (ISAPs).
7	Second chance education	2018-2021	Advancing Action for Adolescent Girls (A3G) for out of school adolescent girls in three of the lowest performing districts of South Punjab	Idara-e-Taleem-o-Aagahi (ITA)
8	Performance Evaluation	2017-2021	Evaluation of programme performance	e-Pact, a consortium led by Oxford Policy Management (OPM)

Together, these components worked towards the following six outputs, reviewed separately in the main body of this report:
1. Strong leadership and accountability
2. Better teaching performance and better teaching
3. High quality school infrastructure
4. Improved access to schools, especially in priority districts
5. Top political leadership engaged on education reform in Punjab
6. High quality technical assistance to government stakeholders that builds sustainable processes and systems

Programme Context

The programme started in 2013 and was designed to respond to the education emergency declared by the Government of Pakistan in 2011. Education access and quality were weak across the country, and because of its size, Punjab had the highest number of out of school children, and the highest number of children with low learning levels in Pakistan. By the end of the programme, access indicators have improved, but strong inequalities remain in both access and learning outcomes with differences by location, gender, and school type.
[note] The Pakistan Education Task Force’s report titled Education Emergency Pakistan 2011 set out the dire state of education in Pakistan and called for education to be made a national priority http://ilearnpakistan.org/wp-content/uploads/2018/12/Education-Emergency-Pakistan-Report-2011.pdf

The political context is a key consideration for assessing the performance of PESP II. From 2012-2018, the Chief Minister of Punjab had a strong vision for and commitment to the education sector and worked with a Delivery Unit to monitor the performance of the education sector through the “Education Roadmap”. This high-level political commitment to education provided a strong rationale for the scale of investment under PESP II. Following a change in government after the 2018 elections, the Chief Minister no longer had the same level of direct engagement in sector management. The Provincial Minister for School Education took a more active role, and there has been a high level of turnover of senior government leaders. At the same time, some major components of the programme started to close, and soon after COVID-19 disrupted the education sector, impacting on access, participation and learning outcomes.

In the context of an already weak education system, disruptions caused by Covid-19 have severely affected the education of millions of children across Pakistan and in Punjab with schools closed for over a year and distance learning opportunities available to only a few. While the government was quick to respond by establishing distance learning platforms on television supported by private digital education providers the period from 2019 to 2021 saw a decline in learning levels as well as access to education. According to the Annual Status of Education Report (ASER) 2021, the proportion of out-of-school children (6-16 years of age) in Punjab has increased from 8% in 2019 to 10% in 2021 with more boys not going to school. Learning levels of children have also declined with 68% children able to read a story in Urdu in 2021 compared to 75% in 2019.
[note] GoPb launched Taleem Ghar on 1 April 2020

Breakdown of Education Expenditure by Educational Level (Rs. Million) / Most notably, the education budget in Punjab increased from ~ PKR 220 billion (~ GBP 1.3 billion) in 2012 to ~ PKR 399 billion (~ GBP 1.7 billion) in 2021, which is an increase of 85% in local currency in 9 years. The increase was most significant in primary and secondary education particularly for girls and other excluded groups and for the poorer districts; and this policy direction was strongly advocated and influenced by PESP II. Detailed breakdown is set out in the table below:
	2012-13		2020-21
	Allocation / (PKR millions)	Expenditure / (PKR millions)	Allocation / (PKR millions)	Expenditure / (PKR millions)
Primary Education	94,995.87	90,272.55	170,889.41	161,313.83
Secondary Education	92,029.29	71,724.14	170,235.82	162,139.77
Higher Education	25,611.75	22,582.10	36,436.63	33,205.64
Others	7,936.91	8,181.11	21,614.31	20,384.85
Total	220,573.82	192,759.90	399,176.17	377,044.09
[note] After adjusting for inflation, it is a 40% increase in real terms which in itself speaks about strong commitment to education expenditure in a developing country context.

As well as improving access to good quality education for all children in Punjab, PESP II had a particular focus on eleven low performing priority districts of south Punjab. These were identified as the most challenging in terms of poverty and marginalization relative to the rest of the province. A range of targeted interventions with the government, private sector and civil society organisations in these districts were included to ensure the programme delivered equitable access to better quality education across the whole province.
[note] Chiniot, Bhakkar, Layyah, Vehari, Muzaffargarh, Dera Ghazi Khan, Lodhran, Rajanpur, Bahawalpur, Bahawalnagar, and Rahim Yar Khan

Key Achievements

Over the period of PESP II, GoPb has shown strong commitment to education with an increasing shift in focus from increasing enrolment to greater explicit attention on learning outcomes and inclusion. This commitment has been reflected in public spending which has generally continued to prioritise education, as well as an active process of development of policies, initiatives and organisational reform, and effective cooperation with the UK and the World Bank as the main external providers of financial support to the sector. There have been significant achievements over the lifetime of the programme in relation to each of the outputs above:

  1. Leadership and accountability: A structured system-wide performance management system providing a systematic approach to reviewing performance at all levels of the education system – province, district, and school. Rollout of a School Improvement Framework across all districts in Punjab, which tracks performance and provides a structured evidence-based accountability tool to drive performance at both district and provincial levels. Strengthening the school monitoring regime in Punjab by introducing new metrics such as the Literacy and Numeracy Drive (LND) and availability and use of data in real time through the use of technology. Timely and efficient utilization of non-salary budgets by schools.
  2. Teaching: increase in the number of teachers (50% increase in the number of qualified teachers), and improved teacher attendance (from 92% in 2012 to 95% in 2019 (pre-Covid-19) and 91% in 2022). Merit based recruitment and continuous professional development of teachers. Support to the Governments of Punjab to design and deliver ‘catch-up’ and accelerated learning programmes to support children returning to school after COVID-19, developing more than 2,600 lesson plans and worksheets for Punjab benefitting around 8.59 million students and more than 250,000 teachers.
  3. School infrastructure and learning environment: more than 6,500 classrooms and 800 learning facilities (libraries, science, and IT laboratories) established during the life of the programme. Improvements in physical infrastructure over the project life – almost all schools now have electricity, drinking water, toilets, and boundary walls.
  4. Access to schools: 1.23 million more children enrolled in government schools from 2012-2021. Support to PEF in the design and implementation of an ambitious expansion plan to enrol 2.8 million children by 2019 through public private partnerships, including identifying and enrolling out-of-school children with mild disabilities in PEF schools through an inclusive voucher scheme. Increased student attendance from 79% in 2011 to 93% in 2019. Over 80,000 scholarships awarded to girls from low-income households for post-primary education, and over 35,000 out-of-school adolescent girls provided with second chance education and vocational skills.
    [note] Annual School Census 2012-13: 10,640,693, 2021-22: 11,870,919
  5. Political leadership engaged on education reform: PESP II played a central role in facilitating education sector reform through the development of the Roadmap and Stocktake process which ensured a focus on a few critical reform priorities and targets, facilitated cross departmental coordination, and prioritized the provision of funding to reach these targets.
  6. High quality technical assistance: TA provided for prioritization of curriculum Student Learning Outcomes (SLOs), development of textbooks and teacher guides, improved integrity of examinations and improved test design and content quality, digitisation and EdTech strategy, COVID-19 Accelerated Response for Education (CARE) including a revised academic calendar, scripted lesson plans for teachers and worksheets, inclusive education strategy, special education policy, and including disability indicators in the PMIU dataset.

Areas of under performance

The British High Commission (BHC) Islamabad team has been flexible and able to work with partners to respond to changing government priorities, particularly following the 2018 elections and the COVID-19 pandemic. Most partnerships were effective, however there were notable problems with two contracts:
- The Technical Assistance and Management Organisation, “TAMO” (partnership between Adam Smith International and McKinsey) initially had some management issues and weak monitoring and evaluation (M&E), however, arrangements were significantly improved in the latter part of the contract period.
- The Technical Assistance for Construction and Engineering “TACE” (IMC Worldwide): concerns arose in early 2017 over the quality of construction work, and appropriateness of design in seismic areas. Technical problems were escalated, and a retrofitting agreement made, but there were long delays until issues with the management of the school infrastructure component were satisfactorily resolved.

Changes to the programme and logframe

There were two distinct phases of the programme: 2012-2018 the original timeframe of the programme when most of programme interventions as envisaged in the BC were underway; and 2019-22 a period of programme extensions which included closing of some components, continuation of others, as well as some new interventions to reflect emerging UK and GoPb priorities. While the adaptive nature of the PESP II programme reflected the changes in context over the span of almost a decade led to improved effectiveness, this resulted in several changes to the logframe indicators and milestones which makes it difficult to assess the achievement of the programme against initial indicators and baselines. Some implications of these changes to the programme and the logframe include: a) while the overall intent and purpose of output statements and output indicators remain consistent, some of the targets/milestones do not always correspond neatly with the output indicator. Milestones have changed when earlier targets have been met, more stretching targets have been added, or support for a particular programme component has ended and a new intervention has been added to the programme, b) targets in the final year of the programme are not cumulative and have been added following various programme extensions, c) based on learning from the programme new outputs (5&6 for Roadmap and TA) were added halfway into the programme to enable the team to monitor and measure progress across all key areas of programme intervention.

Score

This programme has scored an A with a majority of the outputs meeting expectations. The programme scored an A in four of the six outputs, an A+ in one output, and a B in one output. Throughout its life, PESP II has met most of its targets, and there have been impressive improvements in access to education (up until schools were closed due to COVID-19 in 2020 which has impacted school participation and attendance), government leadership, and key reforms due to support from PESP II. Where there have been low or delayed performance, the programme staff have worked to quickly refine ways of working and make improvements to the programme.

Major lessons learned, evidence generated and recommendations

PESP II funded an independent evaluation to complement the programme from 2018-2021. Key findings, lessons, and recommendations from this report are included here, alongside others identified during this project completion review. The recommendations below are aimed at the GoPb and any future UK support to education in Punjab.
[note] https://www.opml.co.uk/projects/evaluating-punjab-education-sector-programme

Access

Lessons learnt: Primary participation rates across Punjab, and in the low performing priority districts, have increased, demonstrating that a higher percentage of primary school age children in Punjab are attending school, although there is weak evidence that children are in the appropriate grade for their age. Secondary participation rates have increased, with more noticeable improvement in low performing priority districts. Access continues to be lower for girls, children with disabilities and those from poorer households. There has been some success in getting more of the poorest into schools, but not always in retaining them in school.

Recommendation: Identify and effectively reach (including through remedial support) children who are out of school or whose learning has been most significantly disrupted, as well as those with special educational needs and disabilities.

Learning

Lessons learnt: School based data demonstrated improvements in learning outcomes in the period 2014 to 2019 with differences by location, gender, and school type. Scores fell slightly in 2020. Children in (rural) Punjab have performed above the national average as compared to other provinces and regions in the country over the period of PESP II, though achievement levels remain persistently low. Progress in priority districts was relatively strong, with children performing above the provincial (and national) average over the period of PESP II. As with participation in education, there is evidence of substantial differences in learning outcomes that are related to household economic status (in rural areas), which are greater for girls than for boys.

Recommendation: Learning-focused support to education requires a focus on the performance of key functions, including the effectiveness of teaching, the environment for learning and the quality of school management and governance.

Equity

Lessons learnt: PESP II consistently emphasised gender and equity considerations, and many of the interventions (such as A3G, support to special and inclusive education, and PEEF scholarships for girls in priority districts) had a specific gender and equity focus, though these considerations were not systematically addressed in the design and implementation of all programme activities.

Recommendation: Ensure a strong focus on gender, equity, and inclusion to address continuing inequalities in education access and performance. This may include additional data collection and analysis to help improve policy.

Teachers

Lessons learnt: While teacher attendance has averaged over 90% and more qualified teachers have been hired, student-teacher ratios have fluctuated and were slightly higher in 2018 than 2012. More evidence is needed to assess whether the effectiveness of teaching has improved.

Recommendations: Teacher recruitment, appointments and transfers should aim towards ensuring optimal student teacher ratios as per government policy. Ensure teachers (in both the government and private sectors) have adequate subject knowledge, use appropriate teaching methods, and are effectively motivated and managed. Measure the quality of teaching to understand the cumulative success of a teacher focused output, and an outcome measurement of teacher quality (or preferably linked student performance).

Public private partnerships

Lessons learnt: PEF’s experience has continued to demonstrate the viability and effectiveness of well-managed and designed Public Private Partnership (PPP) arrangements in education, but also their vulnerability in the absence of a clear long-term government strategy and sustainable funding arrangements which should be a focus for the government going forward. A more systemic approach may be needed to ensure that programmes are not solely focused on increasing enrolment but take into account other measures such as retention and learning.

Recommendation: Ensure effective and sustainable PPP arrangements for education, with the framework of a comprehensive policy towards private education including the appropriate regulatory and facilitating roles for government.

Governance

Lessons learnt: Political ownership is a key ingredient in any reform process. The Roadmap and Stocktake process was effective in aligning the education system on the achievement of specific short- and medium-term targets but not in itself sufficient to guide comprehensive policy and organisational reform. Frequent changes in the senior leadership positions within government, particularly in the last few years of the programme have made it challenging to sustain and institutionalize reforms. Limited progress was made in implementing the model of decentralisation of education management through District Education Authorities (DEAs), and uncertainty remains about how the decentralisation approach embodied in the Punjab Local Government Act (PLGA) 2019 will be implemented for education. While data availability and use have improved over the period of PESP II, some key gaps in data remain including data on school management, teacher competency and classroom teaching practice, private school provision, disability, learning etc. Data available are not sufficient to assess whether there have been changes in equity measures (e.g., participation rates and learning outcomes by socioeconomic status) over the period since the start of PESP II implementation.

Recommendations: Ensure sufficient stability and effectiveness in the senior management of key sector organisations. Build relationships at all levels of institutions to ensure capacity goes deeper than senior management and protect capacity building efforts from staff turnover. Implement a model of decentralised management of education that enables schools to control a greater share of resources while improving accountability especially to pupils, teachers, and communities. Strengthen school-level management and governance and support community and parental engagement – in particular through sharing information about school performance and learning effectiveness. Ensure that the quality of Public Financial Management (PFM) for education is improved, with a view to improving the rate of budget execution for the non-salary and development budget, and to ensuring the policy framework to guide spending decisions is clear. SBS needs to be strongly focused on PFM improvement and effectively aligned with the budget (both in its timing and the process for setting priorities) to have the best prospects of achieving impact. Future programmes should support government efforts to improve data availability and use, in particular data on student learning and teaching quality.

School infrastructure

Lessons learnt: Large-scale infrastructure programmes pose challenges and require particular skills for effective procurement and contract management by the agency commissioning them. This must be recognised and effectively addressed throughout the design and implementation process, including in the design of contract arrangements which should include quality assurance (QA) considerations. While political /economy and other factors may have inhibited devolution and enhanced community engagement and oversight in construction in Punjab, experience from KP and elsewhere internationally still suggests the long-term cost, quality, and sustainability advantages of community engagement in school infrastructure.

Recommendations: Future infrastructure procurements should avoid the risk of appointing a supplier lacking recent in-country experience and possession of appropriate registrations to operate. All supplier designs should be checked and certified by an independent structural engineer. Future agreements must be required to adopt national standards and guidelines relating to access for persons with disability as well as earthquake resilience. To provide an incentive for timely delivery, it is recommended that programmes involving the design and construction of building and civil engineering works should be based on the delivery of outputs rather than the provision of inputs. Innovative design criteria should be tested for value for money before being rolled out on a large scale, piloted for technical suitability and, where necessary, formal approval sought through national standards bodies.

Commercial Contract:

Lessons learnt: The terms of the contract were not aligned and lacked specification of tasks necessary for a construction contract such as design expectations, compliance and verification of standards and sub-contractor management. This resulted in FCDO seeking additional expertise to validate safety concerns and propose solutions. The process being extensive delayed FCDO’s response times.

Recommendation: Standard service delivery contracts are not fit for purpose for large Infrastructure development projects. The contract terms should clearly lay out the tasks including clear roles and responsibilities of parties concerned (including parties that will take over the assets) and process for issues identification and resolution in a timely manner.

Programme design and management

Lessons learnt: The changing context and long-term duration of the programme necessitated an adaptive Theory of Change (ToC) and results framework. The programme design provided flexibility to adapt to changes in context through the annual planning of sector budget support and regular revisions to technical assistance (TA) work plans, as well as reallocating resources between components and adjusting logframe targets through Annual Reviews. However, this resulted in an overly complex programme with multiple components and a logframe that makes it difficult to capture progress against programme outcomes and outputs over time.

Recommendations: Clearer articulation of a Theory of Change (informed by an appropriate conceptual framework) may encourage more rigorous attention to be given to key steps in the causal chain by which results are achieved and ensure that programme outputs and outcomes lead to system-level change. Initiatives that are justified as, and intended to be, pilots of new approaches need to have effective engagement and ownership from key stakeholders and need to be appropriately (and explicitly) designed and managed to maximise the likelihood of success. Gender and equity considerations should be systematically addressed in all aspects of programme design and management.

Financial Aid

Lessons learnt: Financial aid to GoPb under PESP II has supported reforms across a wide range of policy areas. However, the modality through which it can be effectively deployed is context dependent and needs to be adjusted accordingly. PESP II has used both sector budget support and non-sector budget support targeted financial aid with important lessons learnt on both which will contribute to the design of future education programmes. While sector budget support tied to disbursement linked indicators has been instrumental in introducing new routines, enhancing capacity, and informing and influencing polices for improvement in overall education outcomes, non-sector budget support targeted financial aid offers greater potential to support direct service delivery through government and much stronger attribution of results to the programme.

Recommendations: In the context of overall reduction in the volume of Financial Aid, future programmes need to consider the best available means for deploying this, as well as scoping alternative approaches including an appropriate mix of TA complemented with financial aid (FA) and innovative approaches to service delivery to achieve a larger multiplier effect by leveraging increased domestic financing. Provide targeted financial support to government to complement the TA in order to: (i) fund research and pilot initiatives where appropriate; (ii) selectively provide resources where these can be used to achieve high development impact, especially in conjunction with transformational reforms; and (iii) to help resolve key delivery bottlenecks for improving organisational and system performance. Funding may also be provided to NGOs and CSOs where there is a clear strategic rationale for this in relation to the theory of change governing the intervention. Additionally, programmes that provided SBS should include a focus on improving the PFM system. The logframe for future programmes should emphasise and track these measures to better assess impact.

Technical assistance

Lessons learnt: The TA provided has generally been highly effective in producing agreed short-term outputs and responsive and flexible, but its record in contributing to sustainable organisational transformation, and addressing key governance issues for the sector, has been mixed.

Recommendations: TA should be measured against implementation of reforms, as well as policy approval to ensure that plans and reforms take root. As highlighted above, financial aid aligned with the objectives of TA can help incentivise uptake of reforms supported through TA. Select TA providers based on their proven ability to work effectively in the local context and to mobilise both high-quality (in both educational, technical, and ‘soft’ consultancy skills terms) international and local expertise, and to provide effective support both to policy development and implementation. Embedded TA working within the government departments leads to more ownership and acceptance of TA by the Government and is therefore strongly recommended from a VFM (effectiveness) perspective. Institutional partnerships for highly specialised TA could be an effective approach for providing high quality and sustainable technical assistance.

How this review was conducted

This review was conducted by an independent review team consisting of an education, delivery, and social development adviser from the central FCDO office along with a governance adviser, programme manager (who had not worked on this programme), infrastructure adviser and education adviser from the British High Commission (BHC) Islamabad. The review team conducted detailed interviews and discussions with most stakeholders including current and previous technical assistance providers, Government departments and the evaluation partner. The team also reviewed all relevant documents including the Business Case, addendums to Business Case, evaluation reports, management responses and previous annual reviews to agree the narratives and overall PCR score. Due to visa limitations and COVID-19 restrictions, the review team conducted this review mostly virtually and only one team member was able to visit Pakistan to finalise the report with the PESP II team. This also meant that the review team was not able to speak with any beneficiaries (students or teachers) of the programme but did hear indirect feedback from them through partners interviewed. In addition, the independent evaluation that was drawn upon for this review did include a school and district study which included engagement with beneficiaries.

Actions following approval of this report

All closure activities related to PESP II including the asset disposal where required were completed by 31st March 2022. However, the programme manager for PESP II will remain engaged with the partners to process final invoices against the payments accrued. The audited statements from the auditor general of Pakistan will be received by the PESP II team in December 2022 as agreed in the original grant agreement.

The BHC Islamabad is working on an internal report to collate the lessons learned to recommend way forward for future education programmes. In collaboration with our TA partner ISAPs we also plan to co-host an event to share the lessons learned during PESP II where we will be inviting all relevant stakeholders to reflect on a decade of education reforms in Punjab.

## B: Theory of Change and Outcome Assessment

Outcome indicators are set out in the table below. For data sources not comparable over time see footnotes.
	Starting point	Final result
Budget	£350.3mn	£430 million
Timeframe	Six years	Nine years
Outcomes	More children in school, staying longer, and learning more / Outcome indicator Baseline 2012-13 Pre-COVID results (Jan 2019) Final target Final achievement 2022 / 1. Participation rate for primary school aged population (ages 5-9) for: (i) Punjab and (ii) 11 priority districts Punjab: 86.7% / Girls: 85.1% / Boys: 88.4% / Priority districts: 77.6% / Girls: 74.4% / Boys: 80.8% / (Source: PSES 2012) Punjab: 94.9% / Girls: 94.9% / Boys: 95% / Priority districts: 94.4% / (Source: MICs 2017-18) Punjab: 95% Girls: 94% / Boys: 96% / Priority districts: 87% Girls 85 % / Boys 89 % Punjab: 94.1% / Girls: 93.7% / Boys: 94% / Priority districts: 89% / (Source; ASER 2021) / 2. Participation rate for secondary school aged population (ages 10-16) for: (i) Punjab and (ii) 11 priority districts Punjab: 78.5% Girls: 76.2% / Boys: 80.8% / Priority districts: 66.3% / Girls: 61.0% / Boys: 71.6% / (Source: PSES 2012) Punjab:79.1 % / Girls: 78.7% / Boys: 79.4% / Priority districts: 73% / (Source: MICs 2017-18) Punjab: 85% Girls: 83% Boys: 87% / Priority districts: 75% (girls: 71%, boys 78%) Punjab: 85.1% / Girls:85.2% / Boys: 84.6% / Priority districts: 79.7% / (Source; ASER 2021) / 3. Percentage of Grade 3 students that achieve specific SLOs for each subject (English, Mathematics, Urdu) Punjab: 55% / Math: 57% / English: 58% / Urdu: 50% / (Source: six monthly assessment Sept 2014) Punjab: 86.3% Math: 88.5% English: 82.4% Urdu: 88.1% / (Source LND data Jan 2019) Punjab: 83% / Math: 85% / English: 78% / Urdu: 84% Punjab: 64% / Math: 64% / English: 58% / Urdu: 70% / (Source: LND data for Feb 2022) / 4. Student attendance 90% attendance rate each month / (Source: PMIU monitoring data) 93% attendance rate maintained every month 94% attendance rate maintained every month 88% during the month of March 2022
[note] Percentage of children in the given age range enrolled in school
[note] Punjab School Education Survey: Six monthly survey commissioned through the programme and carried out by Nielson. The last time that this survey was carried out in January 2017 the following results were reported: Punjab average: 91% (Girls: 89%, Boys: 92%), Priority Districts: 83% (Girls: 79%, Boys: 86%)
[note] Data is taken from the Multiple Indicator Cluster Survey (MICS) 2017-18 which does not include gender disaggregation for priority districts
[note] Annual Status of Education Report: Primary participation rate ( 6-10 years). Compare with 88.5% in 2012 and 95.2% in 2019.
[note] PSES Jan 2017 results: Punjab average: 82% (Girls: 80%, Boys: 83%), Priority districts: 70% (Girls: 64%, Boys: 75%)
[note] ASER secondary participation rate ( 11-16 years). Compare with 76.9% in 2012 and in 88.5% 2019.
[note] Six monthly assessment commissioned through the programme and carried out by the Roadmap TA team ( McKenzie). Results of the last six-monthly assessment in March 2018: Punjab 77% (Maths:84%, English:68%,Urdu: 75%)
[note] Literacy and numeracy drive instituted by the PMIU/Government as part of routine school monitoring

Overall assessment of programme outcomes, sustainability and VfM

Progress against impact indicators demonstrates a generally positive trajectory over the period of the programme. Literacy rate in Punjab (10+ years) increased from 61% in 2013-14 to 64% in 2018-19. Literacy rates are higher in urban areas (77%) compared to rural areas (57%) and higher for males (73%) compared to females (57%). Literacy rates in Punjab are above the national average (60%) and at the top among all provinces followed by Sindh (57%), KP (55% including merged areas), and Balochistan (40%). The Survival rate in primary has increased from 61% in 2012-13 to 74% in 2021-22 and in secondary from 63% to 91%. The percentage of literate labour force (10+ years) in Punjab has gone up from 61% in 2012-13 to 66% in 2020-21. However, this percentage will be lower if we exclude child labour (<14 years) and persons past retirement age (>60 years).
[note] Pakistan Social and Living Standards Measurement (PSLM) 2018-19
[note] Primary survival rate tracks the cohort entering Class 1 and graduating class 5 and secondary survival rate tracks students entering Grade 6 and graduating Grade 10. Calculations based on Punjab Annual School Census 2017-18 and 2021-22.
[note] Pakistan Labour Force Survey 2012-13 and 2020-21.

Programme outcomes have been partially achieved with overall better results to report pre-Covid-19. Although progress is difficult to assess given the lack of available/consistent data for recent years, similar (positive) trends are seen using multiple data sources. There was evidence of improvements across all indicators over the first six/seven years of the programme, then some slowdown in progress (possibly due to the impact of COVID-19) or gaps in recent data. While attribution for such a large and complex programme which was designed to work hand in hand with the government is difficult make, and it is particularly challenging to assess the contribution of PESP II to overall education outcomes, outcome indicators show improvements in school participation and learning.

Primary participation rates across Punjab, and in the low performing priority districts, have increased by 5-6%, demonstrating that a higher percentage of primary school age children in Punjab are attending school, although there is weak evidence that children are in the appropriate grade for their age. The increase is significantly higher for girls (10%) compared to boys (3%). Secondary participation rates have also increased throughout the programme (11-12%), with more noticeable improvement for girls (15%) compared to boys (4%). Student attendance followed a similar pattern, with consistent improvements until the final year of the programme, then a drop to below baseline levels. Although gaps in participation rate between boys and girls is seen to be reducing over the last nine years, access continues to be lower for girls (particularly at the secondary level and in low performing priority districts), children with disabilities and those from poorer households. School closures due to COVID-19, together with disruption to livelihoods during the pandemic, led to declines in participation in 2020 and 2021.

School based data demonstrated improvements in learning outcomes in the period 2014 to 2019. However, final year scores fell significantly missing the final programme target, albeit with improvements over baseline scores for foundational literacy and numeracy (Urdu and Maths). As with participation in education, there is evidence of substantial differences in learning outcomes that are related to household economic status (in rural areas), which are greater for girls than for boys. Overall the evidence on learning outcomes is incomplete and does not allow a robust assessment of whether there have been changes in equity measures (e.g. participation rates and learning outcomes by socioeconomic status) over the period of PESP II implementation. Similarly, there is limited data on children with special educational needs and disabilities in Punjab, though PESP II consistently emphasised gender and equity considerations, and many, though not all, programme interventions had a specific gender and equity focus.

Key to sustainability is the extent to which PESP II achieved transformational impact towards more effective policies and systems, and sustained GoPb commitment to specific initiatives. This varies across the programme: the e-PACT evaluation concluded that the model of expanding access to education through support to PEEF should be highly sustainable. Similarly, PEF has sustained the Inclusive Voucher Scheme without any additional funding. School infrastructure constructed by PMIU and TCF should be sustainable while future maintenance may be a challenge, especially for innovations implemented by IMC Worldwide. Strengthened policies and systems may be sustained for reforms to continuous professional development (CPD), the Inclusive Education Strategy and information flows from schools. The flexible TA has contributed to the programme’s sustainability, including by responding to changes in GoPb’s priorities, but will be affected by future policy changes and levels of government ownership and political commitment.

Value for Money of the programme:

Using Sector Budget Support to leverage further GoPb investment. The programme had a budget of £437.1 million over nine years (representing approximately 4% of the entire education budget of the GoPb) and was able to deliver concrete results, as well as influence key sector reforms as described above. UK Sector Budget Support (SBS) contribution remained at 1% of the overall education budget for Punjab in the peak years of the programme (i.e. between 2012 – 2017). The respective proportion dropped to 0.2% in the final year of the programme due to both reduced sector budget support between 2018 – 2021 and an overall increase in GoPb’s education budget. Most notably, the education budget in Punjab increased from PKR 220.6, billion (~ GBP 1,300 million) in 2012 to PKR 399 billion (~ GBP 1,700 million) in 2021, an increase of 85% in local currency in 9 years. While at macro level UK SBS leveraged further GoPb investment, in the implementation level the spending became more efficient, as student learning improved, and the cost-per-point of improved learning reduced. While only a correlative observation, from a wider VFM perspective this appears to be a success, as not only did UK investment encourage more GoPb spending on education, but this appears to have become more effective and efficient in terms of delivering student learning.

Development Best Buys: DFID/FCDO published sectoral papers in 2019 that reviewed all the available evidence for a wide range of interventions across multiple sectors and attempted to ‘grade’ these interventions in terms of cost-effectiveness (value for money). A mapping of PESP II interventions against the education development best buys (DBB) spectrum proves favourable. Working on systems change (to set learning goals, curriculum, textbooks and teaching at more appropriate levels) is core PESP activity and is considered a DBB ‘Mega Buy’ - the most cost-effective category. ‘Great Buys’ included in PESP interventions are: (i) structured lesson plans with linked materials with ongoing teacher monitoring and training, (ii) targeting of teaching instruction by learning level, (iii) Community schools where schools do not exist, and (iv) merit-based scholarships.
[note] There are minor exceptions, such as the technical and vocational training (assessed as Bad Buy) provided to 1,370 girls.

Student enrolment is a major VFM attainment story of PESP II. Increasing the supply of education opportunities was a central PESP II objective. This would manifest in higher student enrolment in the public and publicly-funded education system and reduce the number of out-of-school children (OOSC), There are now about 52,500 Government schools filled with 12.6m children - up 1.95m over Life Of Project (LOP) - being educated by 391,800 teachers (increase of 59,600); with a general student-teacher ratio of 32:1. Of every 100 students, 52 are female (46 at project-start). The rate of enrolment has increased at an annualised rate of 2.84%, above the rapid population growth rate of 2.4%. This suggests that government school enrolment over LOP has absorbed natural population growth and contributed the equivalent of an additional 280,000 dent into the OOSC population.
[note] Calculations based on TA-provided data between 2012 and 2020 i.e. pre Covid-19.

Low-cost Schooling. The low-cost, publicly funded, Punjab Education Foundation schools continue to play a crucial role in access to education. DFID/FCDO’s £7.4m grant in 2019 to PEF constitutes one-eighth of the PEF budget. DFID’s contribution supported 333,700 students learning for a year at a cost of c. PKR 7,075 (£37) per student. PEF schools educate 2.64m children bringing the enrolment total (Kachi included) to 15.2m in Punjabi publicly funded schools; private (fee-paying) schools educate another 2.6m. PESP II has driven the expansion of PEF (285,000 new students enrolled over LOP) into priority districts of (mostly) southern Punjab. The quality of education received in PEF schools is leading to student outcomes that are comparable with the many times more expensive public system and play a vital role in reducing OOSC numbers.

The value of the Roadmap is largely manifested in the efficiency gains in delivery that the monitoring routines and stock takes have helped to drive. The Roadmap process and stock takes continued to drive reform and improve performance across the education sector through prioritizing key areas, increasing GoPb budget allocations, and delivering greater efficiency. Teacher and student attendance targets are set at 90%; with teacher attendance at 95% in 2019 (85% in 2011), and student attendance at 93% in 2019 (90% at 2012 baseline). Cost-efficiency gains are achieved as teachers are more often in class and there are more students present for them to teach.

While difficult to provide a summative assessment of the value for money of PESP II, some programme interventions were highly cost effective. PEEF scholarships and PEF programmes were effective based on the value of transfers to beneficiaries and expanded access to education. For example, DFID/FCDO’s contribution to PEF supported 333,700 students learning for a year at a cost of c. PKR 7,075 (£37) per student – a much cheaper rate than Government Schools. The TA provided, despite early delays and some initial challenges, was judged by the independent evaluation to have ensured economy and efficiency. The programme established synergies with the World Bank’s PESP 3 programme, further increasing efficiency. The cost effectiveness of school infrastructure through IMC Worldwide/TACE was low initially with deterioration in VFM for this component over the life of the programme. The value for money of the school construction component improved with the GoPb and The Citizen Foundation. Despite being a small share of the overall GoPb education budget (less than 2%), UK’s sector budget support was used successfully as a lever to push for reforms in the sector and to ensure more and better spend on education. The contribution of SBS is substantial, as demonstrated through the priority given to achievement of Results and Activities Framework (RAF) targets.
[note] OPM Report Template version 5 (opml.co.uk). Page xii, 89-91

Equity is relatively challenging to assess given the lack of robust and consistent data. Some individual components achieved good value for money (e.g. PEEF scholarships and the Siyani Sahelian Programme) and were able to improve access to education for the most marginalised. More broadly, there is evidence that PESP II had some success getting the poorest into school, but not necessarily retaining them in education. There is no data available on the quality of education provided to children with Special Educational Needs and Disabilities (SEND) or results achieved.
[note] e-Pact final evaluation report of Punjab Education Sector Programme II

A more detailed analysis of value for money is provided for each output below.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators.

No full Theory of Change (ToC) was ever articulated for PESP II. Instead, the framework below (essentially a summary of the logframe) was used as an equivalent. This did not identify causal pathways or linkages between levels of the results chain, nor did it set out the assumptions underpinning those linkages. A more fully articulated ToC (ideally jointly owned with the GoPb) may have allowed more robust tracking of system performance and provided clearer guidance for strategic programme decisions.

The PESP II Business Case envisaged that both supply and demand side issues needed to be addressed to improve education outcomes in Punjab. Major supply side challenges were identified related to inadequate infrastructure and poor teaching at the school level and weak governance and accountability at the provincial and district level. On the demand side, economic affordability and cultural deterrence particularly towards girls’ education were identified as the key barriers towards equitable access to education. The ToC below shows the key activities PESP II has taken to resolve these.

The ToC (and logframe) were adjusted during programme implementation to reflect the revision of some outputs and changes to the original activities. The impact and outcomes remained consistent throughout the programme.

In 2019, the programme mapped its interventions against the Global Education Evidence Advisory Panel (GEEAP) ‘Smart Buys’. This report, from a multi-disciplinary panel of independent education experts uses evidence to group education programmes into several tiers of cost-effectiveness. A mapping of PESP II interventions against the Smart Buys spectrum proved favourable. Working on systems change (to set learning goals, curriculum, textbooks and teaching at more appropriate levels) is a core PESP II activity and is considered extremely important for other interventions to work in a sustainable and scalable way. Many of PESP II’s individual interventions are listed as “Good Buys”, which the panel considers have good evidence that they are “highly cost-effective across a variety of contexts”. ‘Good Buys’ included in PESP II interventions are: (i) structured lesson plans with linked materials with ongoing teacher monitoring and training, (ii) targeting of teaching instruction by learning level, (iii) reducing travel times to schools (e.g. community schools where schools do not exist), and (iv) giving merit-based scholarships to disadvantaged children and youth.
[note] GEEAP 2021, Cost-effective approaches to improve global learning, saved: https://documents1.worldbank.org/curated/en/719211603835247448/pdf/Cost-Effective-Approaches-to-Improve-Global-Learning-What-Does-Recent-Evidence-Tell-Us-Are-Smart-Buys-for-Improving-Learning-in-Low-and-Middle-Income-Countries.pdf
[note] There are minor exceptions, such as the technical and vocational training (assessed as Bad Buy) provided to 1,370 girls.

## C: Detailed Output Assessment

Output Number and Title		Output 1: Strong leadership and accountability
Output Score		A
Impact weighting (%)		10%	Impact weighting revised since last AR?	Yes

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
1.1: Number of districts with performance management system	Performance management approach developed and pilot district selected / As programme evolved, the target was changed to teacher attendance in 2017, then to the trainings of AEOs in 2018. Target was set for DRC meetings in 2019 and 2020. In the final years of the programme this target specifically focused on the implementation of the SIF.		School Improvement Framework (SIF) implemented in all districts of Punjab	Target achieved / Following a successful pilot, a comprehensive School Improvement Framework (SIF) has been developed and implemented for all 36 districts in Punjab and performance routines are being conducted by the PMIU in districts
1.2: Frequency of Monitoring and Evaluation Associates (MEA) visits and reliability of data collected	90% school visit rate maintained every month / Interim targets included: Tablet based real time data collection system successfully piloted in 8 Districts with a minimum of two rounds of data collection / Data verified (for sufficient robustness and quality) with monthly variation between audit data (from District Field Coordinator (DFC) spot checks or TPVs) and collected MEA data within +/- 10 % for each district.		90% MEA school visit rate maintained in all districts (average of the months when schools were open)	Target moderately not achieved / On average MEA school visit rate over the lifetime of the programme has been 87% / The MEA school visit rate has been at average of 60% in the reporting year mainly due to high turnover in MEA staff. / Reliability of data verified by the MEA audit and variance remained well within range identified (+/- 10 %)
1.3: Timely release and efficient utilisation of school non-salary budget (NSB)	50% schools utilising the non-salary budget released to districts		70% utilisation at district level (releases to schools), of NSB released to districts from July - March 2022.	Target achieved / 73% NSB budget utilised till May 2022.
[note] 96% of schools visited every month from 2014-16. 90.4% MEA visits took place in October 2020 after schools reopened after extended period of closures.

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

This output tracks the effectiveness of leadership and accountability mechanisms of the School Education Department (SED) at district level. The activities under this output are primarily supported through technical assistance to the GoPb. Progress under this output over the period of the programme has met expectations (2013-19) with challenges in the last two years (2020-22) where results under this output have been assessed as being moderately below expectations due to the impact of Covid and the subsequent loss in momentum behind performance management and monitoring systems and some inefficiencies in budget allocation and expenditure.

Output indicator 1.1: The purpose of this stream of work was: (1) to improve capability of districts to manage and use data to inform district level decisions; and (2) to increase ownership at district level by Education District Officers (EDOs) to review district performance against key performance indicators. Over the period of PESP II an effective district level performance management system was put in place across all districts of Punjab province through District Review Committee (DRC) meetings and Pre-DRC meetings, with DRCs being led by the Deputy Commissioner (administrative head of a district) and attended by district education officials and school monitoring personnel. While the frequency of these discussions has varied over the lifetime of the programme it is encouraging that these routines have been instituted since 2015 and have continued well after support for these routines by the FCDO supported technical assistance ended in 2018. These routine check-ins have resulted in improvements in enrolment, student and teacher attendance, availability of missing facilities and infrastructure at the district level, and contributed towards the achievement of the Education Roadmap goals for Punjab. In 2015 measurement of early grades literacy and numeracy was added to the mix of KPIs, to enable a focus on student learning outcomes. Other KPIs included recruitment of an additional 3,000-4,000 Assistant Education Officers (AEOs) to supervise primary schools across Punjab reducing the span of control (number of schools to be managed) for each AEO thereby enabling a more effective school supervision and support system. This was also a key Roadmap target and was successfully achieved over this period. The fact that district delivery routines, which include a monthly school monitoring and reporting system, pre and post review meetings, in addition to the DRC meetings, continued throughout this period and have transitioned into the following government is a testament that these routines have become sustainable and are embedded within the system. The PESP II evaluation also found these routines to be effective in maintaining district focus on performance management and progress.
[note] Recommendations to DFID, First e-Pact interim evaluation report on PESP2 2018

Building on these efforts PESP II TA supported the design and scale-up of the School Improvement Framework (SIF) from six to thirty-six districts in Punjab. The School Improvement Framework (SIF) organises 24 indicators into four key domains of school performance and calculates a composite School Status Index (SSI) for tracking school improvement. It categorises schools by their need for improvement, based on the SSI and provides feedback to schools for self-appraisal. It also generates actions aimed at improving specific aspects of the school by the different levels of the education system, which are easy to track and enable a more targeted approach towards quality improvement, decision-making and planning for schools. SIF data is used by district managers to assess school performance and address challenges. SIF was designed and implemented in 6 districts in Punjab in 2020 with support from PESP II TA and scaled up to 36 districts in 2021 – making it a province wide reform.

The TA team conducted a sample based structured review of SIF data to validate the different data streams and to document concerns. The review confirmed that “SIF makes schools more visible (in the upward decision-making system)” and identified major data discrepancies around non-teaching staff and overhead expenditure, which have since been addressed through the monitoring routines. The TA team worked closely with the PMIU and the PITB (Punjab Information and Technology Board) to have SIF routines established at the district and province level. SIF enjoys a high degree of ownership across the government given the collaborative approach adopted by TA in both design and implementation of this initiative. From a sustainability standpoint, PITB will manage the dashboard given their digital expertise while PMIU will own the data loops and liaise on the performance routines.

Following the closure of the Education Roadmap routines, SIF has proven its utility for both SED and PMIU as a structured evidence-based accountability tool to drive performance at both district and provincial levels. A key difference between SIF and Roadmap is the high stakes nature of the Roadmap due to the involvement of Chief Minister. SIF, as a nimble low transaction tool, utilises the data routines set up by the Roadmap process and uses the learning about school management over the life of the programme.

Output indicator 1.2: This indicator assesses the frequency of school visits by Monitoring and Evaluation Assistants (MEAs) and reliability of the data collected. The School Education Department has established a comprehensive school monitoring system whereby data on key education indicators is collected every month by 1,068 Monitoring and Evaluation Assistants (MEAs) across all districts of Punjab. A tablet-based real-time data collection system was piloted and rolled out in all 36 districts of Punjab in July 2015. This has further helped reduce the time lag in data collection and improve the validity of the data due to GPS tagging of schools. This data is then analysed and used to monitor progress. MEAs visit at least four schools per day and are rotated to prevent collusion with school staff. Information is gathered through tablets, with an online monitoring application managed by PMIU.

Over the last decade PMIU has continued to improve its monthly monitoring processes, transitioning from a paper based to an online system that can present and use data collected from the districts in real time. PMIU has also conducted regular validation exercises showing the data to be mostly reliable. Regular spot checks have been carried out by district field coordinators (DFC) appointed through PESP II TA looking at the margin of error between the original MEA data and the DFC spot-checks, as a proxy for data quality. In the period that these DFC spot checks were carried out (2014-18/19), DFC audit data showed that the margin of error was lower than 5% for student attendance, teachers’ attendance, and non-functioning facilities, well below the initially agreed threshold of +/- 10%. DFC spot checks have also identified further opportunities for improvement in terms of data collection methods, quality assurance, analysis, and dissemination.

Data produced by the Programme Monitoring and Implementation Unit (PMIU) from MEA visits has helped to produce and communicate reliable and regular data on what is happening at different levels of the Punjab education system, including for use by the Roadmap for stocktake meetings. Steps have been taken to strengthen the reliability of MEA data and verifications have found the data to be credible. Questions were raised about the adequacy of criteria for assessing actual functionality of facilities, over and beyond them simply being in place, and should be taken into consideration as part of future improvements to data collection.

MEA data, coupled with the Roadmap approach, contributed to increasing teacher attendance in Punjab from 85% in 2011 to 91% in 2022, which is equivalent to more than 20,000 teachers attending each day.

In the final year of the programme, between April 2021-March 2022, there was significant field staff turnover leading to approximately 35% vacant MEA posts. Due to Covid-19, there was a surge of data/IT related jobs which paid higher packages than the Government of Punjab could. This led to such high turnover, which PMIU was not prepared for particularly when the Government of Punjab’s recruitment processes are inherently slow. Hence MEA visits and spot checks of data by District Field Coordinators did not take place as planned. Average progress for MEA visit in the final year stands at 59%. In terms of sustainability, 1,068 MEA posts are government sanctioned and will underpin the data collection drive for SIF and other school management routines in the province. Going forward, PMIU should consider both retention approaches for MEA as well as alternate and agile recruitment mechanisms to fill gaps.

Output indicator 1.3: This indicator has historically assessed the effectiveness of school councils by measuring the frequency and regularity of meetings and the utilisation of funds. Almost halfway through the programme the indicator shifted from measuring the functioning of school councils and allocation of Non Salary Budget (NSB) funds (both targets achieved) to measuring the timely release and utilization of NSB funds.
[note] Functional School Councils Index covered monthly meetings, expenditure of grants/ budgets and improvement in teacher presence.

The school based NSB initiative started as a pilot in 2013/14 in nine districts. In 2014/15, the pilot was expanded to include 18 districts and from the start of the 2015/16 financial year all 36 districts of Punjab have been being receiving NSB. Under the initiative, school councils receive a dedicated amount to cover non-salary expenses including day to day operating costs as well as missing facilities. As an innovation, NSB grants are provided to specific schools using formula-based funding which considers the needs of the specific schools with spending authority devolved to the head teachers and local government officials.

Improving the allocation and access of NSB has been a significant achievement of the government with PESP II support. The provision of NSB has helped mobilize councils to take action on school improvement plans. Schools are reportedly using the grant to meet a range of expenses including repairs, utilities, and classroom consumables. Previously, a lack of automation and absence of a tracking mechanism in NSB disbursement led to rent seeking behaviour by district education and finance officials. Through PESP II support and lobbying, an NSB tracking system has been established and the overall NSB share has increased. Utilisation of NSB allocation has improved to ~90% from less than 50% at the beginning of the programme. This was enabled by the programme’s focus on gradual improvement in the capacity of school councils to utilise non-salary budgets efficiently and effectively as part of the wider PFM reforms within SED. This was complemented by a further push by the district level education managers who were actively using the NSB tracking mechanism. Between July to December 2021 the Government of Punjab had already released 50% of NSB in two tranches of 25% each to districts. Following a political transition due to the change in government and an economic recession, the overall NSB allocation was reduced. Thus, weight adjusted NSB releases were 73% in the reporting year.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme
Key achievements that demonstrate VFM under this output include:
- School Improvement Framework - Economy and Efficiency: TA costing an estimated £5,500 resulted in the scale-up of SIF from six to 36 districts in Punjab. This system will now help district officials to manage performance of over approx. 54,000 public schools in Punjab, enhancing the quality of learning. SIF will also be sustainable beyond the life of the programme following a responsible handover to the PITB and PMIU.
- MEA visits - Effectiveness: The MEA visit routines, together with the Roadmap approach, led to a 10% decrease in absenteeism across Punjab between 2011 and 2018. Using a benchmark of 10% acceptable absenteeism, each 1% reduction in absenteeism leads to savings of ~Rs 3 billion (approx. £13 million).
- NSB Share – Efficiency: One of the efficiency issues is the appropriate allocation of “non-salary recurrent budget” – which pays for some key overheads and operations, including electricity and maintenance. PESP II has successfully lobbied for increasing the share of NSB funds in Punjab. NSB grants are now provided to specific schools using formula-based funding taking into account the needs of the specific schools with spending authority devolved to the head teachers and the local government officials.
  Lessons learned through this output, and recommendations for future programming

Lessons for supporting political ownership – to share with colleagues in BHC Islamabad to benefit programmes across sectors:
- Political ownership is important for any performance routine. SIF could only take off once SED’s leadership was fully behind it. In addition to getting senior buy in, TA also got the district level officers onboard by getting their input in data loops and in design of the dashboard. This helped in the uptake of district level routines as key stakeholders were already familiar and owned the process.
- If PMIU had any mechanisms to do temporary hires to fill MEA gaps, the MEA visit target would not have been dropped. This issue is not unique to PMIU, as Government of Pakistan across the board allows limited flexibility to do temporary hires. Future programmes should continue to work with the GoP/GoPb systems to help develop such flexibility.
- Following good progress on increasing the share of NSB and on improving the releases, it will be worth for any successor programme to do a study on efficiency of NSB spend.

Output Number and Title		Output 2: Better teacher performance and better teaching
Output Score		A
Impact weighting (%)		15%	Impact weighting revised since last AR?	Yes

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
2.1: Development, dissemination and use of new textbooks and teacher guides for primary grades	3 model textbooks & workbooks developed & approved by Punjab Curriculum and Textbook Board (PCTB) / Improved Standard Operating Procedures (SOPs) and criteria for textbook review defined based on model textbooks / Diagnostic of PCTB's procurement process and opportunities for improvement identified and quantified / Targets set for PCTB were met by 2019, when the direct support from PESP II ended. There were no targets in the logframe until 2022, when PESP II TA provided some support to PCTB.		PCTB to complete the development of Textbooks and Supplementary Learning Material Policy.	Target achieved: / Textbooks and Supplementary Learning Material Policy developed and in use by PCTB. / Furthermore, regulations on textbook development have been notified and are in use by PCTB.
2.2: Improved reporting, analysis and dissemination of PEC exam results	PEC improvement plan developed and approved by School Education Department / PESP II support to PEC ended in 2019 and no support was provided to PEC during the PESP II extension period.		(By 2019) PEC organizational development plan approved by PEC Board and implementation started	Target achieved: / Organisational development plan approved by the PEC Board and implementation underway with progress on some key areas such as recruitment of vacant positions
2.3: Quality and delivery of teacher training and mentoring	Refine District Teacher Educator (DTE) schedule based on robust coaching model, and define proper monitoring mechanism for DTE visits to establish true baseline / This target was initially monitoring district teacher training routines until 2017, then focused on teacher recruitment and induction in 2018. Finally, the target was set to develop and implement the continuous professional development for teachers in Punjab from 2019.		15,000 elementary teachers trained in 7.500 Afternoon Schools across Punjab through virtual training module developed by the SED	Overall targets achieved although only partially met in the last year / 12,600 elementary and multigrade teachers including head teachers were trained this year under the continuous professional development strategy. The trainings will continue until end of GoP financial year (i.e. June 2022) by QAED.
2.4: Quality, transparency and timeliness of teacher recruitment and deployment.	92% teacher attendance / This target looked at the teacher attendance until 2017, then from 2018 until 2020, an additional target was added to improve the availability of teachers in schools. In the final two years of the programme the target aimed at the deployment of a robust system for teacher transfers.		An effective, transparent and electronic system in place and functioning for teacher transfers and posting across schools. / 95% attendance rate during the months when schools were open	Overall targets achieved although only partially met in the last year / Teacher e-Transfer system in place at the SED for transfer and postings of teachers / 91% teacher attendance (Mar 2022)

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

The milestones for the final year of PESP II are neither cumulative nor representative of the work of the programme over its lifetime, and so this review includes a narrative account of progress in addition to output scoring. The indicators have been updated throughout the life of the programme, shifting from quantitative indicators like the percentage of classrooms with available lesson plans, teacher absenteeism rates and average number of instructional hours per child, to more specific policy related indicators seen in the table above from the very first year of the programme. This enabled annual revisions to the logframe to push toward important reforms, policies, and implementation in the government, and for Annual Review recommendations to be well tracked, but has meant that it is hard to track progress over the programme lifetime. This output met expectations in almost all Annual Reviews (apart from November 2017, when a complex and politically sensitive effort to improve textbooks was underway).

Although there has been an increase in the number of qualified teachers and teacher attendance at school in Punjab between 2012 and 2022, and some key policy reforms put in place (see below), there was insufficient evidence available to assess whether effectiveness of teaching has improved. Available datasets (ASER and EMIS) only captured data on crude proxies for teacher effectiveness (e.g. teacher qualifications and attendance rates) and did not provide information on teacher competency, teaching process and time on task, and link these to pupil learning gains. However, in the period from 2018-2021 data collected by the government through the classroom observation tool (COT) supported by mentoring of teachers, shows consistent improvement in teaching practices. The COT score which is based on the Teach tool, now being used in many countries, went up from just under 3 to over 3.5 on average providing key insights on improving trends in teacher practices as well as areas for continued support and mentoring of teachers.
[note] Teach is a classroom observation tool intended to be used in primary classrooms (grades 1-6) and was designed to help low- and middle-income countries track and improve teaching quality. The tool measures (i) the time teachers spend on learning and the extent to which students are on-task, and (ii) the quality of teacher practices that help develop students’ socioemotional and cognitive skills. The tool has been piloted and adapted for use in public schools across Punjab.

Teacher attendance has increased by 6 percentage points from 85% to 91% from 2011-2022. This is equivalent to over 20,000 more teachers in the classroom each day, and more qualified teachers have been hired (resulting in an increase in the number of primary school teachers of 50%), student teacher ratios have fluctuated (due to increased student access), and some evidence suggests that teachers are not sufficiently prepared to teach in challenging classrooms, are unable to transfer their knowledge to students, and do not show good teaching practices.
[note] Second Interim Evaluation Report on the Punjab Education Sector Programme (PESP2): Education Policy and Reform Review Update
[note] ePact Performance Evaluation of the Punjab Education Sector Programme (PESP2)

Through TA, PESP II has supported the following relevant reforms:
- Merit-based recruitment mechanisms, and professional standards bill.
- Updates to the Continuous Professional Development policy, to move to school-based mechanisms, accompanied by innovative and appropriate teaching tools.
- Policy development and pilot intervention for the Multigrade Teaching and Learning policy.
- Development of the Digitization and Education Technology Policy.
- Institutional capacity assessment of Quaid-e-Azam Academy for Educational Development (QAED).

Output Indicator 2.1: Development and dissemination of new textbooks and teacher guides was carried out early in the programme, and overall responsibility for improved curriculum has been taken up by the government, and this indicator was discontinued in 2020. To support sustainability a new indicator was added in the 2021 logframe to complete the Textbooks and Supplementary Learning Material Policy, which was achieved as planned. Overall, compared to the original aims of the programme, this output has been successful, and the target was achieved.

Output Indicator 2.2: The driver behind this output was to improve the use of learning assessments in Punjab, with the intention of making them more transparent. TA provided support to the reform of PEC. Successes included the introduction of an organisational development plan and Assessment Policy Framework, including reduction in leakage of test papers, improved compliance in timelines, and strengthened question development and marking. While technical assistance to PEC through PESP II ended in 2019, it is encouraging to note that implementation of the PEC institutional strengthening plan (2020-23) continues to be tracked through a detailed implementation plan. Major achievements to date include the development of SoPs, test item banks, implementation of School Based Assessment (SBA) and commissioning of Large scale Sample based Assessment (LSA), both replacing the old regime of Grade 5 and 8 examinations conducted by PEC.

Output Indicator 2.3: Indicators under this output have continued to evolve to cover more of Punjab’s teaching staff, and to support the district level monitoring of teachers. For example, in 2018/19 TA was provided to support a Primary School Continuous Professional Development Programme. In 2021, the team built on this success to develop a similar framework for elementary school teachers and multigrade teaching support. This year, the teachers from elementary and multigrade schools were trained as part of the continuous professional development strategy developed through support from PESP II TA. QAED will continue training more teachers until the end of the financial year of the Government of Pakistan. This is a promising development, however, 12,600 teachers rather than the planned 15,000 teachers were trained in this period. While overall targets on teacher training and mentoring over the life of the programme have been met, the target for the last year of the programme has been partially achieved.

Output Indicator 2.4: This indicator originally tracked the number of primary schools with at least 4 teachers, with the intention of reducing schools with multi-grade teaching and reducing student absenteeism. As set out above, the number of teachers in the province increased over the lifetime of the programme, and other successes included the introduction of an automated mechanism for transfer of teachers. Teacher attendance was slightly lower than the target (91% compared to 95%), but this is in line with the original target (and likely impacted by COVID), and the systems are in place, so this target is marked as achieved.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

Overall: Many of the components of PESP II have involved support to teachers. SBS has been put towards teacher salaries in governments schools, financial aid to PEF has paid for teacher salaries in PEF schools, and TA support has been given to various departments supporting teachers. Quality teaching is the most important influence on children’s learning in school, and so positive impact in this output will have an overall positive impact for the entire programme. While there is limited data to assess exactly how the quality of teaching has improved over the life of the programme, but work to rationalize teacher allocation, increases in teacher numbers, and reductions in teacher absence are likely to have increased the efficiency of spend on teacher salaries – both from PESP II funds, and for the GoPb as a whole.

Economy: Key cost drivers are teacher salaries and TA fee and travel costs. VfM of TA is considered in Output 6 below. Teacher salaries have increased over the course of the programme, and are set following political priorities and therefore out with programme control.

Efficiency and effectiveness: as outlined above, reforms implemented have resulted in lower teacher absenteeism and more time on task and thus likely to have impacted efficiency of overall spend.

Equity: although some efforts have been made through this output to reach the most marginalized children in Pakistan (for example through support to Continuous Professional Development (CPD) at Special Education Department (SpED), there does not appear to have been a consolidated effort across all outputs to focus on equity.

Key lessons from this PCR

Lessons for future programme design and management:
- Measure the quality of teaching: to understand the cumulative success of a teacher focused output, and an outcome measurement of teacher quality (or preferably linked student performance)
- Ensure that equity (for marginalised groups such as girls, children with disabilities) is central to efforts to support teachers

Technical lesson to share with the FCDO’s Education cadre:
The successfully implemented shift to blended learning would be a beneficial lesson for colleagues working on education, particularly following the broader shift to blended learning following COVID-19.

Output Number and Title		Output 3: High quality school infrastructure
Output Score		B
Impact weighting (%)		25%	Impact weighting revised since last AR?	Yes

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
3.1: Improved availability and functioning of basic school facilities (toilets, boundary wall, drinking water, electricity) in all districts	All districts with a functioning of facilities >90% or a clear plan to improve functioning of facilities to >90% within the current school year / (This was achieved in 2018 and we decided to add the targets against the additional classroom construction component we decided to implement through PMIU) / In 2019 this indicator was modified to measure progress on the school construction and rehabilitation work supported through the government		a) Construct and handover 2,031 classrooms / b) Upgrade 110 model schools / c) Rehabilitate 1,000 Sci and IT labs each / d) Rehabilitate 400 libraries / e) Provision of over 60,000 furniture items / f) Provision of over 4,000 water coolers and filters for Insaaf afternoon schools	Target achieved: / a) 2017 classrooms constructed and handed over. / b) 110 model schools upgraded / c) 1037 Sci and IT labs rehabilitated / d) 400 libraries rehabilitated / e) 54,894 furniture items provided / f) 4,101 water coolers and filters for Insaaf afternoon schools provided
3.2: Number of fit for purpose classrooms and toilet cubicles constructed under School Construction and Rehabilitation Programme (SCRP) (Disaggregation gender, disability)	Implementation Phase workplan finalised and TACE rolling into implementation. / 15,059 additional classrooms in existing schools and the provision of missing facilities to 10,187 schools		Handovers of completed schools: / IMC Worldwide completes handover of at least 1040 schools by Sep 2021 in Punjab	Target substantially not achieved: / Although the final year target was achieved, IMC Worldwide only managed to complete 4,508 (30%) of the original target (15,059 classrooms).
3.3: Percentage decrease of failed construction inspections per quarter (where %age is calculated as number of failed inspections divided by the sum of passed and failed inspections)	Not applicable - Indicator introduced in September 2017 / 0.8% for Q4 2017 / Baseline (Sep 2017): 8.8% / Indicator changed 9 Oct 2020: / Quality issues identified through inspection visits (Third Party Validation/others) are rectified by IMC Worldwide as per workplans		IMC Worldwide meets 100% KPI targets related to Quality, retrofitting and handover by 30 Sep 2021.	Target achieved: / IMC Worldwide met 100% of KPI targets

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

Given the complexity of this output’s activities and performance over the life of the programme, a more detailed narrative (including on the background/design of the intervention) is provided.

This output was designed in response to GoPb’s identification of significant needs in school infrastructure. The government’s development budget for education (PKR 4 billion, approximately £20 million) would not have been able to meet that demand. UK funding (£104 million) was therefore allocated for the construction of 15,059 additional classrooms in existing schools and the provision of missing facilities to 10,187 schools. GoPb agreed to maintain its existing annual budget to close the remaining gaps and provide additional funds for maintenance and to make more money available at school level.
[note] PMIU data supported by field investigations identified a need for more than 27,000 additional classrooms in public schools to accommodate children already enrolled. Basic facilities were also required, including drinking water (in about 4,000 schools), sanitation (in over 5,000 thousand schools), electricity (in over 16,000 schools), boundary walls, particularly for girls’ schools (over 6,000 schools), and basic furniture (for nearly 4 million children).

Innovation was central to the programme. Working with the provincial government, the delivery teams would test new approaches and seek to challenge the norms of government practices through devolving contracting to local communities, bringing in innovative and energy efficient designs, building earthquake & natural disaster-resistant structures, using climate-friendly local materials, and engaging School Councils in planning, design and contract management.

While the principal focus of the infrastructure component was to secure availability of classrooms and basic facilities to every student in Punjab, it also recognised the opportunity to address the poor state of school maintenance and facilities management. Pilot interventions were proposed to test transformational changes in the state’s role, and help government to focus on how school design, building, operation and maintenance are commissioned. It was intended that the programme be deployed as a basis for opening up policy dialogue with government on improving both the quality and the cost effectiveness of its own work in this area.

To address fiduciary risk and corruption concerns, the infrastructure component was managed through a specialist Technical Assistance Consulting Engineer (TACE), working closely with the School Education Department (SED). The TACE would be mandated to explore innovative approaches to contracting and DFID/FCDO would dedicate staff time to help bolster an already supportive policy environment. DFID/FCDO would also work with potential investors and financiers to develop viable PPP models that help the reform and modernisation of public services, improve value-for-money procurement, increase contestability in delivery of public services, deliver improved transparency of costs of public services delivery and facilitate arrangements for sustainable models of operation and maintenance over the longer term.

Due to the TACE supplier IMC Worldwide encountering problems with registration and approval to operate in Pakistan, delivery of the infrastructure component did not commence until 2015. It subsequently suffered numerous delays and challenges. Some buildings designs prepared by IMC Worldwide proved to be unsafe due to a shortfall in seismic resilience (subsequently remediated at the cost of the Supplier); local sub-contractors failed to complete construction contracts on schedule; and an increasing number of quality issues identified through Third-Party Inspection (TPI) required remediation. The Supplier’s contract had to be amended and extended on 13 occasions to accommodate delays in delivery as well as a reduction in the budget allocation. Funds released through IMC Worldwide budget reduction were used to support a Financial Aid Agreement with the government and a reimbursable grant with The Citizens Foundation (TCF), both of which focused on school construction and provision of missing facilities.
[note] Design shortfalls were initially identified through Third-Party Inspection. Although IMC Worldwide stated that the designs were safe, they were unable to produce evidence to support that assurance. This led to the Design Review through which the majority of schools (75%) were found to have safe designs, but the remainder required retrofitting to meet the earthquake resilience standards in the Pakistan Building

None of the annual reviews records any attempt by the TACE supplier to explore innovative approaches to contracting nor for “DFID to dedicate staff time to help bolster an already supportive policy environment…”. The close working relationship between the government Communications and Works Department (C&W) and IMC Worldwide mandated by the Business Case was halted at the request of IMC Worldwide. This departure not only blocked dialogue with the government to explore potential innovations; it also sowed the seeds for operational challenges when IMC Worldwide endeavoured to hand over completed works.

On completion, a total of 7,114 classrooms were constructed or rehabilitated and missing facilities were provided at 1,150 schools. The total cost of these investments was £104 million. The Government of Punjab despite its resource constraints managed to construct 6,000 additional classrooms during PESP II. School designs prepared by IMC Worldwide were checked by an independent party and those buildings which failed to meet national seismic resilience standards were retrofitted using a ferro-cement overlay. Retrofit designs were also checked by an independent party.

PMIU adopted building designs based on standard government drawings and specifications facilitating construction as local contractors and material suppliers were familiar with the building requirements. The PMIU component also got off to a slow start and eight months elapsed between the Exchange of Letters in March 2019 and commencement of construction activities in November. However good progress was made thereafter although an accumulation of delays caused by the COVID-19 pandemic required the closing date for the component to be extended on three occasions. By final completion in July 2021, the original target of 2,000 classrooms had been increased to 2,031 and additional facilities such as schoolroom furniture and water coolers were provided (all using exchange rate savings).

Output indicator 3.1: This output was initially to track functioning facilities in schools in Punjab and the target for all districts with over 90% functioning facilities was met by 2018. In early 2019, recognising the slow progress by IMC Worldwide, it was decided to divert SCRP funding for construction and rehabilitation of existing facilities through £35 million of financial aid to the Government of Punjab (GoPb) and through a £4.7 million accountable grant to The Citizen’s Foundation (TCF).

The TCF component also suffered a delayed start and had to be suspended whilst concerns over the seismic resilience of building designs were resolved. Eventually, TCF adopted designs similar to those used by PMIU. However, there were problems with construction quality and 14 classrooms had to be demolished and re-built (at TCF expense). By the time the component was completed in July 2021, TCF constructed and handed over 600 classrooms, built 100 toilets and provided 7,050 furniture units with UK funding and fully achieved the agreed targets by June 2021.

PMIU constructed and handed over 2,017 out of 2,033 classrooms targets and these remaining classrooms are at finishing stages with delays because of administrative changes at the district levels. PMIU has taken responsibility to complete remaining targets. 110 model schools have been fully upgraded. 1,037 Science and Information Technology laboratories against the target of 1,000 each. 400 libraries were built / upgraded and are fully functional. 54,894 furniture units have been procured and delivered against the target of 60,000. 4,101 water coolers for safe drinking have been provided against the target of 4,000. The project overall stands 99% complete which is accepted as progress achieved for this target.

Output indicators 3.2: This output tracks progress of schools constructed and handed over by IMC Worldwide. The overall target for this was to build and handover 15,059 classrooms which is not met. This target was revised down to 4,508 classrooms – which has been met by IMC Worldwide. However, with significant reduction and change in target this is not met.

Output indicator 3.3: This indicator was introduced back in 2017 which tracks compliance to IMC construction quality checks conducted by a third-party monitoring organisation. This is measured in terms of percentage decrease of failed construction inspection per quarter. In the final year of the programme, the indicator was revised to include 100% achievement of Key Performance Indicators related to quality, retrofitting and handover of classrooms. IMC Worldwide has achieved this target to 100%.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

Overall, this output did not represent good VfM, in terms of economy or efficient use of resources. The envisaged volume of infrastructure was not delivered and the intent to show a more effective and sustainable use of resources did not work, with status quo (PMIU) approach being used to greatly improve VfM in the final implementation phase.

Economy. The main cost drivers under this output were construction costs. All building contracts were procured through a competitive tender process. Schools in remote locations were less attractive prospects for local building companies, so, for example, IMC Worldwide promoted the use of ‘lots’ which included a package of schools across the full range of locations. The most convenient parameter for comparing unit cost of construction is a standard 16 ft x 25 ft classroom. Analysis of data from UK funded education sector infrastructure programmes in KP and Punjab showed the following construction costs per standard classroom:

Provider	Punjab PMIU*	TCF (Punjab)	IMC Punjab*	KP PIU**	IMC KP**
£/classroom	6,912	7,100	6,693	11,875	9,374

*Significantly higher overhead/TA costs for TACE SCRP component have not been factored into this comparison
**Significantly higher unit costs in KP reflect requirement for greater seismic resilience and increased construction costs in remote areas.

IMC Worldwide delivered classrooms at 3% less than the cost of Government of Punjab-constructed classrooms. However, as discussed above (and relevant to Efficiency, discussed below), this financial cost saving came at the expense of much higher transaction, management and time costs. At around 35%, IMC’s charges for technical assistance were above the usual range of charges (15%-25%) for development projects. They were also higher than those charged by government partners. However, the reimbursement provisions for both KP and Punjab government technical assistance were capped at 5% and 10% respectively whereas there was no such restriction under the IMC Worldwide contract. In the Exchange of Letters (EoL) with the Punjab Government, no financial cap was placed on the unit cost of classroom construction..

Efficiency and effectiveness. Ultimately, the TACE model failed to deliver the amount of quality infrastructure required in a timely manner. Therefore, although the Business Case dismissed the use of financial aid to support government-led infrastructure delivery due to concerns over corruption and fiduciary risk, the delays and technical problems with IMC Worldwide prompted FCDO to revisit the option. It was decided that £32.97m out of the original £104m would be allocated to GoPb for school construction and rehabilitation works. The greater fiduciary risk and higher build-costs were evaluated to be worthwhile when compared to the delivery challenges presented by IMC Worldwide. Working with GoPb also presented attractive efficiency gains, such as the use of “shovel-ready” designs and ability to deploy GoPb’s own institutional and administrative resources and facilities in support of the works.

Equity. There were occasional instances where the provision of access for persons with disability could have been better: at IMC Worldwide constructed schools access ramps were sometimes provided in locations away from the main entrance to school buildings and at Government constructed schools, access ramps were constructed with gradients steeper than those recommended by national codes of practice. In both instances, a lack of construction space often determined the use of the less satisfactory option.

Lessons learned through this output, and recommendations for future programming

Key lessons from support to school infrastructure are as follows:
- The TACE Supplier contract was awarded following competitive tender. However, the new commitment exceeded 200% of the company’s previous annual turnover and it had to be delivered in a country where they had no established presence. It took over twelve months for the Supplier to obtain the necessary government approvals to commence operations. It is recommended that future procurements avoid the risk of appointing a supplier lacking recent in-country experience and already in possession of appropriate registrations to operate.
- Although the Business Case and the ToRs for TACE clearly identified the requirement for buildings to be seismic resilient, the supplier failed to ensure that their designs met the requirements of the Building Code for Pakistan, Special Provision 2007. For any programme that involves structural design work, it is recommended that all supplier designs are checked and certified by an independent structural engineer (holding and maintaining an appropriate level of Professional Indemnity insurance) to confirm compliance with relevant national standards (or international standards where national standards are not available).
- National standards and guidelines relating to access for persons with disability as well as earthquake resilience had not been adopted by the Provincial Government and it is recommended that such provisions should be a requirement of future agreements supported by Financial Aid and that the FCDO continue to engage the GoPb to review their standards to incorporate better access into their designs or policy.
- The Business Case encouraged innovative and energy efficient design criteria. The IMC Worldwide response was to utilise a form of brickwork construction known as Rat Trap Bond (also referred to as Chinese Bond). Although this form of construction met both criteria, it was not in common use in Pakistan and presented a workmanship challenge to local building contractors. It was probably a significant factor in driving higher than normal construction costs. It is recommended that any requirements for innovation are tested against value for money criteria before they are rolled out on a large scale, piloted for technical suitability and, where necessary, formal approval sought through national standards bodies.
- While political /economy and other factors may have inhibited devolution and enhanced community engagement and oversight in construction in Punjab, experience from KP and elsewhere internationally still suggests the long-term cost, quality and sustainability advantages of community engagement in school infrastructure.
- The TACE delivery model marked a departure from previous arrangements for infrastructure projects where the roles of employer, engineer and works contractor are contractually separated. It is recommended that the standard FCDO supplier terms and conditions are adopted if further contracts are to be invited using the TACE delivery model. This may include adoption of NEC contract models or specific tailoring of standard FCDO services contracts to ensure Special Conditions are adopted that support the nature of the TACE model.
- Where Quality Assurance (QA) arrangements for infrastructure programmes are appropriate, it is recommended that the supplier is required to: provide evidence of their company’s QA registration and QA audits; present a project specific Quality Management Plan during the inception phase of the programme; and to arrange for an annual review of QA arrangements by an independent party.
- To provide an incentive for timely delivery, it is recommended that programmes involving the design and construction of building and civil engineering works should be based on the delivery of outputs rather than the provision of inputs.
- The programme had a very limited provision for technical infrastructure support (0.25 FTE). It is recommended that BC staffing proposals for infrastructure programmes should be reviewed and signed off by the Head of Profession at Quality Assurance Unit (QAU) stage.
- The terms of the contract were not aligned and lacked specification of tasks necessary for a construction contract such as design expectations, compliance and verification of  standards and sub-contractor management.  It is recommended that Standard technical assistance service delivery contracts are not fit for purpose for large Infrastructure development projects. The contract terms should clearly lay out the tasks including clear roles and responsibilities of parties concerned (including parties that will take over the assets) and the process for identification of issues and their resolution in a timely manner.  FCDO programme teams should be established to match the required arrangements.

Output Number and Title		Output 4: Improved access to schools, especially in priority districts
Output Score		A+
Impact weighting (%)		20%	Impact weighting revised since last AR?	Yes

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
4.1: Number of Out of School Children (OOSC) enrolled in priority districts through Punjab Education Foundation (PEF) & Civil Society Organisations (CSOs)s	Select, finalise, and sign agreement with CSOs for OOSC enrolment in priority districts / 32,000 out of school children enrolled in new schools in 2 priority districts		(By 2017) 32,000 out of school children enrolled in new schools in 2 priority districts / (By 2020) 150, 000 out of school children enrolled through FAS, EVS and NSP in new schools across 11 districts / (By 2022) 44,000 out of school adolescent girls are enrolled in and complete (graduate) ALP and TVET in three districts of South Punjab	Targets achieved/exceeded expectations: / 31,772 out-of-school children enrolled into new schools in 2 priority districts / 285,307 out of school children enrolled through FAS, EVS and NSP in 11 priority districts / 49,467 out of school adolescent girls are enrolled in and complete (graduate) ALP and TVET in three districts of South Punjab
4.2: Number of children in school supported through PEF (cumulative); / i) Education Voucher Scheme (EVS) / ii) New School Programme (NSP) / iii) Foundation Assisted Schools (FAS)	(i) 358,000 / ii) 111,000 / iii) 430,000		(by 2018) / Total: 2,620,000 students / i) EVS - 515,357 (Boys: 283,446; Girls 231,911) / ii) NSP - 237,516 (Boys: 130,633; Girls: 106,883) / iii) FAS - 1,872,126 (Boys: 1,029,669; Girls 842,457)	Total target achieved/exceeded with variation in sub targets: / Total: 2,636,528 students / i) EVS 449,150 (Boys 243,735; Girls 205,414) / ii) NSP: 285,808 (Boys 153,811 Girls: 131,997) / iii) FAS: 1,901,570 (Boys 1,011,909 Girls 889,661)
4.3: Number of additional children with special educational needs and disabilities enrolled and supported.	Approval of PC-1 for Punjab Inclusive Education Programme (PIEP) in two districts of Punjab (Bahawalpur and Muzaffargarh)		(By 2020) / 4,700 additional children with SEND enrolled in special education institutions	Target substantially exceeded: / 9,959 additional children with SEND enrolled in special education institutions
4.4: Number of scholarships for poor and able students disaggregated by sex	(i) 260 merit-based scholarships through LUMS ii) 7,000 intermediate level scholarships to girls through PEEF		20,000 additional intermediate level scholarships provided to girls in Punjab by PEEF out of which at least 1,500 scholarships given to children from minority groups / (By 2022) 78,540 intermediate level scholarships provided to girls in Punjab by PEEF	Target substantially achieved: / 25,000 scholarships provided to girls. Out of which 2,620 given to children from minority groups / Total 80,000 scholarships were provided to girls during PESP II by 2022.

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

Interventions under Output 4 aimed to increase marginalised children’s access to education with a focus on poor girls, out of school girls, children with disabilities and religious minorities. Interventions under this output included increasing access for children in poor districts (as characterised by poverty levels and number of OOSC) through PEF’s voucher programmes, accelerated learning programmes for poor out of school girls, technical assistance and SBS to Punjab’s Special Education Department, merit based scholarships for poor girls in secondary schools, LUMS National Outreach Programme (NOP), technical assistance to strengthen capability of the Punjab Special Education Department and inclusive education pilots to enrol children with ‘mild’ disabilities in mainstream schools. This output has consistently exceeded expectations over the life of the programme as results achieved have substantially exceeded targets for each of the components.
[note] The project referred to a mild disability as any restriction or lack of ability (resulting from an impairment) to perform an activity in a manner or within the range considered normal for a human being.

Output indicator 4.1: This output tracked the number of OOSC enrolled through the Punjab Education Foundation (PEF) (via its Education Voucher Scheme (EVS), New School Programme (NSP) and Foundation Assisted Schools Programme (FAS)) from 2014 to 2018 and the Siyani Sahelian programme (delivered through the NGO Idara-e-Taleem Agahi (ITA)) from 2018 to 2022 in poor districts with a high percentage of OOSC. PESP II provided targeted financial aid to PEF to expand EVS, NSP and FAS to 11 low performing districts.

PEF mostly achieved its targets, enrolling over 285,000 children. The e-Pact evaluation found that PEF has continued to be a highly effective organisation, achieved a large increase in enrolment and made incremental improvements in its core programmes. These continue to represent one of the most significant and successful PPP arrangements in education in low or lower middle-income countries.

Siyani Sahelian focused on adolescent girls in three of the poorest districts in Punjab. Throughout, ITA achieved or exceeded programme milestones, equipping more than 49,000 girls who had dropped out or never attended schools with functional literacy/numeracy skills and brought them (back) into mainstream formal schools. A3G has also supported economic empowerment of 3,500 girls (aged 14-21) by helping them train and achieve certified vocational skills. A3G has particularly targeted vulnerable girls and has reached 189 girls with a disability, 1,568 girls who were married as children and 340 girls belonging to minority groups. An external evaluation conducted by OPERA found that ITA had provided a comprehensive and holistic package of support to marginalized girls. There was a quantifiable impact on learning – with scores improving in English, Urdu, and numeracy. For example, while no girls enrolled in the 45-day accelerated learning course were able to read a sentence in English at baseline, by the end of the programme 91% were able to do so. The programme also boosted knowledge and awareness among the cohort on women’s rights and empowerment. Parents of the children attending the programme also reported a change in attitude towards the education of their daughters and higher aspirations for their future education.
[note] https://www.itacec.org/SiyaniSahelian/document/resources/Third_Party_Evaluation_of_the_Siyani_Sahelian_Programme.pdf

Output indicator 4.2: This indicator tracked the total number of children enrolled in the three PEF schemes (EVS, NSP, FAS). PEF met the total target by enrolling 2,636,528 children and met expectations throughout the lifetime of the programme. In addition to these interventions, support was also provided to PEF under the Punjab Inclusive Education Programme (PIEP) pilot which used vouchers (Inclusive Voucher Scheme - IVS) to improve access to education in PEF schools for children with disabilities (2015-2017).

Targeted financial aid to PEF was supplemented through technical assistance to help deliver its programmes and strengthen its management and SBS provided through the provincial budgets against targets agreed in the RAF relating to PEF operations. PEF has provided a cost-effective model (see VFM section below) for increasing attendance in Private Schools, which was the main metric of success. However, evidence captured in the e-Pact evaluation noted that children were not always enrolled in the correct grade for their age. Although it was challenging to capture data on learning outcomes and not possible to draw firm conclusions, the e-Pact evaluation noted there had been some improvement in basic skills and narrowing of educational attainment between the poorest girls and the poorest boys. Due to limitations in the data available, particularly disability data, it was not possible for the programme to draw in depth conclusions about the impact on marginalised girls and boys.

Output indicator 4.3: Under this indicator, PESP II undertook a series of activities and initiatives to improve the quality of education of children with disabilities, and to increase enrolment. Two pilot projects were implemented as a part of this programme: an inclusive education pilot in government (SED) schools in two districts and an inclusive voucher programme (IVS) with Punjab Education Foundation (PEF) partner schools in seven districts. The Pilots took place from 2014 to 2017. Technical assistance and SBS were provided to the Punjab Special Education Department and Education department on special education through various providers, including Cambridge Education and Technical Assistance Management Organisation.

These pilot projects were managed by an independent Punjab Inclusive Education Programme (PIEP) Programme Implementation Unit (PIU). Both pilot projects focused on identification, enrolment and retention; screening and assessment; teacher training and infrastructure; improving planning, co-ordination and communication for inclusive education. The e-Pact independent evaluation surmised that the approach of the PIEP pilot was appropriate, however there were significant weaknesses in the implementation and the overall design (particularly a lack of stakeholder ownership). Problems were most pronounced in Government schools, whereas the PEF pilot was considered a moderate success and was able to be sustained by PEF. After the pilots had been concluded, the overall programme shifted away from support to inclusive education and towards SBS and TA to SpED. The e-Pact evaluation noted that although the switch to SBS to SpED was understandable, it has not been justified by the subsequent results and was a departure from the original objective of the programme. Weaknesses were also identified by e-Pact with SBS as stipulations about where the money should be allocated were not rigidly enforced through a results framework. As a result, SBS to SpED did not result in an increase in funding to special education schools. Despite these challenges, several positive achievements were noted in the e-Pact evaluation as result of the programme’s work in inclusive education - such as the successful implementation of the PEF pilot; institutional strengthening of SpED and collection of data; and the development of the Inclusive Education Strategy (IES) and the Special Education Policy (SEP). The e-Pact Evaluation noted that DFID/FCDO was often the only donor working in the inclusion space. The sustained advocacy from the DFID/FCDO programme made a huge contribution to pushing inclusive education up the agenda. Unfortunately, insufficient budget has constrained the implementation of the Inclusive Education Strategy and Special Education Policy. Significant challenges in the governance of both SED and SpED, data collection, funding and capacity at all levels of the education system remain.

Output indicator 4.4: This indicator was delivered via the PEEF programme, which has provided funding for 80,000 intermediate-level scholarships for female students from eleven less developed districts of Punjab (and in addition funding has been provided for 500 undergraduate level scholarships for both male and female students in Punjab). This programme has achieved its final target. The e-Pact evaluation focused on the intermediate level scholarship and found that the delivery of the scholarships was efficient and had a positive impact on the students (97% considered that it has changed their future prospects). However, the evaluation also noted some weakness in PEEF’s monitoring system and follow-up, which meant it was not possible to draw detailed conclusions about educational achievement. The Fund also had quotas for children from marginalised backgrounds, including children with disabilities and orphans.

A Lahore University of Management Sciences National Outreach Programme (LUMS/NOP) scholarship had been set up in 2001 to ensure that talented students from disadvantaged backgrounds from across Pakistan could get the opportunity to attend LUMS, a leading private university. DFID/FCDO’s support involved organisational development of the LUMS-NOP programme, funding for scholarships and development of the ambassadors programme. This has allowed LUMS to substantially expand the NOP programme, enabling it to reach a greater number of students from diverse backgrounds. The LUMS/NOP scholarship reached 1,168 individuals in total.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

Equity: An assessment on equity for this component is challenging due to lack of robust and consistent data. The e-Pact evaluation was able to conclude that there had been some success getting the poorest into school, but not necessarily retaining them in education. It was not possible to tell whether gender equality in access to school had improved. In regard to disability inclusion, e-Pact was not able to find any data on the quality education provided to children with disabilities. Some areas of success were achieved through TA provision (e.g. formation of the IES), and improvements in access for marginalized groups via ITA and scholarships. Overall, the e-Pact evaluation concluded that the provision education for children with disabilities was still inadequate despite the programme’s interventions. For example, funding to implement policies that would improve equity in education is still limited.

Effectiveness and Efficiency: The TA provided by the programme was generally considered by the e-Pact evaluation as well managed, although as stated above the effectiveness was constrained by limited funding available and the changes in the political leadership throughout the programme. Both the PEF and PEEF scholarships were assessed as highly effective and efficient by e-Pact’s evaluation due to their relatively low cost and high contribution to increasing access to education. For example, DFID/FCDO’s contribution to PEF supported 333,700 students learning for a year at a cost of c. PKR 7,075 (£37) per student – a much cheaper rate than Government Schools. VfM could have been further advanced by mainstreaming an equity approach and further strengthening PEF’s capacity to monitor and evaluate the programme. The LUMs-NOP scholarship was more problematic from a VfM perspective, as it was a relatively high-cost programme with a small number of beneficiaries. Social gains from the programme that could have been linked with diversifying the student base of LUMs were not measured or captured as part of the programme. There were a couple of areas where effectiveness and efficiency were not achieved, for example the PIEP pilots, as mentioned above, were less effective and efficient due to programme management constraints. The switch to SBS also did not translate into an increase in funding for Special Education so scored poorly on effectiveness measures.

Economy: As evidenced by the evaluation, the A3G/Siyani Sahelian Programme performed well on economy measures. The total average cost per beneficiary over the life of the programme has been estimated to be £102 . As the average government school placement cost is £134, this suggests that the programme provides good value for money on economy measures. As stated above, the programme was effective in both advancing educational outcomes but also changing attitudes. The programme had a significant focus on engaging marginalised girls from religious minorities and had also enrolled girls with disabilities.
[note] OPERA Evaluation: https://www.itacec.org/SiyaniSahelian/document/resources/Third_Party_Evaluation_of_the_Siyani_Sahelian_Programme.pdf

Overall: The value for money for this component has been mixed, with some areas of strong performance in scholarships and the ITA component and weaker areas such as SBS and TA. An assessment on equity for this component is challenging due to lack of robust and consistent data. The e-Pact evaluation was able to conclude that there had been some success getting the poorest into school, but not necessarily retaining them in education. It was not possible to tell whether gender equality in access to school had improved. An evaluation on FCDO’s support to Special Education conducted by e-Pact concluded that the level of provision for children with disabilities within the school system was still inadequate. There is no data available on the quality of education provided to children with SEND or results achieved. Stand-alone components such as IVS, ITA, PEF and PEEF have made progress in improving educational access for the most marginalized.

Lessons learned through this output, and recommendations for future programming

Overall: Although some positive gains were made in improving access to school for the most marginalised, the programme experienced some constraints. Equity considerations were not mainstreamed throughout all components, meaning that some opportunities to address for example, disability stigma and discrimination, were not capitalised upon. For future programmes, a strong gender, social inclusion and disability analysis and subsequent framework could help guide activities. A stronger focus on data disaggregation, where possible and relevant, would also help set milestones for equity considerations and assist with monitoring. Future programmes should also be mindful of balancing contextual constraints with the requirements of the UN Convention of the Rights of Persons with Disabilities (CRPD), particularly Article 24 and General Comment 4) which calls for state parties to move towards inclusive education rather than maintaining a segregated system. In alignment with FCDO’s Disability Inclusion and Rights Strategy, the programme should establish ways of working that encourage participation and leadership of people with disabilities and other marginalised groups in areas that impact them.

PEF. PEF’s experience has continued to demonstrate the viability and effectiveness of well managed and designed PPP arrangements in education, but also their vulnerability in the absence of a clear long-term government strategy and sustainable funding arrangements. The e-Pact Evaluation also noted that a more systemic approach may needed to ensure that programmes are not solely focused on increasing enrolment but take into account other measures such as retention and learning.

Siyani Sahelian. The OPERA evaluation particularly highlighted the holistic nature of the approach as key enabler of success– which included life skills, entrepreneurship as well as academic subjects. It also highlighted the provision of safe transport (which allayed safety fears) and the incorporation of ethics and morality into some of the teaching as two initiatives that were instrumental in the subsequent success of the programme. The ITA team acknowledged that further partnerships with civil society and community mobilization could help increase the reach to girls with disabilities. This will be an important factor in future work as marginalized girls, particularly those with disabilities, who are amongst the least likely to return to school after COVID-19 lockdowns.

PEEF. Equity and inclusion objectives (including those related to gender and disability) should be explicitly incorporated into scholarship programme design. And monitoring, evaluation, and learning should be built into the programme design from the start and should be linked to building the capacity of partners in these functions.

SBS, Pilot Programmes. There were a number of lessons learned particularly in the implementation of indicator 4.3. The evaluation found that the potential impact of the sector budget support was constrained as there were not enough parameters put in place to ensure it was spent in-line with targets. Future SBS support should ensure that appropriate targets are agreed and monitored alongside the funding. Pilot programmes need to ensure effective engagement and ownership from key stakeholders as well as being appropriately designed and managed to maximize the likelihood of success.

Output Number and Title		Output 5: Top political leadership engaged on education reform agenda in the Punjab
Output Score		A
Impact weighting (%)		10%	Impact weighting revised since last AR?	No

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
5.1: Data analysis and performance management routines	Indicator introduced in Jan 2017 / (i) Number of formal stock take meetings / (ii) Frequency of pre-stock take meetings and routines versus plan, specifically: / 1. Quarterly review with the Chief Secretary (CS)/Additional Chief Secretary (ACS)/Chairman Planning and Development P&D / 2. Monthly review with Secretary Schools / 3. Monthly note to the CM and senior officials on progress and key actions		(By 2018) (i) Number of formal stocktake meetings (ii) Frequency of pre-stocktake meetings and routines against plan / (By 2022) Monthly data review meetings undertaken with PMIU to discuss and facilitate better data and its usage within the department	Target achieved: / Quarterly stock take meetings and pre-stocktake routines have been carried out as planned / Monthly data review meetings conducted with the PMIU leadership
5.2: Roadmap transition planning and handover	Indicator introduced in May 2017 / At least 20 trainings conducted / Initial target was set in 2017 which focused on the capacity building and in the later part of the programme the focus shift towards setting roadmap routines.		(By 2019) / (i) Perspective on future priorities to be developed as part of the Education Blueprint / (ii) Handover of all Roadmap activities and routines to the appropriate teams	Target achieved: / As part of the transition process, the roadmap team developed future strategy documents on quality, enrolment and delivery approach and fed into the ‘New Deal’ for Education document

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

PESP II was a long and complex programme, with a strong focus on sector improvement. There was a change in Government in 2018, which fundamentally shifted how the government worked with the education sector: before 2018, it was a key priority for the Chief Minister of GoPb who monitored the sector through the Education Roadmap. After 2018, the incoming Chief Minister delegated responsibility for the education sector to the Education Minister. However, from interviews carried out for this review, with government officials, development partners and other stakeholders, it is clear that the government has remained committed to the education sector throughout the lifetime of this programme (i.e. during the rule of both political parties). Punjab is one of the only two provinces in Pakistan who meet the GPE criteria of spending more than 20% of their budget on education; Punjab allocated 23% of its total budget towards education in FY 2021-22. However, it is much harder to attribute how and if this is a result of commitment to PESP II.

In the period before 2018, the Chief Minister of GoPb was highly committed to the delivery of education reforms through the Education Roadmap and related Stocktakes. The e-Pact evaluation of PESP II found that the Roadmap and Stocktake process was largely an effective vehicle for creating momentum for education sector reform in Punjab and monitoring improvements in the education system, and that support from PESP II has played a central role in facilitating this process. This is reflected in the achievement of targets set by the Roadmap: the final stock take held in March 2018 showed that all roadmap goals have been met (or even exceeded), except for school construction targets. Over this period core Roadmap indicators continued to show progress. Significant achievements include: increase in school participation rate of 5-9 year olds from 84.8% in November 2011 to 94.9% in 2018; enrolment of 1.6 million more children in public schools since 2012; 1.85 million additional children enrolled in low cost private schools through public private partnerships; the percentage of schools with four and more teachers increased to 87% in April 2018; and a dramatic improvement in early grade literacy and numeracy levels, with Grade 3 students in Punjab attaining an average score of 77% in March 2018 on independently administered six monthly assessment - an increase from 56% in March 2015.
[note] In the context of Education Roadmap approach, Stocktakes refer to high level periodic performance review meetings (bimonthly or quarterly) chaired by the Chief Minister or Minister to drive accountability and create impetus for urgent progress on agreed targets

The Roadmap also launched a set of new routines (pre-stocktakes with the Chief Secretary, weekly meetings, a monthly note to the CM, Monthly Roadmap Data Review) to drive increased government ownership and a system-wide focus on reforms. Some examples of the effectiveness of stocktakes include: merit based recruitment and continuous professional development of teachers; the creation of new teacher posts and the successful recruitment of over 69,267 new teachers; the hiring of 2,100 additional AEOs to boost overall performance of schools; the expansion of the PEF NSP to provide access to education in underserved areas; partnerships with the private sector to support low performing public schools through Public School Support Programme (PSSP); and the approval for a province wide literacy and numeracy drive to provide the necessary momentum for improved student learning outcomes.

The new political leadership in 2018 identified education as one of the priority sectors for reform, reflected in the “New Deal” for education in Punjab. Despite high commitment, this period since 2018 has seen less sustained progress, due to a process of “bedding in” of a different government, and the onset of the COVID-19 pandemic. There has also been much more churn in senior leadership, and of course significant disruption due to the COVID-19 pandemic, but stakeholders indicate that there is still committed leadership in the line ministries. An indicator was added to the logframe in 2017 to track PESP II’s contribution during this time to the Roadmap process.

Output indicator 5.1: When it was introduced this indicator tracked the effectiveness of the Roadmap Stocktake meetings. Until the transition in government in 2018, Stocktake meetings were held regularly, however, delivery routines (expectedly) went off track during the period of political transition, and the PESP II team tried to work with the government to find ways of institutionalising the delivery approach. DFID/FCDO sought to sustain the reform process by supporting (through the TA team) the development of the incoming government’s New Deal for Education. Initially, it seemed that the momentum behind the roadmap and stocktake process dwindled. DFID/FCDO technical staff and senior management met regularly with the Education Minister, Secretary, and other senior officials to discuss progress in the education sector, and continually improve the TA offering under PESP II. Regular meetings with PMIU to review data collection and usage have been ongoing as planned. This target is therefore marked as achieved.

Output indicator 5.2: The purpose of the Roadmap was to maintain engagement from the most senior political official holder and senior civil servants to drive education reform in Punjab. Progress was tracked by collecting data against 13 indicators. Quarterly stock take meetings chaired by the Chief Minister to report progress against goals were used to flag key decisions required to keep the Roadmap on track. This indicator was introduced to track the quality and use of Roadmap products but changed to map sustainability after the change in government and as the programme came to an end. Trainings were carried out to build capacity during the transition as planned. TA focused on the capacity building of PMIU in data analysis to support evidence-based decision making. As part of transition planning, TA also developed three important strategy documents on quality, enrolment, and future delivery approach – all of which contributed to the development of the ‘New Deal’ for Education in Punjab. This target has been achieved.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

Overall: This output relates to a central issue for the overall success of PESP II: supporting strong political leadership commitment to education reform is vital for sustained improvements to education. However, measuring the value for money of such an output is very difficult. The main cost driver under this output is Technical Assistance. The VfM of TA is explored under output 6 below.

The value of the Roadmap is largely manifested in the efficiency gains in delivery that the monitoring routines and stock takes have helped to drive. The Roadmap process and stock takes continued to drive reform and improve performance across the education sector through prioritizing key areas, increasing GoPb budget allocations, and delivering greater efficiency. Teacher and student attendance targets were set at 90%; with teacher attendance at 95% in 2019, (85% in 2011) and student attendance at 93% in 2019. Cost-efficiency gains are achieved as teachers are more often in class and there are more students present for them to teach.

Lessons learned through this output, and recommendations for future programming

1. Lessons for supporting political leadership – to share with colleagues in BHC Islamabad to benefit programmes across sectors:
  1. Regular stocktakes and data use: The Roadmap and Stocktake process was an effective driver of education sector performance, at least in the specific context of Punjab and the Chief Minister’s management style and strong commitment to education prior to the 2018 elections. Elements of this approach are likely to be widely applicable. This includes the strong focus on clearly defined and measurable targets, and programmes of action to support their attainment. Future programmes should also advocate for regular stock takes at Ministerial level or higher to ensure regular performance monitoring by the political leadership.
  2. Lesson on SBS: The 2018 evaluation of PESP II found that SBS did not provide direct incentives to the organisations responsible for achieving targets as the funding went to the finance department and not the departments responsible for achieving the disbursement linked indicators. To address this issue, in the last couple of years of the programme, non-sector budget support targeted financial aid was provided instead against specific deliverables such as the training of newly recruited AEOs by QAED, scale up of the second shift schooling and transport initiative etc. This approach (also used for support provided to PEF and PEEF) was more effective in delivering results that were directly attributable to PESP II. For future programmes in Punjab non-sector budget support targeted financial aid should be considered as the preferred modality of financial assistance. Also, SBS needs to be strongly focused on PFM improvement and effectively aligned with the budget (both in its timing and the process for setting priorities) to have the best prospects of achieving impact.
    [note] Performance Evaluation of DFID’s Punjab Education Sector Programme (PESP2): First Interim Evaluation Report

Output Number and Title		Output 6: High quality technical assistance to government stakeholders that builds sustainable systems and processes.
Output Score		A
Impact weighting (%)		20%	Impact weighting revised since last AR?	Yes

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
6.1: High quality TA to GoPb	Score of 4: Delivery criteria efficiently and effectively met in line with contractual and customer requirements / The targets were set in 2017 for the first time after TA was on board. As TA evolved, the targets were aligned with TA work plans.		(By 2018) Score of 4: Delivery criteria efficiently and effectively met in line with contractual and customer requirements / (By 2022) Teaching and Learning support provided to SED through revised academic calendar, lesson plans and worksheets for Grade 1-8 / Support provided to SED for improving the teaching and learning processes through content development, capacity building, and implementation of multigrade intervention and CPD framework for Elementary School Teachers (ESTs).	Target met: / Delivery criteria for TA efficiently and effectively met in line with contractual and customer requirements / Academic calendar, lesson plans and worksheets for Grades 1-8 developed and handed over to SED / SED and QAED provided support for content development, training, and implementation of multigrade intervention and CPD framework for ESTs in Punjab.
6.2: Capacity building and transfer of knowledge, skills, and practices to SED and PMIU.	Time bound transition plan including complete milestones documentation and a completion report handed over to DFID / Introduced in May 2017 / this target looked into the sustainability of TA support and focused on the activities facilitating it. Whereas the final years of the programme the target was aligned with TA work plan including COVID related activities.		(By 2020) All knowledge products, progress reports and proposed way forward handed over to DFID and SED. / (By 2022) Support provided to SED for developing skills of district officials, facilitating budget execution reporting, and Taleem Ghar initiative.	Target met: / All products including CPD strategy, School Improvement Framework and PEF review documents are handed over to both DFID and SED. / Capacity building and mentoring of SED officials at provincial and district levels undertaken to develop their skills on budget execution report, Taleem Ghar initiative, and planning and leadership skills.
[note] TA was assessed using the Key Supplier Management (KSM) performance review scorecard, which assesses suppliers from one to six across six performance indicators: KSM scoring methodology: (1) Serious delivery failure and underperformance. Immediate and major changes needed, (2) Some delivery criteria being met, however significant performance concerns and improvements needed, (3) Most delivery criteria is being met efficiently and effectively. Few areas for improvement, (4) Delivery criteria being efficiently and effectively met in line with contractual and customer requirements, (5) Proactive and innovative, delivering with superior efficiency and effectiveness above contractual expectations, (6) As score 5 and is driving industry best practice and is consistently applying this across DFID contracts.

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

TA was included in the programme to underpin each of the other components and has been highly effective in producing agreed short-term outputs. The TA component has been praised by the Government for its support and flexibility throughout. However, its record in contributing to sustainable organisational transformation, and addressing key governance issues for the sector have been mixed. Due to some concerns about the efficacy of the support, the TA component was added to the logframe in 2017 to enable the programme team to track and measure its specific value add. This output met expectations in almost all Annual Reviews (apart from 2017, when the implementtation against a concrete plan began and TAMO started making progress against the work plan agreed with the SED).

Technical Assistance has been provided to GoPb throughout the life of the programme. However, the output indicator to measure the TA performance through the logframe was added in 2017.TA was initially provided through two international providers (The Technical Assistance and Management Organisation, “TAMO”, made up of Adam Smith International and McKinsey) from June 2014, their contract ended, and Cambridge Education took over the role in September 2018, and when their contract ended ISAPs took on the TA role from September 2020.

Through interviews conducted for this PCR, it is clear that the DFID/FCDO team provided the support and flexibility that enabled the TA team to work with the government successfully. However, there was a lack of formalised involvement of GoPb in some key decisions (such as the selection of TA providers and the termination or modification of programme components) which decreased local ownership.

Output Indicator 6.1: TA support was designed to support the delivery of the other outcomes in the programme, and as such many of the reforms and policies referenced in other sections of this review owe their creation and implementation to this output. GoPb feedback has been positive. TA to the SED to mitigate the impacts of the Covid-19 on school education in Punjab has been significant. Over the life of the programme TA has successfully strengthened district monitoring routines, increased government capacity at district and sub-district levels to improve management and oversight, and monitored budget execution. Successes include support to the following reforms:
- A structured system-wide performance management system providing a systematic approach to reviewing performance at all levels of the education system – province, district, and school.
- Strengthening the school monitoring regime in Punjab by introducing new metrics such as the Literacy and Numeracy Drive (LND) and availability and use of data in real time through the use of technology.
- Timely and efficient utilization of non-salary budgets by schools.
- Prioritization of curriculum student learning objectives (SLOs), development of Grade 1-5 textbooks for Urdu, English, Maths, textbooks and their corresponding teacher guides, and Textbooks and Supplementary Learning Material Policy and regulations on textbook development.
- Merit based recruitment and continuous professional development of teachers.
- Improved integrity of PEC examinations (Grades 5 & 8) and improved test design and content quality, and Introduction of an organisational development plan and Assessment Policy Framework.
- Supporting PEF in the design and implementation of an ambitious expansion plan to enrol 2.8 million children by 2019 through public private partnerships, including identifying and enrolling out-of-school children with mild disabilities in PEF schools through an inclusive voucher scheme.
- Automating the PEEF e-scholarship approach to improve transparency and reduce mismanagement. For PEEF, accounting software and training, and automation of the accounts and financing department.
- SpED’s Special Education Policy and Needs Assessment.
- COVID-19 Accelerated Response for Education (CARE) including a revised academic calendar, scripted lesson plans for teachers and worksheets for students of Grade I - VIII for core subjects.
- Digitisation and EdTech strategy.
- Design and scale up of School Improvement Framework (SIF).
- Inclusive education strategy, special education policy, and including disability indicators in the PMIU dataset. Parliamentary caucus on inclusive education being set up in Punjab Assembly – a first in Pakistan.

Output Indicator 6.2: This indicator was introduced to track TA support for capacity building and institutional strengthening. Support provided to key government counterparts over the life of the programme has varied. TA to QAED and PEC in the first two years of the programme was limited but was subsequently stepped up. PCTB, on the other hand, received extensive support in the operational delivery of textbooks, teacher guides and prioritisation of curriculum in the early years of the programme but was reduced considerably in later years and then picked up again in the last year of the programme. These shifts were due to changes in context and the demand and ownership of key reforms by senior leadership in these organizations. In turn the impact and sustainability of key programme interventions has been affected by the changing external context, political economy, churn in senior leadership positions in these organizations and at the departmental level, along with multiple other factors.

To support long-term sustainable capacity building and responding to a key recommendation from the independent evaluation, TA worked with relevant institutional counterparts to outline medium to long-term institutional strategies and plans for all key institutional counterparts (QAED, PEC, PCTB, PEF, and SpED), conduct a needs assessment to prioritise areas for TA, develop actions plans and track their implementation. Throughout the programme, trainings have been provided to education delivery managers including Chief Executive Officers (CEOs), District Education Officers (DEOs), Deputy District Education Officers (DDEOs) and Assistant Education Officer (AEOs) to improve planning and service delivery at the district level.

PESP II has provided technical assistance to the GoPb across a range of reform priorities. However, some reforms require ongoing support to ensure sustainability including: student assessment; teacher certification and licencing; school improvement; district planning and capacity building; data integration and utilization; rationalizing and restructuring financial subsidies, and a Public Private Partnerships (PPP) strategy.

TA appears to have been most effective when it offered flexible and responsive support to the priorities of the GoPb and where there is reform oriented leadership with some degree of stability within government. At the beginning of their programme there was relative stability in the government education departments, enabling both a continuity of relationships and of government priorities. Following elections in 2018, turnover increased substantially, causing delayed approvals and a threat to sustainability of key reforms. A key lesson is to have local ownership of TA – either through using a local provider, or through partnering with local providers. Potentially embedding TA staff in the government departments would be a helpful step to bridge between policies and implementation realities.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

Overall, TA support underpinned the achievements in other areas of the programme, and led to scale up and embedded reforms of successful interventions. For example, the programme originally supported PCTB with results based financial aid, and then moved onto providing TA to embed new processes. Although VfM was reviewed and deemed good every year, overall VfM increased for this component throughout the life of the programme as the FCDO team learned what worked in TA – moving towards a locally resourced, responsive team. For TA to be effective and ensure VfM, a good understanding of the political economy within GoPb is vital. For better VfM, high level political dialogue is needed with the government to reduce staff churn and increase the possibility of sustainability. Future programmes should also engage mid-level technical experts who are less likely to be moved around, and to sustain knowledge within the institution.

Economy: The primary cost of TA was staff fees and travel – normal and expected cost drivers for work of this nature. At the beginning of the programme TA was provided by an international consultancy with senior staff and relatively high staff costs, including significant overhead costs. The TA provided through national consultants during the final two years of the programme was relatively cheaper but equally efficient.

Efficiency: At certain points in the programme, PESP II was the only programme providing TA to certain arms of GoPb (e.g. to SED in 2017), supporting capacity and improving the outcomes of money spent both within and out with the programme. The flexibility of support also increased the efficiency of this output. In some years the TA provider exceeded milestones and delivered additional requests to GoPb, further enhancing the efficiency of this component. The TA teams worked with other programmes in the education sector (e.g. the World Bank), and other programmes within the province (e.g. health programme), thus increasing collaboration and avoiding duplication.

Effectiveness: This depends on the success of the TA in supporting sustained changes in capacity and the delivery of well-managed reforms. At the beginning of the programme partners struggled to bring the government along with them, leading to lower levels of sustained reform. Later TA work recognized this and increased focus on work that was more intensely driven by demand and aligned with GoPb priorities, with a lean core team bringing in more expertise when needed, thus increasing VfM. Also, TA supported with some financial aid, with TA and FA aligned towards similar objectives, making TA more effective.

Equity: TA under PESP II aimed to support the overall goals of the programme, which included improving education for the most marginalized children in Punjab. Support has enabled an increased focus in the government on marginalized children such as orphans, and children with disabilities.

Lessons learned through this output, and recommendations for future programming

1. Lessons for future programme design and management are set below:
  1. Institutional strengthening and capacity building: Experience from the programme shows that TA adds value when the support provided is strategic and proactive rather than operational and reactive. TA should focus more on institutional strengthening support (structures, functions, systems, and processes) to ensure that TA is building government capacity. TA should also maximize opportunities for strengthening and making existing government systems and institutions work better, and wherever possible, avoid creating new structures that may be difficult to sustain beyond the life of the programme. Government counterparts see the real value of TA in introducing evidence-based solutions, including available regional or international good practice. Institutional partnerships for highly specialised TA could be an effective model to ensure appropriate and sustained technical support. In future programmes, TA should be measured against implementation of reforms, as well as policy approval to ensure that plans and reforms take root, and don’t just end up as an unimplemented policy. As highlighted above, financial aid aligned with the objectives of TA can help incentivise uptake of reforms supported through TA.
- Accounting for staff turnover: Frequent changes in the senior leadership positions within government, particularly in the last few years of the programme have made it challenging to sustain and institutionalize reforms. This is a political economy issue which is wider that just the education sector and needs cross-sectoral pressure from the FCDO and other development partners at the highest level. Throughout the programme, there has been a recognition of the need to build relationships at all levels of institutions to ensure capacity goes deeper than senior management and protect capacity building efforts from staff turnover. FCDO and the TA teams should build relationships with lower tier critical staff in the line departments to minimise the impact of such changes.
- Opportunities for embedded TA: Embedded TA working within the government departments leads to more ownership and acceptance of TA by the Government and is therefore strongly recommended from a VFM (effectiveness) perspective.
- Documenting and sharing lessons: some of the successes of PESP II could offer very useful lessons for other education programmes. The BHC education adviser should create case studies of their work and present it to the education cadre. For example, on the success of multigrade teaching initiative, including how the team worked with the government to present the case and help them to see the value of the initiative. Lessons from the TA should also be used in the design of TA for future programmes.
- Use of work of central research teams: it would be beneficial for future programmes to take advantage of the work of central research teams to bring in specific expertise and TA. For example, the EdTech Hub Helpdesk, the What Works Hub, and the proposed UK Centre of Expertise in Education. Some of the tools developed by the TA teams (e.g. a Learning Management System (LMS) and apps) may have benefited from existing expertise on these programmes to reduce overlap and improve efficiency.

## D: Risk

Overview of programme risk during the past year and over the life of the programme, drawing on BHC’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.

PESP II’s overall risk rating was ‘moderate’ through the life of the programme, other than the last two years when the rating was revised upwards to ‘major’ due to the delays under the construction component. The programme had a comprehensive risk register that covered risks at both programme and downstream partner level. Risk was assessed both quarterly and during annual reviews. The main risks to the programme were retrofitting and handover of classrooms in Punjab, delays in the procurement affecting the completion of targets under the Financial Aid component, responsible implementation by mitigating safeguarding risks, programme delivery and fiduciary risks.

The construction component was rated as ‘Severe’ during the life of the programme. However, the annual review in 2020 observed that the programme has demonstrated improvements in both performance and risk controls and revised the rating downwards to ‘Major’. The design review process supported retrofitting and handover of classrooms constructed under IMC Worldwide. However, this only partially offset the reputational damage to UKAID from support to construction of classrooms deemed unsafe. The team had a risk mitigation approach in place with an independent risk register reviewed monthly, weekly update meetings chaired at Director level and Ministers updated monthly through information notes. All payments were approved at Ministerial level after progress assessments. Additional FCDO resources and support on contracting, risk management and financial management remained in place. An overview of the key risks and their mitigation is outlined below.

The political risk associated with frequent changes in the leadership of the SED and its associated departments were rated as ‘Major’ during the life of the programme. The SRO and the PESP II team along with the technical assistance team established effective professional relations with the Minister Education office and with the staff in the SED to streamline delivery. The PESP II steering committee mechanism further allowed all stakeholders to meet on quarterly basis to review progress and take decisions on key issues. These steps helped the team in maintaining the momentum of the programme.

The delivery risk associated with the achievement of results agreed under the Results and Activities Framework (RAF) remained ‘major’ and well within the BHC Islamabad’s appetite - which is severe for delivery due to the challenges of complex and vast geography of the province and limited availability of local suppliers. There were potential risks of delay in procurement affecting the completion of targets under the government school construction component. These risks were partially mitigated through active engagement including fortnightly progress reviews with PMIU and monthly catchups between the SRO and the Project Director PMIU. More generally on results achieved through PESP II, the RoadMap process/Stocktakes provided a senior level entry point to discuss /take action at senior level on delivery risks, up to 2018. BHC Islamabad also escalated the risks to the Secretary School Education Department when required to expedite the process and to avoid procurement delays.

The safeguarding risk was ‘major’ as programme staff and/or beneficiaries remained potentially at risk of sexual abuse, exploitation, and harassment. In addition, PESP activities could unintentionally contribute to the spread of COVID-19 (through continuing enrolment or conducting surveys/field work, etc). To mitigate the risk, the PESP II team sought assurance from all implementation partners that they had systems in place to protect staff and beneficiaries from sexual abuse, exploitation, and harassment. The GoPb School Education established the Hotline (a dedicated phone number) for parents, teachers, and students to provide feedback on public school issues, including any unfair treatment and behaviour of teachers. There is a complete log of complaints both resolved and pending available at district offices. The PESP II team also conducted or updated the detailed due diligences for all Accountable Grants. Safeguarding issues were highlighted regularly at the education partners day and routine meetings with other stakeholders to raise awareness. The team also continuously advocated for use of PPE and to follow SOPs to control spread of COVID-19.

The risks related to the Covid-19 were ‘major’ including lockdown and other associated risks in the final two years of the programme affecting activities on the ground and significantly delaying the project completion timelines. The PESP II team closely monitored the situation with partners on the ground, this included monitoring progress status on a fortnightly / monthly basis and updating overall project delivery risks. The team also escalated the risks to higher management where necessary. These mitigation measures enabled the programme to complete all activities within the programme cycle beside huge challenges posed by the pandemic.

Update on Partnership Principles

The Partnership Principles Assessment (PPA) sets out FCDO’s assessment of commitments made by the Government to the four partnership principles (poverty reduction and achieving the Sustainable Development Goals, public financial management and accountability, domestic accountability, and human rights as demonstrated through its policies and action). We will continue to promote FCDO objectives, partnership principles and international obligations with all our Government Partners and use the PPA to inform our Bilateral Aid Talks with the Government of Pakistan.

Our overall judgement is that the Federal Government of Pakistan is demonstrating a reasonably credible commitment to two of the four partnership principles namely: poverty reduction and financial management. However, there are causes for concern in certain areas of human rights where the trajectory of progress has been downward. Domestic accountability to citizens in the areas of civic space and media freedom has also been constrained with no sign of improvements since the last year. Progress towards attainment of the SDGs and poverty reduction is proceeding at a slow pace with the rapid population growth creating more pressure. Progress on the protection of human rights is mixed. On public financial management and anti-corruption, the direction of travel is broadly neutral, although some evidence indicates improvements. There has been mixed progress towards strengthening domestic accountability with a reduction in civic space and media freedom. Substantial reform is needed in all partnership principles areas (especially on the implementation of commitments where these are in place).

Although the Partnership Principles do not need to play a role in management and monitoring of the programme, the future sustainability of PESP initiatives depends on government’s buy-in and collaboration.

Annual Statement of Progress

PESP II has provided sector budget support and targeted non sector budget financial aid to Government of Punjab (GoPb) to improve access to education and improve quality in government schools incentivizing changes that positively affect the entire education system. This was complemented by the Punjab Roadmap for Education which tracked progress against range of education outcomes and supported policy reforms and decision-making to improve delivery. Furthermore, technical assistance provided through PESP II provided critical support to the government in achieving results agreed under the financial aid component.

Despite being a small share of the overall GoPb education budget (less than 2%), UK’s sector budget support was used successfully as a lever to push for reforms in the sector and to ensure more and better spend on education. The contribution of SBS is substantial, as demonstrated through the priority given to achievement of Results and Activities Framework (RAF) targets. The RAF has defined more stretching targets over the course of the programme shifting focus from process indicators (e.g., procurement and recruitment) to more stretching outcome-oriented targets such as ensuring teachers are trained on effective use of textbooks and demonstrating improvements in student and teacher attendance and priority institutional reforms. Some key successes include securing additional commitments to the education budget (particularly the non-salary budget) in support of the 2018 Roadmap goals; increasing the GoPb’s own commitments to PEF; merit based recruitment of teachers; improved integrity of PEC examinations and improved test design and content quality; a more rigorous and transparent process for development of textbooks & supplementary learning materials; and merit based recruitment and continuous professional development of teachers. There has been marked progress on the data collection front within SED with improvements in processes as well as scope and utilization of data for decision making. PMIU has recently started collecting data on disabilities which will provide necessary information for planning and policy making. In another sign of progress, the SED is moving from a centralised delivery approach to a more district/school level, decentralised approach. This could help in empowering of the DEOs, better budget execution and implementation of development activities. SED has also taken a few timely initiatives to mitigate and address the impact of Covid including the introduction of a digital learning platform called Taleem Ghar to address learning losses resulting from extending periods of school closures due to COVID.

Punjab’s latest fiduciary risk assessment suggests that the risks around expenditure controls and independent scrutiny of Government expenditure remain substantial while risk around procurement remains high. However, BHC Islamabad ensured that the robust financial management system including scrutiny of the expenditure and continuous progress monitoring to avoid procurement delays remained in place to mitigate the fiduciary and procurement related risks. There is a strong need to operationalise the Financial Management Cell (FMC) within SED to improve the budget planning and execution. The FMC was established with support from FCDO in 2017 but could not be sustained without FCDO support. The government has funds allocated in previous budgets to recruit the staff for FMC, however the recruitment could not go-ahead due lack of interest by SED’s leadership. BHC Islamabad through its TA should continue lobbying for the operationalisation of the FMC in SED with the Minister and SED leadership.

Current level of fiduciary risk and direction of travel since last ASP	Major / Stable
Specific assessment of corruption risk and direction of travel since last ASP	Major / Stable

The following documents were reviewed to produce the annual statement of progress above:
- PESP II final evaluation report and management response
- Progress reports produced by technical assistance partners
- Punjab Fiduciary risk assessment report
- Aide Memoires prepared to document the progress made against RAF and SBS

## E: Progamme Management: Commercial and Financial Performance, Monitoring and Evaluation

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency.

PESP II was delivered through diverse partners and modalities, each with its own management, commercial and financial requirements. Delivery partners can be placed in four broad categories: GoPb departments, multilateral organisations (World Bank), commercial organisations and not-for-profit organisations.

Government departments: Performance management of partnerships with government departments was carried out through the Results and Activities Framework (RAF). Targets were agreed annually, and progress was tracked regularly through progress reviews and quarterly through steering committee meetings co-chaired by FCDO and SED. The RAF covered targets agreed for SED and SpEd Department for commitments against the financial aid disbursements. The TA support provided through ASI, Cambridge Education and ISAPS at different times during the programme assisted departments in system improvements in monitoring and budget execution and was instrumental in engaging extensively with all government departments to build strong working relationships. Partners like PEEF and PEF had individual monitoring systems in place (reporting, progress meetings with DFID/FCDO) whereas other departments were covered under SED/ quarterly steering committee updates. PESP II contribution through Sector Budget Support was less than 1% of the overall GoPb education budget for education; however, the political access, influence and coordination gained through financial aid as well as the improvements shown in the education sector on key performance indicators demonstrated the VFM gains on the component.

DFID/FCDO had a separate arrangement with PMIU for the construction component in 2019 due to the unspent budget in the other construction components. This was managed more closely through direct engagement with PMIU for progress updates, results tracking, financial monitoring and quality control as it used a dedicated Results Framework with clear implementation modalities. The funds were treated as earmarked financial aid rather than sector budget support and thus required more scrutiny compared to the other financial aid components and to address risks in government construction departments as flagged in FRAs. PMIU managed overall delivery including handling bureaucratic challenges from within the GoPb on approvals and scope. Coordination with DFID/FCDO remained strong, with routine progress meetings and monthly steering committee meetings chaired by Minister SED and meetings with Secretary SED. Reporting and information sharing remained diligent and findings from the third-party construction inspections were addressed efficiently.  PMIU’s ownership of the process and the presence of a dedicated team kept the activities rolling even during COVID-19. 10% of the overall funding was allocated to operational and management costs and provided good VfM gains on economy and efficiency for management costs.

Funds disbursed to GoPb under sector budget support and financial aid components were released to the State Bank of Pakistan against the formal request received through the Finance Department, Government of Punjab. The funds were then transferred to the relevant account of the Government of Punjab and a notification was issued to the British High Commission confirming the deposits. This disbursement chain was verifiable across Government of Pakistan accounts.

The World Bank, as a multilateral organisation, was involved in providing additional TA to SED using DFID/FCDO funds. Monitoring and oversight for the component followed existing multilateral operating guidelines, with regular check-ins between project teams for progress updates and proceeded smoothly for the duration.

Commercial suppliers included the TA/Roadmap partners (Cambridge Education, McKinsey, ASI), IMC Worldwide and Cardno for the construction components. Overall, most TA partnerships functioned smoothly and continued to evolve as per requirements and recommendations from the annual review rounds. The complexity, risks, costs, and demands associated with PESP II led to frequent changes in how partners operated. TAMO responded positively by incorporating changes such as team restructuring or changing engagement strategies with the GoPb. IMC Worldwide struggled with management challenges until closure, with structures evolving until late into implementation. The contract also ended up deviating significantly from initial proposal in implementation approaches, planned costs and targets. Financial management on the construction component remained weak with variances exceeding 5% allowance on a routine basis. TA and fund management costs made up 37% of the contract value for IMC Worldwide (not counting IMC Worldwide’s own costs on retrofitting); staff fees constituted the largest share for the TAMO and roadmap partners on account of being technical assistance contracts. While not economical (TA contracts tend to be more skewed towards fees and higher rates depending on level of expertise required), the TAMO and Roadmap contracts provided strong VfM in term of efficiency for DFID/FCDO in terms of political access and influence and supporting government departments in planning and implementing systemic improvements. Further gains were achieved during the final three years of the programme when consultant fees and expenses were drastically reduced due to the use of a local organisation for TA support following competitive procurement.

Cardno (on construction quality) and OPM as the monitoring and evaluation suppliers demonstrated good performance. Both contracts were heavily made up of TA inputs due to the monitoring services being provided. Cardno’s deliverables and mandate was expanded significantly to include all construction components across both provincial education programmes (PESP II and KESP). The arrangement provided strong VfM as Cardno engaged actively with implementing partners to address and close out findings on quality. For both suppliers, reporting remained on track and of good quality and teams were responsive to DFID/FCDO’s requests.

Not for profit organisations under PESP II included ISAPs, TCF and ITA. Non-profit organisations were contracted through accountable grants and followed stringent programme and financial management guidelines, which were implemented across the range of partners. Reporting systems were clearly set out and followed across the range of partners and financial disbursements were linked to deliverables, forecasts, and utilisation rates. ISAPs provided TA support during the final year of PESP II after the conclusion of the other TAMO contracts. Management and delivery of the component roughly remained at the same level and the engagement with the government did not suffer due to the shift from an international organisation to local - demonstrating good efficiency. This is a significant lesson also captured in the evaluation report, which acknowledged the implementation support (vs policy) provided by ISAPs.

The Citizens Foundation went through initial delays while school construction designs were reviewed by the GoPb, but successfully completed the project within a short period by June 2021 after mobilising in September 2020. It demonstrated strong VfM as only a small amount of the budget (3%) was linked to management costs and negotiated lower costs with contractors, allowing savings to be directed towards procurement of furniture. TCF had a dedicated team for the project and its coordinating channels with the GoPb remained well executed; additional classrooms constructed are part of the school sites managed by TCF for GoPb, which allows for additional assurances on sustainability.

ITA as a long-standing DFID/FCDO partner showed good performance on Siyani Sahelian programme. The grant was awarded in 2018. ITA minimized impact of COVID-19 by pivoting support to beneficiaries to cover online education, and vocational training continued in line with restriction policies. ITA’s reporting and management systems are strong and well established. Partnerships were developed with other organizations (British Council SOC Films, Circle Women, EdTech Worx, Girls Rising) to create additional training modules and improve sustainability through synergies.

Programme-level approach to monitoring and evaluation

All components of PESP II followed tailored methods for monitoring and assessments at output levels, summarised below.

Component	Implementing partner	M&E Method
Government Departments	Financial aid to SED, PCTB, PEEF, PMIU and PEF	Monthly/quarterly stocktake/steering committee meetings for financial aid components. / Results-based performance indicators for tracking delivery results and disbursements. / Monthly progress updates and meetings with Secretary SED, monthly steering committee meetings chaired by Minister SED for construction component (PMIU only) provided higher level of oversight with senior officials. / Partners leading on the Technical Assistance (TA) oversaw the GoPb departments monitoring processes. / Annual reviews for output and outcome progress.
Commercial Partners	IMC Worldwide, Cambridge Education, McKinsey, ASI, Cardno Emerging Markets	Weekly/monthly partner meetings, narrative and financial reporting (quarterly). / Annual/quarterly reviews on progress. / Third party construction inspections for IMC Worldwide through Cardno. / Infrastructure Advisor at Post reviewed and quality assured the reports.
Grant Agreements	ISAPS, TCF and ITA	Routine progress meetings, quarterly reports with partners. / Quality assurance and oversight of deliverables through field visits and third-party partners. / Field/monitoring visits. / Quarterly reporting against KPIs, thoroughly reviewed by programme teams. / Payment on basis of approval of deliverables by DFID/FCDO.

These dedicated monitoring approaches allowed the programme to course correct during implementation on individual components. Regular interactions with partners facilitated real time risk reassessments and revision of implementation approaches. Across all partners, this approach fostered strong working relationships and open communications processes. Every partner/project also had individual results frameworks which contributed to the programme level impact and outcome statements.

PESP II underwent a formal performance evaluation process, conducted between 2017 and 2021. The final report has been reviewed by DFID/FCDO’s Evaluation Quality Assurance and Learning Services –and rated as ‘Excellent’. The evaluation reviewed all elements of the programme and validated key successes and identified valuable lessons. The evaluation assessed the programme components against six areas: i) relevance (appropriateness of design), ii) effectiveness in achievement of planned results, iii) effectiveness of transformational impact, iv) efficiency and VFM against cost effectiveness, v) efficiency against quality of management, vi) sustainability of results.

According to the final evaluation report, the programme’s overall design approach was appropriate to achieve its objectives, and it proved flexible and responsive through the technical assistance support to meet emerging needs of the education department in Punjab.   Key lessons and gaps were identified, and while the programme team was not able to implement all recommendations given the evaluation timelines coincided with the end of programme, the findings informed the overall organisational approach. The management response covered detailed recommendations and lessons that will help inform FCDO and GoPb’s future education programme interventions.

A strong financial management system remained in place for the programme which enabled the PESP II to demonstrate a good value for money while being a large programme both in terms of budget and tenure. All payments to the government departments were linked to a specific set of disbursement linked indicators agreed through a results and activities framework (RAF). The RAF was reviewed on a quarterly basis to ensure progress remained on track and annual reviews were conducted to take decisions on disbursement which were made after the approvals from delegated authorities. The payments to PEF and PEEF were linked to specific enrolment and scholarship targets which were agreed on annual basis and progress was reviewed on a quarterly basis through quarterly progress reports and reviews.

A percentage of payments to commercial partners were linked to the successful achievement of KPIs. The targets were agreed on quarterly basis and reviewed through quarterly progress reports and follow up review meetings. The payments to the not-for-profit organisations were linked to the specific targets which were also reviewed on quarterly basis to decide on disbursements. All payments were approved by the PESP II SRO, and the invoices were scrutinized by the PESP II programme management team before payments.

	PEEF	PMIU/ SED	ITA	ISAPS
Date of last narrative/ financial report(s)	Jan 2022	March 2022	Jan 2022	Mar 2022
Date of last audited annual statement(s)	May 2022 (FY 2020/21)	Jun 2018	Oct 2020	May 2022 (FY 2020/21)
[note] Final audit report covering the financial aid is pending and will received by end of August 2022
[note] Financial audit will start in July after the end of Pakistan’s financial year and the report to be received by August 2022

## Annex - List of Acronyms

BC / BHC / CE / CEO / CM	Business Case / British High Commission / Cambridge Education / Chief Executive Officer / Chief Minister (Punjab)
C&W / CPD / DA	Communication and Works Department / Continuous Professional Development / Delivery Associates
DEA / DEO / DDEO	District Education Authority / District Education Officer / Deputy District Education Officer
DFC	District Field Coordinator
DRC	District Reforms Committee
EFO / EVS	Externally Financed Output / Education Voucher Scheme
FAS / FCDO / FMC	Foundation Assisted Schools / Foreign Commonwealth and Development Office (UK) / Financial Management Cell
GBP / GDP / GoPb / IMC / ITA / ISAPS / KPI	Pound Sterling / Gross Domestic Product / Government of Punjab / IMC Worldwide / Idara-e-Taleem-o-Aagahi / Institute of Social and Policy Sciences / Key Performance Indicators
LND	Literacy and Numeracy Drive
LUMS	Lahore University of Management Sciences
MEA	Monitoring and Evaluation Assistant
MIS	Management Information System
NOP	National Outreach Programme
NSB	Non-Salary Budget
NSP / OOSC	New School Programme / Out of School Children
OPM	Oxford Policy Management
PCD / PCR / PCTB	Procurement and Commercial Department / Project Closure Report / Punjab Curriculum and Textbook Board
P&DD / PEC / PEEF	Planning and Development Department / Punjab Examination Commission / Punjab Education Endowment Fund
PEF	Punjab Education Foundation
PESP II	Punjab Education Sector Programme II
PKR / PMIU / PPA / PMS / PRAP	Pakistani Rupee / Programme Monitoring and Implementation Unit / Partnership Principles Assessment / Performance Management System / Portfolio Risk Assurance Programme
Pre-DRC / PSLMS / PPP / QAED	Pre-District Review Committee / Pakistan Social and Lifestyle Measurement Survey / Public Private Partnership / Quaid-e-Azam Academy for Education Development
QSC / SDGs / SBS / SCRP / SECP	Quarterly Steering Committee / Sustainable Development Goals / Sector Budget Support / School Construction and Rehabilitation Programme / Security and Exchange Commission Pakistan
SED / SEND / SIF / SIS / STRIDE / STR	School Education Department / Special Education Needs and Disabilities / School Improvement Framework / School Improvement System / Sustainable Transition and Retention in Delivering Education / Student Teacher Ratio
SLO	Student Learning Outcome
SOPs	Standard Operating Procedures
SRO	Senior Responsible Owner
SpED	Special Education Department
TA / TCF / TPV / VFM	Technical Assistance / The Citizens Foundation / Third Party Validation / Value for Money