## Annual Review

Title: Building Resilience in Ethiopia
Programme Value £ (full life): £352 million		Review date: March 2022
Programme Code: 300363	AMP start date: / 30 May 2017	AMP end date: / 31 March 2024

Summary of Programme Performance
Year	2017/18	2018/19	2019/20	2020/21	2021/22	2022/23
Overall Output Score	A	A	A	A	A
Risk Rating	Major	Moderate	Moderate	Major	Severe

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-GOV-1-300363/documents
DevTracker Link to results framework:	https://devtracker.dfid.gov.uk/projects/GB-GOV-1-300363/documents

Acronyms
ANC	Antenatal Care
AR	Annual Review
BRE	Building Resilience in Ethiopia
BC	Business Case
BE	British Embassy
BoFEC	Bureau of Finance and Economic Cooperation
CBT	Cash Based Transfer
CMAM	Community Based Management of Acute Malnutrition Treatment
CINuS	Comprehensive and Integrated Nutrition Services
CP	Cooperative Partner
DPPC	Disaster Preparedness and Prevention Commissions
DRF	Disaster Risk Financing
DRM	Disaster Risk Management
EDRMC	Ethiopia Disaster Risk Management Commission
EHF	Ethiopian Humanitarian Fund
EPHI	Ethiopian Public Health Institute
EPRP	Emergency Preparedness and Response Plan
EUM	End User Monitoring
GBV	Gender-Based Violence
GESI	Gender Equality and Social Inclusion
GMP	Growth Monitoring Promotion
GoE	Government of Ethiopia
GFD	General Food Distribution
HFA	Humanitarian Food Assistance
HRP	Humanitarian Response Plan
ICRC	International Committee Red Cross
ICFRP	Integrated Cash and Food Response Plan
MDAs	Ministries, Departments and Agencies
MoFEC	Ministry of Finance and Economic Cooperation
MoH	Ministry of Health
MUAC	Mid-Upper Arm Circumference
EDRMC	National Disaster Risk Management Commission
NFI	Non-Food Items
NNGOs	National Non-Governmental Organisations
OPM	Oxford Policy Management
PCR	Programme Completion Report
PEFA	Public Expenditure and Financial Accountability
PHEM	Public Health Emergency Management
PLW	Pregnant Lactating Women
PSNP	Productive Safety Net Programme
RCSI	Reduced Coping Strategy Index
RHB	Regional Health Bureau
RRT	Rapid Response Team
SAM	Severe Acute Malnutrition
SBCC	Social and Behaviour Change Communication
SoE	State of Emergency
SRSN	Shock Responsive Safety Net
SSN	Scalable Safety Net
SWAN	Consortium of Save the Children, World Vison, Action Against Hunger and Norwegian Refugee Council
TA	Technical Assistance
TPM	Third Party Monitoring
TO	Tasking Order
ToC	Theory of Change
UNICEF	United Nations Children Fund
VRAM-EPRP	Vulnerability Risk Assessment Mapping – Emergency Preparedness Response Planning
VfM	Value for money
UNOCHA	United Nations Office for Coordination of Humanitarian Assistance
WFP	World Food Programme
WHO	World Health Organisation

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme
The Building Resilience in Ethiopia (BRE) programme was designed to strengthen Government of Ethiopia (GoE) systems so that they can deliver a more effective, self-financed and accountable response to humanitarian and climate shocks. An initial aim was also to respond to acute humanitarian needs through a non-governmental response when needed.

At design stage, BRE comprised four broad components:
1. Delivery of technical assistance to the Government of Ethiopia to build capacity and systems to lead and deliver an effective, more self-financed and accountable response to climate and humanitarian shocks.
2. Delivery of food and cash to people in humanitarian need in the most effective way.
3. Responding to non-food emergency humanitarian needs in the most effective way.
4. Monitoring, evaluation and learning to strengthen humanitarian delivery in Ethiopia, contributing to global best practice.

The programme has been amended three times in 2018, 2020, and 2021 and is now structured around ten outputs. This review covers the fifth year, between 1 April 2021 – 31 March 2022. A cost extension in January 2022 extended the Business Case until March 2024.

Summary supporting narrative for the overall score in this review
Overall, the programme scores an A, Outputs met expectation, despite a continued major shift in the operational context over the last 18 months. Ethiopia has experienced an extraordinary combination of humanitarian challenges during the review period, including large-scale conflict, significant drought, continued impacts of Covid-19, a locust infestation, flooding, and an increasingly restrictive humanitarian operating environment. The wider humanitarian response, inclusive of BRE partners, struggled to quickly adapt to these changes. These events required a significant (and ongoing) shift in humanitarian strategy, and full use of the emergency flexibility built into the BRE business case. One strategy to flex to the changes was to bring on four additional partners mid-way through the review period, who took time to get up to speed. These factors have led to a number of targets not being met.

Major lessons and recommendations for the year ahead
The concept for the BRE programme was developed during a time when drought was considered the most significant risk to the humanitarian situation in Ethiopia. The context has undergone several major changes since then, including spikes in conflict-related displacement starting in late-2017, a change in government in 2019, a locust infestation starting in 2019, Covid-19, and now a major conflict in northern Ethiopia that started in late-2020. In part because of these factors, in early-2022 inflation reached 40%, significantly impacting the purchasing power of poor households.

The wider humanitarian system was slow to adapt to these changes. Challenges included inadequate human resourcing (both quantity of people and mismatched skill sets) and heavy reliance on a government-led system that was unable to adapt quickly. These challenges continue and, in Tigray, the response is additionally severely constrained by a de facto blockade, which has all but cut off fuel and money flows, severely impacting humanitarian agencies’ ability to operate and individuals’ earning ability.

The humanitarian system has also been challenged by shrinking humanitarian space. A government decision to expel seven senior UN staff in October 2021, alongside significant bureaucratic impediments for all non-governmental partners, has resulted in a subdued advocacy effort and a humanitarian response that is unable to operate at full capacity, including on both programme implementation and ability to monitor. The access challenges raise the risk profile for BRE. GoE actions around the conflict have shaken the confidence of donors to continue with strategies to increasingly work towards a humanitarian system wholly operated by government.

The confluence of these factors meant that the envisioned impacts and outcomes of the BRE, which aspired towards a decreasing humanitarian appeal and increasing government ownership of the humanitarian response, have not been achieved. At the outset, 75% of the UK humanitarian spend was either being paid directly to government or channelled through UN agencies to government. That percentage decreased during the reporting period to less than 20%, due in large part to the need for a strong and conflict-sensitive non-governmental mechanism to respond to the worsening crisis in the north. This shift, primarily towards funding for UN agencies, saw the addition of IOM, UNDSS, WHO, and UNHCR as partners during the review period.

It is positive that the programme has been able to flex in this way. The team managing the programme has been under significant pressure during the review period, with staff turnover and incremental increases in the available budget compounding the challenges created by contextual changes. Good decisions were made to shift the focus of the BRE to better respond to the contextual changes, however, the major shift to both BRE and the wider humanitarian response means that continued improvements are needed. The combined GoE and non-governmental response is not operating as needed and going forward a significant policy and programme effort by the UK and likeminded partners will be needed to address the gaps and avert further deterioration.

Recommendations for the year ahead:
1. Continuing major changes in the operating context necessitate a further revision of the FCDO’s humanitarian and resilience strategy for the coming period. The long-term drought risks remain but new challenges around protection, balancing government and non-government humanitarian response, a deteriorating food security situation and famine risk in Tigray, and collapse of basic services and infrastructure as the result of the ongoing conflict need to be additionally taken into consideration. The creation of a (concise) humanitarian strategy document that sets out how strategy will adapt/has adapted to the changing context would make the rationale clear for the wider embassy as well as making clear to other teams how they can contribute to delivering the strategy. The significant changes in the context since the start of BRE in 2017 also underscore the importance of building flexibility into future business cases.
2. To mitigate the creation of additional humanitarian and protection needs, enhance cross-embassy efforts to work alongside likeminded donors to reduce conflict, bring conduct of hostilities in line with international law, improve access and humanitarian space, and ensure partners are adequately mainstreaming protection. To support this, it would be beneficial to retain protection capacity in the humanitarian team to develop and deliver a strategy for addressing these challenges.
3. The logframe and Theory of Change need to be further updated to reflect the significant changes to the business case. To be in line with PrOF, this should take place at least six months in advance of the next Annual Review and changes should be captured in a “change frame” which is part of the new PrOF logframe template. Prior to completion of the new humanitarian business case, consider Value for Money (VfM) assessment of key partners to provide good lessons learned and to inform the upcoming approach.
4. Review the number and type of partners to improve monitoring oversight and reduce risk and team workload. Specific partner suggestions:
  1. OPM: Expand humanitarian advisory involvement in the Technical Assistance (TA) component and deepen links with international humanitarian partners to ensure that it is delivering on humanitarian objectives. An upcoming mid-term review of the TA is a good opportunity to do expand engagement. See specific recommendations under output 1.
  2. GoE: Continue supporting activities delivered through the government while ensuring a non-governmental response with the ability to scale exists alongside government. It will be important to continue to capitalise on years of investment and maintain and/or continue to build government systems. In tandem, clear benchmarks should be set on quality, accountability, and principled humanitarian action and the team should consider working with other donors to agree on these benchmarks. Further recommendations under output 3.
  3. WFP & UNICEF: Continue work with UNICEF and WFP as large and long-standing UN partners and focus on quality and ensuring that they have adapted well to the contextual changes. Detailed recommendations under outputs 2 and 5.
  4. Ethiopia Humanitarian Fund (EHF): UK funding for the EHF should be proportional to the amount of time that the team is able to invest. The mechanism relies on donor engagement at the advisory and technical board level to ensure quality programming. If the UK continues to maintain a high contribution to the EHF, more staff time should be devoted to EHF governance.
  5. It is early to judge the quality of the WHO, UNHCR, IOM and UNDSS programming and the UK’s contribution through them to the overall response, however, it will be prudent to only continue funding for the partners who are both performing well and filling a critical gap. The upcoming two quarterly reports should give a better indication of programme quality.
  6. ICRC is an important partner in major protection crises but have undergone a rapid expansion over the last 18 months in Ethiopia and have struggled, perhaps as a result, to engage well with FCDO. Work with the delegation and their HQ to improve engagement.
  7. Direct funding to NGOs, which tends to provide better VfM than working through UN partners who then sub-contract to NGOs, should additionally be considered. Alongside consolidating partners under point e above, funding could be rebalanced from other large partners to fund an NGO consortium. A cash-focused rapid response consortium, concentrating on conflict-affected areas, to complement slower responses from other partners is an area to explore.
5. Given expanded programme scale, a well-designed Third-Party Monitoring (TPM) mechanism managed by FCDO would help manage risk and improve monitoring access in areas that advisers cannot visit. To minimise burden on partners, ensure light touch monitoring and reporting and explore joint TPM with other donors.
6. A learning output to better understand progress on working with the GoE on humanitarian was initially envisioned in the business case but was removed from the logframe in 2020. Given the contextual changes, it would be beneficial – both to British Embassy Ethiopia and wider humanitarian learning – to commission an external review of BRE’s approach to building resilience in Ethiopia.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
##

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The programme’s intended outcome is that the Government of Ethiopia (GoE) can lead and deliver an effective, more self-financed and accountable response to climate and humanitarian shocks, that will result in an Ethiopia more resilient to climate and humanitarian shocks. Ethiopia is a highly populous country with rising food insecurity affecting an estimated 16.8 million people in 2021 and is prone to multiple hazards which unchecked can cause severe humanitarian crises, slows national economic growth and development objectives, and contributes to unsafe migration and instability.

However, since the design of the programme, the context has changed substantially. The programme was largely designed to mitigate drought hazards through food security and nutrition systems. Widespread conflict and displacement have instead become the major driver of multi-sectoral humanitarian needs beyond immediate food assistance. The programme’s intended outcomes remain more relevant than ever, and strongly aligned to the UK’s humanitarian reform agenda, though the assumptions underlying the outcome indicators and timeframe no longer hold.

The programme has been amended twice with the overall budget increased from £168m to £352m, and the four outputs of the original Theory of Change have become nine, reflecting a significant upscaling of non-governmental response partners. The key outcome assumption has been challenged by:
1. Significant political reform resulting in the formation of a new government in 2018
2. An increase in conflict-induced humanitarian crises across the country and the displacement of over two million people from November 2020 to February 2022, in addition to the onset of a major drought;
3. Inflation, which rose from 5-10% during the drafting of the business case to 40% at the start of 2022.
Government leadership of humanitarian systems remains a desirable goal. The ability to sustain delivery throughout this period of deep political change, to remain impartial and effective at meeting needs when those changes trigger humanitarian crises and the Government becomes party to a conflict, and to navigate significant fiscal reductions and operational restrictions due to the C-19 pandemic within the timeframe of this programme has been unfeasible and gains have been eroded. The results framework needs significant revision. An external review of BRE is recommended in the coming year to contribute to both BE and wider approaches to resilience and working with government on humanitarian.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme is off-track to contribute to expected outcomes and impact due to substantial changes in the operating context. Given the high rate of expenditure on the business case already (approx. 95%), this will not change before closure of the business case. Instead, lessons learned from the BRE will inform the development of new outcomes and impact for upcoming business cases.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

The programme should continue responding to the escalating humanitarian challenges in Ethiopia – both conflict in the north and drought in the south – until the end of the current cost extension in March 2024. Approximately 95% of the programme funds have been spent or committed under current grants, with only a small contingency pot and funding for the remainder of Technical Assistance (TA) component remaining. Both of these will help to bridge funding until a new business case, which is currently under development, is approved.

## C. DETAILED OUTPUT SCORING

Output Title	Technical assistance to the Government of Ethiopia to lead and deliver an effective and accountable humanitarian response.
Output number:	1	Output Score:	A
Impact weighting (%):	5%	Weighting revised since last AR?	Yes down from 10%

Indicator(s)	Milestone(s) for this review	Progress
1.1 Technical assistance to Government of Ethiopia to plan, prepare, prevent, deliver, and budget for humanitarian response delivered and well received.	Six new Tasking Orders (TOs) developed to meet BRE TA strategic objectives	Met expectations. / During 2021 there were six TOs submitted to FCDO and four approved, and six TO amendments approved.
1.2 Significant contributions to strategic plans, systems and procedures in disaster risk management, disaster risk finance, public health emergency management and shock responsive safety nets	Contributions made to three quarters of the following outputs: / Disaster Response Management (DRM): DRM Synthesis Report of four DRM studies, which will support DRM reform processes and changes to institutional architecture, thereby contributing to the intermediate outcomes ‘DRM policy updated (and legal framework approved)’. / Public Health Emergency Management (PHEM): COVID-19 Regional-Intra Action Reviews for six regions used by regional governments for updating their COVID-19 response plans, thereby contributing to the intermediate outcome ‘Stronger region and woreda level PHEM preparedness and response structures and processes based on evidence-based plans.’ / Shock Responsive Safety Net (SRSN): Contribution to the development of the shock responsive component of Productive Safety Net Programme (PSNP) 5’s Project Implementation Manual (PIM) and organisation of a consultation and familiarisation workshop to discuss the SRSN implementation, thereby contributing to the intermediate outcome ‘Effective coordination mechanisms are in place across sectors and relevant Ministries’. / Disaster Risk Financing (DRF): Knowledge Exchange with the objective to get agreement to develop a Disaster Risk Finance Strategy thereby contributing to the intermediate outcome ‘Fiscal risk statement and DRF Strategy developed and used internally’	Met expectations. / DRM: Supported in preparing a new DRM policy and successfully advocated for DRM to be moved to the Office of the Prime Minister. Support on updating the DRM policy progressed well. Supported preparation of a Disaster Risk Informed Planning training manual. / PHEM: BRE-TA supported four regions (SNNPR, Afar, Amhara and Sidama) to prepare regional ten-year PHEM strategic plans and associated operational plans. The same four Regional Health Bureaus were supported to prepare COVID-19 Regional - Intra Action Reviews and revise their regional COVID-19 Preparedness and Response Plans (MoH and EPHI recommended late in 2021 that these first 4 regions were to be followed by Addis Ababa City Administration as the 5th and Oromia as the 6th region. Both started in 2021 but will go through a formal validation process in 2022). At the federal level, support was provided to EPHI in developing PHEM policy guidelines, training manuals and field guidelines. / SRSN: The SRSN component was completed in 2021. A key part of the SRSN operations manual, which OPM helped develop, is the targeting criteria that MoA is now using to compile lists of beneficiaries, which helps to harmonise SRSN delivery systems. In addition, OPM assessments of the SRSN Systems and Structures, Commodity Management system, and Nutrition and Social Protection Assessment, and an ‘Action Plan’ for reform, were finalised at validation meetings led by government and with donors. / DRF - Secured agreement from MoF to design and develop a DRF strategy and started the diagnostic exercise in 2021. This has been a long-term objective and progressed incrementally through building understanding of DRF through fiscal risk modelling and training, and applied policy research. Disaster risks are now more frequently captured in key MoF documents. An increase in budgetary allocation for EDRMC started this Financial Year.

Briefly describe the output’s activities and provide supporting narrative for the score
This output scores an A, met expectations. The Technical Assistance (TA) component of BRE works directly with the GoE to instil and strengthen shock responsiveness into GoE policies, plans, systems and processes. TA is central to the BRE Theory of Change and intended outcomes and delivered well at an output level this year despite the significant changes to the operating context.

All four of the TA workstreams, detailed below, are delivering support to their respective counterparts in the GoE, according to agreed TOs. Following are progress highlights under each of the four project pillars:
[note] Tasking Orders define discrete work objectives under the TA.

- The Disaster Risk Management workstream focuses on strengthening DRM through reforms to the national DRM policy and mainstreaming DRM and there was progress on this during the review period. OPM contributed to a wider advocacy effort to both elevate the Ethiopia Disaster Risk Management Commission (EDRMC) to the Office of the Prime Minister and to prioritise within government the reform of the DRM policy and legal framework. Progress was also made on creating a separation of duties between policy setting, which rests under the EDRMC, and implementation, which increasingly sits under the various relevant line ministries.
- Good progress was made under the Public Health Emergency Management (PHEM) component, which focuses on supporting health systems at the national and sub-national levels to prepare for and respond to humanitarian emergencies. The TA ensured that MoH and the EPHI were central to the planning and roll-out of Vulnerability Risk Assessment Mapping - Emergency Preparedness Response Planning (VRAM-EPRP) exercises, which the TA helped to design, strengthening political and technical buy-in from the government. On C-19, OPM also worked with the government on health information communication around the pandemic and preparation of response plans in six regions.

The Shock Responsive Safety Nets (SRSN) component focuses on improving shock responsive social protection by strengthening SRSN coordination, delivery systems and procedures. During the reporting period, the creation and dissemination of an SRSN operations manual went some way towards achieving a key goal in this workstream, although there are additional significant hurdles to be cleared before operationalisation. The TA has secured important relationships with key counterparts by consistently delivering on the GoE’s SRSN priorities, despite a complicated donor relationship with government. Good collaboration occurred with the DRF workstream in identifying the financial resources required annually by GoE for funding the SRSN component of PSNP.

- The Disaster Risk Finance (DRF) component focuses on improving government budgeting and financial planning so that public finances are better prepared and more resilient to climate and humanitarian shocks. During the period of review the partner reports strong behind-the-scenes support to the MoF that has improved their institutional understanding of quantifying disaster risks. Support included:
  - Production of ‘Opportunity cost of COVID-19 Expenditure Re-allocations’ analysis, which improved understanding on how inefficient re-allocative approaches are for funding shocks.
  - A DRF knowledge exchange workshop that led to an agreement by the MoF for developing a DRF strategy
  - Support from the TA that led to the MoF agreeing to allow the first climate focused Public Expenditure and Financial Accountability (PEFA) in Africa.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

  Overall, BRE-TA is showing good VfM:
- Efficiency: Payment-related deliverables were of a high quality and submitted as planned. Key informants in government and other TA providers attested to the quality and usefulness of the deliverables. Efficiency has been ensured through adaptive programming, responding to emerging opportunities and reallocating resources accordingly between the core budget and Tasking Orders. The programme can demonstrate ways in which being adaptive has enhanced its results, for example by adjusting its approach to the VRAM to include EPRP in response to a change of priorities and schedules within government.
- Effectiveness: The workstreams are broadly on track in making progress against their expected intermediate outcomes at this stage. The no cost extension to March 2024 will allow further progress and consolidation. Key informants provided many examples of the ways in which TA outputs and recommendations have informed government decision-making on the DRM reform process. Nevertheless, consistently across the programme progressing activities hand-in-hand with government, and in-step with other donors, is a lot slower than anticipated. Particularly in some areas, mainly with respect to the Early Warning System and consolidation of the HFA and PSNP, and the transition from PSNP4 to PSNP5. This was due to a lack of consensus in government, beyond TA’s control.
Economy: TA has managed key economy drivers and costs well (staff costs, consultancy fees and key reimbursables). Average unit costs of key inputs are generally below agreed benchmarks. All average unit costs of key inputs have been decreasing year-on-year since the first VfM assessment in 2019, helped by the depreciating value of the Ethiopian Birr against the GBP. This has happened without any loss in quality. Key informants attested to the quality of the consultants and key deliverables. Overall mean cost of fees: £310.24 (Sept 2019-March 2020); £281.85 (Jan-Dec 2020); and £248.23 (Jan–Dec 2021). Mean cost of flights: £645.18 (Sept 2019-March 2020); £621.41 (Jan-Dec 2020); £590 (Jan–Dec 2021). Mean cost of Hotels: £100 (Sept 2019-March 2020); £74.06 (Jan-Dec 2020); £56.82 (Jan–Dec 2021).
Equity: A review of a sample of such key deliverables by the TA Gender Equality and Social Inclusion (GESI) Advisor indicated that GESI considerations are informing workstream design and implementation. Some informants were able to identify ways in which BRE-TA has had some influence on GESI awareness among government counterparts. Nevertheless, workstream staff and informants felt that more can be done to integrate GESI. The recruitment of a full-time Ethiopian GESI Advisor in 2021 will strengthen BRE-TA’s capacity to mainstream GESI and conflict sensitivity good practice into the TA provided to the government. For instance on targeting mechanisms of the PSNP and the Grievance Redressal Mechanism (GRM).

Describe any changes to this output during the past year, and any planned changes as a result of this review.

In line with the adaptive nature of the programme, changes have been made at an activity level to respond to requests for technical support from GoE. These are in response to opportunities or threats to achieving the BRE-TA outcome statements. There have been substantial challenges for the GoE and to the BRE-TA team due to the conflict in the north and COVID-19, as well as drought in southern Ethiopia. The BRE-TA team was required to work from home for much of 2021 and at times struggled to meet regularly with GoE counterparts.

Moving forward, humanitarian advisory involvement in the mid-term review of the TA would be helpful to ensure that, given the contextual changes, humanitarian considerations are being well considered.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations AR 2021	Progress
The TA output will need to consider how the changing context in Ethiopia affects the longer term strategy of how to achieve capacity building and system strengthening and build on work to respond to climate crises to include efforts to strengthen response capacity to political crises, housing, land and property restitution, durable solutions for IDPs, and conflict reconciliation.	The TA made significant efforts to deepen sub-national support in 2021, particularly as it related to the IDP crisis, by helping roll-out federal policies to the regions. The DRM and SRSN workstream Regional Technical Assistants (RTAs) helped facilitate humanitarian and food cluster meetings, supported production of regional early warning bulletins, flood and food security assessments. The PHEM workstream helped identify emergency health needs and intervention measures and supported integration of emergency nutrition into existing government-led humanitarian response systems. In this way, TA strengthened response capacity to crises at federal and regional levels. / Use the upcoming mid-term review to determine effectiveness against this recommendation.
In light of above, the TA should also ensure that the remaining period is focussed on bringing together the different areas of TA to move towards the higher level outcomes for each of the four work streams as well as how these workstreams link together.	As GoE’s understanding and appreciation for the TA has increased, OPM report it has made collaboration across the workstreams much easier. These include nutrition, early warning, knowledge management, financing shocks including the SRSN, and health and nutrition emergencies. / Progress towards the intermediate outcomes has been promising during the reporting period. Achieving them is a pre-condition so that higher-level outcomes to happen.
The TA should also link to other ongoing TA programmes and ensure the timeliness and complementarity of new TA and make these linkages visible. For example, the close coordination of the Scalable Safety Net and the DRF workstream with the WB and other actors on the strengthening scalable safety nets, climate finance and fiscal risk assessments are positive and should be pursued.	Links with the World Bank and others supporting SRSN was strengthened in 2021, with weekly coordination calls, regular briefings to the Donor Coordination Team and sub-committee on SRSN, and other. / Due to the conflict and COVID-19 there were fewer donors to co-ordinate with. Some withdrew financial support from the PSNP, and some were expelled.

Recommendations for the year ahead:
- As humanitarian advisory capacity increases, dedicate resource to engaging more substantively in the TA. The upcoming mid-term review of the TA is a good opportunity to do this including:
  - Following review of the ToC and logframe, ensuring that the TA remains in-step with the current context and the change in strategic direction.
  - Taking stock of how the contextual changes will impact upon the likelihood of achieving the programmes outcomes in the remaining two years.
- Prepare a strategy for how research and advice produced by the programme is going to be taken up and continued after the end of the programme.

Output Title	Effective response to meet food needs through in-kind and cash support, Increased access to quality services for the treatment of moderate acute malnutrition among children and addressing transport capacity gap through (WFP)
Output number:		2	Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 – indicator closed in 2021
2.2 – indicator closed in 2021
2.3 – Number of children and pregnant and lactating women receiving nutritious food, disaggregated by beneficiary category, sex.	By March 2022: / 154,400 children aged 6-59 months / 94,900 pregnant and lactating women (PLW)	Met expectations / On track to meet targets by project end date (March 2022) / As of December 2021: / 122,700 under-fives (60,100 boys and 62,600 girls) (79% of target) / 96,000 PLW (101% of target)
2.4 Consumption Based Coping Strategy Index: The Reduced Coping Strategy Index (rCSI) decreased by 15 % from the baseline status by end of the intervention in Somali region (disaggregated by gender, age and disability)	10	Substantially did not meet expectations / 15.88 (June 2021).
2.5 Number of women, men, boys and girls receiving cash assistance for at least 6 months through existing PSNP delivery mechanism in Somali region, disaggregated by beneficiary category (age, gender and disability)	Rounds 1 to 3, cash distribution through GoE: 229,402 / Rounds 4 & 5, through Financial Service Providers: 291,020	Moderately not meeting expectations / Rounds 1 to 3: 226,252 / Rounds 4 & 5: 218,641
2.6 The proportion of households with poor food consumption score, decreased by 50% and 25% respectively from the baseline status by the end of the intervention in the Somali region (disaggregated by gender, age and disability)	9% HH with poor food consumption scores and 19% HH with borderline food consumption scores.	Substantially did not meet expectations / 27% HH with poor food consumption score and 24% of HH with borderline food consumption score (June 2021)
2.7 Addressing transport capacity gaps to support humanitarian operations through the purchase of trucks under WFP Fleet.	Purchase and preposition of 54 trucks in country across different hubs	Met expectations / Whilst only 44 trucks were purchased, they had a larger capacity than the 54 trucks originally planned (achieving 1760 MT of transport capacity, compared to planned 1620 MT)

Briefly describe the output’s activities and provide supporting narrative for the score.

This output covers three distinct sets of activities delivered through WFP: i) nutrition support in Northern Ethiopia (£9 million covered in this review); ii) cash assistance in the Somali region of Ethiopia (£8.3 million covered in this review); and iii) logistical support for the humanitarian response in Northern Ethiopia (£3 million covered in this review). It scores an A overall, due to meeting expectations for the nutrition and logistics components. However, results were below expectations for the cash support in the Somali region. The delivery of cash support suffered delays, due to the delay in the release of the 2021 HRP and the FCDO’s decision to move to delivery through financial service providers. Benefits for household resilience were lower than hoped for due to the effects of drought and economic challenges.

Nutrition
The first component of this output is nutrition support and has two objectives:
1. Providing support to moderately wasted children and PLW with specialised nutritious foods for nutritional rehabilitation
2. Increasing access to Social Behaviour Change Communication (SBCC) messaging on Maternal, Infant and Young Child Nutrition practices during emergencies to prevent under-nutrition in children under 5 and PLW
The first objective provided a Targeted Supplementary Feeding Programme (TFSP) to strengthen the nutrition status of vulnerable groups affected by the conflict, mainly in Tigray but also zones in neighbouring regions of Afar and Amhara. This critical intervention was also a reform priority for BRE as the treatment of severe and moderate malnutrition have long been managed separately in Ethiopia causing inefficiencies for delivery partners and disruption to the continuum of care for beneficiaries. Under the second objective, WFP planned to support SBCC related activities, specifically relating to capacity strengthening for health staff and health facilities to provide safe and secure Infant and Young Child Feeding in Emergencies (IYCF-e) services. This also included delivery of key nutrition, health and hygiene messages to beneficiaries and target communities to ensure the nutrition response was supported with complementary services for better outcomes. FCDO made a transfer of £4 million in December 2020 for the inception of the Therapeutic Supplementary Feeding Programming and additional £5 million was transferred in September 2021 to scale up with the SBCC component.

During the period under review, WFP provided nutritional rehabilitation to a total of 122,700 moderately malnourished children 6 to 59 months and 96,000 PLW (total 218,700 beneficiaries and 87% of the target). This is a result of concerted efforts to launch and scale up the nutrition response in northern Ethiopia, despite the security, access and operational challenges which affected the programme. WFP managed to scale up the response, first in Afar and Amhara in January 2021, with delayed start in Tigray by mid-March, due to access challenges. Eventually, all regions were accessed, and operations scaled up with support from NGO partners. Since December 2020, WFP has reached 101 woredas across the 3 regions. In the last quarter of 2021, however, the defacto blockade on Tigray had affected operations. During this period, only four woredas (down from 25 in the previous reporting cycle) were supported from FCDO contributions in Tigray compared with 29 and 20 woredas, for Afar and Amhara, respectively, comparable with the previous reporting cycle. Currently, the access situation has improved, and supplies are being delivered to IPs who signed field level agreement with WFP. Parallelly, distribution of supplies to targeted households has been resumed. To allow WFP to continue their implementation, the project agreement is now extended by extra three months.

The spread of conflict across Northern Ethiopia in autumn 2021 also delayed the implementation of the social and behaviour change component of the project. In the rollout of the SBCC component, there have been delays in the engagement of cooperative partner (CP) who were meant to support the setting up of breastfeeding corners. However, some progress has been made through acceleration of activities to deliver within the planned timelines. Slightly over 50 percent of the people targeted for the nutrition and health messages have been reached, while about 75 percent of the health staff targeted for the training on IYCF-e have been trained across the three regions.

Cash in Somali region
The second component of this output was intended to improve food security through the provision of cash to affected and vulnerable people (HFA recipients) in Somali region. The region had a caseload of 1.9 million people who were in need of humanitarian food assistance. The majority of General Food Distribution (GFD) was in-kind. Under their five-year (2020-2025) Country Strategic Plan, WFP committed to scaling up cash based transfer (CBT) to 37 woredas in the region. During the reporting period, WFP reached 25 woredas with cash. To address the food needs of affected and vulnerable households in the region and to strengthen the established system, WFP supported the GoE with the transfer of resources to provide cash disbursements to targeted HRP beneficiaries delivered through the Productive Safety Net Programme (Channel 1). The use of this mechanism enabled WFP to deliver humanitarian support through the national safety net mechanism, as part of a long-term shift towards increasing the shock responsiveness of the PSNP in the Somali Region.
[note] Phase 5 PSNP, intends to improve Shock Responsiveness of the Rural Safety by supporting the Government to expand the geographic coverage of PSNP in addition to drought-prone woredas, and enhancing PSNP capacity to function as an integrated shock responsive social safety net. This component also includes a Contingent Early Response Component (CERC) to facilitate an early response to emerging food security crises through horizonal and vertical expansion of cash or in-kind transfers to shock affected households.

This review covers a total of £8.3million that FCDO allocated for WFP in two phases. In December 2020 £5 million was disbursed to WFP with the intention to channel funds through MoF/Channel 1 of the PSNP based on the Integrated Food and Cash Response Plan (IFCRP). It aimed to provide three rounds of cash transfers for 229,402 people in 13 priority woredas. WFP was able to reach 226,252 beneficiaries in 11 priority woredas. The change in number woredas was based on the request from the region and Ethiopial Disaster Risk Management Commission (EDRMC) to use newly released HRP (2021) figures instead of the 2020 mid-year review figures. Delivery of cash transfers for round 1-3 was delayed due to significant delays in the release of the HRP 2021 and the integrated plan. In March-April 2021 a decision was made across all PSNP woredas to start the first-round of PSNP transfers while awaiting the GoE's endorsement for the HRP.
[note] This project was built on the FCDO supported digital pilot with WFP which ended in 2020. This pilot had many challenges and faced delays in delivery. However, WFP has taken the lessons learnt on board and made improvements to its financial management oversight following on recommendations from an internal WFP audit.

The second allocation, £3.3 million was disbursed in July 2021 and WFP had initially planned to reach some 291,020 people in 13 woredas using contracted Financial Service Providers (FSPs). Aligned to round 4 and 5 of the HRP, the timeframe for payments had been scheduled between mid-September and mid-November 2021, and the cash was intended to be disbursed to the same targeted beneficiaries, as in the previous allocation, through two consecutive disbursements. However, the implementation was significantly delayed due to operational challenges including the revision of transfer value, operational capacity of FSPs, and liquidity. The final revised planning figure was 218,641 in four woredas. However, the actual transfer has been further delayed due to the need for WFP to transfer the funds to the FSP Somali Micro Financial Institution (SMFI) by tranches as FSP didn’t have the required insurance bondage to fulfil WFP’s internal financial accountability requirements. Therefore, WFP confirmed to complete the cash transfers at the end of March 2022 with a double cash payment. The outcome-focused indicators (2.4 and 2.6) for the Somali cash support show disappointing results, with the most recent data showing households are currently showing increased levels of stress due to food shortages (compared to the baseline) and with an increased percentage of households with a poor food consumption score (compared to the baseline). During the project implementation, there were a number of major contextual factors that destabilized food supply and contributed to inflation in the region (including the Somali-Afar conflict, and damage to crops due to flooding). The value of the cash support provided was not able to keep pace with rising prices and protect household resilience in the way that had originally been envisaged.
[note] Due to political developments, delays in the delivery of cash assistance through government, and to support a pilot alternative delivery model that has worked well in other countries, in June 2021 FCDO requested WFP shift to working with FSPs instead of directly through the government. Given the operational challenges faced with the FSP pilot, WFP has made a decision to implement much of their (non UK funded) cash programmes through Channel one in 2022. WFP is aiming to reach 500,000 people through cash-based transfers in three Rounds in the first six months of 2022.  While significant proportion of the cash would be channelled through Channel 1, WFP is committed to maintain its partnership with local FSPs at small scale level and improve their capacity through provision of technical assistance. The capacity building support will include local government partners and WFP’s field staff as the understanding about cash-based programming and familiarization about digitalization is very limited in the Region.

Logistical support
In autumn 2021, FCDO decided to add a logistics component to the BRE support to WFP. The increase in humanitarian needs across Ethiopia was straining logistics capacity. And in Northern Ethiopia, there was an urgent need to create dedicated humanitarian trucking capacity due to the reluctance of commercial trucking companies to operate in the area (following a number of security incidents) and to ensure there were visibly independent humanitarian vehicles for the sensitive transit between conflicting regions.

FCDO originally agreed to fund WFP to procure 54 trucks with a capacity of 30 MT each (total transport capacity of 1,620 MT). However, during project implementation FCDO agreed with WFP to shift to procuring 44 trucks with and increased capacity of 40 MT each (total transport capacity 1,760 MT). So, whilst the number of trucks was lower than originally planned, the final capacity was 140 MT higher. The procurement of trucks was completed on time, and the vehicles are now supporting the delivery of humanitarian assistance in Northern Ethiopia.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

This procurement was an important intervention to improve access to Tigray and the capital investment will continue to support humanitarian operations over the coming years. In addition, given the higher total capacity delivered versus the initially proposed capacity, the VfM of this element is deemed as being strong.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Addition of the output indicator 2.7 on delivery of trucks.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations AR 2021	Progress
Logframe revision: Given the scale of the resource inputs and its link to output 3 and output 5, the results could possibly be better captured in the respective reform outputs related to scalable safety nets and nutrition strengthening, rather than setting out results on a partner basis.	Full logframe revision pending
There should be learnings from WFP support to scaling up the safety net to deliver cash responses in Somali region that should feed into Output 3, especially in light of a model of WFP-supported food assistance via PSNP in Tigray. Building on current and previous pilots, WFP’s Social Protection Learning Facility in partnership with the University of Wolverhampton and the Institute of Development Studies will be a valuable mechanism and should also review the exceptional agreements needed within WFP to deliver through Government systems, the risks and the delays of this modality.	At the inception phase, WFP did have a plan to deploy a full-time consultant from the learning facility to work on the scalable safety net. However, this didn’t happen due to Covid-19 travel restrictions and difficulties obtaining visas for new staff following the outbreak of conflict in Northern Ethiopia. / WFP is aiming to look into it again when the situation improves, and movement become possible.

Recommendations:

Diversify delivery modalities and invest in local capacity: Implementation through the FSPs has been significantly delayed, mainly due to limited FSP capacity and lack of familiarity with mobile money among local government staff. Partnership with FSPs has significant potential for wider scale up, which could improve VfM and reduce protection risks and delivery timelines. Consider additional financial support for WFP’s capacity building initiative for FSPs in order to promote FCDO’s commitment to localisation.

Ensure a joined-up strategy between direct funding to government and funding through UN agencies to government (see recommendations under output 3). After establishing benchmarks for government delivery, payments should be continued through channel one, which at present is quicker than delivery through FSPs and continues delivering on the long-term goal of government ownership.

Transfer Value: The PSNP Shock Responsive Mechanism (SRM) is triggered at time of crises to accommodate additional needs within the PSNP targeted areas. The cash transfer value for people with acute humanitarian food needs, assisted through the SRM, is equivalent to the rate for the (less acute) PSNP beneficiaries, and is significantly below the standard rate for the humanitarian food basket. The low transfer value results in community preference for in-kind food assistance, undermining GoE’s cash first principle and FCDO policy on cash. Different transfer values between SRM/HRP and PSNP should be applied due to the difference in their objectives. This could be achieved through top-ups but requires lobbying with the government and donor partners including the Bank.
[note] The PSNP wage rate is able to cover only 60 percent of the rations in relief in-kind transfers. Transfer Value Adjustment for HRP Relief Response in Somali Region: Comparing the market values of Relief in-kind food basket with PSNP wage rate. WFP. July 2021

Ensure that WFP’s internal protection capacity is strong enough to continue adapting to the changing context.

Output Title	Government of Ethiopia piloting scalable social safety net (GoE/EDRMC)
Output number:		3	Output Score:	B
Impact weighting (%):		10%	Weighting revised since last AR?	Yes: down from 25%

Indicator(s)	Milestone(s) for this review	Progress
3.1 Percentage of budget funded by the UK transferred from MOFEC to BOFEDs in Oromia, SNNPR, Tigray, Amhara and Sidama.	98%	Moderately did not meet expectation / 83%
3.2 Number of woredas piloting operational aspects of a scalable safety net (including one beneficiary list, one audit, use of same pay roll system, common reporting).	26 in Amhara / 23 in Oromia / 1 Harari / 14 Sidama / 44 SNNPR / Total = 108	28 in Amhara / 22 in Oromia / 1 in Harari / 14 in Sidama / Total= 65
3.3 Number of people in receipt of cash support via Government	Up to 1,170,000	Up to 1,170,570

Briefly describe the output’s activities and provide supporting narrative for the score
This output scores a B, Outputs moderately did not meet expectation. The UK has transferred £20m to the EDRMC in December 2020 to cover the food needs in Amhara, Oromia, Tigray and SNNPR through cash-based transfer.. The GoE and donors, including the UK as a chief supporter, have invested huge resource over the last 15 years to building up the government’s capacity to prevent and respond to crisis. In a major humanitarian setting, it is a world-leading government response yet there are significant eand increasing concerns to be addressed on humanitarian principles, response timelines, programme quality, conflict-sensitivity, and monitoring and accountability. The UK’s willingness to continue supporting these mechanisms should be contingent on seeing improvements across all of these areas.

During the reporting period, target numbers were reached and the government’s shock responsive capability was strengthened, but assistance was not delivered in a predictable nor timely manner, which ultimately has failed in reducing people’s vulnerability.

In partnership with the EDRMC, BRE’s support to the inclusion of cash payments to “transitory” relief beneficiaries in PSNP woredas and through PSNP finance systems continued under this output.
[note] The transitory relief beneficiaries are identified via biannual assessments under the HRP programme cycle and targeted through the Integrated Cash and Food Response Plan (ICFRP) as part of an integrated scalable social safety net, bringing together Humanitarian Food Assistance (HFA) and PSNP beneficiaries. Under this integrated system, the HFA beneficiaries are targeted by EDRMC with cash payments provided through MoF’s PSNP system and in-kind food managed through EDRMC, according to whether the target woredas are identified as cash or food receiving woredas.

This review includes three rounds of cash payments, two from PSNP 5 and a bridging round between PSNP 4 and 5, which was delayed, principally due to the Tigray conflict and slow approval of last year’s HRP. The bridging round targeted 1,054,435 people while Rounds 1 and 2 from PSNP 5 targeted 1,170,000 people. These targets are achieved and covered priority 1 and 2 woredas in Amhara, Harari, Oromia, SNNPR, and Sidama. However, the initial number of woredas that the EDRMC was intending to cover under PSNP 5 rounds 1 and 2 was reduced from 108 to 65 due to a decision made by the SNNPR government to shift the payment modality to in-kind for round 1 and 2 due to elevated cereal prices. This reduced the number of pilot woredas overall, but the pilot was rolled out as planned in the other four regions

Tigray was part of the initial plan, the delivery has not been materialized due to the development of the conflict in the region, which impacted the structure and the delivery of cash transfers.

There have been delays in the delivery of the final balance of UK funds (£1.6 million) to the regions requiring safety net scale-up. These funds had been planned to be disbursed to the regions alongside World Bank funding for round 5 in late 2021, however due to internal delays in the release of World Bank funding the EDRMC decided to shift to in-kind assistance for round 5. The remaining UK funding will now be used for round 1 humanitarian cash assistance in 2022 in Amhara, Oromia, Sidama, and Harari regions.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

The VfM assessment for this component shows a mixed picture. A combination of cash-response funding to the GoE and the TA have been helping to strengthen the government’s shock responsive systems, a long-term effectiveness positive for the country. On economy, channelling cash transfers through existing PSNP systems is also a cost-effective way of reaching a large number of beneficiaries with very low overhead and admin costs. On efficiency, however, there have been significant delays in delivering the cash transfers. Targeted communities received the first cash payment only towards end of March/April while the subsequent two rounds were completed in August 2021. This means it has not been effective in reducing people’s vulnerability as cash transfers to beneficiaries have been unpredictable and delayed. In addition, there have been logistical challenges including both liquidity and a cap of cash withdrawals at the banks.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

N/a

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations AR 2021	Progress
The programme team should review the use of the contingency budget in view of challenges faced to deliver timely and targeted assistance to humanitarian caseloads if there are multisectoral or displacement drivers to be addressed.	Recommendation remains relevant and has been refined for this AR
The programme team to review the prioritisation of contingency budget support to priority one woredas only in line with humanitarian principles.	The cash payments covered priority 1 and 2 woredas due aggravating factors for further deterioration of food insecurity for the latter.
OPM to take the TA support to Early Warning forward in close consultation with other stakeholders. The Early Warning system strengthening should encompass a broad range of shocks including climate, health, and insecurity.	During 2021 the federal TA based in EDRMC and regional TA’s under the DRM workstream provided practical support on early warning activities while preparing the ground for an early warning Tasking Order focused on building evidence and support for systemic reform - ‘Early Warning for Early Action’ (approved on 1 October 2021, TO#16). / Coordination efforts continued with the World Bank due to EDRMC’s role in producing an early warning dashboard to inform the DRAP for the SRSN component of PSNP5 (SRSN’s federal TA is involved in preparing the DRAP). / Progress was also made in securing Ministry of Health and EPHI support to increase the coverage of health sector malnutrition information in the Early Warning System to trigger a shock response through PSNP. A recommendation from the ‘Nutrition and Social Protection Assessment’ led by the SRSN workstream.

Recommendations

- Develop a plan jointly with government that details benchmarks and timelines to achieve them on programme quality, monitoring, reporting, timeliness, and principled humanitarian action. Consider adapting the TA to support with this. Communicate the benchmarks clearly to government partners and make funding contingent on them (while recognising that some of these challenges will take time to resolve, may require additional resource to address, and will help to restore wider donor confidence). In the meantime, minimise risk by limiting funding. Consider making these improvements a focus of work with government under a new business case. Update the logframe, or future iterations of it, to capture the above benchmarks. Specific suggestions on performance improvement include:
  - Budget: DRM staff at the federal, zonal and woreda levels have not had funding allocated to do adequate monitoring. The designated budget that could be used for this is instead used by woreda finance offices on other admin expenses, including allowances for woreda staff. At present there is no technical linkage between the finance office and the EDRMC. The Bank has recently seconded a PSNP and HFA linkages Technical Support Specialist who is seated with the EDRMC and FSCD teams.
  - Accountability: As the scalable safety net is functioning based on the PSNP implementation framework, ICFRP, there is no requirement for the EDRMC to submit a project-specific concept note and progress reports to FCDO. FCDO’s team does a regular catch up on the progress and paid two visits (Kalu woredas in Amhara and Boset woreda in Oromia) over the review period. There needs to be a mechanism in place to clarify the partnership and ensure that project compliance requirements are adhered to.
  - Transfer Value: The transfer value for HFA beneficiaries is equivalent to the rate for the PSNP beneficiaries, which is far below the standard rate for humanitarian beneficiaries for meeting their minimum food requirements. The low transfer value results in community preference for in-kind food assistance, undermining GoE’s cash first principle and FCDO policy on cash. The PSNP wage rate is able to cover only 60 percent of the rations in relief in-kind transfers. Different transfer values between HRP and PSNP should be applied due to difference in their objectives.
    [note] Transfer Value Adjustment for HRP Relief Response in Somali Region: Comparing the market values of Relief in-kind food basket with PSNP wage rate. WFP. July 2021

Output Title	Effective response to meet non-food needs (EHF)
Output number:		4	Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR?	Yes, down from 25%

Indicator(s)	Milestone(s) for this review	Progress
4.1 Number of beneficiaries in receipt of non-food support (disaggregated by gender and type of support)	15% of the 2022 HRP	Not assessed / HRP not approved and so not possible to assess.
4.2 Average duration of the allocation process from deadline of application submission to HC approval of selected projects by allocation type (standard and reserve)	Standard allocations: 34 working days and Reserve allocation 23 working days	Meets expectations / Standard allocation: 30 days / Average reserve allocation: 32 days
4.3 EHF funding supports strategic planning and response to needs identified in HRP and sudden onset emergencies through the most appropriate allocation modality	1 standard allocations and 2 reserve allocations by December 2021	Meets expectations / Two standard and two reserve allocations in the calendar year
4.4 and 4.5		Completed in 2019/20
4.6 EHF performance is measured as per the global CPF, which provides a set of management and outcome level indicators under key principles of CBPFs including inclusiveness, flexibility, efficiency and accountability and risk management.	1. Inclusiveness implementation: 25% implemented by UN; 68% by INGO and 7% by national NGOs (NNGOs). / 2. Flexibility: EHF successfully reprogrammed to address operational and contextual challenges. / 3. Efficiency: % of HFU direct costs to total value of allocation. / 4. Accountability and risk management: 90% of EHF funding appropriately monitored, reported and audited	Met expectation with some data pending / 1. Inclusiveness: 27% implemented by UN; 61% INGO; 12% NNGOs / 2. Flexibility: EHF provided significant number of extensions and revisions to changing situations throughout the country including North. / 3. Efficiency: During 2021, the total allocated amount for the EHF is $87.3 million, and an additional $11.2 million allocated in 2022 in top-ups for projects funded during 2021. / EHF management cost constituted 1.4% of the total funds ($98.5M) utilized. / 4. TBC
4.7 Percentage of funding provided for protection response through standalone and/ or integrated projects.	12% of the overall EHF funding supports protection response.	Moderately exceeds expectations / 15.3% ($15.1M out of the total $98.5M allocation-including top ups) of EHF funds allocated to protection

Briefly describe the output’s activities and provide supporting narrative for the score.
This output has scored an A, met expectations delivered through the Ethiopian Humanitarian Fund (EHF), a multi-donor pooled fund managed by United Nations Office for Coordination of Humanitarian Assistance (UNOCHA). In 2021, EHF secured $93.2 million of total new funding, 19.6% (UK’s contribution $18.3M out of the total contributions $93.2M) of that contributed by the UK through BRE, 61% being implemented by INGOs, 27% by UN agencies and 12% by NNGOs. This showed an increase in funding to national NGOs (against a baseline of 6% is only for standard allocations, while for reserve allocations, the baseline is 3% in 2020) but also an increase to UN agencies which displaced funding to the INGOs.

The EHF is primarily a reactive funding mechanism and has room to improve in making disbursements against risks instead of needs realised. Cluster coordination on partner selection and joined up approaches in geographic areas, are additional challenges to be resolved. An area-based allocation model might be a better way to achieve greater efficiencies.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

Overall, the EHF continues to provide reasonable VfM with some areas needing continued attention. Management costs through the EHF Humanitarian Financing Unit (HFU) are cost effective at 1.4% of the total managed fund.

AWhile this represents a significant improvement, it is still above the benchmark of 34 working days. For the reserve allocations, the benchmark has been met, but 23 days could be further improved upon. Given the allocations tend to focus on current needs and gaps rather than risk mitigation, this is too long to wait for funds and impacts the effectiveness of the funding. In addition, application processing timeline for the last three years is 32, 33 and 30 for standard allocation (2019, 2020 and 2021) and 18 and 32 for reserve allocation (2020 and 2021).

Describe any changes to this output during the past year, and any planned changes as a result of this review.

N/a

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations AR 2021	Progress
Complete the SWAN evaluation to inform how to strengthen the EHF’s response to rapid onset crises.	SWAN evaluation complete under OPM component in 2021.
EHF to consider longer funding timelines to allow continuity of a humanitarian response in protracted crisis response in key sectors such as nutrition.	Progress against recommendations from last year’s AR was limited. There are some good reasons for this including major contextual changes, requiring concentration by the EHF and FCDO team on other priorities, and concurrent FCDO humanitarian staff turnover and EHF staff turnover (due to the explusion of UN staff and subsequent visa restrictions), impacting ability to push on effectiveness and efficiency reforms. The EHF has indicated that it intends to follow through on some of these recommendations, for example through: / An expedited reserve allocation process for the March 2022 drought allocation (ongoing at time of drafting); / Recruitment of two new monitoring staff into the OCHA team. / FCDO continues to raise protection capacity and third party monitoring at the EHF advisory board. / There should be concentration in the coming year on following through on these and the below new recommendations through strengthened participation in the advisory and technical boards.
EHF to put in place more rapid and flexible fund reserve allocation timeliness criteria for reserve allocation, as 23 days to sign a project agreement is too long.
Strengthen links between Government response plans and EHF allocations through closer regional sub-cluster and OCHA office engagement.
Protection capacity within the EHF OCHA team needs further strengthening to take the integration of protection into the EHF forward.
EHF should also improve the conflict sensitivity of its programming given an increased conflict-induced humanitarian needs.
Improve monitoring of EHF: develop a pilot to and test an improved third-party monitoring approach for EHF monitoring to ensure vulnerability targeting addresses needs of most vulnerable, including protection concerns.

Recommendations:
- Given the size of the financial contribution, dedicate resource to use influencing roles in the EHF Advisory Board and the Technical Review Committee (or reduce the contribution). Advocacy focus to consider:
  - A model that allows for pre-agreed partners and finance based on risk and operational readiness. This would significantly improve the efficiency and predictability of the allocations.
  - Increased protection capacity.
  - Improved monitoring and ensuring targeting reaches the most vulnerable and addresses protection concerns.
  - EHF should also improve the conflict sensitivity and risk management approaches of its programming.
  - Shorter disbursement times and longer funding periods
  - Responsible and effective localisation.
- To complement enhanced advisory engagement, requesting OCHA to commission an EHF review in light of the major contextual changes would: (1) increase wider UN and donor buy-in on the challenges and solutions, (2) take pressure off the advisory team to identify and follow-up on the mechanism’s shortcomings.

Output Title	Nutrition services are provided in emergencies and in vulnerable districts (woredas), maintained above international standards (UNICEF)
Output number:		5	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	Yes, down from 25%

Indicator(s)	Milestone(s) for this review	Progress
5.1 Number of children under 5 suffering from Severe Acute Malnutrition (SAM) receiving appropriate treatment funded by UK	46,400 (+14,000 in Tigray conflict affected areas)	Meets expectations / 46,400 (+36,912 in Tigray)
5.2 Percentage of Health facilities visited by CMAM/IYCF monitors with acceptable OTP score (>80%) in UK funded facilities and number.	80%	Meets expectations / 76%
5.3 Number of CINUS woredas (districts) implementing the full Community Based Management of Acute Malnutrition treatment (CMAM) package	41	Meets expectations / 41
5.4 Emergency Preparedness and Response Plan (EPRP) for Nutrition developed at federal and regional levels	9	Meets expectations / 9
5.5 Number of beneficiaries receiving WASH supplies, hygiene kits and services	100,000	Exceeds expectations / 167,490 (for Tigray) (95,044 females and 72,446 males)
5.6 Number of children 6-59 months receiving Vitamin A	100,000	Meets expectations / 92,422 (for Tigray)

Briefly describe the output’s activities and provide supporting narrative for the score.
This output scores an A, meets expectations.

Despite the changes in context, UNICEF has managed to achieve almost all milestone objectives and overachieved on two. There were, however, some significant delays and disruption to programming being delivered in Tigray due to access challenges related to the conflict.

Indicator 5.1 shows the target for January has been met and performance indicators (cure rate, deaths and defaulted) have slightly improved throughout the year. The target for SAM treatment activities in Tigray was exceeded (by 260%), showing an unanticipated massive increase of needs throughout the reporting period. Unfortunately, there are no performance indicators specific to Tigray which does not allow an understanding of the effectiveness of the intervention.

Capacity building of health workers for nutrition activities (indicator 5.2) has been implemented through deployment of emergency nutrition officers in OTPs and SCs. This indicator is just below the target but the level of achievement shows some progress from the previous reporting period, due to improved mobility and health facility visits by both UNICEF and government experts. End user monitoring (EUM) has shown improvement in terms of adhesion to correct admission and discharge criteria since last reporting period. However, the EUM also highlighted challenges in terms of supply availability and satisfaction rates.

CMAM (Community Based Management of Acute Malnutrition) package has been implemented in 41 CINuS (Comprehensive and Integrated Nutrition Services) woredas (indicator 5.3), as per the target. This system strengthening approach targeting the most vulnerable woredas permitted reaching better rates for vitamin A supplementation, deworming and GMP (Growth Monitoring Promotion) in those specific woredas as compared to the national coverage. However, related proxy indicators such as percentage of PLWs receiving ANC (antenatal care) or percentage of children who participated in GMP in CINuS woredas fall far below target, indicating challenges in terms of access to qualitative services. Furthermore, coverage trends in CINuS woredas for vitamin A supplementation (proportion of PLWs receiving vit A) and GMP (proportion of U5) have decreased since 2020. Security unrest contributed to reducing demand for services and disrupted health facilities, resulting in heterogeneity across woredas.

Nine Emergency Preparedness and Response Plans have been designed, as per the target for indicator 5.4. UNICEF supports EDRMC in developing and executing EPRPs. Based on the information from the logframe, those plans seem to have been in place since at least 2019 and no information is provided on whether they have been updated during the reporting period given changes in context. Four nutrition officers and one public health specialist have been deployed in four regions to provide guidance on nutrition preparedness and response interventions to government counterparts. In addition, this programme contributes to embed nutrition specialists and information management officers into six regional DPPC (Disaster Prevention and Preparedness Commissions).

Indicator 5.5 has been overachieved by 167%, illustrating a major increase of needs relative to WASH supplies and services in Conflict affected Tigray. WASH Non-Food Items (NFIs) have been distributed to two IDP camps by end April 2021. There is no indication of coverage, satisfaction levels or quality evaluation of this intervention, as the post distribution monitoring of WASH supplies was delayed as the project areas became inaccessible at the end of June. In addition, over 6,500 people have benefited from water point rehabilitation in Tigray.

A measles vaccination campaign was rolled out in Tigray in January and February 22, likely to have contributed to the results linked to indicator 5.6. The January 22 milestone has been slightly underachieved. Tigray Regional Health Bureau (RHB) launched an integrated measles vaccination campaign including vitamin A supplementation and deworming campaign, which constituted a unique opportunity to increase vitamin A supplementation beneficiary numbers.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
Delivery through government systems remain a strong element of VfM although the conflict in the north has very strongly reduced government capacity to deliver in that area, impacting the overall VfM of the project. given the very fluid context and major access issues, operating through NGO partners in conflict affected areas is probably the best compromise between operational capacity and cost. In the second phase of the conflict in the north, UNICEF opted for working mainly through partners or through direct implementation as funds transfers to RHB were no longer an option in Tigray. In Afar and Amhara, UNICEF opted for a mixed approach, with scaling up partnerships with NGOs and partial support to the RHBs.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
N/a

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations AR 2021	Progress
The SBCC work demonstrates positive results across a range of areas, but some practices seem harder to change or the impact less clear – such as working through influential community leaders. UNICEF should continue to do research to understand the barriers and opportunities for SBCC.	Although there have been significant progresses in uptake of nutrition services and practices, there remains barriers to child diets and other nutrition practices. To this effect, UNICEF followed a consultative approach to identify barriers to child diets. / The consultative workshops were conducted at Federal and regional levels in the presence of government nutrition experts, nutrition partners, frontline workers, community representatives etc. This helped in delving into context specific barriers at policy, institution, and community level. Some of them include advertisement and promotion of unhealthy foods, religious barriers related to fasting, lack of context specific SBC strategies. Following the barrier analysis, context specific actions were developed, and UNICEF has started implementation with existing funds and putting the actions into proposals for resource mobilization.
UNICEF’s efforts to improve its monitoring system through the introduction of the end user monitoring tool (EUM) which facilitates monitoring of health workers’ knowledge and skills, quality of nutrition counselling and satisfaction of caregivers is positive. It would be important to capture the lessons learnt and demonstrate how this monitoring information has informed implementation and its results.	The EUM system has been instrumental in identifying gaps and taking corrective action for service improvement. One best experience that demonstrated the importance of EUM is the feedback from beneficiaries on the taste difference between the local and imported RUTF. This is because the texture of the locally produced RUTF was lumpy as the peanuts were not fully mashed and smooth. This finding had been presented to the production company and the RUTF was improved. At woreda and health facility levels, there was a supply breakage whereby health facilities encountered supply shortage while sufficient stock was available at the woreda warehouse. In response, supplies were stocked at health posts and additionally, on-the-job mentoring was provided to nutrition experts on how to forecast, request, receive, and report on nutrition supplies.
A clear analysis is needed what the barriers are and what strategies could be put in place to increase coverage among PLW. For GMP, identify ways to enhance implementation of Mid Upper Arm Circumference (MUAC) screening and ensure referral of acutely malnourished children for treatment.	UNICEF conducted a formative research where the barriers and bottlenecks to three preventive nutrition programmes (vitamin A supplementation to children 6-59 months, Iron Folic Acid supplementation to pregnant women and growth monitoring promotion for children under two years) were identified. some of the barriers include: / •Iron-folic acid supplementation: poor awareness or information about anaemia, social norms around revealing pregnancies early, low number of anti-natal care (ANC) visits, dissatisfaction with ANC services, poor adherence due to fear of side effects, role of other family members. / •Vitamin A supplementation: the transition to routine service delivery and the underlying challenges within health extension programme (HEP), lack of commitment by health staff, missed opportunities to provide vitamin A for children coming to health facilities for other health services, such as immunization / Growth monitoring and promotion: lack of counselling skills, limited accountability, weak monitoring and lack of attention and support by management, outdated equipment to carry out measurements etc. / Based on the findings, strategies have been developed such as replacing outdated equipment with digital scales for growth monitoring and promotion, introducing multiple micronutrient supplementation for pregnant women, developing context specific and integrated nutrition job aids for service providers. UNICEF will pilot the strategies and test for scale up. / For severe acute malnutrition: UNICEF has been conducting research on simplified approach for admission and treatment of wasting which include admission through MUAC, using one treatment product for severe and moderate acute malnutrition etc.
UNICEF needs to continue working with Regional Health Bureaus to push for a multisectoral response with a convergence of integrated services to ensure better results, increase the coverage and quality of nutrition specific services through CINuS, strengthen medical supply chains, and improve the quality and frequency of nutrition and health data.	UNICEF is providing a system strengthening support to the government for integration of services at grassroots level. This include establishing an integrated supply chain system for health and nutrition commodities, pushing for delivery of nutrition services during immunization and vice versa and other programs, training health care providers on CINuS so they have a well-rounded knowledge and skill on life cycle nutrition programming. At upstream level, UNICEF is advocating for multisectoral coordination. This ranges from improving the nutrition literacy of sectors through training, developing a reporting platform called Unified Nutrition Information System for Ethiopia (UNISE) for sectors to report on nutrition sensitive indicators, organizing a multisectoral coordination meetings on a regular basis, supporting development of guidelines and tools. Most importantly, UNICEF initiated a flagship programme called “end stunting” designed through a multisectoral approach involving all relevant sectors in advocacy, implementation, monitoring, and evaluation of nutrition sensitive programmes. The crisis has led to UNICEF having to diversify implementation away from the Regional Health Bureaus.
UNICEF will need to place greater emphasis on how to support and quickly scale up nutrition services in a protracted crisis setting. This is likely to require a shift away from working through government health services, promoting an integrated multisectoral response, capacity building and working closely with WHO on a timely roll out and monitoring of IYCF guidance in emergencies settings.	UNICEF used multiple approaches to ensure continuity of services during emergencies. These comprise program cooperation agreement with NGOs, establishing mobile health and nutrition teams (MHNTs), introducing the find and treat campaign for screening and treatment of children and women suffering from acute malnutrition, provision of micronutrient supplements and other lifesaving services. Thanks to FCDO funding, UNICEF has been able to provide multisectoral response to emergency affected population in the northern crisis. These include health, nutrition, WASH, and child protection interventions.

Recommendations:

1. Strengthen the collaboration between WHO, WFP, and UNICEF on nutrition and CMAM programming
2. Commission an expert review to improve the nutrition information system – including a focus on early warning and the quality of the analysis

Output Title	Improved protection environment for conflict-affected communities by designing tools to analyse and monitor protection concerns, and ensuring safe access to appropriate services for the most vulnerable groups (UNHCR)
Output number:		6	Output Score:	B
Impact weighting (%):		5%	Weighting revised since last AR?	New output

Indicator(s)	Milestone(s) for this review	Progress
6.1 Conflict-affected communities have access to protection services, and are able to meet their basic needs with dignity	7,000 people (milestone January 2022)	Moderately did not meet expectation / 5,215 people met (interim report 31 January). 75% of milestone, but with mitigating circumstances due to insecurity and access restrictions in some regions.

Briefly describe the output’s activities and provide supporting narrative for the score.

The output scores a tentative B, off-track to meet expectations at the point at which the Annual Review was conducted. At time of interim reporting, UNHCR had been able to initiate interventions in three of the planned five regions – Oromia (West Guji), SNNPR (Gedeo), and Afar. However, results reported in this Annual Review include people reached in West Guji and Gedeo only. For Tigray, Afar, and Amhara, interventions had not taken place as of end-January 2022 due to persistent insecurity.

The wider goal of the intervention was to ‘support an improved protection environment for conflict-affected communities by designing tools to analyse and monitor protection concerns and then to ensure safe access for most vulnerable groups to appropriate services’ was ambitious for the implementation period (five months). Protection monitoring requires a process to be established, including common tools for data collection and staff training, as well as access for actors to undertake systematic data collection over time that builds trust with key informants in communities The changing context of northern Ethiopia up to the date of this Review has restricted windows of opportunity for that type of monitoring to be rolled out as envisaged.

Although the initial focus was northern Ethiopia, challenges in access to Tigray and changing front lines meant that FCDO offered geographic flexibility to include Oromia in UNHCR-targeted areas. It was also recognised that partnerships with local universities to run ‘legal aid clinics’ for affected people would take time to initiate, but that the timeframe of the UK intervention would allow for at least two universities to be engaged and for interventions to start. In complementarity with these more mid-term initiatives, a shorter-term component of procurement and distribution of Core Relief Items (CRI) was built into the intervention to support UNHCR connections with communities and ensure people in need were able to access some direct support within the limited timeframe the FCDO could offer for funding.

At time of preparation of this Annual Review UNHCR, in discussion with the FCDO, has only been able to roll out the planned UK-supported protection monitoring in south and north-west Oromia, the Southern Nation Nationalities and People’s Region (SNNPR), and Afar. UNHCR started implementation of the planned protection monitoring tools in the Benishangul Gumuz region – which was not initially covered by the project - again due to changes in conflict dynamics and the operating environment.

Nonetheless, against the planned outcome milestone for end-January 2022, 75% of targeted affected people had had access to protection services and were able to meet basic needs – a total of 5,215 people (1,850 women and people living with disability) of a planned 7,000 as of end-January 2022.

At output level, 2,264 people of a planned 5,000 (45% of target) had benefitted from free legal awareness and legal aid services via 12 legal aid clinics run by Dilla and Bule Hora universities. Further, 537 people of a planned 500 (107%) had accessed protection counselling and referrals; and 1,606 people affected by conflict or flood-induced displacement in West Guji (Abaya and Galana woredas) and Gedeo (Konso, Alle, Yirgachirfe and Kochore woredas) of a planned 2,000 (80%) had received material assistance such as ‘core relief items’ (CRI) or dignity kits.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

The VfM performance of this intervention is moderate when compared to the proposition in the Business Case. The business case envisioned delivery of services through the government as providing the best efficiency and economy, however, acknowledged the importance of augmenting GoE response with non-governmental partners to increase speed of delivery in some circumstances. This is a good example of such a circumstance; protection monitoring and response is a clear gap and increasing funding for monitoring and response activities makes good sense. And in areas where the Government is party to the conflict, it is more appropriate for sensitive protection services to be delivered via independent humanitarian agencies. The major challenge, on equity, was that insecurity and access challenges prevented HCR and partners from conducting programming in the most affected areas.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

This output was newly-created in 2021 to reflect the UK support to UNHCR for IDP response in Ethiopia. UK support was agreed in the final quarter of 2021 (1 November 2021) and runs to 31 March 2022. There are no changes to the output planned as a result of this review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The agreement with UNHCR for IDP response was initiated in the final quarter of 2021, meaning there are no recommendations from the previous AR.

For lessons learned, due to the multiple phases in which FCDO Ethiopia received and allocated funds in 2022, flexibility was required from both FCDO and UNHCR to outline and agree on interventions that were both meaningful in a rapidly changing context but which also allowed for full commitment of available funds in the UK financial year. To achieve this, a proportion of UK support was earmarked for direct supply support (e.g. core relief items), combined with more service- and information-focused interventions e.g., legal aid services for affected populations and mixed cash-based assistance.

Recommendations:

1. At the end of the implementation period, assess whether progress and impact has been sufficient to justify follow-on funding (within the context of the broader management burden – see overall recommendations on p.4).
2. The FCDO has seen several examples of monitoring reports created on the basis of information gathered by the UNHCR’s protection monitoring tool and will continue to explore with the Protection Cluster how these are being used to inform operational response, as well as advocacy. Due to the challenges faced by NGOs and their staff throughout 2021, ranging from bureaucratic and administrative challenges through to harassment and detention of staff, FCDO has noted in conversations in early 2022 the continued hesitancy from actors involved in protection work in Ethiopia to engage in certain types of advocacy, a good example of the broader shrinking humanitarian space.
3. The approach taken by UNHCR in relation to ensuring and expanding legal aid services available via partnerships with local universities to provide legal counselling appears to have been productive so far. There may be potential to scale up this type of intervention.
4. The FCDO should continue to engage with UNHCR in relation to the proportionality of staffing and resources allocated to refugee and IDP programming in Ethiopia.

Output Title	Living conditions of displaced population is improved through timely and quality provision of shelter, NFI, lightning, access to services for protection need (IOM)
Output number:		7	Output Score:	A+
Impact weighting (%):		10%	Weighting revised since last AR?	New output

Indicator(s)	Milestone(s) for this review	Progress
7.1 # of people at risk provided with individual protection assistance (cash) to mitigate risks and meet basic needs	250 (40 men, 90 women, 55 boys, 65 girls) / (March 2022 target)	On track to meet expectations / 172 individuals provided with cash/in-kind assistance (Feb 2022 progress update) 68% of target reached over 66% of implementation period.
7.2 # of individuals reached with medical curative consultations	27,600 people (March 2022 target)	Substantially exceeded expectation / 32,575 people reached (Feb 2022 progress update)
7.3 # of forced returnee individuals receiving NFIs	7,100 individuals (30% women, 70% men)	Not assessed : due to the state of emergency this were no returnees during the period. / 0% of March 2022 milestone reached (per IOM interim report 31 Jan 2022)

Briefly describe the output’s activities and provide supporting narrative for the score.
The wider goal of the International Organisation for Migration (IOM) component of the programme is protection of crisis-affected people through delivery of comprehensive humanitarian assistance in the three northern regions of Tigray, Afar and Amhara.

As such, the component is a multi-sector and multi-outcome intervention covering shelter and NFIs, camp coordination and camp management (CCCM), protection (Gender-Based Violence (GBV) and individual protection assistance (via cash support), health (including medical, reproductive health, nutrition and immunization, and mental health services), and post-arrival assistance to Ethiopians arriving in Addis Ababa as part of forced returns from other countries.

Due to the rapidly changing conflict-dynamics in Northern Ethiopia, FCDO and IOM agreed a number of changes to the project during implementation to adapt to the context. For example, due to difficulties getting cash into the Tigray region and in response to community feedback, IOM moved from the provision of cash to in-kind assistance for at-risk populations in need of protection assistance.

In addition to progress reported against the indicators above, IOM have provided emergency cash support towards shelter and basic items for 3,650 households in Amhara, installed solar streetlights in a displacement location in Tigray that contribute to offering a greater sense of security and accessibility for site inhabitants, supported survivors of GBV with cash to help meet their needs, and have worked to make sure that assistance is delivered in a safe and accessible manner (85% of reached individuals reporting this to IOM and its staff). A portion of UK support is also earmarked to support services and basic items for Ethiopian migrants being returned from other countries to Addis Ababa. Due to the State of Emergency (SoE) imposed by the Government of Ethiopia in early November 2022, return of migrants from other countries – largely Saudi Arabia and Yemen – were paused. The SoE was lifted in February 2022 and returns are anticipated to restart in March 2022.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

It is early in the implementation period to adequately assess VfM, however, IOM have been able to implement in the most affected areas, where other partners have struggled.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

This output was newly-created in 2021 to reflect the UK support to IOM for northern Ethiopia response. UK support was agreed in the final quarter of 2021 (18 November 2021) and runs to 31 March 2022. There are no changes to the output planned as a result of this review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The agreement with IOM was initiated in the final quarter of 2022, meaning there are no recommendations from the previous AR.

For lessons learned, due to the multiple phases in which FCDO Ethiopia received and allocated funds in 2022, flexibility was required from FCDO and IOM to agree on meaningful interventions in a rapidly changing context but which also allowed for full commitment of available funds in the UK financial year.

Recommendations:
At the end of the implementation period assess whether progress and impact has been sufficient to justify follow-on funding (within the context of the broader management burden – see overall recommendations on p.4).

Output Title	Improved access to basic health care, improved management of SAM with medical complications, strengthened disease surveillance system (WHO)
Output number:		8	Output Score:	A
Impact weighting (%):		5%	Weighting revised since last AR?	New output

Indicator(s)	Milestone(s) for this review	Progress
8.1 – Number of emergency health kits provided to implementing partners (RHB & MHNTs).	385	Moderately exceeded expectation / 468
8.2 – Number of health care workers trained on clinical management of GBV, Mental Health/MH GAP and management of acute malnutrition	155 (by 31st March 2022) / 50 GBV/50 MH GAP/ 55 acute malnutrition	On track to meet expectations / 50 GBV / MHGAP training scheduled for Feb/March 2022 / 55 acute malnutrition
8.3 – Number of rehabilitated health infrastructures	5	Substantially did not meet expectation / 0
8.4 – Proportion of children managed for SAM with medical complications cure and/or stabilized, transferred to OTP	>75%	Met expectation / >75%
8.5 – Number of PAED SAM kits procured and distributed in Afar, Tigray, Amhara regions	10 (Kits) - 80 (Modules)	Moderately exceeded expectation / 20 kits / 90 modules
8.6 – Death rate for children managed for SAM with medical complications	<10%	Met expectation / <10%
8.7 – Default rate for children managed for SAM with medical complications	<15%	Met expectation / <15%
8.8 – Number of health care workers trained on IDSR (Integrated Disease Surveillance and Response) and RRT (rapid response) on outbreak investigation and Management	115 (by 31 March 2022)	Not assessed in this review: training scheduled for Feb/March 2022

Briefly describe the output’s activities and provide supporting narrative for the score.
This output scores an A, meets expectations. This AR is being undertaken as this WHO funded project covering the three regions of northern Ethiopia reaches its mid-term, with only two months to go to the end of the project. Based on the mid-term report, and the above progress figures, it appears that, despite the extremely challenging context, WHO has so far achieved reasonably well in terms of supply chain management and end point delivery (Indicators 8.1 and 8.5).

A number of trainings have started late January so cannot be reported as achieved at the time of the mid-term report, e.g. Gender-Based Violence and Mental Health and Psychosocial Support master training workshops (TOT) – indicator 8.2. Capacity building of 55 health workers and health managers on CMAM has also started end January in Amhara.

Reported defaulter rate (indicator 8.7) in the three regions of intervention is aligned with Sphere standards (<15%) however a number of zones experienced an increase in defaulter rates, e.g. in zones of NorthShewa (17.1%), West Gojiam (16.8%) and central Gondar (14.4%). This was largely attributed to the service interruption in those affected woredas due to the conflict and shortage of Ready-to-Use Therapeutic Food supplies. It is worth mentioning that figures must be considered with caution due to major drop in reporting rates in the most affected woredas, which creates challenges to analyse whether management of SAM with medical complications is improving.

There have been serious delays to the planned infrastructure rehabilitation activities (indicator 8.3), due to wider Ministry of Health discussions about recovery and reconstruction plans. At the time that the grant with WHO was signed, it was expected that only minor facility repairs would be required. However the subsequent spread and evolution of the conflict in Northern Ethiopia has led to a level of infrastructure damage that far outstrips the funding available under the BRE programme. As a result it is unlikely that the target of rehabilitating 5 health infrastructures will be met.

Disease surveillance, early warning and response remain challenging across the health sector, with sub optimal weekly reporting due to insecurity, lack of access, disruption in communication. Tigray is an even more challenging environment with lack of fuel, cash, communication severely affecting disease reporting.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

It is early in the implementation period to adequately assess VfM. This will be done following completion of the current round of funding.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

N/a

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

This is a new programme component and as a result there are no recommendations from the previous AR. Assess partner performance when full data becomes available

Recommendations:

1. Strengthen the collaboration between WHO, WFP, and UNICEF on nutrition and CMAM programming
2. Commission an expert review to improve the nutrition information system – including a focus on early warning and the quality of the analysis

Output Title	Provision of safety and security operational support and analysis (UNDSS)
Output number:		9	Output Score:	C
Impact weighting (%):		5%	Weighting revised since last AR?	New output

Indicator(s)	Milestone(s) for this review	Progress
9.1 Number of field officers deployed	3	Off-track / Recruitment ongoing, commenced in March 2022
9.2 Provision of timely written reports and Coordination Meetings / Briefings	Weekly/daily written report >24 / coordination meting > 6	UNDSS provides national and area based weekly briefings for all humanitarian partners (INGO / Donors), biweekly through the Access Working Group and weekly to the EHCT. They also provide – daily internal reports for the UN system. However this has not yet been influenced by UK funded project activities.

Briefly describe the output’s activities and provide supporting narrative for the score.
This output scores a C, does not meet expectations. Due to interruptions and changeover in staffing both at post and within UNDSS, complicated by security-based drawdowns by FCDO the initiation of implementation of the activities under the output were delayed by three months. Hence the main activities which should have commenced in early December did not commence until early March 2022. UNDSS agreed on 1st March to have committed the majority of the funding by 31 March 2022.

Although UNDSS have met the outputs in terms of security reporting and briefings, this is not yet impacted by our funding. Rather the quality and analysis of the content will be enhanced greatly once the staff provided by this programme are functioning in post.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

Due to the delay in commencement of the programme it is not possible to assess the VfM.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

N/a

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

As a results of slow delivery to date, FCDO will be taking an enhanced programme management approach to ensure that the project gets back on track.

Recommendations:
Considering this output is primarily a 10-month staffing package and a set up procurement package, a no-cost extension will likely be requested to allow for three additional months lost at its initiation.

Output Title	Support to ICRC Ethiopia Appeal
Output number:		10	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR	New output

Indicator(s)	Milestone(s) for this review	Progress
Number of health facility staff supported to continue working	Supported 18 health facilities with food for employees, families and patients.	Met expectations / In order to ensure the functionality of health facilities in Tigray in the absence of salaries, supported 18 health facilities with 237,225 kgs of wheat, 23,760 kgs of chickpea, 7,130 liters of cooking oil, and 3,186 kgs of salt to employees of the facilities and their families and patients.
Number of primary health facilities supported	6 in Oromia and Somali region / 11 primary health centres in Tigray	Met expectations / Provided with monthly technical support, medical supplies and post-delivery maternal and hygienic / items to 6 primary health care centers in Husse, Chinaksen, Tuliguled, Meyu, Inango and Guliso districts in Oromia and Somali regions. / The ICRC also gave similar assistance to 11 primary health centers in Tigray region. The supplies benefited over 5,350 mothers who delivered their babies in the centers.
Number of primary health care unit and hospitals / Number of patients treated	Provide basic medical supplies, emergency weapon-wounded kits, medical equipment, mobility devices and personal protection equipment to 44 primary health care units and 57 hospitals. / 133,800 patients treated	Met expectations / Provided basic medical supplies, emergency weapon-wounded kits, medical equipment, mobility devices and personal protection equipment to 44 primary health care units and 57 hospitals in different regions with the objective of enhancing their emergency and COVID-19 prevention and control response capacities. The supplies helped treat 4,250 critically and 13,450 moderately wounded people, and 116,100 other patients.
Number of farming households	Support 16,139 conflict-affected farming households with seeds and fertilizers	Met expectations / Supported 16,139 farming households affected by the conflict in Tigray region with teff and sorghum seeds as well as fertilizers benefiting 96,834 family members.

Briefly describe the output’s activities and provide supporting narrative for the score.
This output scores an A, meets expectations. ICRC is a long-term partner for the UK globally and by contributing to their appeal the UK can ensure they remain capable of responding to protection and assistance needs across the country.

Our expectation is that ICRC would have access in areas that others do not give their specialism in delivering in conflict-affected environments. Up until June 2021, ICRC did manage to reach more areas of Tigray than many other humanitarian actors. However, since the de facto blockade of the region started, they have also been affected by barriers to access. This means that not as much activity and assistance has occurred in Tigray as planned.

Through the course of the reporting period, it has become apparent that the ICRC has not been as coordinated with relevant partners as it needs to be.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
ICRC offer the UK a capability to be flexible in how it responds and provides protection expertise that is unparalled (in some areas), which is important for this crisis response. The UK however should have a stronger relationship with the ICRC to better understand both progress and operational constraints.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
N/a

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
N/a

Recommendations:
Work with ICRC country team and HQ to improve communication with humanitarian team staff.

D: RISK [½ to 1 page]

Overview of risk management
The continuing large-scale shift in the operating environment, caused primarily by the Tigray conflict, requires a further reassessment of the BRE risk profile. The team should assess whether the combined decreasing humanitarian space and minimal oversight on government-implemented programming constitutes a further increase in risk from major to severe (last year saw an increase from moderate to major). There are ways to reduce the residual risk that have been suggested in this AR, including:
- Developing a policy strategy that uses all available levers to improve humanitarian space, with the intended impact of improving the quality and access of partner programming, creating more space for humanitarian diplomacy with the GoE, mitigating the creation of new need, and ensuring adherence to humanitarian principles
- Introducing benchmarks for the government to achieve on quality and accountability – and minimising funding until that point, both direct and through UN agencies. This would improve the FCDO’s oversight of programming delivered through government channels and ultimately strengthen the mechanism and improve wider donor confidence in it.
- Reducing the number of partners to improve the ability of the humanitarian team to engage in detail with partners
- Introducing a TPM mechanism that is directly managed by the FCDO to expand oversight capacity, including in areas with little or no access to advisers.
An additional increased risk under BRE during the reporting period was the significantly reduced programming budget, which reduced by 60% during initial budget adjustments, although subsequently incrementally improved to a 22% reduction from last financial year (£73m in FY20/21 reduced to a final figure of £57m in FY21/22). The biggest impact of this reduction was the decreased number of people assisted with UK aid but an additional risk was created by the incremental addition of funds after initial cuts. All partners who received funding uplifts noted that, despite welcoming the funding, the incremental nature of the increases and the short timeframes for delivery made it difficult to scale-up strategically.

Update on Partnership Principles

During the review period, no financial aid contributions have been made to the Government of Ethiopia under the BRE programme. So there has not been an update on the programme-level partnership principles assessment.

The last financial aid payment made under the BRE programme was a £20 million contribution via PSNP channels in Autumn 2020, but the implementation of this contribution is covered in this review (see output 3). The Annual Statement of Progress was updated in November 2020, and it identified the following key risks that have been tracked during programme implementation:

Risk 1: Coordination of greater numbers of implementing actors may be a challenge unless sufficient capacity is built at different levels.
- Planned measures: A full review of the financial management and procurement requirements of an expanded programme to identify gaps in capacity in existing and any potentially new regions and woredas (districts). This is linked with the WB PAD requirement for capacity building in regions and woredas (districts). More actors have joined the programme and the MoA and MoF should have the necessary capacity to efficiently coordinate this.
- Progress: MOF provided training on the Financial management of the program to Ministry of Labour and Social Affairs (MOLSA) and EDRMC during EFY 2009, and training to Afar and Somali region in EFY 2010, EFY 2011 and EFY 2012. Woreda procurement experts and additional cashiers and accountants have been recruited except SNNP.
- Remedial measures: Recruitment of procurement specialists and finance management staff at woreda (district) level should be monitored in SNNP and Sidama regions and new split woredas. Training on financial management procedures should continue for regional and woreda (district) staff.

Risk 2: Follow up of audit observations in PSNP spending units at all levels appears weak and has been noted in the most recent external auditor’s report.
- Planned measures: An analysis of last 2 years’ audit observations to check follow-up with a view to institutionalising arrangements for regular review and follow-up of both internal and external audit observations.
- Progress: Significant improvements have been noted. MOF now submits audit action plans within one month from receipt of the audit reports. Status reports for actions taken on the audit findings are also submitted on time. Some findings from the EFY 2011 annual audit are pending and will be reviewed in next annual audit report.
- Remedial measures: Continue to monitor audit follow up through UK engagement in financial management task force, PSNP Donor Working Group and PSNP Donor Coordination Team.

Risk 3: Beneficiaries in pastoral regions are now receiving part of their transfers in cash instead of food, which represents a new risk in light of identified challenges in both Somali and Afar regions.
- Planned measures: Dedicated monitoring missions to review financial management, track risk and identify recommendations. Development Partners assigned independent consultants to review the Financial Management in Somali and Afar regions in EFY2010, EFY 2011 and EFY 2013.
- Progress: Three round of assessments were conducted to Afar region while the first round of assessment is conducted to Somali region. Follow-up monitoring mission planned in EFY 2013.
- Remedial measures: Monitor quarterly spot check reports from consultants and feed results back into further programme redesign in lowland areas.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial/financial issues, and including consideration of VfM measures of economy and efficiency.

The programme logframe has been updated to reflect the context change in the country, multiple crises including floods, desert locusts, political unrest and conflict leading to internal displacement activities. The major changes to the logframe in 2021 have been:
- New indicators added on WFP to reflect funding for addressing transport capacity gaps to support humanitarian operations through the purchase of trucks under WFP Fleet.
- Indicators added on output five, UNICEF to reflect the new interventions for the Northern Ethiopia humanitarian response to make progress measurement more specific.
- Additional outputs; output 6 for UNHCR, output 7 IOM, output 8 WHO, output 9 UNDSS and output 10 ICRC included to reflect the new interventions for the Northern Ethiopia humanitarian response
Additional changes to the logframe and to the ToC, suggested in the body of this AR are recommended to ensure that it adequately measures performance given the very large shift towards emergency response activities.

The BRE programme risk matrix has been revised and updated regularly to be consistent with and the overall risk appetite across the British Embassy Addis country portfolio in Ethiopia.

Financial allocations across the BRE programme
[note] Financial allocations in 2022/23 and 2023/24 are subject to confirmation of budgets in the next spending review period.
Current and Planned Programme Components and Partners	2017/18	2018/19	2019/20	2020/21	2021/22	2022/23	2023/24	Total
Technical Assistance (TA) to Government of Ethiopia	-	-	1.7	3.9	4	16.3 / (TBC)	-	25.9
World Food Programme (WFP)	30	12	-	9	11.3	-	-	62.3
Ethiopia Humanitarian Fund/UNOCHA	16.5	19.2	17.8	15	11.4	-	-	79.9
UNICEF	3	4.5	9.3	22.7	20.7	-	-	60.2
Government of Ethiopia (MoF)	25	28.5	27	20	-	-	-	100.5
Emergency Response/contingency	-	-	-	-	-	1.5 (TBC)	6.4 / (TBC)	7.9
Surge support	0.2	0.3	0.3	0.2	0.5	-	-	1.5
NFI support to Gedeo and Guji Internally Displaced People	-	1	0.4	-	-	-	-	1.4
Catholic Relief Service (CRS)	-	0.6	0.4	-	-	-	-	1
International Committee of the Red Cross (ICRC)	-	-	-	2	4	-	-	6
IOM	-	-	-	-	2	-	-	2
WHO	-	-	-	-	1.5	-	-	1.5
UNHCR	-	-	-	-	0.9	-	-	0.9
UNDSS	-	-	-	-	1	-	-	1
Total	74.7	66.1	56.9	72.8	57.3	17.8	6.4	352

Commercial and financial performance
At the beginning of fiscal year 2021 the programme planned to spend £15.7million. However, the increased in humanitarian needs across Ethiopia ministers approved to spend additional £40.9million in June and September 2021. This enable the funds were drawn forward, and the overall spending increased to £57.1 million in total of which £45.7 million specifically allocated to Northern Ethiopia humanitarian response.

To address needs across Ethiopia, BRE provided:

1. £4 million to OPM to provide technical support to the GoE
2. £3.3 million to World Food Programme (WFP) to meet emergency food needs through cash-based transfers in Somali Region using PSNP delivery mechanisms.
3. £3.8 million to UNICEF for nutrition and WASH interventions.

£45.7 million to Northern Ethiopia humanitarian response:
1. £5 million to WFP to provide nutrition support to malnourished children and pregnant and lactating women affected by the conflict in the Northern part of the country
2. £3 million to increase the transport capacity in support of humanitarian operations in Northern Ethiopia by purchasing trucks
3. £11.4 million to Ethiopian Humanitarian Fund (EHF) to support a rapid response to the Northern Ethiopia and other areas of the country humanitarian response covering health, shelter, protection and WASH.
4. £16.9 million to UNICEF for multisectoral famine prevention activities through lifesaving emergency assistance: child protection, health, nutrition and WASH interventions.
5. £4 million to ICRC for their Northern response covering emergency health support, protection, food assistance, and water treatment programmes.
6. £2 million to IOM Lifesaving, multi-sectoral emergency assistance and protection to populations affected by the Northern Ethiopia Crisis.
7. £1.5 million to WHO for providing essential health care services to conflict affected areas in Northern Ethiopia Humanitarian Response.
8. £0.9 million to UNHCR for protection monitoring and response for IDPs in Ethiopia
9. £1 million to UNDSS for provision of safety and security support.
Compliance with the Supply Partner Code.
OPM has complied effectively with the supplier code. OPM has scored Good on Key Performance Indicators for delivery of work and KPI scores have gradually increased over the year.
Compliance with the new cost and transparency requirements
OPM has been compliant with transparency requirements and has used Open Book Accounting.

Performance of partnership (s)
All partners performance meet expectation within the rapid context change in the country.

WFP
WFP’s Audited Annual Accounts for the 12 months period ended 31 December 2020, reflected that External Auditor has completed the audit in accordance with the International Standards of Auditing, and has provided an unqualified audit opinion. The financial statements present fairly the financial position of WFP results of the operations for the period in conformity with the International Public Sector Accounting Standard (IPSAS). WFP shown improving performance working with Financial Service Provider on cash response programme with the change in delivery modality.

EHF
The EHF conducts a Capacity Assessment for each prospective partner, assessing the institutional, managerial, financial, operational and technical ability to deliver under the conditions of the Grant Agreement. This process is managed through the Grant Management System at the country-level and is mandatory before being eligible to apply for funding. Ineligible partners can re-apply after 6 months if they can demonstrate progress in areas deemed insufficient to pass the assessment. FCDO is part of the EHF advisory board responsible for the overall oversight and overall strategic direction of EHF as well as the Technical Advisory committee responsible for reviewing and selecting grants. This puts FCDO in a strong position to ensure that funds are well targeted and spent in line with the UK humanitarian reform agenda.

UNICEF
UNICEF Internal Audit of the Ethiopia Country office period covered January 2019 to April 2020 noted a number of areas where the office’s governance, controls and risk management were functioning well. There was a comprehensive process for the development of the 2020-2025 country programme and a consultative process for developing the related country programme management plan. Key risks to the achievement of results had been identified, and actions proposed to address and mitigate them. The office had conducted a partners’ perceptions study to guide its working relationship with the partners.

ICRC
ICRC have adequate controls in its financial management, including when working with and through partners. The ICRC is a direct implementer of most of its programmes and only a small proportion of its budget is channelled through partners, with the majority of this through the national red cross society. ICRC Ethiopia has its own Financial Regulation Manual for its operations in Ethiopia. The manual, aligned with the central policy of the organisation, sets out clear lines on delegated authority. The delegation authority level is also coded in the systems used by the organisation which blocks people who do not have the delegation authority from approving.

IOM
For the Northern Ethiopia Crisis response, IOM developed a Staff and Programme criticality and related monitoring tool which is followed up on regularly. In view of the recent escalation of fighting in Amhara and Afar regions, IOM is updating its Business Continuity Plan of all units and offices, including designation of critical and non-critical staff, criticality of programme activities, alternate work modalities, and other crisis management scenarios to ensure business continuity in the event of escalating civil unrest.

WHO
WHO’s effective budgetary control through the implementation of financial management policies is evidence based. Program mangers review variances during the reporting exercises and adjustments and related justifications are produced, concurred, and implemented accordingly. WHO produces exception reports periodically reviewed by the Program and Operation teams and corrected actions are implemented accordingly.

UNDSS
UNDSS’ ability to deliver relies on a complex network of collaborations with other enabling UN agencies. Prominent among these are the comprehensive MoU it has with UNDP on managing funds received from donors and managing project staff in accordance with UNDP Financial Regulations and Rules (FRR) and Human resource management rules. The financial management of the proposed project will be implemented by the UNDSS office in Ethiopia, managed by the UNDSS Chief Security Adviser for Ethiopia. The proposed project will be monitored by the CSA /Chief Security Adviser/ and will be reported separately to the donor. UNDP shares a financial report to donors on a quarterly basis. UNDSS relies on the standard UNDP accounting procedures.

Date of last narrative financial report(s)	BRE TA OPM: Progress and VfM report period covered January – December 2021 / WFP: nutrition narrative and uncertified financial report (Dec 2020-Dec. 2021) / WFP: Interim procurement of trucks narrative and financial report (October – Dec. 2021) / WFP: Strengthening Shock Responsiveness under PSNP 5 in the Somali Region narrative and uncertified financial statement (Dec. 2020-Dec.2021) / UNICEF: bi-annual progress and financial report: August 2021 – Jan. 2022. / GoE: Ethiopia Rural Productive Safety Net Programs (RPSNP) Annual Performance Report for EFY 2013 (2020/2021) / EHF 2020 Annual report / ICRC: Narrative report Jan. – June 2021 / IOM: Narrative and financial report period covered 18 Nov. – 31 Dec. 2021 / WHO: Narrative and financial report period coved 1st Oct. – 31st Jan 2021 / UNHCR: Narrative and financial report period coved 1st Nov. – 31st Jan. 2021
Date of last audited annual statement (s)	OPM: Annual Report and Financial Statements for the period ended 31 March 2021 / WFP: Financial Statements of the World Food Programme (WFP), for the 12 months period ended 31 December 2020. / UNOCHA: Internal Audit Division 2019 / UNOCHA: MOPAN Assessment Report United Nations Office for the Coordination of Humanitarian Affairs (OCHA) 2020 Assessment Cycle Published October 2021 / UNICEF Internal Audit of the Ethiopia Country Office September 2020 / ICRC: Africa Report to the Director of Financial Resources and Logistics 2020 / IOM: Financial Report for the year ended 31 December 2020 / WHO: External Auditor on the financial operations of the World Health Organization for the financial year ended 31 December 2020. / UNHCR: Financial report and audited financial statements for the year ended 31 December 2020