 Programme Completion Review

Title: Montserrat Financial Aid
Final Programme Spend £ (full life): £73.88m	Review Date:	June 2022
Programme Code: 204728	Start Date:15/05/2019	End Date: 30/06/2022

Summary of Programme Performance

Year	2020	2021	2022
Programme Score	B	B	B
Residual Risk Exposure Rating	Major	Major	Major

DevTracker Link to Business Case (and any addendum):	https://iati.fcdo.gov.uk/iati_documents/50867289.odt
DevTracker Links to all logframes used during programme lifetime:	https://iati.fcdo.gov.uk/iati_documents/59230418.xlsx

A. Summary and Overview (1-2 pages)

Description of the programme and what it has achieved [1/2 page]

The Montserrat Financial Aid programme was approved in March 2019 for a three-year period to support the provision of all public services to the people of Montserrat, including health, education and securing air and sea access. Financial Aid has been the main form of UK assistance to Montserrat since the volcanic eruptions of the late 1990s. The programme bridges the gap between the domestic revenues collected and the costs of delivering essential public services.
[note] Montserrat was severely impacted by volcanic eruptions 26 years ago, which destroyed the capital, port, airport, much of the housing stock and has left two thirds of the island as an exclusion zone, which contains much of the country’s prime agricultural land.
[note] This support for the recurrent budget, sits alongside UK investment in infrastructure (£30m capital investment programme, a separate project to build a new port), and other smaller scale projects to protect the environment.

The provision of financial aid to the island is in line with the UK Government’s (UKG) obligations to meet the reasonable assistance needs of the citizens of Montserrat and other aided Overseas Territories. It aligns with the 2012 Overseas Territories White Paper, the NSC Strategy (refreshed in 2019), the UK’s UN Charter obligations and relevant elements of the newly approved UKG’s Strategy for International Development (May 2022).
[note] https://www.gov.uk/government/publications/uk-governments-strategy-for-international-development/the-uk-governments-strategy-for-international-development. This does not include all of Governor’s Office’s constitutional duties in Montserrat.

Despite being a three-year Business Case, in line with the current UK Spending Round, funding was determined and allocated on an annual basis, following discussions between the UK and Government of Montserrat (GoM) .
[note] Funding was disbursed in three or four tranches as appropriate. Payments were released by FCDO once GoM had provided evidence of need and satisfied any further conditions of the MoU budget agreement.

Total support consisted of transfers to GoM’s consolidated fund for ongoing operational costs and two ring-fenced budget lines: the Technical Cooperation (TC) programme, offering technical assistance and capacity-building support and earmarked funding to maintain access to the island (air and sea). The settlement for 2021/22 was of up to £23.6m, consisting of £20m to support Government’s recurrent expenditure across its Ministries; £493,151 to support and maintain access to Montserrat and £2.9m to support the Government in filling key posts to deliver public services and build its capacity.

At outcome and impact level the programme aimed to ‘contribute to the human and economic development needs of the people of Montserrat’ leading to ‘a thriving Montserrat economy with a vibrant, healthy and open community’.

The provision of financial aid is only one contributory element of achieving this overall outcome and impact, with its objective being to bridge the gap between the domestic revenues collected and the costs of delivering essential public services. To see sustainable progress on economic and human development, GoM’s economic growth strategy and other relevant development plans would need to be budgeted for and implemented. Whilst providing this type of support is outside of the remit of the Financial Aid programme, there is a risk that we will not see a reduction in the share of financial aid provided, if we do not support programmes aligned with GoM’s growth and sectoral strategies (once satisfied these are strong and sufficiently evidence-based).

This review has scored this Financial Aid programme 2021/22 as a B (moderately did not meet expectation). This is in line with the independent reviews conducted for previous years of the Financial Aid programme. This period was very challenging for Montserrat, during which time action had to be taken to respond to the COVID-19 pandemic, shipping costs rose and international tourism contracted.

In some areas there has been improvement compared to 2020/21, including GoM’s performance with respect to budget reliability. This is reflected in the score of A+ against indicators measuring aggregate expenditure out-turn, domestic recurrent revenue out-turn and expenditure composition out-turn. Other targets at outcome and at output level have not been achieved due to a combination of factors, including resourcing challenges, particularly acute in the education and health sector, made even more challenging due to the pandemic.
[note] Aggregate expenditure out-turn measures the extent to which aggregate budget expenditure out-turn reflects the amount originally approved, as defined in government budget documentation and fiscal reports. Expenditure composition out-turn measures ability to spend resources in accordance with the government’s plans, as expressed in the originally approved budget. Expenditure composition out-turn looks at variation between the composition of the executed budget and the composition of the approved budget. For more information, please see the PEFA handbook here: https://www.pefa.org/sites/pefa/files/resources/downloads/200225%20PEFA%20Handbook%20Vol%20II_v2-New-logo.pdf

There are concerns around the suitability of some of the targets and milestone indicators set within the FCDO logframe, which will need to be reviewed and updated for the new Financial Aid programme. For example, the target for the TC milestone is currently missing for 2021/22. Other milestones are process-oriented and not ambitious enough (i.e. access).

On output 1, relating to the management of public resources according to best public financial management and government practice, ensuring value for money (25% weighting), the programme scored a B overall. Positive performance against budget reliability indicators, whilst targets on sub-indicators 1.3 (improvement in the administration of taxes), 1.4 (monitoring and evaluation to inform planning and policymaking) and 1.5 (procurement reform plan) scored below expectations.

On output 2, ensuring government services are delivered to meet human development needs, with a focus on the most vulnerable, including women, children, the elderly and disabled (35% weighting), the programme scored a B. The target for the number of primary school teachers trained was met whilst the number of secondary school teachers was below target. Progress on the development and implementation of health financing reform and on enhanced secondary prevention were also below target. Whilst progress has been made under this output, in both cases a lack of staffing played a role in meeting targets.

On output 3, relating to recurrent budget providing a supporting environment for private sector led, resilient growth (10% weighting), the programme scored a B. There are questions as to whether the measures and indicators selected are appropriate to measure support provided to the private sector. The Economic Growth strategy remained unbudgeted for and has not been implemented, whilst work on the Sustainable Development plan is delayed by two years. The target indicator for number of people who have completed the workplace awareness training Helping Our People Excell (HYPE) has not been updated in the FCDO logframe to reflect Ministry’s decision to reduce the number of participants, resulting in the programme not hitting the target set out in the logframe.
[note] This is partly due to the impact of Covid-19. The SDP process has been delayed partly due to the impact of Covid-19 and availability of the consultants identified to lead on the SDP process. Work on the SDP has now commenced.

Output 4 is about improving human resource capacity of the public sector (15% weighting), and scored a B. The target for critical posts in the public sector being filled and good management practices pursued was missing in the FCDO logframe for 2021/22. A detailed narrative of challenges in these areas can be found below, including the challenges COVID-19 presented. Information on percentage of public officers completing L&D goals during the reporting year was not made available.
[note] Quarter 4 reports give this in a narrative form.

On the final output area, which covers safe, reliable and regular access to Montserrat that provides value for money (weighting 15%), milestone targets have been met. However, targets for the year were not sufficiently ambitious. A decision was taken to suspend the ferry during COVID-19 by GoM, partly due to reduced passengers numbers, restrictions on international travel, and in recognition that the model did not represent good value for money, based on a large share of public subsidies. Currently, the absence of a ferry has a negative impact on the country’s economy, including the ability of tourists to get to the island, for residents to affordably travel (air tickets are considerably more expensive) and on transportation of goods. In terms of access strategy, there is ongoing discussion about different air options and timeline for the re-introduction of the ferry. Cabinet has requested an updated strategy that will underpin the economic development of Montserrat.
[note] Targets included: access plans remaining within baseline; agreement between GoM and FCDO on process and timeline for engagement and consultation on mid- and long-term access plans.
[note] Limited goods support has been provided by monthly goods vessel. This brings limited stock to the island and is often delayed.

Major lessons learned, evidence generated and recommendations [1/2 page]

Lessons

The Financial Aid Mission (FAM) allocated funding to this programme based on GoM’s prioritisation and projections of spend for the year. There are some basic human development areas that have not been fully budgeted for, resulting in continued challenges in achieving better quality services, including in health and education. Whilst Monserrat could recruit some medical staff (a Cuban medical contingent) and then FCDO funded NHS staff for a brief period, ensuring there is a strategy to retain and attract health workers is of critical importance, especially ensuring appropriate salary levels are allocated and prioritised within Montserrat’s budget.

The Financial Aid programme aims to bridge the gap between domestic revenues collected and the costs of delivering essential public services and should not be thought of as a substitute for the investments needed to propel the island forward socially and economically. Without a budgeted and implemented economic growth strategy, which brings together local initatives and UK support – current and future – it is unlikely Monserrat will be able to reduce its dependency on financial aid.

The Financial Aid programme is the main source of the UK’s offer, together with funding for infrastructure projects. It tends to be seen as the catch-all programme that should help the island grow and move towards economic self-sufficiency. This, together with the fact plans and budgets are presented by GoM on a yearly basis, has had the unintended effect of disincentivising GoM’s longer term planning, with GoM deciding on its broader economic and development plans for the year based on financial aid settlement and its economic and development strategies remaining largely unimplemented and unbudgeted for.
[note] The five year FCDO Capital Investment Programme for Resilient Economic Growth (CIPREG) in Montserrat funds infrastructure projects, including hospital, airport tower, fibre optic cable, and asphalt plant. UK funding is also supporting the port project.

With regard to budgeting, this year GoM has performed well against targets in the logframe on Public Expenditure and Financial Accountability (PEFA). The previous annual review highlighted the impact of COVID-19 and capacity constraints within the Ministry of Finance & Economic Management (MOFEM). The appointment of a substantive Finance Secretary (FS) has helped, with improved scrutiny and a proactive approach in working with Ministries. Similar to previous years there are continued challenges with forecasting and timely action to achieve full budget expenditure and service delivery, as demonstrated by negotiations on unspent funds at near year end. The FS, MOFEM, and Governor and Premier’s offices are working with Ministries to improve their planning, delivery and forecasting to ensure budget and spend are accurately monitored.

A decision was taken by GoM to suspend the ferry service in 2020/21 in response to the impacts of COVID-19, which seriously disrupted movement of people to and from Montserrat. There were concerns about the value for money represented by the model used to operate the ferry, largely based on government’s subsidies and increasing year on year costs. As noted in the previous annual review, notwithstanding the sudden pressures and need for quick decisions, there was insufficient consultation on the decision to cancel the service, which resulted in a significant financial settlement with the ferry operator.

As highlighted in the 2020/21 annual review, the technical cooperation programme continued to struggle with timely recruitment of good candidates into key posts and severe delays during the recruitment process. As highlighted in the Technical Cooperation protocol (2018), there should be a measurable element of knowledge and skills transfer to local staff, reflected in the terms of reference and reported against on a regular basis. This has not taken place systematically, negatively affecting the sustainability of the programme.

The rationale for prioritisation of some TC roles over others is often unclear and feedback received highlighted communication challenges between HR and Ministries on recruitment status and TC roles being shortlisted.

As referenced in the MoU for the programme, FCDO and GoM agreed on a set of reforms for GoM targeting areas that would strengthen assurances of sound public financial management and the main areas of risk raised in the Fiduciary Risk Assessment (FRA). The elevation of monitoring and reviewing of progress against reforms at the monthly Steering Committee (SC), has increased focus on progress.
[note] This consists of FCDO officials, the Governor of Montserrat and the Premier, Ministers and GoM’s officials.

Some areas of improvement identified are to set realistic timelines for delivery (it takes time for reforms to be implemented), prioritisation of reforms and ensuring accountability for the delivery of each reform. A more collegiate approach for agreeing areas of support has been identified for the next financial year. The Governor and the Premier have written a joint letter to the OTD Deputy Director, presenting a set of reforms considered to be deliverable over the next two years to advance the governance agenda and facilitate sustainable economic development. This is a positive step forward that provides further assurance reforms will be prioritised given the senior level commitment and the greater accountability this should bring.
[note] Reforms for 2022/24 have been identified based on an analysis of what would be helpful to drive the economy forward (growth enhancing reforms) in addition to reforms supporting good governance and compliance.

Recommendations

1. To ensure value for money and that financial aid does not continue ad infinitum, FCDO to work with GoM on its development strategies, including the new Sustainable Development Plan (SDP), Economic Growth and relevant sectoral strategies. FCDO would need to be satisfied there is a sound longer term development plan broken down in a 5-year delivery plan, with budget being closely aligned to this. [GoM and FCDO]
2. FCDO to work with HM Treasury about the possibility of securing a change to the budgeting approach, offering a three-year assured process, subject to milestone delivery. This would offer assurance for GoM to make medium term plans a reality. [FCDO]
3. Alongside a renewed effort from GoM to draw up and implement a sustainable economic growth strategy, there needs to be sustained and strategic UK investment in Montserrat’s infrastructure and local capabilities. This needs to balance investment in basic infrastructure and investments which will spur on economic growth. The UK and Montserrat Governments have agreed to begin discussions to scope out a new UK funded capital investment programme as a successor to the existing CIPREG. There is a risk that without the additional investment needed to get onto a positive growth trajectory, Montserrat will remain dependent upon UK assistance. [FCDO and GoM].
4. Ahead of the FAM, GoM should present an evidence-based, fully costed longer term (i.e. five year) plan based on updated development and sectoral strategies alongside plans on how GoM could fund this (i.e. other donors or multilaterals; UKG funding available, FCDO). FCDO and Governor’s Office to provide support, working closely with Ministries. [GoM]
5. Ensuring salary levels at an appropriate level are set for education and public health workers. Consider establishing a partnership between an NHS Trust in England and the Ministry of Health in Montserrat so that health support is being provided in a systematic way. NHS could also provide advice on how to quality assure medical care on Montserrat. [GoM and FCDO]
6. FCDO Development Attaché in Montserrat to finalise TC strategic review commenced in June. It will set out recommendations for both FCDO and GoM to take forward to ensure resources allocated for technical cooperation are put to best use, filling technical gaps in a timely basis. [FCDO and GoM/Office of the Deputy Governor]
7. With GoM, review targets and milestones for the financial aid logframe and GoM’s list of performance indicators to ensure we are tracking the right areas and that indicators help assess quality of service delivery. SMART targets should be set for all outcomes and targets. [FCDO and GoM]
8. Review and update ToC, including assumptions. This should reflect more realistic outcomes and impact targets in the absence of supplementary development programmes. With only infrastructure support and financial aid being provided by the FCDO it’s unrealistic to expect growth and eventual graduation from aid.
9. Provide technical support to M&E Unit and Ministries on data collection and reporting. System is still largely paper-based and of varied capacity within Ministries on data. Ensuring M&E Unit has sufficient resources and accountability is in place should Ministries not report on time. [GoM and FCDO]
10. FCDO team should make sure the logframe is updated monthly, including marking progress against achievements. Risk discussions should take place within the FCDO programme team at least on a quarterly basis as a regular standing agenda item, with the risk register updated accordingly. Major risks should be escalated up the management chain, including using the SC forum. [FCDO]

How this report was conducted [1 paragraph]

The newly appointed FCDO Development Attaché carried out the Programme Completion Review, which has brought a level of independence to this final programme review. Findings are based on a review of key documentation and interviews held with key Government of Montserrat stakeholders and some OTD staff.

Actions following approval of this report [1-2 paragraphs]

Nothing additional to what outlined in the recommendations above.

## B: Theory of Change and Outcome Assessment (1-2 pages)

	Starting point	Final result
Budget	£73,883,564.00	£73,613,790.85 99.63%
Timeframe	01/04/2019 to 31/03/2022	01/04/2019 to 31/03/2022
Outcomes	Financial aid contributes to the human and economic development needs of the people of Montserrat through enabling the provision of essential government services	On meeting economic needs of the people of Montserrat, the programme had one major outcome linked to seeing improvements in the percentage of local revenue generated. Over the duration of the programme there has been an uptick in the percentage of revenue generated locally, although questions whether this can be attributed to the Financial Aid programme. / On contributing to human development needs of the people of Montserrat, performance at outcome level has been variable throughout the duration of the programme. Targets have not been met for FY 2021/22 under both education and health, but there are questions as to whether measures selected are the appropriate ones to track improvements in the area of human development and whether meaningful improvements can take place if structural challenges, such as availability and retention of key public sector workers in the health and education sector are not being fully addressed and the creation of a pipeline of future workers in these sectors. / There has been progress towards accelerating number of assessments completed within 21 days (child and adult safeguarding).

Overall assessment of programme outcomes, sustainability and VfM [1/2 – 1 page]

The Financial Aid Programme met some of the milestones and targets identified at outcome level. There has been gradual improvement in the percentage of revenue share generated locally over time, and targets under safeguarding have been met. Under health and education targets have not been met for FY 2021-22 partly due to underlying health and education staffing issues not budgeted for.
[note] This could be due to a number of external factors, including increase in prices of goods.

There are questions about the relevance of indicators selected to measure progress against meeting human and economic needs of the people of Montserrat. For example, under education, we are currently tracking the percentage of student age cohort gaining five Caribbean Secondary Education certificates (CSECs), including English and Maths, disaggregated by gender. This could be monitored at output level, with outcome level measures tracking retention and matching of skills to workforce needs on the island. This would also require actions at output level seeking to diversify professional and formal education training based on growth areas and workforce demands. Work on this is already underway within the Ministry of Education and milestone/targets for the future Financial Aid programme should reflect this.

Some of the key structural challenges underpinning the achievement of health and education outcome indicators (such as number of students obtaining CSECs and improved disease management) have not been addressed and should be reflected at output level. The Sustainable Development Plan (SDP) for Montserrat had identified in 2018 the need to employ appropriate measures to recruit and retain sufficient numbers of qualified teachers and ensure compensation was comparable to other occupations with similar qualifications and professional requirements. Ensuring sufficient focus and funding is allocated to address these challenges is critical to see progress in education, including availability of teachers who are incentivised to do their job well and the creation of a pipeline of students who, upon graduation, have either academic or vocational training aligned with Montserrat’s growth sectors and workforce needs. This will need to be budgeted for as an important aspect of meeting the reasonable needs of the island.

For health, whilst the programme at outcome level focussed on seeing improved disease management through the application of prevention and management protocols, funding was not allocated to address key underlying challenges in the sector, such as the ability to attract, recruit and retain health professionals, identified as a strategic action in the 2008-2020 SDP. The Ministry of Health and Social Services continues to have the highest level of vacancies across the civil service in Montserrat as of March 2022.

In line with the 2012 White Paper and the new UKG International Development Strategy (2022), the objective is to support OTs and SIDS transition out of financial aid and move towards graduation from ODA. To achieve this objective and improve sustainability and overall value for money for the programme, it will be important FCDO and GoM work together to ensure Montserrat has sound and evidence-based growth and sectoral strategies and that these are budgeted for and implemented.

For these strategies to be implemented and to see progress toward sustainable development, the FCDO and GoM will need to work collaboratively to set out the plan, the constituent programmes and the funding sources over time. This should occur in parallel to support provided via Financial Aid and the CIPREG programme. Whilst this may result in an uptick in upfront investments in the medium term, it would result in improved sustainability and VFM for the programme: as the island’s capacity to generate revenues grows, there will be a decrease in the need to provide financial aid. There is a risk that without the additional investment needed to get onto a positive growth trajectory, Montserrat will remain dependent upon UK assistance.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators. [1/2 – 1 page]

The theory of change (ToC) and corresponding outcome and impact indicators are unchanged from the original Business Case. Overall, the ToC is too ambitious and does not reflect the fact that with the current funding envelope for Financial Aid, there are significant limits to implement growth and sectoral strategies that would help the country move towards reduced dependency from UK aid. The ToC for the programme should be more realistic in terms of what it can achieve, which should be about bridging the funding gap to enable the provision of essential government services. To see progress towards sustainable economic and human development separate programme support is needed, including investment from the private sector, particularly to see the growth strategy implemented.

The complementary activities anticipated from the Governance and Institutional Development (GRID) programme did not materialise as the GRID programme was closed in 2021. CSSF programming continued to operate alongside other smaller pot of funding (i.e. Darwin +), but with a need to ensure all the ODA funding envelop aligns towards a jointly agreed updated Country Business Plan.

## C: Detailed Output Assessment [aim for max. 1 page per output. Repeat for each output]

Output Number and Title		Output 1. Management of public resources according to best Public Financial Management [PFM] and governance practice, which ensures Value for Money [VFM]
Output Score		B
Impact weighting (%)		25	Impact weighting revised since last AR?	No

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
1.1 Aggregate recurrent expenditure (PEFA 1.1) and domestic recurrent revenue (PEFA 3.1) out-turn compared to original approved budget	Score of A++ on both 1.1a and 1.1b = A++ / Score of A+ on both 1.1a and 1.1b = A+ / Score of A on both 1.1 a and 1,1b; or A+ and A on the two indicators = A / Score of B on any or both of the indicators = B / Score of C on any or both of the indicators = C		Score of A++ on both 1.1a and 1.1b = A++ / Score of A+ on both 1.1a and 1.1b = A+ / Score of A on both 1.1 a and 1,1b; or A+ and A on the two indicators = A / Score of B on any or both of the indicators = B / Score of C on any or both of the indicators = C	1.1 a: 98% - Recurrent Expenditure / Logframe Score = A++ / 1.1 b: 108% - Recurrent Revenue / Logframe Score = A / Total: A+
1.2 Composition of recurrent expenditure out-turn compared to approved budget (PEFA 2.1)	Less than 2.5% deviation over FY: A++ / Less than 5% deviation over FY: A+ / Less than 10% deviation over FY: A / Less than 15% deviation over FY: B / greater than or equal to 15% deviation over FY: C		Less than 2.5% deviation over FY: A++ / Less than 5% deviation over FY: A+ / Less than 10% deviation over FY: A / Less than 15% deviation over FY: B / greater than or equal to 15% deviation over FY: C	2.1 % of approved budget / Logframe score: / A++ / MoFEM is making adjustments to the way the deviation is calculated and this will be reflected in future logframe
1.3 Improve the Administration of Taxes on Montserrat	i) 2,000 personal taxpayers’ assessments done by electronic means / iii) establish baseline on No. of company and self-employed tax returns assessed through electronic system		Reinstate collaboration between UK HMRC and MCRS to address system issues to enable digitisation to complete. / Establish regular joint working group to discuss tax matters	Limited progress made since last annual review. Director General for Montserrat Customs and Revenue Service (MCRS), with support from FCDO, has re-established contact with UK HMRC for technical support / Progress on this to be closely monitored and supported. / Regular joint working group not yet established / C
1.4 Government of Montserrat's Monitoring and Evaluation Informs planning and policy making	By November 2019, GoM KPIs indicate benefits delivered to island anticipated in 2021/22 / By December 2019, GoM reports and publishes performance against national level KPIs for 2018/19.		By November 2021 GoM KPIs become a tool for citizens and policy makers in judging quality of delivery in 2020/21 / By December 2021, GoM reports and publishes performance against national level KPIs for 2020/21	Draft prioritized list of indicators for 22/23 selected- No submissions of KPI’s for MoH due to late submission of Strategic plan. / Did not meet the December 2021 deadline. Slow responses from Ministries re further data verification hampered the progress. Data verification conducted until way beyond the December deadline. / The NPR 2020/21 submitted for approval on 29th March 2022. Decision deferred for two weeks to allow for further review by Ministers and updates by M&E. Publication expected for June 2022. / B
1.5 Government of Montserrat delivers against procurement reform action plan	A procurement reform action plan is developed following Montserrat's MAPS assessment and is agreed with the Caribbean Development Bank		100% action plan commitments are delivered	All high priority targets except 6 have been met as of December 2021. This means that more than 80% of high priority targets have been met. / Most of the targets related to the Regulatory Legal Framework. / The next phase included the production of an Act followed by regulations. / This was a 3-year improvement plan so the target should have been March 2023 to have all recommendations completed. Target to finalise Act is by end of July, critical to see progress against procurement reform action plan. The procurement regulations need to be ready by Sept 2022. / B

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score. [1/2 page]

On output 1.1 and 1.2, GoM did well in relation to aggregate expenditure and revenue out-turn as well as on composition of recurrent expenditure out-turn compared to approved budget. One of the challenging areas on public financial management (PFM), is that current budgeting is on a cash accounting basis. Ministries and departments receive allocations against which they spend, but there is little scrutiny until the end of the financial year and when this results in under or overspend there is little consequence. Budget management at department level is mixed, from strong to poor. This has been identified as one of the key areas for reform to be implemented in 2022 as agreed by the Premier of Montserrat, the Governor and the FCDO (see recommendation section below).

Output 1.3 tracks improvements in the administration of taxes on Montserrat. There has been good progress toward the digitisation of the tax system, based on a collaboration between UK HMRC and Montserrat’s Customs and Revenue Service (MCRS). However, HMRC assistance to address issues encountered by MCRS with the electronic system has been slow, resulting in a drop in number of tax assessments completed using the system (803 at end of Q3). MCRS had requested support back in in September 2021 but due to delays on HMRC side a conversation on support needed only took place in February 2022. The Director General of MCRS has successfully re-established dialogue with HMRC and they are exploring how to resolve the known technical issues.

Output 1.4 is about Government of Montserrat's Monitoring and Evaluation informing planning and policy making. Whilst a prioritised list of performance indicators has been produced, there is insufficient evidence that progress against indicators is actively being used to inform planning and policymaking or as a tool for citizens to assess quality of service delivery. For example, evidence that actions have been taken as a result of missed milestones or targets. There are also questions about the relevance of the list of selected KPIs and whether these are tracking the most meaningful and helpful areas based on policymakers and citizen’s information needs. The target for the year was not met as the publication of performance against national level KPIs for 2021/22 was delayed. The M&E lead highlighted challenges in obtaining timely data from across ministries and in assessing quality and accuracy of evidence behind data reported.

Finally, output 1.5 measures progress against the delivery of the procurement reform action plan. During conversations with GoM stakeholders it was pointed out that the target should have been revised and extended to have all recommendations completed by March 2023. In line with the CDB-supported MAPS procurement reform programme for Caribbean territories, the plan is to finalise the Procurement Act by the end of July 2022, which is a critical step to see progress against the procurement reform action plan. The procurement regulations should be ready by September 2022.
[note] The list of reforms for 2022/24 has identified a number of actions that will need to be taken to strengthen the procurement function.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme [1-2 paragraphs]

Progress against the areas identified under this output would result in improved value for money, including in the delivery of public services. Delays in meeting some of the targets negatively affect VFM. The fact the digital system has not been fully functional means benefits from the system are not being fully realised, including full records security, inclusion of business tax records, revenue and efficiency benefits.

Over the course of the programme there have been challenges around the ability of GoM to conduct accurate forecasting, with the caveat that in 2020/21 this was impacted by the uncertainty caused by the pandemic. An agreed set of reforms for 2022/24 will play a key role in seeing continued improvements in budgeting and forecasting and will be monitored and championed by the Steering Committee.

Improvements in public procurement would result in considerable gains from a VFM perspective. It would reduce scope for fraud and corruption risks and provide assurance that due process is being followed. It would also strengthen transparency, accountability and governance as a whole, with positive spillover effects on employment, private sector growth and investment. This area has rightly been included in the list of reforms to be implemented in 2022/24.

Finally, fit for purpose KPIs would enable policymakers to take action as a result of delays and/or use the data to inform policy and plans. Citizens would be better equipped to assess VFM of public service being delivered. However, VFM is not being fully realised on this target given relevance and timeliness of publication of KPIs.

Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]

On public financial management, ministries need support to improve forecasting and spend management to ensure monitoring does not take place only towards the end of the financial year – the new FS has already instigated a MOFEM programme of support and scrutiny. At budget setting stage, growth strategies and sectoral plan should be fully integrated into a longer term and costed budget plan, with spending and resource allocation based on plans/strategies. Part of the budget would be funded via the Financial Aid programme but only to bridge gap between revenue and expenditure. Other sources of funding will need to be sought to cover expenditure needed to move towards a more sustainable growth pattern. At budget planning stage, GoM would benefit from additional support to fully move towards multi-year budgeting, which would avoid short term spending decisions and would enable GoM to better plan resource allocation and spend for each year of the multi-year budget. Technical support to transition out of cash base accounting has been identified as part of the reform package for 2022/24.

The M&E Unit is under-resourced and there are important challenges regarding data collection and the system for collating and storing data, which in most cases is based on a paper system. This makes the validation and verification process particularly difficult, increasing probability of errors. Whilst it is important FCDO monitors progress against KPIs, failure to address underlying challenges will result in production of KPIs that may not be fit for purpose and that are not adequately being reported against. Lack of scrutiny around quarterly performance on what has been achieved across ministries as far as the indicators presented in the logframe is apparent, with requests sent to GoM and the M&E unit to update the team on progress against indicators taking place well after the end of Q4.

Whilst MCRS has been proactive in seeking support from HMRC, FCDO has not played as much as of a coordinating and support function to ensure timely support be given to colleagues in MCRS.

Progress has been made against one of the recommendations put forward under this output in the 2020/21 annual review. The post of Financial Secretary has been substantially filled. However, recommendations 2 and 3 have not been actioned. These included a plan to be developed to achieve improvements in GoM’s KPIs (to be reflected in the Financial Aid’s programme logframe) and the need for KPIs to be more meaningful, simpler to understand and less input focused. The other recommendation was about the tax system; the need to resolve the technical hitch in the digitised tax system and to continue a collaborative and capacity-building relationship.

Recommendations

1. FCDO should continue to play an active role to facilitate cooperation between MCRS and HMRC. This is to be done through the Economics Adviser (to be appointed) and the Development Attaché. MCRS should obtains the necessary assistance to bring the system back to full operation.
2. GoM to revise national KPI list to ensure the indicators are meaningful and better inform policymakers and citizens of effectiveness and quality of services being delivered. This will require technical support to the M&E Unit to upskill Ministries on data collection and reporting and transition out of the current paper-based system. FCDO Development Attaché is seeking support from FCDO Statistics cadre and FCDO EQUALS programme, but programmatic support (i.e. CSSF) is likely to be required to build capacity and transition to digital system.
3. GoM should review resourcing within M&E. Clear accountability lines should be put in place to ensure data is being provided by ministries on a timely basis. Each Ministry should identify challenges encountered in collating data so that specific actions can be taken to address this.
4. Actions to strengthen PFM, budget planning and forecasting have already been identified as part of the reform list agreed to be implemented from 2022 to 2024. Important to monitor progress against this and ensuring growth strategies/sectoral plans are ready and then incorporated into a multi-year budget process.
5. Ensure key roles are filled within MOFEM.
  [note] There are 13 vacancies within MOFEM as of June 2022. See: InSync | Nominal Roll Archive.
How will you disseminate your learning and recommendations within FCDO, among programme stakeholders, and in the broader development community?

- Findings from this review will be shared with key FCDO and GoM stakeholders. For recommendations to be actioned by the FCDO, the delivery plan will identify leads for each action who will be responsible for taking the recommendations forward.
- Workshops with GoM and statistics/evaluation Adviser to review and update KPIs.

Output Number and Title		Output 2. Government services are delivered to meet human development needs, with a focus on the most vulnerable, including women, children, the elderly and disabled.
Output Score		B
Impact weighting (%)		35	Impact weighting revised since last AR?	No

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
2.1 Percentage of teachers with professional training and qualifications (QTS equivalent = Diploma) Primary and secondary and disaggregated by public and private schooling.	1. Primary 95%, Secondary 55% A** 2.Primary (90-94%), / Secondary (50-54%) A* 3.Primary (85%-89%), Secondary (45%-49%) A Data disaggregated by public and private schooling		1. Primary ≥95%, Secondary ≥ 85% Score A** / 2. Primary (85-94%), Secondary (75-84%) Score A* / 3. Primary (75-84%), Secondary (65-74%) Score A / Data disaggregated by public and private schools	73% - Overall trained teachers (Public and Primary) / 73% - Public Primary / 64% - Secondary / Source – Education Officer / B
2.2 Progress on development and implementation of health financing reform	(i) Final report submitted on Audit of Overseas referrals / (ii) Recruitment of Health Economist completed		1. Cabinet paper outlining option(s) for basic package of care and related health financing reform completed and submitted. The Cabinet Paper will also include the health financing implementation plan. / 2. Cabinet approves appropriate Health Financing options for Montserrat. / [PROVISIONAL]	Cabinet paper not yet submitted. / Performance reported during the period: / i) Updated Health Financing Roadmap and milestones and roles - Action plan Gantt Chart shared with Health Project Committee. / ii) Reviewed and summarized scope, next steps and previous related consultancies to inform next consultancy phasing of actions within financing action plan. / iii) Received a contact for Grenada National Health Insurance. Followed up with ECCB for technical assistance support. / iv) Stakeholder consultation with PAHO to determine the level of technical assistance that can be provided to the Ministry to advance the Health Financing Reform. / v) Initiated the process of reviewing the ToRs
2.3 Enhanced secondary prevention due to early detection and timely response to chronic conditions and their risk factors	(i) 160 persons reached with reports on: / 1) No. of males and females / 2) No. of new individuals reached and / 3) No. of persons "followed up" based on results / (ii) Protocol for adults with hyperglycaemia and screening reviewed and updated / (iii) Training commenced and a baseline established for the indicator / (iv) Establish a baseline for registered diabetics: / 1) No. of annual physicals completed and 2) No. of males and females / (v) Establish a baseline for registered hypertensive: / 1) No. of annual physicals completed and 2) No. of males and females / (vi) 20% improvement of baseline on number of children assessed as overweight [21%] / (vii) Review and update protocol for referral of children identified with unhealthy weight during school-health assessment / (vii) 90% of relevant Primary Health Care staff trained in the updated protocol [Established as baseline]		(i) 250 persons screened using the workplace policy disaggregated by M/F / (ii) #/% of persons identified with NCDs and referred to NCD clinics disaggregated by M/F / (iii)#/% who accessed NCD clinics (disaggregated by diabetes and hypertension specialist (>target 50%) / [PROVISIONAL]	(i)188 persons screened / M – 48 / F – 140 / GoM target was changed to: ‘screening conducted at 4 work places’ / ii) 51 persons identified with increased blood glucose / 35 – females / 16 – male / iii) 116/354 = 32.8% Hypertensive completed annual checks at NCD clinics / 92/228 = 40.4% completed annual checks at NCD clinics. / Emergence and subsequent re-emergence of COVID-19 coupled with staffing challenges resulted in reprioritised focus within the department. / B
2.4 Comprehensive range of social care service interventions that meet the needs of children	(i) 35 trained professionals / (ii) Inc in No. of referrals to social services / (iii) Establish baselines for: / - % of core assessments completed within 21 days / - No. of children and young people who are subjected to protection plans in the year / - % of protection plans over two years old / - No. of children in care longer than 6 months declining		50 professionals trained in safeguarding and child protection procedures.	54 - Professionals to include Teachers/Police were trained in Introduction to Safeguarding and Children – (28-MSS, 8- Look-Out Primary School, 9-Brades Primary School, & 9-Police). / 9 - Police Officers, new recruits were trained in Domestic Violence and Five (5) Nongovernmental persons in Cyberbullying, Child Protection. / A
2.5 Develop Social Services Policies and Legislation / A Social Protection Framework that takes into account a wider range of support systems and safety nets.	(i) ToRs for consultant to assist with review (to include integration of all existing Public Assistance Programmes) of the Social Protection Bill to be developed. / (ii) Engage with OECS and UNICEF about procurement and identifying a competent consultant. / (iii) Review of updated Older Persons Policy document by Senior Policy Makers / (iv) Finalise the policy document for Cabinet Approval		Social Protection Bill - To be implemented after August 2021 / National Policy for Older Persons: Training and Implementation and Monitoring of Implementation.	(i) The drafting of the Social Protection Policy commenced. / The Social Protection Procedure Operations / Manual was revised. / Training with the larger team (within Social Services) commenced / Staffing challenges / has delayed further / progress. Emergence and subsequent re-emergence of COVID-19 coupled with staffing challenges resulted in reprioritised focus within the department. / (ii) National Policy for Older Persons is not completed. Training and implementation on pursued over the period. / Progress as follows: - The National Policy on the Care of the Older Persons draft was reviewed and updated. Comments from external stakeholders were integrated into the document. Public consultation on the Policy took place during the month of December 2021. / The consultation process included 4 town hall meetings and radio interviews to sensitize the public. The feedback received was documented and presented to key stakeholders for comments. Preparation of final document for presentation to cabinet in new financial year. / B

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score. [1/2 page]

On output 2.1, performance was just below target to score an A. It has been challenging to receive data on percentage of teachers who gained relevant qualifications and data has not been subject to scrutiny. Some of the challenges highlighted during interviews with GoM stakeholders include difficulties in replacing teachers who retire, as well as to retain, recruit and incentivise teachers, primarily due to current salary levels.

Progress on output 2.2 on health financing reform has been slow. This has been explained in terms of lack of resources to take this work forward within GoM, but that the issue has now been addressed with the appointment of a Health Programme Manager. The position of Health Financing technical expert is currently in the pipeline, but GoM noted serious delays in advancing recruitment (HR Department). FCDO Health Adviser supported in the development of draft ToRs for Health Financing, which the Ministry of Health and Social Services (MoHSS) and MOFEM are to review and share with PAHO. An updated draft is expected by June 2022.

For output 2.3 on enhanced secondary prevention, data collection process continues to be challenging. Based on a paper system, nurses compile and report back on data, which is challenging given current number of nurses and the associated workload, especially since the onset of Covid-19. MoHSS explained that a licence agreement has been signed with the Canadian Health Systems Inc (CHS). The introduction of this new technology should enable the digitisation of existing medical records and create a new digital interface and records system for patient information across primary and secondary care facilities. Healthcare staff will be able to view and update patient records in real time, and the system will provide a new central data hub to inform future service planning and delivery, and health interventions.

Targets for output 2.5 were not met. A Social Protection Bill has not yet been implemented due to staffing issues within social services over the past year. The Social Welfare Act (2013) continues to be the main point of reference for the time being, but this is exclusionary as ‘non-Montserratians’ are not covered as part of the Act meaning that they do not qualify for social welfare support. National policy for older persons expected to go to Cabinet over the next month (July 2022).

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme [1-2 paragraphs]

OECS countries are experiencing difficulties in attracting and retaining qualified teachers to some critical subjects, resulting in no or lower qualified staff on occasion. To fully realise the VFM benefits of training teachers, it is important to assess whether salary and benefit package for teachers, including opportunities for career advancement are proportionate and competitive enough to retain, attract and incentivise teachers to perform to standards.
[note] For example, see a report by the World Bank here: World+Bank+OECS+Attracting+and+Retaining+Qualified+Teachers+in+the+OECS (1).pdf
It is critical to make progress on the health financing front, especially as work on the new hospital progresses. Work on health financing will help identify and cost basic packages of care and it will look at options for sustainable financing ensuring equity in access, including for the poor and vulnerable on island, as well as off island care and support. The decision process should include cost efficiency and cost effectiveness considerations.

MoHSS has been successful in attracting specialists and nursing staff from Cuba which provided a crucial boost not only for their COVID-19 preparedness/resilience building, but also for routine service provision at a time when the MoHSS carried numerous vacancies in its staffing establishment and various approved TC posts remained vacant. With the departure of the Cuban contingent, the FCDO-funded NHS staff from the UK provided some temporary support to cover some of the vacancies during an outbreak of COVID-19. It will be important to find solutions to ensure there is a pipeline of health workers that can be easily accessed, alongside drawing on TC funding so that key positions can be filled in a timely way. Again, from an equity perspective of VFM, ensuring salary levels are on a par with other jobs in the civil service and make it attractive enough for medical/nursing staff to come and work in Montserrat on a permanent basis is of critical importance, including for the sustainability of health service provision.

From an equity viewpoint, a draft Social Protection Bill should be prepared and presented to Cabinet as soon as possible to make sure all the people of Montserrat are included.

Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]

Recommendations

1. GoM to develop a workforce plan, based on an assessment of its workforce and determine what actions need to be taken to ensure future requirements are met. The recruitment strategy, inclusive of a retention package for education and health workers, should be developed based on the workforce plan.
2. With FCDO funding, the UK NHS has provided short term support through a limited number of doctors and nursing staff to Montserrat. The FCDO funded public programme, run by UKHSA, should be used to bring in specialist advice to help GoM draw up a recruitment and retention policy, but also to plan for a strategic workforce strategy for healthcare staff.
3. Draft Social Protection Bill to be expedited and presented to Cabinet.

Output Number and Title		Output 3. The recurrent budget establishes a supporting environment for private sector led, resilient growth
Output Score		B
Impact weighting (%)		10	Impact weighting revised since last AR?	N

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
3.1 Implementation of delivery plan of the Economic Growth Strategy	Commence recruitment of Investment Promotion Director and Chief Executive Officer after completion of election. / Advertise positions by Q4		GoM to set out their plans and timeline for the drafting of the new Sustainable Development Plan.	Targets set by the FCDO not ambitious enough. Economic growth strategy was not implemented, and SDP 2 years delayed. / Covid-19 partly affected progress against this output. / C
3.2 Implement expansion programme to provide information on other natural and man-made hazards/disasters including Tsunami	Establish Baselines: / - No. of community outreach activities held annually / - No. of information brochures produced and delivered island wide / - % of population reached by educational programme / - No. of website and face book visitors / - No. of educational radio spots aired per quarter		Increase on 2020/21 results in: / Percentage of staff trained in Disaster management related disciplines / No. of vulnerability assessment conducted, and maps /reports produced. / No of communities with hazard maps and mitigation plans	50% of staff trained in Disaster management disciplines as per Q1 of reports. / No vulnerability assessments conducted, and maps/reports produced. / Still awaiting data from the GIS Department and Statistics. There remain some challenges with equipment / Induction mapping for the West Coast (Rendezvous to Plymouth) completed for the National Tsunami Plan. / Ongoing rezoning of Zone V and environs in collaboration with the Montserrat Volcano Observatory (MVO) and the scientific Assessment Committee (SAC). / C
3.3 No. of young persons who have completed the training on the HYPE program	Establish a baseline		a) No/% of young persons who have completed the training on the HYPE programme (workplace awareness training) Target of 50 (100%) / (b) No/% of young persons who have gained employment within a year of completing the HYPE training Target of 15 (30%)	33 youths completed training / No person transitioned to permanent employment / B

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score. [1/2 page]

As per output statement, this output should be about establishing a supporting environment for private sector led, resilient growth. The only area that speaks to private sector growth in this section of the logframe is indicator 3.1 (see recommendations section below).

Output 3.1 has not been met. The Economic Growth Strategy drafted in 2018 and its associated delivery plan has not been implemented. The strategy identified economic drivers for the island and put forward recommendations to develop Montserrat’s industries and services that would inject spending into the national economy so the island could grow and gradually reduce its dependence on the UKG for recurrent expenditure. The delivery plan identified specific actions that Montserrat could take to move forward economically, but these were not factored in as part of Montserrat’s budget and no associated programme or resources were marshalled to see the recommendations implemented. The Sustainable Development Plan (SDP) for the island was due to be updated in 2020, but it is only now being developed. Many of the mid-term goals identified in the previous SDP (2008-2020) remained unbudgeted for and unimplemented.
[note] http://finance.gov.ms/wp-content/uploads/2018/12/Economic-Growth-Strategy-Delivery-Plan.pdf

On output 3.2, the milestone indicator changed from 2020/21 to 2021/22. Whilst the focus of 2021/21 was on DMCA’s expansion of the outreach programme, the targets for the last year of the programme revolved around training of staff in disaster management, conducting vulnerability assessments and developing hazard maps and mitigation plans. The target for this year aimed to see an increase on 2020/21 results, however it has not been possible to compare results from last year due to changes in targets. DMCA is eager to have conversations and advice from FCDO on targets to make sure those identified are a meaningful representation of DMCA’s work and priority objectives.

Finally, output 3.3 target has not been met. This should have been revised in light of the decision taken to reduce number of participants to the programme so that these could have a good enough basic salary. No participant transitioned to permanent employment as Government and the private sector were not able to absorb them. Interviews conducted also suggest the current design of the programme needs to be revisited. Currently funding is only for one year of the programme, but this should be longer term to make sure attendees receive sufficient training and that there is a clear plan for their absorption into the workforce. There is no clear alignment between the training being offered and the job market current and/or future needs.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme [1-2 paragraphs]

Central to the wider value for money justification for the Financial Aid programme is that Montserrat makes progress towards achieving inclusive economic growth so that in time the UK can reduce its share of financial aid allocations. However, this has not materialised since the aftermath of the volcanic crisis.

Economic progress has been slow, with no real diversification of the economy nor increased investments by the private sector for a quarter of the century. The implementation of the Economic Growth Strategy or similar is critical to see the island move forward. Based on the identification of key growth areas, this would need to translate into budgeted multi-year plans, with clear identification of potential funding sources to cover initial upfront costs. For example, if the objective is to increase private sector investment in the country, linked to specific industries, GoM in partnership with the FCDO, would need to assess existing barriers to investment and put in place a tailored action plan (appropriately funded) to make progress in this area. An example of ease of doing business is the level of corporate tax and a comparison with other small islands states and Overseas Territories’ models.
[note] In Martinique, for instance, a French OT, corporate tax is based on companies’ revenue out-turn, whilst those domiciled in France which pay corporate tax can recoup 100% of investments in the OTs as tax rebate, if they invest in new productive investments lasting at least five years in industry, fishing, hostelry business, tourism, new energy sources, and other areas deemed of relevance for the OT

Similarly, progress in tourism and the ability of the country to attract visitors, needs continued support in terms of technical expertise and know-how as well as resources to ensure the country can reach new markets and has a good offer for visitors. Progress on this front is unlikely without improved access to the island and an increase in inward investment. Going forward, it is critical the Tourism Division works closely with the Access team and that plans are joined up and appropriately costed and budgeted for.

The programme will not represent good value for money if development and sectoral strategies continue to be unimplemented and unbudgeted for. Financial Aid in this way is not likely to phase out and will continue to keep the island in current status, but with no real growth prospects.

If training programmes like HYPE are not being tailored based on an analysis of market present and/or future needs, there are questions as to whether these programmes do represent good value for money.

Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]

Recommendations

- Measures underpinning this output should be modified to reflect targets related to private sector led, resilient growth. Suggestions include tracking progress against selected areas identified in the Economic Growth Strategy; revenues generated from new private sector enterprises operating in the country; changes in regulatory environment to attract the right investments; expertise and know how needed to attract new investments and to represent the private sector (i.e. an active chamber of commerce, appropriate levels of corporate tax, recruiting experts in business development, etc.).
- Support GoM to identify barriers to private sector growth and action plan to address these. FCDO has reached out to the Department for International Trade in the UK and is seeking to get support.
- Ensuring training and vocational programmes are tailored to the need of the market or future needs of the country (i.e. agriculture, fisheries, etc.).
- Governor’s Office to work with DMCA to review KPIs they report against to make sure these are meaningful and a fair representation of what they are expected to deliver against. This could be included as part of the broader exercise on setting up updated GoM’s KPIs.

Output Number and Title		Output 4. Improved human resource capacity of the public sector
Output Score		B
Impact weighting (%)		15	Impact weighting revised since last AR?	N

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
4.1 Critical posts in the public sector filled and good management practices pursued	(i) TC offers of appointment made within 60-90 days from Advertisement as approved by GoM/DFID, and all newly appointed TCs receive logistical advice/guidance and information on Onboarding & Off boarding within 30 days of acceptance of appointment; / (ii) 360-degree evaluation conducted for all TCs and senior GoM managers as part of the Performance Management system. / (iii) % rating for achieved by all TC of agreed deliverables in accordance with Performance Management System. / (iv) Annual 360-degree evaluation must demonstrate that at least 90% of respondents report knowledge transfer, development of competencies and use of appropriate mentoring and coaching interventions.		TBC	Logframe target not agreed / Over the period under review there are Twenty-eight (28) officers in Post. Two (2) Officers (Tax Advisor and the Financial Secretary) were on-boarded during the period under review. / There are two (2) TC posts that are at the stage of re-advertisement, with one of these posts being advertised for a fourth time. / C
4.2 Delivery of a clear learning and development programme for the public service, including individual learning goals	(i) % of ACTS Awardees suitably employed in Montserrat annually. 2019/2020: 95%. / (ii) % of Public Officers completing L&D goals during the reporting year including formal and informal training and personal study. 2019/2020: 80%;		(i) % of ACTS Awardees suitably employed in Montserrat annually. 2021/22: 95% / (ii) % of Public Officers completing L&D goals during the reporting year including formal and informal training and personal study. 2021/2022: 90%	(i) 100% / Nine (9) awardees successfully completed their studies during this quarter. All have returned to Montserrat and have commenced working with the relevant Ministry/Department to which their degrees align. / (ii) Percentage not given. Unit need to find a way of collating the information. / B

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score. [1/2 page]

The Technical Cooperation (TC) programme is one of the ring-fenced budget lines of the financial aid programme. For financial year 2021/22, a total of $7,897,100 was approved for this and a total of $7.04 million of the allocated funds was spent by March 2022.

The programme provides specialist personnel, technical advice, targeted training, scholarship and research support. TC is provided where these needs cannot be fully met from local resources and human capacity. Personnel can include long or short-term specialists, consultants, individuals and teams.

There is an expectation that where TC support is provided to fill line positions, there should be a measurable element of knowledge and skills transfer to local staff (including any identified local counterpart) reflected in the ToRs and reported against on a regular basis. As set out in the TC Protocol (2018), ‘the local counterparts must be able to benefit from targeted learning and capacity-building under the TC programme, consistent with L&D priorities determined on an annual basis. This is critical as successors are identified and competencies built in order for efficiency in job performance and sustainability fostering economic growth and development for GoM’ (TC Protocol, 2018). However, knowledge transfer and identification of local counterparts to under-study TCs does not always take place, which negatively affects the sustainability of the programme.

Another important challenge is ensuring timely recruitment of TC roles. This was highlighted in previous reviews, but challenges persist. GoM through the HRMU have secured and signed off on a service level agreement with the NICO Agency to assist with the recruitment within the Health Sector as this has proven to be a challenge over the past years. GoM are utilizing some other OECS and CARICOM Regional Platforms to advertise and various social media platforms in addition to those platforms used by Human Resources Management Unit (HRMU).

The process to prioritise TCs to be recruited does not appear to be functioning effectively. Some Ministries are not aware of the status of the TC recruitment process and are not clear as to why the TC roles they put forward are not being prioritised. Whilst FCDO scrutiny has rightly focused on monitoring expenditure and timely recruitment of roles, less attention has been paid at the TC strategy and some of the systemic issues around ensuring sustainability of the programme, including knowledge transfer. The FCDO logframe did not include a target for this important output nor did GoM’s list of KPIs.

The Learning & Development Section of the HRMU is responsible for providing development interventions to ensure all employees across the organisation have the individual capability to deliver the requirements of their current or future jobs. Whilst Q4 reports from HR provide an overview of training accessed by employees, no percentage was available on public officers who have completed L&D goals during the reporting year.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme [1-2 paragraphs]

To represent VFM, timely recruitment, clear alignment of roles being prioritised and GoM’s needs and knowledge transfer and upskilling of local staff are paramount. This has not materialised during the lifetime of the programme. The continued existence of the TC programme is of critical importance given the limited resource pool in Montserrat and the need to fill in important gaps in the workforce. The challenges highlighted above, however, will need to be address if the full benefits of the programme are to be realised.

It is important that sufficient resources are allocated for L&D to make it attractive for staff to remain and work in Montserrat and to progress in their career. It will be important to get a better understanding of whether staff within GoM do have clear L&D objectives and resources are being allocated proportionately and efficiently to allow staff to grow and progress.

Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]

Recommendations

- Development Attaché in cooperation with the ODG is conducting a strategic review of the TC programme. Recommendations from this will be presented to the Governor, FCDO and relevant GoM stakeholders. Work is already under way to ensure streamlining of reporting on recruitment status from HR so that it is clear where we are with recruitment of TC roles. The strategy will also unpack specific challenges encountered with the recruitment process as well as prioritisation of TC positions. Actioning of recommendations will require close collaboration among Office of the Deputy Governor, Governor’s Office and the FCDO.
- New target and milestones need to be identified for the TC output as part of the new Financial Aid programme.
- HR reporting on L&D objectives on a percentage basis or agreement on alternative way to report on this so that it becomes possible to score output.

Output Number and Title		Output 5. Safe, reliable and regular access that provides good Value for Money [VFM]
Output Score		B
Impact weighting (%)		15	Impact weighting revised since last AR?	N

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
5.1 Number of ferry and airline passengers and reduction in average subsidy costs per air and ferry passenger	Increase in travellers / Reduction in average subsidy cost		GoM ensure Access plans remain within baseline subsidies. / Any new access decision and plans are within the Access Ringfence and do not create liabilities in future years either contractually or financially. / GoM’s targets / Based on budget allocated / No. of importers and exporters facilitated by the (ANU-MNI-ANU) cargo service. / Cargo cubic measurement / No. of passengers accessing subsidized airline tickets on MNI – ANU route	B
5.2 Implementation of Access Strategy	I)Access Strategy Implementation Plan finalised by Q3 19/20 / II) Fares and Concessions Policy finalised and approved by start of Q3 / III) Successful tender for 1-year ferry service - Q2, no gap in service / IV) High level plan for procurement/securing new vessel/potential twin otter set out by Q3 / V) Commence procurement (outreach, market research & scope) for new multi-year ferry contract and potential air solutions - Q4		Agreement between GoM and FCDO on a process and timeline for engagement and consultation related to medium- and longer-term access plans. All plans must ensure VFM and be subject to transparent decision making and procurement processes. / GoM’s targets / Approved Strategy rationalised and medium-term Implementation Plan developed / Framework Agreement developed and Strategy for air transportation agreed	B

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score. [1/2 page]

Passenger ferry operations were curtailed by GoM at the end of September 2020. The decision was taken by GoM based on the reduction in number of visitors as a result of the Covid-19 pandemic. It was also acknowledged that ferry operations were not running in the most cost-effective way, being subsidised by the Government rather than being based on an effective public private partnership (PPP model). As noted in last year’s annual review, due to the urgency of the decision making, contractual commitments and liabilities were overlooked. This resulted in significant costs rather than the anticipated savings in the access ringfence, which could not be realised.

A ring-fenced allocation of $5.4m had been allocated to access operations from 2016 to 2020. With the curtailing of ferry operations in September 2020, the assigned budget in 2021-22 was reduced by a factor of 66.67% to $1.8m, aligned with GoM plans.

Total passenger movement in 2021/22 of 4,322 is 88% less than pre-COVID-19 levels in 2019/20 of 36,474 and passenger movement by air in 2021/22 is 67% less than 2019-20 – see data in matrix below:

Total Passenger movement (inbound and outbound)
Mode	2019/20	2020-21	2021/22	2022-23 (Apr-June)
Air	13,159	2,426	4,322	2,470
Sea	23,315	6	0	0
Total	36,474	2,432	4,322	2,470

By the end of end of quarter 4 and at the time of writing this review, no progress had been made on taking actions to reinstate the ferry, which is essential to ensure travellers’ and residents have access to other islands and to complement the air access, which is somewhat limited due to the small carrier (8-seater Islander). A suitable ferry would also enable the transport of small cargo, needed to transport more goods to the island and augment commerce opportunities. Cargo is currently limited to a fortnight service, which results in higher costs and limits availability of products on island. Funding would need to be allocated to allow the ferry service to re-start as well as drafting a PPP and test the market to have a more financially viable option to sustain the service. Ferry operations were previously being subsidized in the order of 66%.
[note] The 2019-20 operational costs for access, including the passenger ferry operations is as follows: expenditure of $9,622,359 and revenue of $3,250,049 or net operating costs of $6,372,310.

In 2021/22, the Access team focused on engaging the market to pre-qualify ferry operators, so that services could be drawn-down, on a needs basis. One ferry operator was pre-qualified in the three-year Framework Agreement in October 2021. However, with an assigned budget of $1.8m, the Access Division explained that it was not possible to call-down on ferry services and the passenger movement level did not warrant this due to the impact of Covid-19.
[note] In 2020, the Access Division developed a cost-benefits analysis for passenger ferry operation.

The current Access Strategy prioritises the introduction of Twin Otter aircraft over the ferry. However, there are still discussions between FCDO and GoM around feasibility of introducing the Twin Otter and a decision has not been taken on this at the time of the review. The Access Division has produced several papers highlighting why the introduction of the Twin Otter would benefit the island, citing possibility of new routes (currently only connection is to Antigua), economies of scale, possibility of inter-line agreements and access to global airline ticketing distribution systems, amongst others. The papers produced by the Access Division with professional input from Trade, Airport and Tourism Divisions, emphasise the benefits of having a blend of transportation modalities via air and sea.
[note] This Air and Sea Access & Strategy was approved by Cabinet in May 2019. This specified a passenger ferry service for sea and twin-otter operations for air. The implementation plan outlines a phased roll-out of this Strategy, based on (a) projected timeline for passenger movements to return to normalcy (2019-20 levels), (b) costs of implementation vis-a-vis assigned budget and (c) lead-time for mobilization of transportation equipment.
[note] A recent tender exercise for a Twin Otter service was unsuccessful, with no bidders that currently have the Twin Otter operational submitting an application.
[note] Islander (8-seater), Twin-otter (19-seater) and passenger ferry – capacity of 200+. In particular, the Islander performing on the nearby routes (Antigua, Nevis, Guadeloupe), Twin-otter (Antigua, St Kitts & Nevis and St Maarten). The focus on twin-otter is based on the stage of implementation of the Strategy. Passenger movements for the first quarter in 2022-23 equals the total movements in 2020-21, hence the introduction of additional airlift capacity to cater to increased demand. The Travel Survey of November 2021 provided empirical indication with 76.4% of the local and 87.6% of the international respondents specifying that they would travel in 2022.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme [1-2 paragraphs]

Having adequate access to the island would represent VFM gains for Montserrat, provided this adopts an efficient and cost-effective PPP model. Ease of access is one of the central areas that private businesses and investors look at when deciding where to do business. At the same time, it is paramount that new ferry and airline agreements are based on smart strategies and sound PPPs to ensure the service is efficient and sustainable. The access strategy will need to strike a trade-off between costs and returns to be had by increase in visitors and investments, including options to expand access to other islands. Currently, Montserrat is only accessible via Antigua, which somewhat may discourage visitors to travel to the island and limits opportunities for residents. Decisions on access will also need to be developed in close cooperation with Montserrat’s Tourism Division and with inputs from the private sector to ensure marketing strategies increase potential number of visitors and maximise return on investments made on access. In terms of the Financial Aid programme, it is imperative to maintain access to and from Montserrat for citizens.

Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]

Recommendations

- GoM has an access Strategy, including a five-year plan presented to the FAM in December 2021. GoM/Access Division to work with the Governor’s Office and FCDO to implement agreed upon access strategy that meets the needs of the people of Montserrat. This should be ambitious and include opportunities for economic growth.
  [note] Informed by stakeholders’ engagement and travel survey results.
- If the plan is to reinstate the ferry, a more cost-effective model should be considered based on a PPP. The latter should drive down costs whilst making the service more efficient. Consider other routes to expand access to other islands and/or partnerships with other islands like Guadeloupe who may use own ferry to bring tourists at no cost for Montserrat.
- GoM to analyse the private sector’s capability to provide air services and set out evidence-based air services strategy. As part of this GoM to review recent barriers to securing a twin Otter service, consider the feasibility of alternatives, and revisit current model and subsidies to FlyMontserrat and SVG air.
- Access Team to continue to work with FCDO, Tourism, Airlines, ferry operators and other key stakeholders. Existing working groups, including with Tourism, should be complemented by monthly meetings between FCDO Development Attaché/relevant FDCO officers and the Access Division.

D: Risk [½ - 2 pages]

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance. [1/2 page]

The Financial Aid programme has a specific risk register, which was last updated in September 2021. This is not in line with good programme management practice, which would require risks to be discussed and updated at least on a quarterly basis. Resource constraints in FCDO have contributed to this, although there will shortly be a fully staffed FCDO team in place.

The current register identifies a number of risks relating to public service delivery and operations, fiduciary risks, policy and programme delivery and safeguarding risks.

Whilst the risk register captures a breadth of programmatic risks, the register should be updated more regularly (at least on a quarterly basis), to capture live risk to the programme. This should include challenges under the TC programme, any delays in meeting logframe targets, as well as other key risks that are relevant to the programme. To improve risk identification and management, in addition to regular conversations on risks, it would be helpful to refine some of the risks so that these could be more specific (i.e. instead of reference to ‘materialisation of fiscal risks’ explicitly set out the most challenging areas) and mitigating actions could include specific timeline for their completion to reduce risk exposure.
[note] Staff shortages in OTD has impacted on the frequency of formal reviews, but recent successful recruit will see a boost in numbers of staff working on the programme.

Recommendations:

- Risks to be included as standing agenda items at monthly FCDO Financial Aid programme meetings. The risk register should be reviewed formally on a quarterly basis at a minimum.
- Review and update risk register in light of recommendations from the PCR.

E: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency. [1 page]

GoM submits monthly financial reports to FCDO, while Ministries submit reports on their KPIs on a quarterly basis. Quality and timeliness of reporting from across Ministries can be enhanced. There have been delays in collating information and progress against KPIs from across Ministries and the M&E Unit has highlighted challenges in receiving timely information from across Ministries. As pointed out above, KPIs against which Ministries report against on a quarterly basis will need to be updated so that these are meaningful and are tracking the correct areas.

Dialogue with GoM has been continuous. At post, with the arrival of the replacement Development Attaché, there has been an opportunity to streamline meetings, ensuring attendance from post when most suitable whilst keeping hybrid meetings for those that require input and attendance from UK-based colleagues. Meetings on reforms and TCs are now led from post to minimise use of resources from the centre and maximise opportunity of having Development representative at post who then reports back to the FCDO.

There are monthly Steering Committee meetings with senior GoM stakeholders, including the Premier of Montserrat, Ministers and Senior FCDO and GoM civil servants. At a working level, monthly meetings with the Financial Secretary/MOFEM to discuss budget (in line with MOU reporting requirements) and with the Office of the Deputy Governor on progress with TCs and with the Access Division. There have also been regular conversations amongst FCDO Advisers and relevant PS/Ministries at the technical level.

Programme-level approach to monitoring and evaluation [1/2 page]

There have been regular conversations between the programme PRO and the Financial Secretary. Going forward, the Financial Aid programme will be based on collective responsibility, with the Governor’s Office, GoM and FCDO working together for the future of Montserrat. This will include regular working level meetings with Deputy Financial Secretary, the Development Attaché and Financial Aid Programme Manager. This will be an important opportunity to formally assess progress against targets, risks, updates on ringfenced areas, etc. These should be standing agenda items each month. A mid-year review will be introduced for the 2022/23 Financial Aid programme. Steering committees will take place at least every quarter, with ad-hoc meetings in addition, as required.
[note] Monthly meetings will resume in July, with the Development Attaché and newly recruited Economist and Deputy Programme Manager (UKB) also joining the meetings.
[note] Due to vacancies, there has been primarily a bilateral dialogue between PRO and SRO.

Development Attaché will play a key role in having conversations on the ground and ensuring progress is being made and that risks are being escalated if outside of risk appetite.

Date of last narrative financial report	24/05/2022	Date of last audited annual statement	July 2021 (for 2019/20 Acct)