Accountable Grant Amendment Letter 9

Project Name: Emergency Preparedness and Response in South Sudan – HARISS Programme
Project Number: 204019-126 and 204019-141
Purchase Order: 40099640

I refer to the Accountable Grant between the Government of the United Kingdom of Great Britain and Northern Ireland acting through the Foreign Commonwealth and Development Office (“FCDO”) and Medair signed on 26 July 2016 and 20 June 2017, Amendment 1 signed on 27 June 2018, Amendment 2 signed on 23 October 2018, Amendment 3 signed on 9 September 2019, Amendment 4 signed on 10 March 2020, Amendment 5 signed on 21 December 2020, Amendment 6 signed on 31 March 2021, Amendment 7 signed on 28 June 2021 and Amendment Letter 8 signed on 31 March 2022.

Following recent correspondence, FCDO proposes to increase the amount made available to Medair by £2,500,000 (Two Million, Five Hundred Thousand pounds sterling).

I propose that the figures and words “£21,994,501 (Twenty-one million, Nine hundred and Ninety-four thousand, five-hundred and One-pound sterling)” in paragraph 3 of Amendment Letter 8, 2022 be deleted and replaced with the figures and words £3,350,000 (Three Million, Three Hundred and Fifty Thousand) pound sterling.

I also propose that the end date of “June 2021” in paragraph 4 of Amendment 8, 2022 be deleted and replaced with “31 March 2023”.

I also propose that the financial year allocation and payment schedule at paragraph 5 of Amendment 8, 2022 be deleted and replaced with the following financial year allocation and payment schedule:

FCDO financial year	Annual allocation
2016/17	£1,407,254
2017/18	£1,979,492
2018/19	£3,216,731
2019/20 / 2020/21 / 2021/22 / 2022/23	£5,643,866 / £4,897,158 / £4,850,000 / £ 3,350,000

Quarter	Payment due date	GBP amount
July – September 2016	November 2016	£1,407,254
October – December 2016	February 2017
January – March 2017	May 2017
April – June 2017	August 2017	£1,979,492
July – September 2017	November 2017
October – December 2017	February 2018
January – March 2018	May 2018
April – June 2018	August 2018	£3,216,731
July – September 2018	November 2018
October – December 2018	February 2019
January – March 2019	May 2019
April – June 2019	August 2019	£5,643,866
July – September 2019	November 2019
October – December 2019	February 2020
January – March 2020	May 2020
April – June 2020	August 2020	£4,897,158
July – September 2020	November 2020
October – December 2020	February 2021
January – March 2021	May 2021
April – June 2021	August 2021	£1,000,000
Jul – Sep 2021	November 2021	£ 3,000,000
Oct – Dec 2021	February 2021
Jan – Mar 2022	May 2022
April – June 2022	July 2022	£850,000
July – September 2022		£2,500,000
Oct - Dec 2022
Jan – March 2023
TOTAL		£ 24,494,501

This letter of amendment will place on record our common understanding of the above changes and will come into operation on the date you sign the confirmation below. This note will be known as Amendment No. 9/2022.

Please sign both copies of this letter; return one to me and retain the other for your own records.

Signed on behalf of FCDO:
Name:
Position:
Address/Contact Details:
Date:

Signed on behalf of the Partner:
Name:
Position:
Address/Contact Details:
Date: