ADDENDUM TO BUSINESS CASE

SUMMARY INFORMATION
Project Name	Building Resilience through Asset Creation and Enhancement (BRACE) II
Country or region targeted	South Sudan
Type of amendment	Cost and time extension – bridge funding
Original project budget	£20,000,000 since extended to up to £39,600,000 (100% ICF)
New project budget	Up to £54,600,000 (100% ICF) / (up to £15m additional)
Original project start and end dates	01/08/2015 – 31/03/2018, since extended to 31/12/2021
New project end date (if applicable)	31/09/2023
Business Case Vault Document No.	5275355

INFORMATION
What is the project’s purpose?
Building Resilience through Asset Creation and Enhancement (BRACE II) is DFID South Sudan’s flagship resilience and international climate finance project. This extension maintains delivery of resilience building work during a period of global uncertainty, and bridges the transition to a proposed multi-year humanitarian and resilience programme. / The programme is centred around four main objectives: / Address immediate food insecurity and basic needs (provision of conditional cash assistance) / Improve longer-term food security (support for agro-pastoral production) / Increase capacity to absorb, anticipate and adapt to climate variability and extremes (support climate change adaptation) / Improve community relationships and social cohesion / Improving food security is critical to reducing the need for humanitarian assistance. South Sudan’s food security crisis continues unchecked, with 6.5m (55%) of the population facing crisis or worse levels of food insecurity in June 2020. This crisis is not only caused by conflict and insecurity but also by the economic crisis that has eroded households’ purchasing power. It is further exacerbated by localised climate shocks as flooding, heavy rains or drought, such as the floods in late 2019 which affected nearly £1m people and were the worst for 30 years. / BRACE II uses a ‘Cash/Food for Assets’ approach in which vulnerable households receive food assistance under the condition that they work on the creation or rehabilitation of ‘assets’, such as anti-flooding dykes, clearing new farm land, water ponds, etc. This approach has double benefits: the food assistance immediately relieves food insecurity while the creation or rehabilitation of assets makes households less vulnerable to climate shocks and helps them produce their own food. Complementary activities are also implemented to improve agricultural practices, access inputs and increase skills and awareness on key areas. Furthermore, communities decide together which assets they would like to create and then work together to create or improve them, helping to build community cohesion. / BRACE II is key part of DFID South Sudan’s strategy of balancing our emergency humanitarian support with interventions that build self-reliance where access and security allows. This also reduces dependence on aid in the longer-term. A key objective of this programme is to increase resilience to climate extremes and funding for this programme is 100% International Climate Finance (ICF). / BRACE II currently comprises 3 components: / A first component delivered by the UN World Food Programme and UN Food and Agriculture Organisation in partnership in former Northern Bahr-el-Ghazal and Warrap. / A second component delivered by an NGO consortium led by World Vision Australia in former Northern Bahr el Ghazal, Warrap and Eastern Equatoria, started in early 2018. / A component for monitoring, evaluation and learning activities. The contract with the previous external supplier expired in July 2019: third-party monitoring (TPM) has been incorporated into the contract for TPM on DFID South Sudan’s humanitarian project HARISS, and a final evaluation will be procured in line with DFID procedures as part of this extension.
What is the objective of the amendment?
The objective of this extension is to continue the work of BRACE II and bridge the transition to a single humanitarian and resilience programme. Resilience-building is also a key approach to helping tackle the secondary impacts of COVID-19, which is having devastating economic and livelihoods impacts on a country already living hand-to-mouth on a daily basis. / The original business case was approved by Ministers for five years, with an initial tranche of £20m for the first two and half years of the programme, and an additional £12.6m for the following 2.5 years. This was further extended in January 2020 by £7m to Dec 2021, to consolidate the previous support UN and NGO components, support the development of South Sudan’s fledgling ‘Partnership for Recovery and Resilience’, strengthen our approach to climate adaptation and natural resource management through the COP 26 period, and allow time for a final evaluation following activity completion. / An extension of funding up to £54.6m through to September 2023 would allow DFID South Sudan to: / Continue DFID South Sudan’s contributions to the International Climate Finance (ICF) commitments ahead of COP 26 in Nov 2021. A review of climate and resilience work across DfID South Sudan in 2019 recommended enhancing climate information services and community based natural resource management. Whilst BRACE II already has climate adaptation as a core objective, there is an opportunity to further consolidate and scale effective practices to meet the ambition set out under the climate and natural resources shift of the strategic approach to Africa. For example, severe flooding in late 2019 demonstrated the need to further help communities anticipate weather related shocks, as well adapt to them. / Extend support to the UN component for an additional two years, reaching over 56,000 people with a package of multiyear cash transfers, training, and further strengthening climate adaptation and natural resource management activities across partners. / Extend the NGO component by supporting an estimated additional 56,000 people over two years, including an additional location if stability allows. The original business case envisaged that the programme would continue operations from BRACE I in Western Bahr el Ghazal, Northern Bahr el Ghazal and Warrap and extend into two new states (Lakes State and Eastern Equatoria). Disruption to the procurement of the NGO led component by the July 2016 crisis and the need for a more flexible geographic remit has led to the current footprint in former Northern Bahr el Ghazal, Warrap, and Eastern Equatoria. This extension offers the opportunity for the NGO component to build on their track record, adapt their package based on learning so far and extend to a new location if stability and funding levels allow. Given shifting contextual dynamics since the original business case, this new location would likely be in Greater Upper Nile. / Support and shape coordination of resilience activities in South Sudan by providing the option to support representation and coordination for the Partnership for Recovery and Resilience (PfRR). Aweil is one of the lead candidate partnership areas under the PfRR, established in 2018 to help development stakeholders work together to reduce vulnerabilities and build resilient households, and has been badly affected by floods in 2019 and market shocks related to the secondary impacts of COVID-19. Supporting a ‘green recovery’ from COVID-19 could include testing and improving approaches to conditional transfers in BRACE II which support natural resource management, and could be shared with other partners investing in similar approaches such as the World Bank. / Invest in a review and final evaluation of the BRACE II programme, building on the mid-term evaluation at the end of 2018.
What is the additional and total support the UK will provide?
The UK will provide up to an additional £15m to deliver this programme, bringing the maximum total programme value to up to £54.6m. This means an indicative split as follows: / Comp-onent Implementing partner Activity delivered Phase 1 budget / (Sep 2015 – Dec 2017) Phase 2 budget / (Jan 2018 – March 2021) Phase 3 extension / (March 2021- July 2023) Total / 1 / (UN) WFP Food assistance / (Food/cash for Assets) £12,300,000 £15,600,000 £8,800,000 36,700,000 / FAO Agricultural and Natural Resource Management training and farming inputs / 2 / (INGO) World Vision Australia Cash for assets and livelihoods assistance (training, inputs etc.) £7,000,000 / [not spent] £10,800,000 [£7m brought forward from phase 1] £6,000,000 16,800,000 / Independent monitoring and evaluation £700,000 £200,000 £200,000 1,100,000 / TOTAL Budget: / £20,000,000 / [£7m rolled forward to phase 2] Budget: / £19,600,000 [£3m not spent due to restricted office budget] Budget: / £15,000,000 / [plus £3m rolled forward from phase 2] Total: £54.6m / The table above assumes the full value of the extension is available as part of the office budget. If less funding is available then reductions would be made to partner allocations based on value for money evidence, availability of funding from other donors/ sources and where DFID can use its strategic influence to maximise impact. Both components are performing very well. / At a budget level of less than £5m per year this programme would struggle to demonstrate value for money within its current structure as it is based on the premise of working at relative scale in communities to build resilience and social cohesion. DFID South Sudan envisages being able to allocate this amount at an absolute minimum through prioritisation within even a reduced office budget.
What are the expected results?
Both components are performing very well and have been able to adapt and continue their work throughout the COVID-19 outbreak so far, meeting the needs of highly vulnerable market dependent communities and helping bolster the food security of families facing multiple shocks from flooding, COVID-19, and potentially devastating desert locust infestation. As the Embassy’s flagship climate finance programme, this extension offers opportunities to demonstrate the UK's commitment to climate adaptation in the run up to COP 26. / The original business case stated that BRACE II would provide assistance for up to 400,000 people over 2.5 years, representing a cost per beneficiary of £50. Those initial results assumed that each beneficiary would be supported for only one year. Building resilience, however, takes time, and, based on the lessons learned from BRACE I, it was agreed that BRACE II would provide multi-year assistance to the same households. The phase 2 addendum to the business case envisaged a cost-per-beneficiary-per-year of £45, with beneficiaries under component one (UN) being reached for 3 years and component two (NGO) for 2 years to enable a comparison of different support packages. Cost per beneficiary per year estimates across the programme haves varied between £49 and £53 in 2017-201920; the latest figures (Jan 2020) estimate BRACE II to have a cost per beneficiary per year as £51.90. / This extension intends to support both the UN and NGO components for an additional 2 years, allowing both partners to take on new cohorts of beneficiaries, with the majority of support being transferred to beneficiaries as cash by December 2021. If the full value of the cost-extension is available, it is expected that this extension would enable at least a further 112,000 people to be reached. All of these results would count towards DFID’s ICF targets.
What is the approach to implementation?
Testing different delivery models/approaches to enhance adaptive programming / As originally intended in the Business Case, DFID have tested two approaches in order to compare and adapt our delivery model. Different support packages and approaches have been tested in the NGO led component since it started work in early 2018, for example on the promotion of savings groups. This process has also helped DFID to identify the added value and unique selling points of different types of implementing partners (WFP, FAO, INGOs, NNGOs). Further adaptation of the approach will be tested through this extension based on learning from the mid-term evaluation, for example by considering a wider set of rural livelihood opportunities. A light touch review in 2021 and a final evaluation planned for 2022 will allow the strengths and weaknesses of the operational models and interventions to be assessed, with learning fed into ongoing and successor programming. / Value for Money / The BRACE II business case said that value for money would be tracked by looking at key unit costs such as the cost of delivering cash transfers, including a comparison between the two delivery mechanisms (UN-led and NGO led). All partners have developed a matrix of indicators to monitor value for money and a tracker to monitor cash transfers and asset creation. The highest costs under BRACE II are cash transfers and staff, reflecting a programme model focused on cash transfers and skills building. / There are some areas that the business case did not envisage, however, including high annual inflation rates, an increasing spread/difference between the official and parallel exchange rate in South Sudan and a loss of value of GBP sterling against the US dollar. UK funds are paid in instalments to BRACE II partners in GBP, who then exchange these funds into USD to pay for some programme inputs, staff and equipment. A further exchange from USD to South Sudanese Pounds is then made for cash transfers and programme costs. This has meant UN partners in particular (the NGO component only began in 2018) have had significantly less budget available to them in USD than was assumed at the programme outset. / Key focuses of a VFM approach include the following: / Economy: WFP and FAO began multi-year agreements with downstream partners in 2019. While it is still too early to be able to quantify any efficiency savings, there are indications that this has led to reduced staff turnover and positive feedback has been received from tier two partners. / Efficiency: A comparison of costs to transfer food and cash demonstrates the efficiency of cash as a delivery modality. In 2019, WFP reported that it would cost $16m (290%) to transfer $5.5m worth of food to people due to the high costs of moving food in South Sudan. To transfer the same value in cash cost $1.83m (33%), demonstrating the continued efficiency of cash where markets are functioning. / Effectiveness: Improved timeliness of cash transfers and agricultural inputs, as the importance of their reaching households ahead of planting and the lean season (so as to be effective in meeting immediate needs and reducing food insecurity) was realised. / Equity: BRACE II targets households that are vulnerable but able to participate in a labour-based programme. The number of people who meet the vulnerability criteria in project areas far outweighs the number who can be supported, but BRACE II partners work with communities to define the determinants of vulnerability and validate the selection of those that participate. Common criteria are poor or very poor female-headed households, households with chronically ill or disabled family member or somebody recently discharged from a nutrition centre, households who do not own productive assets or livestock and rely on casual daily labour for income. Third party monitoring, partner reporting and other learning sources continue to show that BRACE II is reaching the people it is meant to on this basis. / Risk Management / BRACE II’s risk rating is ‘major’ downgraded from ‘severe’ in 2018, reflecting continued delivery in a challenging operating environment. The signing of the revitalised peace agreement R-ARCSS in September 2018 has led to a reduction in politically driven conflict, however, intercommunal violence and insecurity has continued, economic indicators have worsened, and climate risks have materialised. / DFID South Sudan manages risk on this programme closely with all implementing partners, maintaining a risk register which is comprehensively updated each quarter and more often if appropriate. DFID’s Internal Audit Department’s (IAD) recent review of DFID South Sudan’s application of its risk and control framework classified the office as having a mature level of control awareness[[1]] with ‘a high level of risk awareness with consciously developed frameworks and suitable oversight and governance over their implementation.’ / Cross-cutting issues / Climate-sensitivity: Climate adaptation is central to BRACE II, with the mid-term evaluation finding that an estimated 43% of BRACE II beneficiaries have improved climate resilience, and another 67% could be considered shock-proofed, (i.e. better able to manage a climate shock). Severe flooding in late 2019 demonstrated the need to redouble efforts to help people anticipate, absorb and adapt to climate shocks. This will be strengthened through this extension, learning from the central BRACED programme which ended in 2018, the ongoing WISER regional programme as well as other partners. / Gender Equality: The original business case included a gender equality statement and BRACE II has made a deliberate effort to target women and adapt the programme to their needs, for example by starting activities later in the day so women are able to attend after household work, as well as promoting gender equality in programme structures. We will continue to look for ways to gender inform programme activities, conducting more disaggregated analysis of the results and reviewing how gender sensitivity can be incorporated within every aspect of the programme. / Conflict-sensitivity: BRACE II aims to promote social cohesion and reduce the likelihood of communal conflict through community-based planning and governance structures, shared work and management of natural resources and infrastructure. As defined in the business case, implementing partners will continue work to understand: i) the context; ii) the interactions between this programme and the context; and iii) how the programme can address causes of conflict and avoid negative impacts. WFP has an ongoing partnership with the Conflict Sensitivity Resource Facility (CSRF) to document existing good practice in conflict sensitivity, work on an action plan and produce assessment frameworks (e.g. for conflict sensitivity in development of feeder roads and other infrastructural development). Good practice related to BRACE II activities will be shared with other partners in this extension period. / Nutrition: In August 2019 all counties where BRACE II is being implemented were in a serious or critical situation on the IPC for Acute Malnutrition scale. The second phase of BRACE II increased its focus on nutrition based on the increasing amount of evidence linking malnutrition to chronic food security in South Sudan, and this will be continued in the extension. In practical terms this involves including nutrition messages within skills development activities, and ensuring that the project prioritises activities that more directly contribute to nutrition outcomes, for example vegetable production. / Terrorism Act: The risk of terrorism is assessed to be low in South Sudan, as is the risk of programme funds being diverted to fund terrorist activities.
Describe any key changes to the original business case including the theory of change or new evidence from ongoing monitoring, evaluation or learning work?
The theory of change and logframe for the BRACE II programme has evolved since the original business case to reflect our increased understanding and the changing context and to reflect both intermediate and final outcomes. The mid-term evaluation conducted in late 2018 demonstrated progress towards these outcomes as well as recommendations for adaptation which are being considered as part of this extension. / There are two changes to the original business case in the extension of this programme: / Geographic locations of the programme: The original business case pre-identified five former states in which BRACE II would be implemented. This decision was taken when the conflict was mainly concentrated in the three states of Greater Upper Nile. The situation has changed significantly since 2016 when conflict spread to different parts of the country. BRACE II is currently being implemented in three of the former states, with this extension providing the option to extend into new locations based on thorough analysis of need and stability in the short to medium term. / Support for the Partnership for Recovery and Resilience (PfRR): The original business case envisaged a steering committee and technical committee to ensure that the project aligns with local plans, other programmes and includes learning and feedback. State level representation and regular meetings have been a challenge however, and so coordination has been focused at the project level. The creation of the Partnership for Recovery and Resilience in 2018 has provided a platform for UN agencies, NGOs, donors, Government representatives and civil society to work together, supporting a shift away from humanitarian response to locally owned recovery and resilience building in key areas. The activities under BRACE II are well aligned to the pillars and principles of the PfRR, with the UN component providing a practical demonstration of partnership working. National and area-based coordination frameworks are being developed and this extension provides for existing BRACE II partners to be more actively involved in these structures. This is expected to deliver better coordination of programmes at local level, stronger monitoring and learning processes across all agencies and better alignment to local plans and household priorities.
[note] South Sudan Humanitarian Snapshot, OCHA, June 2020.
[note] This single programme was intended to start in early 2021. Due to the wider global and UK political situation, development of this programme has been delayed for 2 years.
[note] The procurement for the second component was launched in late 2015 but received no suitable bids. The process was then put on-hold following the drawdown of the British Embassy in July 2016 and later terminated. It was relaunched in 2017 and the successful partner began activities in 2018.
[note] Some activities are planning to take place between March- July 2021 under the phase 2 extension
[note] These are indicative amounts, tbc pending confirmation of FY 20/21 budget reductions.
[note] To note the model of support provided differs in content and extent as well as length; the UN model is consequently more expensive than the NGO model, hence the similar numbers of beneficiaries reached for differing amounts of money, but has the potential to built resilience to a higher degree. The final evaluation aims to explore these different approaches and assess the costs/benefits of each.
[note] If the economic context/ market functionality deteriorates significantly, food may be provided instead of cash.
[[1]] DFID IAD (2018), Assurance Review of DFID South Sudan (follow-up), 27th July 2018, assurance year 2018/19 (unpublished).
[note] http://www.ipcinfo.org/fileadmin/user_upload/ipcinfo/docs/IPC_South%20Sudan_Key_Messages_August_2019.pdf