 Programme Completion Review

Title: FCDO membership to OECD Development Centre in 2019, 2020 and 2021
Final Programme Spend £ (full life): £1,996,044	Review Date:	21/03/22
Programme Code: 300260	Start Date: 14/03/19	End Date: / 31/12/21

Summary of Programme Performance

Year	2019	2020	2021
Programme Score	A	A	B
Residual Risk Exposure Rating	Moderate	Moderate	Moderate

DevTracker Link to Business Case (and any addendum):	https://iati.fcdo.gov.uk/iati_documents/46439762.odt
DevTracker Links to all logframes used during programme lifetime:

A. Summary and Overview

Description of the programme and what it has achieved

The OECD Development Centre (DEV) is a forum to enable OECD and OECD partner countries to share their experience of economic and social development policies, and to help policy makers find innovative solutions to the challenges of development, poverty alleviation and inequality. DEV aims to contribute expert analysis to the international development policy debate with the objective to help decision makers find policy solutions to stimulate growth and improve living conditions in developing and emerging economies.  Expected results of this programme were for the UK and other members to have an improved understanding of the binding constraints affecting developing countries’ economic growth and well-being and of the policy choices available to address them. Membership would also allow the UK to engage in knowledge sharing and learn from the relevant experiences of non-OECD economies in the face of common development challenges.Through this programme, the FCDO paid assessed contributions of €772,056 in 2019, €754,860 in 2020 and €726,988 in 2021 for UK membership. UK funding contributed to the delivery of outputs identified as core work under the 2019-20 Programme of Work and Budget (PWB) biennium and the first year of the 2021-22 PWB. DEV’s PWB is separated into four workstreams: 1) Inclusive Societies 2) Competitive Economies 3) New Perspectives for Development 4) Regional and National Analysis.

Overall, the programme has scored a “B” after meeting expectations on two of its three outputs. Key output activities included:

DEV’s programme outputs effectively convening countries at different stages of development. Emerging and developing economies demonstrated the value placed in DEV through high-level and active participation in its workstreams, as well as through new membership.

DEV’s Policy Dialogues (on Natural Resource-based Development, Social Protection and Development, and Migration and Development) informing and supporting UK thinking and analysis.

In-Depth Evaluation (IDE) of the Governing Board approved, with six Recommendations for areas of improvement and proposed actions to implement them.

Improved coherence and coordination between DEV and wider OECD development bodies, including important contributions to OECD analysis on women’s role in responding to COVID-19 and to a background paper for the 2021 Ministerial Council Meeting on the impact of COVID-19 on developing countries.

The programme substantially did not meet expectations under Output 3. While the programme demonstrated value and informed the development debate for the broader DEV membership, HMG’s limited engagement and low awareness and use of DEV products raised questions on VfM for UK funding. This influenced the decision not to renew funding after the programme end date of 31 December 2021.

Major lessons learned, evidence generated and recommendations

Although DEV’s PWB includes a workstream which covers strategic guidance and institutional priorities, the level of engagement with it by DEV members varied. A key lesson was that it was important to build a group of likeminded members to ensure strategic or institutional issues were adequately addressed and discussed at Governing Board meetings.

The IDE of the Governing Board served as a useful milestone for DEV members and its Secretariat to review DEV’s engagement with wider OECD workstreams on development. It is recommended that any wider OECD discussions on the Organisation’s strategic approach to development should also consider the value and complementarity that DEV can contribute.

A key lesson was that engagement with the Development Assistance Committee (DAC) Chair and members of both DEV and DAC was important to ensure the visibility of DEV’s work and its join-up with wider OECD workstreams.

With the UK as a non-member/OECD partner, the UK Delegation to OECD (UKDEL OECD) development policy leads should consider how to engage with and raise awareness of DEV’s outputs in order to inform UK policymaking.

How this report was conducted

This report was carried out by the SRO in UKDEL OECD. It drew on sources that included: HQ feedback on engagement with DEV outputs, Governing Board progress reports, the DEV PWB 2019-20 and 2021-22, as well as UKDEL OECD’s active engagement in Governing Board meetings throughout the programme.

Actions following approval of this report

This programme will now be closed in line with PrOF rule 29 (related to effective and responsible closure of programmes).

## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	Original budget of £1,414,592, increased to £2,020,204 to cover 2021 payment.	£1,966,044 (difference explained mainly by fluctuation in exchange rates).
Timeframe	2 years	3-year timeframe after one year extension to end 2021.
Outcomes	OECD Development Centre contributes to shaping the global development architecture, contributing valuable research and analysis to the evidence-based debate, both within the OECD and the wider international context.	Progress demonstrated, with DEV contributing to the development debate through its multidimensional analysis and platform for countries at different stages of development. However, selective HMG engagement with DEV work indicated limited use of its outputs to inform UK analysis and evidence-based policymaking.

Overall assessment of programme outcomes, sustainability and VfM

Progress was demonstrated against the outcome during the programme. Non-OECD member enlargement in particular indicated the value placed in DEV’s outputs by Middle-Income Countries (MICs) and Low-Income Countries (LICs). Members valued DEV’s flagship products for addressing the complex and multifaceted nature of their development. Examples included the Centre’s Multi-dimensional Country Reviews (MDCRs) and its workstream on development in transition (DiT). On the former (MDCRs), reviewed countries often affirmed the value of the reviews and their policy recommendations based on multiple dimensions (such as wellbeing, growth, governance) to address bottlenecks to development. On the latter (DiT), the Centre’s members from the LAC region in particular value the analysis which calls for a different model of international co-operation to promote sustainable development by addressing the complexity of development beyond income levels. DEV’s cooperation with the wider OECD also increased during the programme. One example was DEV’s collaboration with the DAC and the Sahel and West Africa Club (SWAC) on a background paper submitted to the OECD Ministerial Council Meeting in October 2021, addressing the impacts of COVID-19 on developing countries. The OECD’s Policy Dialogue on Natural Resource-Based Development provided a good example of a horizontal, cross-Directorate OECD initiative, hosted by DEV, with active UK engagement (including the UK chairing the Thematic Dialogue on Commodity Trading Transparency in December 2020). Overall, however, there were few examples of UK policy leads engaging with programme outputs, which indicated limited use of DEV’s work and products in influencing UK development policy debates. This was a key factor in the decision not to renew the programme after its closure at end 2021.
[note] For more information, see DEV’s regional work in Africa , Asia Pacific and Latin America and the Caribbean and engagement with DEV members and partners. See here for the list of DEV Governing Board members and their engagement with DEV and wider OECD outputs.
[note] For example, see the Communiqué from the 2021 July Dialogue attended by LAC and European policymakers.

The programme overall was judged to represent less VfM compared to the Business Case proposition. On equity, the programme continued to support DEV’s mandate “to improve well-being through poverty reduction and sustainable, inclusive growth in developing and emerging economies.” As part of this, DEV had a standalone workstream on Inclusive Societies, which included outputs on gender equality and women’s economic empowerment and on ensuring social protection and tackling informality. On economy, the pooling of UK and other members’ funding to invest in Secretariat expertise and analysis, provides “economies of scale”– e.g. more outputs are delivered in support of priorities agreed by members in the PWB. It also allowed for efficiency in funding OECD technical and policy experts to deliver programmed outputs through a multilateral system, rather than through the FCDO designing and delivering the programme on its own. However, questions on the added value of DEV’s outputs to shaping UK policy and research limited the overall cost effectiveness of the programme, in terms of both investing staff and financial resources. While investing in another multilateral forum or think tanks would not necessarily result in lower cost or higher quality outputs, they could be better aligned with UK policy priorities and objectives.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators.

Context

DEV is an established international forum (created in 1961). Membership is open to both OECD and non-OECD countries and currently has 53 members from diverse stages of development (25 OECD and 28 non-OECD members). DEV aims to boost development and poverty reduction around the world through influencing policy makers towards higher quality policy decisions. DEV’s Secretariat provides the policy and analytical support. Decision-making is based on consensus.

Long-term change

To measure progress towards the long-term goal, DEV’s PWB is structured around four objectives:

Identify and frame issues critical to the development dialogue
Influential analysis and evidence base
Mobilise and translate global and OECD expertise to support non-OECD decision makers
Mobilise development knowledge to influence OECD thinking

- In order to achieve long-term change, the UK prioritised DEV’s role in providing clear benefits to Low-Income Countries (LICs) and Least Developed Countries (LDCs), including enabling an exchange of practices between Middle-Income Countries (MICs) and LICs; convening a wide range of development actors, in particular providing a space for dialogue with emerging donors; and in complementing DAC outputs as part of the OECD Development Cluster (comprised of DEV, the DAC and the SWAC).
- DEV produces a yearly report that tracks progress made towards achieving the objectives of the four overarching objectives of the PWB. The final report for 2021 will be issued by end Q1 2022.
- UK assumptions about how long-term change might happen include FCDO’s consistent engagement with priority workstreams; UK engagement with other members that leads to a focused set of outcomes and quality products; and a Governing Board that allows open and constructive exchange between all members.

## C: Detailed Output Assessment

Output Number and Title	1. OECD Development Centre delivers work agreed in PWB to a high quality, supported by good transparent governance of the Centre.
Output Score	A
Impact weighting (%)	30	Impact weighting revised since last AR?	N

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

On PWB implementation, regular Governing Board progress reports allowed members to monitor the delivery of outputs against expected timelines and to raise any queries or issues in plenary. The DEV Secretariat also used a Results Framework to internally track implementation. Although COVID-19 had an impact on output delivery, the Secretariat adapted to the context, both in terms of policy in addressing the impacts of the pandemic on developing countries, and in terms of virtual working methods. Moving to a more virtual platform also allowed for more inclusive participation and representation at HQ level from DEV’s members. OECD Council’s approval of the In-Depth Evaluation (IDE) of the Governing Board in July 2019 was important in terms of improving ways of working. The Secretariat agreed to undergo this voluntary review, which identified areas for improvement and set out six Recommendations. Importantly for the UK, this included a Recommendation on reinforcing coordination and communication with other OECD bodies and programmes. Clear efforts were made by the Chair of the Governing Board and the Secretariat as part of an Action Plan to implement the Recommendations. A monitoring report of the Implementation of Recommendations was submitted for Council discussion in November 2020. Steps taken included: Secretariat launching a Strategic Roadmap on upcoming meetings and actions; updating a Membership and Outreach Strategy which considered regional balance in the drafting process; improving join-up on OECD external communications; and identifying areas for mutual engagement with the DAC.The limitation for the IDE was that, in line with its ToRs, the review covered the Governing Board only and not the role of the Secretariat, which is also key in its interaction with the Governing Board.
[note] The OECD Evaluation Committee carried out an IDE of DEV’s Governing Board, at the latter’s request. The Governing Board was evaluated over the period of 2009 to 2018. The IDE was based on the criteria of relevance, effectiveness and efficiency.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

The programme performed strongly in terms of the equity of outputs. In particular, DEV’s work on gender equality added valuable research and analysis both within the OECD and in the wider international context. For example, DEV contributed to an OECD paper in April 2020 on women’s central role in responding to the COVID-19 crisis. This paper was highly valued by UK gender equality policy leads and built momentum for the OECD’s approach to gender mainstreaming more generally. On an international platform, DEV’s Social Institutions and Gender Index remained an important output given its role as one of the official data sources for monitoring SDG 5.1.1 (on the role of legal frameworks in supporting gender equality and women’s empowerment). The UK also valued the work of the Policy Dialogue on Social Protection and Development, with FCDO policy leads finding the policy papers useful for informing UK policy. However, such examples of HQ engagement with DEV were limited over the lifetime of the programme. This, together with low awareness and use of DEV’s PWB outputs, raised the question of whether the UK was getting sufficient VfM from DEV’s PWB in terms of quality outputs aligned with UK strategic priorities in a challenging fiscal climate.

Lessons learned through this output, and recommendations for future programming

An important lesson was that while strong institutional governance and strategic direction was an important part of PWB implementation, other members were less engaged in this. This may be linked to the limited capacity of delegates from OECD and non-OECD countries to engage with DEV’s strategic issues, in addition to following DEV’s policy outputs. The IDE process provided an opportunity for members to discuss the findings of DEV’s performance and shape a follow-up action plan to implement the Recommendations. It will also be important to consider how DEV’s outputs can add value and coherence to the wider OECD approach to development, in view of ongoing discussions on the Organisation’s strategic direction.

Output Number and Title	2. The OECD Development Centre effectively brings low income countries (LICs) as well as middle income countries (MICs) into the development debate through membership, as well as engagement in knowledge-sharing policy dialogues and networks, and analytical work
Output Score	A
Impact weighting (%)	20	Impact weighting revised since last AR?	Y - decreased

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

DEV’s policy dialogues and networks were effective in convening countries at different stages of development. In particular, DEV’s Mutual Learning Group – initially set-up for peer learning on MDCRs and then peer learning more generally – played a key role in allowing members to share lessons and best practice in the design and implementation of national strategies and policy reforms. DEV’s High-Level Meetings in October 2020 and December 2021 provided a clear endorsement, particularly from MIC and LIC members, of the value that DEV can play as a platform for policy exchange on an equal footing. Membership enlargement (with Ecuador, Rwanda and Togo joining in 2019) over the programme lifetime was also indicative of this. However, two OECD countries (Germany and Poland) did not renew their membership after end 2020. Luxembourg also indicated it would not continue its membership after end 2021. While Germany’s decision was based on internal reforms, these membership changes during the programme lifetime raised questions on DEV’s added value for OECD members as a forum within an increasingly crowded, international development space. The UK’s decision not to continue DEV membership after 2021 was also reflective of this. From a UK perspective, in order for DEV to deliver on its ambition as a “thought leader” on development, it needs to be more strategically focused on its added value and fit within this broader development architecture. In view of membership withdrawal of OECD countries, implementation of DEV’s updated Membership and Outreach Strategy, approved in December 2021, will be an important tool in ensuring DEV’s relevance and visibility within the wider OECD architecture, as well as with external stakeholders.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

The output provided VfM in terms of equity, by convening both members and non-members at different stages of development to engage with outputs often supporting gender equality and the broader ‘leave no-one behind’ agenda. The 2021 SIGI Regional Report for Africa provides a good example of this, with its regional analysis on how discriminatory social institutions, social norms and practices continue to constrain women’s empowerment and restrict their access to opportunities and rights. Input from workshops and high-level policy dialogues organised in West, Southern and East Africa, were credited as valuable in shaping the report. UK also valued the engagement of DEV’s stakeholders in its work on commodity trading transparency and co-Chaired the plenary of the Policy Dialogue on Natural Resource-Based Development in June 2020. However, such selective HMG engagement with these policy networks and dialogues again raised questions on DEV’s VfM for the UK as a multistakeholder platform, in addition to the VfM already provided from engaging with MICs and LICs through other multilateral bodies such as the World Bank, or with partners through overseas Posts.

Lessons learned through this output, and recommendations for future programming

DEV would benefit from ensuring better join-up with wider OECD workstreams, which would provide greater visibility and impact for its outputs. Effective implementation of the IDE Recommendations should support this. DEV’s updated Membership and Outreach Strategy will also be important for allowing forms of engagement beyond membership for non-DEV members who could bring additional development perspectives to discussions, but who may not be interested or do not meet DEV membership criteria. DEV’s adaptation to more virtual working methods allowed for more inclusivity, removing the reliance for physical attendance by leads within a bilateral mission in Paris. More consideration could be given to DEV as a platform for G20 engagement, alongside wider OECD outreach efforts. DEV’s membership includes 13 members of the G20, including eight MIC members (Argentina, Brazil, China, India, Indonesia, Mexico, South Africa, Turkey).

Output Number and Title	3. The OECD Development Centre's work adds value to the development debate through strong performance by the organisation, work being valued and used by stakeholders to inform development debates
Output Score	C
Impact weighting (%)	50	Impact weighting revised since last AR?	Yes – increased.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

As indicated under Output 2, it is clear that DEV’s outputs and role as a forum for policy exchange between countries at different stages of development are valued. The establishment of a Group of Eminent Personalities in December 2021, should also provide valuable expertise in shaping the future policy direction of DEV’s work. As described under Output 1, there were concerted efforts at senior-level to improve coordination and coherence between different OECD workstreams on development. The Organisation’s strategic approach to development policy is part of ongoing discussions at OECD Council. Despite these achievements, given the internal focus of this output (indicators, milestone and targets) on the value-added for UK policy priorities, it did not meet expectations. An internal mapping exercise carried out in 2019 showed very selective engagement by ex DFID/OGDs in DEV’s outputs. Limited input from policy leads in 2020 during drafting negotiations for DEV’s 2021-22 PWB also signalled weak alignment between DEV’s work and UK strategic priorities. In terms of DEV’s role in any wider OECD approach on development policy, there is room for progress in DEV cementing itself as a centre of excellence both for and of the OECD and in achieving a mutually beneficial division of labour.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

Although the outputs met expectations for 2019 and 2020, selective HQ engagement and low awareness and use of DEV’s products raised VfM questions. This was a key factor in the decision not to continue funding the programme after end 2021. The challenging financial climate of COVID-19 and the need for the FCDO to ensure ODA spend brought maximum strategic coherence, impact and value for taxpayers’ money was also a contributing factor to the decision not to extend the programme. As indicated under Output 2, the UK view is that DEV should apply more strategic focus to its work and better identify its value-added within the international development architecture. More strategic focus would improve the quality of outputs, in turn delivering greater impact and VfM.

Lessons learned through this output, and recommendations for future programming

A key recommendation was the need for the OECD to be coherent in its external communication on development policy. This is important given that external partners do not necessarily understand the differences between different OECD development bodies. The UK continues to actively support better join-up across the OECD.

D: Risk

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.

The risk rating over the life of the programme was ‘moderate’. Inconsistent HMG senior and working-level engagement with DEV’s workstreams risked limiting the VfM that the UK received through its membership. To mitigate this risk, UKDEL OECD monitored, identified and promoted opportunities to support UK priorities with relevant HMG workstreams. After a review in Q1 2021 of the VfM of UK funding to OECD development work to support FCDO’s strategic objectives, a decision was taken not to renew the programme after end 2021. The reputational risk of this decision was then managed through stakeholder engagement. The impact of COVID-19 presented a delivery risk for DEV to fully implement its 2020 work plan. To mitigate this, the DEV Secretariat adjusted its workplan to refocus on what it could realistically deliver and quickly adapted to virtual working methods to ensure DEV meetings and external outreach could continue. Inconsistent join-up between DEV, the outputs of the DAC and wider OECD also presented a delivery and reputational risk of an incoherent OECD approach on development policy. To mitigate this, UKDEL OECD engaged with the DEV Secretariat, the Chair of the Governing Board, the DAC Chair and likeminded partners to ensure complementary OECD outputs in promoting sustainable development. Successful implementation of the IDE Recommendation is also a mitigating factor against this risk. Membership enlargement and agreement of an updated Membership and Outreach Strategy mitigated the delivery risk that DEV’s programme outputs were overly focused on MIC priorities. Togo and Rwanda’s membership in 2019 added diversity to socio-economic perspectives of DEV members. The updated Strategy refers to the importance of a geographically-balanced representation among members at different stages of development to inform DEV’s work, as well as the strategic objective to strengthen outreach efforts for engagement with non-members.

E: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency.

The OECD budget is comprised of Part I and Part II programmes of work. All OECD member countries contribute to the funding of the Part I budget. Part II budgets include programmes of interest to some members - or relates to special sectors of activity not covered by Part I. DEV is an OECD Part II body and is funded according to a scale of assessed contributions (based on capacity to pay) and member VCs. The criteria used to determine capacity to contribute is annual national taxable income in Euros.

For UK membership of DEV, FCDO paid €772,056 in assessed contributions for UK in calendar year 2019, €754,860 in calendar year 2020 and €726,988 in calendar year 2021. Payments were made in arrears following submission of the annual invoice to avoid payment in advance of need.  UK funds contributed to the delivery of outputs identified as core work under the PWB and represented around 11% of the budget envelope for assessed contributions in 2021 and around 4% of the total budget envelope for 2021 (assessed contributions and VCs). As with similar core contributions to multilaterals, this is 100% ODA-eligible. The UK also provided a VC of £860k during the programme lifetime in support of DEV’s work on Commodity Trading Transparency, as part of DEV’s Policy Dialogue on Natural Resource-Based Development.

In terms of VfM measures, the UK position was for ZNG to be applied as the annual adjustment rate to the core budget given the budgetary pressures for members in 2020. The DEV Secretariat had applied a 2% annual adjustment rate when first presenting the figures with the draft 2021-22 PWB. The UK joined consensus on applying a 1% annual adjustment rate. For 2021, this meant a €8,5k reduction in UK’s assessed contribution and for 2022, an estimated €15.4k compared to the Secretariat’s initial budget proposal. The Secretariat also undertook to implement appropriate management measures to ensure resource rationalisation and activity prioritisation in view of internal budgetary pressures linked to increase in staff costs as part of wider OECD budget parameters. The Secretariat also committed to further develop its impact tracking tools as part of efforts to maximise impact and value for money, including a clearer targeting of communication, dissemination, influencing and partnership strategies for the PWB’s main outputs.

The vast proportion of UK assessed contributions was used to fund the employment of technical and policy experts working on the programmed activities. A proportion of member assessed contributions is used to cover central OECD support services (legal, HR, financial/accounting services etc.), office space rental and other staff-related operating costs (furniture, IT equipment, phone usage etc.).

DEV adheres to OECD-wide financial and corporate controls. The UK also has governance oversight and influence through representation at OECD Council (body of Permanent Representatives providing the Organisation’s strategic direction), Budget Committee and through DEV. At a corporate level, the OECD’s organisational risk policy and risk register is presented to the Budget Committee annually and audited.  The OECD Audit Committee oversees the work of the internal and external auditor and is kept updated on the implementation of internal and external audit recommendations. The Audit Committee reports to Council, which the UK Permanent Representative attends.

Programme-level approach to monitoring and evaluation

The Governing Board is provided with quarterly progress reports, which provide detailed information on the budget and status of progress achieved at the level of outputs in the PWB. In response to a UK request, the DEV Secretariat also applies a Results Framework to the PWB, an internal management tool that guides planning and monitoring of activities, collection of evidence, and regular assessment of results with respect to progress towards achieving the objectives of the PWB. In addition the programme was monitored by FCDO officials throughout the programme cycle. The SRO represented the UK at Governing Board meetings and being based in UKDEL OECD was able to closely monitor the implementation of the programme and engage with its partners. FCDO policy leads were also able to review and shape the delivery of outputs under key workstreams, when engaging bilaterally with the DEV Secretariat and in plenary with all members. A mapping exercise of ex DFID/OGDs engagement in DEV’s workstreams was completed in 2019 to review the alignment of DEV’s outputs with UK priorities and the scope to further shape and engage with workstreams. A subsequent review of UK engagement with DEV was carried out in Q1 2021 to feed in to wider senior-level programming decisions on future funding to OECD work on development.
Date of last narrative financial report	02/12/21 – Governing Board progress report January to June 2021.	Date of last audited annual statement