## Annual Review
1 April 2020 – 31 March 2021

Title: Humanitarian Access in the Occupied Palestinian Territories
Programme Value £ (full life): £36,213,113		Review date: / September 2021
Programme Code: [AMP ID#] 300001	AMP start date: / 3 June 2016	AMP end date: / 31 March 2022

Summary of Programme Performance
Year	2016/2017	2017/2018	2018/2019	2019/2020	2020/2021
Overall Output Score	A	A	A	A	A+
Risk Rating	Moderate	Major	Major	Major	Major

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300001
DevTracker Link to results framework:	N/A

A. SUMMARY AND OVERVIEW
Context

A protracted protection and humanitarian crisis facing women, men, boys and girls continues in the occupied Palestinian territories (OPTs), leaving many Palestinians struggling to live a life with dignity. It is driven by Israel’s military occupation, including severe movement and access restrictions in Gaza, regular breaches of international law, continuing internal Palestinian political divisions, and recurrent escalations of hostilities between Israel and Palestinian armed groups.

During the reporting period (2020-21), the humanitarian situation in the OPTs was aggravated by three major developments. The first development was the outbreak of COVID-19: the measures imposed to contain the pandemic – including recurrent lockdowns and travel restrictions, school closures, reduction of commercial activities and mandatory quarantines – have severely undermined living conditions across the OPTs. Additionally, the state of emergency and subsequent lockdown, have exacerbated women and children’s vulnerabilities, placing them at increased risk of various forms of violence, including domestic violence.

The second development was the decision by the Palestinian Authority (PA) to halt almost all bilateral contacts with the Government of Israel (GoI) in response to Israel’s plan to formally annex parts of the West Bank. In this context, the PA stopped accepting the tax clearance revenues that Israel collects on its behalf. This policy undermined Israeli-Palestinian joint efforts to contain the pandemic, which were implemented during the two months following the initial outbreak. Coupled with the economic slowdown due to the pandemic, the PA lost 80% of its income, reducing its capacity to pay salaries, deliver services and maintain social safety nets. The burden of this worsening situation falls hardest on vulnerable groups including women-headed households, persons with disabilities, refugees, Bedouin and herders in Area C, internally displaced persons, small-scale farmers, herders and fisher-folk in Gaza, people affected by conflict-related violence and people already living below the poverty line.

The third development was the most serious escalation of hostilities between Israel and Palestinian armed groups in Gaza since the 2014 conflict. Between 10 and 21 May 2021 armed groups fired more than 4,300 rockets towards cities and towns across southern and central Israel, while Israeli forces carried out over 1,500 strikes from air, land and sea across Gaza. The hostilities resulted in significant loss of life and human suffering. The recent escalation in violence in Gaza has exacerbated an already dire humanitarian situation, generated by nearly 14 years of severe movement and access restrictions, internal political divisions, recurrent hostilities and continued COVID-19 pandemic.

In Gaza, the two million Palestinians who have been living under intensified access restrictions for 14 years, have been further isolated from the external world by COVID-19 related restrictions. Since the outbreak, Israel has allowed only the most serious medical cases to exit Gaza via the Erez Crossing. This situation was exacerbated during the PA’s cessation in cooperation with the GoI, with the PA halting the processing of exit permits applications, and the number of permits for traders to work in Israel dropped significantly. The GoI has further restricted access and movement in and out of Gaza during and since the new hostilities in May.

In parallel, there has been a significant rise in protests, clashes and arrests across the West Bank, including East Jerusalem, as well as in some communities in Israel. In the West Bank, Palestinian households and communities in Area C, East Jerusalem and the H2 area of Hebron city continue to face a coercive environment, due to a range of longstanding Israeli policies and practices. The restrictive and discriminatory planning regime applied in Area C and in East Jerusalem prevents Palestinians from addressing basic housing, livelihood and service needs.

Description of Programme

The Humanitarian Access programme in the OPTs has the following components:

Support for humanitarian access and Gaza reconstruction through funding to the United Nations Access Coordination Unit (ACU) and the Gaza Reconstruction Mechanism/Project Management Unit (GRM/PMU). The ACU provides operational support to humanitarian agencies to help resolve permit issues for personnel and goods, thereby increasing their effectiveness and reducing the time and money agencies spend working to resolve access issues. The ACU also provides comprehensive data and analysis on access trends to support the international community’s advocacy on increased humanitarian access. The GRM is a tri-partite agreement between the Government of Israel (GoI), the Palestinian Authority (PA) and the UN brokered in September 2014. The GRM aims at allowing the entry of large amounts of some ‘dual use’ materials into Gaza for the purposes of reconstruction following the conflict in 2014. The GRM established the PMU which oversees the supply chain of materials to ensure they are used for their intended civilian purposes; and facilitate project management.

A Humanitarian contingency to allow for speedy response in case of spikes in humanitarian need. In 2020/2021, FCDO provided:

- £0.8m (re-programmed from 2019/2020) to WHO to provide life-saving medical care and support the COVID-19 response.
- £3.8m to UNRWA to provide food for the most vulnerable refugee households.
- £2.5m to WFP to provide food vouchers and multi-purpose cash assistance for the most vulnerable non-refugee households to meet their essential needs.
- £0.2m to UNICEF to procure medical supplies to help safely identify and treat COVID-19 patients.

Summary supporting narrative for the overall score in this review

The overall score of this review is A+ indicating that the programme has moderately exceeded expected results for 2020/2021. Three outputs scored A++, A+ and A; whereas two outputs (access to reconstruction/construction materials and COVID-19 response) scored B mainly due to external factors and an overestimation of results milestones. Both outputs scoring B contributed to 10% of the total programme score.

Major lessons

FCDO funding to the ACU and PMU has facilitated humanitarian access and enabled the entry and use of materials on the GoI’s ‘dual use’ list to help ensure they are used for civilian purposes. Without an agreed monitoring mechanism, construction materials necessary for reconstruction and construction in Gaza will not be granted entry into Gaza. The PMU’s facilitation of large-scale projects in energy and water has produced great benefits to Gaza residents including women, men, girls, boys, and people with disabilities.

During increased access and movement restrictions and increased demand for ACU services, the ACU’s role has come to the forefront helping personnel get in and out of the West Bank, Gaza and Israel, and keeping people informed on lockdown information; and thus reflecting ACU’s added value in a time of crisis. The ACU played a critical role communicating access restrictions and helping negotiate access during and in the immediate days after the May 2021 hostilities. ACU’s swift and effective response to the COVID-19 crisis provided an excellent marketing opportunity which was seized by the ACU in order to promote its services and resource mobilisation strategy.
As best practice and through WHO’s work, WHO was able to achieve system and health sector-wide improvements in trauma and emergency care in Gaza. This was achieved through implementing a holistic approach, repurposing the use of Trauma Stabilisation Points to COVID-19 triage and testing; and involving key stakeholders under the auspices of the Health Cluster.

UNRWA reviewed its approach to the provision of food assistance in Gaza to sustainably manage available resources; and shifted to a unified food basket to all eligible refugees physically present in Gaza, with certain exclusions based on employment status. The unified approach eliminates the distinction between absolute poor and abject poor recognising the deteriorating poverty status of the majority of Palestinian refugees in Gaza.

UNICEF’s strong procurement policies and procedures enabled the OPTs to be the first country in the region to receive oxygen concentrators and the second to receive a shipment of PPE supplies. UNICEF can play a critical procurement and supply chain role on behalf of the wider humanitarian system.
FCDO leadership and engagement in the MPCA Advisory Board, emerging evidence from the MPCA programme and the collective humanitarian response to the May 2021 hostilities in Gaza demonstrates the need to improve coordination, harmonise approaches and reduce fragmentation in cash programming with greater consideration towards linking humanitarian cash to existing social protection programmes.

Recommendations for the year ahead

- FCDO to continue tracking movement and access trends in order to support UK advocacy to alleviate movement and access restrictions.
- FCDO funding to the GRM/PMU ended in March 2021, yet it is recommended that FCDO remains a member of the GRM/PMU Project Board with observer status to engage in the implementation of recommendations from the Gaza Access Review, continue supporting the improvement of access and movement conditions, and to consider future funding in light of new reconstruction needs.
- FCDO to consider scaling up cash programming in future humanitarian interventions and use our convening role to reduce the fragmentation of cash programming in OPTs.
- FCDO to explore the option of conducting an in-depth value for money analysis for the multi-purpose cash assistance in Gaza with current project partners.
- FCDO should consider supporting the rollout of some strategic workshops with all actors working on cash with the aim of enhancing coordination, harmonisation where appropriate and setting out a joint vision for linking humanitarian cash and social protection between humanitarian and development partners.
- FCDO programme team to seek a year’s extension to the programme components/outputs most relevant to the evolving humanitarian situation in the OPTs, whilst designing a successor humanitarian programme.
- FCDO to consider how the design of the interventions in a future programme can ensure better linkages between output and outcome levels in line with a refreshed theory of change.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The theory of change is based on the assumption that funding the ACU and GRM/PMU will ensure that humanitarian actors are able to access and assist vulnerable Palestinians across the OPTs. This will help ensure that during spikes in humanitarian need, partners are able to deliver assistance at scale and in a timely manner. Summary of the theory of change as in business case:

- Movement and access restrictions are major factors limiting effective humanitarian assistance and economic development across the OPTs. Funding to the ACU will help facilitate humanitarian access. While funding the GRM/PMU will enable reconstruction materials and ‘dual use’ items to enter Gaza faster, at greater scale and more cost effectively than before.
- Without a political solution, there is a likelihood of spikes in humanitarian need being caused by outbreaks in violence. Palestinians are vulnerable to protection concerns caused primarily by disrespect for International Humanitarian Law.
- The OPTs is also at risk of a large-scale earthquake, which could disproportionately affect vulnerable/overcrowded areas with poor infrastructure such as Gaza and refugee camps.
- Pre-positioned partners provide immediate and effective humanitarian assistance during emergencies. e.g. WASH kits, psychosocial support, nutrition, emergency medicines and health care.
- Funding access and facilitating reconstruction is complemented by a scalable emergency response in place to respond to humanitarian needs with agreed partners.

In the OPTs there has been a protracted crisis with a recurrent cycle of shocks reflected by four major escalations of hostilities in less than ten years. Within the business case and the theory of change we have built a contingency component in order to respond flexibly to spikes in humanitarian need – such as a further escalation of violence in Gaza or a major earthquake. This has allowed the UK to promptly respond to the COVID-19 pandemic, socio-economic consequences of COVID-19, increased food insecurity, increased strain on the health system, and the latest escalation in violence.

No changes were made to the Theory of Change during the reporting period; however, the Theory of Change was put to the test and proved that our planning scenario held true with the outbreak of COVID-19 and outbreak in Gaza hostilities. The programme continues to be effective in terms of value for money considerations; since it enabled a rapid and timely response to address increased humanitarian needs, specifically among the most vulnerable refugee, non-refugee women, men, girls, boys and people with disabilities. Having pre-selected partners ensured quality delivery of humanitarian assistance; our delivery partners all have strong mechanisms in place to provide assurance that aid was provided effectively and reached the most vulnerable and those in need.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The project impact is: UK aid saves lives during emergencies in the OPTs and helps rebuild Gaza. Impact indicators are:

- % of people displaced by 2014 Gaza conflict provided with permanent shelter. 99% in March 2020 compared with 87.8% in March 2019.
  [note] No updates for 2021
  [note] https://www.sheltercluster.org/sites/default/files/docs/one_page_factsheet_mar_2020.pdf
- Food insecurity rate in the OPTs (used as a proxy for overarching humanitarian situation). The last food insecurity survey was conducted in 2018 where the percentage of people without food security was 33% (68% in Gaza), up from 27% in 2015. The UN estimates that in 2021, 2 million Palestinians across the OPTs are severely, or moderately, food insecure and will require food assistance, and/or support in maintaining their farming, herding or fishing livelihoods. This represents a net increase of 300,000 newly food insecure compared to 2020. Furthermore, over 217,000 people, previously considered moderately food insecure, have become severely food insecure.
  [note] https://www.ochaopt.org/sites/default/files/hno_2021.pdf
Programme Outcomes

Outcomes	Outcome Indicators	2020/2021 Milestone	Achieved
Outcome 1: Humanitarian access is improved and 'dual use' materials are available for the reconstruction of Gaza.	1.1 Number of completed Projects facilitated by the PMU (average per quarter).	20 Projects	12 projects
	1.2 Average number of UN & NGO staff hours lost per access incident.	2 hours	1 hour and 7 minutes
	1.3 Average tonnes of cement imported per quarter by registered businesses through the Gaza Reconstruction Mechanism (GRM).	85,000 tonnes	1,869 tonnes
Outcome 2: Acute humanitarian needs met during emergencies.	2.1 Percentage of people in need as identified by the UN Humanitarian Needs Overview provided with humanitarian assistance.	70%	50%

Partners delivered significant humanitarian assistance in the OPTs, which helped the most vulnerable Palestinians cope with the worst shocks. However, the context deteriorated due to external factors including COVID-19, the PA’s fiscal crises, deteriorating relationships within OPTs and between the PA and Israel, and the escalating violence in Gaza. Compounded by insufficient donor funding, development partners were not able to address the full extent of humanitarian needs, and three out of four outcome indicators did not meet the milestones set for the reporting period.

The GRM/PMU facilitated 12 critical projects in total, all of which were identified by the Ad Hoc Liaison Committee (AHLC). One project – the Gaza Central Desalination Plant – is a large infrastructure development programme with several sub projects. Although the total number of completed projects facilitated by the PMU did not reach the 2020/2021 milestone, the PMU completed facilitating all the associated work necessary for the Gaza Central Desalination Plant including: reconfiguration of 12km of water distribution systems, construction of 4 concrete reservoirs and rehabilitation of 6 existing concrete reservoirs; in addition to civil and mechanical work for four distant project sites across Gaza. The PMU follows a standardised process to facilitate and monitor critical projects. This includes a monthly report and gathering best practice and lessons learned for completed projects.

The average waiting time per access incident was 1 hour and 7 minutes (1:07h). This is determined by dividing the total time lost to access incidents by the total number of access incidents. Despite different layers of movement and access restrictions including pandemic-related movement restrictions, the average staff hours lost (1 hour and 7 minutes) is well below the projected target of 2 hours, which contributes not only to saving staff time and efforts, but also saving on operational costs of humanitarian and development organisations. It is worth mentioning that for outcome indicator 2, the shorter the time the better, reflecting a positive achievement towards the outcome.

The total amount of cement held by the GRM-approved vendors was 1,869 tonnes (average during reporting period) which is significantly below the set milestone of 85,000 tonnes. This decrease is mainly due to the unilateral decision made by the GoI to remove Cement type 2 from the GRM in January 2020, which resulted in a significant reduction in the amount of cement imported and monitored via the GRM. In addition, outstanding reconstruction needs as a result of the 2014 conflict have slowed down. This by itself has reduced the scale of operations that the PMU used to facilitate with Cement Type 2 used in the residential and shelter stream and the majority of large-scale projects.

Some 2.4 million people have been identified by the UN as in need of humanitarian assistance and protection in 2020, or one in every two Palestinians in the OPTs. Of these, 1.5 million of the most vulnerable will be targeted through the 2020 Humanitarian Response Plan (HRP), a slight increase from 1.4 million in 2019. However, this means that nearly one million vulnerable people, mainly in Gaza, would not receive any assistance through the 2020 HRP, even if the HRP were fully funded. To respond to the pandemic, in April 2020, most of the regular HRP activities were reprogrammed. The cumulative appeal for 2020 increased to US$426 million, combining the original $348 million for the HRP request and $78 million for subsequent COVID-19 appeals. In total, some 1.2 million Palestinians (50% of total people in need) received humanitarian assistance in 2020, including 300,000 targeted in the original HRP. Reaching 50% of the people in need ended up being a realistic achievement given the increasing and competing humanitarian needs across the OPTs; in addition to new needs resulting from the economic slowdown due to the pandemic, and the PA losing 80% of its income, consequently reducing its capacity to pay salaries, deliver services and maintain social safety nets.
[note] https://www.ochaopt.org/sites/default/files/hrp_2021.pdf

The end date of this programme was planned for March 2021; however, given the humanitarian context, it was recommended that the programme team seek a year’s extension to the programme components/outputs most relevant to the evolving humanitarian situation in the OPTs. In April 2021, a time extension for the programme was approved enabling the programme team to extend the life of the programme and spend additional humanitarian funding in response to the May 2021 escalation in violence. Activities and results in relation to the additional humanitarian funding will be reported on in the project’s completion review (PCR).

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

There is good evidence that the Humanitarian Access programme is effectively helping save lives and improving the quality of life for the most vulnerable. The programme is helping prevent a worse humanitarian crisis and maintain stability. This remains an essential outcome for the UK programme in OPTs and hence the programme should continue. Moreover, this programme contributes to maintaining the viability of a Two-State Solution by strengthening the resilience of the most vulnerable and improving response to acute humanitarian crises. However, the design of the programme with limited multi-year funding and a large contingency fund to enable the UK to respond to emerging or new needs impacts our ability to better link outputs to outcomes. The theory of change should be revisited for any future successor humanitarian programme.

## C. DETAILED OUTPUT SCORING

Output Title	Technical access co-ordination provided for humanitarian actors.
Output number:		1	Output Score:	A++
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Percentage of humanitarian access incidents resolved by Access Coordination Unit (ACU). / (Number of successful incidents/number of total incidents received by ACU)	65%	74% of all incidents were resolved.
1.2 Access briefings provided at UNCT, SMT, HCT, AIDA, Security Cell, and donor meetings by ACU	60 per year	155, including 50 COVID-19 task force and coordination meetings.
1.3 UN and INGO personnel receive support in obtaining visas, permits, approvals and/or prior coordination.	3,000 personnel per year	10,456 (including 1,169 females)

Briefly describe the output’s activities, and provide supporting narrative for the score.

Output indicator 1.1: The ACU provides support to UN, International and National non-governmental organisations’ personnel and diplomatic missions during access incidents. The work of the ACU includes direct intervention and follow-up on cases of delays of Israeli-issued permits, liaison with relevant government or military counterparts, as well as local authorities, and provision of access briefs. During the reporting period, 72% of reported access incidents resulted in successful ACU intervention. If GoI searches of UN vehicles at Erez crossing are included, the success rate drops to 34%. However, a successful ACU intervention is defined for this purpose as any intervention that did not result in denial of entry and confiscation of UN property. This definition does not capture vehicle searches.

Output indicator 1.2: The ACU was instrumental in providing comprehensive data and analysis on access trends to support the international community’s advocacy efforts on increased humanitarian access. During the reporting period, the ACU conducted technical access briefings at United Nations Country Team (UNCT) meetings, donor meetings and for international and local non-governmental organisations. This indicator substantially exceeded expectation due to additional COVID-19 task force and coordination meetings which took place during the reporting period.

Output indicator 1.3: The ACU supported 10,456 personnel (of which at least 1,169 are female) in obtaining visas, permits, approvals, and/or prior coordination. ACU’s support included 3,967 critical missions in the West Bank; 1,379 critical missions during Gaza lockdowns; and facilitating the entry of 195 international NGO and UN personnel into the country. Although the milestone for this indicator was previously raised, it continually exceeds the target with sufficient capacity and capability to respond to increased demand due to the increase in access difficulties as well as the restrictions imposed by authorities to counter the coronavirus.

During increased access and movement restrictions and increased demand for ACU services, the ACU’s role has come to the forefront helping personnel get in and out of the West Bank, Gaza and Israel, and keeping people informed on lockdown information; and thus reflecting ACU’s added value in a time of crisis. A UNSCO-commissioned Gaza Access Review noted that the ACU has gender balanced teams and assigns its female staff to provide assistance to female personnel in need.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

We assess that this output remains excellent value for money in comparison to the Business Case and previous years.

The main VfM indicator for the ACU is cost per successful intervention. In 2020/2021, the ACU achieved 10,567 successful interventions with a budget of £773,474. The cost per successful intervention is £73; less than 70% of the cost identified in the baseline in 2015 (£281) and lower than last year (£121). This improvement in programme cost efficiency can be explained by increased demand for services with costs of delivery maintained.

Additional restrictions by Israel, including continuing to deny permits for many international UN and NGO staff based in Gaza, has made it more difficult to access Gaza over the last year and has increased demand for ACU services. In addition, Palestinian and Israeli authorities introduced further restrictions to contain the COVID-19 outbreak. Costs have remained similar to last year, and hence this implies an overall improvement in programme cost efficiency.

We have also seen an improvement in outcome indicators, such as the reduction in staff time lost to access incidents, which implies an overall improvement in VfM of this output.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

An indicator on customer satisfaction was replaced; and a new indicator was introduced. The ACU did not conduct a customer satisfaction survey due a comprehensive Gaza access review, commissioned by UNSCO, which took place during the reporting period. The ACU’s work shifted from responding to incidents on access and movement via the hotline to providing support with visas, permits and prior coordination with the relevant authorities to ensure the movement of UN, INGO and NGO personnel during times of COVID-19 lockdowns.

The new indicator was introduced to capture the ACU’s role in facilitating movement and access during the COVID-19 pandemic. Instead of measuring how many people participated in ACU briefings, the new indicator measures the number of briefings prepared/conducted. This change does not reflect the nature of activities implemented by the ACU. The ACU continued to perform its role of providing information and feeding into various UN and donor meetings.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations from the last Annual Review suggested reviewing the ACU output’s indicators following the Gaza access review, promoting data disaggregation, conducting a meaningful customer satisfaction survey, and reviewing the ACU funding modality. Output indicators were reviewed, and more data disaggregation included. During the reporting period, the ACU prepared a Resource Mobilisation Strategy to expand and diversify ACU’s project portfolio, expand the donor base, and explore new funding mechanisms. The ACU also worked on enhancing its communications by conducting donor briefings and publishing visibility and information materials to inform main stakeholders and new donors about ACU’s work.

The ACU is currently planning an in-depth survey with beneficiaries on access concerns and responses. This will be forward looking to help further develop the support ACU provides to NGOs, while providing feedback on ACU’s service.

The ACU’s swift and effective response to the COVID-19 crisis was an excellent marketing opportunity which was seized by the ACU in order to promote its resource mobilisation strategy. FCDO’s funding to the ACU ended in March 2021; it is recommended for FCDO to continue tracking movement and access trends in order to support with the overall UK advocacy and lobbying efforts.

Output Title	Materials Monitoring Unit (MMU)/ Project Management Unit (PMU) enables beneficiaries to access 'dual use' materials necessary for reconstruction of Gaza and the construction of large-scale projects.
Output number:		2	Output Score:	B
Impact weighting (%):		5%	Weighting revised since last AR?	Yes, down 5% points.

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of monitoring visits conducted by Project Monitoring Unit (PMU).	10% for residential stream / Quarterly visits to large scale projects / Fortnightly visits to all active businesses	12% - 43 visits were made to 365 eligible beneficiaries / Over 4 visits per year to active large-scale projects: 1,284 visits to 149 projects / Visits conducted fortnightly: total of 7,594 visits to 326 businesses
2.2 Number of trilateral meetings conducted.	1 meeting per quarter / (3 meetings per year)	2 meetings (2 meetings in Q1 2021).
2.3 Sector-specific needs are analysed and reported on the suitability of potential interventions through field assessment visits.	500 assessment visits	300 assessment visits.

Briefly describe the output’s activities, and provide supporting narrative for the score.

Output indicator 2.1 met the expectation set for the reporting period: The GRM/PMU has performed its monitoring role in proportion to the scale of construction being undertaken within the reporting period. The PMU successfully fulfilled its monitoring role by conducting visits for 12% of eligible residential stream sites, quarterly visits to active large-scale projects and fortnightly visits to all active businesses. Through its monitoring role, the PMU continues to enable the implementation of a number of vital construction and infrastructure projects within Gaza.

Output indicator 2.2: The PA’s decision to halt all bilateral contacts with Israel had an impact on the number of trilateral meetings conducted during the reporting period. The resumption in PA-Israel security and civilian coordination in November 2020 enabled two GRM-specific trilateral meetings to be held during Q1 of 2021. The slight underachievement of the target related to trilateral meetings is due to external factors beyond the PMU’s control.

Output indicator 2.3: 300 assessment visits were conducted in the priority sectors of energy, agriculture, health and water. This is below the expectation of 500 visits. During the period of August-November 2020, no site visits were officially allowed due to COVID-19 access restrictions. Moreover, the PMU only received limited requests by other agencies on monitoring and needs assessment visits because most agencies introduced restrictions on conducting site visits due to the COVID-19 pandemic. In summary, the underachievement of the target related is due to external factors beyond the PMU’s control.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

We assess that this output remains excellent value for money in comparison to the Business Case and previous years.

The VfM indicator for this output is the cost of facilitating import of cement into Gaza in USD per tonne. The cost per tonne until March 2021 was $5.00. This is 24% less than the cost in 2015 ($6.60 per tonne). In terms of cost-effectiveness, the PMU continues to demonstrate good value for money and appears significantly more cost-effective in comparison with other bilateral facilitation mechanisms, which range from $21 to $96 per tonne. This is mainly due to the light-touch monitoring approach agreed by parties to the GRM agreement.
[note] https://grm.report/#/Reporting/Visualization
[note] Measured using the total PMU expenditure against the total amount of cement. Cement was selected as it the most important material for construction.
[note] Based on publicly announced figures.

The PMU also implemented some cost savings, in 2020: the PMU annual budget was reduced from $5.3million to $3.8million through the following steps:

1. Merging the positions of Project Manager and Senior Advisor into one international post based in Gaza, starting in May 2020.
2. Transitioning of 14 national personnel to another UNOPS project in Gaza by end June 2020.
3. Gradual downsizing of the PMU operation through the closing of 6 international and 17 national posts from July 2020.

Cost savings were achieved without impacting the delivery of outputs, the PMU continued to achieve all monitoring and facilitation requirements during the reporting period.

Equity is not a significant aspect of this project given the nature of its activities: monitoring and facilitating construction materials entering Gaza and, increasingly, programme management according to demand.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes were introduced to this output during the reporting period.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

According to the Gaza Access Review report, the GRM/PMU has been an imperfect mechanism that in hindsight succeeded beyond expectations and can be credited for being one of the primary enablers of the reconstruction of Gaza after the 2014 conflict. The GRM/PMU has been part of a larger effort to prevent renewed violence, support humanitarian response, and promote development.

Recommendations from the last Annual Review suggested revisiting PMU indicators and scope of work in the context of COVID-19 pandemic, identifying new VfM indicators, exploring some analysis of gender and other vulnerable groups, and reviewing the funding modality for the PMU.

The indicators were re-visited, but no changes were agreed as those indicators continue to be valid and reflect the PMU’s monitoring role as well as project management and facilitation roles. The nature of the GRM/PMU project revolves around monitoring and project facilitation and so it is not always appropriate to conduct analysis of gender and other vulnerable groups. However, the PMU’s facilitation of large-scale projects in energy and water brings about great benefits to Gaza residents including women, men, girls, boys, and people with disabilities.

FCDO funding to the GRM/PMU ended in March 2021, yet it is recommended that FCDO remains a member of the GRM/PMU Project Board, with observer status to engage in the implementation of recommendations from the Gaza Access Review and continue supporting the improvement of access and movement conditions.

Output Title	The most vulnerable communities in Gaza have access to adequate treatment, including physical rehabilitation services.
Output number:		3	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	Yes, down 5% points

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number and Proportion of trauma causalities managed directly at the TSP and discharged	65%	52.8%
3.2 # of trauma limb-injured patients benefiting from reconstruction/rehabilitation services.	100	111

Briefly describe the output’s activities, and provide supporting narrative for the score.

Output indicator 3.1: WHO supported Gaza’s health system by enhancing the Trauma Stabilisation Points (TSPs). A total of 10 TSPs were established across Gaza to serve as a treatment point for lightly injured patients, and as a triage and stabilisation point for all casualties. Of 25,587 injured patients, a total of 13,522 were treated and immediately discharged. Simultaneously, 12,052 cases received immediate urgent medical care and were transferred to the secondary care level for further intervention. The proportion of trauma causalities treated at the TSPs was 52.8% (slightly below the expectation of 65%) due to the nature and severity of injuries which required secondary care level.

Output indicator 3.1: WHO established a dedicated multi-disciplinary limb reconstruction unit (LRU) in Gaza to be a centralised centre that provides a unique limb reconstruction service. The need for limb reconstruction became critical in serving patients who were wounded during the ‘Great March of Return’ demonstrations. The LRU provided screening for a total of 1,249 patients; of which 111 patients were admitted to the inpatient department (exceeding the expected target of 100 patients).

A satisfaction survey is regularly conducted for each admitted limb reconstruction case at the discharge point. The satisfaction tool illustrates patients’ feedback regarding the centre’s general environment, physician care, nursing care, physiotherapy and psychotherapy care, as well as patients families’ satisfaction. The satisfaction survey indicated that more than 85% of cases are highly satisfied and recommend the centre as the best place to provide limb reconstruction services.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

We assess that this output achieved reasonable value for money since it enabled a rapid and timely response to address increased humanitarian needs. It was not possible to establish comparators for two out of the three VfM indicators because of the unique context in Gaza. Severe movement and access restrictions, the mass injuries and casualties as a result of the Great March of Return occurring in such a short period of time; in addition to the complexity of wounds and injuries were unique factors to the context in Gaza and so it was not possible to establish any comparators.

VfM indicators were identified:

Cost per case
In terms of economy, the total cost for the rehabilitation services was around $100,650 including procurement and management costs, with total cost of $400 per case. In comparison, if patients were to seek similar services in other private health facilities, the total cost per case is around $780 suggesting that the project is cost efficient

% of people who received rehabilitation services and report improved functioning and reduced symptoms
The LRU staff provided 2,399 physiotherapy sessions in total. 27% of the total cases were discharged with complete physio rehabilitation recovery, which indicates that those cases do not need any further physiotherapy intervention and they can practice their lives as normal. Moreover, more than 5,950 psychotherapy sessions and 742 mental health counselling sessions were provided to patients’ families. 56% of the admitted cases were discharged with complete mental health recovery. The psychotherapists provided a unique service for patients which had a direct impact on the overall wellbeing of patients during the treatment journey.

% of hospital and pre-hospital staff who received training and show improved knowledge
Due to COVID-19 restrictions, it was difficult to deploy external consultants to conduct training courses inside Gaza health facilities. Instead, WHO conducted online training sessions in order to strengthen healthcare capacity. At the pre-hospital level, WHO contracted NYmedic to provide an online theory-based prehospital refresher training course for 212 first aid responders. At the hospital level, WHO contracted an external expert to provide weekly live online sessions for 32 LRU physicians and orthopedic surgical residents. In terms of economy, the total value of training at prehospital and hospital levels was $204,204 with a cost of $837 per each direct beneficiary; which is reasonable for this type of specialised training since the total number of indirect beneficiaries will reach up to 44,000 individuals per year.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The indicator on ICRC’s ILOT Appeal was not included in this review. This indicator was monitored the previous two years to reflect FCDO OPTs’ support to ICRC in 2018 and 2019.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Achieving system and sector-wide improvements requires a holistic approach: there is a need to adopt systematic response strategies involving as many partners as possible. As best practice and through WHO’s work, several partners were brought together to improve the overall emergency preparedness, response and right to health for the most vulnerable.

Recommendations from the last Annual Review suggested improving the value for money metrics by quantifying VfM milestones and exploring future plans for ensuring that the different elements of the trauma and emergency care pathway remain viable, operational and can be used for further emergencies.

WHO reported on two VfM indicators, as per the previous VfM section. Moreover, WHO worked towards the sustainability of the project by laying the foundation for a smooth exit. The TSPs were institutionalised as one of the core Ministry of Health (MoH) emergency and response mechanisms. WHO also worked closely with the MoH to establish the Limb Reconstruction Unit in one centralised location. MoH issued a regulation requiring all major limb reconstruction operations to be held at the LRU. Although WHO’s funding for the LRU ends this year, WHO will continue to provide the unit with technical support.

The utility of the TSPs were illustrated during the COVID-19 outbreak, when the TSPs were re-positioned as respiratory triage centres next to Gaza’s five leading hospitals to help prevent the transmission of COVID-19 into the health system. The respiratory triage centres were considered as an excellent preparedness measure implemented during the pandemic.

There are no further recommendations for the year ahead.

Output Title	Food requirements of food-insecure refugees and non-refugees met.
Output number:		4	Output Score:	A+
Impact weighting (%):		70%	Weighting revised since last AR?	Yes, up 25% points

Indicator(s)	Milestone(s) for this review	Progress
4.1 Refugee households living in poverty meet their most basic food requirements.	1,000,000 (498,000 female; 502,000 male)	1,043,173 refugees (519,277 / female; 523,896 male)
4.2 Number of women, men, boys and girls (including number of people with disabilities) receiving cash-based transfers / food vouchers to improve their dietary diversity.	274,497	361,373 (including 181,724 females and 179,653 males)
4.3 Number of poor non-refugee beneficiaries (women, men, girls and boys) receiving multi-purpose cash assistance (MPCA) to meet their essential needs.	6,864	7,343 non-refugee beneficiaries (1,114 households)
4.4 % of beneficiaries (disaggregated by sex, age and disability) reporting that humanitarian assistance is delivered in a safe, accessible, accountable and participatory manner.	100%	99%

Briefly describe the output’s activities, and provide supporting narrative for the score.

Output indicator 4.1: Access to food in Gaza remains a challenge for the majority of refugees, who struggle with deteriorating socio-economic conditions as a result of the restricted movement of people and goods, electricity shortages and high unemployment. The situation has been compounded by the COVID-19 pandemic and May 2021 hostilities. In these conditions, UNRWA’s emergency food assistance provides a critical lifeline to over one million Palestine refugees in Gaza.

In 2020, UNRWA overachieved the 2020/2021 target and provided 1,043,173 refugees (519,277 female; 523,896 male) with in-kind food emergency assistance on a quarterly basis. This included 16,399 female headed households, 42,392 persons with disabilities, and 45,140 people above the age of 60.

UNRWA’s post distribution monitoring survey of in-kind food assistance in Gaza solicited recipients’ views on the quality of UNRWA’s in-kind food assistance, household coping strategies, as well as feedback on UNRWA service provision. 93.9% of surveyed households were satisfied with the food distribution process. Only 85 households. (6.1%) reported dissatisfaction with the food distribution process – 14 of these being female-headed households. On a scale from 1 to 10, the average respondent satisfaction score was 7.3/10.

Output indicator 4.2: The sustained provision of WFP’s interventions has been pivotal to meeting deepening humanitarian needs; and strengthening national emergency preparedness and response capacity. WFP continues to prioritise the provision of food assistance to the targeted poorest and most food insecure non-refugees in Gaza. Through the Cash-based transfer programme, WFP reached around 361,373 non-refugees (overachieving the target), adjusting the response to alleviate the impact of the pandemic on people’s already fragile livelihoods. To avoid crowding in shops and supermarkets, WFP changed the frequency of its monthly voucher entitlements from weekly to twice a month and then to once a month. WFP also allowed unspent balances to be carried forward from one month to the next, as a precaution in the event of shops being closed because of a lockdown.

Output indicator 4.3: WFP ensured that the multi-purpose cash assistance (MPCA) was implemented safely, appropriately, and respectfully. WFP provided 1,144 households (7,343 beneficiaries) with MPCA to cover food and other needs.

Output 4.4: MPCA accounted for households’ needs, rights and capacities; and did not expose them to safety challenges. 99% of participants reported feeling safe or very safe when traveling to and from ATMs, stores, or outlets. Similarly, all reported they were treated respectfully and were also able to reach the delivery points without access issues.

Throughout the year WFP applied a gender-responsive monitoring system to ensure all individuals and families assessed as being most vulnerable to COVID-19 infection were given priority attention. WFP ensured that its programmes were implemented in a safe and dignified manner, with respect for affected people’s needs, rights and capacities. WFP used a set of monitoring and evaluation tools to track, prevent and mitigate the risk of abuse and harmful practices to beneficiaries.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

We assess that this output remains good value for money in comparison to the Business Case and previous years. We will work with partners to strengthen the value for money analysis of the MPCA pilot project.

In 2020 UNRWA budgeted around $95 (£68.8) per beneficiary for the year to provide food. This is similar to 2019 (£68.25). There is limited good comparator data available. The business case referred to the Coffey assessment of nine African countries in 2012 which found that it cost from £10-£96 per person per year to provide food assistance. The UNRWA cost is within this range.

For WFP, the cost per beneficiary was £7.4 per month, equivalent to £88.8 per year. This is slightly less than the cost per beneficiary from the FCDO funding to WFP in 2014; £10 per month (£120 per year). While the delivery of cash transfers is consistently cheaper than in-kind, in-kind assistance can be more economical overall because of better prices on international markets not available to individual vendors, though international procurement does not support self-sufficiency of local production and markets. There is a need for in-depth value for money analysis of the multi-purpose cash assistance pilot project in Gaza.

From an equity perspective, WFP and UNRWA’s selection processes focus on the most vulnerable, including people with disabilities, female-headed households, children and for WFP Bedouins and herders.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Two new indicators (4.3 and 4.4) specific for the multi-purpose cash assistance were introduced in order to capture FCDO’s funding to WFP’s MPCA pilot project in July 2020.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

During the fourth quarter of 2019, UNRWA started to review its approach to the provision of food assistance in Gaza. To sustainably manage available resources, UNRWA decided to shift away from resource-intensive poverty assessment and distribute a single, unified food basket to all eligible refugees physically present in Gaza, with certain exclusions based on employment status. In 2021, UNRWA started to distribute in-kind food assistance based on this new approach.

Recommendations from the last Annual Review suggested exploring with WFP and UNRWA options for enhancing the scope of the post-distribution monitoring; and for FCDO to explore greater harmonisation and coordination of food/cash programming. WFP and UNRWA conducted post-distribution monitoring for the in-kind food assistance and multi-purpose cash assistance. Key findings are mentioned in the above section. FCDO has been actively participating in the MPCA Advisory Board and other donor-coordination platforms such as the Good Humanitarian Donorship group and the UN Humanitarian County Team plus Donors to help improve coordination and harmonisation of cash programming.

It is recommended that for the year ahead, FCDO considers scaling up cash programming in future humanitarian interventions, while requesting in-depth value for money analysis for the multi-purpose cash assistance in Gaza. The approach to cash programming among partners and donors requires further harmonisation and coordination. The FCDO should use our convening role to reduce the fragmentation of cash programming in OPTs and consider supporting the rollout of some strategic workshops with all actors working on cash with the aim of enhancing coordination, harmonisation where appropriate and setting out a joint vision for linking humanitarian cash and social protection between humanitarian and development partners.

Output Title	COVID-19 preparedness and response activities are supported.
Output number:		5	Output Score:	B
Impact weighting (%):		5%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
5.1 Number of healthcare facilities staff and community health workers provided with Personal Protective Equipment (PPE)	4,500 staff and health workers	4,475 staff and health workers
5.2 Number of testing samples procured and delivered	20,000	18,067

Briefly describe the output’s activities, and provide supporting narrative for the score.

On 7 March 2020, the PA declared a state of emergency to contain the spread of COVID-19 which required people to adhere to the recommended measures, including physical distancing and personal hygiene measures. Since the onset of the COVID-19 crisis, the humanitarian community has been supporting the MoH to address critical gaps in laboratory supplies and other medical equipment, including life-saving ventilators and essential Intensive Care Unit (ICU) equipment.

Output indicator 5.1: UNICEF provided the MoH with 55,783 emergency Personal Protective Equipment (PPE) items – 33,983 gowns, 8,700 face shields, 340 coveralls, 4,760 boxes of medical masks with 50 pieces each (238,000 masks) and 8,000 boxes of gloves with 100 pieces each (800,000 gloves) – supporting 4,475 healthcare workers covering the needs over a two-month period. This figure is slightly less than the agreed target due to an overestimation of the result.

UNICEF equipped 15 implementing partners in Gaza and the West Bank with 3,589 hygiene items (e.g. bleach, hand sanitizer, soap), covering the needs for about three months. This enabled partners to continue providing health and nutrition services to the most vulnerable children and women. UNICEF also provided 13 syringe pumps with accessories and 15 oxygen concentrators to allow the treatment of 56 patients on a monthly basis. Additional shipments of 10 oxygen concentrators and 13 intensive care unit sets have been delivered to the Gaza health facilities to support around 50 COVID-19 patients to receive monthly treatment.

Output indicator 5.2: The number of testing samples procured and delivered (18,067) did not meet the set target of 20,000 due to costs exceeding the estimates quoted. However, WHO enhanced lab testing capacity related to COVID-19 through procured testing kits for the benefit of the central lab within MoH. This lab is considered the main lab responsible for testing COVID-19 suspected cases.

By supporting UNICEF and WHO’s COVID-19 response, the risk of death among COVID-19 patients has been reduced, while the continuum of care was ensured for the high risk and most vulnerable groups. Additionally, UNICEF, in close coordination with the MoH and the WHO, upgraded the designated COVID-19 health treatment facilities, supported case management capacity of the MoH in the West Bank, and supported emergency humanitarian response during the COVID-19 pandemic through international procurement of vital medical supplies.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

We assess that this output remains good value for money in comparison to previous years.

Test kits procured through FCDO funds were used for 18,067 tests out of a total of 259,342 tests conducted during the period representing about 7% of the total conducted tests. The total value of procured lab tests is $413,398. In terms of cost-effectiveness, the total cost per beneficiary is $22, which is less than half of the same test value ($44) if conducted in a private lab.

UNICEF faced several challenges in the procurement of supply items and management of costs to respond to COVID-19, including high demand for items on global markets which led to price inflation and extended delivery lead times. The limitations on airfreight remained the biggest challenge for logistics. Where possible, UNICEF procured items from the local market. For global procurement, the UNICEF Supply Division worked with the industry globally to source additional products and engaged relevant authorities to waive export bans for medical items and PPEs. Despite those challenges, the OPTs was the first country in the region to receive oxygen concentrators and the second to receive a shipment of PPE supplies.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes were made to this output during the past year.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Recommendations from the last Annual Review suggested agreeing clearer milestones and VfM indicators, requesting further analysis on gender and disability disaggregation as per new central agreements, and reviewing priorities for further support to address COVID-19.

A VfM milestone was agreed and included in the above section. It was not possible to request further analysis on gender and disability as the existing agreement with UNICEF ended on 31 March 2021 and no new agreement was signed. This recommendation will be retained in the event of any further funding. By reviewing priorities for further support to address COVID-19, FCDO is exploring addressing the secondary socio-economic impact of COVID-19.

D: RISK

Overview of risk management

The Overall risk rating of the programme is Major. The programmatic risks to the success of the programme are moderate. The overall risk, however, is major reflecting the context risk of a humanitarian intervention operating in a protracted crisis. Mitigating measures include strong enhanced due diligence, working with partners with proven capacity, ensuring we link the programme with diplomatic efforts for a two-state solution and that all parties have respect for International Humanitarian Law.

Main programme risks and mitigation measures:

Overall donor funding is unpredictable for the ACU and PMU with a limited donor pool and few multi-year funding agreements. Efforts by the ACU and PMU to reach out to other potential donors continue; informed by the newly developed Resource Mobilisation Strategy, since both projects are contingent upon a stable and predictable funding stream.

Uncertain political and security environment: The precarious political and security situation could easily lead to events that would further increase access restrictions. For example, unilateral imposition of new procedures at Erez vehicular crossing or Kerem Shalom goods crossing, deterioration in permit processing for national UN and INGO staff, restrictions on items that personnel can carry out of Gaza, and changing restrictions on which goods and equipment can be imported into Gaza. The ACU and PMU have led the collective UN response to the imposed procedures and continue to engage with the Israeli authorities at different levels with the support of the UNRC/HC.

Resumption of conflict: there are a number of conflict drivers that cannot be mitigated by the success of the GRM/PMU. Additional external drivers such as the lack of a permanent ceasefire could lead to a sudden deterioration of the security situation. This would mean monitoring activities will be halted. The PMU Project Board continues to assess risks to the project on an ongoing basis, and where necessary determine the need for diplomatic support from donors to help mitigate them.

Lack of engagement in GRM by GoI and PA: The PMU serves to provide monitoring activities for the GoI and the PA in order to ensure the ongoing success of the GRM. The GRM itself can only operate with continuous active engagement of both Parties; the withdrawal of such engagement represents a high risk to the PMU project. UNOPS continued to work closely with UNSCO to urge the Parties to hold regular meetings in addition to other communication activities. UNSCO continued to work actively to ensure engagement and buy-in from the Parties as often as possible.

COVID-19: Increased restrictions on movement and access due to COVID-19 may hamper the implementation of programme activities resulting in delays and/or under-spending. We are closely monitoring implementation of programme activities and maintain regular dialogue with implementing partners in order to understand the impact of COVID-19 on partners’ delivery.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency.

UNOPS implements both the ACU and PMU. A Project Board, consisting of FCDO and other donors, was established to provide overall guidance and direction to the projects, as well as reviewing, monitoring, and evaluating activities. It has continued to meet twice a year on the ACU project and quarterly for the PMU project. UNOPS’ financial management has continued to meet the standards expected. Both ACU and PMU have databases tracking progress against the log frame: The ACU database is regularly updated and the PMU’s can be viewed in real time on the web. Interim and certified financial reports have been issued on a timely basis, and financial reports are presented at each quarterly PMU board meeting, and every 6 months for ACU. UNOPS manages assets in line with UNOPS’ rules and regulations and also maintains a quarterly asset list for the ACU and PMU which was last updated in March 2021. A virtual monitoring of both ACU and PMU assets was conducted by FCDO OPTs’ programme manager in December 2020, which showed that assets were well-kept and accounted for as per the most up-to-date asset lists.

UNICEF has continued to conduct programme monitoring visits during the COVID-19 emergency to verify partners’ reports and ensure continuation of activities. This included engaging beneficiaries and community members to understand their experience and reflections. UNICEF also provided training to implementing partners to ensure the quality of data collection. A Third-Party Monitoring Team was contracted by FCDO to verify results and review impact and sustainability. UNICEF has undertaken an evaluation (including a value for money assessment) of its water, sanitation and hygiene work in Palestine, covering projects from 2016-19. Moreover, UNICEF provided continuous monitoring and evaluation support to downstream implementing partners in developing methodologies and tools used during programmatic field visits, and through systematically reviewing progress reports generated on the different sub-activities.

UNICEF ensured that all data collected and reported for the project was compiled in accordance with the data quality standards through sample Data Quality Assurance (DQA) sessions . Recommendations from field monitoring reports were utilised to improve the quality of the project and action points were systematically followed up.

For the UNRWA emergency appeal in Gaza (which manages the food distribution), a senior emergency officer oversees monitoring and reporting of activities. UNRWA provides one Annual Report covering all its operations in June each year, as agreed with the donors. This includes progress against all its programme targets using data from its Results-Based Monitoring System.

FCDO also convened a quarterly meeting with WHO and the main donors to WHO’s trauma and emergency care programme.

WFP organises donor meetings twice a year for programme updates, in addition to publishing quarterly operational updates (which include financial updates) and annual detailed financial and narrative reports. WFP conducts post-distribution surveys of a sample of beneficiaries every quarter, which is currently conducted remotely over the telephone.

For the Multi-Purpose Cash Assistance (MPCA) pilot project, an Advisory Board consisting of donors and implementing agencies was established. The Advisory Board’s role is primarily to provide overall strategic direction and guidance of the programme; ensure that the MPCA in Gaza is implemented transparently, efficiently, effectively and accountably; assess progress against deliverables (including at the outcome and impact level) and direct corrective action where needed; coordinate donor funding for the multi-purpose cash assistance and optimise harmonisation of reporting requirements and frameworks; advocate for the participation/inclusion of other donors which could lead to an increase in number of beneficiaries; and ensure synergies between MPCA pilot and other modalities of cash transfer programmes.
All components of the programme continue to represent value for money, outperforming their comparators where comparators were available.

This review was carried out by the FCDO OPTs’ humanitarian programme manager, quality assured by the SRO, results adviser, senior programme manager and economic adviser.

Date of last narrative financial report	UNOPS-ACU 30 April 2021 / UNOPS-PMU 6 May 2021 / UNRWA-30 June 2021 / WFP- 1 July 2021 / WHO- 31 March 2021	Date of last audited annual statement	UNOPS-ACU / UNOPS-PMU / UNRWA- July 2020 / WFP- 11 May 2020 / WHO- 30 July 2021