## Annual Review Template

Title: Sustainable Manufacturing and Environmental Pollution Programme (SMEP)
Programme Value £ (full life): 24.65 million		Review date: 29/07/2022
Programme Code: 300124	AMP start date: / 21 August 2018	AMP end date: / 30 November 2024

Summary of Programme Performance
Year	1	2	3	4
Overall Output Score	A	A	A	A
Risk Rating	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300124/documents
DevTracker Link to results framework:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300124/documents

A. SUMMARY AND OVERVIEW

Description of programme

The Sustainable Manufacturing and Environmental Pollution (SMEP) programme is addressing environmental pollution associated with manufacturing and industrial process in developing countries. The programme is generating evidence on pollution and environmental health, and developing and testing the application of technology-based solutions and cleaner production methods, and associated technical assistance. This has a direct benefit to human health and the natural systems by reducing pollution entering the environment and atmosphere and protecting system resilience, whilst fostering more sustainable livelihoods through business model innovation. The SMEP programme has three core components:
1. Research to support practical solutions to addressing manufacturing pollution with a high chance of take-up and impact;
2. Developing and testing innovative technology-based solutions that improve the environmental impacts of manufacturing; and
3. Identifying and developing suitable supporting business models and policies to adopt innovative technology-based solutions.

Through the achievement of the SMEP programme’s objectives, the programme has three focus areas: human and environmental health, and reducing pollution that contributes to greenhouse gas (GHG) emissions. At the Outcome level, this is achieved through reducing the harmful impacts of manufacturing and plastic pollution on the environment and human health, and at the output level it is achieved through technical approaches that reduce pollution and generating new evidence that prompts pollution reduction action. SMEP activities are presented in Figure 1 below.

The SMEP programme is implemented in partnership with the United Nations Conference on Trade and Development (UNCTAD). Competitively selected, the Programme Management Agent (PMA) manage the SMEP programme’s delivery and comprises a consortium partnership between Pegasys, SouthSouthNorth (SSN) and the International Centre for Climate Change and Development (ICCCAD). UNCTAD and the SMEP Steering Committee work in partnership across the three themes, providing a range of technical assistance and support services to the programme.

Figure 1: Current and proposed SMEP activities underway .

Summary supporting narrative for the overall score in this review

Assessment of the overall programme performance for this annual review concluded that broadly all outputs have met or are on track to meet applicable milestones for the year under review and generated a combined output score of “A”. This is despite the impact of significant global events including the COVID-19 pandemic, the crisis in the Ukraine and associated impacts on official development assistance (ODA), and the operational context. It also reflects adjustments made previously to take account of the broader delivery realities associated with these large-scale global events. At the same time, new geopolitical tensions re-emphasise the importance of the SMEP programme, for example: the crisis in Ukraine adds to compounded problems impacting supply chain across the world, giving further impetus to a global trend towards diversification of critical manufacturing capacities, including repatriation of manufacturing sectors, which bring associated pollution effects requiring mitigation. Noting the importance of reducing manufacturing and environmental pollution for tackling climate change, and SMEP portfolio’s broad-based action to sustainability and resilience, SMEP will now be reporting as an International Climate Finance (ICF) programme. Despite a very challenging, resource-constrained context, the Steering Committee (SC), the PMA and UNCTAD have worked to respond in an adaptive manner enabling clear headway in programme delivery during the reporting period.

Key achievements during the year under review include:

- The PMA completed the plastics call (C_004), launched in May 2021, that focuses on tackling plastics pollution across the plastics chain (upstream, downstream and end-of life) – see Figure 2. Ten plastics projects were contracted in a trail phase, with nine proceeding to full implementation over the coming period. These projects complement HMG’s programmes like Manufacturing Africa that aims to accelerate foreign direct investment in prioritised manufacturing sectors like plastics, and have potential to reduce pollution that contributes to greenhouse gas (GHG) emissions. Even though projects are typically in an early stage of execution, there is already an example of a project team feeding experience and perspectives into policy development by government.
- The PMA acted on recommendations of SMEP-commissioned research studies undertaken in FY 2021-22 and developed four targeted calls to address industrial manufacturing pollution. These calls will be launched in FY22/23, with an open call focused on piloting manufacturing pollution mitigation technologies in East Africa being launched first.
- UNCTAD coordinated the preparation and publishing of four peer-reviewed research articles to convey learning from the SMEP manufacturing pollution research calls undertaken in 2021 and 2022. (SMEP C_002 & C_003, Figure 1). The open access articles focused on four themes, circularity approaches in the South; Manufacturing Pollution; Plastic pollution mitigation strategies; and tanneries pollution. Such reports have been acknowledged in international processes such as the WTO Informal Dialogue on Plastics. Beyond their public goods benefits, the articles also helped inform SMEP design processes around the plastics and industrial manufacturing pollution procurement streams.
Figure 2 (below): Plastics Procurement overview

Major lessons and recommendations for the year ahead

Lessons learnt
Adaptive management within uncertainty: The global financial uncertainty linked to large-scale global events has caused slowed delivery, year-on-year budget uncertainty and capacity constraints. For this reason, a time extension will be needed if the original ambition of the Business Case is to be fully realised. For example, interventions seeking grants to address technical assistance for policy and market innovation require long lead times for the establishment of field partnerships with influential and reputable institutions, as well as budget certainty.
- Monitoring Evaluation Reporting and Learning (MERL): SMEP’s internal learning to inform processes require deepened and more formalised engagement (including on matters relating to Gender Equity, Social Inclusion, the Leave No One Behind Agenda and ICF reporting).
- Maximising VfM by linking research to global processes: There are opportunities to use SMEP analysis and the cases developed by grantees to inform multilateral forums working on plastics pollution issues, such as World Trade Organisation’s (WTO) Informal Dialogue on Plastics Pollution and Environmentally Sustainable Plastics Trade (IDP) and United Nations Environment Assembly-5 (UNEA-5) processes.  SMEP analysis can also inform the Sustainable Development Goals, specifically Goal 12 Responsible Consumption and Production.

Recommendations
- A time extension to the programme of approximately 2 years is recommended This is as a result of the range of global events which have disrupted and delayed SMEP delivery, which will constrain final value for money without an extension to allow the programme an appropriate implementation period to achieve its full potential strategic impact. (FCDO to seek approval by end of March 2023).
- Related to the above, should a programme extension be approved output milestones are likely to require further review (PMA and FCDO undertake an initial review by Q3 FY 2022-23).
- Continued adaptive management approach by PMA, UNCTAD and FCDO is recommended. Flexible management arrangements should be continued to cater for different budget scenarios. Procurement calls should be prepared as far as possible ahead of annual budget allocations, in order to be prepared to launch shortly after a budget allocation has been confirmed (PMA, UNCTAD and FCDO, throughout FY 2022-23).
- It is recommended that a level of budget flexibility should be encouraged, for delivery of high-impact activities which emerge as unforeseen contextual developments or important partnership opportunities (PMA, UNCTAD and FCDO, throughout FY 2022-23).
- Quarterly MERL tool updates were initiated during FY 2021-22. This new process is a result of the reporting tool used by suppliers, which generated a more user-friendly method of tracking. The recommendation is to revise the MERL tool to ensure all verifiable information is captured. The tool will be used by the PMA and UNCTAD to record substantive progress towards logframe milestones and/or strategic opportunities for the programme to link SMEP outputs to outcome level milestones (where possible). (PMA and UNCTAD, by end of Q3 FY 2022-23).
- An ICF-aligned GHG reporting methodology has been proposed and will be implemented from Q2 FY 2022-23 with 7 of the grantees under the plastics mitigation procurement. To complement this, it is recommended that the PMA ensures there is adequate GHG expertise to cover the entire SMEP programme (PMA by end of FY 2022-23).
- Develop a clearer typology of partnership and stakeholder engagement and evolution (for example embracing spectrum from initial outreach through to formal agreements) for improved progress reporting (PMA by end of Q3 FY2022-23).
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The SMEP Theory of Change (ToC), describes the programme impact as follows: “Improved manufacturing processes in target countries, which will lead to a reduction in: i) overall levels of pollution in target countries; ii) mortality levels linked to pollution from manufacturing; iii) morbidity levels and loss of DALYs, directly attributable to pollution from manufacturing”. The programme’s overall outcome states: “transformative changes in manufacturing practices and government policies lead to significantly reduced harmful impacts on vulnerable people and the environment”. This is underpinned by three second-tier outcomes:

1. Partner governments have the necessary tools, technical advice and knowledge to address the problems identified.
2. Increased production efficiency and environmental sustainability of selected manufacturing processes create the business case for adoption and replication of technological solutions and improved manufacturing processes.
3. Businesses are motivated and enabled to improve manufacturing processes through a mix of incentives, enabling solutions, policies and business models.

Following the previous annual review, some output level logframe milestones were revised to reflect the impact of large-scale global events (COVID-19 and associated impacts on ODA, and the Ukraine crisis) that resulted in research and procurement call delays and resulting contracting. The logframe has been updated to include GHG reduction and Gender Equality and Social Inclusion (GESI) considerations noting the significant contribution that reducing manufacturing pollution has on reducing GHGs and building resilience. Specifically, a nested GHG sub-indicator has been added to Outcome indicator 2.a; a nested sub-indicator for GESI has been added to output indicator 1.2; and a new output 3.4 has been added to support GESI considerations. Further logframe refinement is likely to be required in the next reporting period in light of the planned extension to me the original business case ambition, which has been necessitated due to the past and ongoing impact of the large-scale global events already mentioned.

SMEP has sought to maximise private sector involvement through early market engagement during FY 21/22 and outreach dialogues with a range of related initiatives – for instance a joint webinar hosted by the International Chamber of Commerce (ICC). To further maximise VfM efficiency and effectiveness the SMEP programme is continuing to interact with UK-funded programmes, such as the UK-funded GSMA Innovation Fund, and the United Nations Industrial Development Organisation-funded In-tex and Switch programmes delivering cleaner production support to the textiles industry.

Describe where the programme is on/off-track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The large-scale global events have disrupted a range of SMEP programme activities, including research outputs and research calls. The SMEP plastics pollution procurement call (C_004) undertook a phased contracting approach of C_004 grantees in light of these events, as well as an adjusted approach and slowed launch of the manufacturing calls. Consequently the programme is unlikely to achieve its full potential strategic impact within the current approved timeframe. As a result an extension in the programme duration is planned. Nevertheless, the SMEP programme has sought to proactively navigate these large-scale global events as best it can. It has contracted a range of competitively selected projects during the year, which can deliver benefits in a relatively short timeframe, undertaken strategic engagement through UNCTAD activities, and laid the preparatory work for the industrial manufacturing calls (C_005).

In the year ahead key aspects for the SMEP programme include:

1. Seek a time extension to the programme to maintain the existing ambition of the Business Case;
2. Update the logframe should a time extension be approved (by early Q3 FY 2022-23);
3. SMEP aims to work in an integrated and coherent way, capitalising on a number of co-benefit dimensions (GHG, gender etc). Managing and advancing such multi objectives will require proactive ongoing strategic oversight by all parties in the coming year;
4. In light of the ongoing uncertain wider operating context, PMA will continue to execute measured and well-designed procurement frameworks which incorporate flexibility and adaptability, coupled with a strong stakeholder outreach programme (to private, public and agency/NGO sectors) – thus ensuring that the procurement ToRs are designed for local context and are complementary to local and regional initiatives, including related technical assistance efforts being led by UNCTAD, while retain some scope to flex with wider developments if necessary;
5. Cornerstone robust oversight of the implementation of the plastics pollution project portfolio, and of the procurement calls for innovative technology-based solutions to reduce manufacturing pollution.
6. The SMEP PMA and UNCTAD will continue hosting learning dialogues between contracted plastics procurement suppliers during Q3 FY 2022-23 to engage particularly on Greenhouse Gas emission reduction reporting methodologies, as well as Gender and Social Inclusion reporting. This is envisaged to maximise project outcomes, as well as VfM. Dialogues have been started between similar programmes (Basel Small Grants Programme / WEF Global Plastics Action Partnership / UNIDO Switch) for collaborative action on technical assistance related to the plastics procurement cohort.
7. Following the presentation of a SMEP report on plastic substitutes to WTO members, an event is being planned for Q3 FY 2022-23 to discuss plastic substitutes, based on a direct request of WTO (IDP) Country representatives for further support in this area.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The programme should continue. In recognition of wider global developments, the programme has made a strategic decision to increase the focus on plastic pollution mitigation solutions (up to £10m allocated) alongside manufacturing pollution mitigation solutions (up to £9m allocated). SMEP has generated knowledge, developed partnerships, delivered the plastics pollution call with 9 projects underway, and prepared work necessary for the manufacturing pollution calls. The programme has produced significant amounts of novel information through high quality reports linking regional pollution issues with ongoing priorities at the global multilateral level, as well as informing national agendas. Points substantiating the ongoing strategic relevance of the programme include:

- SMEP is addressing major global environmental challenges directly: circular economy, pollution abatement and GHG mitigation. SMEP projects that will seek to find solutions to curtail environmental pollution are for human and environmental health and risk management.
- UNCTAD engagement with international actors, where SMEP results play a key role informing crucial multilateral processes, such as the implementation of UNEA 5.2 resolutions 11 and 14, WTO Informal Dialogue on Plastics and the WTO Committee on Trade and Environment, as well as the UN Environment Management Group on a Pollution-Free planet. Stopping momentum would have negative impacts for UK government and its global environmental governance objectives.
- Research papers based on various reports and workstreams from the SMEP programme resulted in a special issue of the Journal of Developing Societies. The papers have been developed in consultation with various SMEP stakeholders and experts, and focused on:
  - Research paper 1: Sustainable Manufacturing and Environmental Pollution Programme (SMEP): A Circular Economy Experiment in the South
  - Research paper 2: Plastic Waste Mitigation Strategies: A Review of Lessons from Developing Countries.
  - Research paper 3: Shifting to Circular Manufacturing in the Global South: Challenges and Pathways.
  - Research paper 4: Mitigating Tannery Pollution in Sub-Saharan Africa and South Asia

## C. DETAILED OUTPUT SCORING

While the SMEP AR cycle runs on a calendar year from June to June, the SMEP logframe has milestones set in financial years (i.e. April to March); therefore, logframe indicator progress reported in this AR is for the FY 2021/22 (i.e. period 1 April 2021 – 31 March 2022).

Output Title	Improved knowledge and understanding of the environmental and health impacts of pollution from manufacturing, including plastics.
Output number:		1	Output Score:	A+
Impact weighting (%):		15	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1: Number of peer reviewed research papers drafted/submitted/accepted describing results of environmental and/or health impacts of pollution from manufacturing.	1-2 research paper drafted/ submitted/ accepted	Exceeded FY 2021-22: / 4 peer-reviewed research papers coordinated by UNCTAD accepted for publication at the Journal of Developing Societies in Q4 2021-2022. / These were derived from the manufacturing pollution and plastics research, and input was secured from various related initiatives during the seminar process.
1.2: Number of "research outputs" aimed at advancing our understanding of the environmental and health impacts of pollution from manufacturing.	At least 1-3	Exceeded FY 2021-22: / 5 synopsis research outputs were prepared and made publicly accessible in FY 2021-22 under the manufacturing pollution procurement, covering topics of used lead acid batteries and tanneries in Bangladesh and Pakistan, distilleries in Kenya, Leather in Ethiopia and Textiles in Tanzania. Synopsis reports on this research were completed during Q4 of FY 2021-22.
1.3: Number of policy briefings and reports providing a synthesis of academic evidence and results aimed at policymakers, regulatory agencies and planners.	At least 1-3	Exceeded 2021-2022: / 5 policy briefings and reports produced. Instituto 17 (i17) policy briefings and reports have been produced as part of SMEP activities, including 4 country, sectoral and thematic factsheets (Tanzania, Pakistan, Bangladesh, Kenya). A policy factsheet on plastic substitutes has been published.

Briefly describe the output’s activities, and provide supporting narrative for the score.
The SMEP programme has exceeded the milestones for FY 2021-2022 and is on track for exceeding the milestones for FY2022-23.

Improved knowledge and understanding of the environmental and health impacts of pollution from manufacturing, including plastics, has been generated in a variety of ways including:
Manufacturing Pollution – Synopsis Series 1: Kenya – Distilleries; Ethiopia – Leather; Tanzania – Textiles
- Manufacturing Pollution – Synopsis Series 1: Kenya and Uganda – Uptake Of Pollution Mitigating Technologies
- Manufacturing Pollution – Synopsis Series 1: Bangladesh – Used Lead Acid Batteries & Tanneries (Pure Earth)
- Manufacturing Pollution – Synopsis Series 1: Bangladesh – Used Lead Acid Battery Manufacture; Pakistan – Tanneries (Global Alliance on Health and Pollution, in partnership with Sustainable World-Air Quality Asia)
- Through UNCTAD facilitation, SMEP reports and insights were acknowledged by the Informal Dialogue on Plastics at the World Trade Organization, as seen through its factual report of October 2021 and its ministerial statement of December 2021. The SMEP study on plastic substitutes served as an important factor which led to the inclusion of plastic pollution issues to be added to the new UNCTAD mandate through the Bridgetown Covenant in 2021. SMEP was also recognized at the UN-Wide Environment Management Group report of 2021 on the issue of plastic pollution, as well as on a report from the High-Level Committee on Programmes (HLCP) on biodiversity and nature-based solutions, issued in 2021.
- UNCTAD advanced additional studies following the 2020 baseline study mapping the manufacturing pollution hotspots in sub-Saharan Africa and South Asia (link). Those studies focused on the Role of Exports in manufacturing pollution in sub-Saharan Africa and South Asia, and on substitute materials to single-use plastics in sub-Saharan Africa and South Asia. The reports generated various by-products, including executive summaries, various thematic and country-case factsheets, as well as a dashboard toolkit (see output 5). The two reports have also been integral to informing the combatting plastic pollution and manufacturing pollution calls.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

The VfM parameters for this output remain broadly aligned with the proposition presented in the business case. There is now a strong partnership between the PMA and UNCTAD and this is delivering significant value to the programme through oversight and engagement over technical and strategic elements of the programme. The SC and ITAP technical advisory systems which were put in place in 2020 have proven successful, as well as the support provided by Technical Assistant consultants who have contributed valuable experience and knowledge to the programme, particularly in procurement processes and now into project implementation.

VfM has also been achieved through the competitive selection of successful projects under the plastics pollution intervention, which are contributing to the growing knowledge production surrounding the environmental and health impacts of plastic pollution, as well as contributing to both GHG reduction and GESI objectives. Grants are being used as efficiently as possible, through planning cross-fertilization learning forums between grantees, anticipated for Q3 FY 2022-23.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

In the past year under review, an additional nested sub-indicator was added: 1.2.ii) “Number of "research outputs" that address the Gender, Equality and Social Inclusion implications of environmental health impacts of pollution from manufacturing”. The first milestone for this is for the upcoming year, FY 2022-23. Should a programme extension be approved output milestones are likely to require further review that also accounts for the performance to date.

 Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress against previous year’s AR recommendations:
- A review of the programme logframe was completed ahead of end FY 2021-22, although delayed by a quarter. The delay was due to a delayed launch of the plastics procurement intervention which required much of the PMA’s resources.
- The PMA/UNCTAD has ensured that logframe indicators are a focus of procurement calls, contracts and monitoring and evaluation processes, which has resulted in contractors remaining focussed on achieving programme output indicators.
Lessons:
In management terms it has proven beneficial to have additional external assistance for targeted quality assurance and review in areas of particular technical complexity and/or novel approach.
Recommendations:
The MERL tracker and dialogues between the PMA and UNCTAD could be enhanced to ensure closer tracking of progress against the logframe.

Output Title	Identification and development of policy and regulatory models that can promote and facilitate the adoption of technology-based solutions to address the pollution caused by manufacturing sector and plastics in conjunction with key stakeholders.
Output number:	2		Output Score:		A
Impact weighting (%):	15		Weighting revised since last AR?		No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of new policy and regulatory models identified	1-5	Exceeded FY 2021-22: / 9 policy and regulatory models have been identified during phase 1 (Q4 FY 2021-22) of the plastics portfolio delivery, as well as progress has been made towards identifying barriers to solutions. / 7 of the grantees funded under C_004 have identified policy and regulatory gaps. 6 of these grantees will be engaging further with policy makers (one grantee, who identified a policy and regulatory gap, did not advance for further funding.) / i17 report identified gaps on public and private governance of exports-linked manufacturing pollution (link) / Graduate Institute report identified policy gaps and misdirected subsidies which act as barriers to the uptake of plastic substitute materials in SMEP regions (link).
2.2 Number of new policy and regulatory models developed	1-3	Met FY 2021-22: 1 model developed, and others in progress / Factsheet produced on Harmonized System (HS) codes of plastic substitutes identified specific tariff lines which could be used by countries to improve manufacturing and competitiveness of plastic substitutes, receiving high interest by WTO members (link). A follow up event on this theme is being organised by UNCTAD. / Research undertaken and case being built for national level policy on improving the manufacturing and competitiveness of plastic substitutes.
2.3 Number of new policy and regulatory models tested and verified for effectiveness and capacity to achieve results in real-life scenario.	1	Partially met FY 2021-22: / 5 in-country workshops were convened in June 2021 in Kenya, Tanzania, Ethiopia, Bangladesh and Pakistan. Each country workshop, presented new policy and regulatory models for further development, with national stakeholders providing input on their acceptability. These workshops made good ground and will lead to more specific information in regards to regulatory models.
2.4 Programme scoping and outreach including development of partnerships with private sector and civil society necessary for achieving the programme targets.	5 events; 1 partnership	Partially met FY 2021-22: / There has been extensive outreach. Scoping and outreach events have been held with the private sector and civil society, including with the ICC. UNCTAD has established a number of working level partnerships, cooperation with external institutions, and contacts with various stakeholders laying the important foundations for more formal partnerships to be developed. Events included: / 1 joint event on textiles held with the World Bank; 1 plastic substitutes event held; 1 alignment dialogue held with UNDP Uganda; 1 workshop with Graduate institute; 1 workshop with i17 on export-linked pollution; 1 SMEP opportunities dissemination event with the International Chamber of Commerce; 4 research seminar sessions involving academic stakeholders. More formalised partnerships have not yet been agreed.

Briefly describe the output’s activities, and provide supporting narrative for the score.

The SMEP programme has made progress in the identification and validation of policy and regulatory models under both the plastics procurement, phase 1 and also via the analytical work of i17. Contributions notably include:
- The FlipFlopi Project has been an official stakeholder providing feedback and recommendations into the Lamu County Government’s establishment of the Municipality’s first Solid Waste Management Policy – which is currently under review. Further, FlipFlopi established a standardised collection and sorting system for community-based organisations and introduced 16 groups across the Lamu archipelago to improve cost efficiency of the recovery and recycling process. These groups will benefit from ongoing capacity building.
- GAIA Biomaterials has significantly contributed to Output 2 by identifying 4 legislative gaps (South Africa and Tanzania) and intends to lobby for change changes including the revival of the National Environmental Advisory Forum along with bodies for self-regulation and sustainable certification. Further, the project has engaged WWF US, and is in the process of negotiating their involvement in co-designing various aspects of the project.
Policy and regulatory models based on SMEP reports were also discussed in various fora and multilateral processes, through events organised by UNCTAD, and in events which UNCTAD contributed to, including at Basel Convention and at the United Nations Environment Programme (UNEP). Those activities helped to disseminate SMEP outputs, including policy analysis insights from studies on exports-linked pollution and plastic substitutes. Activities also helped to establish links between SMEP themes and its projects with related multilateral processes, such as the United Nations Environment Management Group (EMG) on a pollution-free planet and on the United Nations Environment Assembly (UNEA 5.2), which adopted a resolution creating an intergovernmental process towards a binding treaty against plastic pollution by 2024.

UNCTAD, in close cooperation with the PMA, has developed several working-level partnerships with institutions directly working on SMEP or related themes. Many of those partnerships are increasing SMEP impacts beyond the target regions and forging channels of impact into multilateral processes.

- UNCTAD has established contacts with various stakeholders working on industries and institutions of relevance to SMEP. For example, working-level partnerships with representatives from WWF Pakistan tanneries unit, and from fast-moving consumer goods manufacturers (Danone global packaging unit and Snowpeak India).
- Following a successful submission by UNCTAD to the WTO Committee on Trade and Environment, discussing the theme of ocean plastic pollution, SMEP and UNCTAD Blue Economy colleagues have further engaged in multilateral platforms, bringing in knowledge from SMEP components to the WTO IDP. Those contributions involved presentations on studies on substitutes to plastics, including identification of HS codes of alternatives to facilitate trade of less-polluting substitutes, as well as showcasing SMEP-sponsored projects which help trade negotiators understand critical areas for action at the trade sphere which can help projects on the ground reduce plastic pollution. This assistance has been recognised through a ministerial declaration by IDP members in December 2021.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

Prospects of achieving good VfM remain valid. SMEP now has a set of projects underway to help address various aspects of plastic pollution which are innovative, policy relevant and attracting good stakeholder engagement. Other projects relating to manufacturing pollution are in procurement, furthering the potential reach and impact of SMEP.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no major changes to output 2 during the year under review, however there are recommended changes for the next financial year to account for implementation delays resulting from large-scale global events and a potential programme extension. Planned changes for FY 2022-23 are listed below:
- Output 2.1, planned change for the FY 2022-23 milestone from current 5-8 to 6-7
- Output 2.2, planned change for the FY 2022-23 milestone from current 3-5 to 4-5
- Outputs 2.3, planned change for the FY 2022-23, addition of underlined words: Number of new policy, regulatory and standards models tested and verified for effectiveness and capacity to achieve results in real life scenario.
- Output 2.4, planned change for the FY 2022-23 milestone from current 10 events and 2 partnerships, to 8 events and 3 partnerships.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress against previous year’s AR recommendations
A review of the programme logframe was completed ahead of end FY 2021-22, although delayed by a quarter. The delay was due to a delayed launch of the plastics procurement intervention which required much of the PMA’s resources.
The PMA has successfully used the Monitoring Evaluation Reporting and Learning process to how much current research activities contribute directly to meeting the logframe targets.
Lessons:
There are no lessons for this output in FY 2021-2022.
Recommendations:
- PMA to identify opportunities to test/verify policy and regulatory models in “real life” scenarios through responses to the upcoming manufacturing pollution calls (C_005) so as to ensure full coverage of output indicator 2.3 upon SMEP’s completion.
- Develop a clearer typology of partnership and stakeholder engagement and evolution (e.g., embracing spectrum from initial outreach through to formal agreements) for improved progress reporting. (This is also applicable to Indicator 5.1 under Output 5.)

Output Title	Development of technology-based solutions and supporting business models, to reduce the environmental impact and enhance the gender and social equity of selected manufacturing processes including the plastics value chain.
Output number:		3	Output Score:	A+
Impact weighting (%):		30	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of new technology-based solutions identified across all target countries to address key sustainability and pollution issues related to selected manufacturing processes in SMEP target countries.	3-5	Exceeded FY 2021-22: / During phase 1 of the combatting plastics pollution project delivery, 7 technology-based solutions have been identified during Q4 FY 2021-22 from the University of Cambridge MAKEathon.
3.2 Number of new technology-based solutions developed across all target countries to address key sustainability and pollution issues, in SMEP target countries.	1	Exceeded FY2021-22: / During phase 1 of the plastics procurement intervention delivery (Q4 FY 2021-22), 3 new technology-based solutions were developed. Two Biodolomer Ocean prototypes have been developed by GAIA Biomaterials, and a fibre-based lateral flow test cassette developed through the work of PA Consulting.
3.3 Number of successful pilot projects and/or field testing of technology-based solutions developed by SMEP programme across all target countries, providing proof of technical and commercial viability.	No specific milestone for this year. The first milestone of “2 new pilot projects and/or field testing” is set for 2022-2023	On track to exceed FY2022-23: / 1 project under the plastics procurement intervention has already begun testing of technology-based solutions during Q4 FY 2021-22, with at least 5 tests to take place in FY 2022-23. / Additionally, the cleaner production and private sector business models research reports are informing a research call (to be contracted by Q4 FY 2022-23) to advance piloting and testing of technology-based solutions to address manufacturing pollution that (Figure 1).
3.4 Number of grants with objectives to improve GESI as part of the technology or business model being developed	(New output indicator) / 1-2	Met: FY 2021-22: / 2 plastics projects in particular, the University of Cambridge and FlipiFlopi, are demonstrating strong GESI progress through aspects including female participation and employment in the projects.

Briefly describe the output’s activities, and provide supporting narrative for the score.

Despite the impact of large-scale global events resulting in a slower launch of research and development activities, these advanced well in the first half of 2022. The Management Team are taking budget uncertainty-related implementation risks into account and monitoring the evolving situation closely. The combatting plastics pollution intervention has been the main contributor to this output during the past year under review, and the industrial manufacturing pollution call set to launch in Q2 FY 2022-23 is expected to be an integral area for the SMEP Programme’s progress against this output.

FCDO, the PMA and UNCTAD have worked closely to translate the recommendations for technology-based solutions from the SEI-York scoping study into the design of the industrial manufacturing pollution call. In addition, the research on cleaner production and private sector business models in Africa report (link) identified several technology-based solutions relevant to the food and beverages, textiles, metals, cement, paper and pulp, plastics, electrical, pharmaceuticals and motor assembly industries for Kenya and Uganda. Two themes have been identified for a procurement call launching Q2 FY 2022-23: waste to energy (with a focus of organic waste) and industrial reuse of by-products with a focus on water filtration technologies and other chemical recovery processes. Details here for the SMEP piloting technology solutions brochure and here for the SMEP textiles brochure. This research call will very directly contribute to meeting objectives of this output.

Examples from the plastics procurement cohort contributing to Output 3 (see appendix 2 for further details):
- RiverRecycle deployed the first river cleaning technology of its kind in Accra, Ghana.
- University of Cambridge identified 7 new technology-based solutions in Nepal, during the first MAKEathon event. All of the seven MAKEathon teams that generated innovations had a minimum 50% female participants. These technology-based solutions include an insultation layer for highland homes; upcycled mattresses; joinery unit for refugee tents; insulated roofing sheet; sandwich insulation panel and wallpaper; and an insulated water harvesting roofing tiles.
- PA Consulting developed a cassette that is produced using dry moulded fibre technology to replace the plastic in LFT cassettes. The fibre-based solution is biodegradable, whereas the traditional plastic cassettes are not. This technology is expected to reduce the level of plastic waste generated from lateral flow testing.
- The Flipflopi project is planning to do direct purchasing of plastics from local communities and specifically women-led centres. The project is already working to build the capacity of women in their own workforce.
SMEP grantees have also been involved in research and policy events. For example, Chinhoyi and FlipFlopi project team members contributed to research workshops led by UNCTAD in December 2021 and March 2022. Going forward, 7 of the grantees from the plastics pollution mitigation procurement are progressing technical solutions that are expected to enhance quality of life or reduce the burden on women and marginalised communities.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
VfM prospects for this output, building on action achieved under Output 1 & 2, remains valid, although at an earlier relative stage of delivery. The PMA is delivering several procurement new calls and supplier outputs that will be delivered in FY2022-23, which are important to overall VfM of this Output.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

In the past year under review, an additional Output indicator was added: 3.4: Number of grants with objectives to improve GESI as part of the technology or business model being developed. No output milestones were adjusted for the year under review.

The planned adjustments factor in delays resulting from large-scale global events, as well as the likelihood of a programme extension. The planned change is described below:
Output indicator 3.1: the milestone for FY 2022-23 is adjusted from current 5-10 to 6-9
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress against previous year’s AR recommendations:
The SMEP Programme logframe was reviewed in Q4 of FY 2021-22, with proposed changes including GESI and Greenhouse Gas reduction considerations.
Lessons:
With the launch of a large industrial manufacturing procurement call in Q2 FY-2022-23, one important lesson from the plastics pollution intervention is the importance of flexible contractual modalities, with built in adjustment mechanisms to more smoothly cater for subsequent budget modifications if and where needed.
Recommendations:
Should a programme extension be approved output milestones are likely to require further review
Output Title	Establishment of new symbiotic production processes that reduce environmental damage and industrial waste, from manufacturing and plastics value chain, and establish new sources of wealth and growth.
Output number:		4	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1 Number of new symbiotic production processes identified, aimed at reducing waste and pollution from selected manufacturing production processes and value chains in target countries.	1-3	Met FY 2021-22: / Of the plastics procurement cohort, 3 new symbiotic processes have been identified during phase 1 of delivery. RiverRecycle has identified additional business opportunities for PET flakes; Flipiflopi are using waste aluminium as recycled plastic moulds; and PA Consulting are utilising agricultural waste for lateral flow test cassettes.
4.2 Number of new symbiotic production processes developed and established, aimed at reducing waste and pollution from selected manufacturing production processes and value chains in target countries.	No specific milestone for this year. The first milestone of 3 is set for FY 2022-23	On-track FY2022-23: Progress against this future milestone for this indicator is dependent on the foundational work under 4.1 above, which has progressed well. Associated enabling work is underway. Therefore, there is grounds for confidence of the prospects of developing new symbiotic production processes by FY 2022-2023. It is important to note that symbiotic processes require lead time for implementation. / Between 3 and 6 new symbiotic processes developed are anticipated for FY 2022-23 under the plastics procurement stream of work. / The manufacturing pollution intervention contracts completed in FY 2021-22 identified several opportunities for symbiotic processes. These are to be reviewed and evaluated for potential for implementation through SMEP procurement for development in FY 2022-23 under C_005.
4.3 Number of successful pilot projects and/or field testing of new symbiotic production processes, providing proof of technical and commercial viability.	No specific milestone for this year. The first milestone of to Launch procurement contract to identify more detailed symbiotic production processes is set for FY 2023-24	Potentially on track FY 2022-23: Given the foundational progress under 4.1 and some preparatory work under 4.2. At least 3 and up to 5 projects under the plastics procurement stream of work have confirmed they are on track to pilot and/or field test new symbiotic production processes by end FY 2022-23.

Briefly describe the output’s activities, and provide supporting narrative for the score.

SMEP has met milestones set for the year under review is broadly on track to deliver against the milestones of developing and successfully piloting new symbiotic processes. The combatting plastics pollution portfolio of projects has been the main contributor to this output during the past year under review, and the industrial manufacturing pollution call set to launch in Q2 FY 2022-23 is expected to be an integral area for the SMEP Programme’s progress against this output.

During the year under review, the PMA successfully completed the plastics pollution intervention process which resulted in the contracting of 10 grantees for phase 1 (Q4 FY 2021-22), 9 of which have progressed to phase 2 (FY 2022-23). Activities undertaken to achieve output 4 indicators are listed below.
- RiverRecycle’s research has found the PET recycling industry is quite common in other African regions but not in Ghana. From their observations and work with local partners, PET still holds untapped commercial potential in Ghana. Therefore, RiverRecycle and partners are developing an additional PET flakes business to enhance the resource efficiency of the high value plastic waste, and keep PET waste in the loop of plastic recycling and production.
- The variety of sorted materials from FlipFlopi’s collection activities can be utilised directly or indirectly in combination with the plastic recycling facility. Opportunities identified include
      - Using waste aluminium to make moulds for recycling plastic.
      - Using the plastic shredder to shred old slippers and use them in products.
      - Using the energy of non-recyclable waste plastic (incineration/pyrolysis) to heat moulds for the plastic recycling process.
      - Using glass bottles to build functional and infrastructure on the site.
    - PA Consulting has identified material for the dry moulded fibre LFT cassettes could be provided from non-wood waste materials. This feedstock takes waste agricultural materials from local farming and incorporates it into the manufacturing process, acting as a symbiotic process of reducing waste both form the farming process and a reduction in the virgin material required for the manufacturing process
    - Chinhoyi identified plastic solar roof tiles using plastic waste as a raw material to develop the roofing tiles for the construction industry, which have been designed and are currently in the process of piloting.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

The VfM basis remains broadly aligned with the business case. The studies contracted to date have strategic relevance underpinning and shaping future activities. Further, the upcoming industrial manufacturing procurement call is being guided by studies completed during the year under review FY 2021-22. In terms of the plastics pollution intervention, delivery of output 4.1 builds the foundation for the delivery of subsequent output elements 4.2 and 4.3.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

In the past year under review, no changes were made to Output 4.

The planned adjustments factor in delays resulting from large-scale global events, as well as the likelihood of a programme extension. The planned change is described below:
Output indicator 4.1: the milestone for FY 2022-23 is adjusted from current 3-5 to 4-5
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress against previous year’s AR recommendations:
- The SMEP Programme logframe was reviewed in Q4 of FY 2021-22, with proposed changes including GESI and GHG reduction considerations. A further review of the logframe and SMEP Theory of Change is planned for FY 2022-23.
- Pro-active engagement with civil society and organisations working on similar areas as SMEP has proven important to produce a good market response to SMEP calls. It is recommended, similarly to the previous AR, that the SMEP team should maintain and continue to build on the dialogues that were initiated with private sector, multilateral organisations and civil society partners during FY 2021-22.
- The importance of producing primary data collection via fieldwork and engagement with national stakeholders has been built into supplier terms for the industrial manufacturing pollution procurement call; in order to optimally target interventions. This will help identify and develop accurate solutions to the targeted pollution pathways.
- On-ground work with stakeholders advanced, even with enduring COVID restrictions delaying full-fledged technical assistance, due to a pro-active engagement of grantees and local institutions in SMEP-related events and research workshops.
Lessons:
There are no lessons for this output in FY 2021-22.
Recommendations:
- Output milestones are likely to require further review if programme extension is approved.
- A more immediate recommended change to output indicator 4.1 is as noted above.

Output Title	Co-design/development of toolkits to be used by policy makers and planners.
Output number:		5	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
5.1 Number of policy makers and regulators engaged in scoping of needs, as well as co-design and co-production process.	5-10	Met FY 2021-22: / Good initial outreach which has potential to mature into substantive engagement. Initial outreach comprised: / 19 stakeholders engaged as part of country case studies in the role of exports report (Pakistan 7, Bangladesh 1, Kenya 1, Tanzania 10) / 62 stakeholders were also consulted in initial baseline assessment (Nepal 17, Bangladesh 20, Kenya 25)
5.2 Number of toolkits developed and tested through pilot projects and or field-testing.	2	Met FY 2021-22: / 3 tools/toolkits developed: / Interactive dashboard of trade & pollution impacts developed and placed online in beta version as part of the role of exports report, and hazard impact ranking tool tested in 2 target countries as part of the South Asia impact pathways report – in FY 2021-22. See more here / Hazard impact ranking tool tested in 2 target countries as part of the South Asia impact pathways report. More here. / A CSO Coastline Litter Characterisation & Monitoring Toolkit is also in production by FlipFlopi
5.3 Number of policymakers and/or regulators providing a positive assessment/review of toolkits developed and adopting early versions for further development.	No specific milestone for this year. The first milestone of 3 is set for FY 2022-23	Progress FY 2021-22: / Dashboard of trade & pollution impacts expanded (i17) (link) / GAHP impact ranking tool (share point link) trialled in 2 target countries, but policy-makers were not engaged in a formal review process of the tool. / Country members of the WTO informal dialogue on plastics received positive feedback regarding SMEP-related plastic substitutes factsheet (link), calling for dedicated meeting in Q4 2022.

Briefly describe the output’s activities, and provide supporting narrative for the score.

Despite the impact of large-scale global events delaying the launch of research and development activities, SMEP contracted 10 plastics projects under the combatting plastics pollution intervention ahead of Q4 FY 2021-22. 9 plastics projects have proceeded to phase 2 and are on track to contribute to the FY 2022-23 milestone. This highlights that SMEP is beginning to showcase impact in tackling plastics pollution.

Activities undertaken by the plastics procurement cohort during the year under review (phase 1, Q4 FY 2021-22) are listed below:
- International Synergies Limited: The B-Prism conference held in February 2022 involved policy makers and regulatory consultees (academics; industry representatives);
- FlipFlopi: The project is working closely with the Lamu Municipality to determine the logistics, streamlining, and management of waste management systems, through the drafting of the Solid Waste Management policy. Regarding the testing/piloting of toolkits, a baseline survey was conducted using a sampling methodology from the African Marine Litter Monitoring Manual developed by the Sustainable Seas Trust (SST); and a Production Data Calculator has been created and currently being tested to bring together the full chain from collections to manufacturing. From this, FlipFlopi is also creating a standardised toolkit for communities to use where the data can be aggregated to one centralised system.
- GAIA Biomaterials: In Tanzania, consortium members were able to meet officials and institutions whom have a direct influence on the policy and regulatory environments within the Tanzanian fishing sector. Support has been offered in piloting and policy amendment.
The two reports mentioned in Output 1, prepared by UNCTAD, enabled toolkit development. This includes the interactive dashboard developed with Instituto 17. This dashboard combines economic, trade and product life-cycle analysis, to provide governments and industry actors with key export pollution data for manufacturing sectors in 13 countries in sub-Saharan Africa and South Asia. See more here. The dashboard was presented in meetings with policy makers related to the C002 & C003 procurement streams, including the Ethiopian Society of Chemical Engineers, the Cleaner Production Centre of Tanzania, and the Kenya national Cleaner Production Centre. This dashboard is currently expanding for all 13 SMEP target countries to include a thematic focus on plastic substitute materials that can serve as practical options for single-use plastics.

SMEP research prepared by UNCTAD in cooperation with the Graduate Institute has also identified 29 materials and products traded in the Harmonized System whose production could help substitute for the function performed by single-use plastics, contributing to lower environmental pollution. An analysis was also performed for their suitability in the specific context of 3 SMEP target countries. The produced list of potential plastic substitutes has been presented to various audiences, including at the World Trade Organization. The policy recommendations from this work in the Harmonized Commodity Description and Coding System could enable symbiotic processes as it would make it possible to accurately measure the trade flows of materials used for plastics substitution, and apply appropriate tariffs where possible to incentivise changes.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

The VfM parameters for this output remain broadly aligned with the proposition presented in the business case. Planned procurement calls in FY 2022-23 will be crucial for future progress against these output indicators.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no changes to this output during the past year. Should a programme extension be approved output milestones are likely to require further review that also accounts for the performance to date.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress against previous year’s AR recommendations:

- The SMEP Programme logframe was reviewed in Q4 of FY 2021-22, with proposed changes including GESI and Greenhouse Gas reduction considerations. A further review of the logframe and SMEP Theory of Change is planned for FY 2022-23.
- Dialogues which began in the previous FY were continued in order to deepen partnerships with existing programmes for instance Manufacturing Africa and the Circular Economy and Plastics programme to maximise innovation potential and VfM.
Lessons

There are no lessons for this output in FY 2021-2022.
Recommendations
- Output milestones are likely to require further review if programme extension is approved.
- Develop a clearer typology of partnership and stakeholder engagement and evolution (e.g., embracing spectrum from initial outreach through to substantive engagement) for improved progress reporting. (This is also applicable to Indicator 2.4 under Output 2.)

D: RISK

Overview of risk management

The overall risk rating for the SMEP Programme (“moderate”) remains unchanged. Since the last annual review, risks associated with the crisis in Ukraine (context, policy, delivery) have emerged. COVID 19 related budget uncertainty also remains a significant risk to delivery.

Large-scale global events, as well as climate induced disasters continue to pose risk implications for SMEP in the following ways:
1. the increased need to make decisions under uncertainty e.g. procurement planning under year-on-year budget uncertainty resulting from a contraction in UK GNI and the reduction in ODA from 07% to 0.5%, and;
2. the need for regular adjustment of delivery timelines to respond changing global/local priorities.

In light of the disruptions and delays from the above an extension to the programme duration is planned. On an operational level, the PMA has continued to put in place measures to minimise disruption and manage the changing working structure to hybrid work environment. The SC has also continued to convene regularly, meeting virtually two times since the last annual review, providing the necessary oversight for the management of risks being experienced by the delivery team. The PMA has also made use of its Independent Technical Advisory Panel for guidance in several instances where considerations regarding delivery required detailed opinions. In its quarterly reports, the PMA updates the programme risk matrix which tracks programme risk against the FCDO risk categories. The table below summarises the primary risks experienced during the year under review, and the mitigating actions:

Risks	Mitigating actions
Policy and programme delivery: The financial position within FCDO will likely be constrained for FY 2022-23 given the contraction within the UK economy thus the PMA have tapered the procurement trajectory to match available funding. This may impact on the ability to execute the business case’s budget if there is year-on-year budget uncertainty. / Grant finalisation on the plastics portfolio has shown that current FCDO IP related clauses if fully cascaded in entire delivery chain has the potential to be a major disincentive to interested entrepreneurs and effective leveraging of market led responses. This issue may similarly manifest for the new manufacturing pollution related calls being undertaken, and so risks undermining the cumulative scale and VfM of SMEP potential impact.	The PMA’s delivery strategy has been to get multiple contracts into implementation utilising break clauses in contracts to enable a pause in delivery (pending confirmation of annual budget) or, indeed, contract cancellation if required. Furthermore, the PMA has amended its original procurement strategy from three large procurements down to two. The success of the plastics intervention (C_004) procurement has opened the possibility or reducing the total number of procurements necessary for disbursing the total grant fund. / As far as feasible, phase communication with potential grantees such they are not unduly discouraged too early. Ensure variety of SMEPs overall risk management modalities in grant agreements that provides ability to deliver effectively while remaining within overall risk appetite. Continue to share experience of most problematic current IP clauses with PCD, in light of implementation experience. to help inform any wider review of current content of standard contracts
Policy and programme delivery: Ineffective communication of research outputs with policy-makers / decision-makers leads to reduced uptake of SMEP-funded recommendations, policy frameworks, piloting and/or business case implementation.	Work with Supplier Partners' pre- and post- contracting to understand their uptake pathways and, where possible, support these through partnerships (those of PMA/UNCTAD/FCDO or otherwise) and any additional support that the SMEP programme can offer. PMA/UNCTAD to convene quarterly Monitoring, Evaluation, Reporting and Learning Dialogues to highlight areas for joint tasks that can assist programmatic research uptake.
Policy and programme delivery: The Ukraine crisis has and is leading to further global inflation, particularly in the logistics and transport areas, including global shipping.	Ensure regular communication with Supplier Partners and PMA remaining on-hand to find context-appropriate solutions where required. To date, this inflation risk has been relevant for several plastics projects, where for example feedstocks or by-products are transported (including shipping) as part of the commercial model and overall feasibility. This may have consequences for SMEP’s own budget forecasts and the overall business models for the plastics projects themselves.
Context: The Ukraine crisis is leading to both hyper-inflation and shortages in basic foodstuff, and in turn, to scenarios where food security in the SMEP target countries is (and will) become a critical issue. The risk for SMEP is that the relevance and legitimacy of a programme that focusses on manufacturing pollution mitigation may come into question.	The wealth creation and social inclusion aspects of the SMEP projects will become ever more critical and PMA will identify ways to where these aspects can be supported or enhanced. Improved quality of environment also holds potential for improved food production and productivity.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency.

Date of last narrative financial report	15/4/22	Date of last audited annual statement	28/2/21

Financial and commercial performance:
The PMA have spent a total of £967,997 to date (from inception to end of FY 2021-22 - i.e., 31 March 2022) on fees and travel and £1,868,919 on Grant fund drawdown. UNCTAD have received a total of £815,000 in FCDO funds from inception to July 2022.
Projected total payments under the current contract are £1,784,473 inclusive of VAT for the PMA, up to £20,000,000 for the Grant Fund and up to £2.6million for UNCTAD. A contract amendment for PMA and Memorandum of Understanding (MoU) no cost extension for UNCTAD, to reflect changes to budget profile including a time extension and other routine changes, is planned during FY 2022-23. This will ensure VfM and delivery of Outcome.

Reporting and invoicing by the PMA and UNCTAD has been timely and accurate with updates made to the delivery chain mapping accordingly. An asset inventory is being maintained by PMA.
Grant Fund:
Up to the end of FY 2021-22, the PMA has drawn down grant funds from FCDO for four separate procurement exercises. This is summarised in the table below:
Procurement	Grant fund drawdown
Plastics Specialist Technical Assistance	£48,420
Pollution Abatement Intervention Research	£126,750
Private Sector Pollution Mitigation Analysis	£150,000
Plastics Pollution Intervention	£1,543,749
Total	£1,868,919

The Plastics Pollution intervention represents the biggest draw on financial resources to date, and this is anticipated to ramp up in forthcoming financial years, with a potential total budget of approximately £10m. The £1.5m drawn down so far reflects payments made to 10 grantees in the first phase of their projects. Due to budget constraints, 9 grantees of the 10 were retained. These 9 organisations have forecast spend for FY22-23 of £2.2m.
The PMA continue to utilise two payment two modalities, (1) in arrears upon successful delivery of meeting an output or (2) in advance alongside strict financial reporting requirements to determine accurate spend and minimal variance from the original budget. Contractual delays due to uncertainty to the budget and capacity constraints resulted in a delay in delivery by the grantees, however the PMA is confident that the subsequent quarters will realise more effective delivery and robust performance against the set targets.
Partnership commercial considerations:
UNCTAD and the SMEP SC work in partnership across the three themes, providing a range of technical assistance and support services to the programme. In the reporting period, UNCTAD continued as a proactive partner on SMEP providing professional and administrative staff time as in-kind resources. Payments from FCDO to UNCTAD are made based on a bilateral MoU between the two institutions and according to justified payment requests.
VfM considerations:
Economy: the PMA continually to strive to ensure that the lowest possible price has been achieved for programme inputs of the required quality, including noting the key factors that have influenced costs, and applying cost saving measures. The PMA have limited travel, including flights as well as the purchase of assets resulting in a 0% CAPEX costs incurred. Fees will continue to be the cost driver throughout the rest of the programme, although their dominance is likely to decline once the PMA have enhanced their current processes and systems. Spend in the use of experts is still relative with the PMA actively requiring experts to lower their rates where possible without comprising on quality of work. PMA are also undertaking a contract amendment to lower fees when compared to the original budget in the ITT. Grantees are required to secure three quotes for procurement of assets or equipment. Indeed, grantees also apply VfM principles by ensuring that purchased goods and services are produced at the lowest cost, while at the same time ensuring quality and products and services that are fit for the purpose.
UNCTAD, through its partner network, has enabled dissemination of SMEP results in various for fora which were self-funded, and thus provided a means of impact at no direct cost to the programme. UNCTAD’s activity at the 4th Oceans Forum on trade-related aspects of SDG 14 profiled SMEP’s plastics work and involved significant co-contributions in terms of facilities provided, organisational support and staffing from UNCTAD and partner agencies (Commonwealth, The Organisation of African, Caribbean and Pacific States (OACPS), the Development Bank of Latin America (CAF), International Ocean Institute, and the Food and Agriculture Organisation).
Effectiveness: the PMA monitor how the grantees inputs have been converted to programme outputs in terms of quality and quantity. Several of the grantees delivered in line with the project plan and in time with the agreed-upon time frames and have successfully achieved their intended outcomes. UNCTAD has leveraged their established multilateral and international relationships and networks. This included extensive liaison work between the technical assistance components of SMEP, including projects being commissioned and deployed, and related multilateral processes (such as UNEA 5.2, WTO IDP, and related activities such as by Basel Convention and World Economic Forum Global Partnership on Plastics Action.
Efficiency: the PMA encourages and monitors that the grantees activities remain focused on achieving the required outputs and that the correct staff members were assigned to the activities that played to their strengths. The PMA conducts this through a MERL system where Grantees / Service Providers are required to submit a quarterly report 1-month post-quarter-end. This reporting template is submitted via the Caspio online portal - it includes questions related to progress against logframe outcome and output indicators - as well as a chance to elaborate on plans with respect to indicators. PMA can then monitor progress and evaluate the efficiency (and effectiveness) of the grantees. PMA.
Equity: An important aspect of SMEP’s delivery risk is to ‘avoid doing harm’. This includes important Equity considerations, including the Leave No One Behind (LNB) and GESI (Gender, Equality and Social Inclusion) agendas. SMEP’s PMA is also committed to guaranteeing the most effective and high-quality results through open and competitive procurement exercises, which are focused on attracting the highest possible number of suitably qualified potential bidders. Attracting the best possible suppliers includes actively encouraging and enabling a diverse field of bidders, considering factors such as GESI, country of origin and inclusion of people with disabilities. The PMA’s GESI obligation – to promote gender equality of stakeholders in the implementation of its project – is in accordance with the International Development (Gender Equality) Act (2014). GESI considerations are included in the quarterly reporting requirements of the grantees to measure their commitment and adaptation to the requirements. See also section C Output 3 reporting (especially indicator 3.4). Finally, the PMA is currently led by a majority female led team which is positive attribute to the programme’s commitment to equity.
Compliance with FCDO’s Supply Partner Code: Updates to the SMEP Supplier Management Manual (SOMM) has been undertaken and continues to use the Supplier Partner Code (and Programme Operating Framework (PrOF) as core reference points for any standard setting. This is applied in the operations of the Fund and management of downstream partners.

# APPENDIX 1 – EXAMPLES OF PLASTICS PROCUREMENT OUTPUTS

1. https://smepprogramme.org/resources/profile-sheet-pa-consulting/ PA Consulting, the global innovation and transformation consultancy, partnered with Global Access Diagnostics Ltd (GAD) to displace single-use plastic in lateral flow tests (diagnostic cassettes) by replacing them with a cellulose fibre-based product, and ultimately producing these from local agricultural waste.
2. https://smepprogramme.org/resources/profile-sheet-b-prism/ Bangladesh-Plastic Pollution Reduction through Industrial Symbiosis Matching (B-PRISM) aims to foster industrial symbiosis in Bangladesh to divert plastic waste from disposal, mitigating the harmful environmental and social impacts of pollution from manufacturing sectors.
3. https://smepprogramme.org/resources/profile-sheet-gaia-biomaterials/ GAIA Biomaterials, in collaboration with South African-based Kompost-it, FishSA, Alnet, and the Norwegian Independent Research organisation, SINTEF, are replacing harmful polyethene fishing nets with biodegradable nets engineered to match the performance of conventional fishing nets, but if lost or dumped, these nest will disintegrate into biomass without any toxins or micro-plastics.
4. https://smepprogramme.org/resources/profile-sheet-agribiomulchfilm/ The Council for Scientific and Industrial Research (CSIR), South Africa, has collaborated with Elizade University, Nigeria, in AgriBioMulchFilm Project to develop biodegradable mulch films (BDM) by using locally available natural polymers such as starch and other additives to customise biodegradation rates of mulches, to replace the current non-biodegradable Polyethylene (PE) mulch films.
5. https://smepprogramme.org/resources/profile-sheet-the-chinhoyi-university-project/ The Chinhoyi University of Technology, Zimbabwe and Kudiwa Waste and Energy Solutions have teamed up to prototype and then produce solar roofing tiles from plastic waste composite material. By creating a demand for plastic waste as feedstock for the roof tiles, the project plays a vital role in supporting the increased collection of plastic waste and improved revenues for existing waste collectors.
6. https://smepprogramme.org/resources/profile-sheet-ghana-clean-up/ River Recycle, in collaboration with Beach Clean-up Ghana Ltd and Ambitious. Africa is implementing river cleaning technology to collect plastic waste in the Kpeshi Lagoon, engaging the local community in a land-based collection system and creating value for the plastic waste collected by utilising the waste as feedstock for mechanical and chemical recycling.
7. https://smepprogramme.org/resources/profile-sheet-givo-warwick/ The University of Warwick and GIVO Africa have teamed up to tackle the problem of plastic waste in Nigeria by deploying a simple, modular, readily-scalable, sustainable, digital-enabled waste management solution. The GIVO project will develop digital tools to enable smart and efficient operations of GIVO centres.
8. https://smepprogramme.org/resources/fact-sheet-the-plastic-to-ghar/ The University of Cambridge, Impact Hub Kathmandu and Field Ready UK have teamed up to establish an innovation and business support ecosystem to incubate new and emerging businesses working to provide solutions that address plastics wastes, transforming these into durable, long-lasting housing products in Nepal.
9. https://smepprogramme.org/resources/fact-sheet-freshppact-impact-hub/ Blue Skies, in collaboration with Waitrose, has launched the FRESHPPACT Impact Hub (FRESHPPACT) to create a platform that facilitates research and development into the shared environmental challenges facing the fresh produce industry, specifically those with food supply chains rooted in developing or emerging economies.
10. https://smepprogramme.org/resources/fact-sheet-the-flipflopi/ The Flipflopi project has teamed up with CORDIO East Africa, the University of Northumbria and the University of Portsmouth to tackle marine ecosystem health and sustainability challenges by combining indigenous knowledge with modern innovation by constructing traditional sailing and motorised vessels from plastic waste. The project is called Mitigating Plastic Pollution through Heritage Boat Building.