 Programme Completion Review

Title: CSSF Economic Stabilisation Project II
Final Programme Spend £ (full life): £3,109,902.14	Review Date:	April-June 2022
Programme Code: 301189	Start Date: 23/09/2020	End Date: 31/03/2022

Summary of Programme Performance

Year	2021	2022
Programme Score	A	A
Residual Risk Exposure Rating	Major	Major

DevTracker Link to Business Case (and any addendum):	N/A – this programme is CSSF
DevTracker Links to all logframes used during programme lifetime:	N/A – this programme is CSSF

## A: Summary and Overview

Description of the programme and what it has achieved

Yemen’s economy remains in crisis, fragmented, and at risk of further deterioration, exacerbating humanitarian need. The depreciation of the Yemeni Rial has dramatically reduced households’ purchasing power whilst the illegal war economy continues to drive the conflict. While the UK’s main political objective for Yemen is to work towards an inclusive peace process and comprehensive nationwide ceasefire, it is important to recognise the intrinsic relationship and critical contribution of economic and stabilisation activities in achieving that goal.

The CSSF Economic Stabilisation Project II aimed to directly contribute towards Yemen’s economic stability, which is a key outcome in the development/humanitarian pillar of the UK’s National Security Council Strategy for Yemen. The pillar aims to reduce humanitarian suffering and enhance the protection of civilians and build resilience, in line with Campaign Goal 2 of the Yemen Country Business Plan. The project also contributed towards Campaign Goal 3 of the Yemen Country Business Plan. This Goal aims to promote economic stability by supporting the development of sustainable economic policies that prevent economic collapse, increase resilience, and provide incentives for an inclusive political settlement.

Building on the first phase of support in 2019/20, the CSSF Economic Stabilisation Project II responded to political developments in Yemen. It aimed to complement the UK’s political engagement and commitment on the economic and wider economic stabilisation efforts in Yemen through capacity building of key economic institutions, supporting the collection of reliable national statistics, developing analysis on key economic issues and trends, supporting consultations on economic issues related to the peace process, and supporting the creation of a Country Economic Memorandum for Yemen. Due to the conflict having divided the country, the project predominantly operates with institutions in the south of Yemen under the control of the internationally-recognised Government. The exception is the component which worked with the Central Statistical Organisation, which is one of the few national institutions which has not fragmented into North and South.

The CSSF Economic Stabilisation Project II was originally approved in August 2020 with a budget of £1,655,817. The final programme spend (full life) was £3,109,902.14 across seven parts:

1. Capacity building of the Central Bank of Yemen (CBY) and Ministry of Finance (MoF): On the job training and development of operational manuals to support improved public financial management and greater accountability and transparency, leading to increased ability of institutions to stabilise Yemen’s economy. The total value of the component was £1.8 million, and the partner was Pragma, funded through USAID.
2. Restoring capacity of the Central Statistical Organisation: Preserving the capacity of the CSO to compile reliable and more up to date national accounts data, to inform effective economic policy making. The total value of the component was £150,000 and the partner was the World Bank.
3. Analysis of key economic trends and risks and economic data made available: A range of detailed thematic and rapid analysis reports on economic issues and the development of the Yemen Economic Tracking Initiative to track key economic issues. The total value of the component was £668,312, and the partner was ACAPS.
4. Online convening of Yemen economic stakeholders: Consultations on economic issues related to the economic dimensions of the peace process. The total value of the component was £15,853, and the partner was the International Growth Centre (IGC).
5. Assistance to the Executive Bureau to support the development of key policy reform priorities for the Government of Yemen: The total value of the component was £437,801 and the partner was the IGC.
6. Capacity building support to the General Secretariat of the Government of Yemen: Capacity building support to strengthen the General Secretariat’s institutional capacity to facilitate decision-making by the Council of Ministers (CoM). The total value of the component was £121,981.49 and the implementing partners were Adam Smith International and Deeproot.
7. Support the World Bank’s efforts to produce an Analytical Roadmap for Yemen: Supporting the creation of an Analytical Roadmap for Yemen to support and substantively prepare for any potential peace-building discussions. The total value of the component was £115,000. The implementing partner was the World Bank.

Major lessons learned, evidence generated and recommendations

Lessons:

- Quarterly progress reports contained valuable detail. However, requiring this level of details sometimes resulted in FCDO receiving reports later than agreed, making it difficult to pick out the most crucial, relevant information linked to the activities FCDO had funded in a timely fashion.
- In addition to regular informal catch ups to highlight achievements, more formal meetings are required to ensure the project is on track to finalise deliverables within the allocated time period. Otherwise, there will be negative impacts on Value for Money. This formal process should include maintaining a clear framework to track progress against indicators and ensure the content of meetings is recorded in writing, with follow-up tracked.
- Strong and regular communication between implementing partners and their downstream partners is required to keep FCDO updated regarding progress, delays to delivery, and managing expenditure in line with the budget.
- It is essential that logframe indicators sufficiently capture the breadth of work carried out under each output in order for results to be accurately monitored and scored by FCDO.
- An Externally Financed Output (EFO) is a useful agreement to quickly mobilise funds to implement important pieces of work within a tight timeframe. However, it does not always offer FCDO the greatest opportunity to track allocation and expenditure of funds or receive timely formal progress reporting.
- The FCDO programme team decided to decrease the appetite for safeguarding risks under the successor programme ‘Affordability of Food and Finance in Yemen’ (AFFY) due to the high-profile nature of the partnerships/individuals and to reflect FCDO’s zero tolerance for any forms of sexual, physical or psychological harassment, abuse or exploitation of staff, downstream partners or beneficiaries.
- It was identified that not all partners had been subject to a Due Diligence Assessment (DDA) carried out by FCDO Yemen prior to agreements being signed. Therefore, under the successor programme additional vigilance is being applied to ensure that thorough DDAs are in place for each partner to provide assurance of their policies and ability to deliver, and that these are updated every three years.
- Programmes designed to be implemented in a dynamic context such as Yemen, should have high tolerance and flexibility embedded within its components, allowing for the programme team to tap into emerging opportunities.
- The FCDO Yemen team should maintain closer relationships with benefiacaries through regular monitoring and evaluation sessions, in-person and virtual, reflecting end beneficiaries’ comments into current and future programming and allowing FCDO to help resolve any communication issues between partners and beneficiaries.
- Developing risk management measures for better financial management of programme budgets is essential. This includes allocating no more than 50% of programme budget to one component/partner without implementation or financial need guarantees.
- Developing exit strategies as part of any advisory support programming is essential to ensure sustainability and on-going development.
- In the short lifetime of this programme, the turnover within the FCDO Yemen programme team was very high. This was exacerbated by the merger and transformation process. In one year, the programme was managed by three different programme managers and four SROs. Although this was a difficult risk to mitigate, it highlighted the need for record keeping to be efficient and logframes to be accurate.

Recommendations:

- FCDO should carefully produce the new logframe for the successor programme, gaining support from Monitoring, Evaluation and Learning (MEL) and statistics experts, to ensure indicators are relevant to the work being completed, and that targets are stretching, whilst still achievable. The logframe should be reviewed regularly, at least every 6 months, and amended if necessary.
- Under the successor programme, FCDO and implementing partners should formally discuss progress quarterly, with a particular focus on delivery risks to ensure deadlines are met and delays are highlighted as early as possible. This should be in addition to regular informal catch ups.
- FCDO should encourage implementing partners to be more proactive in raising concerns related to slow progress against logframe targets. FCDO should also ensure all partners send written progress and financial updates at least quarterly, and for these to be on time.
- Under the successor programme AFFY, ACAPS are expected to uphold clearer and more regular communication with their downstream partners to ensure expectations and understanding of budgets and targets are aligned. The FCDO Yemen programme team should work with ACAPS to help them meet these expectations. It is recommended that downstream partner communication is monitored quarterly, and reported on in the first Annual Review for the successor programme.
- Under the successor programme, FCDO should be wary of partner deadlines for formal progress reporting to ensure this is aligned to FCDO reporting requirements such as Annual Reviews and Programme Completion Reviews. Careful planning will ensure that results and Value for Money can be more accurately monitored.
- It would be useful for ASI and DeepRoot to present to the World Bank their achievements under output 6: Capacity building support to the General Secretariat. This may influence further capacity building support to the General Secretariat through the World Bank Multi-Donor Trust Fund which FCDO are supporting under the successor programme.
- Under the successor programme, FCDO should ensure exit strategies are in place when applicable to ensure continuity, sustainability and VFM.
- Under the successor programme, FCDO should carefully monitor the World Bank Multi-Donor Trust Fund progress against spending as it represents more than 80% of programme budgeting during the first year of programming. To allow for more flexibility and viability within the Yemeni dynamic context, FCDO programming should embed higher flexibility and on the spot identification of interventions.

How this report was conducted

This PCR was conducted with a desk-based approach and no site visits were completed. It draws on evidence from partner reporting, information from FCDO’s financial management system, and the 2021 CSSF Economic Stabilisation Project II Annual Review.

The FCDO Yemen programme team also conducted a series of in-person and virtual meetings with implementing partners and downstream partners, in addition to beneficiaries such as; the Central Bank of Yemen (CBY), Ministry of Finance (MoF), and the Executive Bureau of the Prime Minister’s Office.

Actions following approval of this report

The FCDO programme team should work with partners to implement the recommendations of this Programme Completion Review to enhance delivery under the successor programme ‘‘Affordability of Food and Finance in Yemen’ (AFFY).
## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	Initial budget: £1,655,817	Final spend: £3,109,902.14
Timeframe	September 2020 - March 2022	September 2020 - March 2022
Outcomes	Integrity of key Yemeni economic institutions maintained; with more economic opportunities for women/youth / Budget prepared for 2021 / Updated national accounts data used to inform interventions / High quality data on the economy made available / Improved understanding of key economic issues related to the peace process	The following Yemeni institutions were supported: The CBY and MoF under Output 1, the Central Statistical Organisation (CSO) under Output 2, the Executive Bureau under Ouput 5, the General Secretariat of the Government of Yemen under Output 6 / This was achieved through FCDO’s funding to USAID and Pragma under Output 1, by providing capacity building to the CBY and MoF / Under Output 2, the base year for national accounts series was changed and best practice for data collection mechanisms training delivered to the CSO. It was concluded that compiling quarterly national accounts of good quality was unfeasible in Yemen at time of this output’s operation. / Under output 3, ACAPs published the interactive Yemen Economy Tracker Initiative (YETI) dashboard with three specialist economic analysis modules / Output 7 aimed to leverage innovative analytical frameworks and advanced econometric approaches for the estimation of economic aggregates, and to identify possible avenues forward after the conflict

Overall assessment of programme outcomes, sustainability and VfM

Progress towards achievement of programme outcomes included: enhanced independence and capacity of the Central Bank, as evidenced through improvements to CBY governance and structure, establishment of an FX auction, and implementation of recommended policy actions from the IMF staff review; preparation of the first state budget since 2019; leadership role played by the Executive Bureau across institutions, including on the fuel grant programme, government energy strategy, and macro-economic stabilisation plan; establishment of an economic track within the UN-led peace process with the framework produced by this programme’s fourth component being used as a foundational, guiding document by the UN Special Envoy’s team; establishment of a high quality platform with live economic data, open to policy makers and humanitarian partners.

The programme outcomes were partially dependant on external factors. As outlined in the theory of change, this was based on assumptions that a peace process remains viable and parties to the conflict are engaging on it; the conflict does not escalate to the extent that project activities are no longer possible; the effects of project activities are sustainable over time and there is continuous engagement and coordination with key stakeholders. Over the programme period, the UN-led peace process continued to face delays and there were escalations in both military and economic conflict. However, the theory of change assumptions continued to hold, and economic deterioration – the main factor behind rising levels of humanitarian need over the period - strengthened the justification for this programme.

The CSSF Economic Stabilisation Project II delivered good Value for Money in a number of ways. It was FCDO Yemen’s flagship contribution to Campaign Goal 3 – promote economic stability. It also directly contributed to Campaign Goal 2 – alleviate humanitarian crisis – and Campaign Goal 4 – support institutional resilience. In addition to the achievements at output level, this programme helped FCDO Yemen establish political influence in Yemen, facilitating a number of direct engagements with the Central Bank of Yemen, Ministry of Finance, Prime Minister’s Office, and the Executive Bureau of the Prime Minister’s Office. Therefore, Value for Money was maximised as UK policy decision making and advisory services were supported.

The CSSF Economic Stabilisation Project II demonstrates the UK’s continued leadership and determination to end the world’s largest humanitarian crisis through sustainable solutions. It rightly recognises and champions the intrinsic connection between economic stability and humanitarian needs.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators

The theory of change which underpinned this programme is that technical assistance to key economic institutions and analysis of economic issues (outputs) will support improved understanding by FCDO, the Government of Yemen and the Central Bank of issues related to the economy, ensure high quality data on the economy is made available to a range of stakeholders and support improved functionality of economic institutions (outcomes) and this in turn will contribute to economic stability, reduced humanitarian need and a sustainable peace process that gives due consideration to the economic drivers of conflict (impact).

The theory of change was not amended during the life of the CSSF Economic Stabilisation Project II.

## C: Detailed Output Assessment

Output Number and Title		Capacity building of the Central Bank of Yemen (CBY) and Ministry of Finance (MoF)
Output Score		A+
Impact weighting (%)		50%	Impact weighting revised since last AR?	No

Output Indicator	Final Logframe Target		Final Result Achieved
1.1	Assistance provided to CBY to facilitate continued progress towards full scale reorganisation of the Banking Supervision Department		Met expectation: ERLP experts developed the 2022 Annual Bank Inspection Plan and circulated it to CBY senior management. They also completed on-site expections of two commercial banks.
1.2	Technical assistance and training provided to implement organisational restructuring reforms and promote systematic progress in anti-money laundering / counter-terrorism (AML/CFT)financing onsite inspections		Met expectation: ERLP collaborated with the Financial Intelligence Unit (FIU) of Yemen on the inspection of two banks and 12 exchange houses to look at their AML/CFT procedures and standards.
1.3	Technical support to CBY to efficiently manage major frozen reserve accounts, to introduce more competitive, transparent FX allocation policies, implement foreign reserve investment guidelines, and systemic restructuring and skills upgrading of the FX Management Department		Moderately exceeded expectation: The FX auction process exceeded FCDO’s expectations. The ERLP team provided hands-on training during each of the auctions and coordinated closely with the IMF to ensure best practice was applied.
1.4	Assistance provided to further advance CBY’s institutionalisation of macro-financial data collection/analysis and related reporting efforts		Moderately exceeded expectation: ERLP experts delivered essential training to CBY staff on monetary programming, policy, and in conducting transparent FX auctions. This was done in line with the money supply parameters set out in the annual monetary plan, which ERLP experts also designed and implemented for 2022.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

Component funded from September 2020 – 31 March 2022 (reported on in 2021 Annual Review)
Component budget: £1.8m
Component final spend: £1.8m
2021 Annual Review Score: A+

FCDO renewed its support to the provision of technical assistance to Central Bank of Yemen (CBY) Aden for a second phase, through USAID’s Economic Recovery and Livelihoods Programme (ELRP) under the CSSF Economic Stabilisation Project II, starting in September 2020. This built on Phase I of the FCDO’s partnership with USAID and downstream partner Pragma under a previous project. FCDO provided a third batch of support to USAID covering November 2021 – March 2022 to provide additional strategic assistance through a combination of on-site mentorship and on-the-job training support to CBY and Republic of Yemen Government (ROYG) Ministry of Finance (MoF) stakeholders in Aden. Technical assistance and capacity building during the third phase was successfully delivered on the following functional areas:

1. Bank Supervision and Risk Management
2. Anti-Money Laundering and Counter Financing of Terrorism (AML/CFT)
3. Foreign Exchange (FX) Management
4. Macro-Financial Statistical and Policy Analysis Activities

This review will focus on the achievements linked to FCDO’s third phase of funding as these build on the second phase targets which were all met and explicitly covered by the 2021 Annual Review.

Output indicator 1.1: Bank Supervision and Risk Management

The 2022 Annual Bank Inspection Plan was developed and circulated to CBY senior management. The Plan sets out the fundamental principles governing the assessment of information collected on each bank during the ongoing on-site inspections. This resulted in elaborating a comprehensive inspection schedule based on the level of risk each bank demonstrates. The On-Site Inspection Division performed inspections of two commercial banks between January-March 2022, of which the ERLP supervision expert reviewed the initial findings; and provided recommendations regarding the need to expand the review of particular aspects for greater accuracy. Officials from the On-Site Inspection Division received a series of targeted training sessions on risk-based supervision concepts related to the analysis of prudential standards, and the assessment of risk, risk rating, and ranking. In addition, the CBY Off-Site Supervision Division received additional training on risk analysis, and the Exchange House Off-Site Supervision Unit received capacity-building training to establish a set of prudential standards and corresponding thresholds that will be applied to the exchange houses.

Output indicator 1.2: Anti-Money Laundering and Counter Financing of Terrorism (AML/CFT)

ERLP assisted the Financial Intelligence Unit (FIU) of Yemen in strengthening and expanding its international AML/CFT relationships by helping them develop and execute Memoranda of Understanding (MOU) with other national FIUs on AML/CFT cooperation. Each MOU provides for the exchange of AML/CFT information in accordance with the requirements of international standards. The FIU of Yemen executed MOUs with two nations and sent letters to six other national FIUs. ERLP also supported the FIU with conducting inspections of financial institutions to determine the extent to which they were adhering to AML/CFT procedures and standards. ERLP collaborated with the FIU on the inspection of two banks in addition to 12 exchange houses. As a result of the inspections, seven financial institutions were found to have material deficiencies in their AML/CFT compliance systems; and the FIU sent directives to these establishments advising them of the deficiencies and the required corrective measures.

Output indicator 1.3: Foreign Exchange (FX) Management

Approximately USD400 million of the USD455 million of Yemen’s frozen reserves was being held in two major accounts; Bank of England (BoE) and Bank of International Settlements (BIS). ERLP experts worked with the CBY to finalise the required documentation to release the frozen BoE and BIS deposits and received strong indication that this was imminent at the end of March 2022. Following the closure of this programme, the BoE reserves were unfrozen, which is also a key step towards a successful conversion of up to $665 million of IMF Special Drawing Rights for Yemen. ERLP produced ‘The Reserve Investment Management Policies and Guidelines’ prototype covering the general policies and procedures linked to reserves management. The proposal was well received by the CBY and full adoption was expected in the quarter following March 2022. In addition, the ERLP FX advisory team developed a comprehensive FX auction regulatory framework to provide flexibility for the CBY to intervene as needed, safeguard the stability of the Yemeni Rial, and step back to its traditional regulatory and oversight function. FX live auctions commenced in October 2021 with a majority weekly frequency, increasing to twice weekly for a period. The ERLP experts provided hands-on training during each of the auctions. They also coordinated closely with experts from the IMF to ensure best practice was applied, and to support the CBY team in adjusting the approach according to market response. In addition, the ERLP experts submitted a proposal to the CBY, outlining a significant revamp of their organisational structure. This includes the renaming of the department from ‘The Department of Foreign Operations’ to ‘FX Reserves Management and Foreign Banking Operations’, changes to the make-up of their current divisions and the creation of three new divisions to modernise the structure and enhance efficiency. This proposal was endorsed in principle by the Governor.

Output indicator 1.4: Macro-Financial Statistical and Policy Analysis Activities

ERLP experts assessed the implementation of the annual CY 2021 monetary plan and related cash currency circulation programme and designed and implemented a sound monetary plan for CY 2022. In addition, the experts finalised the related cash currency management programme as a core document to guide the CBY in performing effective monetary control. ERLP collaborated intensively with the Monetary Research Department to strengthen staff capacity to conduct rigorous research and relevant analysis of macro-financial developments to support well-informed and calibrated monetary policy decision-making. This included targeted training and drafting and disseminating flagship publications such as the Quarterly Bulletin – Economic and Monetary Development. The training delivered to CBY staff focused on the areas of monetary programming, money demand estimation, and monetary policy formulation. As mentioned above, ERLP experts also assisted CBY staff in conducting transparent FX auctions. This was done in line with the money supply parameters set out in the annual monetary plan, with the primary objective of reinforcing the new monetary policy transmission channels and facilitating the adoption of more proactive liquidity management policies by banking institutions.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

The quality of deliverables and relationships built through this output constitute good VfM (Effectiveness). Similarly, the broader impact of this work is beneficial to FCDO’s other programmes in Yemen and diplomatic engagements.

This output delivered VfM as FCDO capitalised on USAID’s existing Economic Recovery and Livelihoods Programme (ERLP), saving on procurement and administrative time and costs. Support to this programme also brought the work of the FCDO and USAID closer together, complementing diplomatic engagement between the US and the UK on Yemen’s economy. Finally, the fee rates of the ten ERLP consultants were initially examined by FCDO’s Procurement and Commercial Department and deemed to be competitive. The ERLP consultants are the only specialists engaged in economic capacity building operational on the ground from Aden, making this programme unique within the donor community’s offering to Yemen.

Lessons learned through this output, and recommendations for future programming

Lessons:

- Pragma quarterly progress reports are incredibly detailed. However, this can result in FCDO receiving reports slightly later than agreed and it can be difficult to pick out the most crucial, relevant information linked to the activities FCDO has funded.
- The ERLP experts coordinated closely with IMF experts to ensure best practice was applied, and to support the CBY team in adjusting the approach for the FX auctions according to market response. This is a prime example of strong international coordination and open collaboration.

Output Number and Title		Restoring capacity of the Central Statistical Organisation
Output Score		A
Impact weighting (%)		5%	Impact weighting revised since last AR?		Yes, reduced from 15% to 5%

Output Indicator	Final Logframe Target			Final Result Achieved
2.1	Update the base year of the national accounts			Met expectations: Completed March 2021
2.2	Compile supply-use table (SUT) for the new base year			Met expectations: Completed
2.3	Compile annual national accounts series			Met expectations: Completed
2.4	Compile quarterly national accounts			Cancelled: Detailed evaluation suggested that compilation of quarterly national accounts was unfeasible given the lack of good quality short-term indicators
2.5	Review the CSO’s data collection mechanism for national accounts compilation			Met expectations: Completed September 2021

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

Component funded from September 2020 – September 2021 (reported on in 2021 Annual Review).
Component budget: £150,000
Component final spend: £150,000
2021 Annual Review Score: A

As outlined in the 2021 Annual Review, the Central Statistical Organisation (CSO) is a vital economic institution that remains united and politically neutral. Due to the departure of a large number of managerial and experienced technical staff, the CSO’s capacity was severely eroded in the past few years, while deteriorating security conditions and geographical divisions significantly reduced the CSO’s ability to collect statistical information to cover all activities and all parts of the country. In the absence of reliable statistics and up-to-date information, the IMF and World Bank were unable to update a Debt Sustainability Analysis for Yemen, which was last conducted in 2014. Given the importance of reliable statistics and evidence for the formulation and monitoring of reconstruction and development plans in the future, it is crucial to rebuild and preserve the CSO’s capacity to compile reliable National Accounts indicators.

Under this output, FCDO funded two economists and two national accounts experts from the World Bank’s Research Department to provide technical assistance to the CSO to restore and preserve their technical capacity eroded by the conflict and produce Yemen’s national accounts (NA) indicators, information vital for the effective decision-making for reconstruction and development.

2.1: Rebasing of National Accounts Series entails replacing the old base year used for compiling the constant price estimates to a new, more recent base year. This allows for comparisons with more recent prices in the economy and increases the relevance of the information.

Completed in March 2021. The World Bank developed a good understanding of Yemeni national accounts, data sources and compilation methodology, updated the methodology with CSO to better suit the context, provided training on national accounts compilation, and reached a consensus with the CSO to change the national accounts base year from 2000 to 2012 (the year with the best data quality and quantity across sectors).
2.2: Supply use tables (SUTs) provide an overview of the availability of goods and services (supply) and the destination (use) of the production, among the different sectors of economic activity.

Completed in December 2021. The CSO had never produced a comprehensive SUT before. To build a brand-new SUT, the Bank team designed a complete SUT compilation framework in Excel, with more than 40 standardised files, all linked to a standard SUT. The team trained CSO officials in the use and update of such a framework for national accounts compilation purposes, which can be easily re-used to compile SUTs on a regular basis. The various compilation files were populated by CSO staff with the Bank team’s support by the end of December 2021, slightly after the end date of this project.
2.3: The completion of a SUT enables the compilation of national account series. Once the SUT is completed and balanced, GDP components can be extrapolated. GDP can then be calculated as the aggregation of the extrapolated components. A balancing process is then required at the national accounts series level to ensure supply and demand GDP are equal.

Completed in January 2022. The Bank Team designed and presented a simplified GDP extrapolation framework in Excel based on price, volume and/or value indicators for the different GDP components. This framework can be used by CSO to produce GDP estimates on the run, and figures should be updated when revisions to annual GDP figures are conducted. Separate files for supply-GDP and demand-GDP were elaborated, and chain-linked GDP figures can be easily obtained from it. This component was completed by the end of January 2022, slightly after the end date of this project.

2.4: Compilation of quarterly national accounts had never been completed for Yemen.

Cancelled. Following a detailed assessment of data availability and quality of information, the Bank team concluded that compiling quarterly national accounts of good quality was unfeasible in Yemen at that time. The Bank team agreed to design comprehensive material and train CSO staff in the techniques that should be applied, so that CSO has the capacity to compile quarterly national accounts once the availability and quality of short-term indicators and annual accounts is ensured.

2.5: The Bank team viewed the strengthening of CSO’s data collection mechanism as one key component of national accounts (NA) compilation.

Completed in September 2021. The Bank NA experts identified CSO’s data collection mechanism to be a major weakness in NA compilation. The mechanism was based on an old collection approach, which relied on a lengthy process of transmitting data through multiple government agencies, not allowing the CSO to obtain information directly from the original sources. This approach is complex, extremely time consuming and costly as it requires setting up multiple intra-agency/ministry committees to complete the task. While there was scope to modernise the existing mechanism, the conflict situation, including the fragmentation of government functions, prevented the introduction of a new system. In this context, the Bank team presented international good practices of data collection mechanisms for their future use.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

Effectiveness: The quality of deliverables and relationships built through this project constitute good VfM. Similarly, the broader impact of this work is beneficial to FCDO’s other programmes in Yemen and diplomatic engagements.
Reliable and up-to-date information is crucial for the formulation and monitoring of development plans. Therefore, other FCDO programmes will benefit from this project’s outputs, through improved evidence for decision-making and planning.

Economy: The FCDO and World Bank teams negotiated a lower allocation of overheads for this project, compared to the organisational standard rate. This reduced the project cost and increased the percentage of funding going to direct activities.

Lessons learned through this output, and recommendations for future programming

Lessons:

Informal reporting and partnership communication is particularly important in addition to formal reporting.
Recommendations

FCDO should proactively engage with other institutions considering funding technical assistance to the CSO to ensure the sustainability of this project’s outputs and discourage fragmentation. FCDO should leverage its relationships to encourage other institutions to consider the most appropriate timing for further technical assistance (e.g., immediate term, or recovery/reconstruction period). Future technical assistance could address related information areas, such as external debt or public finances, that will improve the quality and overall statistical capacity in Yemen.

Output Number and Title		Analysis of key economic trends and risks and economic data made available
Output Score		A
Impact weighting (%)		15%	Impact weighting revised since last AR?		No

Output Indicator	Final Logframe Target			Final Result Achieved
3.1	Interactive YETI dashboard with a landing page and 3 specialist economic analysis modules			Met expectation: https://yemen.yeti.acaps.org/ is now live
3.2	Interactive display of daily monitoring and tracking of key economic trends and risks of Yemen based on Yemen Economic Analytical Framework			Met expectation: Available to view on https://yemen.yeti.acaps.org/
3.3	Two thematic products: One product on Yemen Financial sectors and another one on Private Sector			Moderately did not meet expectation: Yemen Financial Sector analysis paper finalised and draft paper on Innovation in the Yemen Private Sector delivered before 31 March 2022
3.4	Rapid analysis support to FCDO on demand (4 products) - Topics will be emerging trends in Yemen economic and will be based on FCDO requests			Moderately did not meet expectation: Four flash analysis papers delivered, however one paper was still in draft form on 31 March 2022
3.5	Joint analysis meetings to disseminate findings from the research (4 sessions including dissemination of two thematic research products)			Met expectation: Joint analysis sessions conducted with ICG, FCDO, MC, UNOCHA, UN Special envoy office, and INGOs for the Yemen fuel price analysis paper and the economic benefit of peace flash analysis paper

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

Component funded from November 2020 – 31 March 2022 (reported on in 2021 Annual Review)
Component budget: £668,312
Component final spend: £649,896
2021 Annual Review Score: A

The purpose of this output is to provide a platform, which tracks key economic trends, developments and risks in Arabic and English to support economic policy making for Yemen; and to make these accessible to a wide range of Yemeni and international stakeholders through an online interactive dashboard.

The Yemen Economy Tracker Initiative (YETI) dashboard landing page was made live with the addition of three new modules; FX rate and commodity price, import and export, and IPC food emergency analysis. An interactive display of daily monitoring and tracking of key economic trends and risks of Yemen based on the Yemen Economic Analytical Framework was also added to the platform. On the 14th March 2022 more than 64 people attended the YETI platform webinar to launch the new modules, while there were over 10,000 twitter engagements with the announcement of the platform’s launch. Between April 2021 to March 2022, the YETI platform had more than 3500 unique visitors with the average visits per month being 294.

Following the completion of a thematic analysis paper on remittances split into two phases as reported in the 2021 Annual Review, a further two thematic papers were delivered on the Yemen Financial Sector and Innovation in the Yemen Private Sector. However, FCDO received the draft Private Sector paper at the end of March 2022 and therefore was unable to comment and finalise the paper within the CSSF Economic Stabilisation Project II timeline. The previous thematic paper on remittances was downloaded more than 415 times between publication and March 2022 and was referenced in various reports by USAID, Save the Children, Yemen HNO 2022 and others.

Following the completion of two flash analysis papers as reported in the 2021 Annual Review, a further four flash analysis papers were delivered on the economic benefit of peace, fuel price analysis, an ESCROW account, and a political economy analysis on the Private Sector in Wartime Yemen. However, similar to the above, FCDO received the draft political economy analysis at the end of March 2022 and therefore was unable to comment and finalise the paper within the CSSF Economic Stabilisation Project II timeline. As a result of the two papers not being finalised, there was an underspend against the ACAPS budget for phase 3 of YETI.

The following joint analysis sessions were undertaken to disseminate research findings:

- The Fuel analysis paper was presented to the FCDO and UN Special envoy Yemen office. More than 15 people attended.
- The paper on Yemeni remittances was presented to the IMF, World Bank, UN Special Envoy Office Yemen, UNOCHA Yemen, and CCY Yemen. More than 40 people attended across different dates.
- The Yemen Financial thematic paper was presented to Technical Advisory Committee (TAC+) members (with representatives from FCDO, KSA, UAE, IMF, World Bank, and USAID). 31 people attended.

It must be noted that at the end of May 2022, FCDO had not received the final quarterly progress report for January-March 2022 from ACAPs. Therefore, the results recorded in this PCR were taken from an informal written update of progress against the output indicators.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

One thematic analysis paper and one flash analysis paper was not finalised when the CSSF Economic Stabilisation Project II closed. FCDO received the draft reports on the last operational day of the programme which did not allow time to provide comments and revise the reports. Although this resulted in a cost saving for this component, FCDO received a reduced value for the funds already disbursed as the draft reports were not in the condition expected in order to have the required impact. It also created an underspend against the programme budget.

However, this output delivered Value for Money in other aspects. ACAPS and Mercy Corps saved the set-up costs of the online dashboard by utilising an existing agreement with Amazon Web Services to host it at no additional cost to the FCDO. The dashboard also built on existing, established analysis capacity already available within ACAPS and Mercy Corps. This helped keep cost down by sharing costs including office rent, management and support staff across a broader base, which freed up funding to focus directly on delivering analysis products.

Lessons learned through this output, and recommendations for future programming

Lesson:

- In addition to regular informal catch ups to highlight achievements, more formal meetings are required to ensure the project is on track to finalise deliverables within the allocated time period. Otherwise, there will be negative impacts on Value for Money. This formal process should include maintaining a clear framework to track progress against indicators and ensure the content of meetings is recorded in writing to be followed up on.
- FCDO identified a lack of communication at times between ACAPS and their downstream partner, Mercy Corps. For this reason, FCDO was not informed of the delays in drafting two of the analysis papers until it was too late to rectify, resulting in an underspend against the budget.

Recommendation:

- Under the successor programme AFFY, FCDO and ACAPS should discuss progress at least quarterly with a particular focus on delivery risks to ensure deadlines are met and delays are highlighted as early as possible.
- Under the successor programme AFFY, ACAPS are expected to uphold clearer and more regular communication with their downstream partners to ensure understanding and expectations around budget, deliverables, and deadlines are aligned. The FCDO Yemen programme team should work with ACAPS to help them meet these expectations. It is recommended that downstream partner communication is monitored quarterly, and reported on in the first AFFY Annual Review.

Output Number and Title	Online convening of Yemen economic stakeholders
Output Score	A
Impact weighting (%)	5%			Impact weighting revised since last AR?	No

Output Indicator		Final Logframe Target	Final Result Achieved
4.1 Number of consultations and accompanying reports on topics agreed with FCDO Yemen		3	Met expectation: Consultations were conducted and reports delivered on 3 topics agreed with FCDO Yemen and OSESGY.
4.2 Number of consultation findings reports presented to the OSESGY		3	Met expectation: Reports delivered on 3 topics presented to the OSESGY

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

Component funded from 25 September 2020 – 31st March 2021 (closed by the time of the 2021 Annual Review)
Component budget: £15,853
Component final spend: £15,853
2021 Annual Review Score: A

Between November 2020 and March 2021, the IGC held consultation sessions with Yemeni and international stakeholders regarding three main topics:

- Public sector salaries in Yemen: Towards building confidence in the peace process
- Fuel imports to Hodeida: Towards building confidence in the peace process
- Options for an economic track of the Yemen peace process

The consultations aimed to better understand and document the views of different stakeholders regarding these critical issues, in an attempt to provide a structured framework and common base for discussion that could support the ongoing peace negotiations. IGC produced 3 reports, one on each topic, detailing the findings from the consultations and suggesting potential solutions to these issues.
All three reports were presented to the Office of the Special Envoy of the Secretary General for Yemen (OSESGY). OSESGY welcomed the engagement with the IGC and expressed the value of the work. The newly appointed Senior Economic Adviser to the Special Envoy has since explained that these reports have been foundational documents in supporting the establishment of a new economic track within the UN-led peace process. The third report came as a direct request from OSESGY. Reports were also shared with international organisations and multilateral development banks involved in Yemen. All reports were translated to Arabic.

The project initially envisioned Yemeni economic advisors being trained on peace processes in-person. Due to the outbreak of Covid-19, in-person training was no longer possible. As a result, the scope and activities of the project were changed to instead involve the IGC conducting several rounds of consultations. The consultation rounds took longer than initially envisaged, due to involving a greater time commitment than anticipated and delays in scheduling consultations. As a result, the following adjustments were agreed i) no-cost extension to 31 March 2021 and ii) a reduction in the number of consultation topics from 4 to 3.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

The reduction in the number of consultation topics from 4 to 3 resulted in a reduction of the project budget from £19,484 to £15,853.

This output delivered VfM as FCDO maximised a small amount of funding to successfully engage and bring together key economic actors on critical economic priorities

Lessons learned through this output, and recommendations for future programming

Lesson:
In order to deliver effective consultations, more time, effort and resources needed to be committed than originally planned. IGC encountered delays beyond their control when scheduling the consultations, but also engaging with partners and local and international stakeholders proved to be a lengthy process.
Recommendation:
For holistic cohesion, FCDO should ensure that any future work in this area is based on: an economic track, recommendations to OSESGY from this component, and additional analysis as required.

Output Number and Title	Assistance provided to the Executive Bureau to support the development of key policy reform priorities for the Government of Yemen.
Output Score	B
Impact weighting (%)	15%			Impact weighting revised since last AR?		No

Output Indicator			Final Logframe Target		Final Result Achieved
5.1 Electricity sector reforms: a. identification of interventions that could improve service and reduce costs b. number of policy papers developed c. number of workshops held with key stakeholders			a. complete / b. 2 (1 complete, 1 expected) / c. 1		a. complete / b. 1 complete, 1 to be finalised / c. dissemination for one report done, not for other / Moderately does not meet expectation
5.2 Macroeconomic stabilisation: a. identification of interventions to control inflation, stabilise the currency, and coordinate monetary, fiscal and trade policies b. number of policy papers developed c. number of workshops held with key stakeholders / d. number of strategic reflections on reform priorities / e. review of EB’s draft macro reform framework			a. complete / b. 3 / c. 2 / d. 2 / e. 1		a. complete / b. 3 / c. several workshops or roundtables for the 3 policy papers / d. none, consultations were internal to government / e. none, not yet requested by Executive Bureau / Moderately does not meet expectation
5.3 Telecommunications sector reform: a. identification of urgent priorities including the feasibility of and best approaches to implement PPP projects, potential tools and approaches to de-risk private sector investments, and identifying priority sectors for investments b. number of policy papers developed c. number of workshops held with key stakeholders / d. focus groups with private sector actors and others			a. complete b. 1 c. 1 / d. 3		a. complete / b. 1, although still in draft / c. none, to be held imminently / d. none, to be held imminently / Moderately does not meet expectation
5.4 Support to prioritisation of key policy reforms: a. advice on best approach to prioritise reforms identified by the government b. number of policy papers developed c. number of workshops held with key stakeholders			No targets set		No targets set
5.5 Number of strategic conversations between senior GoY leaders and relevant IGC experts, including under 5.4c.			3		1 delivered, 1 ongoing / Substantially does not meet expectation
5.6 Number of embedded technical specialists			4.5		5 embedded specialists in post (4 full-time, 1 part-time) / Met expectation

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

Component funded from December 2020 – March 2022 (reported on in 2021 Annual Review)
Component budget: £437,801
Component final spend: £437,739
2021 Annual Review Score: B

FCDO provided the founding £3 million contribution to the World Bank trust fund that oversaw the establishment of the Executive Bureau, as part of efforts to take forward the Mutual Accountability Framework to track economic and policy reforms. Following the Executive Bureau’s recalibration in 2019, the FCDO provided further funding to hire policy experts on consultancy contracts to deliver priority projects. These five experts were embedded into the Executive Bureau, complementing and maximising the impact of GoY’s own funding.

FCDO’s funding under this output supported much needed reforms on food prices, electricity and the private sector. The majority of the final indicator targets were not fully met, meaning that this output scored a consecutive B. However, the logframe indicators do not sufficiently capture the breadth of work completed. The following list is a small selection of the additional activities carried out by the embedded experts which were not linked to indicator milestones:
- Providing input to the Saudi Fuel grant negotiations
- Producing a policy brief on enhancing local revenue mobilisation in conflict
- Identification of priority projects for usage of Yemen’s Special Drawing Rights
- Producing a policy brief on government approaches to addressing the issue of war risk insurance

5.1 Electricity sector reforms:
One policy paper on improving electricity services in Yemen has been published. The second paper on private concessions in the electricity sector was not finalised by 31 March 2022. There has been dissemination and engagement with government and non-government stakeholders on the first report. The same is envisioned for the second report after it has been finalised.

5.2 Macroeconomic stabilisation:
Policy papers were developed by experts on monetary analysis, the Economic Stabilisation Framework, and enhancing local revenue collection. This provided input to the Quad-TAC meeting in Dec 2021 on the fiscal situation and measures taken by government. Several workshops and roundtable discussions were held to either prepare or disseminate these three policy papers. However, consultations on the policy issues were internal to government and an external review of the Economic Stabilisation Framework was not requested by the Executive Bureau and therefore has not been completed.

5.3 Telecommunications sector reform:
One policy paper on telecommunications sector reform was developed and shared within government for feedback and discussion. However, this was not finalised by 31 March 2022 when the CSSF Economic Stabilisation Project II closed. As a result, a workshop to disseminate findings of the policy paper and discussions with telecommunication firms were not held until after the programme end date.

5.4 Support to prioritisation of key policy reforms:
There was no final target under this indicator. The 2021 Annual Review recorded this indicator as moderately not meeting expectations as the policy paper was still in draft and undergoing quality assurance at the time. Following this, the draft was not finalised as the Executive Bureau expressed their desire for a substantive reform agenda to be produced, in comparison to the draft which outlined the thinking behind prioritisation. The IGC did not feel that they were best placed to produce this as their expertise was limited to economics, the agenda required full ownership by government, and there were difficulties in doing this consultatively without a presence in Aden. A reform prioritisation workshop was led by one of the embedded experts. Inputs from participants were captured and the findings helped develop a reform prioritisation framework, which was used by the Ministry of Finance as a guiding document. The aforementioned Economic Stabilisation Framework also gave further detail to economic reform elements.

5.5 Number of strategic conversations between senior GoY leaders and relevant IGC experts:
Only one strategic conversation was completed between Neil McCulloch, the Executive Bureau, the Prime Minister and the MOEE. A further conversation between Plum Consulting and the Ministry of Trade was ongoing at the time of programme closure.

5.6 Number of embedded technical specialists:
At the time of the 2021 Annual Review, there were three technical specialists embedded in the Executive Bureau. This was then increased to 4.5 specialists (4 full-time, 1 part-time).

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

Economy: IGC’s daily rates were benchmarked against FCDO’s framework of economic consultants and found to offer good VfM.

Effectiveness: By funding positions within the Executive Bureau, the FCDO complements and maximises the impact of GoY’s own funding. The programme allows for targeted support to Yemen’s nascent reform agenda while helping accelerate delivery of short-term priorities that benefit Yemen’s humanitarian, economic and stability agenda. Supporting a key state institution through this project also offers insights and relationships which benefit FCDO’s broader portfolio and policymaking.

Lessons learned through this output, and recommendations for future programming

Lesson:
Output 5 failed to meet expectations against the indicator targets in both the 2021 Annual Review and the Programme Completion Review, scoring consecutive B’s. However, the logframe indicators do not sufficiently capture the breadth of work carried out by the experts embedded in the Executive Bureau and the volume of achievements throughout the life of the programme, as well as the flexible leadership and coordination role the Executive Bureau plays, responding to emerging priorities of the Prime Minister. More effort could have been employed to update and amend the logframe to ensure it accurately reflected the activities under this output.

Recommendations:
- FCDO should carefully produce the new logframe for the corresponding output under AFFY with the IGC, with support from IGC’s MEL lead, to ensure indicators are relevant to the work being completed, and that targets are stretching, whilst still achievable. The logframe should be reviewed regularly, at least every 6 months, and amended if necessary.
- Going forward under the successor programme AFFY, IGC should be more proactive in raising concerns with FCDO related to slow progress against logframe targets, and FCDO should require more regular written progress and financial updates.

Output Number and Title	Capacity building support to the General Secretariat (GS) of the Government of Yemen
Output Score	A
Impact weighting (%)	5%		Impact weighting revised since last AR?		N/A
Output Indicator		Final Logframe Target		Final Result Achieved
6.1 Approve project workplan		Hold a workshop with the Secretary General (SG) and General Secretariat (GS) leadership team to approve the project work plan and build ownership		Met expectation: Online kick-off meeting attended by SG, senior members of the GS, and FCDO on 14th December 2021. This led to the approval of a finalised workplan
6.2 Obtain and translate core GS documents on mandate, functions and structure		Draft discussion paper on mandate, functions and structure		Met expectation: Draft discussion paper on the GS mandate, functions, and structure complete
6.3 Review of policy proposals to CoM		Produce an Adapted International Assessment Tool and Summary analysis		Met expectation: Adapted International Assessment Tool and summary findings of reviewed policy proposals complete
6.4 Conduct skills audit		Produce skills audit report		Met expectation: The approved questionnaire for the skills audit was produced following a meeting with HR and the final report was completed
6.5 Draft roadmap for GS capacity building		Produce a draft roadmap for a 3-year programme to build the GS’s institutional capacity, supported by a workshop with the GS leadership group		Moderately exceeded expectation: The discussion of the GS mandate in two workshops was incorporated into the draft roadmap. The draft roadmap has been submitted to the Secretary General. It will remain a draft within Yemen until it is formally endorsed by the GS and discussed with the Prime Minister
6.6 Establishment of a Rapid Response Unit (RRU)		A) Drafted function statement and job descriptions for key RRU positions		Met expectation: Draft Resolution of the Prime Minister on the RRU submitted to the Secretary General which includes a function statement and draft generic RRU protocols
		B) Drafted protocols for establishing and managing rapid policy and/or operational responses to urgent issues facing the Government		Moderately exceeded expectation: Draft Resolution of the Prime Minister on the RRU submitted to the Secretary General which includes draft generic RRU protocols. The RRU was discussed at length during the capacity building workshop in Amman, Jordan between 27 – 29 March
		C) Operational support for the RRU to establish one or more responses		Moderately did not meet expectation: The RRU is not yet formally established and therefore no RRU reviews have been initiated

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

Component funded from 9 December 2021 - 31 March 2022 (not reported on in 2021 Annual Review).
Component budget: £121,981.49
Component final spend: £120,906
2021 Annual Review Score: N/A

Effective Council of Ministers (CoM) decision making is essential to deal with the challenges faced by the internationally recognised Government of Yemen. Its ability to make coherent decisions, and coordinate their implementation, is necessary to demonstrate the viability of the Government to the citizens of Yemen, the parties that make up the Government and the wider international community. The smooth functioning of the CoM is critical to the survival of the Government itself and progress in the peace process.

The General Secretariat of the Government of Yemen provides administrative and policy support to the CoM. Through administrative support and advice, the Secretariat has a key role in supporting the CoM to build trust between the political, regional or tribal factions within the Government, so that Ministers and factions feel their interests have been properly taken into account in decision-making and there is a degree of ownership of the overall Government agenda.

Under this output, Adam Smith International (ASI) and DeepRoot Consulting responded to the General Secretariat’s request for urgent capacity building support following the establishment of the power-sharing Government in December 2020. The project sought to strengthen the General Secretariat’s institutional capacity to support the decision-making by the CoM, by addressing immediate needs and building a foundation for further capacity building supported by the UK and/or other donors.

6.1 Approve project workplan:
ASI organised an online kick-off meeting which was attended by the Secretary General, several senior members of the General Secretariat, and representatives from the FCDO on 14th December 2021. This led to the approval of a finalised project workplan.

6.2 Obtain and translate core GS documents on mandate, functions and structure:
ASI reviewed government legislation related to the General Secretariat (GS) including the Republican Decree of 2005 and the Prime Minister’s Resolution of 2007 as well as various other Government decrees and resolutions to produce a draft discussion paper on the GS mandate, functions, and structure.

6.3 Review of policy proposals to CoM:
Fifteen policy proposals to the Council of Ministers (CoM) were analysed using an adapted International Assessment Tool. The sample included proposals from ten different Ministries and one Supreme Council comprising multiple Ministers and other senior officials. A summary analysis report was produced outlining the findings of the review.

6.4 Conduct skills audit:
In order to identify the major skill gaps, a confidential audit was undertaken of the current skills in the General Secretariat (GS). A total of 63 staff responded to the survey and were asked to provide details of their educational qualifications, years of experience in the GS and employment status. The audit included both skills needed to perform their current duties and skills required to undertake the strengthened GS roles planned over the next three years.

6.5 Draft roadmap for GS capacity building:
A 2022-2025 roadmap on building institutional capacity of the General Secretariat of the Yemen Council of Ministers was produced that provides a basis for discussions with various international partners and also includes capacity building activities that can be undertaken internally or with local support. It has been submitted to the Secretary General, but it will remain a draft within Yemen until it is formally endorsed by the GS and discussed with the Prime Minister. At the end of March 2022 there was no estimate as to when the roadmap would be finalised, due to the uncertainty of external factors, however, ASI are continuing to follow up regarding progress.
ASI facilitated two workshops, attended by the GS leadership group, at which the draft roadmap was extensively discussed. ASI were able to quickly mobilise underspend on another component of the CSSF Economic Stabilisation Project II in March 2022, increasing their budget, to hold the second capacity building workshop, exceeding the initial target to hold one workshop.

6.6 Establishment of a Rapid Response Unit (RRU):
ASI reviewed the previous Prime Minister Resolution 4 of 2006 and Prime Minister Resolution 3 of 2008 to inform their draft of a Prime Ministerial Resolution on the establishment of a Rapid Response Unit (RRU). The draft Resolution was submitted to the Secretary General and includes sections outlining; RRU functions, the Special Projects the RRU will be assigned and the terms of reference for these, and details regarding the members of the RRU. The RRU was discussed at length during the additional capacity building workshop delivered in March 2022. The RRU was not formally established and therefore no RRU reviews had been initiated at the time of programme closure. Delays in the RRU being established were due to the political instability during March 2022, with ongoing government consultations and the need for the Prime Minister’s support. It was anticipated that the Unit would be established soon after programme closure.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

In March 2022, ASI were able to quickly mobilise underspend on another component to hold a second capacity building workshop, exceeding the initial target to hold one workshop. FCDO could not disburse the total funding required to facilitate this workshop without exceeding the financial limit of the low-value contract held with ASI. In response to this, ASI and Deeproot contributed to almost half of the workshop costs from their own funds, the remaining funds being paid by FCDO. This significantly boosted the value of deliverables that FCDO received for the amount on funding they committed.

Lessons learned through this output, and recommendations for future programming

Lessons:
- The project team was able to quickly develop an effective working relationship with the General Secretariat leadership based on mutual respect and the team’s mix of expertise.
- The substantial meeting held with the Prime Minister on 20 March provided valuable insights and validation, confirming that the major findings and proposals in the draft Roadmap aligned closely with the PM’s priorities and enabling the draft to be fine-tuned to reflect some additions from the PM.
- The focus on improving the low implementation rate of Yemen Government decisions, as well as the baseline studies that were undertaken, helped significantly to build support for the proposed institutional capacity building plan from the PM, the SG and the other senior GS officials
- The GS exercises good practice in managing the quality of inputs to the CoM and are eager to continue to do so but they are short staffed of well qualified personnel. Their capacity needs to be boosted with both short-term external support and long-term capacity building.

Recommendation:
Aligned to the project aim to build a foundation for further capacity building supported by other donors, it would be very useful for ASI and DeepRoot to present their achievements under this output to the World Bank. This may influence further capacity building support to the General Secretariat through the World Bank Multi-Donor Trust Fund which FCDO are supporting under the successor programme AFFY.

Output Number and Title		Support the World Bank’s efforts to produce an Analytical Roadmap for Yemen
Output Score		A
Impact weighting (%)		5%	Impact weighting revised since last AR?		N/A

Output Indicator	Final Logframe Target			Final Result Achieved
7.1	Carry out a study analysing the impact of the conflict on several socio-economic indicators, by leveraging on innovative approaches such as Night Time Lights (NTLs) technology and big data to complement the understanding of Yemen’s economic context and history			Met expectation- in progress, EFO completion report expected 30 August 2022
7.2	Carry out a political economy diagnostic to pinpoint how the institutional complex has impacted the development/growth path of Yemen and to gain better understanding of the state-building story from an economic perspective by examining the relationships between society, state institutions, and growth, with a view to identify relevant bottlenecks			Met expectation- in progress, EFO completion report expected 30 August 2022
7.3	Collect data in various forms (remote-sensing, survey-based, experimental, key informant / interviews, and potential purchase of proprietary data), conduct empirical assessments, and perform dissemination activities including communication materials, key stakeholder meetings, including donors, host communities, civil society, and key informants			Met expectation- in progress, EFO completion report expected 30 August 2022

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

Component funded from 9 February 2022 - 31 March 2022 (not reported on in 2021 Annual Review).
Component budget: £115,000
Component final spend: £115,000
2021 Annual Review Score: N/A

Since 2014, Yemen has endured a devastating armed conflict which has depressed the country’s economic prospects and created one of the world’s worst ever humanitarian crises. Given very recent developments in the country, the possibility, albeit still speculative, of upcoming post-conflict scenarios, stresses the criticality of a strong analytical foundation, to support and substantively prepare for any potential peace-building discussions.

Work under this output aimed to leverage innovative analytical frameworks and advanced econometric approaches for the estimation of economic aggregates, and to identify possible avenues forward after the conflict. Managing such data is typically complex and costly but would complement and deepen our understanding of the economic developments in Yemen. This workstream also set out to run a political economy diagnostic to pinpoint how the institutional complex has impacted the development/growth path of Yemen. This should achieve a better understanding of the state-building story from an economic perspective: examining the relationships between society, state institutions, and growth, with a view to identify relevant bottlenecks. These efforts built on and complemented Yemen-specific and regional analytical activities such as the Country Economic Memorandum, the Country Engagement Note, and at a broader level, the World Bank Group FCV Strategy.

FCDO Yemen funded this output through an Externally Financed Output (EFO), meaning that funds would be commingled with the World Bank’s own commitment. It was agreed that although the EFO would be completed by 30 August 2022, the World Bank would utilise all of FCDO’s funding by 31st March 2022 (the end of the CSSF Economic Stabilisation Project II). It was confirmed by the World Bank at the end of March 2022 that this had been achieved. However, this means that FCDO would not receive a formal progress report until August 2022, after the deadline of this PCR.

7.1 Economic and data analysis:
The aim of the work under this indicator is to carry out a study analysing the impact of the conflict in Yemen on several socio-economic indicators, by leveraging approaches such as Night Time Lights (NTLs) technology and big data to complement the understanding of Yemen’s economic context and history. This indicator is on track to be completed by the 30 August 2022 EFO deadline, although it is the most innovative part of the analysis and requires more time dedicated to its finalisation. At the time this PCR was drafted, FCDO had received a very early draft of the Night Time Lights (NTLs) study.

7.2 Political economy analysis:
Under this indicator, the World Bank should carry out a political economy diagnostic to pinpoint how the institutional complex has impacted the growth path of Yemen and to gain better understanding of the state-building story from an economic perspective. This should be done by examining the relationships between society, state institutions, and growth, with a view to identify relevant bottlenecks. This indicator is on track to be completed by the 30 August 2022 EFO deadline. The interviews carried out under indicator 7.3 have been instrumental in shaping the framework and narrative of this report. At the time this PCR was drafted, FCDO had not received a draft report, as it was still being finalised.

7.3 Data generation:
This indicator is, in essense, a prerequisite for the other two under this output to be completed. The target was largely met at the time this PCR was drafted. The World Bank team engaged in key informant interviews with more than 50 individuals, that are either Yemenis or internationally recognised experts on Yemen. The interviewees are made up of academics, former decision-makers and politicians, private sector representatives, and experts on Yemen from different backgrounds such as the UN system and NGOs. The wealth of information gained from these interviews is significant. The World Bank team also developed databases on a variety of issues including; nighttime lights; prices; environmental indicators; demographic indicators; and security/conflict indicators, that are now being used to complete analysis and data crunching.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

The programme team were able to quickly mobilise £115,000 of CSSF underspend on the ex-FCO financial baseline to complete the work under this output in the final two months of this programme, using it to deliver against FCDO Yemen’s Campaign Goal 3 – promote economic stability, with a budget uplift.

Support for this analytical project has strengthened the FCDO partnership with the World Bank, ahead the establishment of a multi-donor trust fund for Yemen under the successor programme AFFY.

Lessons learned through this output, and recommendations for future programming

Lesson:
An EFO is a useful agreement to quickly mobilise funds to implement important pieces of work within a tight timeframe. However, it does not always offer FCDO the greatest opportunity to track allocation and expenditure of funds or receive timely formal progress reporting.

Recommendation:
Under the successor programme AFFY, FCDO should be wary of partner deadlines for formal progress reporting to ensure this is aligned to FCDO reporting requirements such as Annual Reviews and Programme Completion Reviews. Careful planning will ensure that results and Value for Money can be more accurately monitored.

D: Risk

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.

The risk rating for the CSSF Economic Stabilisation Project II remained major throughout its lifetime. The ongoing conflict in Yemen restricted FCDO access and partner presence in project locations, and therefore programming was managed remotely. The Yemeni context is highly volatile. FCDO accepted the need to take on risk, albeit with the appropriate monitoring and mitigation measures in place, to achieve results.

The risk appetites for this programme were as follows:
Risk Category	Programme Appetite
Reputational	Eager
Financial & Fiduciary	Cautious
Safeguarding	Receptive
Policy & Programme Delivery	Eager
Strategy & Context	Eager
Public Service Delivery & Operations	Cautious
People	Cautious

These appetites are aligned to FCDO Yemen’s ratings and take into account the extremely challenging and risky context the programme operated in. After re-reviewing the risk appetites upon programme closure, the FCDO programme team decided to decrease the appetite for safeguarding risks from receptive to cautious under the successor programme Affordability of Food and Finance in Yemen (AFFY). Although our programming has minimal interaction with communities and potentially vulnerable groups, the high-profile nature of the partnerships/individuals involved would have significant negative impacts if safeguarding risks materialised. This decision also reflects FCDO’s zero tolerance for any interventions which might inadvertently cause harm or any forms of sexual, physical or psychological harassment, abuse or exploitation of staff, downstream partners or beneficiaries.

Given the UK’s sustained public commitment to economic recovery and reform in Yemen, and the volatile context meaning the reform agenda could be deprioritised with little warning, there was a higher appetite for strategy and context, reputational and delivery risks under the CSSF Economic Stabilisation Project II. Risks within these categories were mitigated by ensuring continued engagement with the Quad Ambassadors and Technical Advisory Committee (TAC), key donors and IFIs to ensure activities were aligned, in addition to consulting FCDO Yemen’s Conflict Adviser to continually monitor the effects of the programme.

Partners for this programme were specifically selected due to their robust expertise. It was identified that not all partners had been subject to a Due Diligence Assessment (DDA) carried out by FCDO Yemen prior to agreements being signed. Therefore, under the successor programme AFFY additional vigilance is being applied to ensure that thorough DDAs are in place for each partner to provide assurance of their policies and ability to deliver, and that these are updated every three years. This risk mitigation measure is an essential lesson learned from the CSSF Economic Stabilisation Project II which will positively impact future programming.

Programme partners under the CSSF Economic Stabilisation Project II each maintained project risk registers and escalated major or emerging risks to FCDO as necessary. The FCDO programme team used this information to regularly update a programme-level register, feeding key risks into the portfolio-level risk register which is co-ordinated by the FCDO Yemen risk specialist as part of the overall ODA spend risk management strategy for Yemen.

E: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency.

Project Management Performance
Partners have generally performed well in providing regular informal reporting via weekly or fortnightly meetings. This has allowed FCDO to remain appraised of project progress, receive advance notification of emerging risks and issues, and make necessary amendments to agreements to uplift budget or extend the length of engagement. However, formal progress reporting was often not received on time and had to be chased. Under the AFFY programme, it is recommended that formal meetings are set up at least quarterly, in addition to regular informal catch ups, to discuss the content of progress reports and ensure they are on time and linked to logframe indicator milestones.

The majority of outputs met FCDO’s expectations. In regard to the one output which did not, this was primarily due to the logframe indicators not sufficiently capturing the breadth of work carried out. More effort could have been employed, by both the FCDO programme team and the partner, to regularly review the logframe and update and amend it as necessary, to ensure the activities under this output were accurately reflected and scored. One factor that impacted this was the high turnover within the FCDO Yemen programme team. In one year, the programme was managed by three different programme managers and four SROs, meaning that capacity and institutional knowledge regarding the programme and its design was low.

Financial and Commercial Performance
Partners’ financial and commercial performance was generally good, albeit predominantly reliant upon informal reporting during the course of implementation. Financial reports submitted to FCDO have been of suitable quality and partners have remained open to queries as needed. However, formal financial reports often had to be chased and updates on monthly estimated expenditure was not always received in time for the end of month financial process. Going forward under the successor programme AFFY, FCDO should set clear expectations for when formal financial reports and monthly expenditure updates should be submitted and when payments should be made.

The CSSF Economic Stabilisation Project II’s FY 2021/22 financial position reflected an underspend of approximately £50,000 However, the programme was able to quickly mobilise £115,000 of CSSF underspend on the ex-FCO baseline in early 2022 to agree activities with the World Bank under Output 7. The programme’s underspend was predominantly due to ACAPS and their downstream partner not finalising two reports under output 3 before the programme end date, resulting in reduced staff costs, in addition to budget being allocated to activities supporting the Yemen peace process, which was consequently not started, and no agreement was signed. In addition to the £115,000 of CSSF underspend, the programme was also able to absorb a further £400,000 of underspend from across the Yemen CSSF portfolio to increase the contribution to USAID under output 1 from £400,000 to £800,000 in FY 2021/22. However, this was included in the budget figure for the programme.

There was one commercial contract under the CSSF Economic Stabilisation Project II, which covered the activities carried out by Adam Smith International (ASI) under output 6. This was a low-value contract which was amended in March 2022 by FCDO Yemen’s Delegated Procurement Officer (DPO) to increase the financial limit from £99,993.00 to £121,981.49. The other agreements used to deliver the programme were either an Accountable Grant, EFO, or Delegated Cooperation Agreement.

Programme-level approach to monitoring and evaluation
The programme did not undergo any third-party monitoring or external assurance activities in its lifetime. However, the FCDO programme team have requested that an evaluation of the CSSF Economic Stabilisation Project II is carried out in Financial Year 2022/23 under the Yemen Independent Monitoring, Evaluation and Data Analysis (IMEDA) programme by external contractors. The programme team have the opportunity to shape the objectives of this evaluation to focus on the key issues and aspects not thoroughly covered by this PCR.

Value for Money
FCDO uses the ‘4 Es’ framework (economy, efficiency, effectiveness and equity) to ensure that its funding maximises impact. With a relatively small budget (compared to humanitarian programming) the programme helped further HMG’s economic stabilisation objectives and represents good VfM within the overall FCDO Yemen context and programme portfolio.

Economy:
- Utilising USAID’s existing programme with Pragma provided the Economic Stabilisation project with a ready-made intervention without the costs associated with an open procurement process, with USAID undertaking the administrative costs. Support for this programme allowed the UK to demonstrate added value, and to claim attribution for the benefits of the whole project whilst only providing a portion of the funding.
- As the main cost of the project with USAID, the fee rates of the ten consultants were examined by FCDO’s Procurement and Commercial Department and deemed to be competitive.
- Similarly, IGC’s rates were benchmarked against FCDO’s Procurement and Commercial Department economic consultancy framework and found to be competitive.
- ACAPS and Mercy Corps saved the set-up costs of the online dashboard by utilising an existing agreement with Amazon Web Services to host it at no additional cost to the FCDO.

Efficiency:
ACAPS’s dashboard builds on existing, established analysis capacity already available within ACAPS and Mercy Corps. This helped keep cost down by sharing costs including office rent, management and support staff across a broader base, which freed up funding to focus directly on delivering analysis products.

Effectiveness:
- FCDO’s support to USAID’s ERLP gave the FCDO contributed towards a larger impact beyond the amount of its support. It also brought the work of the FCDO and USAID closer together, complementing diplomatic engagement between the US and the UK on Yemen’s economy
- ACAPS collaborated with other FCDO partner organisations, utilising their broader organisational access to data sources in order to enhance the rigour and coverage of their analysis.
- The impact ACAPS’s activities have had on HMG’s and other relevant stakeholders’ efforts far exceeded the amount of funding provided by FCDO. The analysis contributed to a broader discussion on how to strengthen monitoring and contingency planning for economic risks in Yemen. Key economic risks identified by ACAPS were referenced by the UN Humanitarian Country Team, and in HMG engagements to generate buy-in among key stakeholders.
- FCDO maximised a small amount of funding to successfully engage and bring together key economic actors, including OSESGY on critical economic priorities.

Equity:
- IGC’s work on the economic considerations of the peace process sought to bring greater breadth and inclusion to the Track I peace process.
- ACAPS track and promote gender equality in staffing and hiring. This ensures a greater range of experience and perspectives inform the analyses.

USAID (Output 1)- Capacity building of the Central Bank of Yemen (CBY) and Ministry of Finance (MoF)
Date of last narrative financial report	25/05/2022	Date of last audited annual statement	Not received, FCDO programme manager will ensure these are sought under the successor programme AFFY

The World Bank (Output 2)- Restoring capacity of the Central Statistical Organisation
Date of last narrative financial report	23/11/2021	Date of last audited annual statement	Not received, FCDO programme manager will ensure these are sought under the successor programme AFFY

ACAPS (Ouput 3)- Analysis of key economic trends and risks and economic data made available
Date of last narrative financial report	08/05/2022	Date of last audited annual statement	Not received, FCDO programme manager will ensure these are sought under the successor programme AFFY

IGC (Output 4)- Online convening of Yemen economic stakeholders
Date of last narrative financial report	Narrative report: / 12/07/2021 / Financial report: 23/08/2021	Date of last audited annual statement	Not received, FCDO programme manager will ensure these are sought under the successor programme AFFY

IGC (Output 5)- Assistance provided to the Executive Bureau to support the development of key policy reform priorities for the Government of Yemen
Date of last narrative financial report	May 2022	Date of last audited annual statement	Not received, FCDO programme manager will ensure these are sought under the successor programme AFFY

ASI & Deeproot (Output 6)- Capacity building support to the General Secretariat (GS) of the Government of Yemen
Date of last narrative financial report	April 2022	Date of last audited annual statement	Not received, FCDO programme manager will ensure these are sought under the successor programme AFFY

The World Bank (Output 7)- Support the World Bank’s efforts to produce an Analytical Roadmap for Yemen
Date of last narrative financial report	Expected by end August 2022	Date of last audited annual statement	Not received, FCDO programme manager will ensure these are sought under the successor programme AFFY