Business Case – November 2021

Summary Sheet

Department CDD/Portfolio/ Business Plan Summary: / EECAD business plan impact: Our Vision is of stable, resilient and prosperous Eastern European and Central Asian states who uphold the global rules-based system and directly contribute to UK security and prosperity. Our four NSC strategies set out the policy framework that underpins this vision in the medium term. / Campaign Goals: / Lead international coordination and cooperation to manage the effects of Russia’s continued challenge and confrontation, thereby stabilising the Russian threat to UK interests. / Promote increased regional stability and resilience to external, transnational and hostile threats, reducing the risk to UK National Security / Support reforms across the EECA region to further embed democratic principles, strengthen sovereignty and drive more Open Societies / Support economic growth across the EECA region which contributes towards UK prosperity goals and in a way that is greener, more resilient and tackles issues that are barriers such as corruption / Promote the UK's "force for good" credentials, driving forward work for a more equitable EECA region including on gender

Title: / Good Governance Fund Eastern Neighbourhood – Phase Three
Programme summary (100 words maximum): / The Good Governance Fund (GGF) Phase 3 will deliver demand-led support to governance reforms that allow open societies and economies to flourish. The GGF will focus on improving democratic and economic governance, primarily through strategically targeted technical assistance. The GGF programme will deliver interventions on a flexible basis, based on identified needs and/or requests from government counterparts or civil society in beneficiary countries (Armenia, Georgia and Moldova) in support of governance and economic reforms. This will support delivery and seek to prevent/reverse democratic backsliding. The GGF is part of an integrated portfolio of programmes operating in the EECAD region and supports the delivery of four NSC strategies and the Integrated Review. This business case is for the GGF Eastern Neighbourhood – Phase Three.
What is the rationale for UK Aid spending? (200 words maximum): / Security, stability and economic growth in Eastern Neighbourhood countries is of critical strategic importance to the UK national interest. Eastern Neighbourhood countries have faced significant and increased Russian interference aimed at undermining democracy, economic independence and engagement with the UK, EU and NATO. Unresolved protracted conflicts (Abkhazia and South Ossetia, Nagorno Karabakh and Transnistria) have the potential to re-surface, and have done in NK during the last 12 months, leaving the region vulnerable to malign influence. Eastern Europe continues to be a testing ground for hybrid threats to the West, while conflict and poor governance provide a permissive environment for serious and organised crime. Eastern Neighbourhood countries had pro-reform governments in 2015 but have recently witnessed democratic stagnation and backsliding with limited resilience to the economic effects of COVID-19. Delivery of reforms has reduced, bud demand remains strong in the three countries. / The programme forms a central element of delivery campaign goals within Country Plans, the Integrated Review, EECAD Business Plan and Russia Strategy. The UK’s objectives, as part of forging a Network of Liberty, is to strengthen open societies and open economies in Eastern Neighbourhood countries as they achieve greater stability and resilience from malign state and non-state interests. / UK support enables reform-minded governments to deliver for their people, establish political, cultural and economic independence and assert sovereignty with a viable alternative to state threats and oligarchic interests. Improved governance and economic management contribute directly to UK interests, including reducing instability, reducing inequality as a driver of instability, increasing prosperity and decreasing countries' vulnerability to external and internal economic and political pressure.
Programme Value: / £38 Million		Country/ Region or Sector: / Eastern Neighbourhood (Armenia, Georgia, Moldova)
Department/Country Office confirmation / Contact name		Scott Macdonald – Head of Programme, Advisory and Results Group, EECAD
Threshold for Approval of Business Case:
Date of Approval of Concept Note:	02/08/2021	Name of Approver / Minister Wendy Morton
Date of Approval of Business Case	dd/mm/yyyy	Name of Approver / Minister Wendy Morton
Programme Code:	Start Date: April 2022	End Date: March 2025
Overall programme risk rating:	Major
Vault Number:

## Strategic Case

The Eastern Neighbourhood remains strategically important to UK national security, foreign policy and strengthening economic cooperation, including UK energy interests in the Caspian (fields in Azerbaijan and pipeline through Georgia). The region is on the front line of Russia’s challenge to the rules-based system, freedom and democracy. Programmes delivered through the GGF are therefore a critical element of delivering the Russia Strategy (Constrain and Build pillars), the NSC Eastern Neighbourhood Strategy 2020-2025 (Good Governance and Prosperity pillars), the Country Plans, Integrated Review, and EECAD Business Plan. The GGF focuses on delivery towards the UN Sustainable Development Goals - 5 (gender equality and empowerment), 8 (decent work and economic growth) and 16 (peaceful, just and inclusive societies).

Democratic decline is taking place where there are weak institutions, safeguards or a limited history of democratic culture. The three countries have fragile and immature democracies where the legitimacy of political and governance systems are undermined by opportunities for personal enrichment, power and influence. The region is also on the forefront of a coordinated rollback on the rights of key groups including women, girls and LGBTQ people – where narratives on gender are at times used to polarise public debate, challenge UK-backed values and undermine social cohesion.

Democratic backsliding in the region remains a significant threat to European security as it increases vulnerability to malign influence. Russia has shown that through restricting energy supplies, trade, or work permits, it can exert significant influence in the Eastern Neighbourhood which is especially reliant on Russia for its gas and for remittances. Evidence indicates a diversified economy and increased energy efficiency can drive energy and economic independence, bolstering resilience to external malign influence. Potential reductions in support for democratic governance risks increasing the influence of malign actors and increasing risks to European security.

A legacy and risk of violent conflict from the last three decades continues to affect economic, social and political development. Institutions are weak and dysfunctional, the private sector is limited due to poor economic governance/management, corruption is endemic and exacerbates popular discontent, civil society is weak, media is subject to political pressure and self-censorship, there is uneven and often non-inclusive economic development, and populations are increasingly frustrated, disenfranchised, apathetic and resentful.

Despite these challenges, however, these countries have economic and governance reform agendas which can contribute to more open societies and economies, where this is backed by the domestic political will. GGF interventions will help countries to safeguard fragile gains, lock-in improvements to democratic governance, become increasingly resilient and prosperous as the result of inclusive economic growth and transparent, responsive, and effective governance institutions which are held to account by informed and active populations. The GGF focuses on technical assistance that responds to local demand and may catalyse broader reform or support for reform. This programming will reinforce HMG political engagement and messaging on wider UK Government objectives in the region including building stability, fostering open and inclusive societies, countering Serious and Organised Crime (SOC), enhancing prosperity and building resilience to State Threats.

Why should this economic and governance reform be addressed by technical assistance in economic and governance reform?

The Good Governance Fund (GGF) is a proven model. The GGF has been in operation since March 2015, providing a package of support for economic reform and good governance initiatives, initially in Ukraine, Moldova, Georgia, Serbia and Bosnia and Herzegovina (BiH) and in April 2018 extended to Armenia and North Macedonia. At the launch of the GGF the then Prime Minister said: “Ensuring we have strong partners on the EU’s border is not only essential for Britain’s security but our long-term prosperity. UK expertise can play a crucial role in bringing about the reforms needed to build lasting stability in the region, especially in the face of Russian intimidation, and it is right that we step up our efforts alongside international partners”.
[note] https://www.gov.uk/government/news/new-uk-funding-to-help-build-stronger-and-more-democratic-nations-in-the-eastern-neighbourhood-and-balkans

The GGF is embedded in the local political economy, building political momentum and tailoring its approach to focus on consolidation and protection of fragile gains as well as progressing on new reform areas. Recent democratic backsliding (including violations of democratic norms, restrictions on the media and emergency measures without time restrictions) particularly in response to the COVID-19 pandemic, risks compromising gains made under previous investments. In some contexts, governments have reduced internet freedom, civic space and political rights. In GGF countries, economic and governance reform is necessary for stability and prosperity. The NSIG Strategy states that: “Not only would improvements to the region’s mixed record on democracy and governance act as a counterweight to the argument that only authoritarianism delivers stability, it would also increase their resilience to political pressure and have a positive impact on the region’s prosperity, including the UK’s economic interests”.
[note] V-Dem ‘Autocratization Turns Viral’: https://www.v-dem.net/media/filer_public/74/8c/748c68ad-f224-4cd7-87f9-8794add5c60f/dr_2021_updated.pdf
[note] Freedom House: https://freedomhouse.org/issues/democracy-during-pandemic

1. Evaluations of past GGF investments have noted numerous instances where projects have contributed to longer term outcomes, including better services for citizens through digitisation, reduced corruption, and improved businesses operating conditions. The first five years of GGF’s operation have consolidated the fund’s niche in supporting economic and governance reform.
  1. In Moldova, Election Codes amended with support of GGF brought important new solutions for election processes, including a more effective gender quota on party lists and improved placement of women candidates within the political party lists,
  2. In Georgia, support to the implementation of a new corporate tax model led to the adoption of new legislation, reducing the compliance burden for businesses and increasing reinvestment rates.
  3. In Armenia, GGF support to the Central Election Committee has helped to establish a Training and Resource Centre that has received state funding for continuous trainings, testing and certification of the PEC candidates.

1. The UK’s comparative advantage, assessed from the previous two phases of the GGF, to deliver development programmes in the region includes:
  1. The availability of strong in-house (HMG) professional expertise, particularly in economic reform, democratic governance and private sector development;
  2. Deep understanding of local political context, including through Political Economy Analysis;
  3. Flexible, responsive programmes, with rapid decision making that align with the partner governments’ top priorities for reform, harnessing this momentum;
  4. Willingness to support innovation, combined with a readiness to accept and manage higher risks where there are prospects of high impact returns, including through political momentum-building.

Focusing on these areas also ensures that the GGF complements and does not duplicate CSSF funded programmes. GGF activity will reinforce activity funded through CSSF (e.g. work on anti-corruption and transparency through GGF can reinforce efforts to tackle Serious Organised Crime), recognising that the previous programme’s lessons was that coherence with other instruments as well as political and advisory capacity is important for the success of the GGF.

In line with the Strategic Framework for ODA, the UK will focus on technical assistance in order to build governments’ own capability to deliver growth and development and to build demand for reform. Technical assistance, capacity building, institution building and policy reform are therefore appropriate approaches for middle-income countries who are able to finance their own development (which includes Armenia, Georgia and Moldova) and where the UK can best provide support in enabling the political and economic conditions for stability and development. National level policy advice and technical assistance to promote pro-growth policies are considered a “great buy” with the potential of high returns when effective. Strengthening the demand side of reform through supporting civil society and independent media is central to improving government accountability for delivery of reform agenda, including where government appetite for reform may be reducing.
[note] Technical Assistance (TA) can be defined as “knowledge-based assistance to governments intended to shape policies and institutions, support implementation and build organisational capacity”. While ‘Capacity’ can be defined as “the ability of organisations to carry out, effectively and efficiently, programmes of coordinated action in pursuit of formal agreed goals” (Cox and Norrington-Davies, 2019).
[note] Chief Economist Office (2019) Sector Best buys: Economic Development

The GGF is agile and responsive – whereas many donor reform programmes in the Eastern Neighbourhood are hampered by an inability to adjust priorities quickly, the GGF is able to mobilise at pace. The World Bank notes that in top reforming economies about 85% of economic reforms took place within 15 months of a change of government, pointing to the need for donors to respond quickly where there is political appetite. Responding to windows of opportunity for reform provides a stronger basis for reform than a narrow focus on technical reform. The GGF is designed to address this through an ability to respond to evolving priorities, step in rapidly, scale up or scale down as necessary, and unblock longer-term support from donors with larger budgets. It also aims to use political capital to support political momentum-building, which is critical for reform.
[note] World Bank (2007). Doing Business 2007: How to Reform.
[note] Overseas Development Institute (2013). Unblocking results: Using aid to address governance constraints in public service delivery

What will the UK deliver to meet this need?

1. The GGF will continue to focus activity in areas where HMG priorities (through the NSC Strategy and Post Country Business Plans) and host government priorities coincide. We will focus on programming which can demonstrate impact and contribute to sustained and sustainable reform; and which builds long term democratic governance, stability and resilience. Interventions will be decided on a flexible basis based on identified needs and/or requests from government counterparts or civil society in beneficiary countries in support of governance and economic reforms. These could include:
  1. Supporting democratic systems development, including broad participation in democracy, particularly for women and under-represented groups, and improving the state-citizen relationship.
  2. Embedding democratic principles and behaviours, such as the de-politicisation of justice and relationship between parliamentarians and citizens.
  3. Institutional capacity building to develop more effective governance, public administration and management of public finances to improve the delivery of public services.
  4. Anti-corruption measures and judicial reform to strengthen rule of law and build trust
  5. Stronger and more independent media and civil society to ensure the public can engage in active, informed debate to encourage delivery and hold the government to account
  6. Modernisation of key sectors such as energy, banking and reforming state-owned enterprises to strengthen transition to market driven, vibrant, modern economies.
  7. Reform to regulation and institutions of the business environment and economic governance to bring target countries closer to international standards.

GGF Phase III funding will see a return to previous levels of funding, allowing time to build projects that will run for multiple years. By March 2022, the GGF will have spent £180m in 8 countries since 2015 (covering Eastern Neighbourhood, Ukraine and Western Balkans.) Following the previous Spending Review and decision by the former Secretary of State for Foreign, Commonwealth and Development Affairs to move the programme from the CSSF to the FCDO, the GGF spent £5m in the Eastern Neighbourhood. GGF Phase III funding will return to previous levels of funding for multiple years. FCDO funding will be in addition to CSSF programmes in the region that in FY21/22 equalled £10 million.

Table 1. GGF Financial Allocations

	GGF Phase II / (CSSF)	GGF Phase II / (FCDO)	GGF Phase III / (FCDO baseline)
Financial Year	20-21	21-22	22-23	23-24	24-25
GGF Eastern Neighbourhood	£12m	£5m	£10m	£14m	£14m

The UK will retain its place as a responsive and targeted partner, seeking to influence larger sums of funding from other donors such as USAid, the EU and International Financial Institutions such as the EBRD and World Bank.

The impact will be: Improved democratic and inclusive governance (including prevention of democratic reversals) and inclusive economic growth which helps GGF countries in their resilience against malign influences and shocks.

The outcome will be: Governments increasingly protect, consolidate, and advance reform in selected GGF priority areas* to improve inclusive and democratic governance reform and inclusive economic resilience with strengthened civil society and private sector engagement in reform; and strengthened partnership between UK and EN countries and like-minded partners supports UK global campaigns.

How does the programme comply with the Gender Equality Act and Public Sector Equality Duty?

Gender and inclusion sensitive programming. We expect as a minimum that all projects should be gender sensitive and able to demonstrate that they are doing no harm to women, men, girls, boys, or any particular group or community and effectively safeguarding against sexual exploitation, abuse and sexual harassment (SEAH). The GGF will only support programmes that contribute to gender equality (following on from the previous annual review which identified 15 projects at Gender Equality Marker (GEM) 0). Specific actions will include:
- Gender and social inclusion (GESI) analysis (including conflict and political economy analysis that embeds an inclusion lens) will be required by each programme to identify socially excluded groups, causes of exclusion, key risks and opportunities to mitigate these factors, and a plan to advance inclusion through the programmes.
- FCDO will support and work with implementing partners to utilise GESI analysis to identify programme adjustments, ensure sufficient implementing partner capabilities, and shift towards measuring GESI outcomes and impact. This will address a consistent recommendation from GGF annual reviews by taking active measures to address previous poor performance from the outset of committing any funds.
- Safeguarding against SEAH and mitigating risks of backlash.

Gender and inclusion transformative programming. In addition to the above, a smaller number of programmes will work towards GEM 2 and gender transformative standards. EECAD’s Gender Roadmap aims for 15% of its overall programme spend to go towards gender targeted interventions in line with recommendations from the UN Secretary General.

How does the GGF ensure conflict sensitivity?

Unresolved conflicts in all three GGF EN countries continue to undermine political stability and territorial integrity. All three GGF EN countries suffer from political instability and a weak history of peaceful transition through elections, marked by frequent protests and changes in government (Georgia 2020, Armenia 2017, Moldova 2021). The inability of government to mediate conflictual situations effectively and peacefully highlights the immaturity of the political systems and risks further instability within the region. The Nagorno Karabakh conflict is a recent and ongoing illustration of how easily these conflicts can reignite and cause devastating loss of life, increase risk of backsliding on reform, and shift of focus and budgets towards military activity.

GGF interventions address the foundational causes of instability and support the ‘building blocks’ of stability including fair power structures, effective and legitimate institutions and inclusive economic development. The GGF aims to mitigate risks to UK strategic interests in areas of green investments, commercial, human rights and broader strategic stability.

1. GGF III will take the following steps to improve conflict sensitivity:
  1. Conflict analysis - Sustainable pathways towards more effective and inclusive systems requires the need to think and work politically ensuring that interventions are grounded in and are able to adapt to contextual realities. A Joint Analysis of Conflict and Stability for the South Caucasus (due end 2021) will provide a common understanding of the context and identify competing interests and interconnections between dynamics of instability. This analysis will help underpin robust GGF risk management and conflict sensitivity approaches.
  2. Conflict sensitive implementation - While GGF does not have active conflict programming, GGF will adopt a deliberate and systematic approach to ensure programmatic decisions are made on the basis of robust and credible analysis of the context. It will involve adopting a critical lens and challenging assumptions about how we contribute to sustained stability. Every GGF intervention will conduct a proportionate screening to assess the interaction with the conflict context. A conflict sensitivity tool will identify the key trade-offs and dilemmas of our actions and seek the right balance between different objectives.
  3. Conflict sensitive monitoring - If programme teams consider that the intervention might have a significant impact on conflict and stability, further analysis will be conducted and ongoing adjustments to the intervention will be made as necessary. As noted in the Management Case, the GGF uses a robust risk monitoring and mitigation approach and any emerging potential harmful consequences will be assessed as they arise and corresponding action taken.

Key risks to the success of the programme

The overall risk is assessed as Major. The primary risks to the programme’s control and delivery are the proliferation of small, low impact programmes; weak programme management; supply led portfolios (including a failure to build political momentum) and a failure to deliver adaptive programming and potential of key reform programmes to be captured by entities involved in fraud and corruption. There is also a risk that multi-lateral channels offer less profile for the UK and affects our influencing ability. The proliferation of small programmes will be managed through the development of clear criteria for GGF support (including results and value for money) and limiting the number of projects, linked to NSC strategies. Delivery chain mapping and political economy analysis will ensure that reform is demand-driven and mitigate risk of fraud and corruption. Regular (at least annual) updated to political economy analysis (including by implementing partners) and updates to results frameworks will help to check progress and encourage adaptation. Firm oversight and monitoring will ensure a demand led approach focused on strategic priorities. Robust systems and use of evidence and feedback/learning outcomes will help to deliver adaptive programming. Influencing will be tracked through appropriate M&E metrics. UK profile will be maintained through more focused and strategic engagement with multilaterals and civil society implementers.

There are a number of risks in implementing the GGF that are beyond the UK’s control, including: political or economic shocks which could disrupt delivery of the reform agendas; over ambitious reform plans that raise unrealistic expectations; reform hindered by vested interests (political, business, civil society, media); deteriorating conditions undermining public support for reform; instability/violence; lack of progress. We have sought to manage this by ensuring that GGF operates in countries and areas where there is commitment to reform agendas, where FCDO colleagues overseas work with key national interlocutors and GGF advisers to ensure early warning of such issues.

The risk of aid being diverted to terrorist groups and activities is assessed as low. Safeguarding risks are also assessed as low but increasing since the onset of COVID-19, with further analysis needed to understand risks at various stages in the delivery chain. The GGF will continue to be delivered through reliable international partners and local NGOs with control mechanisms judged to be sufficiently robust to ensure full compliance with UK legislation and policy on terrorism and financing as well as FCDO guidelines on safeguarding. A full risk register is included in Annex A.

We do not expect to work outside of the FCDO risk appetite statement.

How will the programmes incorporate the Partnership principles?
A key factor that will impact the effectiveness of the GGF programmes will be the approach and commitment of recipient governments. Colleagues in Embassies will help to build political momentum for reforms where UK or donor involvement may help to catalyse reform. PARG in close coordination with Embassies will use the four Partnership Principles to assess and monitor this element of the country context. This will include considering the recipient governments commitment to:
- Reducing poverty and achieving the sustainable Development Goals (SDGs)
- Respecting human rights and other international obligations
- Strengthening financial management and accountability and reducing the risks of funds being misused through weak administration or corruption.
- Strengthening domestic accountability.

Climate and Environment
1. In line with the Paris Agreement on Climate Change, the programme team will track possible impacts on climate and environment through ensuring all projects:
  1. Cohere with National Plans on Climate: Post programme leads consider how GGF projects and programmes align with Eastern Neighbourhood countries’ commitments under the Paris Agreement and related national plans.
  2. Risk Assess: As the programme is providing technical assistance there is unlikely to be direct climate or environment impacts though there may be secondary impacts including risks related to greater economic activity and extensive use of air travel. Due Diligence Assessments and Project Approvals will consider these risks at Post Programme Boards.
  3. Not supporting Fossil Fuels: The programme will not support initiatives that are linked to investments in fossil fuels.
  4. Reviewed for ICF Financing: The programme governance structures will review grant spending regularly to determine if any of the grants meet the criteria to qualify as ICF.
2. Any proposals from multilaterals to Boards should set out relevant Climate and Environment policies and how risks will be mitigated.

Through engagement in programme management communities of practice, the programme team will stay up to date on the latest requirements for Climate and Environment, e.g. the planned Environment Bill.

Key stakeholders and consultation

The Good Governance Fund Phase Three was developed in close consultation with key partners in the region, including Embassies, partner governments, bilateral and multilateral donors and other international and national partners. Embassy-based teams play a critical role in identifying priority areas in each country, owning the country theory of change, holding relationships with key stakeholders and engaging with other donors and recipient government priorities. Aside from recipient governments, international financial institutions and other donor partners have been key partners, including: the European Bank for Reconstruction and Development (EBRD), the World Bank (WB), the International Finance Corporation (IFC), the European Investment Bank (EIB), the European Union (EU), GIZ (German technical cooperation), United Nations Development Programme (UNDP) and the United States Agency for International Development (USAID); as well as key international NGOs such as NDI. Within HMG, GGF works closely with colleagues on other UK Government programmes in the region and will continue to work on integrating more closely to ensure coherence across the range of relevant programmes. Project delivery through UK cross-government entities e.g. Government Communication Service, NICO, NSGI has proved valuable in the GGF as a way of offering valuable UK expertise and securing influence over reform processes.

## Appraisal Case

This section appraises the different ways for delivering the third phase of the Good Governance Fund in the Eastern Neighbourhood.

The GGF currently uses three delivery mechanisms to deliver its goals of democratic governance and economic resilience:

- Development Partnerships funding larger projects with the UK’s key strategic partners in country. This mechanism works with multilaterals and IFIs operating in multiple countries.
- A Managed Fund for Technical Assistance, contracted to an external commercial supplier, supporting emerging and time-sensitive interventions. To keep costs at reasonable level relative to output the Fund would require a minimum level of projects to achieve VfM (ca £3m).
- Strategic Support Fund will focus on the demand-side of reform, increasing and catalysing civil society’s ability to demand reform and implementation from the government. This delivery mechanism tends works with CSOs, think tanks and private sector associations operating in multiple countries or in a single country. The reorientation of the Strategic Support Fund towards local grants responds to the previous GGF Phase Programme Completion Review (PCR) from August 2021 which recommended revisiting the fund’s purpose – this is supported by evidence on the key role of a diverse and inclusive set of representative civic actors in strengthening the demand side of reform. Delivery of TA towards these organisations will remain.

Assessment of options
The Appraisal Case assesses the following options using the following criteria:
1. Effectiveness: Comparing reform outcomes in relation to the total cost of inputs.
2. Efficiency: Comparing the different option outputs in relation to their total cost of inputs.
3. Economy: Comparing the choice of options in relation to their input costs.
4. Equity: Comparing options on their scope to potentially address gender and social inclusion.

 Table 2. Assessment of Options

	Option A: Do Nothing	Option B: Refreshed	Option C: Development Partnerships only	Option D: Focussed
Delivery mechanisms	None	Development Partnerships, Managed Fund, and Strategic Support Fund	Development Partnerships only	Development Partnerships and Strategic Support Fund
Effectiveness	LOW / End of GGF, loss of some political influence on reforms, and the chance of back-tracking on existing open society reforms therefore increases.	HIGH / Longer term engagement on reforms, which continues after technical assistance ends, increases chances of sustainability (also builds relationships and enhances creditability). / GGF can continue to be flexible which had enabled it to score ‘A’ scoring programme.	MEDIUM / Multilateral engagement is sustained. Scope for undertaking ongoing support (like option B). / Much less scope to be responsive to change and flexibly respond to change.	HIGH / Same as in Option B but now the same funding is more focused on fewer projects. The unit cost of a reform outcome falls (inputs delivers greater economies). / Balanced demand and supply side engagement allowing reforms to be citizen and politically supported, increasing chance of sustainable reform. / The option retains flexibility to respond quickly
Efficiency	LOW	MEDIUM / Highly responsive but the unit cost of outputs is higher. Many mechanisms/ instruments mean fixed overheads incurred with higher number of providers as they are not averaged down – as would be the case when higher spend per provider	HIGH / Less responsive but more strategic. Fewer projects than option B. Units cost per output kept down by doing greater activity with a limited number of partners	HIGH / Development Partners – moderately less responsive than Option B. Much more responsive relative to option C. Issuing local grants/ contracts will allow unit cost of per output to be managed and local engagement will increase relevance and responsiveness
Economy	N/A / Transfer of some resources to increase capacity by Embassies to lobby locally	LOW / Higher staff engagement with different implementers., Higher implementer management costs. A low level of funding through flow per country means limited scope for economies.	MEDIUM / Lower-level staff engagement per implementer, and lower management cost are feasible. The minimum level of project funding needed to justify the overheads can be easily delivered. Provides a greater opportunity to remain under threshold for costs	MEDIUM / Medium staff engagement, lower management cost relative to option B
Equity	LOW	HIGH / All options allow scope target equity. Ranking based on which option is likely to give the more sustainable impact.	MEDIUM / All options allow scope target equity. Ranking based on which option is likely to give the more sustainable impact.	HIGH / All options allow scope target equity Ranking based on which option is likely to give the more sustainable impact
Downside risks	LOW / Undermines previous progress and UK reputation	MEDIUM / Larger diversity of instruments but less scope to actively manage prioritisation with fewer staff resources	LOW / Lower UK visibility and flexibility – interventions less adaptable once started	MEDIUM / Use of an FCDO Framework Agreement requires focused resources.
Net Score / Range	LOW	MEDIUM	MEDIUM	HIGH

Detailed appraisal

Option A: Do Nothing

Overview: No governance or economic reform programming in Armenia, Georgia and Moldova. Embassies could continue to advocate for democratic governance and economic resilience through diplomatic tools but with no GGF programmatic resources.

Impact: This option would deprive Embassies of a critical source of funding to support host nations in design and implementation of reforms that deliver more transparent and accountable governance as well as inclusive economic growth. Absence of GGF will impact relationships and reputation in-country and miss the opportunity to demonstrate the UK’s support to the host government

Risk: Other donors may step-in, but no other donors focus on technical assistance that is similarly fast-paced, flexible and responsive. The programme has a strong UK brand and there may be reputational risks for the UK more broadly from withdrawing, which may negatively affect HMG engagement on other policy areas. Embassies would also lose a deeper understanding of specific problems and add less value in policy dialogue with governments. It would weaken our lobbying approach and reduce our ability to influence reform.

Value for Money: ODA funds would be allocated elsewhere in the FCDO. This would lose impact in a region of importance in the Integrated Review and damage country relationships where we have previously supported governance and economic reforms.

Option B: Refreshed

Overview: Use of the same delivery mechanisms (Development Partnerships, Managed Fund, and Strategic Support Fund) as GGF Phase Two but applying lessons learned from the PCR. Reinstatement of the Managed Fund following suspension of its EN work in 2020/2021. Programme management would be regional (a hub in Tbilisi and existing staff in three countries) and advisory support from the UK. The continuation of existing relationships would help to start delivery quickly. In line with review recommendations of Phase II, GGF Eastern Neighbourhood would reduce the number of projects and have a stronger focus on implementation of reform and delivering political momentum through technical assistance.

Impact: This option would maintain the UK’s relationships, access and influence. It would allow delivery from an early stage, continuing relationships with Development Partners, continuing the Managed Fund and support to CSOs through the Strategic Support Fund.

Risk: This option would require a consolidation of the number of projects and focus on ensuring they add up to more than the sum of their parts. All projects would need to align with the new PROF and deliver results and value for money. Phase 3 would encourage fewer more targeted projects.

Value for Money: Timely and responsive, however, requires greater management resource relative to all the other options.

Option C: Development Partnerships Only

Overview: This option would channel all funds to Development Partners, for example the World Bank, the EBRD and NDI. This would involve fewer but larger projects to improve programme management. The GGF would provide support for both the supply and demand of governance and economic reform, but support for demand (for example via CSOs) would be channelled by Development Partners. The Managed Fund and the Strategic Support Fund would not continue.

Impact: This would be highly focussed on Development Partners. The focus on a small range of Development Partners would help to maximise intervention impact, for example allowing for a greater focus on ‘unlocking’ additional support from other donors. Projects with development partners are better positioned to respond to above-mentioned concerns around sustainability, given their longer-term nature and ability to influence and support further lending and technical assistance operations.

Risk: The focus on Development Partners would risk a lower profile for the UK and potential for the UK to use its political capital to enable reform. Project design should focus on identifying UK engagement and political obstacles that the UK could seek to tackle to encourage reform. To ensure that the GGF is gender-sensitive in its approach, efforts would need to be taken to improve their performance in this space. EBRD’s upcoming Gender Empowerment Strategy will be one opportunity to drive forward the changes needed. Our ability to influence would be limited and would require strong engagement at HQ level for influencing.

Value for Money: More sustainable impact and resource efficient but this option loses the ability to respond in a timely manner.

Option D: Focussed

Overview: The GGF would move to a more focussed approach, working with Development Partnerships to supply national government’s demand for reform and continuing with a more focussed Strategic Support Fund, including support to civil society organisations, think tanks and private sector associations to increase and catalyse local demand for reform. In lieu of the Managed Fund (which will only apply to Ukraine and not the Eastern Neighbourhood), this option could include the use of FCDO Framework Agreements (such as the Expert Advisory Call down Service (EACDS) for specific, technical support where this is not available through other Delivery Mechanisms. This option responds to Mid-Term Evaluation and Project Completion Report recommendations relating to greater clarity around the purpose and use of each delivery mechanism, and more selective and coherent programming with a stronger focus on outcome level change. It is guided by recent strategic documents, including the Integrated Review which state focuses on bringing our diplomatic and development expertise and policy together and working with allies, like-minded partners and civil society worldwide to protect democratic values, build their resilience to state threats and shore up stability and improve socio-economic conditions in fragile regions.
[note] EACDS expires in October 2022. Any call downs undertaken before the end date will run on past the Framework end date as the call downs and Framework agreement are not co-terminus. EACDS will be replaced with another Framework which will be tendered in 2022 and will be live to ensure no service gap.

Impact: This would be a more focussed approach. The more focussed approach would include working with a limited number of Development Partners, to maximise economies of scale. It would also include replacing the Managed Fund with the use of an existing FCDO Framework Agreement to maximise efficiency. The Strategic Support Fund would continue with a greater focus on the demand-side of reform. A limit on the number of projects through each delivery mechanism and in each country would help to reduce resource requirements for programme management. However, a clear spend target for gender and social inclusion targeted interventions would ensure our ambitions to inclusive, open governance and economies remains consistent. A stronger focus on building political momentum would help to maximise impact and the sustainability of the interventions.

Risk: The loss of the Managed Fund and its replacement with the use of an FCDO Framework Agreement may impact the ability of the programme to deploy rapidly. The use of an FCDO Framework Agreement would require staff resource at Post level. The focussing of the Strategic Support Fund on a more limited number of projects may risk the ability to engage with a broad range of actors but would help to support organisations more strategically and potentially for longer periods of time.

Value for Money: Will require resource requirements in using FCDO Framework Agreements, though delivers better economy than the Managed Fund under Option B. Provides a good compromise between responsiveness and delivering sustainable intervention.

RECOMMENDED OPTION: Option D: Focussed. A focus on Development Partnerships, the potential use of an FCDO Framework Agreement (rather than the Managed Fund) and more focussed Strategic Support Fund would be more manageable within the likely levels of staffing. This would enable a more balanced approach to reform and greater focus on strategically engaging with reform processes to build political momentum and provide technical assistance. We would be able to respond to emerging priorities and scale up/scale down as necessary. A stronger focus on Development Partnerships may encourage more innovation of approach.

Assessment of evidence

Technical Assistance Overall
The evidence base for interventions that would be supported through options B, C, and D above is assessed as medium. The evidence on whether technical assistance ‘works’ is limited, and there is little evidence of technical assistance leading to cumulative impact and better development outcomes over time, in part due to underinvestment in monitoring and evaluation and methodological challenges. There is, however, consensus on the factors that make TA more effective. These conditions for success underpin the GGF model and ToC, and include the importance of – among others:
[note] Literature used to draft this paragraph includes: Cox, M., & Norrington-Davies, G. (2019). Technical assistance: New thinking on an old problem. Open Society Foundations. London: Agulhas Applied Knowledge; Megersa, K. (2019). The Effectiveness of Technical Assistance in Middle Income Countries. K4D Helpdesk Report 705. Brighton, UK: Institute of Development Studies; The Organisation for Economic Co-operation and Development (OECD). (2012). Supporting Partners to Develop their Capacity: 12 Lessons from DAC Peer Reviews. Paris, France: OECD Publishing. http://www.oecd.org/dac/peer-reviews/partneringwithcivilsociety.htm; Price, R.A. (2019). Technical assistance and capacity building in institutional reform: lessons learned. K4D Helpdesk Report 669. Brighton, UK: Institute of Development Studies; Timmis, H. (2018). Lessons from donor support to technical assistance programmes. K4D Helpdesk Report. Brighton, UK: Institute of Development Studies; GGF Midline evaluation.
  1. A demand-driven approach with buy-in from recipient country governments: Supply-driven TA has been unsuccessful. The GGF external midline evaluation found the GGF Phase 2 was strongly demand-driven, projects were designed to meet government demand, built on identified political support and were aligned with key reform agendas.
  2. Locally-driven and politically informed solutions: TA has been criticised for promoting technical solutions to political challenges, and insufficient adaptation to the political economy context. Under all appraisal options, GGF Phase 3 will focus more on political economy analysis and building the political momentum for reform via programming and political engagement.
  3. Capacity transfer not capacity substitution: This has been a limitation in some previous GGF projects and this will be addressed by placing a firmer emphasis on sustainability, including through a greater focus on building institutional support and organisational capacity to support handover, and making greater use of mentoring and learning-by-doing as opposed to formal training.
  4. Conducive institutional settings: Some of the most effective TA has been in institutional settings that are well defined and relatively insulated from political pressures, such as central banks or specialised units within line ministries. This resonates with GGF’s experience and we will continue to explore opportunities to deliver TA in such settings, especially during periods of political uncertainty.
  5. Iterative and adaptive approaches: Learning by doing and adapting during implementation is crucial for effective TA. This requires tolerating a level of unpredictability and accepting occasional failure, as well as the time and resources to work adaptively. The GGF’s adaptive working was identified as a critical contributory factor to success in its second phase.
  6. Realistic timelines and sustained engagement: Realistic implementation timelines and expectations based on thorough assessment are necessary for TA effectiveness. Reform is a long-term process and the expected horizon for outcome achievement in governance related interventions can be as long as 10-15 years. The importance of developing and sustaining relations of trust and credibility with partners is emphasized across the literature. Sustained engagement with particular national institutions can help in identifying and responding to entry points and political openings and offer the UK influence.

GGF Historic Performance
The GGF has consistently scored A in Annual Reviews. Significant progress has been achieved in policy and delivery reform (outcome 1) during previous phases of the GGF. There are numerous examples of draft laws, regulations, and systems developed or revised with support of GGF projects being adopted in national legislation or otherwise institutionalised, or embedded within national structures. Several GGF projects have paved the way for follow-up activity undertaken by other donors and/or have facilitated other funding and financial resources. However, implementation has in some cases lacked behind. The PCR assessed that while output targets have been achieved, the programme did not fully meet all outcome targets due to an ‘implementation gap’. Wavering political support was a common inhibiting factor due to – among other factors – government instability, change in political leadership and staff turnover. Sustainability has therefore been identified as an area that requires further attention, including by strengthening incentives during programme design and delivery These lessons relate to for instance alignment to international commitments, close collaboration with like-minded donors, focussing on tangible political pay-offs.
[note] GGF Midline Evaluation 2021, Annual reviews 2018-2021, Managed Fund phase 2 final reporting.
[note] # North Africa Technical Assistance Facility (TAF)/ TAF Sustainability Review: March 2020

Literature highlights the importance of adopting a system-wide approach in TA and working with multiple actors, including non-state actors. Both institutionalisation of citizen engagement and civil society networking are important in securing government accountability. GGF projects that connected the supply and demand side of reform (outcome 2), were found to be particularly successful. Phase 2 of GGF included projects that have successfully strengthened independent media outlets and supported demand-side accountability through civic monitoring of elections, political party funding, and procurement. Progress has also been made in strengthening public-private dialogue in EN countries through GGF support to investors councils, resulting in tangible improvements to the business environment. Support to civil society will be delivered in line with evidence on effective capacity development interventions. Interventions will be underpinned by a comprehensive mapping and analysis in view of Russia’s active support for pro-Russian civil society groups in EN countries.
[note] Price, R.A. (2019). Technical assistance and capacity building in institutional reform: lessons learned. K4D Helpdesk Report 669. Brighton, UK: Institute of Development Studies; Timmis, H. (2018). Lessons from donor support to technical assistance programmes. K4D Helpdesk Report. Brighton, UK: Institute of Development Studies.
[note] e-Pact (2016). Macro Evaluation of DFID’s Policy Frame for Empowerment and Accountability. https://itad.com/wp-content/uploads/2017/06/EA-Macro-Evaluation-Technical-report-Dec16-FINAL.pdf
[note] GGF Midline Evaluation 2021; Partner reporting.
[note] For instance SCS Global programme (2018). Capacity Development Interventions: A Guide for Program Designers.
[note] Chatham House (2018). Civil society under Russia’s threat: Building resilience in Ukraine, Belarus and Moldova; Emerson, M., Cenusa, D., Kovziridze, T., & Movchan, A. (2018). The struggle for good governance in Eastern Europe. Brussels: CEPS.

Political Access and Influence
There is case study evidence of GGF interventions cultivating access to decisionmakers and strengthening partnerships (outcome 3). Programme interventions have helped to open doors, build trust and give greater depth to relationships. There is less evidence on whether GGF involvement has facilitated UK strategic objectives due to challenges in differentiating GGF’s contribution. Phase 2 has surfaced lessons on strengthening diplomatic synergies, as well as the measurement of political access and influence. Evidence highlights the importance of a clear strategic direction and priorities to guide selection of activities, as responding to ad hoc requests for support from reform-minded counterparts does not necessarily lead to influence. This phase of the GGF will see strengthened monitoring of political access and influence.
[note] IMEL (2020). Political Access and Influence Assessment. Georgia: GGF Support for a business and investment environment that promotes a dynamic and inclusive MSME sector; IMEL (2020). Political Access and Influence Pilot Assessment. Serbia: E-government, including one stop shop for Real Estate Registration.
[note] Cox, M., & Norrington-Davies, G. (2019). Technical assistance: New thinking on an old problem. Open Society Foundations. London: Agulhas Applied Knowledge

Catalytic Funding
The UK will continue to seek to influence larger sums of funding from other donors. While there is limited research and evidence on the ways in which donors influence other donors, both GGF experience and wider literature offer examples. The PCR has highlighted several success stories where development partners have been able to leverage much wider impact by influencing loans/ investments and strengthening government capacity and transparency. Evidence suggests that by supporting Trust Funds, donors can incentive the World Bank to adjust its activities, particularly around thematic issues such as gender. The programme team and Advisers, working across FCDO, will work to draw influence from our wider investments as the largest World Bank shareholder. GGF’s Trust Fund with the World Bank has contributed to enhancing World Bank operations and programming, as well as influenced the Bank’s lending operations. The programme team and Advisers will also use the programming in the Eastern Neighbourhood to influence the wider relationship and operations of the World Bank, encouraging innovative approaches in the EN that could be tested and scaled in other regions.
[note] Haider, H. (2018). Donors influencing others donors and development. K4D Helpdesk Report. Brighton, UK: Institute of Development Studies.
[note] https://doi.org/10.1111/1758-5899.12464
[note] Good Governance and Investment Climate Reform Trust Fund Interim Report 2015-2021

The UK’s ‘Governance for Growth, Stability and International Development’ paper shows the importance of governance for stability, including negotiating between elite interests, peacefully managing tensions and preventing the recurrence of violent conflict. HMGs ‘Economic Development Strategy’ emphasises the importance of accountable institutions for preventing narrow, vested interests from capturing economic benefits at the expense of the economy.
[note] https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/786751/Governance-Position-Paper2a.pdf
[note] https://www.gov.uk/government/publications/dfids-economic-development-strategy-2017

Value for Money

GGF is expected to undertake a range of projects in a complex and changing contexts. In line with HMG guidance GGF will adopt 4E framework’ to assess the VfM of its programmes, aiming to balance:
economy (the cost of inputs) - example indicators could include primarily salaries and costs of technical events like workshops; Many Posts have relationships with Development Partners and have negotiated good management rates which will help to ensure economy.
efficiency (how quickly and easily the programme produces outputs) - example indicators could include unit cost of outputs and speed of output delivery.
effectiveness (outcome-level results) – example indicators relative unit cost of outcomes (capacity building) such as instances when partners translate TA into substantive policy commitments by Government
equity (how the benefits of programmes are shared to excluded groups) -- example indicators could include identify percentage of projects meeting GEM2 target

GGF will track and compare operational costs to benchmark rates and keep fees low. However, this linear approach is unlikely to capture the complexity and the uncertainty of contexts in which GGF operates. Past evidence shows that such contexts better results are delivered when we engage on not only reforms that have probability of success, but projects adapt and learn as they go forward including based on political context. We propose to record this adaptation throughout life of GGF activities so as implement the lessons learnt on an ongoing basis. The focus programme will be on monitoring that the project’s benefits delivered exceed cost. Under this approach the emphasis will shift to desired outcomes achieved. The GGF Value for Money strategy will be updated to reflect these changes.

To achieve the stated outcomes, the GGF will support reforms in targeted areas where beneficiary countries demonstrate reform commitment, and that align with HMG priorities. The GGF may also support reforms where beneficiaries either: (1) would gain from seed funding to pilot and test a concept or (2) where development partners would like to test approaches that could lead to significant learning and application elsewhere.

Theory of change
The hypothesis that underpins the GGF is that well-targeted, adaptive technical assistance provided to GGF countries will support reform in selected priority areas, strengthen demand-side accountability, and strengthen UK partnership with EN countries. This hypothesis forms the basis of the high-level theory of change presented below, which covers all EN country contexts. Country theories of change will elaborate change processes and assumptions for selected priority reform areas and contexts. The ToC responds to recommendations from the midline evaluation and PCR.

The impact that GGF aims to contribute to alongside wider government and partner efforts is: Improved democratic and inclusive governance (including prevention of democratic reversals) and inclusive economic growth which helps GGF countries in their resilience against malign influences and shocks. This long-term objective has a timeframe of around 15 years.

To achieve this, the GGF will deliver interventions that lead to three major outcomes:
1. Governments protect, consolidate, and advance reform in selected GGF priority areasto promote inclusive democratic governance and inclusive economic resilience, with reform also promoting greater gender equality
2. Civil society, media and private sector have increased capability to demand for and engage in reform, with spaces for engagement and inclusive democratic processes protected and strengthened
3. Strengthened partnership between UK and EN countries and like-minded partners which supports UK global campaigns.

Outcome level targets are expected to be delivered within the life of the programme (April 2025), subject to stated assumptions holding true. The pace and depth of reform and change will vary across countries, and the GGF will respond and adapt to this through a country specific focus which recognizes the trajectory that countries are on, and that governance and economic reform are often non-linear. GGF’s level of ambition and what is achievable by 2025 will hence vary across contexts, and may involve ensuring that countries do not reverse on key governance indicators (e.g. efforts to mitigate the rollback on women’s rights in some contexts). The maturity of the GGF country portfolio in a certain sector/thematic area may also influence what is achievable. GGF interventions may be scaled down or up depending on the level of traction.

To achieve these outcomes, the GGF will deliver the following outputs:
- Government institutions, parliament, civil society and media have enhanced capacity, support (knowledge, skills, evidence, models and political momentum/support) to protect/demand/drive/influence/implement reforms and influence social norms (with support to women’s rights organisations and other representative civil society)
- Critical GESI-sensitive / transformative legislation, policy, regulations, strategies and implementation plans designed and adopted (in line with international standards), and supported in implementation
- Expanded and strengthened UK dialogue and relationships/collaboration with government, like-minded actors and civil society to achieve programme impact and benefit wider HMG agenda
- Strengthened mechanisms for better two-way engagement (including in policy design, implementation and accountability) between the state and citizens (with a particular focus on marginalised groups) and strengthened private/public dialogue platforms
- Technical assistance approaches tested and evidence and learning informs programming

Outputs will be tailored to country context, ensuring complementarity with the work of others.

GGF projects will involve the delivery of responsive, adaptive, conflict- and GESI-sensitive technical assistance. TA modalities may involve: different approaches to capacity development, generation of evidence and analysis, technical advice and support, setting up of private/public dialogue platforms, and the use of UK political capital for unblocking reform and to build coalitions for change. The programme will make an active contribution to trialing and testing different technical assistance approaches and concepts.

Based on experience from the previous phase of GGF and similar programmes, a number of “mechanisms of change” can be distinguished that explain how delivered outputs can bring about outcome level change:
- Opening doors: The delivery of high quality, relevant TA builds the UK’s access and credibility and provides an entry-point for HMG into dialogue and relationships with new parts of government, donors or multilaterals, or into dialogue on new issues (relevant to outcome 3).
- Unblocking: TA can help to unlock a process or remove barriers. Examples include strengthened private/public dialogue platforms enabling the design and implementation of more relevant policy; or supporting countries to meet international standards which subsequently enables broader change (outcome 1, 2).
- Leveraging: Attracting, generating or mobilising additional resources or effort that enables the continuation of change in the process or system. This could involve unlocking funding or loans by IFIs and other donors, or allocation of government resources (outcome 1, 2).
- Improving quality and inclusiveness: Improving a process through promoting, inducing or enhancing change in policies, institutions and capacities. This may include enhancing the quality of investments by others, for instance by providing the analysis and evidence to strengthen gender sensitivity, anti-corruption and green growth dimensions of new projects (outcome 1, 2)
- Demonstrating: This could involve the piloting of new ideas/approaches or diplomatic influence to create bigger activity. Demonstration effect may also include governments experiencing the benefit of reform, or citizens identifying the benefits of reform on their lives, leading to broader reform or the demand therefore (outcome 1, 2).
- Learning & Adapting: Generating and compiling evidence and learning will promote an adaptive approach for greater impact and contribute to evidence base on technical assistance (all outcomes)

Projects will be identified and approved based on a range of factors, in particular:
- Political will/political economy analysis that shows broad support for reform
- Sustainability and potential for long-term results

Key assumptions underlying outcome-to-impact change relate to political context remaining sufficiently stable to embed reforms / not undermine benefits, sustained support and funding from other development actors, and the economy not being further de-railed by economic shocks (incl. Covid-related). Assumptions are discussed in further detail in Annex A.

The GGF EN Results Framework will be finalised prior to the programme start, drawing on learning to date and best practice from other programmes. Impact indicators will likely include (a subset of): EBRD transition indicators which measure the extent to which a country’s economy is competitive, green, resilient and integrated; Trends in citizen trust in government and citizen sentiment towards the West (subject to availability of secondary data sources); Selected World Bank Worldwide Governance and/or Varieties of Democracy (V-Dem) Indicators. At outcome level, indicators will focus on – among others- measuring: reform progress in selected priority areas (through progress markers or policy quality tracking), investment in reform by government and other development actors, contribution to gender equality objectives, strength of UK partnerships and reputation.

## Commercial Case

The GGF EN programme will align to existing Departmental-wide commercial processes and ensure key commercial risks are flagged.

1. The Appraisal Case sets out the case for Option D. This involves the following two strands:
  1. Development Partnerships (£xxm): funding larger projects with the UK’s key strategic partners in-country. These partnerships accounted for 56% of GGF spend in Phase One.
Partners: This strand tends to work with multilaterals such as the UN and IFIs operating in	multiple countries. The focus will be on associated technical assistance to support the supply of capacity to aid reforms. Reforms are often delayed due to development partners having insufficient technical assistance resources.
Advantage: Access to expertise, established relationships with governments, and ability to operate at scale and sustain longer term interventions. They are better able to catalyse funding for related to supply capacity building activities and set conditions with government for its delivery. Less programme management intensive than individual contracts and grants.
Disadvantage: Can be slow to mobilise. Less visible UK brand and less frequent reporting.
  1. Strategic Support Fund £xxm): largely grant-based fund, with some TA, focused on the demand-side of reform, increasing and catalysing civil society’s ability to demand reform and implementation from the government. This accounted for 12% of GGF spend in Phase One. It also includes ability to leverage FCDO frameworks for technical assistance if necessary.
Partners: This strand tends to work with CSOs, think tanks and private sector associations	either operating in multiple countries or in a single country.
Advantage: Ability to operate even as political appetites changes; builds long-term support	for reform demand; more responsive and agile
Disadvantage: Substantial programme management cost; Less able to provide funds for related capacity building activities.

Each GGF country will have a theory of change, for specific activity. Country Business plans set out where GGF, CSSF and other levers are used to achieve country level outcomes. Lessons have been learned from GGF Phase 1 and Phase 2, including a greater focus on Value for Money indicators (see Appraisal Case) as well as Gender Equality and Social Inclusion (GESI) indicators.

Value for Money

The primary cost driver for the GGF is international expertise (fee rates). The use of commercial suppliers is likely to be very limited (as development partners are typically multilaterals or established INGOs and the SSF prioritises CSOs). We will use existing frameworks for any commercial requirements, and these are evaluated against market rates with a preference for output based payments where feasible and proportionate.

Programme delivery costs via IFIs, multilateral organisations, NGOs and other donors include cost recovery rates plus any administration and management costs. We will negotiate these as appropriate to drive further value for money, and reflect agreed benchmarks used by FCDO in broader institutional agreements. Embassies negotiate contracts with implementing partners as they have a good knowledge of local market rates.

There is a vast wealth of local knowledge and expertise that is being drawn upon in GGF countries. Not only does this often demonstrate better value for money in terms of immediate costs, but by using local expertise we are more likely to cement government buy-in and produce more sustainable results from the GGF. As such, wherever possible, we seek to work with local partners or implementing organisations directly (largely through smaller SSF projects) or as part of delivery through other organisations (for larger projects where fiduciary concerns making working directly with smaller suppliers less appropriate).

Trust Funds could be either single or multi donor. For the World Bank GGF had a Framework arrangement, bringing projects under an umbrella bringing better Value for Money. A similar approach is being sought for the next phase.

Our market knowledge in country is supported by that of Embassies on the ground and our approach to date, informed by the Partnership Principles, has been to minimise risk by working with known and trusted partners.

Performance, costs and risks to delivery will be monitored regularly by programme staff and through regular partner meetings.

Which suppliers/implementing partners are expected to deliver the programme?

Strand I - Development Partnerships
Development Partners, such as multilateral organisations and established INGOs offer comparative advantages based on their networks, relationships with government, expertise and scale of activity. International Financial Institutions have scope to provide funds for related capacity building activities and set conditions for the use of these funds.

The selection of development partners will be determined based on a range of criteria including, but not limited to: Relevance of activity to FCDO priorities, relative thematic expertise, potential to deliver sustained engagement beyond life of GGF investment, their convening power and access to government networks as well as value for money. Under previous phases of GGF, MoUs and contribution agreements were established with a range of International Financial Institutions, multilaterals and bilateral partners, including but not limited to the European Bank for Reconstruction and Development (EBRD), the World Bank (WB) and the United Nations Development Programme (UNDP). All agreements will be subject to review of performance, value for money, and relevance of proposed projects and activities to GGF strategic interests.

Terms of Reference (ToRs) and MoUs are concluded with delivery partners using FCDO templates and frameworks. Agreements include options to adjust support upwards or downwards as required in the programme, often identifying key break points aligned to programme funding to make adjustments.

Competence of delivery institutions will be assessed through existing instruments such as Due Diligence Assessments, using existing assessments where possible. We will also link to key findings from any past and future Multilateral Aid Review. We will supplement these with assessments of previous performance in relevant GGF countries, and other evidence of their understanding of local markets, ability to allocate and manage risk, cost drivers and management of downstream partners. These assessments will focus on the partner’s capability to perform appropriate procurement, financial and risk tasks ensuring they have key mechanisms in place to deal with such issues as corruption and fraud. MoUs also will detail key performance indicators to measure and manage performance.

Strand II – Strategic Support Fund

SSF mechanism funds fast and flexible grants and TA for innovative policy engagement activities and pilot interventions, primarily to local organisations. These projects are delivered on a short timescale (usually within a year) and are catalytic in nature. Proposals are submitted by applicants for review and endorsement by programme boards at Post and approved by GGF SRO.. Non-profit, public and for-profit organisations are eligible to apply as well as IFIs. This includes civil society organisations, think tanks and private sector associations. Criteria include: how they will apply value for money principles, appropriate use of local expertise, level of political will and how they will build political momentum, innovation and alignment of proposed projects with GGF ToC. Specific criteria have also been established including proportionate due diligence and risk assessments arrangements.

For specific, short-term technical work, the GGF Eastern Neighbourhood intend to use the FCDO Expert Advisory Call Down Service framework (EACDS).

EACDS will expire in October 2022 but is set to be replaced by a similar framework Overseas Development Assistance Programme Services (ODAPS). Where Framework arrangements do not already exist, the Programme Hub will negotiate fees and overheads when putting in place new Memorandum’s of Understanding and Accountable Grants. Likewise the GGF country leads work with other Embassy colleagues to negotiate contracts with SSF partners as they have a good knowledge of local market rates.

Monitoring, Evaluation and Learning
The GGF will draw on support from an external MEL supplier, that EECAD intends to procure through the CSSF framework. It is expected that this regional contract will start to be operational during 2021/22. The MEL provider is expected to offer services to strengthen MEL capability across the programme (HMG and partners), support the establishment of robust baselines and measurement of outcomes, support the generation of (evaluative) evidence, and facilitate learning. Lessons from GGF’s previous MEL contract (2018-2021) and other similar contracts are feeding into the ToR and design of the EECAD MEL contract. The contract will be managed by the EECAD MEL advisers.

## Financial Case

The GGF will spend up to £38 million in the European Neighbourhood during FY2022-25 and will be resourced from FCDO baseline (previous GGF Business Case funded under CSSF). This has been requested in the 2022/23 – 2024/25 Spending Review and will be fully Programme funded (RDEL). There are no capital costs (CDEL).

Specific allocations for each country will be flexible and agreed through the Eastern Neighbourhood Strategy Board on an annual basis according to strategic need and progress in delivering meaningful reforms. Indicative annual allocations based on FY22/23 figures are.

Table 3. Anticipated Annual Budget Allocations European Neighbourhood

Financial Year	Budget
22/23	£10m
23/24	£14m
24/25	£14m
Total	£38m

Table 4. Indicative Country Allocations 2022/23

Country	Programme Allocation
Armenia	£3
Georgia	£4m
Moldova	£2.5
MEL	£500k
Total	£10m

The GGF will use a two delivery mechanism approach where it has demonstrated results through combination of short and longer term initiatives. The GGF’s allocation will be delivered through partnerships with a range of international and local partners including international financial institutions; international NGOs; UN agencies; other bilateral donors such as USAID and GIZ; and, where possible and appropriate, local civil society organisations. As a flexible responsive fund, Development Partners and SSF partners will be identified based on priorities falling from theories of change. This flexibility also enables the fund to adapt to changing circumstances and reprioritise the budget to need changing needs.

As well as MEL costs with projects themselves there is up to £500k set aside for MEL work through the EECAD MEL supplier in 2022/23, £500k in 2023/24, £500k in 2024/25.

The GGF does not pay in advance of need and presumes to pay in arrears. Where partners request advanced payment, these will be considered by the PRO in line with FCDO criteria for advanced payment.

Prior to agreements, tax costs, in the UK and in country will be considered and factored into budget.

Cost Profiling and Planning:

Specific country allocations are determined based on the contextual environment, existing programmatic commitments and an assessment of the strategic value and programmatic risk within each pipeline proposed by Embassies. As a demand led fund, country allocations will be agreed yearly and depend on a combination of need and absorptive capacity. Need can broadly be assessed using the following criteria:
- GDP/capita
- Population
- Fragility and risk of instability
- Freedom House – Democracy Score
- Transparency International Transparency and Corruption indices
- V-Dem
- World Bank Doing Business Indicators
- World Bank Worldwide Governance Indicators

Absorptive capacity will depend on presence of other donors, how ‘aided’ the country is and whether there are policy/thematic gaps which align with GGF priorities, and institutional commitment and capacity to deliver reform. We have not developed a rigid resource allocation model, but will assess need, demand and absorptive capacity through an iterative process during planning stages each year.

Anticipated Quarterly Spend 2022/23
Across the portfolio we will generally seek to include proposals at the start of the FY up to around 120% of the funds available, in the expectation of slippage through the year. Country teams and the PARG will then work through the FY to monitor spend and only agree proceeding to bring through spend beyond 100% where there is underspend elsewhere which will allow for this, or where additional funds can be secured. These allocations have been incorporated in the FCDO Spending Review commission.

Table 5. Anticipated Spend 2022/2023
	Q1	Q2	Q3	Q4
Anticipated Spend	£1m	£3.5m	£4.5m	£1m
%	10%	35%	45%	10%

Key assumptions / Potential Risk
Although first year usually spend less with start-up of projects, this is expected to be mitigated with design starting in Q4 of 2021/22.

Given the nature of the fund, it is not possible to state upfront the detailed Input Sector Code breakdown (for example Economic Reform may be in a variety of different sectors) and we anticipate it to be broadly as follows. The below figures are indicative and will be amended upon completion of MOUs, grants and contracts.

Table 6. Estimated Funding by Sector Code.

Development Partners Strand
Funding Type: Multilateral Organisations, Not for Profit Organisations, Other Bilateral Donors
Benefiting Country: Armenia, Georgia, Moldova
	Input Sector	Input Sector Code	Indicative Percentage Allocation
1	Strengthening Civil Society	15150	29
2	Economic and Development Policy/Planning	15110	70
3	Legal and Judicial Development	15130	1
SSF
Funding Type: Not for Profit Organisations, Procurement of Services
Benefiting Country: Armenia, Georgia, Moldova
	Input Sector	Input Sector Code	Indicative Percentage Allocation
1	Strengthening Civil Society	15150	71
3	Economic and Development Policy/Planning	15110	27
3	Legal and Judicial Development	15130	2

Table 7. Markers

Marker	Outcome consideration
Gender	Significant
Disability	Not targeted
Climate	Not targeted
HIV/AIDS	Not targeted

Financial and Fraud risk assessment

The GGF operates in countries where there is a significant fiduciary risk. This is mitigated by ensuring that:
- No financial aid will be used. Any support to a government institution will be earmarked and paid in arrears based on delivery and results.
- All funding is to be channelled through trusted partners with sufficient financial capabilities who are aware of FCDO policy on fraud and fiduciary risk management. Proportionate due diligence assessments are carried out prior to the disbursement of funds.
- Where we are less familiar with partners’ financial systems and procedures in country, we will be conducting in-depth, local level due diligence assessments, and will monitor closely any actions arising from these assessments. Funding will not be disbursed if we have concerns about an organisation’s track record.
- Project risks are monitored and escalated by Post Boards on a quarterly basis
- We will use political economy analysis and lessons learnt from past programming to understand incentives and risks in working with government agencies and anti-corruption institutions and particularly in relation to any work around privatisation and restructuring of state-owned enterprises, to avoid elite capture and misuse of aid resources.

Disbursements will broadly be split as follows. Delivery Chain Mapping is conducted for projects to assess aid diversion risks and mitigation as well as Due Diligence for each partner:
- Development Partner payments will be quarterly or six monthly, depending on the individual agreement and an assessment of need. These payments are generally made against a predetermined schedule, with payments conditional on the receipt of financial and progress reporting for the previous disbursement period demonstrating that 80% of resources provided in previous payment has been utilised.
- SSF payments will be made quarterly, upon receipt and agreement by Embassies of financial utilisation reports from implementers.

Due Diligences will be assessed for each project where there isn’t a current valid one for that partner and completed by the relevant Country Programme Manager and Adviser, clearing through Posts for context. Key recommendations noted in Due Diligences will be followed up. In instances where an earlier Due Diligence is valid for a similar project by that partner, a review will be completed as to additional information (e.g. country context). Delivery Chain Mapping will be conducted for projects to assess aid diversion risks and mitigation and reviewed throughout the lifecycle of the projects.

Finance processes will continue in the same manner in the Covid-19 context, but with accuracy of forecasting likely to be more difficult due to challenging circumstances and likely delays to or requirement to reformat activity. There may also be opportunities or requirements to consider new activity with potential to increase spend/financial pressure

Tracking, reporting & accounting for funds

The GGF is monitored in line with FCDO PrOF processes and procedures. Monitoring arrangements have been established for each component. The GGF Programme Team in the EN Hub will hold regular (progress review and finance) face-to-face or virtual meetings at least quarterly with IFIs/multilateral partners. Small grants partners in country agree reporting cycles and project completion reviews.

Accounting takes place on a resource basis. Across all strands, partners are required to provide GGF with regular (normally monthly) financial reporting identifying spending against agreed project budgets, regularly updated forecasts and remaining cash balances. The GGF does not pay in advance of need and presumes to pay in arrears. Where partners request advanced payment, these will be considered by the GGF EN PRO in line with FCDO criteria for advanced payment.

The GGF is represented reports alongside the EN CSSF to the European Neighbourhood Strategy Board and the Eastern European and Central Asia Directorate.

We will use existing tools to monitor and report on financial and project performance (including progress on delivery) to senior management on a monthly basis. These processes will allow us to identify and flag any risks or issues of concern as well as ensure compliance with best practice.

The GGF follows FCDO accounting rules. Regional Team Leaders serve as SRO for their region and report to Regional Boards (via the Scrutiny/Portfolio Advisory Boards in EECAD. The PARG finance analyst is responsible for overall management of the GGF’s financial reporting, with Quality Assurance from the PRO and overall oversight from the SRO. HEO GGF country leads are responsible for financial management of their respective programmes.

Assets:
The majority of programme activity will be technical assistance, which will not generate assets. However, some assets will be purchased where there is a strong case, for instance IT hardware where needed to make progress on key reforms or as part of SSF projects. Procurement of such assets will undertaken as FCDO guidance. All assets are recorded at the project-level by Programme Managers. A central register is maintained. Regular spot checks will be carried out.

At the end of project activities, a decision will be taken on whether to transfer ownership to the partner. Where the assets will continue to be used for the intended purpose, and the Programme Team are confident that the partner has adequate capacity and capability to maintain assets, the normal outcome will be to transfer assets. If there are concerns, a decision will be taken between the Embassy and the Programme Team on what to do with assets (including whether to transfer them to another partner).

Financial accounting considerations
The GGF expects that there will be no legally binding agreements or other liabilities under this Business Case.

## Management Case
#### Programme Management Changes
#### The next phase of GGF will be taken forward through a single department, FCDO. The entirety of the GGF portfolio (now split into Eastern Neighbourhood, Ukraine and Western Balkans) will fall under EECAD and Western Balkans remits respectively. The Portfolio SRO is the Additional Director, EECAD who will have oversight of this programme. The descriptions below mainly pertain to the Eastern Neighbourhood programme.
#### Under this new phase of GGF the bulk of programme management and decision-making will move from London to sit at regional level in the EN hub with the Head of the EN CSSF hub acting as SRO for the GGF EN. PARG will convene a workshop with relevant teams following business case approval to ensure clarity on the transition of management arrangements.
#### PARG will continue to work with the EN hub in Tblisi, to bring together EECAD GGF and CSSF programme teams to ensure complementarity between funding streams, consistency in programme management standards, and coherence with FCDO policy priorities. The last PCR identified that the blend of political, advisory and programme management experience is important for the success of the GGF.
Figure 2. Management and Approvals

#### Programme Management Set Up

The Eastern Neighbourhood GGF will be led by a Grade 7 Senior Responsible Officer (SRO), supported by SEO Programme Responsible Officer who will coordinate the effective delivery across three countries. The SRO will provide updates into the EN Programme Board, which has responsibility for setting overall programme direction in EN. The EN Programme Board includes the Governance, Economics and M&E Advisers.

A programme team in each country will be led by a HEO programme manager (also lead for CSSF programmes in country). This will ensure cohesion between programme funds and delivery to country board objectives.

EECAD Programme, Advisory and Results Group (PARG) will provide:
  1. 1 Governance and 1 Economic Adviser will provide thematic expertise to all EN programmes (GGF and CSSF); they will sit on each board and have a vote on approvals;
  2. MEL, Conflict, Gender advisory capacity
  3. support on specific aspects of the programme finance and corporate compliance support, through a shared Finance Analyst.
  4. Resource to manage whole of GGF trust funds and large arrangements with IFIs including EBRD and World Bank that provide efficiency savings, support good financial management as well as ensure consistency between three GGF programmes.

EECAD intends a whole of portfolio M&E programme, that will be available to EN GGF. Coordination, cohesion and lesson sharing will be provided by Head of EN Programme Hub, Head of Delivery Ukraine Head of PARG. The SRO’s work also includes encouraging lesson sharing across the GGF network, engaging with priority countries and supporting advisory collaboration with EECAD PARG.

The SRO, working with Deputies for the specific sub-regions, is responsible for the delivery of excellent technical advice across all GGF countries and ensuring quality advisory inputs are given across all GGF countries and mechanisms, managing and supporting the team of advisors and thought leadership.

Post Programme Boards are responsible for overseeing day-to-day project activity across their whole programme (including GGF) in their country, leading on strategic direction with technical support and voting from the Governance, Economics and M&E Advisers, and escalating risks. Consolidated finance reports are considered by the EN Hub on a monthly basis; and risks escalated by Post Boards on a quarterly basis.

Programme teams in Embassies
(Note some positions may be consolidated into one GGF role though most roles will likely be a combination of GGF/CSSF)
Armenia
- 0.5 FTE Country Programme Management (HEO)
- 1 FTE Country Programme Management (EO)

Moldova
- 1 FTE Country Programme Management (SEO)
- 0.5 FTE Country Programme Management (HEO)

Georgia
- 1 FTE Country Programme Management (HEO)
- 1 FTE Country Programme Management (EO)

Regional Programme Hub (Georgia)
- 0.2 FTE Hub Programme Hub Lead and SRO (Grade 7)
- 1 FTE Hub Programme Responsible Officer (SEO)

PARG, EECAD London
- 1 FTE Governance Adviser
- 1 FTE Economist
- 0.5 FTE MEL Adviser
- 0.3 FTE Conflict Adviser
- 0.3 FTE Gender Adviser
- 0.2 FTE Team Lead

Advisers will keep a strategic view of the trends and issues though may get involved in project-level dynamics if this is pertinent to understanding the broader context. For example, this could be a structured/dedicated engagement as questions emerge around project design and then a regular monitoring touchpoint. Ambassadors and post will be able to go directly to advisers – they are not a programme only resource and some issues will not need a programme to achieve objectives.

Figure 3. Programme Development

1. Project approvals will take place through Post Programme Boards (PPB) and the SRO. PPBs for Armenia, Georgia and Moldova approve all project concept notes with at least two weeks for review, before being sent for approval to the SRO. The Governance, Economics and M&E Advisers sit on each of these boards and have a veto/vote. Some Programme Boards may be by email; these also require at least two weeks for project concept note review.
2. Projects will be assessed against the factors listed above, including:
1. Political will/political economy analysis that shows broad support for reform, or where reform is slowing or showing signs of regression;
2. Understanding of key stakeholders including unsupportive and influential stakeholders, and how they will be mobilised to build political momentum;
3. Sustainability and long-term results, including potential to influence major donors; and
4. Value for money
GGF in the Eastern Neighbourhood operates alongside the Eastern Partnership CSSF Programme. The GGF SRO is a Board member for the EP Programme and EECAD scrutiny and regional boards.

Table 8. Board Governance

BOARD	MAIN RESPONSIBILITIES
Regional Programme Boards	Responsible for ensuring the successful delivery of Programmes contributing towards the relevant regional NSC strategies. The Boards provide strategic oversight and direction, ensuring Programme allocations are spent in line with NSC strategic priorities and objectives.
Scrutiny Board	Accountable to the Regional Board to ensure co-ordination of activities across programmes and to monitor and assess how cumulative outcomes deliver towards the NSC Strategy. Makes recommendations to the Regional Board on delivery of the Programme, and highlights issues requiring escalation and action. Monitors quarterly narratives from programmes on impact, spend and risk.
Post Programme Board	Responsible for the implementation of programmes and projects. Includes the Governance, Economic and M&E Advisers. General responsibilities may vary between Posts, but include: / Project approvals within delegated authority / Ensuring join up of policy and programming / Ensuring coherence between different programme strands / Monitoring and evaluating project progress and reviewing outputs to activity schedules. / Ensuring procurement complies with HMG/EU guidelines. / Monitoring and managing project level risk / Financial management; prism procurement, monthly reporting on spend (actuals and forecasts).

The EN programme hub will also work closely with CSSF country programme teams and continue to focus on strengthening this alignment, simplifying governance arrangements and taking advantage of an expected streamlining of processes as FCDO structures and arrangements evolve. The GGF also works closely with the Counter Disinformation and Media Development (CDMD) programme, ensuring shared objectives and avoiding duplication.

The main areas of overlap between the GGF and other programme strands are around Media Freedom, economic reform, Rule of Law, Democracy and Justice and Anti-Corruption.

FCDO programme guidance and processes across the department were brought in for FY 2021-22, and PARG will therefore apply the FCDO programme guidance and rules. There may also be some requirement to operate on parallel systems e.g. for finance until FCDO systems are in place.

What are the management arrangements for implementing the programme?

The SRO for the EN hub will report to the EN Board Chair, working closely with the Deputy Head of PARG.

What are the risks and how will these be managed?
1. Overall, we assess the programme risk to be major taking into consideration the scale, complexity and geographical coverage of the programme.
2. Risk (set out in the Strategic Case and Annex A) will be closely tracked by the PRO who will hold ownership and report to the SRO routinely on risk. Individual country risk registers for the programme will be held by post and maintained by the HEO with support from the EN hub.
3. The risk statement is included in Annex C.

The top-level risks across the portfolio:
1. The GGF has developed a GGF Risk Approach Document based on best practice which defines GGF’s risk governance, appetite and management approach across portfolio, programme and project level. This programme will be updated to reflect the GGF requirements.
2. For the next phase of GGF EN, the top risks are:
1. Political risk through resistance to our efforts from host governments, political instability (frequent changes of government/reshuffles/elections) or worsening socio-economic conditions or lack of progress in reforms leading to protest or instability – mitigated through using HMG analysis and early warning to inform strategic and adaptive programme delivery.
2. Reputational risk connected to political developments and UK relationship with/support for less reforming administrations
3. Financial risk through lack of sufficient oversight, leading to risk of underspend or overspend – mitigated through strategic over-programming, rigorous financial profiling and engagement with partners to ensure timely delivery.
4. The GGF not being sufficiently strategic across the portfolio – mitigated through regular political dialogue, focusing on areas where UK has added value, high quality Theories of Change, and working closely and coherently with other CSSF programme teams to remain focused on the NSC strategies and GGF comparative advantage
5. An increase in the size and geographical application of the fund also carries risks (particularly operational, delivery, and around whether GGF countries have the capacity to absorb additional technical assistance) which we would mitigate through careful forward planning, building capacity of the existing team, and planned and targeted recruitment.
More detail is available in the GGF Risk Approach Document and the risk registers. The full risk table in Annex A also includes mitigation measures and net ratings (following mitigation). Working across three countries spreads the risk allowing the programme to scale up or down.

Covid-19 and risk
Top Covid-19 related risks which the GGF programme teams will continue to monitor are:
- Political risk due to the impact in GGF countries and the region, further exacerbating existing risks and means host governments priorities on reform slow or at worse undermine civil liberties and freedoms in the long term;
- Delivery, operational and monitoring risks due to changes (such as travel restrictions) in the operating environment;
- Fiduciary risk due to delay or pause in activity leading to underspend;
- Increased safeguarding risks given exacerbated vulnerabilities, increased concentration of power and opportunity to abuse that power, riskier coping strategies, remote management, and rapid deployment of new actors.

Monitoring and Evaluation:
The GGF will continue to make systematic, planned and intentional use of evidence to drive decisions on strategy, portfolio, and individual projects. The objective of MEL in GGF is to provide an assessment of results to support accountability of funds spent, and support evidence-based programming, decision-making and inform policy discussions. The MEL approach integrates principles adaptive management, to ensure that the programme can deliver in changing and politically volatile contexts. It adheres to the FCDO Programme Operating Framework and responds to PCR recommendations. MEL activities will support monitoring of country business plans, the EN and relevant components of Russia NSC strategies.

Projects will each have their own results framework and risk register, which will be aligned with the overall programme results framework and risk register. These are reviewed and updated regularly (at a minimum quarterly). A single Delivery Plan for the GGF has been established and is regularly monitored. Posts will have a Theory of Change that includes GGF. This should be updated annually with input from the Governance, Economics and M&E Advisers.

M&E Governance
Four groups of stakeholders are involved in the collection, analysis and reporting of MEL information to support the SRO and PRO in performing their MEL-related responsibilities:
- Implementing partners – undertake their own MEL to support results management and ensure that evidence and learning guide project decision making, in line with guidance established by the GGF (based on PrOF requirements)
- Staff at Post (where relevant supported by policy teams) - monitor the implementation of projects on the ground, lead on GGF components of country ToCs and relevant KPIs, report against relevant indicators in the GGF results framework.
- Programme Advisory and Results Group in London (with Monitoring and Evaluation Advisory capacity) – support the SRO and PRO by advising on the overall GGF MEL approach, the GGF ToC and programme results framework, as well as MEL arrangements with implementing partners.
- Independent Regional MEL provider for EECAD – will, once in place, support selected MEL functions focussing on the assessment/verification of outcome level change, generation of (evaluative) evidence, and the capturing of key lessons around implementation, bringing in innovative M&E approaches.

Exact MEL arrangements vary according to delivery strand. For the development partner strand, particular focus is on ensuring that projects focus on outcome level change and integrate GESI and VfM. Phase 2 of the GGF has generated further lessons around how to work within the parameters of – sometimes rigid – IFI partner monitoring and reporting systems, which is being considered in the design of new projects. In line with PrOF principles, monitoring of SSF projects will be proportionate to their value, risk profile and strategic importance. Strengthening conflict sensitive MEL will be an area of attention across the programme.

Monitoring

Programme level
The GGF programme will be monitored against its results framework which will be finalised prior to the start of the programme and updated on a six-monthly basis (at a minimum). The results framework contains adaptive elements considering that results cannot be fully defined upfront. It will be a living document that is reviewed at a minimum on an annual basis, to confirm the appropriateness of indicators, milestones and targets. Depending on resource, the EN hub could develop a project database to ensure consistency and strengthen information management.

Country portfolio level
GGF components in Country ToCs will be revisited periodically (annually at a minimum)– informed by political economy analysis, conflict and gender analysis- to review whether change processes are transpiring as expected, challenge assumptions, analyse barriers and identify new opportunities for change. This process aims to ensure an adaptive portfolio that retains relevance and avoid the risk of HMG investing in areas/projects that will not deliver desired change. Relevant stakeholders are consulted as part of this process to test and challenge thinking, including for instance implementing partners, other donors and development partners, researchers and civil society representatives. Approaches to measuring political access and influence will be trialled and -where appropriate- rolled out, building on experiences from GGF phase 2 and FCDO guidance.

Proportionate, adaptive country results frameworks will be developed to underpin the GGF Programme results framework, outlining country-specific contributions to the programme outcomes and outputs. This would involve compilation of baseline information, drawing on PEA analysis and external data sources.

Project level
Implementing partners are expected to develop separate but nested ToCs and results frameworks for each project, with results feeding into the country and ultimately programme results framework. Delivery partners will be responsible for the collection of data under each project, and for analysing and reporting this to the GGF– with progress reporting requirements set out in each funding agreement. VFM indicators should be included in the results framework. At a minimum, data must be disaggregated by gender, unless there is a specific reason why this is not possible. Dedicated GESI indicators and conflict sensitive indicators are to be included where appropriate. Wherever relevant and possible, data will be disaggregated by other relevant variables, i.e. age, income-level, disability status. GGF teams will verify the satisfactory delivery of agreed outputs through regular monitoring of project activities (e.g. attending of project activities, meetings with stakeholders), incorporating beneficiary feedback. Quarterly, strategic meetings are held with implementers with a focus on results, risk and adaptation. The GGF will encourage partners to integrate monitoring approaches that are more suited to flexible / adaptive projects, such as strategy testing and outcome mapping.

Evaluation

A detailed evidence and learning strategy will be developed prior to the start of the new programme, based on an evaluability assessment and more detailed review of evidence gaps. This strategy will inform the type of evaluation that may be undertaken (e.g. process, performance) and respond to common challenges in evaluating technical assistance programmes which include time lag (outcomes not transpiring until long after projects have ended) and attribution, influencing factors, and the complexity of reform processes, as well as integrate learning from evaluation during phase 2. Any evaluative work commissioned by HMG will be done in line with FCDO’s evaluation policy, ethics principles and will be submitted to FCDO’s independent quality assurance service (EQUALS).
[note] # Ecorys (2021). Learning from GGF Mid-Line Evaluation: Evaluation Reflections.

Programme and country portfolio level
Where possible, a formative approach to evaluation will be taken to provide feedback and learning over the lifetime of the programme to assist programme adaptation and decision-making. Evaluation questions at programme level will be guided by evidence gaps and could include:
- What incentives are most likely to stimulate meaningful government-led reform and institutional support for implementation?
- Which TA modalities are more effective/sustainable, and under which conditions?
- How and to what extent has TA programming contributed to UK political influence?

In case of relevant commonalities across countries (e.g. in terms of themes and sectors of intervention), evaluation may take a multi-country thematic perspective. Lessons from phase 2 on past country level and thematic evaluative work will be acted upon. Evaluation at this level will be led by the GGF M&E Advisor, with support of a reference group, and implemented by the external MEL provider.

Project level
Decisions around project evaluations (process or performance evaluations) will be taken in line with the abovementioned evidence and learning strategy and consider – among others – existing evidence, evaluability, and utility of findings. Project evaluations will be managed by implementing partners or co-funders, unless there is a preference to bring in the external MEL provider. When managed by an implementing partner, GGF will confirm that the partner has demonstrated the capacity to manage a robust evaluation and feed into and quality assure the draft evaluation ToRs and inception report, with support of the external MEL provider or EQUALS.

Learning
Learning involves the integration of evidence - from within GGF, HMG and the wider evidence base - to inform decision-making or programming. In addition to specific learning activities planned by implementing partners as part of their project MEL plan, learning is supported through the following mechanisms/activities:
- Commissioning of evidence synthesis products through available helpdesks to inform programming (e.g. on thematic areas of intervention, gender equality, disability inclusion).
- Governance and economic networks (run by PARG) used for the exchange of experiences, lessons, ideas and to highlight latest evidence.
- Learning sessions on specific topics (e.g. MEL, GESI, VfM)
- Annual workshop to bring brings together those working across the GGF alongside colleagues from wider programmes.
- Production of user-friendly evidence products and thematic learning pieces (based on GGF MEL, network meetings, wider evidence base)

Learning questions will be identified as part of the above-mentioned evidence and learning strategy. Draft questions are:
- What are the advantages and disadvantages of different TA delivery methods?
- How can GGF better integrate GESI across the portfolio?
- What are the most appropriate strategies for influencing IFIs?
- Which projects or elements of the TA delivery models contributed the most / the least to political access and influence?
- How can we incentivize sustainability in project design and implementation?
- How do project efficiency results compare across projects and countries?
- What is the most appropriate mechanism to monitor and report on longer term governance impacts of TA?

Budget
Programme resources are set aside for the external MEL function. Implementing partners/managing agents will set out their budgets for MEL activities during project design, to be agreed as part of funding agreement. Combined, expenditure on MEL will be around 5% of the programme budget (with a maximum of 10% in the case of highly adaptive, innovative programmes).

Annex A: GGF Eastern Neighbourhood Risk Register and Assumptions

Key:
- Likelihood – 5, almost certain; 4, likely; 3, possible; 2, unlikely; 1, rare
- Impact – 4, severe; 3, major 2, moderate; 1, minor

Risk	Impact	Gross / Likelihood	Mitigation	Impact	Net / Likelihood
External/Contextual Risks
Vested interests or other blockers prevent progress on reforms and/or there is a general decline in public demand for reform, undermining the impact of the GGF.	4	3	Political and Economic Appraisal (PEA) of context and robust M&E informs a phased and adaptive approach to technical assistance; targeting areas where political will exists and progress is demonstrated.	3	3
External political or economic shocks disrupt delivery of reform agendas.	4	3	HMG diplomatic and GGF programme builds resilience and helps countries deal with internal and external shocks. / GGF uses HMG analysis and early warning to inform strategic and adaptive programme delivery.	3	3
Covid-19 Economic impact worsening socio-economic conditions and disillusionment undermines public demand for reform.	4	3	Technical assistance complimented by ongoing advocacy and communication strategies to communicate the opportunities and benefit of reforms with a focus on building resilience.	3	3
Covid-19 Inability of government to achieve its strategic reform agenda which GGF projects are supporting due to shifting priorities.	4	3	Regular political dialogue: work in sectors with UK added value; ensure a focussed, PEA-informed and conflict sensitive approach; work in partnership with other donors where appropriate. Theories of change developed for each GGF country maintain a close monitoring of PEA of context and robust M&E to inform phased and adaptive approach to programmes and targeting areas where political will exists and progress is demonstrated.	3	2
Host Governments over ambitious reform plans raise unrealistic expectations and exacerbate instability or tensions.	4	3	HMG encourages Govt to have conflict sensitive, focused, realistic reform priorities.	3	3
Operational Programme Management / /Delivery Risks
Fund is not sufficiently strategic and too many initiatives result in limited overall impact.	3	3	Regular political dialogue: work in sectors with UK added value; ensure a focused, PEA informed and conflict sensitive approach; work in partnership with other donors where appropriate. Retain focus on long-term impact and use M&E oversight, ARs and lesson learning to develop value-added, focused portfolios whilst remaining open to new opportunities.	2	1
Engaging through multilateral dilutes UK profile and affects influencing objectives	3	4	UK profile will be maintained through more focused and strategic engagement with multilaterals and civil society implementers – in and outside of project design and at HQ level.	2	3
Weak donor coordination undermines impact	2	3	Effective engagement with other donors, including considering secondments where appropriate. Explore potential to work in partnership with other donors to improve their programme effectiveness.	2	2
Principal-agent problem results in supply-led portfolio with poor VFM.	3	3	Effective and engaged oversight and monitoring of delivery partners ensures demand-led, strategic approach.	2	1
Covid-19 pandemic reduces ability of implementing partners to deliver or oversee programmes effectively, and/or diminishes capacity or ability of beneficiary partners to absorb support.	3	3	Early and regular engagement with delivery partners to assess capability of absorption and mobility and scope out implications of Covid19. Ongoing GGF to closely monitor/assess spend and forecasting advise on flexing/adapting/halting/slowing.	3	2
There may be a limited pool of CSOs teams are able to work with due to capacity constraints	3	3	Keep programme resource under review and maintain updated on PrOF approach to proportionality. Streamline processes related to programme management, e.g. through supplier days and consistent messaging on standards.	2	2
Inadequate capacity and/or capability of staff reduces ability to provide sufficient oversight and assurance.	3	2	Plan for and recruit sufficient staff, build capability and set effective standards through adherence to Smart rules.	1	1
Inadequate capacity and/or capability of advisory staff prevents advisory unit from providing and drawing upon analysis of local context and political economy.	3	3	Plan for and recruit sufficient advisory staff and build capability. Pursue close engagement with XWH policy teams.	2	1
Insufficient monitoring and evaluation, evidence and/or oversight undermines delivery of adaptive programming.	3	2	Generate and use effective feedback, lesson learning and timely evidence to support adaptive programming. Sufficient resources to provide robust M&E.	1	1
Changes in primary stakeholders leads to diminished engagement in reform work.	3	2	Development of deep and broad delivery relationships with key government counterparts. Continued political engagement and close monitoring of overall local context.	4	2
Financial Risks
Fraud or corruption leads to misuse of UK taxpayer money	3	3	Robust financial systems; strong fiduciary controls; no use of financial aid; adequate training of staff and application of FCDO policies, including proportionate due diligence.	2	1
Insufficient oversight or management leads to resource and programme slippage	3	3	Strategic over-programming; rigorous financial profiling and variance management; engagement with partners to ensure timely delivery.	2	2
Safeguarding Risks
Covid19-Lockdown and economic crisis increasing vulnerability and exposure to abuse and exploitation concentration of power with concentration of power, limited capacity of staff and partners to identify and manage risk implications – in a context of remote programme management	3	3	Regular engagement with implementing partners to review heightened risk in light of Covid-19 - Safeguarding risk is assessed as part of due diligence assessments and raised at regular (quarterly) meetings with implementing partners in line with downstream partners risk mapping. Would recommend an additional mapping of risk across delivery chain.	2	2
Increasing awareness of poor governance and/or high public expectations of reform as a result of UK and other donor projects or diplomatic pressures leading to protests and instability.	2	2	Project delivery accompanied by clear advocacy and communications strategies around benefits and importance of reform; work with government counterparts to ensure reforms are realistic and reflect the right priorities.	2	1
Reputational Risk
UK supports reform that bear negative unintended consequences or disproportionately empowers certain groups.	3	2	Regular conflict sensitivity support/considerations in project approvals and PEAs will help programme teams track political developments and reflect on conflict sensitivity and political economies	2	2

Key assumptions underpinning the theory of change are rated according to their likelihood of holding true, based on available evidence. Assumptions are of varying levels of criticality and have not been ranked based on their significance to causal pathways in the ToC.

Assumption		Rating	Comments on evidence base
Outcome - Impact
	Sustained support and funding from other development partners in priority reform areas and in the longer-term		To be monitored based on donors’ multi-year plans/programmes
	High quality reform, representative policy agenda and more effective service delivery strengthen citizen confidence in reform-minded government; citizens do not become disillusioned with the pace of reform		Causal link supported by evidence – but assumption may not hold true due to pace of reform
	Strengthened accountable institutions that have public buy-in reduce opportunities for malign influence
	A diversified economy and increased energy efficiency can drive energy and economic independence, bolstering resilience to external malign influence
	Supported reforms have been institutionalised to ‘a point of no return’, and can withstand changes in the political context
	Economy is not further de-railed by shocks (e.g. covid, Russia energy), and countries maintain fiscal space and can devote resources to reforms and investment.		To be monitored during programme lifetime
	Increased civil society engagement on reform is constructive and keeps adequate external pressure for government reform; / Governments are responsive to pressure from civil society and private sector.		See evidence referenced in appraisal case
	Complementarities and synergies between sector/thematic reforms and other HMG programming/policy lead to broader impact (e.g. job creation)		To be monitored through country business plan
	Delivery and implementation of reforms leads to more reform through a demonstration effect: Governments experience the benefit of reform, and/or citizens identify the benefits of reform on their lives, leading to broader reform or a greater demand for reform
Output - Outcome
	Political commitment and support for targeted reforms enables implementation and institutionalisation of reform (legislation, policy etc). GGF programmes are able to adapt effectively to any changes in political context		Political commitment may waver and efforts to institutionalise reform may not always be effective. Requires close monitoring and understanding of the political context
	Continued complementarity with the work of other development partners supports effectiveness and sustainability of GGF interventions, including through leveraging and TA complementing a wider intervention		Evidence from midline evaluation and PCR demonstrates GGF’s track record in this area.
	Institutional context, staff motivation and turnover, absorption capacity and potential resource constraints (human, financial) are sufficiently managed so as not to undermine the effectiveness and sustainability of GGF capacity building interventions and support		Evidence from the midline evaluation suggests that staff turnover and resource constraints have been barriers to sustainability. MEL will provide insight whether GGF efforts to overcome sustainability challenges are effective.
	Successful support to targeted priority sectors/services, is well communicated so as to maintain momentum and serve as a catalyst for change in other sectors/ services.		To be monitored, internal and external communication will be considered for each project
	Synergies take place between GGF projects, and from coordination of GGF with other initiatives (incl. HMG)		Prioritisation will support strengthened synergies. Coordination has found to be strong
	Opportunities for scale up / scale down and replication of GGF-supported reforms acted upon		Largely within HMG control, though subject to funding
	Politically informed and flexible / adaptive technical assistance is an effective approach to achieving results		Evidence of its effectiveness is still emerging. There is growing evidence that positive results are being achieved, but the basis for attributing results is not always clear (Cox & Norrington-Davies, 2019)
	The wider political context and climate does not significantly prevent or restrict GGF-supported civil society, media and private sector activity		Our current assessment is that strengthening the demand side of reform is feasible, but will depend on political developments in each country.
	Relations and partnerships build/strengthened through GGF projects benefit UK reputation and support progress in other areas of HMG agenda		There is limited evidence on whether GGF involvement has facilitated UK strategic objectives due to challenges in differentiating GGF’s contribution
	HMG is able to influence IFIs through close collaboration with IFID and existing relationships, despite modest funding. IFID has sufficient capacity to lean in on EN issues
	HMG staff turnover does not negatively impact on relationships with implementing partners and key development actors, including as a result of effective handover		To be monitored during programme lifetime

Annex B: Risk Statement for Good Governance Fund

### DRAFT proposal of GGF Risk Appetite in line with FCDO approved Risk Appetite 4 Dec.2020:
GGF Risk App.	Strategy & Context	Policy & Programme Delivery	Public Service & Delivery Operations	People	Financial Fiduciary	Reputational	Safeguarding
	Receptive /Major	Receptive /Major	Cautious/ Moderate	Cautious/ Moderate	Cautious/ Moderate	Cautious/ Moderate	Cautious/ Moderate

### This risk appetite outlines the level of risk GGF are prepared to accept within the portfolio. The Heads of GGF EECAD and Western Balkans sets the risk appetite once approved by the Regional Boards across the portfolio and delegates responsibility for managing this risk across parts of the portfolio to specific individuals. In-common with HMG’s wider approach to programming internationally, the GGF has a Receptive/Major overall risk appetite when balanced alongside likely pay-off. The GGF is therefore willing to have large elements of the GGF Portfolio Risk containing receptive/major risks and some eager/severe risks. Whilst overall large elements of the portfolio risk may have receptive/major risks and some severe risks, this is not equitably distributed between categories of risk and/or projects within the portfolio.

(DRAFT) GGF Risk appetite per category:
### Strategy & Context: defined as risk arising from pursuing diplomatic and development objectives which are undermined by a changing context, a lack of clarity or a weak evidence base. These risks undermine our delivery and impact.

The GGF’s risk appetite for Strategy and Context risk is Receptive/ Major reflecting our acceptance of this risk in order to pursue ambitious objectives and innovate in a changing global context. This risk appetite allows the GGF to seek programming that has meaningful impact on the issues the GGF was designed to tackle; these are the areas where our help and assistance is most required.

This applies to all GGF interventions that we currently undertake that flex and adapt to the ever evolving context throughout the GGF region that currently focus on:
- Improvements to the business climate, reform of tax systems, bureaucracy reduction
- Anti-corruption measures to help improve transparency and encourage effective public financial management;
- Modernisation of key sectors such as energy and banking;
- Reform of justice systems, including policing, to strengthen the rule of law and democratic accountability; and
- Strengthening independent media and strategic communications to promote public awareness of and support for reform

We work in fragile and conflict affected situations, and also in contexts where political stability is low or where political or economic governance compromises the rights of citizens. For example, a change in government policy has the potential to halt GGF progress/impact overnight. It is therefore crucially important that the external context’s impact on the ability of GGF to operate is taken into account to allow us to invest in understanding the dynamic contexts in which we work, have stringent mitigations in place that allow us to continually adapt our strategy as they evolve.
### Policy & Programme Delivery (Partner) - risk arising from implementation of our core business of diplomacy and development, due to weaknesses in influence and engagement, programme delivery, commercial management, resourcing and/or operational support. These risks undermine our impact and influence.

The GGF’s risk appetite for Policy & Programme Delivery is Receptive/ Major reflecting our acceptance of this risk in order to drive long-term change in diverse and challenging contexts, building shared global prosperity, eradicating poverty, tackling climate change, strengthening the international rule of law and global security, and promoting free, open societies.

These risks relate to the effective delivery of the programme including the capacity and capability of our partners and the technical complexities of the programme. It is the risk that the intended benefits of the programme will not be achieved because our effort is not sufficient to bring about change.

The nature of the GGF means that we sometimes work in difficult operating environments with a limited choice of implementing partners, or where there is a narrow evidence base, or where we take an innovative approach to deliver high impact programmes. We will be flexible to accept a higher risk appetite in the contexts where these factors exist, but seek to minimise and mitigate risks during the delivery process. We use a range of delivery mechanisms, including Post Programme teams, NGOs, the private sector and multilateral agencies, to deliver in hard-to-reach or contested spaces. Delivery partners can adversely impact our reputation. Therefore, it is important that they understand our expectations of them and that we have a good understanding of the behaviours through the delivery chain. We transfer key delivery risks to our implementing partners, wherever possible, but we cannot transfer all this risk as we are ultimately accountable to ministers for the results we deliver. We are also clear on the risk to partners potentially created by their relationship with the UK.

Public Service Delivery and Operations – risk arising from weaknesses in the delivery of consular services or the delivery of internal operations which support our core business and wider HMG, including security, legal, technology and information and property risks, impacting delivery, our people and British citizens.

The GGF’s risk appetite for Public Service Delivery and Operation is Cautious/Moderate.

This risk appetite allows the GGF to seek programming that has a meaningful impact on the issues GGF tackles and acknowledge the difficulties within the contexts we work, whilst expecting greater reporting within risk registers of identified risks compared to Strategy & Context and Political & Delivery risks. We strive to ensure the highest possible professional competence, experience and appropriate level of resource in managing our programmes and funds whilst understanding that for many programming areas finding adequately skilled implementing partners is difficult.

Operational risks relate to our capacity to oversee implementation of a programme of work, ensuring we operate to the highest level of professional competence and have the appropriate resource capacity and capability in teams. It also relates to our duty of care towards our staff. Risks and challenges include:
- Capacity - ensuring there are sufficient numbers of staff to deliver the programme or team objectives
- Experience - dealing with complex relationships and implementation challenges
- Capability - making sure staff have the appropriate skills to contribute effectively to the team
- Succession planning and working patterns to ensure sufficient continuity in programme oversight and management
- Duty of care – taking all appropriate measures to ensure staff are not placed in harm’s way and are mindful of their operating environment.
### Financial / Fiduciary - risk arising from our funds being used for unintended purposes or not managed in accordance with requirements and constraints, or poor management of assets/liabilities, resulting in weak value for money, compliance and delivery failures and reputational damage.

The GGF has a Cautious/Moderate risk appetite for Finance/ Fiduciary risks. We manage these risks robustly and require those entrusted with our resources within our delivery chains to do so too. We will not tolerate UK taxpayer money being mishandled, misappropriated or otherwise spent beyond the pre-agreed scope of our programmes. We take a zero tolerance approach to fraud and corruption and report all suspicions to the relevant departmental counter fraud service (FCDO). We realise, however, that we have chosen to operate in a context where there are generally very high levels of fiduciary risk and we cannot eliminate these risks entirely. Consequently, we design, deliver and monitor our programmes using a full range of tools, including third-party monitoring and the latest digital technology, to mitigate our exposure to fiduciary risk.

Our approach to managing fiduciary risk has been set out in the GGF 5 Year Business Case:
- No financial aid will be used; no payments will be made to government institutions. Payments to delivery partners will only be made after submission and review of project and financial reporting,
- Where possible, funding is to be channelled through trusted partners with an established track record of delivery and where there is evidence of sufficient financial management and oversight capabilities. Funding agreements will specify a requirement to have robust fraud and fiduciary risk management policies and procedures in place, consistent with DFID standards.
- Where we are less familiar with partners’ financial systems and procedures in country, we will conduct local level due diligence assessments before any agreement to fund is finalised, and will monitor closely any actions arising from these assessments. Funding will not be disbursed if we have concerns about an organisation’s track record.
- We will use political economy analysis and lessons learnt from past programming to understand incentives and risks in working with government agencies and anti-corruption institutions and particularly in relation to any work around privatisation and restructuring of state owned enterprises, to avoid elite capture and misuse of aid resources.
### Reputational - risk arising from political or adverse events, including delivery failures and ethical violations, damaging FCDO’s and/or the UK’s reputation.

The GGF has a Cautious/Moderate risk appetite for Reputational risks reflecting our limited acceptance of the reputational risk necessary to pursue our national interest overseas with public resources.

The UK government, like many others, is concerned about managing public expectations through improved service delivery and project management. The behaviour and actions of our partners (and downstream partners) or poor project management, the misuse of funds, major programme failure, or other issues regarding the successful delivery of programmes, can all risk damaging our credibility in the eyes of both parliament and the public. This then is one of the most potentially damaging risks facing us and we ensure to implement stringent mitigations to contain this risk and act early in escalating this risk for attention and action accordingly.

People - risk arising from weaknesses in leadership and engagement, culture and behaviours and/or workforce capacity and capability, impacting on performance.

The GGF has a Cautious/Moderate risk appetite for People risk in line with FCDO’s risk appetite for People. It is in reflection of our limited acceptance of risk in order to build a high-performing, common culture with diversity and inclusion at its heart across our global network, during a period of high pressure from COVID-19 and the transformation process.

This includes risks to:
- Workforce capacity and capability across our global network. Our staff are the organisation’s most important asset. We strive to ensure the highest possible professional competence and appropriate resource to manage our diverse areas of work. We reprioritise effectively when resources are constrained.
- Staff engagement and well-being. We invest in good management to empower and support staff and maintain balanced workloads. We show zero tolerance for bullying, harassment and discrimination. We maintain openness and transparency with staff to enable trusting relationships.

We strive to ensure the highest possible professional competence, experience and appropriate level of resource in managing our programmes and funds

Safeguarding - risk arising from failure to establish and maintain strong safeguards to prevent harm to beneficiaries of our programmes, staff and those implementing our programmes, the communities where we work, or the environment, resulting in ethical violations and reputational damage.

The GGF has a Cautious/Moderate risk appetite for Safeguarding risks. The GGF operates some projects in areas where safeguarding could be at risk especially in-light of the socio-economical impacts felt by the covid-19 pandemic.

We understand that the principles of safeguarding are to “Avoid doing harm by ensuring that our interventions do not sustain unequal power relations, reinforce social exclusion and predatory institutions, exacerbate conflict, contribute to human rights risks, and/or create or exacerbate resource scarcity, climate change and/or environmental damage, and/or increasing communities’ vulnerabilities to shocks and trends. Ensure our interventions do not displace/undermine local capacity or impose long-term financial burdens on partner governments.”

We have a zero tolerance to sexual exploitation harassment, and abuse; we will do all we can to prevent it and we will act immediately upon all reports and suspicions that it has occurred. We operate within our international obligations including for human rights and for environmental conservation and protection and aim to set high ethical and moral standards. We expect our partners to follow our lead and apply robust safeguards and reporting measures, throughout their own processes.

Annex C: Sector Codes

The following sectors codes could be expected to be used:

Input Sector	Input Sector Code
11330	Vocational Training, Education
12110	Health Policy and Administrative Management
14010	Water Resources Policy and Administrative Management
15142	Local Government Administration:
15152	Legislatures and political parties
15161	Elections:
15163	Free Flow of Information:
15164	Women's Equality Organisations and Institutions:
15210	Security System Management and Reform:
15220	Civilian Peace-Building, Conflict Prevention and Resolution:
21010	Transport Policy and Administrative Management
22010	Communications Policy and Administrative Management
23010	Energy Policy and Administrative Management
24010	Financial Policy and Administrative Management
25010	Business Support Services and Institutions
31110	Agriculture Policy and Administrative Management
32130	Small and Medium-Sized Enterprises (SME): Development
33110	Trade Policy and Administrative Management
41010	Environmental Policy and Administrative Management