 Programme Completion Review

Title: Global Environment Facility (GEF) Seventh Replenishment
Final Programme Spend £ (full life): £250m (FCDO £200m, DEFRA £50m)	Review Date:	12 July 2022
Programme Code: 300057	Start Date: 1 July 2018	End Date: 30 June 2022

Summary of Programme Performance

Year	2019	2020	2021	2022
Programme Score	A	A	A	A+
Residual Risk Exposure Rating	Minor	Minor	Minor	Minor

DevTracker Link to Business Case (and any addendum):	37917779
DevTracker Links to all logframes used during programme lifetime:	52177823

A. Summary and Overview

Description of the programme and what it has achieved

The Global Environment Facility (GEF) was set up in 1991 to provide funding to developing countries to address global environmental challenges, including climate change, biodiversity loss, land degradation, marine degradation, and chemicals pollution.  The GEF provides funding in support of five major international environmental conventions, which are the Convention on Biological Diversity, United Nations Framework Convention on Climate Change, Stockholm Convention on Persistent Organic Pollutants, UN Convention to Combat Desertification, and Minamata Convention on Mercury.  The work the UK funds and catalyses through GEF underpins the UK position in the international climate, biodiversity and other environmental negotiations and agreements.  GEF funding also supports UK Government priorities including combatting the illegal wildlife trade and marine protection and contributes to the achievement of the Sustainable Development Goals (SDGs).

The GEF provides grants and other support to developing countries for projects and programmes to address global environmental problems.  The GEF works with developing countries, and a set of 18 accredited agencies (including multilateral development banks (MDBs), UN agencies and environmental NGOs), to develop and implement projects and programmes. The GEF is governed by a balanced board (GEF Council) of developed and developing country representatives; its work is co-ordinated by a Secretariat and the World Bank is Trustee.  The UK has its own constituency seat on the board, represented by FCDO.  The projects and programmes funded by the GEF are developed in accordance with a set of Programming and Policy Directions set at the start of each four-year replenishment period.

For GEF’s seventh replenish period, GEF7 (2018-2022), programming and policy intentions included continuing the piloting of a set of integrated programmes to achieve greater value for money in delivering global environmental benefits by promoting greater sectoral and thematic integration in tackling environmental degradation. On the policy side, amongst other priorities, the GEF aimed to strengthen policies on gender and fiduciary standards, and enhancing engagement with the private sector.

Over the GEF7 period, GEF has made progress, despite a significantly changed global context:

- As with other institutions GEF has had to adapt to the global Covid-19 pandemic. Over the four-year period they have done this through establishing a response task force to make recommendations for GEF’s operations; all projects now undergo a Covid screen that assesses the risks and opportunities associated with each project; and programming policies have been amended to enable projects to move forward where there are pandemic-related disruptions.
- The GEF has maintained its focus on integrated programmes, with good progress in the GEF7 period e.g. as of June 2022, while Integrated Programmes only received 22% of GEF7 finance, they were delivering 49% and 68% of the core indicators on green-house gas emissions mitigated and land restored respectively. This progress has led to an increased number and volume of finance for integrated programmes in the next replenishment period (GEF8) covering a wider range of GEF’s focal areas.
  [note] Corporate Scorecard June 2022
- The GEF has continued to deliver strongly against its results framework, despite the current context, reaching (and in a number of cases significantly exceeding) targets in 7 out of 10 results areas.
- The new policies and guidelines on gender equality and environmental and social safeguards are considered to be consistent with international good practices and perceived by stakeholders as appropriate for the GEF partnership, demonstrating good progress.
  [note] GEF partnership is used to refer to the broader group of GEF partners (countries, conventions, agencies, civil society, private sector), however, GEF Partnership is used in GEF governance documents in a more strict sense to mean the 18 GEF Partner or implementing Agencies.
- The GEF has made substantial progress in adapting its strategy and plans for engaging the private sector. A major new framework for engagement with the private sector was developed and approved over the GEF7 replenishment period. While it is too early to evaluate the outcomes of the new framework, it is positive that this strategy is now under implementation.

Major lessons learned, evidence generated and recommendations

Over the GEF7 replenishment period GEF was independently evaluated by two separate organisations.
GEF’s results for projects completed and expected results from projects started during the period were independently evaluated at the end the replenishment period by GEF’s Independent Office of Evaluation (IEO). The Overall Performance Study (OPS7) drew on 34 separate evaluations conducted over the 2018-2021 period. OPS7 also drew on the terminal evaluation reviews of 1,806 completed GEF projects and the entire GEF portfolio of 4,786 approved projects from inception through to June 15, 2021.
[note] OPS7- Exec Summary xvi

In 2017-18 Multilateral Organisation Performance Assessment Network (MOPAN) carried out a performance assessment of the GEF, which reported in June 2019. GEF also provided 6-monthly reports on performance against indicators. In summary, these evaluations and reports found that:
[note] MOPAN report

- The GEF continues to be a relevant financing mechanism of numerous conventions and multilateral environmental agreements, while advancing integrated programming on priority environmental issues and systemic transformation.
- The GEF has a strong and consistent track record in achieving good project performance with 80% of all projects achieving expected outcomes.
- The GEF is a robust and adaptable partnership, comprising environmental, development, and financial expertise, convening multistakeholder programmes and projects at multiple levels.
- The GEF is a source of predictable environmental finance, enabling the mobilisation of co-financing and project scale-up.
- Durability of projects, which has been flagged as an issue in the past, has improved over time with 63% of all projects found to have durable outcomes.
- The MOPAN review concluded overall GEF is a relevant, capably managed and effective facility. Its strategies, plans and programmes are rigorously discussed and reviewed every four years based on comprehensive evaluations by IEO.

Lessons and recommendations, particularly from the more recent IEO evaluation, provide valuable pointers for the next GEF replenishment period – GEF8 (2022-26). Key recommendations from the GEF7 period are set out below. To a large extent these have already been picked up and acted upon in the negotiations for GEF8, which concluded in April 2022:
[note] OPS7 – Exec Summary xix

- GEF should continue pursuing integration in programming but should clearly demonstrate the additionality of this approach, with clarity in roles and coordination between GEF Agencies.
- GEF should review its requirements, processes, and procedures to allow countries, Agencies, and the private sector to secure GEF resources and move to implementation and execution more quickly in the post-pandemic period.
- GEF should develop and implement a more strategic and coherent approach to engagement at the country level to better address varying country needs and capacities.
- GEF should increase its support to LDCs and SIDS to have greater impact in these priority countries.
- GEF should strengthen private sector engagement with targeted support.
- GEF should continue to pursue innovative projects to advance transformational change. Since innovation is associated with some level of risk, the GEF Council, together with the GEF Secretariat and the GEF Scientific and Technical Advisory Panel, should clearly articulate the level of acceptable risk across the various instruments and approaches for clarity across the partnership and to encourage innovation through a managed approach. The GEF could consider establishing a specific window for financing innovation with a higher risk tolerance.

How this report was conducted

This was a desk-based review against the GEF7 Business Case and logframe, drawing on documents provided biannually to the GEF Council, and independent evidence presented to the GEF Council, and GEF replenishment negotiations conducted over 2021 and 2022. A major source of evidence was the GEF’s Independent Evaluation Office’s Comprehensive Evaluation for the GEF7 period (2018-22), the Overall Performance Study (OPS7).

Actions following approval of this report

The programme will remain under “implementation” to enable all GEF7 promissory notes to be encashed.

## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	Up to £250m	Final spend £250m
Timeframe	1 July 2018 to 30 June 2022	1 July 2018 to 30 June 2022
Outcomes	Outcome statement from the logframe: / “GEF demonstrates broader adoption of approaches and systemic change in critical drivers of environmental degradation”	The conclusion on GEF performance in the OPS7 evaluation, which includes as assessment of the outcome statement was that: / “Overall, GEF projects continue to deliver strong results and maintain an improving trend in performance. However, many aspects related to the efficiency of the activity cycle were affected by the COVID-19 pandemic”.
[note] OPS7 Evaluation (see chapter 2 page 16)

Overall assessment of programme outcomes, sustainability and VfM

The outcome indicators in the UK logframe are covered by the GEF’s Independent Evaluation Office (IEO) in their comprehensive evaluation (OPS7) for the GEF7 period. . With respect to project outcomes this draws on the terminal evaluations of completed projects. With regard to performance against outcomes OPS7 has the following overall conclusion on GEF:

Over its 30-year history, the GEF has demonstrated improvements on all performance measures. Cumulatively, 80 percent of all completed GEF projects, accounting for 79 percent of GEF grants, are rated in the satisfactory range for outcomes. Since it takes time to observe outcomes, currently outcomes on GEF-5 indicators are being observed. The GEF is on track to meet the GEF-5 replenishment targets for 7 of 13 results indicators. Sustainability of outcomes has improved in recent GEF periods.
[note] Ibid xvi.

As highlighted by the above statement, the sustainability of GEF projects continues to improve. Cumulatively 63% of GEF project’s outcomes are durable with the project likely to achieve its expected long-term impact. In the OPS7 cohort of reviewed projects this figure is 65%. The progress is also clear in that up to GEF3 59 percent of approved projects outcomes are sustainable on completion in comparison to 68 percent of projects approved from GEF-4 onwards.
[note] Ibid p28.

With regards to broader adoption of approaches to tackle environmental degradation (which takes place when
non-GEF actors adopt, expand, and build on GEF funded projects) OPS7 presents a mixed picture:

Broader adoption was reported in 40 percent of the projects of the OPS7 cohort at completion, which is lower than 55 percent reported for the OPS6 cohort. Nonetheless, a higher percentage of OPS7 cohort was achieving broader adoption at a large scale as compared with the OPS6 cohort. One of the reasons for this difference is that a higher proportion of GEF projects in recent years have addressed upstream and systemic issues. This facilitates broader adoption at a large scale but at the same time involves a longer time lag before such adoption takes place.

With regards to value for money, investment in GEF remains good value for money. As highlighted above 80% of projects were rated by IEO as satisfactory. Other important elements for the UK on value for money is the leverage of funds. By June 2021, UK contributions to GEF7 had mobilised an additional £1.82bn, more than 7 times the UK investment in GEF7.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators.

The theory of change is built around the contribution the GEF makes in supporting sustainable development and reducing the detrimental impact of climate change and environmental degradation on the poor.  In summary, the assumptions made in the business case and theory of change are that an adequately resourced GEF, which is managed effectively, through delivery of high impact projects will deliver sustained global environmental benefits.  Given the poorest people and the poorest countries in the world are the most reliant on the environment for their incomes and livelihoods, delivering these global environmental benefits contributes to delivering the Sustainable Development Goals, particularly those related to the environment: SDG13 (climate action) SDG14 (life below water), SDG15 (life on land). GEF’s role in this context is to provide the leadership in demonstrating the practical actions to tackle environmental degradation.

No major changes have been made to the GEF’s theory of change or the outcome indicators over the four-year replenishment.  However, like all programmes, GEF has been affected by Covid-19.  The UK has continued to keep a close eye on this. GEF responded quickly to the Covid-19 pandemic: A Response Task Force met throughout 2020 to assess the pandemic and implications for environmental programming; In November 2020 it published a policy paper identifying future risks linked to emerging infectious diseases and outlined possible investments that could mitigate them; GEF has prioritised projects that help countries respond to urgent environmental needs, and those that enable countries to plan a green, blue, clean, and resilient recovery from the pandemic; and have amended programming policies to enable projects to move forward where there is pandemic-related disruptions.

While the Covid-19 pandemic continues to require new business practices and adaptation to more virtual interactions, the GEF partnership found ways to get back to business and continue the implementation of existing projects and engage with the proper stakeholders and country agencies to submit pipeline of projects. GEF internal procedures for project review now include a COVID-19 screen that assesses the risks and opportunities associated with each project being submitted for consideration by the GEF. Special attention is given to projects that can contribute to a resilient blue and green recovery.
## C: Detailed Output Assessment

Output Number and Title	1.Global environmental benefits to be delivered through approved GEF7 projects and programmes
Output Score	A+
Impact weighting (%)	70		Impact weighting revised since last AR?	N

Output Indicator		Starting Target	Logframe Target June 2022	Final Results	Extent target met
1.1 Terrestrial protected areas created or under improved management for conservation and sustainable use (million hectares)		0	200	116.6	Marginally missed
1.2 Marine protected areas created or under improved management for conservation and sustainable use (mha)		0	8	1390.5	Substantially exceeded.
1.3 Area of landscapes restored (mha)		0	6	8.2	Exceeded
1.4 Area of landscapes under improved practices (mha; excl. protected areas)		0	320	160.8	Significantly missed
1.5 Area of marine habitat under improved practices (mha; excl. protected areas)		0	28	105.3	Substantially exceeded.
1.6 Greenhouse gas emissions mitigated (million metric tons of CO2e)		0	1500	1542.0	Exceeded.
1.7 Number of shared water ecosystems (fresh or marine) under new or improved cooperative management		0	32	62.0	Substantially exceeded.
1.8 Globally over-exploited marine fisheries moved to more sustainable levels (thousand metric tons) (Percent of fisheries, by volume)		0	3500 (15%)	3779.9	Exceeded.
1.9 Reduction, disposal/destruction, phase out, elimination and avoidance of chemicals of global concern and their waste in the environment and in processes, materials and products (thousand metric tons of toxic chemicals reduced)		0	100	90.4	Marginally missed.
1.10 Reduction, avoidance of emissions of POPs to air from point and non-point sources (grams of toxic equivalent [gTEQ])		0	1300	2895.3	Substantially exceeded.
1.11 Number of direct beneficiaries disaggregated by gender as co-benefit of GEF investment		0	In absence of past, portfolio-level monitoring of beneficiary data, no GEF-7 target was included in the business case.	222.1 million (of which female 113.1m; of which male 109.0m).	n/a

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

The GEF7 results framework is linked to the GEF7 programming strategy through 11 agreed core indicators. Output 1 of the UK’s logframe for GEF7 uses these agreed indicators and targets. The framework allows for the comprehensive monitoring of the results expected by GEF projects and programmes, including multiple benefits across focal areas as well as tracking data on beneficiaries disaggregated by gender.

The above results for GEF7 represent good progress, with 7 out of the 10 indicators (where initial targets were set) easily exceeding and in a number of cases significantly exceeding the original targets. There are three indicators to highlight:

- The two landscape targets, 1.1 and 1.4, of terrestrial protected areas and area under improved landscape management have missed the original targets. This was carefully examined and questioned in the June 2022 GEF Council. There are two reasons behind these two slower results areas. Firstly, it is ultimately countries’ choice on where they programme their GEF resources. With partial flexibility in GEF7, countries have not prioritized projects that will deliver against these two indicators. Secondly, this highlights GEF Secretariat’s role to predict targets at the start of the replenishment period, based on previous country priorities. They acknowledge the targets set were too ambitious.
- Indicator 1.2 is a significant outlier, with results significantly exceeding the original target set for GEF7. These significant results come from one project approved during the GEF7 period for international waters, which aims to conserve a significant area of the Ocean (3.5% of it).

The above results are a significant achievement in a period where more than 50% of time for developing programmes was marked by the Covid-19 pandemic, irrespective of the pandemic, targets set at the start of a 4-year period for programming across 144 countries are never a totally exact science. However, the two significantly missed indicators have taken down the output score from substantially exceeding expectation to moderately exceeding expectation.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

The business case considered value-for-money from a 4 E’s perspective (economy, efficiency, effectiveness and equity) of most relevance to this output is the importance of effectiveness (spending wisely) i.e., ensuring the chosen outputs of an intervention are those most likely to result in the desired outcomes. The new GEF results framework of eleven core indicators, covering the five focal areas for GEF, transparently captures, monitors, aggregates and reports on results across the different types of intervention financed by GEF. This contributes to driving effectiveness in the design of projects, through choosing the activities that will deliver the outcomes and results desired. This is most relevant to Integrated Programmes, which seek to provide multiple benefits across different focal areas, significantly they deliver a higher percentage of core indicator results (e.g. 49% of green-house gas emission mitigated against only receiving 22% of GEF7 finance). In the current context of Covid-19, the good progress in programming GEF7 resources to deliver higher than expected results against target is an indication that the GEF can be seen to be delivering value-for-money against the results for this output.

Lessons learned through this output, and recommendations for future programming

A key lesson from this output over the last 4 years is the difficulty of programming across 144 countries, and five focal areas to deliver across all eleven targets set at the start of the replenishment period. There will be two significant drivers influencing how successful this approach will be over the next period:

- The full flexibility given to countries to programme allocated resources across climate change, biodiversity and land-degradation. While giving countries more flexibility, this could potentially make it harder to deliver the proposed targets for this period. In response to this a mid-term review of the full flexibility policy will take place.
- Secondly, an increasing number of integrated programmes means that these types of programmes will be responsible for a significant proportion of GEF8 targets, increasing their importance in delivering value-for-money. As a consequence, the UK as part of the GEF Council will need to carefully scrutinise the integrated programmes’ framework documents when they do come through for approval, ensuring they are delivering the results we expect.

Output Number and Title		2.GEF7 policy recommendations delivered successfully
Output Score		A
Impact weighting (%)		30	Impact weighting revised since last AR?	N

Output Indicator	Starting Target		Final Logframe Target at June 2022	Final Result Achieved
2.1 Resource allocation (System for Transparent Allocation of Resources)	Proposal for updating STAR presented to the Council, including agreed policy recommendations on GDP weighting and flexibility: / • adjustments to the minimum allocation floors / • an increase in the weight of the GDP per capita index to -0.12 / • ensuring that no more than 30% of total STAR country allocations is subject to flexibility		Review of experiences of the increase in flexibility presented to Council. / Secretariat reporting to Council on the programming of funds and expected global environmental benefits across core indicators	Target met / The Use of Flexibility within STAR document was shared at the December 2021 Council and informed the preparation of further work as part of GEF-8 Replenishment negotiations. This paper confirms that the increase in flexibility provisions across GEF phases has been accompanied by a simultaneous increase in countries’ utilisation of flexibility. It demonstrates that countries indicate both the demand for full flexibility and have the capacities to absorb it. In addition, the latest edition of the GEF-7 Scorecard continued to provide an update on the utilisation rate of funds, use of flexibility and expected global environmental benefits.
2.2 Optimising the use of GEF resources in different countries	Updated co-financing policy and associated guidelines presented to the Council, including definitions, agreed levels of ambition and monitoring and reporting (below): / • Overall GEF portfolio ambition to reach at least 7:1 Co-Financing ratio to GEF Project Financing / • For the portfolio of projects and programs approved in Upper-Middle Income Countries and High-Income Countries that are not SIDS or LDCs to reach a ratio of Investment Mobilised to GEF financing of at least 5:1		• Overall GEF portfolio to reach at least 7:1 Co-Financing ratio to GEF Project Financing / • For the portfolio of projects and programs approved in Upper-Middle Income Countries and High-Income Countries that are not SIDS or LDCs to reach a ratio of Investment Mobilised to GEF financing of at least 5:1	Target exceeded / Co-financing 8.2:1. / Investment Mobilised in Upper-middle- and High-income countries 6:1.
2.3 Results	Updated results architecture for GEF7 presented for Council consideration, addressing agreed policy recommendations		Council agreed measures on results and sustainability being implemented. / Concrete measures undertaken in the design, monitoring and evaluation of projects and programmes that would allow for increased sustainability, including financial sustainability	Target met / Continuing with the implementation of the GEF-7 Results Architecture, granular reporting at sub-indicator level took place in the Scorecard, as well as more in-depth results analysis in the 2021 Monitoring Report. There has been a significant focus by the GEF Secretariat and through discussions at the GEF Council to increase the sustainability of GEF projects. Detailed documents on sustainability, including concrete measures that can be taken to improve sustainability have been presented to the Council by the GEF Secretariat and STAP. Sustainability has also been a strong feature of IEOs OPS7 and constituent evaluations. A number of measures (integration of theories of change and multi-stakeholder processes) are increasingly being incorporated into programmes and project design.
2.4 Private sector engagement	Terms of reference for the Private Sector Advisory Group presented for Council consideration		Council agreed strategy on private sector engagement being implemented.	Target met / Following the approval of the Private Sector Engagement Strategy, the strategy has moved into implementation. The first GEF Private Sector Engagement Strategy Annual Report was shared with the GEF Council in December 2021. / As of December 2021, the private sector accounted for 18% of total indicative co-financing mobilised by GEF-7.
2.5 Operational efficiency and transparency	Proposal with additional policy measures to enhance the operational efficiency and transparency presented for Council consideration		Council agreed measures to enhance operational efficiency and transparency being implemented	Target met / The measures to enhance operational efficiency were approved in December 2018. These were implemented from March 2019. The annual GEF Monitoring Report provided a progress update on these efficiency metrics, through a new Portfolio Scorecard introduced in December 2020.
2.6 Improved management of data and information	GEF Portal operational		Continued implementation of the improved information management system, with regular reporting to IATI registry	Target met / GEF started publication to the IATI standard in 2019, with scaled up reporting from August 2021. / The GEF Secretariat have introduced a strengthened ‘Portal’ in GEF7, which tracks key information during project implementation, including progress in achieving expected results; materialised co-financing; speed in reaching project milestones, and; implementation of core GEF Policies on Gender Equality, Stakeholder Engagement and Environmental and Social Safeguards.
2.7 Gender equality and women’s empowerment	GEF-7 gender implementation strategy approved by the Council		Review of experiences of the implementation of the Strategy / Annual updates by the Secretariat on the progress on activities outlined in the Strategy, as well as on the results framework. / Percentage of projects that have conducted a gender analysis, plan to carry out gender-responsive activities and include sex-disaggregated and gender-sensitive indicators / Percentage (and number) of female beneficiaries.	Expectation met / The GEF corporate scorecard provides annual updates on the indicators covered in the GEF-7 Results Framework on Gender Equality and Women’s Empowerment: / 100% of projects that considered gender issues at the initial project design. / 91% of projects expecting to develop gender sensitive indicators. / 96% of projects tagged to close gender gaps. / 48% of the expected beneficiaries in these projects are women.
[note] Use of flexibility within STAR
[note] June 2022 Scorecard
[note] Policy Directions for GEF8.
[note] Private Sector Engagement Strategy
[note] PSES Annual Report.
[note] GEF Corporate Scorecard June 2022

As part of the Seventh Replenishment of the GEF, Trust Fund participants agreed a set of Policy Recommendations, in line with UK priorities, These form the basis for the indicators of this output and included:

System for Transparent Allocation of Resources (STAR). At the start of the GEF7 replenishment the GEF Secretariat presented a new Policy for the STAR, which introduced new focal area floor allocations, increased the weight of the GDP index, and increased flexibility. This project completion report confirms that the increase in flexibility provisions across GEF phases has been accompanied by a simultaneous increase in countries’ utilisation of flexibility. It demonstrates that countries indicate both the demand for full flexibility and have the capacities to absorb it. In summary a positive direction of travel on flexibility of resources.

Optimising the use of GEF resources in different countries with a view to mobilising greater investments to achieve global environmental benefits. This included: updating the co-financing policy; introducing the concept of “investment mobilised”; raising the level of ambition for the overall GEF portfolio to reach a co-financing ratio of 7:1; and setting out clearer requirements for Agencies and the Secretariat to document, monitor and report on co-financing and investment mobilised at the project, programme, and portfolio levels. Despite the covid-19 pandemic, when co-financing could have declined, co-financing has surpassed the replenishment level ambition of 7:1. In addition the Investment mobilised in Upper Middle Income and High-Income countries surpassed the target of 5:1. This is a significant achievement.

Results. Updated Results Architecture for GEF7 included: a simplified results framework of eleven core indicators and associated sub-indicators; agreed GEF7 targets across the core indicators; streamlined monitoring and reporting requirements; measures to enhance the availability, accessibility, quality and timeliness of data and information on results; and the capture of data on beneficiaries. Milestones under this indicator also include measures to increase the sustainability of GEF projects, including their financial sustainability. For the second year the GEF Secretariat is reporting on results at the sub-indicator level. The detailed analysis and measures to improve sustainability of projects will now be taken forward under the next replenishment cycle. This represents good progress.
[note] GEF8 Policy Recommendations.

Enhanced engagement with the private sector. The GEF7 replenishment agreed two pillars to improve GEF’s engagement with the private sector: expanded use of blended (non-grant) finance instruments; and mobilising the private sector as an agent of market transformation, through the development of a private sector engagement strategy. Following discussion at the 57th and 58th Council meetings (which resulted in recommendations for improvement), and the formation of a Working Group of interested Council Members (including the UK), the Private Sector Engagement Strategy and associated Implementation Plan, were approved at the 59th Council meeting in December 2020. The first report on implementation of the private sector engagement strategy was presented to the Council in December 2021, assessing progress against a series of metrics for GEF engagement with the private sector including: the number of companies engaged in GEF activities; a classification of companies by sector; an assessment of geographic coverage and multistakeholder platforms engaged. It reported for example that 991 private sector entities engaged GEF7 projects; and there was $833m of private sector co-financing across 204 projects. This demonstrates that the Strategy is now under implementation and moving forward.

Operational efficiency and transparency. In December 2018 the Policy Measures to Enhance Operational Efficiency, Accountability and Transparency was approved and came into effect in March 2019. These included: a new provision to address timely project preparation; the speed of implementation and Agencies’ compliance with key reporting requirements (e.g. the final 30% of agency fees tied to the submission of mid-term reviews); and the timing of financial closure (FC) of projects, to require closure within 12 months of submission of a Terminal Evaluation (TE). The Portfolio Scorecard, was launched in 2020, which provides a framework to track and push for progress against these key effectiveness and efficiency areas. The GEF Monitoring Report 2021 provided a progress update on these efficiency metrics, as highlighted above. This represents successful implementation of the GEF7 policy recommendation.
[note] Policy Measures to enhance operational efficiency.
[note] Dec 2021 Monitoring Report.

Improved management of data and information. Continuous improvements to the GEF Portal and GEF data governance have been instrumental in arranging reporting to the IATI registry on a regular basis. Since the first publication to the IATI standard in 2019, the GEF Secretariat has scaled up and organised publications across the portfolio of GEF-funded ongoing and completed activities with regular reporting starting in August 2021.

Strong systems and data governance overhauled in GEF-7 underpin programming, portfolio and results monitoring analysis through the GEF Portal. Over the past few years, Portal improvements have transformed the Secretariat’s ability to inform the GEF Partnership on implementation progress and challenges. The Secretariat is working to implement systemised reporting to IATI registry on a regular basis.

Practical approaches to gender mainstreaming and capacity development. Since the Policy became effective in July 2018, the GEF’s improved standards and increased ambition on gender equality has been translated into practice across GEF-7 portfolio. Projects are now better designed with gender sensitive stakeholder consultations and informed by gender analyses. Most projects incorporate gender-responsive measures to address critical gender gaps and include gender sensitive indicators to monitor progress and results over time. There has been good progress on gender mainstreaming in GEF.

In summary for Output 2, across the 7 areas of policy there has been consistently good progress, meeting the expectations set at the start of the GEF7 period. In light of this, this output is scored as an A.

VfM of this output compared to the proposition in the Business Case, based on performance over the past year

The business case included consideration of ‘equity’ or how benefits are distributed amongst the population and emphasised that equity was particularly important in delivering FCDO’s commitment to ‘leave no one behind’. GEF’s new “Policy on Gender Equality” (and the gender implementation strategy) requires gender analysis as part of project design, and improvements on monitoring and reporting in GEF financed projects. This is an important commitment by GEF to leave no one behind. Indicator 2.7 of this output (articulated above) directly relates to that policy and demonstrates GEF’s continuing commitment to monitor and deliver against this aspect of equity.
[note] GEF Gender Equality Policy - 2017
[note] GEF_Gender_Implementation_Strategy_1.

Lessons learned through this output, and recommendations for future programming

Good progress has been made through the close monitoring of the policy recommendations agreed as part of the GEF7 replenishment negotiations. A new set of policy recommendations have been agreed as part of the next replenishment cycle (GEF8), where equally close monitoring and follow-up through the GEF Council will be appropriate. From the above recommendations the following will warrant monitoring:

- While good progress has been made on the private sector engagement strategy, the assessment by the IEO of GEF’s Private Sector work in OPS7 demonstrates this is an area for further close monitoring and engagement by the Council.
- With good progress on the gender implementation strategy, GEF8 will build on the progress made on gender to undertake a gap analysis of any other potentially marginalised groups, including those with disability.
- The good progress allowing countries flexibility of using their resources under GEF8 will now allow full flexibility of resources. However, this will require close monitoring to ensure this doesn’t significantly impact the GEF’s ability to deliver results in any particular sector.

D: Risk

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.

The overall risk category of ‘minor’ has been maintained in the last year.

The programme’s risk register for GEF based on the Business Case risk assessment, which is aligned with the FCDO risk management policy and framework, has been maintained and updated throughout the GEF7 period.

The Due Diligence and the new Enhanced Due Diligence on Safeguarding, were both completed in January 2020. These indicated that the controls in effect were sufficient to monitor and respond to GEF risks as needed. These controls apply to all GEF’s implementing agencies, including: Minimum Fiduciary Standards for GEF Implementing and Executing Agencies; Minimum Fiduciary Standards on Issues Related to Anti-Money Laundering and Combating the Financing of Terrorism, and; an updated Policy on Environmental and Social Safeguards.

The UK has actively engaged with the GEF Secretariat and at Council meetings, and closely monitored a number of risks. These include:

- Ensuring a robust response to the Independent Audit UNDP undertook on its GEF portfolio published audit in November 2020. Follow-up action and reporting to the Council is ongoing, including monthly updates on matters relating to this process to the GEF Council.
  [note] Council update on review of UNDP.
- Developing a portfolio wide approach to risk and risk appetite. The UK has engaging the GEF Secretariat directly and raised this in GEF Council meetings. In the June 2022 Council meeting Scientific and Technical Advisory Panel (STAP) presented a paper on Risk Appetite, with a corresponding decision that the Secretariat would produce a paper on GEF’s risk appetite for the 64th Council meeting.
  [note] STAP Risk Appetite paper.
- Monitoring the risks to implementation in light of the Covid-19 pandemic. All project reviews include a Covid-19 screening that assesses the risks and opportunities associated with each project being submitted for consideration by the GEF. Special attention is given to projects that can contribute to a resilient blue and green recovery. To mitigate implementation risks many forms of adaptative practice are maintained in project preparation. These include: some form of virtual engagement for the stakeholder engagement processes; the use of local technical expertise has become more prevalent due to the difficulty of travel of consultants; and more reliance on local government entities that are closer to the project areas.
- In relation to safeguarding, per the December 2109 GEF Policy on Environmental and Social safeguards&, the GEF continues to rely on its Agencies’ Environmental and Social Safeguards policies and procedures to supervise, monitor and report the implementation of Environmental and Social Safeguards management plans or equivalents. The GEF Secretariat is in close communication with its Agencies regarding updates on GEF projects under implementation and continued adherence to GEF environmental and social safeguards.
  [note] Progress report on agencies compliance with minimum standards
  [note] GEF’S Policy on Environmental and Social Safeguards

E: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency.

The GEF’s ‘partners’ include both recipient countries and the implementing agencies. The performance of these partners is covered under the results reported under output 1 and 2 above. The UK, represented by the FCDO, has been a member and major contributor to GEF since its inception in 1991. FCDO works closely with other UK Government Departments who lead on some aspects of policies delivered by GEF, most notably DEFRA, but also BEIS and currently the COP26 Unit in Cabinet office.

The UK is a permanent member of the GEF Council, which functions as an independent board of directors, with primary responsibility for commissioning, approving, and evaluating GEF programmes. The UK has influence over policy priorities and level of ambition through the replenishment process, and in driving monitoring of operational effectiveness and efficiency through the Council. The experience of the UK team has enabled development and application of innovation and improvements in implementation, as indicated by the proportion of UK policy proposals adopted through successive replenishment negotiations and the increase in GEF resource allocation to UK priorities, such as integrated programming, and increased engagement with the private sector.

The business case considered a number of economy and efficiency measures as part of the value for money assessment: Office costs, cost of travel, consultants (economy), and upgrading GEF IT systems for more efficient streamlining of quality assurance and transaction processing. The last 2 ½ years of this GEF7 period (2018-22) have been extraordinarily impacted by Covid-19. While some intended efficiency measures have been addressed, for example the introduction of a ‘portal’ to enable real-time reporting and geo-location information, the pandemic has had a significant impact on Secretariat costs: This has resulted in significant (but unintended) savings on travel costs – due to restrictions in travel, the halting of in-person meetings throughout the period of the pandemic and in particular the whole of the negotiations for the next replenishment period (GEF8 2022-2026) being conducted virtually. In the final budget within the GEF7 period, there is an increase in some costs, both to meet the needs of some activities that could not be conducted during the pandemic, but also to kick-start the implementation of the next replenishment, GEF8, which is significantly larger (30% increase) than for GEF7. Despite both savings and expected increases in the final year of the four-year budgeting cycle, the Secretariat costs fall well within the overall four-year administrative budget envelope developed for the GEF7 period – see details in the table below.
[note] Final year budget for GEF7 period.

Agreed GEF7 budget/$m	FY 2020 / Actuals	FY 2021 / Actuals	FY 2022 / Estimates	FY 2023 / Estimates	7th GEF Assembly	GEF7 projected total	Savings
103.5	22.388	21.524	23.120	26.990	1.700	95.722	7.778

Programme-level approach to monitoring and evaluation

The GEF has distinct monitoring and evaluation policies, which were updated and agreed during the GEF7 period. These policies set out monitoring and evaluation from a project and programme level i.e. requirements on setting out expected results, providing mid-term reviews and project terminal evaluations, up to the portfolio level for review by the GEF Council.
[note] Monitoring policy
[note] Evaluation Policy

At the portfolio level, the GEF Council received a series of reports over the 4 year period, including a bi-annual corporate scorecard (setting out progress against core indicators), an annual monitoring report (setting out progress in implementation of the programme directions for the period), an annual performance report by GEF’s Independent Evaluation Office (IEO - based on completed projects), a series of evaluations by IEO - 34 over the GEF7 period, and finally, a comprehensive evaluation over the 4 year period – the Overall Performance Study (OPS) to assess performance over the whole period and draw together the findings from the other evaluations conducted. The evaluations by the IEO draw on a wide range of sources, including literature and document reviews, desk studies, field visits and verifications, interviews, surveys, portfolio analyses, and stakeholder consultations. The comprehensive evaluation for the GEF7 period - OPS7 – was published in January 2022, it together with the above reports have been a major source of evidence for this PCR.
[note] ops7-0

GEF’s Independent Evaluation Office was considered ‘highly satisfactory’ by the MOPAN evaluation and conducting evaluations in line with the international community’s evaluation standards. And in the 3rd professional peer review of IEO, it considered IEO had high credibility in the international evaluation community.
[note] 3rd peer review of IEO

Date of last narrative financial report	30/11/21	Date of last audited annual statement	31/10/21