## Annual Review

Title: Climate Smart Jobs Immediate COVID Response (Output 1)
Programme Value £ (full life): £2,500,000		Review date: December 22
Programme Code: 301227	AMP start date: 13 Oct 20	AMP end date: 31 December 22

Summary of Programme Performance
Year	2021	2022
Overall Output Score	C	B
Risk Rating	Moderate	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/57718025.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/60160711.xlsx

A. SUMMARY AND OVERVIEW

Description of programme
This is the second annual review of the £3 million ‘Uganda - Climate Smart Jobs: Immediate COVID Response’ Programme (“The programme”). This was designed as a response package to support the Ugandan Government’s efforts to shield viable firms and supply chains in Uganda from the economic shock of the COVID-19 pandemic. The targeted outputs were to pave the way for larger interventions, notably a $120 million World Bank IDA-funded liquidity facility aimed at providing financing to the private sector and the Ugandan Government’s own economic stimulus package.

The original programme had three components:
1. Output 1: Support the set-up of the World Bank Liquidity Facility (£2.5m), including the establishment of a project management unit to manage the facility; due diligence on participating financial institutions, as well as potential beneficiary firms. It also included support for establishing operation manuals and systems; social and environmental safeguards; monitoring and evaluation systems; and grants to cover administrative fees for micro and small to medium enterprises to access finance through the facility.
2. Output 2 [COMPLETED]: Support to Ministry of Finance Covid Economic Response Unit (£0.2m). Building on work started under the Manufacturing Africa programme, this funded additional technical assistance (TA) to assist the Ugandan Ministry of Finance Planning and Economic Development (MoFPED) Economic Response Unit (ERU) and relevant agencies in the design, delivery and monitoring of the Ugandan Government’s COVID-19 economic stimulus package, including credit facilities of the Uganda Development Bank.
3. Output 3 [COMPLETED]: Commercial feasibility study for strategic supply chains in the agro-processing sector (£0.3m), with a focus on the commercial investment opportunities in the processing and export of grains, cassava, tea and fruits. This was to facilitate a potential £120 million investment in post-harvest storage facilities.

Summary supporting narrative for the overall score

Outputs 2 and 3 were completed at the time of the last Annual Review, therefore this Annual Review is solely focused on Output 1. The overall score for the programme (Output 1) in this annual review is B. The programme was stalled at the time of the last review and was given 3 months to reach approval from the Government of Uganda (GoU) to start. This agreement was reached in December 2021 and this year has seen substantial progress in the Bank executed elements of the programme. Delays to approval of the IDA loan though have still resulted slower progress than expected. The IDA loan is now with Cabinet and expected to begin implementation in March 2023. Therefore, the programme has not met expectations but is being recommended for an extension by a further 6 months to allow for the delivery of the programme as outlined in the business case. This will offer the FCDO the best value for money and ensure the expected results are delivered.

In its last annual review (August 2021) the overall programme (covering the three components) scored a C. The reason for this was the ongoing delays linked to Output 1 which carried the major weighting (70%).

Summary of lessons and recommendations from this review

1. FCDO should allow a final extension of the programme until June 2023. This will allow all the preparatory activities to be completed (where UK funding has been committed). Action: Programme Responsible Officer (PRO); December 22.
2. FCDO should continue to support the World Bank in their push to get the IDA programme approved by Cabinet and Parliament.
Action: Team Leader; December 22.
The Lead Adviser seconded to the Bank should continue to play a key role in communicating FCDO’s views to the Bank and ensuring the MDTF remains relevant to UK priorities in terms of economic response to Covid and subsequent economic uncertainty.
Action: Lead Adviser; January – June 23.
The programme has now had two successive not meeting expectations reviews and should go onto a Performance Improvement Plan with close monitoring by the Programme Responsible Officer, Senior Responsible Officer alongside the lead adviser. This should include monthly meetings to track progress against the agreed workplan.
Action: PRO; Monthly
The programme should be extended to June 2023 to ensure that the FCDO finances invested to date deliver the VfM as outlined in the business case.
Action: PRO submission to Development Director; Dec 22
Lesson: The World Bank’s initial planning and timelines were unrealistic. Such timelines should be challenged robustly in any future programmes with decisions based on the data of how long World Bank programmes take on average from conception in Uganda to implementation.

All recommendations from the last review were completed.

The Lead Adviser undertook a review of Output 1 in October 2021 and recommended to continue with the programme but extend it to December 2022. A series of political-economy factors had continued to delay the World Bank securing final approval for the new IDA programme to which the MDTF - which the UK is supporting – was linked.

At a political level, the British High Commissioner - in consultation with the World Bank Country Manager - played an active role in lobbying the Government, especially the Permanent Secretary Ministry of Finance, to address the reasons for the delays.

The FCDO agreed a way-forward with the World Bank in terms of giving the GoU a fixed timescale for approval of the IDA programme and the related Grant Agreement for the Multi Donor Trust Fund (MDTF) which included the Liquidity Facility. If there was no progress on GoU approval by the end of October 2021, then the FCDO would look to withdraw its funding from the MDTF. The danger of FCDO funds being pulled was communicated to the Minister of Finance.

In December 2021 final approval was finally secured between the Bank and GoU and on 20 December 2021 the World Bank Board approved the new IDA programme.

The Lead Adviser ensured that environmental factors were firmly embedded in the criteria for selection of firms. The implementing agency – the Private Sector Foundation of Uganda (PFSU) – drafted a new operational manual which set out the social-environmental criteria for selection of beneficiary firms and the Bank of Uganda – the key partner in Government – agreed to a plan to strengthen the capacity of its own social-environmental safeguards unit.

The log-frame for output 1 was revised in May 2022 to include more immediate inputs and intermediate outputs funded under the MDTF programme. The original log-frame relied heavily on the theory of change of the World Bank Facility which resulted in it overvaluing outputs that are being delivered outside the purview of this programme, whilst not fully capturing the inputs that are funded through it. This made it difficult for the programme team and any external parties to get a good sense of the work that is being delivered and whether expected outputs are on track.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The World Bank Liquidity Facility (in so far that it will be enabled through the activities funded under this programme) is expected to lower loan repayments and greater capital availability in affected sectors. This in turn is expected to lead to systemic change in terms of fewer bankruptcies and better financial sector stability and higher investment levels in affected sectors. Despite the delays, there is compelling evidence of the need still for this kind of liquidity provision within the enterprise sector in Uganda. Only around 50% of SMEs are operating at pre-Covid rates of capacity and the return to basic on-farm employment during the pandemic (a reverse urban-rural migration) has meant recovery in some SME sub-sectors has been sluggish two years on. The impact of covid alongside Ebola and the Ukraine war supply side shock means the programme will deliver the results as outlined in the business case despite the delay.

Figure 1 Theory of Change

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Under output 1, there had been limited progress during the period of the last annual review due to delays in discussions with the GoU on the approval of the larger IDA operation which was linked to the MDTF Liquidity Facility. There were concerns that the Liquidity Facility might not commence if delays in the GoU side continued.

However, the Ministry of Finance approved the IDA programme in December 2021 and the subsequent approval of the MDTF Grant Agreement in March 2022 meant the important pre-cursory activities, funded under the MDTF, commenced. The Project Management Unit (under the PFSU) is now staffed; operational manuals drafted (including modus operandi for selection of firms); a new web-platform launched to process applicant-firms’ bids; and financial intermediaries identified with training to commence in the coming months.

In the next 6 months (up to June 2023), feasibility studies for industrial parks will be undertaken; a range of Covid response credit instruments and business support-services to export-sector firms will be designed and piloted; and procurement of equipment for the Project Management Unit will be completed by the PSFU.

Justify whether the Programme should continue, based on its own merits and in the context of the wider portfolio

Despite the delays, the development case for the Liquidity Facility remains sound. The effects of the COVID crisis and ebola on SMEs and other parts of the economy are still felt and there is a need for targeted liquidity support that can reach productive value chains. In parallel, an effective and sustainable economic recovery to COVID-19 will depend on investments that develop and revitalise supply-chains in high potential sectors, including in the agro-processing sector.

## C. DETAILED OUTPUT SCORING

Output Title	Increased access to finance / liquidity for firms during and in aftermath of COVID crisis.
Output number:		1	Output Score:	B
Impact weighting (%):		100	Weighting revised since last AR?	Yes (from 70% to 100%)

Indicator(s)	Milestone(s)	Progress
1.1 Liquidity Facility successfully set up providing greater liquidity / financial support to firms, including increased level of support for women-led enterprises.	All operational manuals drawn up and necessary training completed.	Achieved: The web platform is completed and launched to Ugandan business community in December 2022. Implementation manuals for the planned credit guarantee windows have been completed. Training materials developed; training courses for implementing agency (PFSU) commenced.
1.2 New framework for extension of banks and financial institutions' services to SMEs and micro-enterprises sector in place following COVID crisis.	Participating banks/ financial institutions trained up and first tranche of loan restructures selected in liaison with Bank of Uganda.	Partially achieved: The first tranche of beneficiary firms has not yet been identified but financial institutions have been selected with due diligence undertaken. The Bank of Uganda is now overseeing the participating banks / financial institutions.

Briefly describe the output’s activities, and provide supporting narrative for the score

This output has set up and will go forward in the next 6 months (after a further extension to June 2023) to pilot an approach to protecting viable private sector firms and supply chains in Uganda from the current decline in both domestic and external demand. It will directly provide liquidity to manufacturing and export-led firms, and to those firms engaged in delivering strategic public investment projects. Once these systems are set up and tested, they will be used at scale by the World Bank. This will be through the $120m IDA finance due to come onstream by the 2nd quarter of 2023, if Cabinet approves the loan as expected in the next few weeks.

There have been chronic delays due to a series of factors: a second Covid lockdown in the second part of 2021; a gap in leadership in the Ministry of Finance; and inter-departmental disagreements within Government. Progress started in December 2021 (during this review period) when the IDA programme was agreed at a technical level with the GoU and the MDTF Grant Agreement was signed in March 2022. In light of this progress a 7-month no cost extension was approved from March – December 2022.

During the review period, the Bank has successfully delivered on its bank-executed elements of the MDTF including the scoping and piloting of new financial instruments for micro, small and medium sized enterprises (MSMEs) and the formal launch of the web-platform and communications strategy. The web platform is crucial to the Liquidity Facility as it will be the means by which applicant firms will submit their bids and financial flows will be monitored. The financial institutions that will be receiving bids and screening potential beneficiaries of the Liquidity Facility have been selected and due diligence has been undertaken.

In terms of recipient-executed activities by the Government, the Project Management Unit for the Liquidity Facility and web platform has been set up in the PFSU and six proposed sites for industrial parks have been selected for feasibility-studies with ToRs finalised with the Uganda Investment Authority and Uganda Free Zones Authority.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year.

Delays mean that VfM has not yet be shown, but money has not been wasted, it simply hasn’t been spent at the pace originally expected due to delays. The VfM arguments related to delivering this output as part of a World Bank MDTF remain as set out in the business case. Whilst Covid has passed, many parts of the business sector are still vulnerable. A survey by Ugandan Federation of Small and Medium-Sized Enterprises (SMEs) showed that some 64% of SMEs in Uganda are still operating at less than 50% capacity compared to pre-Covid levels. Liquidity pressures and loss of markets are cited as the main constraining factors. Ebola and Ukraine war supply side shock have maintained the need beyond the initial covid crisis.

The UK investment will still maximise the results and impact of the much larger loan and enabling fast paced delivery. New funding to the MDTF which is due from Sweden means that the UK funds will be significantly supplemented during the second part of 2023 again ensuring that UK funding has been catalytic within the financial sector.

Recommendations / Lessons from this Annual Review.

1. FCDO should allow a final extension of the programme until June 2023. This will allow all the preparatory activities to be completed (- where UK funding has been committed). Action: PRO; December 22.
2. FCDO should continue to support the World Bank in their push to get the IDA programme approved by Cabinet and Parliament.
Action: Team Leader; December 22.
The Lead Adviser seconded to the Bank should continue to play a key role in communicating FCDO’s views to the Bank and ensuring the MDTF remains relevant to UK priorities in terms of economic response to Covid and subsequent economic uncertainty.
Action: Lead Adviser; January – June 23.
The programme has now had two successive not meeting expectations reviews and should go onto a Performance Improvement Plan with close monitoring by the Programme Responsible Officer, Senior Responsible Officer alongside the lead adviser. This should include monthly meetings to track progress against the agreed workplan.
Action: PRO; Monthly
The programme should be extended to June 2023 to ensure that the FCDO finances invested to date deliver the VfM as outlined in the business case.
Action: PRO submission to Development Director; Dec 22
Lesson: The World Bank’s initial planning and timelines were unrealistic. Such timelines should be challenged robustly in any future programmes with decisions based on the data of how long World Bank programmes take on average from conception in Uganda to implementation.

D: RISK

Overview of risk management

The overall programme risk remains as moderate. The programme team has actively monitored, and escalated programme risks as they materialise, and they have been maintained within the BHC risk appetite. Output 1 has been hit by delays and therefore the delivery and challenging political environment risks have materialised.

These challenges have been discussed monthly between the programme team and have been escalated to the Development Director and High Commissioner as necessary. The politically challenging environment remains a key risk to programme implementation.

Update on Partnership Principles
The Business Case doesn’t mention the role of Partnership Principles in managing and monitoring the programme delivery. There is no funding that is channelled directly through Government systems. The major component of the programme is delivered through the World Bank which works closely with the Government of Uganda through MoFPED.

The Partnership Principles have been highly relevant to this programme. Recent analyses indicate a decreased GoU commitment to poverty reduction, rights, improved financial management and accountability. This decrease has resulted in delays in the programme and the need for significant political engagement to move the World Bank IDA programme and MDTF to approval. This engagement will be necessary to ensure the IDA programme gets final Cabinet and Parliament approval and the effective implementation.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Financial Performance
Initially, output 1 was designed for one year with a budget of £2.5 million but was extended for a further 7 months until December 2022 and now will be extended for a further 6 months (if extension is approved). The programme was funded through a single disbursement. Delays in implementation mean that the finances have not been spent at the time forecast. Currently, 72% of the budget is spent or committed by the World Bank.

Programme Delivery
The programme has been well-resourced with additional support from the Programme Funded Adviser position (Private Sector) based at the World Bank. However, the programme has faced challenges in terms of delays on the GoU side. The programme underestimated the challenge of getting the Grant Agreement and IDA programme approved by the GoU.

The Joint Advisory Committee meetings have discussed these challenges every six months and it was agreed that the donors of the MDTF – UK, Netherlands, and Sweden – should deploy their ambassadors to lobby Government. The BHC Kampala has used its political influence and diplomacy to highlight concerns about the delays to the IDA programme, with the High Commissioner raising the matter with the Minister of Finance on a number of occasions. This political engagement has moved the programme as outlined over the review period.

Value for Money

The business case noted the potential economy, efficiency, and effectiveness VfM dimension being delivered by way of the funding being directed through a World Bank administered multi-donor trust fund arrangement. Notwithstanding the delays, the development case for the World Bank Liquidity Facility remains sound. The funding has not been wasted, simply not spent at the pace expected. The need for such a facility remains.

Date of last narrative financial report	The JAC report in June 2022	Date of last audited annual statement	NA