## Annual Review

Title: Infrastructure for Climate Resilient Growth in India
Programme Value £ (full life): £25m		Review date: January 2023
Programme Code: 204794	AMP start date: 08 January 2016	AMP end date: 31 March 2024

Summary of Programme Performance
Year	2017	2018	2019	2020	2021	2022	2023
Overall Output Score	B	A+	A+	A	A	A+	B
Risk Rating	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Major

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-204794/documents
DevTracker Link to results framework:	http://iati.fcdo.gov.uk/iati_documents/58408005.xlsx

A. SUMMARY AND OVERVIEW

Description of programme

Infrastructure for Climate Resilient Growth (ICRG) is a technical assistance (TA) programme, delivered in partnership with the Ministry of Rural Development (MORD), Government of India (GOI). The programme contributes to the UK’s climate commitment under the International Climate Fund (ICF), with 100% of the budget tagged as ICF. ICRG aims to improve abilities of poor and vulnerable people to cope with climate change impacts by integrating climate information services and risk management into India’s social protection framework. It does this primarily by working with MORD and state governments to mainstream climate resilience into planning and implementation of the Mahatma Gandhi National Rural Employment Guarantee Scheme (MGNREGS). MGNREGS is one of the world’s largest social protection programmes, supporting around 100 million rural households and communities to cope with poverty and marginalisation every year.
[note] Total Number of Active Job Cards under MGNREGS

The programme is being delivered by 3 implementing partners in 6 states (Odisha, Bihar, Chhattisgarh, Madhya Pradesh, Jharkhand and Rajasthan) – UNDP India; Partnering Hope Into Action Foundation (PHIA), civil society partner strengthening community engagement; and International Institute of Environment and Development (IIED), research and innovation partner.

This Annual Review (AR) covers ICRG’s 6th year of implementation, during which the focus has been on sustaining impacts, building capacities of sub-national and local institutions on climate information systems to maximise the sustainability of benefits, and disseminating learning nationally and globally to promote uptake of ambitious adaptation action. Over the years through concerted efforts, ICRG has been successful in getting the buy-in of senior officials at MORD to take appropriate action in mainstreaming climate change across MGNREGS planning and delivery.

Summary supporting narrative for the overall score in this review

The programme has kept momentum and progressed slowly towards its intended outcome in this year, scoring a ‘B’ overall. While the priority this year was to achieve institutional adoption of climate information systems and practices across MGNREGS machinery, the programme fell short of the effort required to fully embed frameworks and tools within an existing system. This being a challenging year with uncertain and curtailed budgets, the programme focused on less resource-intensive activities in order to maintain existing partnerships with Ministry of Rural Development (MoRD), Ministry of Environment, Forest and Climate Change (MoEFCC) and state governments, in particular through (i) advocate for embedding ICRG’s good practices and tools within existing MGNREGS mechanisms by demonstrating results; (ii) improving coherence and synergies with other government schemes, programmes, development partner initiatives and local projects (iii) generating and disseminating knowledge from the programme nationally (to inform India’s Climate Action Plan) and internationally at COP27.
ICRG continued to:
- respond to prolonged economic crisis that increased overall vulnerability of poor households in the last couple of years, by focusing on community needs and improving access to safety nets to build overall resilience of poor.
- Improve climate information services and decision support systems that enhances coping capacities of poor households against climate shocks and reduces losses and damages.
- provide the necessary programmatic hook that helps deliver a coherent offer of joint leadership on adaptation and resilience, as stated in UK-India Road Map 2030.
In the reporting year the programme also strengthened its strategic partnership with international institutions such as UK led Risk Informed Early Action Partnership (REAP), Coalition for Disaster Resilient Infrastructure, World Bank, TERI, Shakti Foundation and UNDP by sharing lessons and exploring synergies in the area of early action and early warning.

Key achievements in the reporting year
With targeted and focussed interventions the programme made some significant achievements in terms of (i) policy and institutions; (ii) community-level impacts; and (iii) knowledge generation and dissemination.

Policy and Institutional Engagement
  - MGNREGS is recognised as one of the key initiatives in delivering climate adaptation locally: With support from ICRG team, MORD has brought climate change at the forefront of MGNREGS design and planning, with recognition at COP27 under India’s banner. MORD commissioned a study, with advisory support from ICRG, to estimate Soil Organic Carbon from MGNREGS work which will feed into India’s updated NDC tracker. India’s Long-term low carbon development strategy (LT LCDS), released on 14th Nov2022, also places MGNRGES as one of the key initiatives on existing adaptation actions.
  - Several government institutions/departments in Odisha, Bihar, Chhattisgarh and Madhya Pradesh have reported improved ability to integrate Climate Information Services (CIS) into design and delivery of social protection projects/schemes.
  - ICRG team Supported GoI and State departments on their flagship programme – Amrit Sarovar, by mainstreaming climate considerations in its planning and delivery.
  - Setting up a resource centre at Madhya Pradesh Council for Science and technology (MP CST) that will help scale up of Climate Resilience Information System and Planning Tool (CRISP-M) across India and sustain programme impacts beyond its timeline. The resource centre will focus on Institutionalising, Embedding and Scaling-up early action and early warning tools/mechanism. In the reporting year the tool was implemented in two districts of Raisen and Sehore in MP.
    [note] Functions of CRISP-M: (I) Climate risk informed planning of integrated natural resource management assets of MGNREGS to strengthen climate resilience; (ii) Drought concurrent monitoring and reporting system to support early action; (iii) community engagement through remote sensing-based monitoring.
  - Launch of JHAR-CRISP tool by Government of Jharkhand: customised CRISP-M tool modules for Jharkhand state based on the local context, distinct climate vulnerabilities, river basin and community profile were developed in the reporting period. The JHAR-CRISP was officially launched by Hon’ble Chief Minister Hemant Soren along with the British High Commissioner to India, Alex Ellis on 23 August 2022 at Ranchi, Jharkhand.
  - Expanded use of ICRG tools in other development programmes: (i) Supported Rajiv Gandhi Watershed Mission under the Department of Rural Development, Government of Madhya Pradesh to use CRISP-M tool for development of climate resilient asset plans for 82 milli watershed projects which are part of the Pradhan Mantri Krishi Sinchayi yojana (PMKSY); (ii) worked with National Remote Sensing Centre (NRSC) Indian Space Research Organisation (ISRO), to integrate application of CRISP-M into the new GoI Yukthdhara tool. (iii) Exploring scale-up of CRISP-M in non-ICRG states: request to scale-up CRISP-M is received from Gujarat Institute of Disaster Management (GIDM) and Tamil Nadu through support from DHCs.
    [note] Yuktadhara is a geospatial planning portal for facilitating Gram Panchayat level planning of MGNREGS activities across India using Remote Sensing and GIS-based information.

Community engagement:
- Supported 85,222 poor households with enhanced livelihood and income generation opportunities by connecting them to relief measures, avail agriculture support inputs from converging schemes in 4 states – Bihar, Odisha, Chhattisgarh and Jharkhand.
- Influenced the design of more than 2,000 MGNREGS NRM assets to improve climate resilience (that will result in flood protection, increase in net irrigated area, groundwater improvement, carbon sequestration, etc.), leveraging £4.7m in the reporting year. Approximately 370,000 people will benefit from these structures.
- Supported communities to use technology to ensure greater participation. CRISP-M tool supports a top-down and bottom-up approach to help communities make climate-smart decisions. During its implementation in 2 districts of MP, the tool was handed over to the community to engage them better in the asset planning process of MGNREGS.
- Around 216 Gram Panchayats (GPs) integrate climate resilient planning into labour budgets and the technical team influenced the Labour Budgets (LBs) of 9398 GPs to incorporate climate proofing through training and capacity building. Additionally in MP, 82 milli-watershed projects spread across 64 blocks in 36 districts used CRISP-M tool in the development of Climate resilient asset plans.
- COP 26 President - Mr Alok Sharma interacted with migrant community workers in Kapashera, Delhi- NCR region on 22 July 2022. The visit was facilitated through ICRG partners with the purpose to build general understanding on the frequency and intensity of climate change impacts in India in the last one year.

Research and Knowledge dissemination
- The programme collaborated with FCDO’s South Asia Research Hub (SARH) to carry out research on climate change, migration and vulnerability to trafficking. This research is among the first to provide an empirical and compelling evidence base on the links between climate change, migration and trafficking, and how lack of social protection to community - before, during and after migration- exposes them to the vulnerability of trafficking. The findings of the paper were acknowledged by GoI’s leading thinktank Niti Aayog who recognised the need to prioritise the human rights of the workers forced to migrate due to climate crisis. Siobhán Mullally, UN Special Rapporteur on trafficking in persons, especially women and children, quoted evidence from this paper in her report to UN General Assembly on 17 October 2022. The report was also shared with COP26 president during his visit to India which also facilitated his interactions with migrant workers.
  [note] OHCHR | A/77/170: Report of the Special Rapporteur on trafficking in persons, especially women and children. Link: https://documents-dds-ny.un.org/doc/UNDOC/GEN/N22/427/23/PDF/N2242723.pdf?OpenElement
- Collated 75 case stories from ICRG intervention blocks, in a compendium to commemorate 75th Independence year of India: 75 success stories from 4 ICRG states – Jharkhand, Odisha, Bihar and Chhattisgarh highlighting practices that have helped build climate resilience of vulnerable households through locally led adaptation practices were documented.
- Released report on - the power of ‘tech plus people’ in collective climate action: this report was launched on 20 October 2022 in an international event that saw participation from Hon’ble Minister Shri Giriraj Singh, Ministry of Rural Development, GoI and Alex Ellis, British High Commissioner to India.
- Using international platforms to showcase learning for replication and adoption: ICRG work, and lessons were presented jointly with Ministry of Rural Development at COP27, World Sustainable Development Summit – WSDS 2022. In this year, forged strategic partnership with social protection working group under Risk-informed Early Action Partnership (REAP) to help share ICRG learnings with its member countries and organisations. REAP secretariate has keenly followed progress on the implementation of CRISP-M tool and has supported learning and dissemination workshops organised under the programme.

Major lessons and recommendations for the year ahead

A key lesson in the reporting period with limited resources, is realising the importance of concerted and collaborative effort in moving towards achieving overall programme goals. The three delivery partners – UNDP, PHIA and IIED collaborated and aligned their work plans to deliver the intended outcome in 3 states (Bihar, Jharkhand and Madhya Pradesh) as opposed to spreading thin across all 6 ICRG states.

In a budget constrained scenario, the programme learned ways to be effective with limited resources and keeping its focus on sustaining impacts by advocating for systemic change within MGNRGES machinery using their own resources. While the team collectively made difficult choices and dropped key activities in the reporting period that were originally part of ICRG’s final two-year work plan it concentrated on forging partnerships with different stakeholders, building capacities of national and sub-national institutions, and using technology to strengthen community participation and access to information.

The main recommendations for the next year are as follows:
- The top priority in the last year of implementation will be to strengthen the integration of climate information services into the social protection systems by (a) scaling up the CRISP-M tool in Madhya Pradesh, Jharkhand, Bihar and Chhattisgarh, and (b) integrate CRISP-M’s climate components in MORD’s Yuktadhara (Action: FCDO, August of 2023).
- Develop and implement an exit strategy to ensure sustained impacts, e.g., through:
  - Establishing a formal mechanism to bring together different stakeholders working on climate adaption and social protection to promote learning and collaboration for greater impact. (Action: FCDO with support from MORD, Sept,2023)
  - Develop one Light house in each partner state that present good practices on locally led adaptation for cross learning/replication within India and regionally (in neighbouring countries). (Action: FCDO with all implementing partners, Aug,2023)
- Disseminating existing evidence to influence uptake, adoption of practices promoting early action and early warning in building local resilience. Engage with like-minded development partners and explore ways in which India adopt a systematic change in how it delivers adaptation for the people. (Action: FCDO with all implementing partners, throughout 2023)
- Expand CRISP-M tool to other development programmes and Leverage UK’s private sector investment in Early Warning Systems in India (including Agri-Tech, Food-Tech and Fin-Tech) that helps reduce loss and damage, improves global food security and build resilience of communities. Explore opportunities with UK’s Department on International Trade (DIT) and DHCs. (Action: FCDO, by Sept 2023)
- Consider India’s G20 Presidency objectives linked to climate and disaster risk resilience and universal access to early warning information, to build an adaptive social protection architecture globally and within India. (Action: FCDO, by June 2023)
- Engage with organisations supporting preparation of India’s National Adaptation Plan (such as World Bank, UNDP, CEEW, WRI) to use lessons from ICRG on how to build local climate resilience through social protection. (Action: FCDO, by March/April 2023)
- Explore options and new instruments to build the UK-India partnership on Adaptation and Resilience through policy dialogue, institutional arrangements and knowledge exchange that leverages opportunities created by ICRG and G20, beyond 2024. (Action: FCDO, August 2023)
- Review the programme Log-frame in the present context. (Action: FCDO, April 2023)
List of Abbreviations

Acronym	Full Form
AR	Annual Review
A&R	Adaptation and Resilience
CAMPA	Compensatory Afforestation Fund Management & Planning Authority
CIS	Climate Information System
COP	United Nations Climate Change Conference
CRW	Climate Resilient Works
CRISP-M Tool	Climate Resilience Information System and Planning Tool for Mahatma Gandhi National Rural Employment Guarantee Scheme
CSO	Civil Society Organisation
DPR	Detailed Project Report
FCDO	Foreign Commonwealth and Development Office
GIS	Geographic Information System
GOI	Government of India
GP	Gram Panchayat
ICF	International Climate Fund
ICRG	Infrastructure for Climate Resilient Growth
IIED	International Institute for Environment Development
IMD	Indian Meteorological Department
MGNREGA/S	Mahatma Gandhi National Rural Employment Guarantee Act/Scheme
MOEFCC	Ministry of Environment, Forest and Climate Change
MORD	Ministry of Rural Development
MP	Madhya Pradesh
MPCOST	MP Council for Science and Technology
NDC	Nationally Determined Contributions
NIH	National Institute of Hydrology
NIRD	National Institute of Rural Development
NRM	National Resource Management
OLM	Odisha Livelihoods Mission
P&RD	Panchayats & Rural Development Department
PHIA	Partnering Hope Into Action Foundation
SARH	South Asia Research Hub
SDG	Sustainable Development Goals
SLSC	State Level Steering Committee
TA	Technical Assistance
TERI	The Energy and Resources Institute
ToC	Theory of Change
UNDP	United National Development Programme
UP	Uttar Pradesh
WSDS	World Sustainable Development Summit

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

ICRG’s theory of change is well aligned with the principles of adaptive social protection. Evidence highlights that when anticipatory action is layered with social protection it can help address climate risks affecting the most vulnerable populations in a timely, sustainable, and cost-effective manner. Social protection plays an important role in reducing poverty and vulnerability and is more and more seen as a critical instrument in responding to climate change and reducing loss and damage caused by climatic events.
[note] Paper on social protection: 10197IIED.pdf

Social protection plays an important role in reducing poverty and vulnerability and responding to climate change, including in the following ways:
  - Routine social protection builds resilience before shocks hit through improvements in health, education, and nutrition.
  - Shock-responsive social protection supports people to better cope with climate shocks and stresses, reducing the adoption of negative coping strategies including selling of assets and removing children from school.
  - Social protection, including cash plus interventions, can help people and communities adapt livelihoods and mitigate climate change.
  - Supporting climate mitigation goals by promoting enhanced ecosystem services on which livelihood activities like Agriculture, Fishery, Forest products are dependent. India’s MGNREGS is the world’s largest public works schemes that helps in drought proofing and water resource management and evidence suggest that it contributes to India’s mitigation targets by helping in creating additional carbon sinks.
    [note] Mitigation co-benefits of carbon sequestration from MGNREGS in India | PLOS ONE
At the impact level, ICRG continued to work with MORD and State Governments to enhance climate resilience of people, environment and economy by building systems and individuals’ ability to move beyond vulnerability thresholds in the ICRG focus states. The programme aims to deliver the impact through MGNREGS existing mechanisms and resources, with improved capacities to integrate climate information services in its planning and delivery and reaching the poorest and most vulnerable people in targeted states. At the outcome level, ICRG focuses on building climate resilient assets and livelihoods promoted by MGNREGS and state led initiatives.

Based on suggestions from QAU, that randomly selected and reviewed ICRG’s 2021 annual progress, the team revised the graphical representation of theory of change (TOC), depicted above to highlight clearer links from inputs to outcomes, including clear identification of ICF indicators. However, there was no changes made to the input, output, outcome or impact statement.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme has kept momentum and progressed towards its intended outcome in this year. However, due to budget cuts and pause on payments announced for a substantial part of this year, the programme activities were reduced, slowed down and stopped in some instances. Activities that were not taken up in the reporting and pushed to next year are as follows (i) Technical and advisory support to MORD on Net Zero Villages/climate smart village (aligned with India’s Net Zero 2070 target and NDCs); (ii) Developing state modules of CRISP-M tool for Bihar and Chhattisgarh; (iii) Developing a tool to Monitor ecological co-benefits of ICRG’s adaptation actions; (iv) Piloting the drought early warning feature of CRISP-M tool in MP or Jharkhand and Design and pilot the Climate Data & Information Governance Framework in 4 districts-each of ICRG states. The programme meeting its intended objective will be dependent on the final year’s budget allocation.

In the reporting year, despite slowing down some activities, the team-maintained traction with MORD, State Departments and MOEFCC through direct advisory on creating the need to integrate climate risk into overall design and delivery of MGNREGS at all levels. This integration was primarily demonstrated to MORD and MOEFCC by implementing CRISP-M tool, introduced in October 2021, in 2 districts of Madhya Pradesh. Early results and learning of using this decision support system were shared with the Ministry and State departments and other stakeholders (e.g., REAP, CDRI, NDMA, NRSC, GEF) to influence its scale-up and replication in India and other countries.

To deliver the programme’s exit strategy the focus next year will be in terms of consolidating ICRG’s learning on using adaptive social protection principles in delivering local climate adaptation action and addressing loss and damage. Primarily through:
1. Engaging with various Departments (inhouse and external), Development Partners (including MDBs, Bilateral Agencies, etc), State Governments and National technical institutions, NITI-Aayog, and national and international think tanks.
2. Customising early warning tools and create replicable social protection models for other developing countries – collaborate with UK led AAC, REAP, CDRI and GEF to support uptake.
3. Strengthening the resource centre at MP CST to act as one stop knowledge base on Climate information system – helping in the scale up of CRISP M Tool across India:
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Adaptation & Resilience is a priority theme under the climate pillar of UK-India Road Map 2030. As the only bi-lateral partnership on adaptation with the GoI, ICRG paves way for the UK to work closely with India in accelerating adaptation action to support the most vulnerable and help to inform India’s NAP and contribute towards its international public commitment to triple adaptation finance. Good practices from ICRG were showcased under the India pavilion at COP27, with acknowledgement from the senior officials of MOEFCC for its contribution in delivery resilience locally to the most vulnerable. ICRG also aligns well with PM Modi’s LIFE Initiative and Amrit Sarovar. The programme is regularly reviewed by senior officials at MORD including the Secretary who takes personal interest in the progress made especially on scaling up CRISP-M tool and integrating it with Yuktadhara.
[note] Yuktdhara is a geospatial planning portal for facilitating Gram Panchayat level planning of MGNREGA activities across India. To represent MGNREGA assets spatially, the Yuktdhara portal will serve a repository of geo-tagged assets that have been created under several national rural development programs such as MGNREGA, Rashtriya Krishi Vikas Yojana, Integrated Watershed Management Programme, Per Drop More Crop, etc along with field photographs.

The programme also uses its influence of working with MoEFCC in showcasing India’s lead on Early Action and Early Warning in minimising losses from Climate extremes. The research and evidence generated under the programme has the potential to influence global policies around ecosystem-based approaches, locally led adaptation actions and mobilising critical domestic finance in addressing loss and damage.

Going forward, ICRG programme will continue to maximise UK’s development offer in India and support UK’s effort in becoming the partner of choice on Adaptation and Resilience for MoEFCC. ICRG in its last year of implementation will develop influencing pathways to reach opinion-formers and decision-makers to strengthen climate governance around early action, early warning to reduce climate impacts of the most vulnerable by integrating climate risk into development plans. It is recommended that the team explores options and new instruments to build on UK-India partnership on Adaptation and Resilience through policy dialogue, institutional arrangements and knowledge exchange that leverages opportunities created by ICRG and G20 beyond 2024.

## C. DETAILED OUTPUT SCORING

Output Title	Government Departments, Civil Society and community organisation with improved capacities on climate risk management; integrating climate information services and climate data governance
Output number:		1	Output Score:	B
Impact weighting (%):		30%	Weighting revised since last AR	No

Indicator(s)	Milestone(s) for this review	Progress
Governance structure created (such as climate cell, advisory committee, etc.) for planning, implementation and monitoring of climate resilient integrated planning and delivery	5	Partially Achieved / Number = 4 / Climate Change Working group was created in Jharkhand post launch of the state module. Secretary, MoRD Mr. Nagendra Nath Sinha (IAS), asked Chief Secretary, Govt of Jharkhand to set-up a formal unit to implement JHAR-CRISP. / A working group was established at NRSC to integrate CRISP-M climate information features into MORD’s GIS based tool – Yuktdhara. MORD is directly following up on its progress. / Climate Change Resource Cell (CCRC) is formed in Odisha that will oversee roll out of climate objectives demonstrated under ICRG. / Constituted 1 state level Climate Resource Cell along with 4 cells in each of the 4 Agro-climate zones in Bihar is under process.
Number of Govt officials, Community mobilisers, PRI member, trained on climate information services, climate risk management and M&E of climate impacts.	8000	Achieved / (approx. 17,000) / The team continues to focus on institutionalisation of ICRG approaches by building capacities at national state and gram panchayat levels to ensure sustained impacts. ICRG PMU at MORD provided nation-wide trainings for Yuktadhara planning portal, Amrit Sarovor and GIS based GP plans. / State-wise trainings are listed below and detailed in Annexures. / Madhya Pradesh, Jharkhand, Bihar / Capacitated 6741 community cadres (community Volunteer, PRI, front line workers) to ensure effective community participation and ownership. / 300 Government official were trained on climate information and risks; 125 officials trained on structural design of Climate resilient works; 1230 PRI members trained on Climate Resilience Planning in Bihar. / Odisha / A total of 4,350 officials and community members were trained on climate change, resilience and climate smart livelihoods. / 318 MGNREGS technical officials, line department and other government officials were trained on ICRG programme in the district level workshop. / 106 block-level officials were oriented and trained on ICRG programme in the block-level workshops. / 1198 government-level officials, PRI members, and community mobilizers were trained on CLART, labour budgeting, PRA exercise, and also on finalizing MGNREGA works for the FY 2023-24. / 2693 village institutions and their leaders were trained on drumstick cultivation and seedlings, model village planning for sustainable agriculture, sustainable water use, climate change impacts, and livelihood generation.
Number of modules and guidebooks developed, adopted and embedded for capacity building, training and awareness generation about climate responsive social protection/adaptive social protection.	15	Partially Achieved / Number = 13 / Modules and guidebook adopted / Module on GIS based planning and Community based tool on GIS planning in Hindi / Compendium on Social Protection schemes - Bihar & Jharkhand / A guidebook on "convergence opportunities under ICRG project" has been prepared and distributed to districts for the development of convergence action plans in Bihar. / Training manual on “Climate Resilience” prepared for the Odisha cadre officers being trained by Gopabandu Academy of Administration (GAA) / A concept note on Life for Environment (LiFE) was developed and shared at district level in Odisha for display at MGNREGS worksites and PIMs. / The Frequently Asked Questions (FAQ) to train the newly appointed PRIs on CC and the role of PRIs to address CC at the GP level developed and adopted in Odisha. / The Frequently Asked Questions (FAQ) for manuals to train the newly appointed PRIs on climate change, its impacts, and the role of PRIs to address climate change and also a microlearning module on "Organic agricultural systems to mitigate climate change" in Odisha. / Disaster risk management plan for the FY 2023-24 for Odisha. / Two modules on adoptive climate resilience planning for PRI and technical persons in Bihar. / One Amrit Sarovar Guideline for Climate Resilience Structure for Bihar State and ICRG’s Integrated NRM and River rejuvenation Guidebook.

Briefly describe the output’s activities and provide supporting narrative for the score.

Due to MORD’s commitment in contributing towards India’s Climate Action, the programme is able to establish institutional links at all governance levels. In addition to actively getting involved in ICRG’s implementation and scale-up of its approach across India, MORD is also looking at ways at its own capacity to contribute towards India’s climate goals. It has initiated a study (with technical support towards its framing from ICRG) on estimation of carbon off-set generated by plantation works being carried under Mahatma Gandhi National Rural Employment Guarantee Scheme to monitor the scheme contribution towards India’s NDCs and Net Zero target.

The programme puts great emphasis on creating governance structures or measures that can help plan, implement, and monitor integration of climate resilience and its impact in creating local adaptation. The team focused on creating a climate change cell embedded within the state departments with appropriate expertise that helps establish flow of climate information and funds. Additionally, all state departments are encouraged to hire or include a climate expert in other departments within rural development to ensure climate change considerations are integrated. For Example – one expert from ICRG Chhattisgarh State unit continues to be part of the Executive Committee of Compensatory Afforestation Fund Management and Planning Authority (CAMPA).

Besides creation of a formal structure, the team continued to strengthen reporting and monitoring mechanism in the joint implementation under Ministry of Rural Development and State Departments.
- Quarterly review meetings were set-up by MORD to review progress on the programme and address policy and delivery issues linked to programme objectives in the reporting period, led by Joint Secretary.
- In Odisha, the team joined state led committees to provide technical inputs for better management of climate issues.
  - Balangir district “Jal Shakti Abhiyan Committee” was formed at Zilla Parishad, ICRG team is appointed as one of the core members to discuss on climate issues.
  - In Kandhamal district, “Jal Shakti Kendra” was formed at the Zilla Parisha in which the ICRG staff is nominated as the nodal person.
- In Rajasthan, a dialogue was initiated with Principal Secretary, Department of Forest, Environment and CC on strengthening the existing Environment and CC Cell at State level.
In Jharkhand and Bihar: The team engages with the community through community meetings and household visits to create awareness on various social protection schemes, livelihoods and climate resilience. The vulnerable households are identified, and asocial map is developed in consultation with the community for ICRG intervention blocks in the two states. To build awareness on climate issues and link beneficiaries to various social protection scheme the team has undertaken capacity building of the community leaders and community volunteers.

In Odisha: The team focused on Scaling up phase I best practices across the high potential districts. The programme introduced the concept of Nature Positive (N+) economy by synergizing with Forests, Environment and Climate Change Department to work on ecosystem (forest) based adaptation strategy to climate change. By integrating climate change into Eco DRR, the programme collaborated with Kerala Institute of Local Administration (KILA) and UNEP to impart trainings to various stakeholders.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

Economy and Efficiency: The programme approach ensures value added support to MORD and State line Departments by complementing existing systems rather than creating parallel ones.
- Out of the total annual budget of INR 73,000 Crore (£7.4 bn), 95% has already been spent till Nov 2022 under MGNREGS. Around 52 million households benefited from the scheme in India in the reporting year. Besides, embedding climate considerations in MGNREGS design and promoting greater uptake of NRM structures in the Gram Panchayat Development Plans (GPDPs), the team also contributed towards climate proofing of Amrit Sarovar.
  [note] Amrit Sarovar, a flagship programme of GOI that was launched in April 2022 – with a target of 50,000 Ponds across India (75 in each district of India). These Sarovar/Ponds will boost agriculture productivity, ensure water resource management and contribute towards climate adaptation targets.
- Although the programme in the reporting year had to slow down and stop certain activities, but with limited budget it maintained its focus and concentrated its energies on establishing a Climate Information System within MGNREGS. For this, it continued the implementation of innovative CRISP-M tool in 2 districts of MP and produced some early results that were shared with Govt Agencies. This strengthened the efforts towards institutionalising ICRG approach under MGNREGS and sustaining impacts.
- The current year also saw concerted efforts in engaging with other organisations such as the World Bank, Shakti Foundation, CDRI, UNDP and REAP to leverage expertise and funds that can complement ICRG activities. Going forward the programme will attempt to liaise with these bilateral, multilaterals with the intent to explore adoption and scale up of tools, techniques and practices.
Effectiveness: Capacity building of community members, community cadres and strengthening community institutions by establishing CBOs of women members and gram sachiwalayas (village secretariats) to ensure better community participation has been taken up this year which has enabled community owned and led processes to assess and address climate risks, mitigation and adaptation. The engagement with PRI members and government officials ensures ownership from the government and also enhances the quality and sustainability of the outcomes. These trainings were organised by government which ensured value for money, as well as helping institutionalise the training need assessment and capacity building on climate risk management. The engagement and endorsement by state government has also given impetus to scaling up of climate resilient processes and actions.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no changes made to this output in this reporting year.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Collaborating with other development partners and organisation to create larger impact was a recommendation that was taken forward this year. The team explored working with other state departments to share learnings and converge resilient infrastructure planning under MGNREGS with regional micro-irrigation projects and larger watershed structures. Although, we were successful in Madhya Pradesh by working with Agriculture department and climate proofing milli-watershed projects, the same effort in Odisha had to be dropped due to limited resources. In the coming year the team plans to work with the Social Protection Cell set-up under Odisha Integrated Irrigation Project for Climate Resilient Agriculture (OIIPCRA), a connection formed last year to promote climate resilience planning at the state level of all social protection programmes/schemes.

Going forward, the focus will be to set-up a formal mechanism to help bring different stakeholders working in climate adaption, social protection areas (especially development partners) together to offer support that makes Indian economy, its people and environment more resilient to climate and disaster shocks and continue to make UK a relevant partner of choice.

Lessons learned and recommendations for the year ahead
Lessons:
- The regular review meetings at both national and sub-national level helped the programme to be on track and keep climate resilience as one of the top agendas within MORD esp. in light of budget constraints.
- The programme team will engage with MOEFCC to include Adaptive Social Protection as a critical instrument in delivering local resilience to climate change in the National Adaptation Plans.
- Since, MORD has shown keen interest to Monitor and Capture critical Impacts of NRM assets built under MGNREGS, in the coming year we will explore ways in scientifically monitoring carbon sequestration potential of drought proofing (NRM structures) activities of MGNREGS through CRISP-M tool so that it can be reported against India’s NDC progress update.
- Collaboration with other organisations and within FCDO/ HMG (SARH, DHC) proved effective in delivering ICRG’s objectives. Such collaboration can help deliver impact for programme with smaller budgets.
- Efforts towards identifying complementary activities and expertise in the region on climate resilient planning and supporting the most vulnerable resulted in enhancing the impact of ICRG programme and leveraging additional external resources to achieve the objectives.
Recommendation:
- In the next year we will use our existing partnerships with the World Bank and UNDP to influence policy shift towards adaptive, climate responsive social protection delivery architecture in common states and with national Government.
- Next year the focus will be on delivering the exit strategy that ensures the institutional structure across different levels of MGRNEGS design and delivery is able to mainstream climate objectives and delivers concrete benefits that build resilience of the poor.
Output Title	Building evidence and contributing to international research on adaptive social protection, result oriented climate resilience planning and implementation under UK-India partnership.
Output number:		2	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR	No

Indicator(s)	Milestone(s) for this review	Progress
Number of knowledge products, policy and strategy briefs, video documentaries and peer reviewed papers developed and disseminated to key stakeholders (internationally and nationally)	15	Achieved / Number = 15 / The team collated a compendium of ’75 stories of climate resilience through MGNREGS’ as part of India’s Azadi ka Amrit Mahotsav. The compendium is being reviewed by MORD to be released in a national event early next year. 2 short videos were produced for COP27. / Video, working paper, and report on the power of ‘tech plus people’ in collective climate action: How CRISP-M’s online technology and community-driven approach support inclusive climate resilience in India. / Published following working paper/compendium of case study / Social protection and informal job market reform for tackling climate migration nexus. / MGNREGS: Integrated watershed management and climate resilience. / Blogs / Briefing Paper -4 (links in the footnote) / Film/Videos developed and shared / Film based on CRISP-M Scale up in Madhya Pradesh / The interventions of Balangir District captured for the video shown at COP 27 / Odisha promotional video of the ICRG works that focusses on SDG 13.
Number of new research, evidence used to influence adaptive social protection/climate resilience - internationally in collaboration with UK bodies of excellence.	2	Partially Achieved / Number = 1 / New Research and evidence work were stopped in the reporting period to reduce programme costs. The one research that was supported using SARH’s funds is as below: / Research report on Climate change, migration and vulnerability to trafficking provided empirical and compelling evidence base on the links the nexus and how lack of social protection to community - before, during and after migration - exposes them to the vulnerability of trafficking. The research also highlighted the role of social protection in reducing losses and damages related to climate impacts. / The following two evidence papers are under development / Analysis and results from CRISP-M tool implementation in 2 districts of MP. Early results were shared with MORD and also presented at COP27. / A study to develop adaptation strategy to climate change for Kondh Tribes of Odisha is under discussion with University of East Anglia, UK.
Number of knowledge dissemination events organised internationally/nationally under UK-India partnership.	7	Achieved / Number = 8 / Knowledge sharing event at a community centre for COP26 President on the nexus between climate change migration and human trafficking. / Launch of JHAR CRISP tool by Government of Jharkhand at a national event on Chevening scholarship / Technical Workshop on climate resilient action plan for the state of Jharkhand. / Knowledge Dissemination event – Launch of ‘’The power of ‘tech plus people’ in collective climate action’’ / Presented learnings from ICRG in several side events at COP27 / WSDS-2022, BHC hosted a e-booth where knowledge products from ICRG were showcased and shared. / Several Events in Odisha and Bihar
[note] Azadi Ka Amrit Mahotsav is an initiative of the Government of India to celebrate and commemorate 75 years of progressive India and the glorious history of its people, culture and achievements.
[note] Briefing papers developed in the reporting year: How are women leaders getting better social protection for the vulnerable? https://www.iied.org/how-women-leaders-are-getting-better-social-protection-for-vulnerable A helpline that is a lifeline for migrants https://www.iied.org/helpline-lifeline-for-migrants Social protection to enhance climate resilience: what works where? https://www.iied.org/20821iied Firm foundations for child-centred climate resilience. https://www.iied.org/sites/default/files/pdfs/2022-04/20766iied.pdf
[note] https://www.youtube.com/watch?v=1Z9su_46jj4
[note] Events in Odisha and Bihar State Level Workshop on “Ecosystem based Disaster Risk Reduction and Climate Change Adaptation” organised on 21st November 2022 in collaboration with UNEP and Kerala Institute of Local Administration (KILA) A talk on “SDGs and Climate Change” delivered at Utkal University students on 27th September 2022 and on “Leadership for achieving SDGs” delivered at KIIT university on 13th August 2022 A paper on “Climate Induced Migration: patterns, causes, consequences, and implications” for the seminar organized by the IUSSP Scientific Panel on Historical Demography in collaboration with the Centre for Social Research, Guanghua School of Management, Peking University on 28th October 2022 3 District level workshops were organised in Balangir, Mayurbhanj and Kandhamal districts of Odisha to decide the Labour budget planning for the year 2023-24 2 workshops in Nalanda and Saran conducted on River rejuvenation DPR. Two workshops with District officials of Saharsa and Gopalgaj on Fusibility study finding on River revival; One Workshop on fusibility of Check dam by GIS in Nalanda; One workshop on Guideline of Amrit Sarovar

Briefly describe the output’s activities and provide supporting narrative for the score.

This year the programme disseminated its key results and learnings at various events organised through Delivery Partners, MORD/State Governments and at Global platforms (such as COP27, WSDS 2022). These events influence and contribute towards global discourse on locally led adaptation actions and Early Warning and Early Action mechanisms.

1. Knowledge sharing event at a community centre for COP26 President on the nexus between climate change migration and human trafficking: Mr Alok Sharma (now ex-President of COP26) interacted with migrant workers in a community centre at Kapashera, Delhi- NCR region on 22 July 2022. This visit was facilitated by PHIA Foundation in collaboration with Change Alliance and other local NGOs. The purpose of his visit was to meet the migrant workers who had migrated from faraway places like Jharkhand, Bihar and West Bengal state to Delhi – National Capital region to understood how their lives and livelihoods are impacted due to climate vulnerabilities.
2. Launch of JHAR CRISP tool by Government of Jharkhand: Climate Resilience Information System and Planning (CRISP-M) tool for integration of climate information in Geographic Information System (GIS) based watershed planning under MGNREGA was launched by Hon’ble Chief Minister of Jharkhand, Shri Hemant Soren and High Commissioner of UK to India Mr. Alex Ellis on 23 August 2022.
3. Technical Workshop on climate resilient action plan: A technical workshop was organised on 24 August 2022 in Ranchi with the representation of key officials from various departments, FCDO and Civil Society to discuss the implementation scope of the tool in the State. The workshop was joined by Mr NN Sinha, Secretary, Ministry of Rural Development, India, several other Principal Secretaries of the relevant departments from the Government of Jharkhand along with various space research, scientist, CSOs and department officials.
4. Knowledge Dissemination event – Release of report – ‘The power of ‘tech plus people’ in collective climate action’ developed by IIED in partnership with PHIA foundation on 20 October 2022 in an international event joined by Hon’ble Minister Shri Giriraj Singh, Ministry of Rural Development, government of India and Alex Ellis, British High Commissioner to India, government of the United Kingdom. The release was followed by a panel discussion that explored the value of ‘tech plus people’ approach in early warning, early action and climate risk management. (https://www.iied.org/power-tech-plus-people-early-warning-early-action-climate-risk-management )
5. Showcase of ICRG learnings, approach and tools at Sharm El-Sheikh, COP 27 (Nov 2022) - Emerging lessons and trends from ICRG and CRISP-M scale up in India were shared to inform locally led adaptation plans, climate information systems, early warning, and climate tech in India and beyond. The team had the opportunity to present ICRG’s work at four different events at COP 27 in India and water pavilion.
1. Delivering climate resilience through social protection India Pavilion event on 6 November 2022.
2. Role of rural women in delivering local climate action, 8th November 2022
3. Converging top down and bottom-up pathways to achieve climate resilience India Pavilion event on 10 November 2022.
4. DRR and Sustainable Cities for improve Livelihoods on 10 November 2022.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

Evidence generation is considered a key component of the programme to ensure policies linked to adaptive social protection and climate resilience are influenced at national and sub-national levels. The KPs developed during the reporting period helped improve understanding on whole-of-system approach to social protection and climate and disaster resilience. The team worked in close collaboration with National Resource Group and Research Institution Network of MoRD and fostered sustainable partnerships to help embed climate information in the existing MGNREGS planning systems.

Economy and Efficiency: The programme leveraged existing platforms such as COP27, WSDS 2022, State and National Government Events to disseminate and showcase evidence from ICRG programme. The launch of JHAR-CRISP was included in the event, that saw formal launch of the Joint Chevening Marang Gomke Overseas Scholarship 2023 (a partnership between Govt of Jharkhand and United Kingdom), implying reduced costs inputs. Other events were conducted virtually to save money and ensure participation of international experts and audience. The virtual event on Power of ‘people plus tech’ in climate action was organised jointly in partnership with REAP, MORD and IIED and promoted through their channels.

Effectiveness: At COP27, Social protection was recognised as a cost effective and essential instrument in (i) achieving Just transition to low-carbon economy; (ii) reducing loss and damage through anticipatory safety net measures and (iii) adapting to climate crisis by increasing the scale of social protection. Keeping the principles of SP in mind, ICRG continued to emphasise the need to ensure all vulnerable households get linked to a reliable social protection and a safety net measure. MGNREGS, being the largest SP scheme in India, significantly contributes to the average annual incomes of the poor households and provides an important buffer during a crisis, acting as an important mechanism to deliver climate adaptation action. ICRG continues to contribute towards global knowledge and evidence on social protection and white paper, policy brief produced under the programme significantly get cited in these discourses.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

While there was no formal change to the output, this year no new research was funded through the ICRG budget due to ODA prioritisation exercise and reduced allocations due to Ukraine humanitarian response. The emphasis however remains on result-oriented research highlighting benefits of climate resilience planning and implementation that has the potential to influence global and national policies on adaptive social protection.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Last year’s recommendation was to use global forums such as COP27 to raise the level of implementation on adaptation and resilience (A&R) and build India’s confidence in adopting ambitious domestic A&R target. India has started working on its National Adaptation Plan and has finalised its adaptation communication this year.

ICRG has helped firm up UK-India’s partnership on Early Warnings and Locally led Adaptation Actions, this was seen few times in the reporting year during joint events hosted by both countries (such as JHAR-CRISP Launch, People plus tech online event and COP27). ICRG was showcased at COP27, and its approach and tools were shared with other developing countries for replication. Scientific evidence from ICRG has already created interest within REAP, Global Environment Facility (GEF), Gujarat Institute of Disaster Management (GIDM), and the World Bank and initial discussion have been triggered in replicating CIS tools like CRISP-M in other parts and programmes within India, Asia and African countries. This has also helped build confidence of programme partners (especially MORD) to put greater effort in institutionalising approaches that show results on ground.
[note] COP27 was seen as the Adaptation and implementation COP, protecting developing countries agenda on greater support towards building resilience of the most vulnerable

Lessons learned and recommendations for the year ahead
One important lesson has been to find like-minded organisation working on similar issues is useful for enhanced impact e.g. Disseminating results through collaborating with Global institutions such as Coalition for Disaster Resilient Infrastructure (CDRI) and Risk-informed Early Action partnership can go a long way in generating interest and likelihood of adoption and replication of tools/approaches in other areas and geographies. With CDRI, the programme team will continue to explore ways to go beyond climate proofing of MGRNEGS small NRM infrastructure to regional climate resilient infrastructure planning - at a more impactful scale.
Recommendations:
- Disseminating existing evidence to influence uptake, adoption of practices promoting early action and early warning in building local resilience. Engage with like-minded development partners and explore ways in which India adopt a systematic change in how it delivers adaptation for the people. (Action: FCDO with all implementing partners, throughout 2023).
- The programme will continue to deliver on FCDO’s high level vision through its result-oriented research and knowledge dissemination, which will contribute towards:
  - establishing the UK as a partner of choice on adaptation and resilience.
  - building trust and informing GOI’s National Adaptation Plan
  - designing concrete actions and outputs that help achieve India’s climate adaptation ambition, through practical and on ground actions.
  - Forging partnership with global networks like REAP, CDRI and GCA to build better understanding of Adaptive and Anticipatory Social Protection programs.
- Encourage scaling up and replication of good practices, knowledge products from the programme, where possible, will be made available in a wider range of audio/video and text formats and in local languages. This will also ensure greater accessibility of resources developed under ICRG.
Output Title	Build Community Networks and Strengthened community participation on shock responsive social protection planning and implementation.
Output number:		3	Output Score:	B
Impact weighting (%):		30%	Weighting revised since last AR	No

Indicator(s)	Milestone(s) for this review	Progress
Number of people additionally linked to rights, entitlements, relief measures, skill Development, health care provisions (w.r.t COVID19 like vaccines) and services especially related to livelihoods / Social Protection / safety net schemes from central / state government.	40,000	Over-Achieved / Number = 95,519 / In Bihar the team reached out to 60,200 individuals directly in the six intervention districts and ensured they were linked to one or more relief measure and are aware of MGNREGS provisions. / In Jharkhand, the team continued working with the vulnerable households and migrant workers to ensure they are connected to relief and social security measures. The numbers are as follows for Bihar and Jharkhand: / 14,544 beneficiaries were linked with various social protection schemes. / Total 3046 beneficiary received access to the MGNREGS in the reporting year. / 440 beneficiaries were linked to livelihood convergence schemes (opportunities such as Goat rearing shed, seed distribution schemes, cow shed etc) / In Odisha, a total of 16,202 people were linked to various rights and social protection schemes. / In Rajasthan, through convergence the team has supported 1087 farmers to get access to high yield variety of seeds, bio-fertilisers, pesticides. Around 75 families were linked to MGNREGS in two districts of the state.
Increase in uptake of average number of wage days under MGNREGS (percentage increase) through community mobilisation activities (esp. For critical blocks)	10%	Partially Achieved / In the reporting year the programme only supported 2 states- Bihar and Jharkhand for extended community engagement through CSO partners to work extensively at the Gram Panchayat and Block level. The following are the results achieved: / Bihar: Increase in 18 - 20% of households employed under MGNREGS and 12% increase in the total person days in MGNREGA works over the previous financial year in the project year. Further, increase of 1.6% in NRM work compared to last year / Jharkhand: witnessed 16% HHs increase and 17% increase in person days except for two project blocks Rania and Mahuadanr which recorded decrease in the number of HHs employed that led to the decrease in person days’ work done under MGNREGA. This decrease was mainly due to labour returning to cities with opening up of the economy post COVID-19 pandemic and low demand insitu. / Odisha: State allocated additional funds to MGNREGS last year (due to the pandemic) to support additional number of days over and above the 100 days supported from the centre. In the reporting year since there was no additional allocation and reported delay in fund release, most of the muster rolls were not being entered. Hence offtake can only be considered after March 2023.
Increase participation of marginalised HHs (such as PVTGs, Women, Tribal groups, PWD) in MGNREGS planning process (LBs)	50% of ICRG GPs	Partially Achieved / More than 50% increase in participation of marginalised HHs in ICRG Blocks of Bihar and Jharkhand. Community cadres including volunteers, PRI members, CBO Members SHG/VO members helped build awareness and mobilise communities and their effective participation. / Odisha: For the LB of 2023-24, palli sabha (village meeting) is going on now and the CSO partner is actively facilitating the participation of marginalised HHs. The present trend shows the level of participation is more than 50 percent in the operational villages of 16 blocks.

Briefly describe the output’s activities and provide supporting narrative for the score.

Through concerted efforts by CSOs and community mobilisers, the year saw an overall increase in average number of wage days, in Bihar and Jharkhand specifically where the programme has a good presence of community mobilisers and women groups supported through ICRG partner organisation like PHIA and UNDP. Due to financial cuts, the programme reduced resources deployed at the community level from almost all other states of ICRG except Bihar and Jharkhand.

Bihar and Jharkhand reported high number of people additionally linked to rights, entitlements, relief measures, skill Development, health care provisions and services especially related to livelihoods / Social Protection / safety net schemes from central / state government. Through focused community engagement support was provided towards:
- Improving awareness on COVID-19 vaccination and its facilitating
- Linkage and accessibility for marginalised groups to Social Protection schemes, MGNREGS and strengthening Climate resilient information
- Linking individual households that are vulnerable to climate change to existing livelihood Opportunities.
- Skill Development and convergence with other departments.
- Build awareness of the frontline workers and PRI representatives at GPs
ODISHA: supported district administration for revising the existing labour budget, demand generation and reaching at vulnerable households were the key strategies in the achievement of higher person-days generation across ICRG blocks and districts. Conducted trainings on climate responsive planning to increase the participation of women, average days and NRM offtake in the ICRG 4 districts. In Odisha, the team also supported:
Linkage and accessibility for marginalised groups to Social Protection schemes: Through focused engagement this year the programme was able to:
- Build awareness on Social Protection schemes
- Build awareness of the frontline workers and PRI representatives at GPs for facilitating social protection schemes
Promotion of livelihood opportunities: In 16 new blocks the team was engaged in (a) mapping of possible livelihood opportunities in farm and non-farm sectors in the intervention areas; and (b) linking the interested individuals and households to appropriate opportunities. Climate smart livelihoods practices were introduced in 2 GPs of Kandhamal district. Climate smart agriculture practices introduced in 10 villages of Balangir.

Rajasthan
NRM expert trained mates and MGNREGS Functionaries on proper waste ware/ Gully plug construction on Naadi/canals and trenches. Further, the state team focused on community mobilization to support plantation, seed collection and capacity building of MNREGS labours and mates on plantation techniques and leading to plantation of 3100 trees.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

Economy and Efficiency: FCDO’s support to social protection and humanitarian cash transfers recognises that there is strong evidence on their effectiveness and value for money. As also recognised during the pandemic prioritisation exercise, social protection programmes and/or cash transfer programmes have high returns by preventing a fall back into poverty poor nutrition. Safety Nets and SP programmes help people to meet their basic needs (such as food, clothes, shelter, clean water, soap), support human development (through impacts on access to education and health services, and nutrition), enable households to save and invest in productive assets and economic activities; and prove to empower (particularly for women) by allowing people to make their own decisions, and help households to be more resilient and cope better with shocks and stresses (e.g. not be forced to sell assets in the face of illness or drought). In addition, the crowd sourcing and social audit component of CRISP-M tool will increase transparency and accountability of MGRNEGS overall, further improving social and economic returns.

Equity: The team has reached out to more than 50% of women and more than 50% of socially excluded communities in all the target states, enabling the poorest of the poor access safety nets. The awareness and linkages with social protection schemes, livelihood opportunities have tremendous social return on investment which has both economic and social impact. ICRG interventions are designed to be inclusive from the beginning and this year the focus remained on women headed households and persons with disabilities (PwD). More than 50% women participate under MGNREGS in the reporting year as well. Their participation in labour budget preparations and planning slightly improved from last year, the programme will continue to work towards increasing women’s participation in local decision making in the project areas using programme evidence.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

This output is additional to the earlier log-frame from Phase I and was introduced last year due to enhanced community engagement in the extended period to recognise their voice in local adaptation action. The team collated 75 impact stories from 4 states in the reporting period that highlighted community participation in decision making process of climate resilient planning under MGNREGS. No change will be carried to this output and the focus in the last year of implementation will be to consolidate results from the field.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

In the reporting period, where the CSO partners continued to work, the focus remained on strengthening civil society networks and organisations to deliver local actions and respond to the ongoing economic crisis and its impact on livelihoods. The poor households were linked to one or the other Social Protection scheme to reduce their vulnerabilities to climatic events. The HHs were also provided with additional support from various local schemes available through convergence – that contributed to their overall livelihood plans for the year (increase and sustaining their annual incomes).

Lessons learned and recommendations for the year ahead
Lessons:
Locally led adaptation actions are centred around community needs, capabilities and participation in decision making. The programme demonstrated by implementing the CRISP-M tool at the village level on - how an inclusive, volunteer-led community engagement process supports climate technology to work in favour of poor and marginalised communities. An important aspect of ICRG work is towards strengthening capacities of community-based organisations (CBOs); Civil Society Organisation (CSO) and local NGOs to provide immediate response to disasters and help link beneficiaries with welfare schemes and relief measures; spread awareness on the preventive measures; protect and safeguard the interests of the poor and ensure their overall wellbeing.

Recommendation:
- Community engagement is to be carried to ensure rural people have complete ownership of adaptation actions, using the tool as an input to support and aid decisions related to planning, implementation, monitoring, management, and maintenance.
- Enhancing livelihood opportunities for poor through convergence with other rural development programmes further helps the poor absorb climate shocks. ICRG will institutionalise systems that converge livelihood schemes available at different levels to make climate resilience central to livelihood support for the vulnerable groups. District level committees, plans help bring different social programmes together to support overall welfare of the poor – schemes like PDS; subsidies around fertilisers/pesticides, seeds and irrigation etc help support their agriculture production; MGNREGS; Ayushman Bharat, etc.
- Climate proofing of rural infrastructure improves ecosystem health on which these livelihoods are dependent, helping HHs gradually move beyond vulnerability thresholds. Based on this, the programme will continue to strengthen capacities of local government and communities alike on planning and implementing climate informed rural infrastructure projects under MGNREGS in the coming year.
Output Title	Innovative tools (e.g., IT based), techniques, mechanisms to strengthen social protection programmes delivery on climate and environmental impacts/benefits promoted.
Output number:		4	Output Score:	B
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number of IT/Tech based tools developed/supported and piloted under the programme through UK-India collaboration.	3	Not achieved / Number = 1 / The customisation and scale up of CRISP M across all the 6 states was slowed down due to pause and budget cuts. The programme focused on implementing the tool in 2 districts of MP and bringing out early results and learnings from the process and designing the state module for Jharkhand (JHAR-CRISP was developed on the lines of CRISP-M). Three modules of CRISP-M were customised for Jharkhand state based on the local context, distinct climate vulnerabilities, river basin and community profile.
Number of innovations, technologies and approach introduced under the programme mainstreamed into existing systems to improve the effectiveness of social protection in building climate resilience.	0	Not applicable / No new tool or technology was introduced in the reporting period. The focus remained to roll out the CRISP-M tool in Raisen and Sehore districts of Madhya Pradesh and introduce a state module in Jharkhand.
Number of directives issued to scale up the innovations, tools/tech and frameworks.	3	Achieved (number = 3) / MORD issued directives to NRSC and NIRD to help integrate climate information into Government’s existing tool – Yuktdhara, with the plan to scale CRISP-M tool across India. / Government of Jharkhand issued directives to set up a climate change cell to administer the scale up of CRISP-M in the state. / Rajiv Gandhi Watershed Mission under the Department of Rural Development, Government of Madhya Pradesh adopted CRISP-M tool to develop climate resilient asset plans for 82 mili watershed projects which are part of the Pradhan Mantri Krishi Sinchayi yojana (PMKSY).

Briefly describe the output’s activities and provide supporting narrative for the score.

Evidence suggests that integrating Climate Information Services (CIS) can help enhance the climate resilience impacts of MGNREGS. MoRD acknowledges this potential which can be seen in the annual master circular 2019 of MGNREGS that specifically mentions the use of CIS in planning and design of works. However, the practical implementation of this guidance faces a number of challenges relating to access, communication and use of CIS in MGNREGS planning and decision making. CRISP-M addresses these challenges at community as well as household level. CRISP-M tool since its launch has received support from the senior most level of MORD where, Shri Giriraj Singh, Union Minister, Government of India not only launched the tool but also addressed the event that showcased early results and learnings from its implementation in MP in October 2022.

Secretary, MORD has also taken keen interest in the scale-up of CRISP M across India and has mobilised resources and delegated responsibilities within his ministry and other departments (such as NRSC, NIRD) to integrate climate features of the tool in MGRNEGS in-house tool – Yuktadhara. With support from Secretary, MORD and senior officials from Jharkhand a state module was customised for Jharkhand and launched by Hon’ble CM of Jharkhand and British HC in August 2022. Shri Hemant Soren, CM of Jharkhand also hosted a meeting post the launch to discuss how the tool can be adopted by the state in delivering a climate resilient Jharkhand. The functioning of the tool and its features were shared with senior officials from the state – Chief Secretary and Principal Secretary to CM at a technical workshop and the state team continues to work closely with Government in operationalising its adoption and implementation. A climate change cell is being constituted within Chief Minister’s Office (CMO), Jharkhand to help with the implementation in the coming months.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

Economy and Efficiency: Evidence suggested that the benefits of MGNREGA natural resource management activities strengthened by integration of climate information carried out in one village, go beyond the geographical boundaries of that village. For example, afforestation and desilting of percolation tanks have increased groundwater levels in neighbouring villages of intervention blocks under ICRG. It is envisaged that the climate informed GIS based watershed planning carried through JHAR-CRISP tool will help enhance Jharkhand’s overall agriculture productivity and environmental prosperity in the coming years.

Effectiveness: Climate information is widely viewed as critical for building resilience to evolving climate hazards and enabling adaptation to climate change. However, there are several shortcomings in the way climate science is currently used in resilience and adaptation practice. These result in low uptake of already-available information, emphasising the need to bridge the gap between producers and users and translate existing information into appropriate forms. The CRISP M tool will address this gap as it focuses on proper communication of climate information. Such an approach can be very effective in dealing with the uncertainties of climate information.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The programme placed great emphasis on developing innovations, technologies and approach that help improve the effectiveness of social protection in building climate resilience since its inception, this output did not change from last year. The delivery against this output of building innovative tools began taking shape in 2018 and with the launch of CRISP-M tool has achieved the programme’s original intention. There are no planned changes envisaged as a result of this review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Last year’s recommendation was to work closely with MORD as they scale up GIS planning across India and use it as an opportunity to promote integration of climate information into the overall planning process. Further, it was recommended to co-develop frameworks and tools with government institution and line departments to ensure greater buy-in from them.

This year the team initiated the integration of MORD’s Yuktadhara and ICRG’s CRISP-M tool by developing a road map and submitting it to MORD. The road map laid out various steps on coordination between several institutions to make the integration possible, the team has made significant progress in this regard in the reporting year and was able to influence Secretary, MORD to issue a directive to National Remote Sensing Centre (NRSC) to collaborate with ICRG team on this.

Further, the team focused on co-developing state versions of CRISP-M tool to support outcome-based long-term perspective planning with state departments and institutions. Co-developing the state modules can transform MGNREGS interventions from being just recharge and conservation activities to landscape-based area treatments using watershed approach, with defined outcomes of drought-proofing or flood resilience.

Lessons learned and recommendations for the year ahead
- Buy-in from senior officials at MORD is essential in scaling up CRISP-M tool (climate resilience planning) across India. MORD has issued several directives post which steps have been taken by National Remote Sensing Centre (NRSC) in supporting the integration of CRISP-M tool with Ministry’s existing systems such as Yuktadhara, Bhuvan (GIS based Planning), Amrit Sarovar implementation, etc. Regular engagement from the team with MORD and NRSC will ensure this agenda remains a priority for Senior GOI officials.
- Develop a road map that will help embed CRISP-M within MORD’s Yuktadhara – GIS based planning system by working closely with NRSC, NIRD and State council of science and technology.
- Global evidence has shown clearly that poor communication with users, limits the use and impact of climate information – i.e., how it is made available and the capacity of the end users (both government agencies and community) to interpret and use it for decision-making determines the success of any CIS. In the next year a feedback loop will be setup to keep the CRISP-M tool updated to the contextual needs and demands of both the community and local governments
- It is seen that co-developing frameworks and tools helps in greater buy-in from the government, line departments. The team will work with Government of Jharkhand specifically to help roll out JHAR-CRISP implementation across all districts and set up a monitoring mechanism within the Chief minister’s office to take update on its progress.
- The drought management aspect of the tool for MGNREGS can provide communities and authorities the lead time to prepare for climate crisis. This aspect of the tool however needs to be refined further in consultation with National and State Disaster Management Agency (NDMA and SDMA), to ensure it gets embedded within the system.
D: RISK

Overall risk rating: Major
During the review period, a refreshed risk assessment of the programme was undertaken, drawing from the wider FCDO guidance on risk. Overall risk of the programme has moved from Moderate to Major in the reporting year due to additional policy and programme delivery risks.

The global economic slowdown due to Russia Ukraine conflict along with the ongoing pandemic acted as the biggest contributor towards programme risk which led to budget realignments and pause in any new activities of the delivery partners. While the programme managed to control the risk to a large extent by deprioritising some resource intensive activities and focused on providing direct technical advisory to state governments. This helped in maintaining the team’s relationship with the line departments so that the agenda of climate proofing MGNREGS remains a priority at both national and state level.

The continued pause and prioritisation of available funds have added additional risks to ICRG implementation and overall impact. These have been shared with the team leader and the risk register has been updated accordingly. Detailed assessment of risks and mitigation strategy is available here. Key risks and mitigation measures detailed below.

Key Risks (and Residual Risk Rating Post Mitigation)	Mitigation measures
Policy & Programme Delivery: / Managing delivery partners and programme outputs: As a result of extended financial pause and delay in payments to delivery partners against ongoing activities/incurred expenditure has led to transfer of financial risk at partners’ end. Slowing down of activities in this uncertain period is adversely impacting the momentum of institutionalising ICRG approaches and tools, increasing the likelihood of not meeting the programme objectives. (Major)	Ensure clear and timely information flow on finances and being transparent with partners. Conducting frequent assessment with the partners on their fixed and subsistence cost to ensure the programme is relevant and delivering priority ongoing and committed activities.
Reputational: / Earlier closure and continued financial cuts: Further budget reductions and potential early closure could have a negative impact on the UK’s relationship and reputation with MORD and State Governments, that has gradually been built during the last 2 years in run-up to COP26 and COP27. This would partially reverse the gains made in establishing adaptation as an important part of the UK-India partnership alongside mitigation and recent commitments made to MOEFCC, MORD and various state governments. (Severe)	Mitigated through: / Ensure timely and careful communication of any early closure decision to GoI and state govt partners, stressing achievements to date and sustainability measures. / Explore tapping into other resources available within the network (DHC, SIN, SARH, etc.) to support some of the outputs. Explore complementary projects in the region and potential for ICRG approaches and support to be taken up through other organisations such as World Bank, GEF and UNDP. / Work closely with the line departments to align ICRG interventions with National and State Government priority and leverage public funds (such as MGRNEGS, climate finance) to deliver climate adaptation objective.
Delivery: Frequent transfer of senior government officials involved in project may delay interventions that require government approvals [Minor]	The Programme Team regularly monitors government counterpart movements and takes measures for smooth handover process for such transitions. Over the years the team has built a health working relationship at all administrative levels and is entrenched in the MGNREGS system. Team members ensures that directives and meeting minutes are issued and put on file as appropriate, to maintain continuity irrespective of the officer in-charge. There is a constant focus on strengthening systems and policies to avoid risk related to individuals (such as inclusion of climate change in the Annual Master Circular of MGNREGS, directives issued by Secretary MORD, etc.).
Safeguards: Exploitation of vulnerable population who have an interface with ICRG Programme - directly or indirectly due to non-compliance of safeguarding policies by implementing partners. [Moderate]	Regular monitoring (through field visits, spot checks, calls with downstream partners) along with conducting structured discussions with partners on FCDO's safeguarding standards. Delivery partners who work with CSOs and community mobilisers in the field have been instructed by Programme Team to follow FCDO's safeguarding standards. Although, FCDO conducts a due-diligence assessment of potential partners and reviews organisations’ safeguarding policies, the programme team will also remind first tier partners of their responsibility every six months to ensure appropriate safeguarding standards are cascaded down the delivery chain. Evidence that the standards have been shared and that partners are clear about the expectations will be recorded and reported duly in the reporting period. This practice will continue until the end of project.
Safeguards: Project beneficiaries/households knowingly and intentionally obtaining or attempting to obtain benefits from the project to which there is no entitlement. (Minor)	Appropriate controls in place i.e., cross-checking of bills and vouchers as per the submitted invoice and checking authenticity of bills on random basis. Existing Anti-Fraud and Anti-Corruption in place with stringent action.
Fiduciary: Instances of corruption and fraud in Downstream Partner's operations. (Moderate)	Due Diligence as appropriate is conducted for downstream partners and appropriate controls in place for random checking

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Delivery against planned timeframe; Monitoring of the interventions:

Programme progress is on track for some of the outputs but is slowed down for others due to prolonged uncertainty of long-term budgetary allocations. Delivery against the agreed outputs is monitored and reported on a periodic basis, as listed below –
- FCDO ICRG Task team holds monthly review meetings with all the delivery partners. These meetings are used to track the progress of the programme as per the agreed work plan. Key risks and mitigation strategies are discussed and agreed.
- Monthly review meetings have enabled shared ownership of the programme, enabling partners to escalate risks and challenges, share insights on interventions, collaborate for joint initiatives, and promote exchange of ideas.
Periodic meetings were held with the Line Ministry, State and District Departments, National and International Agencies and other Stakeholders. These meetings helped to inform, adjust and refine deliverables. In addition to the monthly meetings, the partners and their management have been carried through study and monitoring visits to the states and districts (where interaction with downstream partners were also carried), planning and jointly coordinating external facing events and collating and disseminating programme results at the global and national level.

The annual review for this year was initiated in September’22 by developing a work plan that was shared with each partner who reported back on key results against the programme log-frame. Field visits, workshops and partner meetings were conducted to review the results and collate key achievements that informed the overall annual progress.

Quality of Financial Management
Overall, the programme is delivering well against its annual financial allocations. Spend under the programme since April 2022 is £395,000 (as on Nov’22), as against the forecasted spend to March 2023 of £943,000.

Annual workplan linked budgets were agreed at the beginning of the year (April 2022) and continued to evolve/amend due to ODA cuts. Forecasting and monitoring for the project was reviewed monthly by the ICRG task team and deliberated during the task team meetings to ensure that the future spending profile aligns with forecasts, this has been a major challenge during the reporting year with prolonged uncertainty on budgets and spending restrictions.

Decisions regarding early closure and further cuts should be accompanied by a rounded exit strategy that not only reduces the risks linked to FCDO’s reputation and programme delivery but also ensures safeguarding programme input costs till date.

FCDO’s working relationship with its delivery partners continued to be collaborative. In particular:
- FCDO mandatory requirements (including fraud, safeguarding, transparency etc) have been informed to all the delivery partners.
- An audit trail has been maintained for all key programmatic and financial decisions.

Overall, the programme continues to deliver high value for money.

Date of last narrative financial report	10th November 2022	Date of last audited annual statement	April 2022

ANNEXURES
Annexure 1: ICRG’s Progress against Outcome Indicators
Outcome Statement: Integrating climate information services into the design and delivery of social protection architecture of India (in particularly MGNREGA) to build transformative resilience of the poor and most vulnerable.
Indicators	Results (Jan 2022 – Nov 2022)
Indicator 1: Number of government institutions/departments integrating climate information services into design and delivery of social protection projects/schemes [disaggregated by district, state and national]	Ministry of Rural Development / State Rural Department – Odisha, Bihar, Chhattisgarh, Madhya Pradesh, Jharkhand and Rajasthan / Pradhan Mantri Krishi Sinchayi Yojana in Madhya Pradesh / In Odisha: At state level the following departments are capacitated to integrate CIS in planning process- OLM, COE, Odisha Climate Change Cell, Forest Department. At District Level - ORMAS, ITDA, Horticulture, Millet Mission, Soil Conservation, Fishery, Minor irrigation, Ground water division, BKN milk union were influenced to use CC in their programmes.
Indicator 2: Number of GPs/PRIs integrating climate resilient planning (CIS) into Labour Budgets/GPDPs	In the reporting year the focus was to use CRISP-M tool in the planning process of MGNREGS in Madhya Pradesh. A total of 50 Gram panchayats 25 each in Sehore and Raisen were able to develop community-based climate resilient asset plans / In Madhya Pradesh - 82 mill watershed projects spread across 64 blocks in 36 districts used CRISP – M tool in the development of Climate resilient asset plans / In Bihar 40 GPs have been directly influenced by the team. Further, a State Guidelines for Labour Budget Integrated Action Planning was issued last year (prepared by ICRG team) that has been used for all 8378 GP for this year labour budget. / PHIA, ICRG’s CSO partner have also supported 50% intervention blocks (i.e. 46 GPs) in Bihar and Jharkhand. / In Odisha a total of 1100 GPs in 4 operational districts) were influenced directly and indirectly through direct planning, handholding and trainings at the block and district level. / 80 GPs (5GP/block) used CC integrated planning from the support provided directly by the ICRG team. / Indirectly, 242 GPs in the 16 operational blocks through handholding support of the NGO; 778 GPs used CC integrated planning through training and capacity building.
Indicator 3: Number of MGNREGS infrastructure influenced through the programme which will lead to climate resilience improvement (such as but not limited to flood protection, increase in net irrigated area, groundwater improvement, etc.).	Total structures = 1981 / Total HHs / Bihar and Jharkhand / 11 Number of Climate resilient works (CRW) were influenced directly and approved. Total Household identified around the selected CRW = 536 HH. Beneficiaries’ details in table below / SC 290 / ST 92 / OBC 162 / Others 92 / Total 536 / Technical design support of 500 Amrit Sarovar is carried by state ICRG team. ICRG state team also studied Amrit Sarovar in 4 districts of Bihar and the findings of the study was issued as state guideline in the reporting period to be followed for implementation of 3369 selected structures. The CSOs in Bihar also helped in identifying and getting 30 Amrit Sarovar (individual and community ponds) approved during Amrit Sarovar campaign in Madhubani, Bihar. / Around 210 NRM structures influenced indirectly under the programme through orientation programme of the PRI members enabling them to Plan NRM and Climate resilient works benefitting approximately 5800 households. All the newly selected PRI members (ward members, Mukhiya, Sarpanch) were trained in the month of Feb- March 2022 on climate risk and importance of Climate resilient works. The training enabled building perspective around NRM works and climate resilient structures reflecting in their plans. / In Odisha, it was ensured that at least 1 integrated plan per GP in the LB was done in line with Climate Resilient Works (CRW) way. Hence for 322 GPs (80 direct and 242 through handholding), 322 integrated plans were prepared that cover about 1932 infrastructures on an average (1 core structure and 5 complimentary structures). / In Rajasthan, more than 130 Hectare land has been restored and developing as a Pastureland under MGNREGA. In this process, 8 DPR have been prepared and submitted to concern GP for Approval. Most of the DPRs have been approved in the reporting period and the remaining are likely to be approved soon.
Indicator 4: Amount of finance mobilised, leveraged, and repurposed (disaggregated by national/international/UK/public/private) ICF KPI 11	Total = INR 471 million (4.7 million GBP) / In Bihar: Estimated value of 11 CRW = INR 71,25,380 (~£71,000) Estimates of some of the proposed work in the CRW is still under progress. / In Odisha, approximately INR 457.5 million (4.58 million GBP) leveraged through convergence and influencing increase in NRM works under MGNREGA in project blocks. / In Rajasthan INR 65 Lakh (~£65,000) have been mobilised under ICRG Project in Udaipur district. The fund was mobilised from the Signify -a Social Corporate Responsibility institute of Philipps company.
Indicator 5: Number of poor HHs with enhanced livelihood and income generation opportunities (such as diversified / alternative livelihoods, increase in agriculture productivity, annual income, etc)	Total = 85,222 / In Bihar and Jharkhand 62,422 poor HHs were supported with enhanced livelihood and income generation opportunities. More than 50% increase in participation of marginalised HHs in MGNREGS. / In Odisha 20,800 HHs are direct beneficiaries of the project (16 blocks with 5 GPs/block are covered). Out of the 5 GPs in each block, one most vulnerable GP is identified which is demonstrated as model GP. The baseline of all households on the 16 GPs were done. / In Rajasthan, 2000 Households have been linked to various schemes to improve their livelihoods. Most of them have been engaged in Goat farming, Dairy farming, MGNREGA wages and linked to Social Security Schemes like Pension (old age, widow and disability)

Annexure 2: Detail report on few of the Output indicators
Indicator 1.2: Number of Govt officials, Community mobilisers, PRI member, trained on climate information services, climate risk management and M&E of climate impacts
In the reporting period the programme was able to produce the following results against the first output on training in five of ICRG states:

Madhya Pradesh, Jharkhand, Bihar
- 300 Government official were trained on climate information and risks; 125 officials trained on structural design of Climate resilient works; 1230 PRI members trained on Climate Resilience Planning in Bihar.
- Built capacity of 6,741 community cadres comprising members from community-based organizations, village organizations and self-help groups which included 5156 (76%) women and 1575 (23%) men having beneficiaries from various social categories such as 2814 [42%] from SC, 2736 [41%] from ST, 638 [9%] from OBC and 559 [8%] others including 50 [1%] PwD. This includes 725 PRI functionaries wherein 318 [44%] women, 407 [56%] men and members from 144 [20%] SC, 481 [66%] ST 49 [7%] OBC and 51 [7%] from other social category and 6 [1%] PwD.
- Facilitated and capacitated 13,365 community-based organization members, village organization members and self-help groups members which included 10557 [79%] women and 2808 [21%] men. The social category break-up included various social categories such as 7280 [55%] from SC,2517 [19%] from ST, 564 [4%] from OBC and 3000 [22%] others including 38 PwD.
- Awareness training on MG- NREGS, Social protection, skilling and Livelihood opportunities was given to 66,088 beneficiaries in which 36,688 [56%] women and 29,396 [44%] men. The social category break-up indicates 94% were from socially excluded communities (SC-33%, ST-48%, OBC-8% and Other-11%. including 1% PwD).
- Facilitation of Gram and Ward Sabhas: The team mobilized marginalized communities to participate in Gram Sabhas. Currently 18 Gram Sabha Secretariat have been established in the villages in Jharkhand. These Gram Sabha Secretariat are established as a functional unit of local governance and have oriented the representatives of the sub committees about their role and functioning.
  [note] These secretariats were established in tribal areas of Jharkhand which were under Panchayat Extension in Scheduled Areas (PESA) Act where in tribal communities constitute and organise their own Gram Sabhas which are chaired by the village traditional leaders but with limited information regarding their roles and functions in the panchayat raj system.
In addition to training officials the team also help build understanding of communities, individuals and established informal platforms to facilitate participation of the most vulnerable households.
- Awareness training on MGNREGS, Social protection, skilling and livelihood opportunities was given to total 66,088 beneficiaries.
- 18 Gram Sabha Secretariat have been established in the villages in Jharkhand to strengthen community participation in governance processes of various schemes aimed at the development and mitigation of climate impacts to the community.

Odisha
- Organised 3 inception workshops in Balangir, Mayurbhanj and Kandhamal district to discuss the workplan and prepare for the labour budgeting for 2023-24.
- Partnered with Zilla Parishad in all working districts to implement Jal Shakti Abhiyan, a flagship programme of MoWR, Govt. of India. Also, provided technical assistance in design, construction/ rejuvenation and monitoring of Amrit Sarovars
- In association with Odisha Integrated Irrigation Project for Climate Resilient Agriculture (OIIPCRA), and Water Resources Dept, Govt. of Odisha to strengthen Pani Panchayat activities in ICRG working districts with convergence of MGNREGA.
- Partnered with Krishi Vigyan Kendra (KVK), Balangir to implement climate smart village under National Initiative on Climate Resilient Agriculture (NICRA) program.
- For PRIs members, a microlearning module on "Organic agricultural systems to mitigate climate change" has been designed, and virtual training of RCs and DCs on the training module has been performed in preparation for delivering the training programme at the Gram Panchayat level.

Trainings
- A total of 4,350 officials and community members were trained on climate change, resilience and climate smart livelihoods.
- 318 MGNREGS technical officials, line department and other government officials were trained on ICRG programme in the district level workshop.
- 106 block-level officials were oriented and trained on ICRG programme in the block-level workshops.
- 1198 government-level officials, PRI members, and community mobilizers were trained on CLART, labour budgeting, PRA exercise, and also on finalizing MGNREGA works for the FY 2023-24.
- 35 key stakeholders trained on Climate Change Adaptation and Eco-DRR in a state-level ToT cum Workshop.
- 2693 village institutions and their leaders were trained on drumstick cultivation and seedlings, model village planning for sustainable agriculture, sustainable water use, climate change impacts, and livelihood generation.
Rajasthan
- 14 batches of the training for 222 farmers were conducted on Climate Smart Agriculture practices for vulnerable farmer community
- ICRG team conducted training in 16 batches where 193 persons were trained on water harvesting and purification. This resulted 178 families to initiate water harvesting and water treatment with chlorine and using the same water for daily use and drinking.
- MGNREGS Mate training: two batches (1 in each GP) were organized by ICRG team and trained 36 mates.

Indicator 1.3: Number of modules and guidebooks developed, adopted and embedded for capacity building, training and awareness generation about climate responsive social protection/adaptive social protection.

The section above details out the guidebooks that were adopted by the state, the following provides Manuals/modules/concepts developed which are being used for training by the ICRG team but yet not adopted officially.
1. Revised manual for training of administrative staff of MGNREGS on adaptive social protection.
2. A concept note on "Climate Smart Gram Panchayat" was developed, and initial conversations about its implementation with 2 district administrations were held.
3. Revised manual for training of technical staff of MGNREGS on climate resilient planning and design.
4. A revised Migration Reduction Strategy for Western Odisha developed.
5. Training manual on forest ecosystem-based adaptation strategy to climate change prepared for Kandhamal district, Odisha.
Indictor 3.1: Number of people additionally linked to rights, entitlements, relief measures, skill Development, health care provisions (w.r.t COVID19 like vaccines) and services especially related to livelihoods / Social Protection / safety net schemes from central / state government.

Bihar and Jharkhand reported high number of people additionally linked to rights, entitlements, relief measures, skill Development, health care provisions and services especially related to livelihoods / Social Protection / safety net schemes from central / state government. Break-up of individuals based on gender, socio-economic parameters, is as follows:
- Awareness on COVID-19 vaccination and support drive: Facilitated 43,554 doses of COVID 19 vaccination including 21,454 first dose, 20,320 second dose and 1,780 booster doses in Jharkhand and Bihar in collaboration with the state in hard-to-reach areas and communities
- Linkage and accessibility for marginalised groups to Social Protection schemes, MGNREGS and strengthening Climate resilient information: Through focused engagement on strengthening community members resilience this year the programme was able to:
1. Build awareness on Social Protection schemes, MGNREGS and climate change: Under this total 66,088 beneficiaries consisting of 36,688 [56%] women and 29,396 [44%] men. Owing to the focus on the women and socially excluded communities the social category bifurcation constituted 94% socially excluded. The social category bifurcation included SC-33%, ST-48%, OBC-8% and Other-11%. including 1% PwD.
2. Linked with various social protection schemes: 14,544 beneficiaries having 8,303 [57%] women and 6264 [43%] men. The social category bifurcation constituted 4792 [33%] SC,7421 [51%] ST,1722 [12%] OBC and 609 [4%] others including 92 [1%] PwD.
3. Received Benefits: Out of the above linked beneficiaries total 8,671 beneficiary received benefits/access to the social protection schemes which included 4,925 [57%] women and 3692 [43%] men. The social category bifurcation constituted from 2815 [33%]SC, 4598 [53%] ST,946 [11%] OBC and 288 [3%] others including 14 PwD.
4. Linked to MGNREGS schemes: 3,763 beneficiaries applied for job cards, work demand and other application including 1880 [50%] women and1883 [50%] men. The social category bifurcation constituted 1160 [31%] SC, 2318 [62%] ST ,224 [6%] OBC and 61 [1%] others including 4 PwD.
5. Received access to the MGNREGS: Total 3046 beneficiary including 1483 [49%] women, 1563 [51%] men. The social category bifurcation constituted 906 [30%] SC, 1940 [64%] ST,154 [5%] OBC and 46 [2%] others including 1 PwD
6. Promotion of livelihood opportunities: This activity involves (a) mapping of skills and possible livelihood opportunities in farm and non-farm sectors in the intervention areas; and (b) linking the interested individuals and households to appropriate opportunities and convergence with various departments to strengthen livelihoods.
- Linked to livelihood Opportunities: 440 beneficiaries were linked to livelihood convergence schemes comprising of 203 [46%] women and 237 [46%] men. The social category bifurcation constituted 73 [17%] SC, 361 [82%] ST, 5 [1%] OBC and 1 other. Out of this linkage 304 beneficiaries 86 [28%] women, 218 [72%] men, 303 [100%] ST,1 OBC got benefits of the livelihood convergence opportunities in form of Goat rearing shed, seed distribution schemes, cow shed etc. and the rest are in the process.
- Skill Development and convergence with other departments: 121 beneficiaries; 73 [60%] women, 48 [40%] men were linked with skill development programme like mushroom farming, fishery training and livelihood promotional schemes. The social category bifurcation constituted 60 [50%] SC, 38 [31%] ST, 23 [19%] OBC List of 200 families were given to Agricultural Technology Management Agency (ATMA) for training and later subsidy on the farming in Bihar.
- Build awareness of the frontline workers and PRI representatives at GPs: The PRI members are entrusted with responsibility to ensure that the CRW sites is further incorporated in the MGNREGA action plan. In order to ensure incorporation, team liaised with the Block officials and submitted the panchayat wise list of identified CRW so that no sites are missed out in the process.
  - Team capacitated 725 PRI members 318 (44%) women and 407 (56%) men,144 (20%). The social category bifurcation constituted SC, 481 (66%), ST, 49 (7%) OBC and 51 (7%) Other.
  - 744 frontline workers were also covered including 670 (90%) women and 74 [10%] men. The social category bifurcation included 124 (17%) SC,490 (66%) ST,102 (14%) OBC and 28 (4%) Others. 515 community volunteers were reached including 212 (41%) women and 293 (57%) men. The social category bifurcation included 155 (30%) SC, 342 (66%) ST and 17 (3%) OBC to ensure effective community participation and ownership
  - Team facilitated and capacitated 6171 members from community-based organization, village organization and self-help groups which included 3873 [63%] women and 2298 [37%] men. The social category bifurcation constituted 2798 (45%) from SC, 799 (13%) from ST, 426 (7%) from OBC and 2148 (35%) others.
ODISHA: supported district administration for revising the existing labour budget, demand generation and reaching at vulnerable households were the key strategies in the achievement of higher person-days generation across ICRG blocks and districts. Conducted trainings on climate responsive planning to increase the participation of women, average days and NRM offtake in the ICRG 4 districts. In Odisha, the team also supported:
Linkage and accessibility for marginalised groups to Social Protection schemes: Through focused engagement this year the programme was able to:
Build awareness on Social Protection schemes: 16,202 individuals were covered under various social protection schemes through outreach interventions.
- 172 were enrolled in Biju Swasthya Card.
- 649 labour were engaged in Odisha Building & Other Construction Welfare Board (OBOCW) in convergence with MGNREGS.
- 52 farmers land were regularised under Forest Rights Act (FRA).
- 51 social security application made for physically disabled application and certification
- 2006 Pradhan Mantri Fasal Bima Yojna (PMFBY) applications were sanctioned for the farmers.
- 72 persons were assisted for widow and old age pensions
Build awareness of the frontline workers and PRI representatives at GPs for facilitating social protection schemes: The project reached out to 5,357 individuals with 2254 men (42%) 3,103 women (58%) and socially excluded communities (1727 SC 1684 ST, 661 minorities, 20 Disabled and 1946 others)
Promotion of livelihood opportunities: In 16 new blocks the team was engaged in (a) mapping of possible livelihood opportunities in farm and non-farm sectors in the intervention areas; and (b) linking the interested individuals and households to appropriate opportunities. Climate smart livelihoods practices were introduced in 2 GPs of Kandhamal district. Climate smart agriculture practices introduced in 10 villages of Balangir.
  - The programme with the support of partner organisations and district level line departments empowered community on rights and entitlement over forest, land and water resources using Forest Rights Act (FRA). Also strengthened community institutions – Forest Rights Committee, Water user Association, Van Samrakhyan Samiti, etc. to facilitate the rights and entitlements over natural resources.
  - The programme provided essential support to district level line departments and institutions including ORMAS, OLM, DIC, RSETIs, and KVKs that covers fundamental computer skills, make-up artistry, tailoring, and handicrafts. Through connecting beneficiaries to outside efforts under the DDU-GKY programme, ICRG also works to support skill training.
  - To promote non-farm-based livelihoods, convergence with Rural Self Employment Training Institutes (RSETIs) and District Industrial Centers (DICs) at district level established, where youth are trained on income generating and vocational skills to improve their productivity, income, and quality of life.
Rajasthan
NRM expert trained mates and MGNREGS Functionaries on proper waste ware/ Gully plug construction on Naadi/canals and trenches. Further, the state team focused on community mobilization to support plantation, seed collection and capacity building of MNREGS labours and mates on plantation techniques and leading to plantation of 3100 trees. The following are some of the results from the state
  - Plantation and seed sowing in Pastureland: Plantation is one of the key mitigation strategies of climate change. Through regular mobilization and motivation by team Taragarh Gram Panchayat planted 250 plants on Amrit sarovar site and 800 plants on pastureland and 1 kg custard apple and 500 gram of Neem seed sowing on pastureland and in Badakheda Gram Panchayat total 2100 plants on pastureland and 13 kg seed sowing of Neem, black berry and grass seed sown on pastureland. The team trained MGNREGS labour on plantation techniques and plant protection.
  - DPR of Pastureland: NRM expert and team prepared 08 DPRs (02 each GP) for pastureland development in targeted GPs.
  - Support provided through convergence with other local schemes/projects:
    - Green Gram High Yield Varieties (HYV) seeds were given to 27 farmers and 120 farmers received Bajra HYV seed from department of Agriculture in Kahrif (Summer) season.
    - 20 farmers benefited from receiving Bio fertilizer and pesticides provided by Department of agriculture. This comprised of 13 compost pit including 2 bags single super phosphate.
    - 25 Kg chlorine powder provided by PHED for water treatment was given to 178 Households which treated more than 7,00,000 litre of harvested water.
    - 65 HHs were linked with Prime Minister Kisan Samman Nidhi and 313 applications are under process for labour welfare schemes.
    - 152 Applications for Wire fencing subsidy have been prepared and submitted and 13 HHs were supported with sprinkler
    - 75 Applications of Job card holders under category B works of MGNREGA were submitted and 8 works has been sanctioned, works are under progress
    - 27 Goat entrepreneurs identified for commercial goat farming.
    - 23 vegetable growers identified, and technical support started.
    - 03 farmers documentation completed for solar pump scheme (Kusum Scheme).

Annexure 3: Directives, Letters and Media coverage of ICRG Programme
Directives and Official letters (few examples from the reporting period)

Media coverage on the Launch of JHAR-CRISP and Technical Workshop in Jharkhand
1. https://www.telegraphindia.com/world
2. https://indianexpress.com/article/india/british-high-commissioner-alexander-ellis-listening-jharkhand-village-shares-its-problems-8105803/
3. https://www.businesstoday.in/education/story/uk-announces-chevening-scholarships-for-jharkhands-marginalised-communities-345350-2022-08-23
4. https://theprint.in/world/uk-signs-mou-with-jharkhand-to-create-new-scholarship-programme-for-marginalized-communities-2/1096479/
5. https://www.dailypioneer.com/2022/state-editions/govt--stakeholders-discuss-climate-resilience-information-system-and-planning.html
6. https://youtu.be/_5hOk0SMcPY
7. http://magahiawazz.in/?p=7339
8. http://aawazaapki.com/news-details/16835
9. http://dhunt.in/By43d?s=a&uu=0xba99a31bd30bb3be&ss=pd
10. https://link.public.app/e7wZE
11. http://sachbharatnews.com/4466/
12. https://gyanmalatv.com/?p=13169
13. https://bit.ly/3zvhHNy
14. https://link.public.app/DMoj
Case studies demonstrating community engagement work under ICRG
1. A compendium ‘’The power of ‘tech plus people’ in collective climate action’ developed by IIED in partnership with PHIA foundation ( https://www.iied.org/power-tech-plus-people-early-warning-early-action-climate-risk-management )
2. A Film based on CRISP-M Scale up work in Madhya Pradesh was developed by IIED. https://www.youtube.com/watch?v=1Z9su_46jj4