## Annual Review

Title: Climate Adaptation Water and Energy Programme (CAWEP)
Programme Value £ (full life): £19,550,000		Review date: 10 February 2023
Programme Code: [AMP ID#]300164	AMP start date: 10 November 2019	AMP end date: 30 March 2026

Summary of Programme Performance
Year	2021	2022	2023
Overall Output Score	B	B	A
Risk Rating	Major	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300164
DevTracker Link to results framework:

A. SUMMARY AND OVERVIEW

A.1 Description of programme
The Foreign Commonwealth and Development Office (FCDO) in Zimbabwe is funding the implementation of CAWEP through the United Nations Development Programme (UNDP) and UNICEF. The programme works to strengthen the ability of vulnerable communities to withstand climate shocks. Through this programme FCDO is supporting the development of climate resilient water and renewable energy infrastructure in vulnerable communities of Zimbabwe to enable: (i) continued access to water for productive and household use, including during droughts and floods, and (ii) improved access to clean and affordable energy to support economic activities and ensure more sustainable livelihoods. CAWEP will also strengthen Early Warning Systems (EWS) in vulnerable districts, enabling timely access to and use of weather & climate information to better anticipate and respond to climate shocks. The programme will provide technical assistance to the government and other non-state actors to support the wider use of climate science in designing and delivering resilient water and energy infrastructure. Evidence generated through this programme will be used to influence climate policy improvement and support national climate adaptation plans. As such, it aims to build and demonstrate an understanding of what works and what challenges must be overcome to deliver resilient and sustainable outcomes.

FCDO supports the delivery of this programme in fifteen districts across the country and intends to help over seven hundred thousand people to better adapt to the effects of climate change through sustainable access to solar powered multiple use water and energy systems including through access to reliable weather and climate information.
[note] Chipinge, Insiza, Binga, Chivi, Chimanimani, Buhera, Bikita, Mutare, Makoni, Mutasa, Gweru, Zaka, Chiredzi, Gutu, Chikomba

The programme has two main components that this review looks at. The components are briefly explained below:

A.1.1 Adaptive & Flexible Water and Energy supply- Component 1
Given the increased exposure to extreme climate or weather-related events in Zimbabwe, this component was designed to flexibly respond to emerging water & clean energy priorities including providing infrastructure support to avert the impact of potential climate or weather-related disasters. This £2.5 million funded component was implemented through UNICEF, providing sustainable basic water supply using climate resilient infrastructure, through the installation of solar powered water schemes in nine districts. It was implemented between July 2021 to June 2022.

A.1.2 Climate Adaptation - Community water & renewable energy infrastructure & Early Warning Systems (EWS) – Component 2
This is the main CAWEP component that seeks to contribute towards community and institutional climate resilience in Zimbabwe. Work under this component is designed to boost climate change adaptation through enhanced climate proofing and development of climate resilient community water and renewable energy infrastructure and strengthening EWS and response in selected vulnerable districts. UNDP Zimbabwe is leading the delivery of this component in seven districts. The total funding for this component is £12 million over three years.
[note] Measures taken to prevent infrastructure from being vulnerable to potential long-term climate impacts. Under this project, this involves infrastructure improvements, solar pumping, and water-use efficient, irrigation technologies (drip, sprinkler systems)

A.2 Summary supporting narrative for the overall score in this review
In this review, the programme scored an A, indicating it has met expectations at this stage. Three of the four outputs scored at least an A, with one moderately exceeding expectation, scoring A+. Main achievements in the past year include supporting over 77,000 people and 59 social institutions to better adapt to the effects of climate change in nine vulnerable districts. This was achieved through the completion of planned multiple use solar powered piped water schemes. Other achievements include setting up and strengthening community management structures, upscaling innovations for sustainable management of community water infrastructure and positive CAWEP contribution to support improvement and implementation national policies on climate change. These achievements are helping to keep the programme on course to deliver expected outcomes. Success factors that enabled these achievements include (i) lifting of COVID-19 restrictions, allowing delivery partners to work more effectively, (ii) completion of the programme feasibility study that allowed key programme decisions to be made on outstanding projects, and (iii) good working relationship with government stakeholders.

A.3 Major lessons and recommendations for the year ahead
The following sections highlight key lessons learnt in the year under review and provide recommendations to be taken forward in the coming year.

A.3.1 Key lessons learnt
Programmes provide many policy benefits beyond service delivery. A significant part of CAWEP is strengthening climate adaptation through improving access to multiple use water and energy to vulnerable communities. This is essential. However, to sustain these benefits there is need for strong policies that promote sustainability and enable wider action. CAWEP in the past year, has provided good opportunities to (i) support and improve national policies on climate resilience and (ii) help to deliver some of the climate policy priorities in the national climate policy. CAWEP, through UNICEF, has upscaled trials on models to improve sustainability. Most notable is the community piped water insurance scheme to cover physical loss or damage and major mechanical breakdowns, which ensures sustainable water access. Through such initiatives, CAWEP is helping to build a strong case to get this kind of insurance adopted as a policy if successful, which would strengthen the resilience of community infrastructure nationwide.

Early and meaningful engagement with government at the programme design stage is critical. It increases government buy in and can improve value for money, impact, and sustainability. For example, Government through the Rural Electrification Fund (REF) is contributing to the Hakwata solar project. REF resources have already delivered a 6.2km power line to be complemented by CAWEP support on a 152kW solar minigrid that enable the local community and businesses to have improved access to clean renewable energy.

The Government of Zimbabwe has set out ambitious climate goals for example in the National Development Strategy 1 and the forthcoming National Adaptation Plan. FCDO, UNDP and UNICEF programme teams have worked hard to ensure CAWEP is fully aligned to these goals, and thanks to strong engagement and genuine desire expressed by national and subnational Government of Zimbabwe staff to use CAWEP to support and deliver these national climate adaptation and resilience policy priorities in Zimbabwe.

The CAWEP multiple water use approach presents a very good opportunity for mainstreaming climate change in essential sectors such as education, health, food security and nutrition. Section C.1 and Annex 1 provide in detail how this approach has enabled education and nutrition outcomes in some communities. This includes testimony from the communities. It is important to take a multisectoral approach when designing climate adaptation and resilience approach.
A.3.2 Key Recommendations
- FCDO and UNDP should consider how to harness CAWEP to support and actively participate in the National Resilience Platform that is currently under discussion. This would enable CAWEP to: (i) learn from and develop previous work on resilience and (ii) contribute to the platform based on several pieces of operational research within the programme to inform strategic policy decisions. This should be used as a basis to replicate and scale up best practices. (By May 2023)
- CAWEP should continue to support the pilot scheme for community piped water insurance and make a strong case to the government that it is a good policy to adopt to ensure sustainability. (By December 2023)
- FCDO and UNDP should update the programme logframe following changes in some milestones across the four outputs. This include updating impact and outcome milestones for future years. (By May 2023)
- UNDP programme planning for the year ahead should be realistic considering likely disruptions due to upcoming elections in Zimbabwe. (By March 2023)
- FCDO and UNDP need to update risk registers regularly to reflect significant changes. (Monthly)
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

B.1 Theory of Change Description
The programme Theory of Change (ToC) largely maintains the logic it had at programme design, despite a slight change on the impact and adding two more outcomes. The initial overall programme outcome was to improve capacity at community, local and national levels to adapt to increasing risks of climate change. This will be achieved through improving access to climate resilient community water & renewable energy infrastructure & enhanced weather & climate services or Early Warning Systems (EWS). The programme is still working towards delivering this high-level outcome. However, following the conclusion of the programme feasibility study that provided additional information that was not available at design stage, the following changes were made on the ToC.

Table 1: Summary of changes to the Theory of Change
Changes made	Rationale
Rewording the impact from ‘Reduced Poverty in selected districts in rural Zimbabwe’ to ‘Communities and public institutions supported by CAWEP are more resilient to respond to adverse effects of climate change (droughts & floods).	Cyclical poverty caused by climate change in Zimbabwe requires people and institutions to become more resilient to climate shocks first to be able to deal with poverty in the future. This means with available programme resources, recurring climate, and economic shocks, building resilience to selected communities and government institutions is the impact that CAWEP is seeking to make as a priority.
Splitting the original outcome into three outcomes	Improve measured Value for Money (VfM) due to the scope of works that can deliver multiple outcomes.

The above changes do not present any material change to the programme design initially approved. They seek to strengthen the initial design. Splitting the outcomes helps to align and be able to track the contribution of programme inputs and outputs to different components that were in the initial outcome. Fig 1 below is the revised Theory of change.

Fig 1: CAWEP Theory of Change

There is ample evidence that shows the above logic is still relevant and will support Zimbabwe to better adapt to climate change and become more resilient to climate change. The four outputs are still relevant to achieve this. The following key sources provide evidence for this: (i) Zimbabwe’s Initial Adaptation Communication to UNFCCC in November 2022, (ii) FCDO funded Feasibility Study Report and (iii) World Bank 2021 Zimbabwe Climate Country Profile Report. In addition to this, CAWEP work that has already been completed in nine districts through UNICEF has demonstrated that the current ToC remains logical and appropriate and should be upscaled through UNDP in other seven districts through UNDP.
[note] United Nations Framework Convention on Climate Change
[note] zimbabwe-adcom-2022_final.pdf (unfccc.int)
[note] 14956-WB_Zimbabwe Country Profile-WEB (1).pdf (worldbank.org)

B.1.2 Stakeholder and beneficiary engagement
In the past year the programme has extensively engaged key stakeholders at all government levels and has engaged with beneficiaries through field visits and community meetings. This has enabled them to participate at each stage of the programme cycle. To optimise the expected programme outcomes and impact and achieve sustainability, CAWEP has a strong focus on inclusion. One good example where the programme is doing this is the Direct Implementation Modality (DIM) that UNDP is using. The approach allows the programme to use existing government technical and policy expertise and community knowledge and resources to help deliver outputs. The model also allows the programme to strengthen stakeholders and community capacities in project delivery. DIM is also opening more space for communities to participate in choice of interventions/projects through assigning them specific programme roles and responsibilities that they are accountable for and meeting them regularly to discuss progress.

B.1.3 Adaptive programming
The programme theory of change considers the existing internal uncertainties, risks, and challenges in the operating environment. The programme team has built in measures that help the programme to adapt to any of these factors should they materialise. The following are some examples of adaptations in CAWEP that ensure the expected outcomes are delivered:
1. By design the programme has an adaptive and flexible component meant to provide urgent, low-cost sustainable basic water supply using climate resilient infrastructure, through the installation of solar powered water schemes. This component has already been used, delivering thirty-five solar powered piped water schemes reaching over seventy thousand people with drinking and productive water. In the event there are changes in funding circumstances – this component will be used to still deliver some outputs although reduced in scale.
2. Using the Direct Implementation Modality (DIM) through UNDP. The approach allows the programme to use existing government technical and policy expertise and community knowledge and resources to deliver outputs. This entails working more through local government officials and communities and limited number of implementing agencies (NGOs) unless they have particular expertise that is not available in the existing programme delivery structure.
3. The programme team has in the past year secured a time extension from 31 August 2023 to 30 March 2026. This has considered likely implementation delays due to upcoming elections in Zimbabwe, potential outbreaks such as COVID-19 and other disasters.
B.2 Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
Overall, the programme is on track to achieve the expected outcomes. This judgement is based on the following evidence:

Expected results at this stage were met on three of the four outputs on:
 (i) delivering climate resilient multiple use water and energy infrastructure supporting 77,768 people to better adapt to climate change, contributing to achieving outcome 1.
(ii) enabling 51 schools and 8 clinics to access water for multiple use through solar powered PWS, resulted in CAWEP delivering on Outcome Indicator 1.3 . This is one of FCDO International Climate Finance (ICF) Key performance Indicators.
[note] Number of social institutions with improved access to clean energy as a result of set-up solar micro-mini grids, disaggregated by 1. community and 2 type of institution.
[note] UK Official Development Assistance (ODA) supporting climate change response
(iii) establishing and resuscitating community management structures to maintain installed infrastructure.
(iii) strengthening key national policies and strategies.
1. Good progress has been made in preparation for accelerating delivery of the above-mentioned outputs and to start full delivery on Early Warning Systems (EWS) and policy strengthening. Key preparatory work now at an advanced stage includes procurement of essential goods and services and strong stakeholder and community engagement. At the programme national launch held in December 2022, CAWEP was strongly endorsed and got commitment from national and subnational government structures. This gives confidence that they will participate and contribute towards delivering the outputs.
2. There has not been any change to the programme budget, implying there should be minimal alterations or delays because of budget cuts. A programme time extension has also been approved during the year. The new end date is now 30th March 2026 from 31st August 2023.
In the coming year, the programme will prioritise delivery of the following key activities:
1. Policy engagement and strengthening strategic relationships with government, the private sector and other development partners to help CAWEP to effectively support and help Zimbabwe to deliver policy commitments on climate change.
2. Installation and completion of Hakwata minigrid and installation of eighteen Automated Weather Stations, strengthening Early Warning Systems.
3. Preliminary installation of water works in Binga and technical feasibility work in Insiza and Chivi districts.
4. Light touch baseline is planned for the second and third quarters for the indicators that do not have baseline data and other relevant impact data. The project will also make use of some of the baseline data from the Green Climate Fund project recently concluded baseline, the Zimbabwe Resilience Building Fund endline survey.
Delivery of all outputs in the coming year is likely to be disrupted by upcoming general elections in Zimbabwe. Planning for the above planned work has considered potential disruptions likely to be experience pre and post elections.

B.3 Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
The compelling reasons why this programme should continue include:
- Zimbabwe is one of the most climate-vulnerable countries in the world: it was ranked second most affected by severe climate-driven weather events in the Global Climate Risk Index 2021. The intensity and frequency of droughts and floods has increased in recent years, negatively affecting critical sectors of the economy including agriculture, water, energy, infrastructure, and industry.
- Zimbabwe’s vulnerability is a factor of climate sensitivities and limited adaptive capacity (IPCC, 2018). This emphasizes the importance of CAWEP in continuing to help in strengthening the adaptive capacity and resilience.
  [note] Intergovernmental Panel on Climate Change (IPCC), Annex I: Glossary, Global Warming of 1.5ºC.
- In the initial FCDO supported Adaptation Communication submitted to UNFCCC ahead of COP27, Zimbabwe listed the following priority support needs for adaptation: institutional support for meteorological service, climate resilient water infrastructure to support small–large scale irrigation, strengthening institutional arrangements and coordination on adaptation. All these align with CAWEP.
  [note] UNFCCC 27TH Conference of Parties held in Egypt
- It is helping to deliver the UK’s climate ambition as set out in the International Development Strategy (IDS) as well as the 2021 Integrated Review, and on the COP26 Glasgow Climate Pact commitment to support vulnerable countries to adapt to the effects of climate change. This includes addressing poor access to water and clean energy as key factors that undermine the potential for women and girls in poor communities to succeed.
- Overall, the programme continues to represent good value for money through its multiple use water and energy approach which is showing great potential and having an impact on other UK development priorities on girls’ education and health.

## C. DETAILED OUTPUT SCORING

Output Title	Developed climate resilient multiple use water and energy infrastructure
Output number:		1	Output Score:	A
Impact weighting (%):		40	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 No. of community multipurpose water & clean energy infrastructure developed/rehabilitated with special technical designs and features that respond to climate risks. Disaggregated by type (i) Solar Piped Water Systems (PWS) (ii) mini/micro grids, (iii) small dams (iv) Irrigation systems/networks	35 PWS	35 PWS
1.2 Proportion of functional water and renewable energy infrastructure	80%	100%
1.3 Proportion of water and renewable energy infrastructure with a community management structure and business model for maintenance	80%	100%

C.1 Briefly describe the output’s activities and provide supporting narrative for the score.
All key performance indicators under this output were met, resulting in the output scoring an A in this review. The main achievement being the successful completion of thirty-five solar powered piped water scheme in nine drought and flood prone districts, supporting 77,768 people to better adapt to effect of climate change through improved access to water for multiple uses including for drinking, small scale irrigation and livestock production. As result of CAWEP, community capacity to cope with effects of climate change is improving following programme interventions in developing sustainable water sources, water storage, water supply and demand management, use of solar technology and climate proofing of water and solar infrastructure. In the year under review, forty-nine community nutrition gardens, were established. Eight dip tanks and eighteen cattle troughs were also built. These are examples of what was achieved under this output that is helping people to better adapt to different climate shocks. Work under this output is also having a positive impact on education and health sectors, helping increase the programme impact and value for money. In Chiredzi district, CAWEP-supported solar powered piped water schemes have helped three schools to get registered as independent schools with the Ministry of Primary and Secondary education. Access to reliable and clean water is one of the key requirements for schools to get registered in Zimbabwe. Annex 1 provides a summary of beneficiary feedback following CAWEP interventions.
[note] Buhera, Mutare, Makoni, Mutasa, Gweru, Zaka, Chiredzi, Gutu, Chikomba
[note] Planned, designed, built, and operated in a way that anticipates, prepares for, and adapts to changing climate conditions and can also withstand, respond to, and recover rapidly from disruptions caused by these climate conditions.
[note] Nyavasikana, Manhekwe and Bilingwe Primary schools.

The functionality rate of piped water systems is 100%. However, given that the water systems have just been completed in the last seven months they need to be given more time to run and be tested technically.

Based on progress made in the past year on delivering successfully on all indicators and advanced preparations to accelerate delivery under this output, this review judges that the programme is on track to deliver end of programme targets by 2026.

C.1.1 Challenges
There have not been significant challenges that affected implementation of activities under this output. Delivery partners, UNICEF and UNDP had mitigation measures to address macro-economic challenges that could have negatively affected implementation of key activities under this output especially procurement of water and energy supply equipment and other services.

C.1.2 Describe any changes to this output during the past year, and any planned changes as a result of this review.
The output description remains the same. However, the following changes were made on output indicators in the past year. These changes do not have any negative implications on the programme.
1. Indicator 1.1 description changed to be clearer and more specific. This now refers to specific works the programme will deliver.
2. Indicator 1.2 was split into two, creating an additional output indicator 1.3. The main reason for this is to be able to track and put more support on measures the programme is doing to ensure sustainability.
3. Milestones/targets were adjusted following the conclusion of the feasibility study that provided clarity on the scope of works and people to be reached. As the programme engages more with programme sites and communities and upcoming elections in Zimbabwe, there could be changes in milestones for the year ahead.
C.1.3 Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

C.1.3.1 Recommendations from the previous AR
The previous AR recommended the following:
Recommendation 1:
Update the output description to reflect the work being delivered through UNICEF and results of the feasibility study. This include standardising the output indicators.
Progress:
This was achieved. The current results framework reflects this.
Recommendation 2:
Consider a no cost extension of up to three months given the likely disruption of works due to tropical cyclones. Targeted districts fall within the cyclone paths based on previous trajectories. At the time of this review, some of these districts experienced extreme weather conditions due to Tropical Storm Ana. This decision should be made by end of February 2022.
Progress:
This was achieved. A programme time extension was approved in July 2022.
C.1.3.2 Lessons learnt
The following are key lessons learnt under this output in the past year:
The piloting of the insurance policies for piped water schemes provided opportunities for strengthening the community-based management approach and building on sustainability of piped water schemes. This innovative approach is new in managing community water infrastructure in rural Zimbabwe. It is expected to have a positive impact on sustainability of water and energy systems. In the past, communities have always struggled to keep water systems functioning due to prohibitive cost of replacing essential parts of water and energy systems

Provision of water for multiple use is providing opportunities for building community resilience by supporting various livelihoods projects. The project ensured that water was not only provided for basic use but catered for other livelihoods needs – community nutritional gardens, dip tanks, cattle troughs. In addition to providing food for the households, proceeds from the nutritional gardens were also used in some cases to pay for school fees, as well as contributing towards operation and maintenance. Livestock is a source of wealth in the targeted districts. The CAWEP project ensured availability of water for dipping animals and cattle troughs for drinking, contributing to the wellbeing of the livestock, and retaining the household value and assets.
C.1.3.3 Recommendations for the year ahead
In the coming year, this review makes the following specific recommendations under this output.

1. Continue to support outstanding beneficiary communities to finalize insurance policies for piped water schemes already completed. (By June 2023). UNDP to scale up the insurance initiative, collaborating with other partners such as UNICEF to come up with a policy brief that could be used lobby for the adoption of this as a national approach to sustainability. (By December 2023)
2. Update milestones for the coming year in view of the risk around general elections. (By May 2023)
3. CAWEP should work up a plan and set aside resources to monitor thirty-five solar powered piped water systems installed in the past year. Monitoring will focus on functionality, aptitude of operation and maintenance structures put in place to keep then running and robustness of business models that have been put in place to help sustain these facilities. (By December 2023)

Output Title	Established/resuscitated community governance structures are effective in managing installed infrastructure.
Output number:		2	Output Score:	A+
Impact weighting (%):		30	Weighting revised since last AR?	Yes - Up

Indicator(s)	Milestone(s) for this review	Progress
2.1 No. of governance structures trained to operate, manage, and maintain installed infrastructure are operational. / Disaggregated by (i) community/ districts	35	35
2.2 %ge of people in community governance structures who are women	50%	70%
2.3 %ge of representative community governance structures engage effectively with both community and external stakeholders, including maintenance service providers. / Measured by No. of regular community & stakeholder meetings	60%	100%
2.4 %ge of the households that pay for water and/or power use/maintenance. / Disaggregated by (i) community	60%	80%
2.5 %ge of targeted communities with a functional income generation/Business model to finance operation and maintenance	50%	90%

C.2 Briefly describe the output’s activities and provide supporting narrative for the score.
This output is aimed at helping communities to be able to organise themselves and have strong, inclusive, and capable management structures that help to sustain built community water and energy infrastructure. In this review, four of the five indicators exceeded expectations with one meeting the target, resulting in the output being scored an A+. Besides meeting the targets on most indicators, other notable achievements in the past year are:
1. Fifteen CAWEP supported water committees being able to organise themselves and mobilized financial resources to pay for the yearly insurance premium for their water schemes. These premiums ranged from US$250 – US$350 per scheme, depending on the scope of the works. Each household contributes an average of US$2 per year towards the premiums which is affordable for most of the targeted households. This model is showing potential to help CAWEP deliver at good value for money if successful. This still needs to be tested in the coming year.
2. 80% of supported households being able to pay for water. This a key component of Zimbabwe’s Community Based Management systems (CBMS) and critical to support routine operation and maintenance of facilities and
3. 90% of supported water management committee have set up business models to fund the operations and maintenance of water systems. This includes paying tariffs and selling produce from established community gardens. However, the sustainability of these initiatives is yet to be tested. They need to be continuously assessed in the coming year.

C.2.1 Challenges
No major challenges experienced in implementing activities under this output. Lifting COVID-19 restrictions helped allowed implementing partners to engage fully with communities,

C.2.2 Describe any changes to this output during the past year, and any planned changes as a result of this review.
This output was fully developed in the past year, following the completion of the feasibility study and the programme component 1 (Adaptive & Flexible Water supply) that was delivered through UNICEF provided more clarity on targeted communities and scope of works. As a result, the main changes made on this out in the past year are:
1. Revising the output description, making it more specific and measurable. It previously read ‘Strengthened and self-financed community-based infrastructure management structures’ The former is now reflected in the indicators.
2. Five new indicators were added to this output mainly to be able track and account for essential factors that help community management structures to become more effective in managing water and energy infrastructure.
C.2.3 Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

C.2.3.1 Recommendations from the previous AR

Recommendation:
The feasibility study recommends that a portion of the CAWEP budget be allocated to support local production of agricultural produce, provide nutritional advice, technical support on productive use of renewable energy, to support women’s economic empowerment. This will ensure sustainability and success of the projects through enhanced community ownership and direct access & benefits to basic needs such as food and income. The programme should ensure and work with existing extension services. Local Government should be engaged to commit to complement this work by coordinating and providing extension services to local communities.
Progress:
This is still work in progress. Good progress is already happening on (i) engaging and working with government on coordination and providing extension services – Government departments are a key CAWEP delivery partner, and (ii) planning and funding training sessions to support productive use of renewable energy and water, women economic empowerment and access to markets.

C.2.3.2 Lessons learnt
Inclusion of vulnerable groups (elderly, youth, women and disabled) into local management committees ensured that voices of the vulnerable was heard. Leaving no one behind.

C.2.3.3 Recommendations for the year ahead
- To keep tracking the above recommendation from the previous AR as it has not been fully achieved yet.
- Track and understand possible barriers that could affect community capacity to pay for water and explore ways to support them.
Output Title	Enhanced Early Warning Systems (EWS), helping vulnerable communities to better anticipate, plan and respond to negative impacts of climate change and extreme weather events
Output number:		3	Output Score:	B
Impact weighting (%):		20	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
3.1 No. of districts/communities that receive EWS strengthening support from CAWEP. disaggregated by type of support e.g., Hardware (Equipment), Software (Training)	3	0
3.2 No. of people that regularly (monthly) receive and understand weather & climate information	50000	0

C.3 Briefly describe the output’s activities and provide supporting narrative for the score.
At this stage, CAWEP was expected to have set up EWS in three of the initial ten targeted districts. As a result, at least fifty thousand people were expected to be reached with accurate and reliable weather and climate information, helping them to adapt to climate change. However, due to delays in the procurement process, partly due to FCDO funds disbursement limits introduced midway through the year, these targets were not met, resulting in this output scoring a B. Nevertheless, at the time this review was conducted, there has been good emerging progress on delivering this output. In particular, the procurement of eighteen Automatic Weather Stations (AWS) to strengthen EWS. These will soon be installed in fourteen districts in Manicaland and Matabeleland North Provinces. Work on this output has been widely welcomed by senior government official as relevant. At the national programme launch, the Director in the Meteorological Services Department (MSD) acknowledged the unique and widely consultative approach the programme has taken to select appropriate interventions to deliver this output. Progress made in procuring AWS and dedicated government personnel from MSD to work on CAWEP, gives assurance the overall programme target will be met by the end of the programme.
[note] Integrated system of components that are used to measure, record, and often transmit weather parameters such as temperature, wind speed and direction, solar radiation, and precipitation. They are used to monitor weather phenomena for forecasting, climatology, and research. They are an integral part of EWS.

C.3.1 Describe any changes to this output during the past year, and any planned changes as a result of this review.
There were no changes on this output in the past year. In the coming year and later programme years, milestone targets for indicator 3.1 will increase from ten to eighteen districts. During the past year, following wide consultations with MSD and the Department of Agriculture and Extension Services (AGRITEX), there was scope to reach out to more districts than planned at a minimal cost, giving the programme good value for money on this output.

C.3.2 Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

C.3.3.1 Recommendations from the Previous Annual Review
There were no specific recommendations given on this output in the last AR. This is an output that was fully developed following the completion of the feasibility study that helped to inform the output, scope of work required to deliver the output and performance indicators.

C.3.2.2 Lessons Learnt
Key lessons learnt on this output in the past year are:
Full engagement of and joint working with key government department helps the programme to be more effective, achieving more at optimal cost and helps to achieve a sustainable outcome. This should continue in the coming years. This has helped the programme to target more districts and people than initially planned as explained in section C.3 above.
C.3.2.3 Recommendations for the year ahead
- Ensure the foundation work is continued and built on so that the programme catches up and achieves the targets for the coming year.
- Preparing for unforeseen shocks such as funding delays. Programme should build in flexibility to respond to such shocks while still able to deliver this output.
Output Title	Improved National Climate adaptation policies/Strategies/learning material supported/developed
Output number:		4	Output Score:	A
Impact weighting (%):		10	Weighting revised since last AR.	Yes - Up

Indicator(s)	Milestone(s) for this review	Progress
4.1 No. of policies or strategies developed/supported as a result of programme influence. Disaggregated by Type e.g., specific policy, strategy, learning	2	2
4.2 No. of policy briefs developed using evidence generated by the programme to influence upscaling or changes to different approached to climate adaptation/resilience	0	0

C.4 Briefly describe the output’s activities and provide supporting narrative for the score.
An A score is awarded to this output following the programme’s strong influence and support towards two national policy strategic pieces of work that are expected to improve the sustainability of climate resilient and multiple use water supply infrastructure in rural communities. In the past year CAWEP, through UNICEF, UNDP and the Government contributed significantly to the development of the national manual for ‘design, operation, and maintenance of Solar Powered Water Schemes’ (See Annex 2). The manual will guide the construction and sustainability of PWS. Secondly, work delivered under the CAWEP adaptive programming component through UNICEF is directly supporting the implementation of the National Climate Policy priorities on adaptation in the water sector. In the past year, CAWEP has contributed to the following Climate Policy actions:
[note] https://climatechange.org.zw/wp-content/uploads/2022/10/National-Climate-Policy.pdf

- Section 2.1.7 Ensure water sources for domestic consumption are within national standards radius of household reach.
- Section 2.1.8 Ensure children’s right to quality and safe drinking water to help them stay healthy is observed.
- Section 2.1.9 Ensure improved water supply for livestock and environment is in line with changing climate.
Other areas of the National Climate Policy that CAWEP will support in coming years include:
- 2.2.3 Undertake comprehensive analyses to understand barriers to adaptation to climate change, including human, institutional and financial barriers.
- Promote irrigation and water use efficiency in agriculture including adequate assessment of irrigation potential and irrigation demand under climate change.
- 2.2.9. Strengthen relevant early warning systems on cropping season quality, rangeland condition, droughts, floods, disease/pest outbreaks and wildlife movement in order to enhance farmer preparedness.
In the year under review, CAWEP has already been identified as a strategic programme that can help inform policy on climate adaptation through learning and building evidence. Having aligned to national adaptation priorities, CAWEP will in the coming year help to inform and support the implementation of the National Adaptation Plan (NAP) when finalised. This includes supporting national policy priorities on mobilising climate financing for adaptation, strengthening coordination and institutional capacity. Based on several policy support areas identified for the year ahead and subsequent years and strong government endorsement on this programme, CAWEP is on track to influence a positive contribution and improve the climate policy framework in Zimbabwe.

C.4.1 Describe any changes to this output during the past year, and any planned changes as a result of this review.
The only change to this output in the past year was the inclusion of specific policy areas the programme will support following the previous year’s Annual Review recommendation. More changes are expected in the coming year as the programme continues to engage more with policy work and learn more from implementation.

C.4.2 Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

C.4.2.1 Recommendations from the Previous Annual Review
The previous AR made the following recommendations.
Recommendation 1:
Identify and mention specific policies or strategies that could be influenced by delivering this programme. Indicators should also be updated accordingly. This review identifies the National Adaptation Plan (NAP) as one of the priority and relevant strategy CAWEP could engage with and influence the planning process and delivery. The programme team needs to work closely with the Government’s Climate Change Management Department to prioritise work that CAWEP can support. Explorations should continue to look at climate change mainstreaming in education, health, and agriculture sectors.
Progress:
This is achieved and now reflected in the logframe. The programme continues to engage the climate change management department, in particular the Chief Director on strategic policy issues that CAWEP can contribute to. CAWEP will be helping to strengthen district institutional capacity in mainstreaming climate adaptation in planning, approval, and delivery of projects at local level.

Recommendation 2:
Share findings and lessons learnt from the feasibility study with the government of Zimbabwe and present available opportunities from implementing CAWEP where they can learn from to improve the country’s climate change policy framework.

Progress:
This was achieved. The reports were shared widely with stakeholders and several meetings to discuss the findings were held and helped to shape programme work.

C.4.2.2 Lessons learnt
Please see section A.3.1 for the main lesson learnt under this output.

C.4.2.3 Recommendations for the year ahead
For the year ahead, this review recommends that FCDO and UNDP programme teams continue working with and engaging the government on critical policy issues to ensure a shared vision on building an enabling policy environment that helps to build community and institutional adaption and resilience. The review recommends regular policy discussions that track progress on this output. Scheduled programme meetings should be used to discuss this. CAWEP should provide support on the planned National Resilience Platform and be able to use as an opportunity to influence policy discussions.
## D: VALUE FOR MONEY

D.1 Key cost drivers and performance
In the past year, the cost drivers were on direct programme delivery costs including procurement of goods and services such as water supply, solar pumping, and AWS equipment. During the review, there were no observed variations on expected cost drivers. The programme is still operating within the agreed budget.

D.2 VfM performance compared to the original VfM proposition in the business case
The Business Case committed to assessing VfM during the life of the programme. It sets out clear VfM indicators for major costs drivers. CAWEP is still tracking VfM using these indicators. This review finds that the programme is on course to deliver at good value for money. This is based on the following achievements under each of FCDO VfM parameters:

D.2.1 Economy: CAWEP established ten (10) additional solar piped water schemes compared to the initially targeted 25 schemes. It reached more institutions (59 compared to initial 25 schools/ HCFs) and more people with basic water. This is a factor of working together with existing government institutions and communities, making savings on certain budget lines.

D.2.2 Efficiency: CAWEP has mitigated the potential risks from procurement of goods and services by allowing programme NGO partners to undertake the procurement, lowering the volume of procurement per partner, and spreading the risk across all partners. Regular monitoring of the prevailing exchange rates was done to safeguard exchange losses from global and domestic shocks, that could have potentially led to failure to achieve targets.

D.2.3 Effectiveness: Using the same budget, CAWEP achieved more than expected. A total of 77,768 people out of the initially targeted 53,600 people were reached with basic water services, including school children.

D.2.4 Equity: The project also mainstreamed gender and disability, prevention of sexual exploitation and abuse (PSEA) and accountability to affected populations. Piped water systems have improved access to water for people living with disabilities and school children. The project led to resumption of school feeding program in schools supported with basic water.

D.3 Assessment of whether the programme continues to represent value for money
The programme still presents good VfM. UNDP has provided co-financing to CAWEP by proposing £673,457 over the three-year life span. Additionally, the government contribution (cash/kind) to the project has been costed as £340,555.20. These have been unlocked by FCDO’s £12m commitment. Communities will also be expected to contribute in various ways. FCDO’s investment has unlocked additional finance from REF on Hakwata Mini grid. CAWEP will also be used to demonstrate approaches that can be replicated and leverage funding from sources such as the Green Climate Fund (GCF). CAWEP is supporting government policy to help attract private sector investment in water and renewable energy sectors and influence treasury resource allocation. The project sites will bring scale and provide evidence to encourage the government to replicate and adopt best practices.

In addition, the programme is still expected to deliver good VfM through providing sustainable access to long-term climate resilient and multiple use water and renewable energy infrastructure and improved EWS to an estimated 700,000 people – this is up from an initial 450,000 in the original business case. This target is conservative as does not take into consideration the multiplier effects of the EWS. Estimates on indirect reach indicate 3,237,778 individuals in both urban and rural areas. The benefit-cost ratio for the programme is therefore projected to be about £2.00: £1 which demonstrates the efficacy of the value for money strategy. UNDP report on savings when purchasing vehicles of about $3,000. Two vehicles were paid for at $48,579.50 against a budgeted 50 000 each.

E: RISK

E.1 Overview of risk management
Overall project risk rating is moderate and remains within FCDO’s risk appetite. The project has been delivered in line with FCDO Zimbabwe’s funding policy and so no UK funding is passed directly to the Government. No fraud incidents were reported during this reporting period. Both partners UNICEF and UNDP have developed detailed delivery chain mapping that regularly monitored. A due diligence assessment was conducted on UNDP. The findings and recommendations will be monitored for implementation. Table 2 below provides an update on how key risks were managed in the past year.

Table 2: Risk management update
Risk Type and Appetite	Risk description and mitigation actions
Strategy and Context / (Receptive & Moderate)	Risk: COVID 19 resulted in lockdowns and COVID-19 related restrictions in movements. / Mitigation: 1. UNICEF requested for an exceptional physical access space for partners to continue implementing COVID-19 pandemic response activities.
Policy and Programme Delivery / (Receptive & Moderate)	Risk: Delay in selection of main delivery partner and unknown budget level may result in shortening of the implementation period and can affect amount of CDEL spend at programme and portfolio level / Mitigation: / 1. Programme launched the call for proposal process and selected UNDP. 2) A no cost time extension moving project end date from November 2023 to up to 2026 was approved.
Financial and Fiduciary / (Cautious & Moderate)	Risk: Risks of financial exposure and abuse of project budgets by partners (contractors, NGOs, UN Staff) leading to funds misappropriation. / Mitigation: / 1. UNDP undertakes extensive supplier/contract checks. 2. Direct payment modality is being used where UNDP make the payments direct to the suppliers upon receiving requests with full support documents from the Government Partners.
Safeguarding / (Cautious & Moderate)	Risk: Programme activities causing negative environmental and social impact including land degradation, disruption of social norms and values and specific. Contractors and partner staff exploiting communities. / Mitigation: / 1. Conduct social & Environmental Impact assessments and design mitigation measures that are closely monitored. 2. UNDP to ensure contractors and their respective workers sign code of conduct on Sexual Exploitation and Abuse (SEA). 3.Communities and district stakeholders are trained on safeguarding.
Reputational / (Cautious & Moderate)	Risk: Politicisation of support which may exclude deserving and vulnerable people from participating in the project. / Mitigation: / 1. Ensure the selection is clear for all project participants at local and national levels. 2. Involve appropriate and diverse actors to ensure that decisions are made with clear rationale. 3. UNICEF ensured inclusion of vulnerable groups (elderly, youth, women and disabled) into local management committees ensured that voices of the vulnerable people were heard. 4. Branding of materials used by partners during the intervention. 5. CAWEP work continued to be amplified on FCDO, UNDP & UNICEF Social media platforms such as twitter and Facebook.

E.2 Key risks that will be monitored in the year ahead:
In the coming year, the programme will continue to monitor closely the above-mentioned risks on fiduciary/financial, safeguarding, and reputational. Given it is an election season in Zimbabwe in the coming year, the programme team will particularly track developments and work to ensure the programme is not negatively affected by risks related to politicisation of the programme, limited access to project sites and low participation of government staff on the projects. Other risks include:
Inflation - Delivery teams will continuously assess the purchasing power or cost of delivery and think through acceptable cost benchmarks and VFM indicators that inform the next appropriate action which could be suspending, postponing, or stopping certain activities or the whole programme.

Climate change & variability such as drought, floods, temperature increase affect the delivery of programme activities. The programme will continue to track this, working closely with the MSD and consulting UKMet.

E.3 Update on Partnership Principles
It remains UK policy that no UK aid should be under the management or direct control of the Government of Zimbabwe. The Partnership principles are reviewed regularly. A substantive review is being undertaken and expected to finalise by March 2023. FCDO’s contribution to the CAWEP programme is in line with this policy and no UK money is used to directly fund the Government of Zimbabwe.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

F.1 Programme Overview
The full Business Case value is £19,550,000. CAWEP utilizes funds categorized as International Climate Finance (ICF) which should be spent on capital outputs/inputs. The FCDO programme has disbursed £7m by the 31st of December 2022 which is 36% of the full programme budget. See below the components that relate to the 2023 Annual review.
[note] ICF is the UK’s financing that is committed to mitigating future climate change through supporting low-carbon development and to adapting and building resilience to the impacts of climate change now and in the future.

F.1.1 UNICEF Component 101 - Adaptive & Flexible Water supply, Value £2,500,000
Operation period: 19 July 2021 to 30th June 2022
The UNICEF partnership is delivered through a MOU. An Amendment was provided to UNICEF which extend the end date from 31st March 2022 to 30th June 2022. Implementing partners are Welthungerhilfe, CAFOD, Mercy Corps and Christian Care, Ministry of Lands, Agriculture, Fisheries, Water and Rural Resettlement, Department of Climate Change Management (CCMD) and the District Development Fund (DDF). FCDO disbursed funds to UNICEF in one tranche.

UNICEF has submitted the interim financial report for CAWEP which outlines that all funds provided by FCDO have been used (see table 3 below). FCDO has reviewed the report and now awaits receipt of the Certified Financial Statement from UNICEF by June/July 2023. This report will cover expenditure up to December 2022. The Final Certified Financial Statement for a grant that ended 30 June 2022 is prepared 18 months after grant expiry period, so FCDO expects it in December 2023.

Table 3: UNICEF full expenditure breakdown of £2.5m
Description	USD Currency Value	Utilisation Percentage
Programme Delivery Costs (plus staffing costs)	3,014,179.07	87.6
County Office Operating Costs	173,238.68	5.0
Indirect HQ Support Costs 8%	254,993.42	7.4
TOTALS	3,442,411.17	100.0

F.1.2 UNDP Component 103 - Community Water & Renewable Energy Infrastructure & Early Warning Systems (EWS), Value £12,000,000
Operation period: 1 August 2022 to 30 November 2025
UNDP will deliver this programme under the Direct Implementation Modality (DIM), implying they will deliver directly without downstream NGO partners but working very closely with government departments at national and Subnational level. FCDO has committed a budget to UNDP that is valued at £12m. UNDP and FCDO have agreed a detailed budget and workplan. The project’s budget is linked to the log-frame, activities, and outputs. This will ensure coherence and a logical flow between the budget, theories of change, log-frame and interventions being implemented.

UNDP has provided a quarterly narrative and finance reports. Disbursements to date for FY 22/23 total £3.6m (84%) of the planned annual budget £4.3m. By the time of this Annual Review, UNDP had recruited 4 key staff positions of Project Manager, 2 Project engineers and an M&E analyst confirmed to begin in January 2023.

UNDP will provide a certified financial statement within 6 months from the end of their Financial Year – usually July of each year. UNDP will continue to provide project specific reports:
1. Quarterly Narrative and Finance Utilisation Report
2. Cashflow Forecast Report
3. Comprehensive Finance report sections in the narrative reports.
4. Donor disbursement schedule.

F.2 Progress on partnership(s)
UNICEF provided strong coordination and collaboration with government stakeholders from central to district offices, with implementing partners, and contractors for services. At a community level Sub-Committees were engaged. In July 2022 UNICEF and FCDO were able to showcase to senior government officials physical and digital outputs and outcomes of the lengthy partnership in water and sanitation support to vulnerable communities.

The UNDP and FCDO partnership have expanded to now cover two programmes (ZRBF and CAWEP) that both cover support to climate adaptation and resilience. The partnership resulted in a successful High-Level launch of the CAWEP Project. It included Senior Government officials, Provincial heads of various government departments, FCDO, Heads of UN Agencies, and members of the media. Subsequent provincial launches are expected to take place in the second quarter.

F.3 Asset monitoring and control
No physical asset assurances required for UNICEF as the component did not procure assets but used its own assets. UNDP manages assets through the Asset Manager, Programme/Project Asset Focal Points, and Asset Verification Coordinator who conducts bi-annually asset verification for all programme/project management units. UNDP have on-going procurements for vehicles, furniture, and laptops but no large assets will be purchased. As per the Due Diligence Assessment and Framework agreements UNDP will provide assurance to FCDO on all asset procured with FCDO funds.

F.4 Governance and Accountability
The UNICEF and FCDO partnership had a strong delivery structure which enabled frequent engagement characterised by scheduled monthly meetings to discuss progress and risks. This monthly arrangement has also occurred for the UNDP component. For the UNDP component a programme Steering Committee (SC) will be established. It is the highest programme decision making body. It comprises of 5-7 voting member organisations drawn from FCDO, the Fund Manager (UNDP) and senior officials from key government ministries. Other donors that may support the programme will also sit in the SC. Beneficiaries are represented in the governance structure through carefully selected and trained technical and social committees. The first meeting for the SC will be in the first quarter of 2023.

Recommendation: UNDP and FCDO to ensure that findings of the UNDP-CAWEP Due Diligence Assessment are addressed. The DDA proposes quarterly review meetings. The first meeting is scheduled for March 2023.

Date of last narrative financial report	UNICEF – October 2022 / UNDP – January 2023	Date of last audited annual statement	UNICEF – June 2022 / UNDP – N/A expected July 2023

Annex 1: Beneficiary Feedback

Annex 2: National manual for ‘design, operation, and maintenance of Solar Powered Water Schemes

Annex 3 UNDP CAWEP Proposed Indicators

Proposed Economy Indicators:
1. Overhead costs to programme costs.
2. Unit cost of items procured. UNDP will track this indicator to assess how VFM was achieved in our procurement processes.
Proposed Efficiency Indicators:
1. Unit cost of delivering each climate adaptation intervention per beneficiary- Comparator costs will be established. Indicator will be measured and tracked annually and at evaluation.
2. ROI (Return on Investment) per intervention: This measures the efficiency of converting inputs into outputs. It is a comparison of costs and benefits per every investment made under the project. Will be measured at evaluation.
 Proposed Effectiveness Indicators:
1. Number of institutions with improved access to clean energy and potable water. Disaggregated by (i) community (M/H) (ii) type of institution
2. Number of people with improved access to clean energy. Disaggregated by (i) community (M/H) (ii) sex (iii) age (iv) disability
3. Number of people with improved access to potable water. Disaggregated by (i) community (M/H) (ii) sex (iii) age (iv) disability
4. % Of the community understand the EWS information as communicated
5. X% of planned land under irrigation
6. Irrigation infrastructure stoppages less than X%
Proposed Equity Indicators:
1. x% of the community governance structures are women. Disaggregated by (i) community (M/H)- outcome indicator 4.2
2. Number or % of women benefitting from CAWEP.
3. Number of People with Disabilities (PWDs) reached.