ADDENDUM TO BUSINESS CASE INCLUDING FOR BRIDGE FUNDING AND SCALE-UP COST EXTENSIONS

SUMMARY INFORMATION
Project Name	Climate Adaptation Water and Energy Infrastructure Programme (CAWEP)
Country or region targeted	Zimbabwe
Type of cost extension (if applicable)	Not Applicable
Original project budget	£19,550,000
Original projects start and end dates	10 November 2019 - 30 November 2023
Cost extension value (if applicable)	Not Applicable
New reduced budget (if applicable)	Not Applicable
New project end date (if applicable)	31 March 2026
Business Case Quest Document No.

INFORMATION
What is the project’s purpose?
Why is the Intervention needed? / Zimbabwe is one of the most climate-vulnerable countries in the world: it was ranked second most affected by severe climate-driven weather events in the Global Climate Risk Index 2021. This is despite being a small net emitter of greenhouse gases and not a major contributor to climate change. The intensity and frequency of droughts and floods has increased in recent years, negatively affecting critical sectors of the economy including agriculture, water, energy, infrastructure and industry. Some of the notable negative impacts of climate change in Zimbabwe include: / More people becoming food insecure due to droughts: 7.7 million people were food insecure in 2020, up from 4.1 million in 2016 (WFP). Around 38% of rural households are projected to be cereal insecure in 2022, up from 27% in 2021 (ZIMVAC, 2022). In addition, drought contributed to more outbreaks of livestock diseases, accounting for 61% of reported cattle deaths between 2015-2016. / Reduced hydro-power generation especially at Kariba Dam, the biggest power plant by installed capacity in Zimbabwe. Reduced rainfall worsens power shortages (of 8-12 hours a day) and severely hampers economic activity. / Loss of physical and productive infrastructure such as small, medium, and large dams, water and energy supply systems and transport networks. In March 2019, Tropical Cyclone Idai and the resultant flooding destroyed bridges, roads, telecommunications infrastructure, agricultural land, crops, livestock, and several buildings/houses estimated at US$2 billion. / Zimbabwe’s vulnerability is exacerbated by (i) lack of timely access to and dissemination of reliable weather and climate information, which reduces the ability of communities and government institutions to better anticipate and respond to climate and weather-related shocks, and (ii) lack of climate resilient community water and energy infrastructure in Zimbabwe, undermining communities’ ability to respond and reduce the impacts of climate change on livelihoods, clean water and energy and ability to access education and health services. The UK in Zimbabwe will help to reduce these negative impacts of climate change in targeted vulnerable communities through the Climate Adaptation Water and Energy Infrastructure Programme (CAWEP). / What will the programme do? / CAWEP works to strengthen the ability of vulnerable communities to withstand climate shocks. Through this programme FCDO is supporting the development of climate resilient water and renewable energy infrastructure in vulnerable communities of Zimbabwe to enable: (i) continued access to water for productive and household use, including during droughts and floods, and (ii) improved access to clean and affordable energy to support economic activities and ensure more sustainable livelihoods. CAWEP will also strengthen early warning systems (EWS) in vulnerable districts, enabling timely access to and use of weather & climate information to anticipate and respond to climate shocks. The programme will provide technical assistance to the government and other non-state actors to support the wider use of climate science in designing and delivering resilient water and energy infrastructure. Evidence generated through this programme will be used to influence climate policy reforms and support national climate adaptation plans. As such, it aims to build and demonstrate an understanding of what works and what challenges must be overcome to deliver resilient and sustainable outcomes. / How does it support UK priorities? / CAWEP is delivering on the UK’s climate ambition as set out in the recently launched International Development Strategy (IDS) as well as the 2021 Integrated Review, and on the COP26 Glasgow Climate Pact commitment to support vulnerable countries to adapt to the effects of climate change. This includes addressing poor access to water and clean energy as key factors that undermine the potential for women and girls in poor communities to succeed. We are using the programme to leverage policy on climate change and delivery of COP26 commitments. Building up to COP26, the UK supported Zimbabwe to deliver an ambitious Nationally Determined Contribution (NDCs) and to sign up to the Forest and Land Use Declaration, and committed to support Zimbabwe to meet its commitments in the National Adaptation Plan (NAP). CAWEP is directly in line with Government of Zimbabwe (GoZ) priorities on adaptation, which are: (i) Developing Climate Resilient Infrastructure, (ii) Strengthening EWS, (iii) Scaling up climate smart agriculture solutions and (iv) Developing resilient water resources management. On 28 March 2022, FCDO Zimbabwe had an all-stakeholder workshop where CAWEP received strong GoZ endorsement and support from other donors.
What is the objective of the cost extension or other changes?
A time extension of twenty-eight months (28) is needed to fully implement programme activities and ensure the outcomes are sustainable. The time extension is in response to developments that have taken place since the design phase. / The programme has experienced unforeseen and significant delays since inception, particularly due to the impact of COVID-19. Financial approval was granted by HM Treasury at the end of 2019, but the ensuing pandemic in 2020 had a severe impact on the UK’s economy and official development assistance (ODA) budget. This resulted in a suspension on spending through some programmes including CAWEP while a prioritisation and allocation process took place. Procurement resumed in September 2020 and a feasibility contract was signed with Pegasys in November 2020. In addition to this, other COVID-19 restrictions slowed down engagement with key stakeholders due to (i) remote working which was affected by connectivity challenges for most government stakeholders, (ii) illness and (iii) more deployments to respond to the pandemic. In addition, there was a long delay in securing a procurement specialist by the commercial unit. / As a result, the latest annual review recommended a time extension to enable smooth implementation of projects that came out of the feasibility study.
What is the additional and total support the UK will provide?
The total project value will remain at £19,550,000 and is categorised as 100% International Climate Finance (ICF). This is part of the UK’s global commitment to doubling climate finance and a key pillar of the UK effort to fight climate change in Zimbabwe. Specifically, the money will be spent on: / Developing climate resilient water and renewable energy infrastructure in rural districts exposed to the effects of climate change. / Strengthening the ability of communities to adapt and deal with the effects of extreme weather conditions by improving weather and climate forecasting, information dissemination and use. / Providing technical assistance (TA) to the government to support the creation of an enabling policy and regulatory environment that promotes investment in climate smart energy and water infrastructure. / Delivering TA to community based small and medium-sized enterprises involved in the installation and distribution of productive renewable energy infrastructure to promote sustainability. / Supporting learning, monitoring, and evaluation to influence climate policy and technical work, and / Developing markets for renewable energy infrastructure such as off-grid solar to avoid widespread use of diesel power.
What are the expected results?
CAWEP’s main aim is to help break the cycle of poverty in Zimbabwe through building climate resilience in vulnerable communities. Increasing frequency and intensity of climate shocks, mainly droughts and floods which are among the main drivers of extreme poverty in Zimbabwe, affecting access to water and clean energy for productive and domestic use. This has also affected community access to education and health services. CAWEP is designed to reduce future humanitarian needs and minimise the impact of climate shocks through improved access to sustainable water and clean energy for multiple uses – both household and productive/economic uses. These are essential services for building resilience and exiting poverty in Zimbabwe. / The programme will deliver sustainable access to long-term climate resilient and multiple use water and renewable energy infrastructure and improved EWS to an estimated 700,000 people – this is up from an initial 450,000 in the original business case. CAWEP will directly support 50 schools, 12 Health Care facilities and 5 irrigation schemes in 14 vulnerable and underserved rural districts. This will help them to adapt, preventing them from falling into extreme poverty due to the impacts of climate change by: / increasing household incomes through improved agricultural productivity and diversified livelihoods. / improving health, nutrition, and education outcomes through sustainable access to clean and reliable access to water and energy. / enhancing EWS, helping them to better anticipate, plan and respond to extreme weather events and negative impacts of climate change. / improving relevant policies in climate, water and renewable energy enabling and empowering the government to implement sustainable policies and programmes. / Achieving the above will (i) enhance community and institutional resilience to climate shocks; (ii) improve government capacity and approaches to planning and delivering climate resilient water and energy infrastructure projects; (iii) enable a policy environment that attracts private sector investment in water and renewable energy sectors; (iv) improve the mainstreaming of cross-cutting issues such as women, girls and disability in local development processes and (v) promote environmental sustainability through climate smart land and water use management and use of clean renewable energy.
What is the approach to implementation?
CAWEP has a clearly laid out approach to implementation which follows the five stages set out below: / Stage 1: Understanding & Scoping (By February 2022) / This stage was designed to consolidate and analyse available evidence to determine the technical, financial, social, and environmental feasibility of climate adaptation programme through establishing community-owned and managed multiple use water and renewable energy infrastructure and improving access and use of weather and climate information services. This process is now complete. The findings of the feasibility study are being used to shape the full programme implementation including specific programme deliverables (Results Framework), identifying the right delivery partner, and identifying areas of collaboration with the government and other donors. / Stage 2: Contracting & Mobilising (By September 2022) / Following an evaluation process of programme delivery proposals from a range of delivery partners, UNDP came out the best. FCDO will sign a Memorandum of Agreement with UNDP to be the main programme delivery partner and fund manager. FCDO will disburse funding to UNDP to deliver the expected results. UNDP will mobilise and work with all key stakeholders including government, NGOs, and the private sector to come up with an inclusive implementation plan. FCDO will closely monitor the partner engagement process, ensuring the UK funding policy in Zimbabwe is adhered to. This includes ensuring CAWEP funding is not passed directly to the Government of Zimbabwe unless approved by ministers. UNDP will at this stage do a lot of procurement for goods and services required to deliver the programme. / Stage 3: Delivery of projects (By November 2025) / This is where identified project activities are implemented. UNDP will work with NGOs and private companies to deliver the agreed outputs, getting policy and technical support from relevant government ministries. Given the imbalances that constrain women and girls’ ability to adapt to climate related stresses, CAWEP will ensure delivery process provides equal access for women and girls to productive and domestic water and energy infrastructure. A Gender Equity & Social Inclusion (GESI) Strategy has already been developed for this programme and all delivery partners are expected to use it throughout the implementation period. / Environmental and social safeguards will be an integral part of programme delivery, ensuring potential harm arising from the project on the environment, local communities, social norms, and institutions is detected and effective mitigation measures are identified and implemented. / Delivery partners will take the following specific measures to minimise environmental and social harm because of project activities: / Carry out environmental impact assessments (EIAs) before developing any infrastructure to assess the impact of on the environment and social norms and provide sustainable mitigation measures. / Explore the opportunity to use the GESI study to identify the project impact on the most vulnerable in targeted communities including women and girls and ensure that the project does not inflict more harm to them but ensure an equitable share of project benefits. / Ensure all downstream delivery partners, including contractors, have safeguarding policies in place that they will use effectively in delivering CAWEP. / The Global Terrorism Index rates Zimbabwe as being at the lowest impact of terrorism. CAWEP is at extremely low risk of funding terrorism. / Stage 4: Monitoring, Learning & Evaluation (Ongoing) / CAWEP will have robust monitoring and learning systems that will be used throughout the programme cycle to enhance delivery and lesson learning. FCDO will ensure the programme has: (i) a strong results framework that has clear and measurable key performance indicators at outcome and output level that help in tracking progress and identifying policy, social and technical barriers, or opportunities the programme needs to address, and (ii) learning platforms that enable efficient data collection, analysis, and dissemination to all stakeholders in the most appropriate formats, including digital platforms. / FCDO will ensure that delivery partners have strong monitoring and learning systems that include frequent field visits and comprehensive stakeholder and policy engagement. The FCDO programme team will visit project sites every quarter to track progress and learn. The team will also use the annual reviews process engage with communities, government, and other partners. Given the programme has a significant policy influencing component, CAWEP will ensure that the delivery partner builds in an evidence documentation hub where all good practices/learning are documented. The expectation is these will lead into developing policy briefs and recommendations that the programme will share with government and key stakeholders. / Given the dynamic operating context characterised by a challenging economic environment and upcoming general elections, the programme will have a robust risk monitoring system with strong mitigation measures that minimise the impact on the programme. / Stage 5: Closure (By February 2026) / A Programme completion Review (PCR) will be undertaken at the end of the implementation period. This will look at the extent to which the programme delivered its outcomes and measures put in place to sustain these outcomes, and key lessons learned and recommendations for future policy and programme implementation.
Describe any key changes to the original business case including the theory of change or new evidence from ongoing monitoring, evaluation or learning work?
The main changes to the original Business Case are: / Extending the implementation period by twenty-eight months. The new end date will be March 2026. / Increase in number of beneficiaries targeted from 450,000 to over 700,000. This is informed by the findings of the feasibility study. The early warning system component is expected to help the programme to reach out to more people especially in Manicaland Province. / The programme Theory of Change (ToC) has not changed from what was originally proposed in the original Business Case. The programme is still expected to deliver the same outcomes as originally intended. The programme feasibility study, which was completed in February 2022, has helped to shape, and identify key activities and outputs needed to deliver the expected outcomes and impact. / At the initial programme design stage, the programme identified AfDB as the main delivery partner. This was reflected in the original Business Case. However, this is now changing. UNDP will be the main implementing partner and fund manager following a recent competitive bidding process in which they demonstrated the most suitable experience and capability to deliver CAWEP versus AfDB and other bidders. / AfDB does not currently have a readily available delivery mechanism in country which would result in a prolonged programme preparation phase before implementation can start. At the design stage, AfDB assured the FCDO that CAWEP was going to be delivered through the Zimbabwe Multi Donor Fund (ZIMFUND). However, ZIMFUND’s mandate was not renewed. As an alternative, AfDB proposed to deliver CAWEP through the Africa Water Facility (AWF). The Africa Water Facility (AWF) is the bank’s special fund established to provide grants, mobilise investment financing, and offer expert technical assistance to support the preparation and implementation of innovative water and sanitation projects throughout Africa. However, this is not a viable option considering the lack of country presence and the amount of time it takes to mobilise a programme delivery team and establish relationships with key stakeholders including the Government of Zimbabwe. It is against this context that an open competitive call for proposals issued was undertaken in which UNDP was successful.
[note] The focus is on supporting the development of community water and energy infrastructure for productive uses such as irrigation to support economic activity and for consumption enabling health and education outcomes by keeping more children in school.
[note] 2022 Global Terrorism Index - Global Terrorism Index 2022 - World | ReliefWeb
[note] Multi Donor Trust Fund set up in Zimbabwe in 2010 to support emergency rehabilitation of emergency and power infrastructure in selected urban areas. ZimFund was managed by AfDB