Annual Review Template

Title: Green Climate Fund First Replenishment
Programme Value £ (full life): 1,440,000,000.00		Review date: 25/09/2022
Programme Code: [AMP ID#] 300856	AMP start date: 25/09/2020	AMP end date: 31/12/2027

Summary of Programme Performance
Year	2021	2022
Overall Output Score	A	A
Risk Rating	Major	Major

DevTracker Link to Business Case:	DevTracker Programme GB-GOV-1-300856 Documents (fcdo.gov.uk)
DevTracker Link to results framework:	DevTracker Programme GB-GOV-1-300856 Documents (fcdo.gov.uk)

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme [1-2 paragraphs]

The Green Climate Fund (GCF) is a multilateral climate fund, commissioned under the UN Framework Convention on Climate Change (UNFCCC) in 2010 as the principal dedicated multilateral vehicle to support low carbon and climate-resilient development in developing countries. The Fund became operational in 2015 and since then has committed over $10bn to climate projects in developing countries. The UK has committed £1.44bn for the current ‘GCF1’ replenishment period (2020-23), making the UK the top donor to the Fund (the total amount pledged for GCF1 is around $10bn).

The objective of GCF is to promote paradigm shifts towards low-emission and climate-resilient development pathways by providing support to developing countries to limit or reduce their greenhouse gas emissions and to adapt to the impacts of climate change. This will help vulnerable people cope with the impacts of climate change and, through reducing emissions, help slow down the rate of climate change and reduce the severity of its impacts. The GCF aims to have a balanced portfolio, with half of its funding supporting low carbon growth (mitigation) and half building climate resilience (adaptation), with at least 50% of the adaptation funding allocated to particularly vulnerable countries (and a target to meet or exceed the Initial Resource Mobilization [IRM, 2015-19] phase result of 69%) including Least Developed Countries (LDCs), Small Island Developing States (SIDS) and African States. GCF has a dedicated Private Sector Facility to promote private sector partnerships and leverage private finance for climate action. The UK sits on the GCF Board, which has oversight of the GCF’s strategic direction and programming, and through our £1.44bn contribution to GCF1 we expect to achieve the following:

Outputs:
GCF raises its portfolio performance and its effectiveness as a financial mechanism to meet developing country needs, channelling climate finance at scale to high quality climate projects in developing countries
Progress is achieved in priority policy areas, including to increase value for money (VfM), strengthen safeguards and improve the functioning of the Board.
[note] Value for money of HMG ODA programmes is assessed against FCDO’s four Es framework, comprised of economy, efficiency, effectiveness, and equity considerations

Outcomes:
GCF demonstrates increased effectiveness in achieving results as an integral part of the multilateral system, contributing to implementation of the Paris Agreement through its ability to deliver results at scale, measured through the indicators of:
- Tonnes of carbon dioxide equivalent (CO2e) emissions (cumulative) mitigated through approved GCF projects, attributable to the UK contribution
- Number of direct and indirect beneficiaries (cumulative) of GCF support through approved projects, attributable to the UK contribution, to build resilience.

Impact:
Increase in developing countries implementing high ambition, low-carbon, climate-resilient development pathways, consistent with the goals of the Paris Agreement (as reflected in countries’ Nationally Determined Contributions and National Adaptation Plans).

Summary supporting narrative for the overall score in this review [1-2 paragraphs]
This reporting year continued to be a period of uncertainty and constraint caused by the COVID-19 pandemic. The GCF Board, Secretariat and agencies all had to adjust to deal with these constraints. But this reporting year was also one in which the GCF made significant progress, with policy development picking up in particular once the Board returned to ‘in-person’ meetings from May 2022. Overall we assess good progress has been made both on programming, with $2bn committed to new projects during this reporting year; and on policy, with a number of new policies adopted, including to further simplify project approvals and for more strategic engagement with the private sector.
On programming, the GCF committed a total of $2bn to 23 new projects in the course of the year, taking the overall portfolio to 200 projects with a total of $10.8bn of GCF funding and $30bn of co-financing mobilised. The portfolio remains balanced between mitigation and adaptation. Of funding allocated to adaptation, 64% is committed to the most vulnerable countries, including LDCs, SIDS and African States (considerably above the minimum 50% “floor” that was agreed for the targeting of adaptation funding to these countries, but not yet at the 69% target for the GCF1 replenishment period). The share of the portfolio invested in private sector programmes rose from 33% last year to 35% (as at Sept 2022) and is on track to meet the target for this period. Developing countries’ demand for GCF funding remains high, with a project pipeline of over $20bn and demand set to significantly outstrip supply for the foreseeable future.
GCF’s network of accredited implementing agencies has remained steady this year (113 entities in total with 71 direct access entities). This reflects a focus on re-accreditation of previously accredited entities, as entities reach the end of their 5-year accreditation term, rather than accreditation of new entities. However, it remains a concern (for developing countries in particular) that 78% of the portfolio (by value) is being administered through international access entities. Efforts to address this are ongoing in the coming year, including support for capacity building through the GCF’s ‘readiness’ programme.
In terms of efficiency, the average time from project appraisal, through Board approval to first disbursement has reduced from 26 months in 2018 to 12 months in 2021. Approval times for readiness proposals are also down, averaging 177 days in 2021 (19% reduction from 2018). The number of GCF projects moving straight from approval to implementation continues to grow.
On policy, challenges remained in the first half of the reporting year. However, with the easing of COVID-19 constraints and a return to in-person Board meetings (in May and July 2022) the Board was able to approve a number of new policies that, when implemented, will help improve developing countries’ access to GCF funding and increase the impact of projects on the ground. Notable amongst these were the approval of an enhanced Simplified Approvals Process, a new Private Sector Strategy, and policies on GCF’s support to adaptation and on ‘climate rationale’.
We continue to hear concerns from developing countries that GCF funding is hard to access, and we are working with colleagues to address key bottlenecks and identify options for improvement. We are continuing to work on these issues in the GCF1 period and in our work to shape GCF’s new Updated Strategic Plan (USP2) for the next replenishment period.
This year also saw GCF launch the next replenishment process (for the ‘GCF2’ period – 2024-27). Our efforts in the coming year will be focused on (i) further progress on programming and policy to enhance access and impact before the end of the current GCF1 period (2020-23) and (ii) developing and seeking Board agreement to a new Updated Strategic Plan (USP2) for GCF2 that reflects UK priorities.

The overall output score is ‘A ‘, based on the component output scoring set out below. The overall risk rating (major) is unchanged.

Table 1: Summary of output scores

Output	Weighting	Output score	Risk rating
Output 1 / During GCF1, GCF raises its portfolio performance and its effectiveness as a financial mechanism to meet developing country needs	50%	A	Major
Output 2 / Reform of policy priorities achieved during GCF1, including to increase VfM, strengthen safeguards and improve the functioning of the Board.	50%	A	Major
Overall output score		A	Major

Major lessons and recommendations for the year ahead [1/2 page]

Key priorities for the year ahead include:
- Maintain UK efforts to improve access to GCF funds, impact of GCF investments, and mobilisation of co-financing
- Seek Board approval of a new Accreditation Strategy, to promote accreditation of the right organisations needed to deliver GCF’s mandate
- Push for greater coherence and complementarity of GCF’s work with other climate funds, building on work already ongoing between GCF and the Global Environment Facility (GEF)
- Continue to focus on implementation, achieving - and measuring - results on the ground
- Ahead of the next replenishment (GCF2) work with like-minded countries and others to (i) build alliances around key UK priorities and (ii) push for their inclusion in GCF’s Updated Strategic Plan for GCF2 (‘USP2’ – which is being worked on over the next 12 months)
- Continue working closely with GCF’s Private Sector Facility to support effective implementation of the new Private Sector Strategy.
- Review the logframe well ahead of the next AR to consider, inter alia, updates to future milestones required in light of the Board’s updated workplan.

B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

The Theory of Change (ToC) diagram below was developed as part of the Business Case for our 2020-23 contribution to GCF.

The ToC sets out how the GCF seeks to help countries move to low-carbon, climate resilient development pathways, including through projects designed to drive a broader shift towards climate-smart investments. The outcome that the GCF seeks to deliver is a rapid scaling up and replication of successful approaches to addressing climate change (indicated primarily through tonnes of CO2 emissions avoided and the number of people made more resilient to climate change). The impact that this feeds into has many facets: sustainable development results on the ground; support for developing countries to deliver and, over time, the enhancement of their commitments on greenhouse gas emissions reductions, thereby meeting or exceeding their national climate plans (Nationally Determined Contributions), a central element for implementing the Paris Agreement; achieving a transformation in the volume of climate finance and developing countries’ access to it; and better equipping climate finance institutions collectively to manage climate impacts. We consider the ToC still to be valid.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]
As shown in the table below, the programme is on track to meet expected outcomes identified in the logframe that accompanies the Business Case for our 2020-23 contribution to the GCF.
The expected outcome of the programme is that the GCF demonstrates increased effectiveness in achieving results as an integral part of the multilateral system, contributing to implementation of the Paris Agreement. Three key outcome indicators were identified in the logframe. On outcome indicator 1, the GCF has exceeded the 2022 milestone by approving projects that are expected to avoid a cumulative anticipated total of 2.1bn tonnes of carbon dioxide (CO2) equivalent emissions over the project lifetimes. On outcome indicator 2, GCF projects approved to date are expected to provide 637m people with increased resilience. On outcome indicator 3, the GCF exceeded the 2022 milestone on co-finance (cumulative) mobilised to scale up successful, high-potential, climate-compatible investments, including the milestones on public and private sector co-finance mobilised.

Progress towards Outcomes

	Outcome Indicator	2022 milestone – expected results	GCF progress in achieving outcome
1.	Cumulative total number of tonnes of CO2 equivalent emissions avoided as a result of GCF projects	2.01bn	2.10bn tCO2eq avoided (based on forecasts)
2.	Number of people with increased resilience resulting from GCF projects, disaggregated by sex (cumulative from IRM and GCF1 period.)	620m female proportion of projects’ beneficiaries: 48% on average	637m / Female proportion of projects’ beneficiaries: 49% on average
3.	Co-finance (cumulative) mobilised to scale up successful, high-potential, climate-compatible investments. (i) public (ii) private	$28.6bn co-finance / $16.1bn public / $12.5bn private.	$29.4bn co-finance: / $16.3bn public; / $13.1bn private

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

Based on the above (and the progress against outputs detailed in Section C), there is good evidence that the programme is making progress against expected milestones and should continue, not least as progress and performance in the past year has been in the context of ongoing constraints caused by the global COVID pandemic. Progress against outcomes is sufficient and the ToC remains valid; and now use of the GCF’s new Integrated Results Management Framework has started, we should be better able to assess and measure actual impact and progress in future. However, to reach its full potential there are still areas where the GCF needs to make progress in the remainder of the GCF1 period, in line with commitments set out in GCF’s Updated Strategic Plan (USP) for 2020-23. Working with others, we will continue to press for these improvements, in particular to (i) promote better access to climate finance for developing countries, including meeting the 69% target for adaptation funding to the most vulnerable countries for the 2020-23 period (currently at 64% so not being met), (ii) support high impact projects to help people on the ground, and (iii) maximise the mobilisation of private finance for climate action.

C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	During GCF1, GCF raises its portfolio performance and its effectiveness as a financial mechanism to meet developing country needs
Output number:		1	Output Score:	A
Impact weighting (%):		50%	Weighting revised since last AR?	Yes (was 60%)

Indicator(s)	Milestone(s) for this review	Progress
Cumulative total value of GCF projects under (i) implementation and (ii) disbursement (to AEs)	$8.4bn under implementation $3.2-3.5bn disbursed	Substantially did not meet expectations: As of July 2022, out of $10.8bn that has been approved in GCF funding, $7.6bn is currently under implementation; with $2.7bn disbursed. Although an improvement from 2021 milestone, ($5.8bn under implementation), this is considerably below the secretariat’s projected milestone for this year.
% of GCF funding allocated to (i) mitigation and (ii) adaptation projects.	50% of funding in GE terms allocated to Adaptation.	Met expectations: As of July 2022, 50% of approved GCF funds in Grant Equivalent (GE) terms has been allocated for adaptation projects. After a slight dip in 2021, to 47.2%, a strong pipeline of adaption proposals coming to the Board in 2022 has ensured that the target of maintaining 50% adaptation funding, has again been achieved.
% of adaptation funding allocated to the most vulnerable countries, including Small Island Developing States (SIDS), Least Developed Countries (LDCs) and African States.	At least 69% of adaptation funding allocated to the most vulnerable countries.	Moderately did not meet expectations: As of July 2022, 64.1% of adaptation funding was allocated to SIDS, LDCs and African States. This shows a slight dip from 2021 achieved result of 66.4% and baseline IRM target of 69%. Improvement will be needed in 2023 to maintain the overall programme cycle target of 69% for GCF1.
Private Sector engagement: (i) % of GCF investment through Private Sector Facility, and (ii) private sector co-financing ratio	(i) 16-20% of the portfolio in GE terms / (ii) Private sector co-financing 1:3-1:3.3	Met expectations: As of July 2022, 17% of GCF projects in grant equivalent terms have been delivered through the Fund’s private sector facility. Additionally, the private sector co-financing ratio of 1:3.3 also meets the milestone target for this review.
Funding Proposals approved: (i) by $ value and (ii) by number.	10.58bn committed to 200 projects	Met expectations: As of July 2022, a total of $10.8bn of GCF funding has been committed to 200 projects demonstrating a good level of programming during the reporting period (up from $8.8bn in 2021, and $6.3 as the current cycle’s baseline).
Readiness activities approved: (i) by number and (ii) by $ value.	491 projects / $342.5m	Substantially exceeded expectations: As of July 2022, 600 readiness requests have been approved, worth $423.5m. This includes 82 grants for adaptation planning and 508 grants for other readiness support. This shows a significant improvement against the baseline and milestone 1 (2021) targets.
Cumulative number of implementing entities accredited, including direct access entities	113 AEs, including 72 DAEs	Met expectations: As of July 2022, 113 Entities have been accredited, including 71 Direct access entities.

Overview

The GCF has continued to maintain a good level of programming during this review period, including approving $1.2bn of projects at the Board meeting just before COP26. This large volume of approvals meant that the Fund’s commitment authority was lower for subsequent Board meetings – and subsequently lower volumes of projects could be approved. However, throughout the review period, the GCF still retained momentum in attracting scalable and large projects, further mobilising more funds. Overall, from September 2021 to July 2022, 23 projects were approved worth $2bn and mobilising a further $5bn. The project pipeline at ~$20bn indicates that demand for GCF resources remains high – and will exceed available funds for the foreseeable future. Project approvals this year contribute to the current cumulative total of 200 projects, worth $10.8bn in GCF funds. Additionally, the GCF reached a milestone of total assets under management at $40.2bn, having mobilised $29.4bn from other public and private sector entities.

In 2022, 163 projects are now under implementation worth $7.6bn in GCF funding. Although this did not meet the milestone target, implementation rates have seen considerable gains from the previous year, with over $2bn more in the implementation stage compared to 2021. While amounts under implementation and disbursed did not meet our milestone targets, the GCF Secretariat has explained that this is due not to low implementation/disbursement rates but to our milestone being based on the Secretariat’s projections for the end of 2022 (rather than September 2022, which is the end of our reporting period). We will ensure future milestones for this indicator are aligned with our reporting period.

The portfolio of funded activities under implementation has grown by over 100 per cent from $3.5bn (75 projects) in 2019 to $7.6bn (163 projects) in 2022. Additionally, the total amount of co-financing mobilised for the portfolio under implementation amounted to $11.5bn with the private sector leveraging the largest proportion of co-financing. This represents a considerable improvement in the GCF’s implementation rates.

The GCF’s portfolio continues to reflect a good geographic balance and reflects the Fund’s emphasis on providing support for LDCs, SIDS, and African States. The portfolio now has 84 projects in African countries, 84 in the Asia-Pacific region, 55 in Latin America and the Caribbean countries, and 12 in Eastern Europe. In line with its focus on supporting the most vulnerable countries to cope with the effects of climate change, African states, LDCs and SIDS now account for $3.8bn, $3bn, and $1.3bn of the GCF funds committed respectively.

Accreditation and Direct Access

The number of accredited implementing entities is similar to 2021. This is because, due to the limited capacity of the Secretariat to review new applications, the large number of already accredited entities (AEs), and the time limit on GCF accreditation (which expires after 5 years), the Secretariat has been focused on the re-accreditation of AEs and improving the Fund’s utilisation of Direct Access Entities (DAEs). This is because, despite there being 71 Direct access entities out of 113 AEs, 78% of GCF funds are still being channelled through International Access Entities (IAEs). This highlights the need to focus on the support and improvement of access for the current roster of AEs.

Readiness funding is deployed to strengthen the Fund’s DAEs. As of July 2022 the Secretariat had approved 600 readiness requests for a total value of $423.5m (more detail below).

This review period has seen 15 re-accreditations of accredited entities but only 1 new accreditation. During the approval of re-accredited entities, one focus has been on ensuring the alignment with Paris Agreement goals, particularly on aligning financial flows (article 2.1c of the Paris Agreement).

Continued efforts in improving accreditation support include the adoption of the Fund’s Updated Accreditation Framework, aimed at streamlining support and access, with a further accreditation strategy due to be approved in 2023. With this pivot towards improving the utilisation and supporting the current roster of AEs, we will re-consider how we continue to measure progress of indicator 1.7.

Readiness
The GCF has exceeded expectations regarding its readiness support with the Secretariat having approved 600 readiness requests for a total value of $423.5m, including 84 grants for adaptation planning and 508 grants for other readiness support (including 19 multi-country grants). As of July 2022, at least 489 grants have been disbursed, totalling $222.5m. 86 grants with total expenditure of $15.83m have been completed under other readiness support; this involves 31 grants for support to NDA strengthening, including country programming; 9 grants for support to strategic frameworks; and 46 grants for support for DAEs.

The GCF’s Independent Evaluation Unit (IEU) published an evaluation of the Readiness and Preparatory Support Programme (RPSP) in 2020. Overall, the IEU report states that there has been some success in supporting DAEs and the RPSP has been effective in organising information sharing events that have enabled engagement with GCF. However, it found that support for DAEs is yet to translate into significant progress and it is unclear whether RPSP financial or capacity building support is sufficient to achieve this objective. The RPSP has provided support to countries identifying and nominating candidates for accreditation but has been less effective in moving candidates through basic accreditation.

Africa still has the highest proportion of regional distribution with 32%, followed by Asia-Pacific 31%, Latin America and the Caribbean (LAC) at 30% and Eastern Europe and Central Asia (EECA) at 6%. 148 countries have established NDAs (National Designated Authorities) to the GCF and 141 of those (developing countries) have approved readiness requests.

This review period has shown the extent to which the GCF is continuing to provide a good level of readiness and preparatory support for developing countries. It has emphasised supporting country-driven initiatives in LDCs, SIDS and African countries to strengthen their institutional capacities, governance mechanisms, planning and programming frameworks towards a transformational long-term climate action agenda. However, the programme could be strengthened, including by adopting recommendations from the IEU review.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

GCF funding proposals are reviewed by FCDO and BEIS analysts and commercial advisors on a project-by-project basis before each Board meeting, to ensure projects deliver good potential VfM. Therefore, the economy of this output is ensured at the project level with scrutiny of project costs and planned expenditure being part of the project approval process. Costs are required to be clearly separated and justified, and fees paid to entities are comparable to other similar institutions.

Approved projects give an indication of the GCF’s effectiveness, in particular the ability of the GCF to lever the resources of others and incentivise private sector investments at scale. The 200 funding proposals approved so far, for a total GCF funding of USD $10.8bn, have enabled co-financing of USD $29.4bn from other contributors, of which $16.3bn is public finance and $13.1bn private finance. This indicates good leverage ratios compared to other ICF investments (higher than at the previous AR), and strong VfM. However, fuller implementation of the new Integrated Results Management Framework (IRMF) is needed across the portfolio for fuller achieved/actual cost-effectiveness metrics, such as abatement and abatement costs, to be known.

In terms of efficiency, disbursements (now at $2.7bn) have been made for $7.6bn worth of projects under implementation (out of the total $10.8bn portfolio). This means the amount disbursed as a proportion of the portfolio under implementation is higher than at the time of the last AR.

As noted in the Business Case, directing a greater share of GCF funding to the Private Sector Facility and the most vulnerable countries, as well as introducing a new programming modality that targets priority sectors or countries/regions, would increase effectiveness and equity for this output. At least 50% of the GCF’s adaptation funds (i.e. at least 25% of GCF’s total funding when factoring in the 50/50 split between adaptation and mitigation spend) are earmarked to support resilience in the poorest and most vulnerable countries –SIDS, LDCs and African States. In practice, the GCF is exceeding this floor, demonstrating good VfM in terms of equity. For the GCF1 period GCF is aiming for a greater proportion of funds to reach the most vulnerable countries (69% of GCF’s adaptation funding) and is currently behind on this target (64%).

GCF’s rate of programming has decreased over this review period compared to the previous year, with 19 projects approved (compared to 35 in the last period). However, this was due to GCF effectively utilising all of its commitment authority (funds available to approve projects) ahead of COP26 and therefore having less funding available for projects in the first half of 2022 (rather than being a reflection of decreased efficiency in preparing/approving projects). As project pipeline (‘demand’) is anticipated to exceed commitment authority (‘supply’) for the foreseeable future, availability of funds will remain the limiting factor determining the rate of project approval.

The programme is considered to represent good VfM and utilises its comparative advantage in providing support to all developing countries on suitable financial terms as set out in the Business Case.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

This is the second Annual Review for the GCF1 replenishment period covered by the Business Case for the UK’s £1.44bn contribution for 2020-23. The logframe for this period includes output indicators reflecting UK priorities outlined in the business case. Based on recommendations from the previous AR we have changed the weighting of outputs 1 and 2 from 60-40, to 50-50. This is to better reflect our high expectations for the programme, and the importance of the policy agenda (Output 2). We have also revised targets for September 2022 in line with updated projections that were sent by the GCF secretariat in February 2022.

Following the findings of this AR, we will consider changing indicator 1.7 (accreditation) to better reflect current priorities of the fund. i.e., potentially also measuring percentage of GCF funds being channelled through DAEs and GCF’s success at building support for DAEs.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

In the year ahead we will continue to push for progress on the indicators within this output, in line with UK priorities as set out in our Business Case. We will revisit the logframe and assess the appropriateness of future milestones.

A continued key recommendation is improving the accessibility, availability, and efficiency of climate finance, including GCF resources. Specific recommendations include:

Seek Board approval of a new Accreditation Strategy, to promote accreditation of the right organisations needed to deliver GCF’s mandate
- Continue to focus on implementation, achieving - and measuring - results on the ground, including through implementation of the new Integrated Results Management Framework
- Better understand how readiness funds are supporting direct access entities, and push for implementation of IEU’s recommendations to improve the impact of the readiness programme
Continue working closely with GCF’s Private Sector Facility to support effective implementation of the new Private Sector Strategy.

Output Title	Reform of policy priorities achieved during GCF1, including to increase VfM, strengthen safeguards and improve the functioning of the Board.
Output number:		2	Output Score:	A
Impact weighting (%):		50%	Weighting revised since last AR?	Yes (was 40%)

Indicator(s)	Milestone	Progress
Policies adopted/updated and/ or sufficient progress made with implementation to improve value for money and programme management.	Possible milestone: Further development of the Simplified Approval Process •Review and updated readiness strategy and workplan for 2022-23, including funding allocation •Policy on concessionality •Review of RfPs and funding allocations •Private sector strategy and review of PSF modalities •Policy on programmatic approaches	Met expectations: / The GCF approved the adoption of a number of policies including an enhanced simplified approval process (SAP), climate rationale, support for adaptation, project specific accreditations, and private sector strategy. The following have direct relationship to enhancing GCF’s programming added value and streamlining processes: / the ‘updated Accreditation Framework’ streamlines the accreditation process by removing duplication across review stages, / the Updated SAP’ streamlines some procedures and expands the scope of the SAP modality / the Private Sector Strategy sets out four pillars for engagement with countries and the private sector and the outcomes sought through GCF support to the private sector / the ‘Principles for demonstrating the impact potential for mitigation and adaptation activities” set out an approach for demonstrating climate impact to be followed by the Secretariat and iTAP in the review process, expected to further standardize project proposals, therefore reducing the burden on those preparing projects. / the Guidance on the GCF’s vision, approach, and scope for providing support to enhance climate adaptation sets out four pillars through which GCF seeks to enhance its adaptation programming. This benefits organisations applying for funding by providing clearer guidelines on GCF’s approach to adaptation and the type of activities GCF is likely to fund. / Several operational decisions also provided additional budget for the Readiness and PPF modality for the remainder of GCF-1, with a revised Readiness Strategy and budget planned to be considered at the start of 2023. / However, outstanding key items still include the policy on concessionality and Review of RfPs and funding allocations.
Policies adopted/updated and/ or sufficient* progress made on implementation to improve safeguarding, fiduciary standards, integrity policies	Possible milestones include: / •Review and update of the initial Fiduciary Standards, including to integrate the: / - Policy on Prohibited Practices / - AML-CFT Policy and Standards; Review of GCF's Environmental and Social Safeguards submitted to the Board.	Met expectations: / For the reporting period the GCF concluded its updates to the Environmental and Social Policy to include SEAH components and further advanced open consultations on the development of GCF’s own Environmental and Social Standards. / The GCF also adopted the Investigations Standards approved by the Board in December 2021. / The update of GCF’s fiduciary standards will be undertaken in 2023 in line with the Board Work Plan.
Policies adopted/updated and/ or sufficient*progress made on implementation to improve the functioning of the Board, secretariat, and Independent Units.	Possible milestones include: / -Policy on decision making between Boards adopted -Policy addressing Secretariat capacity	Met expectations: / During the period covered the GCF took a range of decisions covering these matters, including: / a decision on the Secretariat’s capability review expanding GCF’s headcount to meet the new programming and operations goals under the USP. / Three decisions related to the operations of the Board and Committees: “general Guidelines for the operation of Board committees”; “Guidelines to determine in which cases decisions without a Board meeting may be requested”; “Next steps in the event that a Board member is unable to join consensus regarding the outcome of the balloting procedure”.

Briefly describe the output’s activities and provide supporting narrative for the score.

Overall progress for this output has met expectations in 2022 and shows considerable improvement from the previous year. Policy progression, within and outside of Board meetings, has reflected reform priorities laid out in the Board workplan, the Independent Evaluation Unit’s (IEU’s) forward looking performance review, the UK business case and subsequently the GCF’s Updated Strategic Plan (USP).

A key priority for this year was to address the backlog of policy gaps that had built up over the COVID-19 pandemic with Board meetings being held virtually (which impacted the Board’s ability to progress key items to improve the effectiveness and functioning of the Fund). Following two years of slow progress, key policies to improve VfM were approved during this annual review period including the Fund’s Private Sector Strategy, Simplified Approval Process, updated accreditation framework (including project specific accreditation approach), and policies on climate adaption and rationale, which will all help to enhance the added value of GCF programming, further streamline processes, and improve access. Overall, the GCF adopted 10 policy items between August 2021-July 2022 relating to this objective. Furthermore, the GCF Board has put in place mandates to ensure a discussion/approval of the accreditation strategy (how to optimise access) and readiness strategy by the October 2023 Board Meeting.

Safeguards, Fiduciary, and integrity policies

Along with progress made in the previous review period on environmental safeguards, and the gender policy, this reporting period also saw the conclusion of updates to the Environmental and Social Policy, which now includes Sexual Exploitation, Abuse and Harassment (SEAH) components. The GCF Secretariat has also now further advanced open consultations on the development of GCF’s own Environmental and Social Standards. See further detail below in the Risk section.

The GCF also adopted new Investigations Standards, which were approved by the Board in December 2021. These set out the principles and general procedures applicable to GCF investigations, ensuring consistent, objective, and effective investigations that align with international best practice within the context of GCF’s legal and policy framework as adopted by the Board. The Standards also provide certainty and transparency to investigation participants, the subjects of investigations, and other stakeholders about the investigation process.

The update of GCF’s fiduciary standards was not addressed this review period due to other items being prioritised for the Board but is due to be undertaken in 2023 in line with the Board Work Plan.

Gender

Continued progress has been made on gender. Since its inception, the GCF has had gender at the heart of its operations and included provision for a gender sensitive approach in its governing instrument. The Gender Policy, which was adopted in November 2019, is being actively implemented, and all funding proposals approved in this review period contain gender action plans, gender disaggregated data and gender assessments.

Functioning of the Board and Fund

Policies aiming to improve the functioning of the Board had been previously delayed due to a combination of the remote setting of Board meetings and the need to revise expectations and priorities. During this period, key outstanding matters such as the guidelines on committees and secretariat capacity have now been approved by the Board.

The GCF Board is currently supported by six committees: accreditation, budget, ethics and audit, investment, risk management and performance oversight. Each committee has clear terms of reference which are reviewed every three years. During COVID-19 it was difficult for committees to meet regularly. Moving forward GCF are due to produce detailed guidance for committees aimed at enhancing the effectiveness of their work in support of the Board.

Additionally, Secretariat staffing is now at 225, within range of our Business Case target of 250. The Independent Unit’s head count has also increased, with the IEU now reducing previous years’ vacancies from 12 to 4 during this period.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

To assess the economy of the GCF, budget breakdowns have been reviewed. For 2021 a budget of USD 75m was approved for Board, Secretariat, and Trustee activities (the largest part of this is for Secretariat staff salaries). In addition, the Board approved budgets for each of the three independent units of approximately USD 10.1m in total.

For 2022, the approved budget for the Board, Secretariat and Trustee was USD 89m. Overall, the budget represents an increase from 2021 of USD 14m. The bulk of the increase in 2022 budget relates to an increase in Secretariat staffing to deliver on the USP.

The UK is a strong proponent of achieving good VfM in the GCF. At the Board we seek to maximise VfM through our positions on a range of issues relating to economy, efficiency, effectiveness and equity. For example, on funding proposals we pay particular attention to the terms of the financial support requested, to ensure that this is appropriate to the country context and to the specific activity, following the principle of using the minimum level of concessionality required.

The Business Case noted that measures to achieve VfM are central to the GCF’s Investment Framework. Strengthening the policy on concessionality and fully implementing the Integrated Results Management Framework would further improve VfM in terms of efficiency and ability to monitor effectiveness through achieved results.

The rate of progress in approving new policies has increased significantly this year, in particular aided by the return to in-person Board meetings (following slow progress on policies during the COVID pandemic when Board meetings were held remotely). We would hope to build on recent progress at the Board and further improve efficiency for example through greater use of written procedure to make decisions between Board meetings, and potentially through greater delegation of authority to the GCF Secretariat.

The Fund’s Gender Policy, outlined above, demonstrates progress under the equity component of FCDO’s VfM framework. All projects financed by the GCF are required to align with the Fund’s gender policy.

Overall, the GCF continues to demonstrate good VfM, but with scope for improvement. We will continue to focus our efforts on key areas in the coming year, both to push for progress in the final year of this replenishment period (GCF1) and to develop a strong strategic plan reflective of UK priorities for the next period (GCF2).

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

Following recommendations from the previous Annual Review, the weighting for the two outputs has changed from 60-40, to 50-50. This is to better reflect our high expectations for the programme, and the importance of the policy agenda which were key priorities in supporting the GCF-1 Business Case (2020-23). We have also revised targets for September 2022 in line with updated projections that were sent by the GCF Secretariat in February 2022.

For output 2, we have also changed the wording for the indicators to account for implementation of policy / delivery improvements outside Board meetings, as this was a key area of progression during the pandemic and has continued to be so (I.e. where improvement in performance has been seen over time without the Board necessarily adopting a new policy/approach - e.g. time taken from first review of a project to first disbursement).

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

A key recommendation from the previous AR was how to emphasise the importance of improving the GCF’s governing and policy framework which aids improving the Fund’s efficiency. After 2 years of virtual meetings where lack of policy progress was a real concern, there has been a renewed push by the UK and by others at Board level to decrease the policy backlog, resulting in many of the UK’s reform priorities set out in the Business Case being achieved.

Despite the progress seen in this period, there is still a question over Secretariat capacity, the concessionality policy has not been further considered, and there remains potential for increased utilisation of other decision-making methods (notably the written procedure for between Board meetings decisions).

Areas that still need to be addressed include:

Improving the functioning of the Board and Fund, including through increased use of decision-making by written procedure between Board meetings, and other improvements to standards.
- Further improving the targeting of GCF grants and concessional resources to increase impact by providing support in accordance with country needs and capabilities (concessionality policy).
- Adoption of an Accreditation Strategy, to ensure the right organisations to deliver GCF’s mandate are accredited as project partners.
- Continuing to increase staffing at the Secretariat towards the maximum complement of 350 by 2023, to:
  - effectively manage the existing portfolio as well as continue to bring quality new pipeline to the Fund;
  - continue to focus on implementation, achieving - and measuring - results on the ground.

D: RISK [½ to 1 page]

Overview of risk management

The overall risk rating for the programme remains major since the last AR in 2021 was conducted. The risks have been updated ahead of the AR and remain relevant in the current circumstances. Mitigations have been identified for each risk and the UK team continue to review these on an ongoing basis.

GCF approach to risk management

The GCF has a continued strong focus on risk management. The GCF’s Risk Management Framework is made up of several components including a risk register, risk appetite statement and risk dashboard. The UK FCDO team receives regular updates at Board meetings including from the GCF’s Risk Management Committee (RMC). This is drawn from the GCF’s quarterly risk dashboard circulated to the Board.

The GCF has existing policies on anti-money laundering and countering the financing of terrorism in line with other multilateral organisations, as well as a policy on the prevention of and protection from sexual exploitation, abuse and harassment (SEAH).

Safeguarding risks are assessed to be major given the size and complexity of the GCF programme. As noted above, updates are provided to the Board regularly and we will work with the GCF to promote ongoing effective implementation of safeguarding policies.

In terms of case numbers, the GCF’s Independent Integrity Unit (IIU) has received an increase in numbers of safeguarding reports related to GCF projects and programmes in 2022 compared to the previous two years. As of 15 September 2022, 22 new cases were registered since the beginning of the year. In total, 9 of these cases were referred and investigated as per the contractual agreements in with GCF’s policies. 12 of the cases are now closed. The IIU have also updated key operational forms and templates for use in investigation activities, they ensure proper and timely follow up with delivery partners. This includes an automated referrals tracker that alerts it at designated periods.

The FCDO team will continue to monitor these risks and case numbers and support the GCF in strengthening and implementing its safeguarding policies.

Risks to the UK’s contributions in GCF

As noted above, the programme’s risk rating remains at ‘major’ with appropriate risk mitigation in place. The FCDO team regularly assesses the risks associated with our contribution to GCF and keeps our Risk Register updated. The main risks are as follows:

Risk Description	Mitigation Strategy	Comments
Risk 1: Different priorities of developed and developing countries (G77) and/or obstruction by minority interests on the GCF Board lead to an erosion of trust in dialogue and lack of progress on key issues, including the adoption of new Updated Strategic Plan for 2024-27 and implementation of lessons learnt from the Second Performance Review.	[Treat] 1. In Board meetings, committees and 1:1 relationships, work to find common ground and consensus where possible. 2. Support efforts to improve decision-making (including via use of between Board meetings decisions and better devolution of responsibilities to committees and secretariat. 3. Apply pressure for effective implementation of improvements through USP, Board and GCF1 UK Performance Arrangement. Work with co-chairs and Board to promote actions that deliver impact and VFM, per GCF's USP, where necessary through appropriate diplomatic channels and jointly with other like-minded countries.	This risk remains major. It has improved significantly during 2022 as the Board is now meeting face to face again. We will also push for greater use of decisions by written procedure in between Board meetings to help support efficient and timely decision-makings / The UK team have been engaging with developed and developing country members on various issues throughout the year including the new Updated Strategic Plan (USP2) for 2024-27. The UK will work closely within the developed country group and the new co-chairs in 2023.
Risk 2: COVID-19 reduces the effectiveness of GCF operations by affecting staffing (individuals’ health / working patterns), programmes (implementation delays), international co-operation (limiting in-person Board meetings or other outreach) or countries’ ability to advance mitigation and adaptation activities due to the wider economic effects of the pandemic	(a) Continued adherence to national and organisational health and safety rules in relation to vaccinations, quarantining, social distancing etc; (2) adapt to emerging operational challenges including using online collaboration tools and encouraging the use of between Board meeting decision-making modalities; (3) monitor GCF’s risk dashboard for data on programme / operational impacts	This risk currently is assessed as moderate. Although COVID-19 does not longer impose a major impact on the programmes results it should still continually be monitored as a risk. / The long-term impact remains and countries are still reverting back to normal which will essentially impact the project delivery across GCF. The UK team should continue to assess and raise any issues where necessary to minimise the impact.
Risk 3: Cases of sexual exploitation, abuse and harassment at the GCF Secretariat or in its funded projects are not prevented or responded to effectively, causing both harm to people and undermining trust in the GCF.	[Treat] 1. Deepen engagement with the GCF safeguarding leads on their updated Environmental and Social Safeguarding (ESS) standards, drawing on the expertise of the FCDO Safeguarding Unit and Safeguarding Investigations Team as needed. 2. Review and log the reporting we get on SEAH cases to the Board via the IIU and any ad-hoc cases of concern raised with us directly. 3. Ensure UK BM is aware of any issues related to safeguarding and escalate where necessary using the Board seat as required.	We assess this risk as moderate. The IIU has further advanced the development of the Investigation Manual and SEAH Interview procedures, with the aim of engaging in consultations with relevant divisions of the GCF Secretariat. They have also updated key forms and templates for use in investigation activities. We will continue to monitor case reporting and engage on policy strengthening / implementation.
Risk 4: GCF's partner entities are unable to access GCF funding or find the process of project approvals and/or accreditation and reaccreditation too burdensome and time-consuming. Both a delivery and reputational risk.	(Treat) 1. Articulate and advocate need for ambitious reforms on access and accreditation via new USP2, by July 2023. 2. Engage with most critical voices including working with key FCDO leads across out network. 3. Engage in Board discussions on accreditation and pipeline development, building on lessons learnt from the IEU evaluation on support to SIDS and feedback from partner entities. 4. Use USP2 consultations to target an ambitious amount (>69%) of adaptation funding to the most vulnerable and encourage progress in providing project funding in specific countries having access issues.	We assess this risk to be major and will push for reforms in this area via the new USP2 and related Board decisions. The GCF pipeline continues to grow as AEs submit more projects (approximately $22bn now in pipeline when concept notes included). Delays in programming and concerns over quality are mainly due to outstanding operational and policy issues, which require Board decisions for progress to be made. Whilst pipeline volume risk has receded (demand for GCF funding now well outstrips supply), there is still a risk around quality of projects, which we are addressing through actions to tighten relevant policies (e.g. concessionality guidelines) and improve GCF’s overall efficiency.
Risk 5: Fraud and corruption in relation to GCF activities, or failure of the GCF Secretariat to exercise effectively its fiduciary duty related to the operations of the Fund, undermines trust in the organisation, lessens its effectiveness and wastes / misdirects donor money.	[Treat] 1. Ensure that a new Central Assurance Assessment is produced, building on the recommendations of the previous CAA and the Internal Audit review. 2. Ensure the GCF's accreditation process identifies risks of fraud and corruption associated with Accredited Entities (AEs), implementing robust internal controls and regular assessment of compliance with fiduciary standards; ensure risk management framework is in effect; ensure the Secretariat carry out ad-hoc checks. 3. Ensure all integrity policy pieces are finalised as soon as possible. 4. Review GCF case numbers, ensuring these are logged with FCDO IAID and that we challenge if reporting numbers seem too low	We assess this risk to be moderate. The UK has no evidence of any fraud or corruption and considers the GCF to have a satisfactory set of controls in this regard, although we will test the extent to which low reporting relates to low incidence or low awareness. However, there remain elements of the integrity policies and standards which remain outstanding. The UK has invested a sizeable sum in the GCF – a high profile and relatively new institution whose operational performance has yet to be fully tested. We should remain vigilant in tracking performance as these systems are tested and bed down.
Risk 6: The UK and other donors lacking sufficient evidence of impact and lesson learning, owing to an inadequate and/or poorly implemented results management framework.	[Treat] 1. Call for full implementation of recommendations from relevant reports, including IEU Results Management evaluation. 2. Support the operationalisation of the Integrated Results Management System to move to actual/timely results reporting.	We assess this risk to be moderate. Achieving, recording and learning from results is essential to demonstrating that the GCF has positive impact and gives good value for money. Now that the IRMF has been launched we need to see reporting of actual results.
Risk 7: The secretariat lacks the institutional capacity fully to implement the reforms required to make it effective.	[Treat] 1. Work through our seat on the Board to ensure the GCF secretariat has sufficient resources to handle its workload - and sufficient authority to implement reforms. 2. Work with like-minded countries to secure a common position on what is required and take necessary actions including decisions in the Board. 3. Fund FCDO secondee into GCF's adaptation team to work on adaptation programmes in African countries, liaising regularly with secondee to support and maximise the secondee’s influence/impact.	We assess this risk to be moderate. GCF staff numbers remain a challenge with high turnover rates. As the portfolio matures, more projects will require monitoring and programme management. In addition, the GCF will require considerably increased resources to implement key reform policies.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency. [max 1 page]

GCF model

The GCF is a multilateral fund, with the World Bank serving as Trustee. The World Bank’s functions include the receipt, holding and investment of financial contributions from contributors and preparation of summary financial reports. The GCF’s day-to-day operations are run by the independent GCF Secretariat (currently around 225 staff, based in South Korea), and the UK contribution to GCF is governed by the Contribution Arrangement between FCDO, BEIS, GCF and the World Bank as Trustee. GCF delivers its funding through ‘accredited entities’ – i.e. implementing agents accredited to channel GCF finance and deliver the projects on the ground. As of September 2022, a total of 200 projects had been approved, for a total of $10.8bn of GCF funding, $40.2bn when counting co-financing, demonstrating sustained evidence of GCF’s ability to programme at scale. The number of projects in implementation stands at 163 – over 80% of the portfolio. GCF’s Annual Results Report for 2021 is available here.

Financial management

Financial reporting
The GCF and Trustee provide financial reports at each Board meeting (usually three times per year but four in this reporting year), to assess the financial situation of GCF setting out information including inflows, outflows and commitments vs disbursements. This gives the Board – aided by the Budget Committee – oversight of GCF’s finances.

Financial position

The GCF’s financial position is overall stable at the moment with donors having committed $10bn funding in total for the current replenishment period (2020-23). The Secretariat plans a pipeline of projects to put to the Board for approval based on available commitment authority, utilising the $10bn over the 4 year period. Administrative budgets are approved annually by the Board – and progress against these is reported on at each Board meeting.

The next replenishment process (‘GCF2’) for 2024-27 has recently launched. The UK will work with others for a successful replenishment ahead of pledging in autumn 2023.

Monitoring

The UK GCF team ensure accurate forecasting on a month-by-month basis, ensuring that the correct figures are inputted on FCDO’s internal systems and updating where required. The UK team work closely with the financial team in the GCF to enhance effective programme management. The UK makes payments to GCF by Promissory Note (PN), based on GCF’s project pipeline and available commitment authority (funding available to commit to projects). The UK team works closely with FCDO finance and the GCF Secretariat on our PN deposits, including discussing and agreeing the disbursement and encashment schedule. The encashment schedule is currently paused and the UK GCF team is focused on agreeing a new encashment schedule with the GCF in the next reporting period.

The UK GCF team engage FCDO posts and country offices at the time of each Board meeting on any upcoming projects in the pipeline. This ensures a coherent approach to assessing project proposals and identifies any risks to the project going ahead. The UK also funds a secondee to the GCF Secretariat - an Adaptation Advisor - based in Songdo, to help strengthen Secretariat capacity on adaptation and support the development of a strong pipeline of financing proposals.

The UK is represented on the GCF Board by the FCDO Deputy Director Head of Climate Finance and International Systems Department, supported by a BEIS Alternate Board Member and a joint FCDO/BEIS team of advisors. This gives us oversight of and opportunities to influence GCF’s operations and strategic direction. The UK Board member will sit on the upcoming panel Selection Committee for the new GCF Executive Director. The UK Alternate Board Member sits on the Investment Committee.

Date of last narrative financial report	Year ended 31/12/21	Date of last audited annual statement	Year-ended 31/12/21