## Annual Review Template

Title: Annual assessed contribution over four calendar year-period 2020-2023 to the United Nations Educational, Scientific and Cultural Organisation
Programme Value £ (full life): £48,100,000 (£~12m p/a)		Review date: / 13 June 2022
Programme Code: / 300677	AMP start date: / March 2020	AMP end date: / March 2023

Summary of Programme Performance
Year	2016	2017	2018	2019	2020	2021	2022
Overall Output Score	C	B	A	A	A	A	A
Risk Rating	Major	Major	Major	Major	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	N/A
DevTracker Link to results framework:	N/A

A. SUMMARY AND OVERVIEW

Description of programme

The Foreign, Commonwealth & Development Office (FCDO) is the lead department for the UK’s relationship with the United Nations Educational, Scientific and Cultural Organisation (UNESCO) and is responsible for paying the UK’s annual assessed contribution to UNESCO. The annual assessed contribution is mandatory and pays for the UK’s membership to this multilateral organisation. UNESCO member states’ assessed contributions are based on a UN formula that assesses a country’s dues in line with their relative share of the global economy.

UNESCO is a specialised agency of the UN with 193 member states. As an intergovernmental organisation it provides a normative forum for the negotiation of global agreements, and a facility for policy exchange and capacity building. The UK works with UNESCO for the delivery and promotion of international collaboration in education, sciences, culture, and information and communication. The Organisation is a key partner for the UK on issues including: the delivery of global education (SDG4); girls’ education (including our two SDG4 girls’ access and learning objectives); protection of cultural heritage; ensuring the protection of journalists and a free media; the promotion of open science; ethics of AI; oceans; and climate change. UNESCO is also responsible for biosphere reserves, UNESCO University Chairs, World Heritage Sites, Creative Cities and other similar accreditations.

Under the leadership of the current Director-General, UNESCO began a reform process to improve its effectiveness. The DG’s ongoing reform efforts have enabled UNESCO to lay the foundations for a better management culture, greater openness to partnerships, better approach to evaluation and greater staff mobility. UNESCO’s Strategic Transformation Programme has been implemented, and in November 2021 the Director-General was re-elected for a second term.

Summary supporting narrative for the overall score in this review

As noted in the 2021 annual review, the management and operation of UNESCO has improved significantly under the leadership of the current Director-General. Since then, the UNESCO General Conference has elected Ms Audrey Azoulay to a second term. The General Conference also adopted a new Medium Term Strategy, which will guide how the organisation will deliver on his mandate for 2022-2029. In particular, the Strategy builds on the Strategic Transformation Programme of Azoulay’s first term, specifically enabling the Organisation to break out of its typically siloed means of operation. A ‘strengthening of synergies and linkages’ will take place, allowing the organisation to most effectively harness its functions at each level of action (global, regional and national), leading to more integrated thinking and action. This more integrated approach – combined with a tighter focus on reporting on performance and impact – is welcome and important, but there remains scope to improve UNESCO’s effectiveness, particularly in terms of: providing strong global leadership for SDG4; improving the sustainability and delivery capacity of the field network; focussing the organisation’s limited resources on its comparative advantages; and ensuring long-term financial sustainability.

UNESCO needs to maintain its focus on organisational transformation, efficiency, and ensure its limited resources are not spread too thinly.

The overall score for this programme over this review period has been assessed as an A (outputs met expectations). This score has been given following a balanced assessment of progress against specific outputs:

Output 1 (UNESCO develops reporting on results and impact so that it is able to demonstrate the difference it is making, with a greater focus on measuring outcomes rather than outputs and demonstrating that it is engaging with partners in the process): UNESCO scored an A rating as it met expectations across 5 of the 6 milestones. UNESCO has recognised the importance of effective impact measurement and reporting, both to member states and for the buoyancy of the organisation’s own reputation. There is scope for UNESCO to do more to communicate on results and impact outside the member state bubble (beyond the scope of this output), for example in relation to the conflict in Ukraine.

Output 2 (UNESCO demonstrates its leadership of the education 2030 agenda and sector, effectively convening and coordinating member states and global education actors in education, and influencing governments with its policy analysis, advocacy and capacity building roles): UNESCO scored a B rating as it met expectations across 3 of the 5 milestones, partially meeting the remaining 2. While UNESCO has met expectations around reporting and utilising its convening power to bring Member States and other global actors together (eg through the Global Education Meeting and in advance of the Transforming Education Summit), the organisation is not yet delivering the focused leadership required to make sufficient progress towards SDG4. The opportunity to feed into the Global Cooperation Mechanism is also minimal, with papers being shared often just a few days ahead of the meetings meaning there is no space for internal consultation which would lead to more wholesome and meaningful input into the meetings. It is still unclear how decisions are made within the GCM and we would welcome a more transparent decision making framework.

Output 3 (Organisational effectiveness and risk management - reform, transparency, accountability and efficiency): UNESCO scored an A rating as it met expectations across 4 of the 5 milestones. UNESCO has improved significantly in recent years in terms of organisational effectiveness and risk management, and continues on that trajectory, with particular improvement with respect to transparency and reform.

Output 4 (Partnerships and effective coordination): UNESCO scored an A rating as it met expectations across 3 of the 4 milestones. UNESCO’s network is one of its key strengths, the Secretariat is clearly engaged with UN reform efforts, and is similarly involved in the implementation of a number of the Our Common Agenda recommendations.

Major lessons and recommendations for the year ahead

The Covid pandemic has continued to present challenges for UNESCO during this review period, but operations are now largely back to a pre-pandemic footing, with meetings once again taking place in presentia. The recently adopted Medium Term Strategy provides an important opportunity for the organisation to build on the lessons learned from the pandemic (chief among which is the need to take a more integrated approach), while the UN’s Our Common Agenda provides opportunities for UNESCO to play to its comparative advantage and to work more closely with relevant elements of the wider of the UN system.

The current war in Ukraine presents new and unprecedented challenges for UNESCO. On the one hand, the UNESCO Secretariat was slow to condemn Russian aggression in Ukraine. On the other, the breadth of Russia’s influence within the organisation is only now being fully realised by Member States. UNESCO rules and procedures were not designed with a view to excluding or isolating individual states, leaving the Secretariat with few levers to address the situation. Russia remains, for example, Vice Chair of the Bureau of the International Programme for the Development of Communication, at a time when they are killing journalists and peddling vast disinformation campaigns. Similarly, the World Heritage Committee was due to take place during 2022 in Kazan, hosted by Russia. It has now been postponed, but it remains unthinkable that it should be hosted by Russia at a time when they are actively engaged in the destruction of cultural heritage in Ukraine. The UNESCO Secretariat is not prepared or equipped to deal with existential issues of this kind, placing newly critical importance on UNESCO committees as diplomatic fora.

The key recommendations for this programme for the year ahead are to:

Pursue a narrower, more targeted approach to realising SDG4, recognising the importance of foundational skills, focussing minds through international events and communications on making meaningful, measurable progress to tackle the global learning crisis.

Ensure sufficient expertise in the Secretariat and the Institute of Statistics to mainstream gender equality as a core element of UNESCO’s approach and reporting.

Provide more detailed, proactive communication to Member States on the implementation and effectiveness of reform initiatives (including UN reform, alignment with other UN agencies in the field, internal cooperation, and initiatives undertaken to close underperforming projects/field offices).
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

A business case and theory of change are not applicable for this programme.

The UK contribution is an assessed contribution which is an obligation of membership. The funding is provided in accordance with the pre-agreed schedules and spent as per the budget agreed by the governing bodies. In light of this, any Business Case loses its central rationale (whether or not to fund). For this reason, the UK’s assessed contribution to UNESCO is business case exempt.
Performance and progress of UNESCO as an Organisation and its programmes are assessed and monitored on a continuous basis.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The UNESCO assessed contribution programme is continuing to deliver toward expected outputs. The overall risk of the programme remains at moderate, reflecting ongoing organisational reform progress.

Output 2 received a B rating, as UNESCO is not meeting UK expectation in terms of providing effective global leadership on SDG4 (quality education for all). The UK will continue to engage with UNESCO on this important agenda, and looks forward to the Transforming Education Summit in September as a critical opportunity for UNESCO to demonstrate leadership and drive for meaningful results.

While no significant changes to the programme’s design are anticipated, the FCDO will continue to consider appropriate performance indicators for this programme, drawing on the UK’s new International Development Strategy and emerging HMG policy priorities. Indicators and milestones will be revisited for the next review period, aiming to better evaluate outcome and impact.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The UK pays a mandatory annual assessed contribution to UNESCO. The UK is obligated to pay this as a condition of our membership to the Organisation.

## C. DETAILED OUTPUT SCORING

Output Title	UNESCO develops reporting on results and impact so that it is able to demonstrate the difference it is making, with a greater focus on measuring outcomes rather than outputs and demonstrating that it is engaging with partners in the process.
Output number:		1	Output Score:	A
Impact weighting (%):		30	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
UNESCO adopts a more strategic approach to assessing and defining the impact of programmes and the concrete results they are producing on the ground, with an increased focus on measuring outcomes rather than just outputs.	UNESCO focuses on reporting on outcomes through key documents shared with member states including the SRR. / SRR and PIR reports are shorter and more succinct, with more figures and graphic indicators that clearly indicate outcomes rather than outputs.	Met expectations: UNESCO has maintained its focus on reporting on outcomes rather than outputs. The new Medium Term Strategy for 2022-2029, adopted by the General Conference in November 2021, frames UNESCO’s strategic and enabling objectives in the context of their corresponding outcomes. This strategic framework in turn underpins the Programme and Budget for 2022-2025. / Met expectations: The Strategic Results Report (SRR) and Performance Implementation Report (PIR) have not been published during this review period (see below). It is expected that these will benefit from UNESCO’s (now) tighter focus on reporting on performance and impact.
UNESCO clearly evaluates and reports on results, impact and partnerships, and enhances the use of results in decision making.	UNESCO further develops performance indicators to ensure that evaluation is more precise and consistent across all UNESCO programmes. / UNESCO reporting enables the clear identification of programme performance across the portfolio, and enables informed decision-making, clearly capturing and communicating results and impact to member states. / Board and Secretariat decisions include clear use of evidence of performance and impact. / UNESCO systems and strategy explicitly showcase how they are engaging and influencing partners.	Met expectations: Reporting clearly against performance indicators is at the heart of UNESCO’s new approach to reporting on impact. From next year, member states will receive an annual summary and assessment of status and progress in the achievement of C/5 (programme and budget) outputs, measured through performance indicators. Details of these performance indicators are provided against each output of the Organisation’s main programmes in the / Programme and Budget for 2022-2025. / Partially met expectations: UNESCO now has in place a reformed and appropriate structure for reporting on programme performance, the full benefits of which should begin to be realised over the next year. / Met expectations: The last SRR served as a basis for the development and negotiation of the new Medium Term Strategy and Programme and Budget, both adopted by the General Conference in November 2021. / Met expectations: UNESCO’s plans to consult and/or partner with relevant other bodies are routinely encoded in the proposals and reports put before the member states (eg from partnership work with Unicef and the World Bank on post-covid education recovery, to undertaking to consult with the International Coalition of Inclusive and Sustainable Cities and NGOs on the design and funding of the UNESCO Roadmap Against Racism and Discrimination).

Briefly describe the output’s activities, and provide supporting narrative for the score.

UNESCO met expectation across 5 of the 6 milestones for this output, therefore scoring an A rating.

UNESCO has recognised the importance of effective impact measurement and reporting, both to member states and for the buoyancy of the organisation’s own reputation. This was evident in private conversations with various ADGs in September 2021, and is reflected in the reform of the organisation’s previously overly complex reporting system. The shift in focus towards outcomes over outputs, particularly in the context of the new integrated approach, is particularly welcome, although sustained effort will be required to fully realise and communicate the benefits. The effectiveness and efficiency of the new reporting system will be evaluated at the end of the 2022-2025 quadrennium.

The next quadrennial Strategic Results Report (SRR) is due in 2024, and the Executive Board has approved the replacement of the Performance Implementation Report (PIR) and the Analytical Programme Implementation Report (APIR) with a single annual C/5 Implementation Report – the first of which is due in Spring 2023. In this way, the UNESCO Secretariat intends to streamline future reporting and support more focussed, strategic discussion at the Executive Board. This has been appropriately timed to coincide with the inception of the new Medium Term Strategy and Programme/Budget.

There remains scope for UNESCO to better communicate its activities to a wider audience than member state representatives. The Secretariat was slow, for example, to publicise action taken in the wake of Russia’s invasion of Ukraine. There also remain concerns that while UNESCO’s performance measurement structure is right, there is insufficient funding available to the Institute of Statistics (IOS/UIS) to gather a broad enough sample of data to accurately assess performance across the span of the organisation’s portfolio and geographical network. The UK encourages UNESCO to restore funding to the IOS/UIS to enable effective field evaluation to supplement desk-based analyses. The organisation’s ability to effectively communicate on impact and potential will be key to securing additional funding.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There have been no major changes in the past year that would have any implications for the programme or its delivery, and no significant changes at the output level are planned as a result of this review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

This is the second annual review of the current programme cycle (2020-2023). New outputs and indicators that were put in place for the first review period captured key lessons and recommendations from the previous programme cycle, and were rolled across for this review period. On the basis of the progress made by UNESCO in terms of both impact measurement and reporting – the essence of last year’s recommendations – the indicators and milestones will be revised for the next review period.

Recommendations for the year ahead:

Seek appropriate funding for the Institute of Statistics, enabling sufficiently broad sample evaluations to inform performance reporting

Ensure that the first C/5 Implementation Report effectively beds in the full suite of appropriate performance indicators, and communicates findings clearly (and visually) to member states

Remain alive to the need to communicate clearly and effectively to publics and partners, not just member states, in order to enhance the organisation’s reputation (and consequent scope for partnerships, funding etc)

Output Title	UNESCO demonstrates its leadership of the education 2030 agenda and sector, effectively convening and coordinating member states and global education actors in education, and influencing governments with its policy analysis, advocacy and capacity building roles.
Output number:		2	Output Score:	B
Impact weighting (%):		30	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
UNESCO progresses work on the SDG4 agenda up to and beyond 2030 with vision, policy and impact results reporting.	Strategic documents and reporting to the General Conference and Executive Boards reflect UNESCO’s role, action and forward planning for the Education agenda and sets out results and impact achieved towards the 2030 agenda. / UNESCO ensures that different UNESCO-led education initiatives all work within and toward the SDG4 framework and agenda.	Met expectations: UNESCO’s education agenda continues to be clearly reflected in strategic documents, including the Medium Term Strategy. Likewise, reporting such as the Education 2030 global/regional coordination and support paper clearly update on progress towards reforming the Global Education Cooperation Mechanism and High-Level Steering Committee (and UNESCO’s role therein). The Global Education Meeting, held during the General Conference in November 2021 discussed results, impact, and plans. / Partially met expectations: Although SDG4 is codified and prioritised as UNESCO’s ‘Strategic Objective 1’ in the Medium Term Strategy, the UK remains concerns that progress towards SDG4 is off track and the opportunity presented by the upcoming Transforming Education Summit is not being appropriately harnessed.
UNESCO is able to demonstrate improved approach to convening and coordinating member states and global education actors in its Education work, and to demonstrate its advocacy, policy setting and capacity-building engagement with member states.	UNESCO to demonstrate Education leaderships through launching Education events and initiatives where it convenes member states and global education actors. / UNESCO to demonstrate coordination with other UN players on the Education agenda.	Met expectations: UNESCO has reformed the SDG4 high level steering committee, and convened the Global Education Meeting during the General Conference 2021. However, the decision-making processes around the HLSC need to be more transparent and the donor constituency formally defined. / Met expectations: UNESCO is engaged in the implementation of a number of the “Our Common Agenda” recommendations, including: leading the Transforming Education Summit in 2022. UNESCO also has a good record of collaboration with other UN agencies on education and other matters, eg it is a permanent member of the SDG Education 2030 Steering Committee (with UNICEF and the Global Partnership for Education).
Utilise and demonstrate the value of UNESCO’s specialised education institutes (Category 1 institutes) around the world in advancing work on SDG4.	Increased cooperation between UNESCO Headquarters and UNESCO’s specialised education institutes (Category 1 institutes) around the world on SDG4.	Partially met expectations: The UK is aware of cooperation between UNESCO HQ and the Institute of Statistics and International Institute for Educational Planning, but not of any particular increase thereof. There are also a further 7 category 1 institutes on which UNESCO does not communicate clearly to Member States. UNESCO plans to improve reporting (including from category 1 institutes) is therefore welcome.

Briefly describe the output’s activities, and provide supporting narrative for the score.

UNESCO met expectations across 3 of the 5 milestones for this output, partially meeting expectations on the other 2, therefore scoring a B rating. While UNESCO has met expectations around reporting and utilising its convening power to bring Member States and other global actors together (eg through the Global Education Meeting and in advance of the Transforming Education Summit), the organisation is not yet delivering the leadership required to make sufficient progress towards SDG4. The UK continues to see greater scope for more practical coordination and support for prioritisation. With specific regard to the Transforming Education Summit, the UK feels that by maintaining a broad focus, UNESCO is missing a key opportunity to drive forward meaningful change in specific, prioritised areas (eg recovering learning losses in the wake of Covid).

While UNESCO has made important improvements to its reporting processes – including a focus on impact over output – a clearer assessment of where UNESCO advocacy, capacity building and policy analysis have influenced government policies and legislation would be welcome.

The UK supported and welcomed the reform of the SDG4 High Level Steering Committee. It is early days for the new HLSC so it is hoped that teething troubles (eg papers being circulated with little time for consultation, opaque decision-making process) will be worked through in a timely manner.

The UK continues to see great value in the work of the Institute of Statistics (category 1 institute) and the Global Education Monitoring report, but would like to see greater emphasis on the disaggregation of data (and analysis and communication thereof) combined with a mainstreaming of gender expertise within the UNESCO education sector and reporting. Furthermore, there are currently significant gaps in the data we need to track progress against SDG4. In poorer countries, reliable information on what children are learning, especially in primary school, is not collected frequently or at all. There is therefore no ‘feedback loop’ to national education policy and planning. The Covid pandemic has deepened the learning crisis; and understanding students’ learning levels – as they return post school closures – has never been more urgent.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There have been no major changes in the past year that would have any implications for the programme or its delivery, and no significant changes at the output level are planned as a result of this review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

This is the second annual review of the current programme cycle (2020-2023). New outputs and indicators that were put in place for the first review period captured key lessons and recommendations from the previous programme cycle, and were rolled across for this review period. While last year’s recommendations (to increase efforts to ensure that UNESCO is better at leading, convening and coordinating member states and global education actors on SDG4, and to continue improving cooperation between UNESCO HQ and category 1 institutes) have been partially addressed, the indicators and milestones for this output will be revised for the next review period to better capture UNESCO’s impact in the pursuit of SDG4.

Recommendations for the year ahead:

Pursue a narrower, more targeted approach to realising SDG4, recognising the importance of foundational skills, focussing minds through international events and communications on making meaningful, measurable progress on the global learning crisis.

Ensure sufficient expertise in the Secretariat and the Institute of Statistics to mainstream gender equality as a core element of UNESCO’s approach and reporting.

Seek greater disaggregation of education data, to enable a more insightful, reliable and effective data-driven policy response

Output Title	Organisational effectiveness and risk management - reform, transparency, accountability and efficiency
Output number:		3	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
UNESCO shows commitment to, and demonstrates, improving transparency.	UNESCO publishes project data on its Transparency Portal in accordance with the IATI Activity Standard and advances its Transparency Portal beyond IATI to be a vehicle to support discussions on integrated budgets and structured financing dialogue, enhance user interface and functionality of the Transparency Portal. / UNESCO provides thorough updates to member states on progress made towards greater transparency and accountability, both through detailed and well-structured presentations and during the administrative sessions of the Executive Boards.	Met expectations: The UNESCO transparency portal has been recently relaunched and is much improved. The Secretariat have made welcome progress in improving the timeliness and accuracy of the data. / Met expectations: The requirement for a culture of transparency and accountability to be embedded across the organisation is embedded in the new Medium Term Strategy. The Secretariat plans to achieve this through internal audits (providing assurance on adequacy and effectiveness of internal controls, risk management and governance processes), investigations (promoting accountability), and evaluations (informing decision-making to improve relevance, coherence, efficiency, effectiveness, impact and sustainability of UNESCO’s actions). Examples include reports by the Ethics Office and Internal Oversight Service.
UNESCO has robust systems in place to prevent and respond to fraud	UNESCO has robust procedures in place for effectively preventing, detecting, investigating and sanctioning cases of fraud, corruption and other financial irregularities, effectively training staff and taking a position of maximum transparency with member states on any fraud or corruption issues.	Partially met expectations: As noted in last year’s review, UNESCO has the appropriate policies in place, but currently still lacks sufficient resources to fully manage financial risk. UNESCO is aware of this risk and is strengthening the Secretariat’s capacity to do so. A dedicated team is in now place, but is not yet fully staffed up. An expansion of the current team has been approved by the General Conference as part of the new Programme and Budget, so should be in the pipeline for this coming review period.
UNESCO works to streamline services and reduce costs	Operational effectiveness is improved through further reduction of administration costs, reform of UNESCO’s network of field offices, improved resource mobilisation capabilities and improved approach to prioritisation when looking at programme areas.	Met expectations: Over recent years, much progress has been made to improve the operational effectiveness of the Secretariat. Within this review period, the adoption of a new intersectoral approach through the Medium-Term Strategy and Programme/Budget mainstreams the concept of transversal priorities, aimed at incentivising sectors to work and deliver jointly. Significant initiatives are also underway to exploit opportunities for efficiencies through collaboration with other UN bodies within the field network.
UNESCO to demonstrate further progress on its reform programme.	UNESCO to regularly report to and consult member states on implementation of reform plan and demonstrate progress on implementing UN wide reforms	Met expectation: The UK welcomes UNESCO’s continued focus on organisational reform, following the conclusion of the Strategic Transformation Programme. Reforms have been embedded in the Medium Term Strategy and Programme/Budget and progress against recommendations will be reported on through the Internal Oversight Service. UNESCO have also presented a paper to Member States detailing UNESCO actions as part of the wider repositioning of the UN development system.

Briefly describe the output’s activities, and provide supporting narrative for the score.

UNESCO met expectations across 4 of the 5 milestones for this output, partially meeting expectations on the remaining 1, therefore scoring an A rating.

UNESCO has improved significantly in recent years in terms of organisational effectiveness and risk management, with further gains made in this review period. The Secretariat has performed particularly strongly on commitment to, and demonstration of, transparency and reform. More detailed reporting to Member States on the latter, and in particularly with respect to reform of the field network, would be welcome.

There remain a couple of key issues to address on the financial front. While UNESCO has clear policies and procedures to prevent, detect, investigate and sanction fraud and other financial irregularities, operational and financial risk management capacity continues to be overstretched, risking the effectiveness of those policies and procedures. There also remains a sense that UNESCO is institutionally reticent to close projects or field offices where their performance cannot be clearly evidenced. More detailed reporting to Member States on when this does occur would be helpful.

Describe any changes to this output during the past year, and any planned changes as a result of this review

There have been no major changes in the past year that would have any implications for the programme or its delivery, and no significant changes at the output level are planned as a result of this review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

This is the second annual review of the current programme cycle (2020-2023). New outputs and indicators that were put in place for the first review period captured key lessons and recommendations from the previous programme cycle, and were rolled across for this review period. The indicators and milestones for this output will be revised for the next review period to better reflect progress to date and the specific recommendations below.

Recommendations for the year ahead:

More detailed communication to Member States on reform of the field network (including alignment with other UN agencies in the field), and initiatives undertaken to close underperforming projects/field offices. This will give Member States greater confidence in the continued efficacy of UNESCO’s institutional reform.

Ensure the financial risk management is adequately staffed.

Output Title	Partnerships and effective coordination
Output number:		4	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
UNESCO has a clear strategy regarding its interaction with other international organisations that overlap with/ complements areas of its mandate.	UNESCO strengthens, continues and creates partnerships and synergies, demonstrating to donors the organisation’s impact and comparative advantages compared to other United Nations agencies. / UNESCO’s systems and strategy are explicit in showcasing how they are influencing or attempting to influence partners.	Met expectations: UNESCO has a Comprehensive Partnership Strategy and maintains an extensive list of partners on a dedicated webpage designed to demonstrate the value of partnering with UNESCO. / Met expectations: The Secretariat’s reports to the Executive Board are explicit in demonstrating the Organisation’s approach to partnership and the success thereof. The Secretariat has undertaken to report on the Comprehensive Partnership Strategy as part of its new approach to programme and budget reporting (the ‘C5’).
UNESCO demonstrates full engagement and coordination with UNSG’s UN reform efforts.	UNESCO engages with and implements UNSG reform plans concerning the Resident Coordinator system.	Met expectations: UNESCO participated in the UNSDG Task Force on Resident Coordinator Talent Management which developed the new ‘Resident Coordinator Leadership Profile’. UNESCO is also engaged in a multi-year development process for a new coordination instrument to support the work of UN Development and Resident Coordinators. UNESCO actively advocates for deeper integration of UNESCO work within Cooperation Frameworks across the regions, and incentivizes Regional Coordinators to advance a normative agenda including through proposing changes to their results framework.
UNESCO further improves collaboration between headquarters, institutes, regional and country offices to translate the emerging priorities into coherent action.	UNESCO reports to member states on progress made towards improving partnerships and better internal and external coordination, both through detailed and well-structured presentations and during the sessions of the Executive Boards.	Partially met expectations: UNESCO continues to report to member states on progress and plans for improving partnerships and for better streamlining and inter-sectoral working internally during Executive Board sessions. While ambition on better internal coordination is high, UNESCO still needs to demonstrate better coordination between Headquarters, field offices and its Category 1 institutes.

Briefly describe the output’s activities, and provide supporting narrative for the score.

UNESCO met expectations across 3 of the 4 milestones for this output, partially meeting expectations on the remaining 1, therefore scoring an A rating.

UNESCO’s network is one of its key strengths – its network of 193 member states, 199 national commissions, its own network of field offices, and its wider network of implementation partners. As a normative body it is reliant on policy implementation partners for action and delivery. In recognition of this, reporting on partnerships is now embedded in key papers presented to the Executive Board by the Secretariat to a greater degree than was previously the case (as reflected in last year’s annual review).

It is also clear that UNESCO has taken steps to improve its engagement with UN reform efforts at HQ and network level. UNESCO cooperation with other UN agencies has increased markedly since 2019, and the organisation is directly involved in the implementation of a number of the United Nations’ “Our Common Agenda” recommendations (not limited to those listed under Output 2). This is evidence of the intensification of UNESCO’s activity at the UN level, trailed in last year’s annual review. However, while details of relevant activities are provided on request by the Secretariat – and recognising that the SRR and PIR have not been published during this review period – detailed progress updates on such reform activity could usefully be more proactively and routinely shared with Member States.

The assessment of UNESCO’s approach to collaboration and support between headquarters, institutes, regional and country offices remains the same as last year. The Secretariat recognises that progress in this area is central to achieving effective field reform.

Describe any changes to this output during the past year, and any planned changes as a result of this review

There have been no major changes in the past year that would have any implications for the programme or its delivery, and no significant changes at the output level are planned as a result of this review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

This is the second annual review of the current programme cycle (2020-2023). New outputs and indicators that were put in place for the first review period captured key lessons and recommendations from the previous programme cycle, and were rolled across for this review period. The indicators and milestones for this output will be revised for the next review period to better reflect progress to date and the specific recommendations below.

Recommendations for the year ahead:

Reporting should include an assessment of the effectiveness of initiatives undertaken (across UN reform, internal cooperation, and implementation partnerships), not just listing what has been done, but the impact, reach and VfM of those activities.

D: RISK

Overview of risk management

The overall risk of the programme remains moderate, reflecting UNESCO’s ongoing efforts to strengthen internal risk management policies and processes while recognising there are still some areas in need of improvement.

FCDO has assessed that risks related to this programme exist in the following areas: financial and fiduciary, safeguarding, delivery, operational and reputational. Major risks are recognised in the following areas:

Risk management: UNESCO has insufficient resourcing/capacity to prevent, detect, investigate and sanction fraudulent activity, leading to frauds potentially not being prevented, detected, properly investigated or sanctioned, and defrauded funds recovered. The FCDO is mitigating this risk by conducting robust due diligence and having strong Board oversight, engaging closely with UNESCO's Secretariat and Internal Auditors to push for improvement in systems and processes to improve handling.

Reputation: the lack of institutional levers with which to challenge Russian influence within UNESCO leave the organisation open to severe reputational risk, particularly if Russia hosts the next World Heritage Committee meeting). The FCDO is mitigating this risk by using its position as chair of the Group of Friends of Ukraine at UNESCO to raise this issue with the Secretariat leadership, and to seek and encourage alternative solutions.

All risks are continuously monitored, managed and updated by the UNESCO SRO, who keeps Directors and Ministers updated on emerging issues.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency

The UK’s contribution via this programme is an assessed contribution which is an obligation of membership. The funding is provided in accordance with the pre-agreed schedules and spent as per the budget agreed by the Governing bodies.

Multilateral organisations generally perform a wide range of functions, and many operate across multiple sectors.  This gives rise to conceptual difficulties in assessing their value for money, often compounded by practical problems of gaps in the data on both outcomes and costs.   However, UNESCO has taken significant steps to improve its internal operations and delivery, and offers better value than it did at the time of the last Multilateral Development Review in 2016. The efforts of the current (and recently re-elected) Director General, the completion of the Strategic Transformation plan (which addressed the optimisation of administrative and management issues), and the embedding of transformation recommendations into the new and improved Medium-Term Strategy, remain UNESCO’s best route for maximising progress on effectiveness and organisational capability.

UNESCO’s draft programme and budget and Medium-Term Strategy is building on past achievements and lessons learned, including through the recommendations of relevant evaluations and findings of programme assessment exercises. New work plans for each programme sector have sharpened their focus on areas in which UNESCO has a comparative advantage. The key priorities are the embedding of the principles of the 2030 Agenda for Sustainable Development into UNESCO’s programmes, new partnerships (resource mobilisation) and stronger integration within the United Nations System, focusing on Africa and Gender Equality, responding to the needs of LDC’s, SIDS and Youth, improving its Field Network Programme Implementation, better delivering UNESCO’s programmes through interdisciplinary and intersectoral approaches.

Assessing the results of UNESCO’s new Medium-Term Strategy and ongoing transformation efforts will provide for a good measure of the Organisation’s effectiveness and organisational capability and will inform the value for money question in coming years.

Date of last narrative financial report	17 September 2021	Date of last audited annual statement	17 September 2021