ADDENDUM TO BUSINESS CASE INCLUDING FOR BRIDGE FUNDING AND SCALE-UP COST EXTENSIONS

SUMMARY INFORMATION
Project Name	Project Coordination Units (PCUs) -AMP 300715
Country or region targeted	Nepal
Type of cost extension (if applicable)	Bilateral MOU with UNOPS
Original project budget	£2,612,125
Original project start and end dates	31 October 2018
Cost extension value (if applicable)	£156585 over nine months (to be agreed between BEK and UNOPS)
New reduced budget (if applicable)
New project end date (if applicable)	30 September 2022
Business Case Quest Document No.	56826286

INFORMATION
What is the project’s purpose?
The Project Coherence Units (PCUs) were established in the context of Nepal’s transition to a federal republic resulting in formation of seven provincial and 753 local governments with significant devolution of executive and legislative functions. The then Department for International Development (DFID, now Foreign, Commonwealth and Development Office (FCDO) or British Embassy Kathmandu (BEK)) Nepal contracted United Nations Office for Project Services (UNOPS) to establish three provincial units to help DFID respond to the new context. / Provincial Coordination Units (PCUs) were established to build relationships with the new provincial and local Governments; develop an understanding of their needs and the political context they work in; coordinate DFID programmes in the province and link the provincial and local Governments with technical assistance through existing programmes to support the newly elected officials to create effective, accountable, and inclusive institutions. / This was also in the context of closure of DFID/GIZ funded Risk Management Office (RMO) which had previously provided analysis, risk management and capacity building services to DFID, GIZ and their partners. It was envisaged that the new Project Coordination Units (PCUs) would assume some of the responsibilities and intellectual property of the RMO, but with a broader mandate to support coordination and coherence work amongst FCDO partners in Karnali, Lumbini and Province, as well as play the role of connecting FCDO more closely with the new Provincial Governments.
What is the objective of the cost extension or other changes?
The PCU field offices have been fully operational since April 2019. Since then, UNOPS has been providing the project services to support partners with activity mapping, coordination, and coherence activities at the local and provincial level. The UNOPS PCU has also served to increase contact and information exchange between FCDO and the Provincial Governments, as well as providing FCDO with high quality context analysis and reporting. The UNOPS PCU also provides context specific conflict sensitivity capacity building to FCDO partners, as well as acting as a resource for other FCDO Country Offices. PCUs extensively reported on situation at the provincial and local level during COVID pandemic including needs. It also reported on provincial and local government’s response to the pandemic and whether and how FCDO partners could help. This was an important support at the time when FCDO’s ability to monitor programmes and maintain contact with provincial and local stakeholders and implementing partners were limited. / The programme, started in 2018, has an MoU to run until September 2021. However due to the substantial funds remaining in the Project budget, it is recommended that the timeline of the project be revised to a later closure, with a 11-month extension to the business case until September 2022. We will provide a nine-months no-cost extension to UNOPS to run PCUs until June 2022, with all major activities to be completed by March 2022. We will further consider a cost-extension once we have assessed if the FCDO needs additional support from PCU if there are further COVID related restrictions, and/or political instability or elections.
What is the additional and total support the UK will provide?
The support amount remains at £2,612,125 for now with a no-cost extension. If the expected cost extension is agreed depending on FCDO’s need and UNOPS HQ approval, the total support will be £2,768,710 (including the additional £156,585).
What are the expected results?
The six-month phase of work will consist of deliverables around coordination and coherence activities, context analysis, Provincial Government liaison and capacity building, as well as the new activity of sourcing and overseeing substantive research pieces. / Details of deliverables, timeline and reporting will be laid out in the agreed terms of reference. Broadly, UNOPS will produce the following deliverables as agreed with FCDO: / 1. Provide FCDO with analysis of and engagement with the implementation landscape in provincial and key municipal spheres / 2. Coordination of FCDO programmes in Province 2, Lumbini and Karnali Provinces; identifying possible linkages between existing FCDO programmes and identified support needs of Provincial Governments / 3. Provision of context analysis to FCDO and partners / 4. Provision of Training Services to FCDO and Partners to promote safe and effective development / 5. Risk Management, Security/HR Monitoring / 6. Design, sourcing and oversight of substantive research pieces at request of FCDO
What is the approach to implementation?
The proposed no-cost extension will allow PCUs to continue to deliver against their agreed outputs. This will be funded through the unspent amount of £818847 (approximate as of 27 September 2021). If a cost-extension is granted soon (contingent upon FCDO’s needs depending on COVID and political context and UNOPS’ approval), the additional £156,585 will allow the PCU to extend its support to FCDO Nepal’s understanding of COVID, political, governance and electoral context especially in the context of another lockdown and impending elections.
Describe any key changes to the original business case including the theory of change or new evidence from ongoing monitoring, evaluation or learning work?
The original approach and theory of change are still valid. However, PCUs have greatly adapted and refined their political and context reporting and coordination activities since the inception. Lessons from these adaptations have been captured in earlier Annual Reviews and amendment in the logical framework. Political and context reporting were continuously improved based on feedback from FCDO readers to make them more relevant and timelier. And their activities mapping reports have informed SROs, partners and BEK leadership on the progress and challenges to shift our approach in support of federalism. It has established excellent relations with other BEK evidence partners providing them support with contextual and programmatic information and coordinating and streamlining feeding evidence to BEK leadership.