 Programme Completion Review

Title: Democratic Republic of Congo Food Insecurity Crisis Reserve Project
Final Programme Spend £ (full life): £4,000,000	Review Date:	December 2021
Programme Code: 301274	Start Date: 10 November 2020	End Date: 30 September 2021

Summary of Programme Performance

Year	20/21
Programme Score	A
Residual Risk Exposure Rating	Major

DevTracker Link to Business Case (and any addendum):	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-301274/documents
DevTracker Links to all logframes used during programme lifetime:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-301274/documents

Description	Score
Outputs substantially exceeded expectation	A++
Outputs moderately exceeded expectation	A+
Outputs met expectation	A
Outputs moderately did not meet expectation	B
Outputs substantially did not meet expectation	C

A. Summary and Overview

Description of the programme and what it has achieved

The humanitarian crisis in the DRC is one of the largest and most complex in the world, with 27m people now severely food insecure. Covid-19 exacerbated the vulnerability of the population, especially urban poor and internally displaced people. The DRC Food Insecurity Crisis Reserve Project (FICR) was designed to provide urgent lifesaving food assistance to 13,607 vulnerable households (81,643 people) living in the Nsele commune in Kinshasa, the epicentre of Covid-19 in the country, and in the Greater Kasai provinces where community clashes aggravated an already precarious food security situation. £3m of the £4m total was spent on the Nsele programming, and the remaining £1m in the Kasais.

Given the scale of need and worsening trajectory of food security in the country, the UK approved £4m in short-term humanitarian funding through the Crisis Reserve to address needs across Kinshasa and the Kasais. This was delivered through a project with the World Food Programme (WFP), with downstream partners UNICEF, World Vision, and Vodacom, and with the Ministry of Social Affairs (MINAS) as a technical, non-funded partner. It focused on distribution of cash to the most vulnerable, primarily through mobile phone electronic cash transfers.

In Nsele, the intention was to mitigate the socioeconomic impacts of Covid-19 by improving the food security of targeted groups and limiting the spread, and supporting the prevention of, the disease. The project also aimed to support the establishment of a shock-responsive social safety net in Kinshasa by working alongside a new World Bank-funded programme and through building the capacity of the government in the development of a social registry and tools. In the Kasais, the funding targeted some of the most food insecure people in the country, a legacy of underdevelopment and widespread conflict in 2017-18.

The project met food security targets for both Nsele and the Kasais, as well as targets on the longer-term programme and policy goals of expanding government capacity in this area, linking humanitarian cash with the development vision for a cash-based social protection system, and influencing the development of the World Bank-funded Shock Responsive Social Protection (SRSP).

During the implementation period, 77,720 programme participants (against a target of 81,643) were reached with cash assistance for a total value of £2,043,454 (against a target of £2,146,600). As judged by the affected communities, the programme was delivered in a manner that was contextually appropriate (cash was preferred) and safe for participants.

Major lessons learned, evidence generated and recommendations

Lessons learned during this project will inform future humanitarian and SRSP assistance to urban Congolese. Key lessons include:

- A scaleable, protection-sensitive targeting and distribution mechanism adapted to the urban environment is feasible. Prior to this project there was no mechanism for delivering humanitarian cash assistance in Kinshasa. Under the FICR, criteria for selecting the most vulnerable people were developed, a list of project participants was created in a participatory manner that minimised community tension, and a mobile money mechanism was established.
- The FICR funding was catalytic in expanding assistance in Kinshasa. The project put a nascent system in place that has been further developed and is now being funded by other donors. USAID funded and expanded phase two of the Nsele project, and Belgium is funding phase three. The time investment at the outset resulted in a response that was slower than desired but resulted in a well-targeted and good quality mechanism that was replicable.
- The cash distributions covered a gap but the benefits were short term. This is a trend that has been noted with other WFP cash programming in DRC so we are piloting a new methodology, which includes giving more cash over a longer period, to understand whether this has a positive impact on the sustainability of the intervention.
- The programming helped attain good policy leverage, cementing the UK as a key policy stakeholder in the development of a national social protection programme. Cash-based social protection is flagship programme of the World Bank in DRC and, based on lessons from Nsele, we have had the access and knowledge to provide clear recommendations on its development. A report, commissioned through a centrally managed programme (SPACE) looking at how the Nsele project could contribute to the design of the World Bank SRSP, judges the early stages of the SRSP to be flawed. The report provides valuable recommendations that will help to shape the design (ongoing).
  [note] SPACE: Social Protection Approaches to Covid-19: Expert Advice, DRC Report. SPACE (CHASE CMP). Simon Levine and Ric Goodman. June 2021.
- Teething issues with mobile money remain in DRC. Mobile money has not yet been widely adopted and many of the project participants were unfamiliar with the modality. This meant that over one quarter of all participants experienced some problems with withdrawing their cash. The vast majority of these were resolved by mobile money provider (Vodacom). In the future, WFP needs to have a more hands-on approach to troubleshooting these issues and should work with the mobile provider as they would any downstream partner, instead of as a contractor.

The component of the FICR implemented in the Kasais yielded relatively few new lessons learned. Although responding to a new hotspot, the project was conducted in an area where WFP has existing UK-funded programming. Previous visits to the Kasais by the humanitarian team resulted in BTORs with recommendations that continue to be implemented, including on protection of participants and cash distribution methodology.

How this report was conducted

Given the length of this project, no Annual Review is required and this Project Completion Review is the only formal assessment of performance covering the whole lifetime of the project. It was primarily conducted by the Programme Officer and Humanitarian Advisor of the British Embassy Kinshasa (BEK).

The primary document that the review has drawn on:
- Readouts of monthly progress meetings with the WFP team in charge of implementation
- Back to Office Reports of four field visits conducted in December 2020, March and June 2021 in various locations in the Nsele
- A project wrap-up meeting and presentation of achievements with WFP
- A Post Distribution Monitoring survey report conducted by WFP
- Reporting against the initial logframe

Actions following approval of this report

No action is to be taken following approval as there is no closure activity required.
## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	£4,000,000	£4,000,000
Timeframe	5 months (November 2020 to March 2021)	6 months (December 2020 to May 2021)
Outcomes	Percentage of households who report being able to meet the basic needs of their households, according to their priorities. Baseline: 38.3%	Endline: 58.9%

Overall assessment of programme outcomes, sustainability and VfM

The outcome sought by the programme was to enable targeted shock-affected households to meet their basic needs. A logframe target measuring the percentage of households who reported being able to meet the basic needs of their households according to their priorities upon the baseline was exceeded by 15%, suggesting that the project had a positive impact on food security and other basic needs during a crisis period.

In addition to the short-term support provided through the cash disbursements, a key project goal was to contribute to the development of a sustainable shock responsive cash payment system in Kinshasa, and eventually across DRC. The FICR has performed well in this regard, working closely with UN agencies, MINAS, and the World Bank to inform the development the SRSP system. This remains a work in progress: the Nsele component has supported the operational roll out of SRSP but there continue to be significant political and financial hurdles that will impact its longer-term sustainability. The UK’s involvement in the development of the Nsele cash programme, the first of its kind in Kinshasa, has positioned us a key stakeholder in the continued development SRSP, which is part of a wider target to improve the sustainability of cash transfers in DRC.
[note] SPACE: Social Protection Approaches to Covid-19: Expert Advice, DRC Report. SPACE (CHASE CMP). Simon Levine and Ric Goodman. June 2021.

A drawback of the project, in part due to the desire to improve its sustainability, was that it took too long for the first phase of assistance to reach affected populations. While the reasons for the delay is well understood – principally the establishment of a new targeting system together with the Government of DRC (GoDRC) and expanding mobile money to a new area – the first cash disbursement was not released until nine months after the onset of Covid-19. While this was not too late to mitigate the negative economic impact of the pandemic, it was nevertheless longer than anticipated and missed the initial economic shock.

In terms of Value for Money (VFM), the project performed satisfactorily. The FICR did not score well in terms of the final amount that reached the community: £2.04m out of £4m, or 51%. This is less than our other cash programming in DRC, which delivers approximately 60% to programme participants despite significantly more difficult operating conditions. The primary reasons for this low ratio of funds going to participants are: The involvement of two large UN agencies with high operating costs, delays due to set up of a new targeting and cash distribution system, and funds spent on training government and community members involved in the project (which would not typically be spent in a humanitarian intervention). The assistance provided through mobile transfers in Nsele allowed participants to buy goods and services according to their needs and to manage their money with minimal risk of theft, an improvement over physical cash. Further, use of mobile money as a modality significantly reduced operating costs when compared with physical cash transfers (from 10% fee to 2-5% fee).
[note] Standards and Practices Report for Electronic and Mobile Payments. USAID. June 2012.
There remains a high likelihood of future shocks in Kinshasa from disease outbreaks, conflict, flooding and other, and establishment of SRSP in the city will both improve the speed of response and reduce costs associated with setting up future humanitarian interventions.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators.

The theory of change (ToC) for this programme had two pillars aimed at contributing to the project impact of “reduced mortality and suffering and improved coping capacities among affected populations”. The pillars were (1) for acutely food insecure populations to meet their basic food and nutrient requirements and (2) for assistance to be delivered in a manner that is contextually appropriate, does no harm, and strengthens local capacity for social protection.

As outlined in the above section on outcomes, there has been some success against Pillar 1 on food security targets. Programming of this short duration is likely to provide only short-term support, and this was borne out in the results: food consumption scores for community members who did not benefit from latter more focused phases of the project returned to pre-intervention levels several months after the distributions stopped. We are working with WFP to determine how cash amounts and duration of funding may lead to longer term positive change.

Pillar 2, which looks at doing no harm and strengthening local capacity for social protection, was an equally important element, focused on the longer-term benefit of this project. Pillar 2 remains a work in progress although there have already been some concrete deliverables, some of which are also described above. Because of MINAS’s active involvement in Nsele, at least 46 government staff have now been trained in setting up and running mobile money cash programming in Kinshasa in a way that meets expectations on do no harm and targeting the most vulnerable.

While both of these pillars contribute to the project impact, lasting improvements against targets focused on mortality and suffering necessitate broader political and economic change (including a commitment for the government to invest in large-scale social protection), underlining the importance of a cross-embassy approach to humanitarian issues.

In the project design phase, we chose to not select detailed quantitative food security indicators, such as food consumption score (FCS) or coping strategy index (CSI), because the short duration of the project meant that these indictors would be unlikely to shift. Instead we selected a perception-based indicator that allowed project participants to report on their view of the improvement in their situation. While this was the right decision given the short duration, a more detailed analysis of food security indicators captured by WFP will be important to inform future phases of the project and we have asked WFP to produce this next year.

Given the short-term nature of the project, there was only one change to the logframe and that was to remove the erroneous use of food consumption score as a high-level impact indicator. FCS is generally a detailed output level indicator, which would only have reported against a small element of the overall impact.

## C: Detailed Output Assessment

Output Number and Title	Acutely food insecure populations targeted receive sufficient cash - or food to enable them to meet their basic food and nutrient requirements.
Output Score	A
Impact weighting (%)	75%		Impact weighting revised since last AR?	N/A

Output Indicator		Final Logframe Target		Final Result Achieved
Number of people receiving assistance		81,643		77,720
Total amount of cash transferred to targeted beneficiaries		£2,146,600		£2,043,454
Number of people receiving sensitization on COVID prevention measures		81,643		77,720

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

Whilst the final targets were not reached at 100%, the completion rate of 95% of all agreed outputs still represents a significant achievement. Taking into account the short timeframe and contextual challenges these results met expectations at the start of the project, which is why this output scores an A.

During the project design phase, indicators were selected that focused on quantity rather than quality because the short duration of the intervention meant it was unlikely that significant shifts would be seen in community food security. However, the following data from post distribution monitoring does indicate that the funding plugged a critical food gap and did so in a way that improved protection:
1. 88% of targeted households prioritised food expenditure, indicating that food was a critical need that the cash assistance helped to pay for. We do not have data from other parts of Kinshasa to show whether areas without assistance were worse affected but given reporting on increased food prices and reduced household income, it is likely that food security deteriorated elsewhere.
  [note] RDC Covid-19 bulletin conjoint des marches. REACH. Mars / Avril 2020
2. In the Kasais, while the FCS similarly did not significantly improve, the coping strategy index for female-headed households – an indicator that looks at harmful behaviours that individuals resort to to plug income gaps – improved by almost 10%. Globally Covid-19 has had an outsized negative impact on women and girls in situations of displacement and crisis, and so the project did well to attain this target.
  [note] Women’s economic empowerment in the face of Covid-19 and displacement. Humanitarian Policy Group, International Rescue Committee. October 2021.

Delivering assistance through mobile transfers was a new modality for the area and came with risks that could have affected results. In the context of the DRC, WFP usually favours direct cash distribution over mobile money due to the following considerations: (1) cash availability from mobile money vendors; (2) the availability of phone/SIM cards; (3) heavy investment in sensitisation efforts needed for beneficiaries and agents to mitigate potential fraud and safeguarding risks at the point of withdrawal of funds.

The fact that the programme managed not only to reach a high number of beneficiaries but also to transfer almost 90% of the cash assistance to them through mobile money is deemed a success.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

Considering the pilot nature of the programme with it operating in a new area with a new delivery method and higher operating costs than for other cash programming funded by the FCDO in DRC, VfM was observed for this output over the duration of the project.

95% of the targeted community members were reached with the assistance, mitigating the economic impact of Covid-19 and demonstrating equity. 90% did so by way of mobile cash transfer. With mobile money transfers costing 2-5% of the total transfer amount as opposed to the 10% generally charged by banks for the delivery of physical cash, significant cost savings were made therefore demonstrating the efficiency of the approach over the delivery of physical cash. Economy was not expected to be fully reached during this pilot programme as cost per participant is generally high when operating in a new context, using a new delivery mechanism, and working with multiple UN agencies. This was only expected to significantly improve after the pilot phase of the programme.

Lessons learned through this output, and recommendations for future programming

The modality of implementing mobile cash transfers to enable food insecure populations to receive sufficient assistance and meet their basic food requirements was successful in Nsele. In this particular context of mitigating of the socioeconomic impacts of Covid in an urban setting of DRC, it was not only successful in identifying, reaching and sensitising a large number of beneficiaries (90% of beneficiaries now have SIM cards through which they can be reached directly), but also in ensuring general satisfaction amongst beneficiaries due to the security and flexibility of the assistance received. Some issues were however observed, such as poor understanding of the mobile money withdrawal procedure, resulting in less than half of the recipients being able to withdraw the money independently without sensitisation by programme staff. Furthermore, despite very few complaints on the modality of the transfer, other issues observed included many beneficiaries having to regularly travel involving additional time or costs in order for them to actually find a point to withdraw money.

The success of the novel approach via this pilot project should be used as the basis upon which FCDO should increasingly advocate for the introduction/use of mobile money transfers as a modality of cash assistance in future programmes, particularly in urban areas.

Output Number and Title	Assistance is delivered in a manner that is contextually appropriate, does no harm and strengthens local capacity for social protection
Output Score	A
Impact weighting (%)	25%		Impact weighting revised since last AR?	N/A

Output Indicator		Final Logframe Target		Final Result Achieved
2.1. Proportion of targeted people accessing assistance without protection challenges		> 90 %		99%
2.2. Number of tools to support targeting, registration developed for implementation of Shock responsive social protection programmes		4 (finalized questionnaire, data collection tool, social registry tool, PDM tool and validated targeting approach)		3 (eligibility standard questions, community-based targeting mechanism, PDM)
2.3. Number of Government staff whose capacities on shock responsive social protection and humanitarian cash programmes have been built/strengthened.		40		46

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

Indicators under this output have been met and it is therefore assessed as an A.

Post distribution monitoring (PDM) surveys determined that over 90% of the targeted beneficiaries have been able to access assistance without protection challenges (Indicator 2.1). No beneficiaries interviewed reported security incidents at any distribution site over the duration of the programme and no reports were made of attempts to ask for money in exchange for assistance. Almost three quarters of beneficiaries reported throughout that they knew the value of assistance they should receive and the location and date of distribution in advance, limiting opportunity for fraud risk.

Three tools (out of four planned) were developed to support targeting and registration for the implementation of SRSP programmes: eligibility standard questions, a community-based targeting system, and a PDM tool (Indicator 2.2.). This was done as part of WFP and downstream partner UNICEF’s partnership with GoDRC, with the goal of enhancing its capacity to create a SRSP system. The prior presence of UNICEF in the area and connection with MINAS were particularly useful in targeting. Although only planned to be implemented in future phases of the project not funded by FCDO, the Community-Based Targeting (CBT) tool to identify the most vulnerable households through the collection of additional data was also developed in collaboration with MINAS. Finally, the PDM survey used to assess the first phase of the project was designed in collaboration with Institut National de Statistique staff, improving government buy-in and knowledge of the project.

46 community members (out of a planned 40) were trained on aspects of SRSP and humanitarian cash programming (Indicator 2.3.). This was done through UNICEF’s existing relationship with local Cellules d’Action Communautaires (CACs) in the areas of intervention. CAC members were engaged in the community validation and verification process, improving community buy-in. CACs generally cover a group of streets and have lists enumerating all the households living in those areas. It was these lists that UNICEF used to identify target households, which was followed by a community validation process to ensure that all listed households belonged to the targeted neighbourhood and to avoid inclusion and exclusion errors.

Lessons learned through this output, and recommendations for future programming

Despite drawbacks on the timeliness of the cash distribution, overall this was a worthwhile intervention due to the mitigating effect it had on food insecurity during a crisis period and for its contribution to the development of a long-term system for SRSP.

In selecting UN agencies to be the implementing entities, stronger bonds were likely formed with the government and World Bank social protection teams than if we had selected NGO implementers. However, costs were likely higher and timeliness less strong, as implementation of the cash transfers did not begin until nine months after the onset of Covid-19.

Whether the government and World Bank will develop a functional and sustainable SRSP system is yet to be determined and ultimately the longer-term policy success of this intervention will be judged on whether we can influence SRSP in a positive direction. SRSP has the potential to be transformative for vulnerable communities in DRC but success in this area will take time and commitment from the Bank, government and other stakeholders.

D: Risk

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.

During the lifetime of the programme, the overall risk level of the programme was assessed to be major, within the British Embassy Kinshasa’s (BEK) risk appetite. A risk register was maintained and updated outlining gross risks, mitigating measures and residual risks. Specific major and severe risks, or quickly evolving risks, were reviewed more often than others.

The BEK humanitarian team met on a monthly basis with WFP and downstream partners and risk was a standard agenda item for discussion, including the relevance and effectiveness of our mitigating measures. No major specific developments leading to an increase or reduction in originally identified risk rating occurred during the reporting period.

The main risks to which a particular attention was given throughout the duration of the programme included:

Strategy and context risk – A key context risk was the exacerbation of Covid-19 as the DRC continued to suffer from the pandemic, with Kinshasa a particular hotspot. Mitigation measures implemented on the ground by WFP, such as the application of Covid-19 distribution management standard operating procedures, the organisation of capacity development, and sensitisation sessions provided to partners and beneficiaries proved to be effective keeping the net risk steady throughout.

Financial and fiduciary – Risks were high not only due to the fact that corruption is prevalent in the DRC but also due to the inherent fiduciary risk associated with cash distribution projects (as experienced under other similar programmes implemented by the BEK with WFP). Although the BEK had confidence in WFP’s systems in place to mitigate the risk, particular focus was placed on ensuring WFP systematically implemented its own measures and protocols at every stage of the implementation. This included among others biometric registration and deduplication, digitisation of programme participant tracking, and engagement and sensitisation of community, beneficiaries and mobile money operators.

Safeguarding – Over the last three years we have worked with WFP on strengthening their protection capacity and are generally confident in their mechanisms for managing safeguarding risks associated with humanitarian response in the DRC, particularly in the context of cash delivery programmes. Rapid gender assessments before activities, training and sensitisation on sexual abuse and harassment for all stakeholders, and the strengthening of complaints mechanisms are among examples of mitigation measures that were systematically implemented by WFP and on which they were questioned.

E: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency.

WFP was the single implementing partner selected to implement the programme and was chosen based on its proven ability to deliver cash assistance programmes in the DRC and in over 75% of BEK humanitarian cash programming over the past 4 years. WFP in turn worked with downstream partners UNICEF, World Vision, and Vodacom.

WFP did well to establish a mobile money cash distribution project in Kinshasa, despite the significant challenges of this project being the first of its kind and the occasionally severe government-imposed Covid-19 movement restrictions. Regarding project delays, these were caused in large part by a lengthy community-led targeting exercise and the mobile money modality, which was selected because of its perceived safety and efficiency and because of the social protection links.

A single payment was made in advance to WFP to ensure they had sufficient funding to plan and procure ahead for activities. Detailed financial reporting and oversight is normally limited to those set out in the terms of the centrally-negotiated FCDO standard MoU arrangements. However, excellent communication and collaboration was achieved with the team locally throughout the duration of the programme and WFP agreed to monthly monitoring meetings and visits to facilitate programme oversight. WFP showed willingness to produce more regular narrative reporting despite this also falling outside the terms of the MOU arrangement.

Programme-level approach to monitoring and evaluation

BEK maintained monthly meetings with WFP and its downstream partners to discuss policy, technical and programmatic issues as required. Despite Covid-19, this worked well and allowed for participation of almost all implementing parties involved. The proximity of the project made four field visits possible.

Owing to the terms of the FCDO standard MoU arrangements, formal narrative reporting for the project is not going to be published at the time of completion of this review as it will be included in the Annual Country Report of 2022. However, other forms of reports such as PDMs (assessing the effectiveness of the assistance provided after distributions) or the report produced by the centrally managed programme SPACE looking at the programme and links with social safety nets (SSN) and SRSP helped providing additional assurances in programme performance.

Date of last narrative financial report		Date of last audited annual statement