## Annual Review Template

Title: Annual assessed contribution over four calendar year-period 2020-2023 to the United Nations Educational, Scientific and Cultural Organisation
Programme Value £ (full life): £47,354,834.95 (£~12m p/a)		Review date: / March 2023
Programme Code: [AMP ID#] / 300677	AMP start date: / 25 March 2020	AMP end date: / 31 December 2023

Summary of Programme Performance
Year	2016	2017	2018	2019	2020	2021	2022	2023
Overall Output Score	C	B	A	A	A	A	A	A
Risk Rating	Major	Major	Major	Major	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	N/A
DevTracker Link to results framework:	N/A

A. SUMMARY AND OVERVIEW

Description of programme

The Foreign, Commonwealth & Development Office (FCDO) is the lead department for the UK’s relationship with the United Nations Educational, Scientific and Cultural Organisation (UNESCO) and is responsible for paying the UK’s annual assessed contribution to UNESCO. The annual assessed contribution is mandatory and pays for the UK’s membership to this multilateral organisation. UNESCO member states’ assessed contributions are based on a UN formula that assesses a country’s dues in line with their relative share of the global economy.

UNESCO is a specialised agency of the UN with 193 member states. As an intergovernmental organisation it provides a normative forum for the negotiation of global agreements, and a facility for policy exchange and capacity building. The UK works with UNESCO for the delivery and promotion of international collaboration in education, sciences, culture, and information and communication. The Organisation is a key partner for the UK on issues including: the delivery of global education (SDG4); girls’ education (including our two SDG4 girls’ access and learning objectives); protection of cultural heritage; ensuring the protection of journalists and a free media; the promotion of open science; ethics of AI; oceans; and climate change. UNESCO is also responsible for biosphere reserves, UNESCO University Chairs, World Heritage Sites, Creative Cities and other similar accreditations.

Under the leadership of the current Director-General (Audrey Azoulay), UNESCO underwent a ‘strategic transformation programme’ to improve its effectiveness. The DG’s ongoing reform efforts have enabled UNESCO to lay the foundations for a better management culture, greater openness to partnerships, better approach to evaluation and greater staff mobility.

Summary supporting narrative for the overall score in this review

In the 9 months since the last review, Putin’s illegal war in Ukraine has continued to dominate business at UNESCO, while rising costs (inflation and UN staff salaries) have exacerbated concerns over UNESCO’s ability to fund its core functions through the regular budget. The UK recognises that late payment of assessed contributions (as was necessary in 2022 due to the temporary pause in ODA payments in the UK last year) is a further contributing factor to the financial instability of the organisation.

Against that backdrop, however, UNESCO successfully co-convened the Transforming Education Summit, raising the profile of education within the UN system and paving the way for global action on 6 specific and targeted initiatives. Much more work is required to get SDG4 back on track, but the UK is pleased to see strong continued UNESCO involvement in the Global Coalition, including at ADG level. UNESCO has also brought forward much needed proposals for the reform of the UNESCO field network, securing hard-won agreement from resistant member states to begin the reform progress. UNESCO needs to maintain its focus on organisational transformation, efficiency, and ensure its limited resources are not spread too thinly.

The overall score for this programme over this review period has been assessed as an A (outputs met expectations). This score has been given following a balanced assessment of progress against the specific outputs detailed in section C.

Major lessons and recommendations for the year ahead

The key recommendations for this programme for the year ahead are:

Leadership: Deliver on the potential of the 6 Global Initiatives agreed at the TES by continuing to be an active partner in the Global Coalition (getting foundational learning right is critical to getting SDG4 back on track), gripping the coordination of the other 5, and bringing all 6 together. UNESCO should use its position to ensure that education is a key theme at the UN Summit of the Future.

Funding: Seek adequate and more predictable core funding for organisational priorities, specifically the Institute of Statistics and the Intergovernmental Oceanographic Commission.

Reporting: Use the next (and first full) iteration of the C5 Implementation Report to assess the effectiveness of initiatives undertaken (across UN reform, internal cooperation, and implementation partnerships) – not just listing what has been done, but the impact, reach and VfM of those activities.

Reform: Make meaningful progress on field network reform, engaging member states to secure support for stage 2.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

A business case and theory of change are not applicable for this programme.

UK funding provided through this programme is an international subscription, an assessed contribution which is an obligation of membership. The funding is provided in accordance with the pre-agreed schedules and spent as per the budget agreed by the governing bodies. In light of this, any business case loses its central rationale (whether or not to fund). For this reason, the UK’s assessed contribution to UNESCO is business case exempt.

Performance and progress of UNESCO as an Organisation and its programmes are assessed and monitored on a continuous basis.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The UNESCO assessed contribution programme is continuing to deliver toward expected outputs, scoring A in three of the four outputs reviewed. The overall risk of the programme remains at moderate, reflecting ongoing organisational reform progress.

Output 2 received a B rating for the second year in a row, reflecting UK concerns that SDG4 (for which UNESCO is the lead UN agency) remains significantly off-track. The UK does recognise, however, UNESCO’s important contribution to the UN Transforming Education Summit in September 2022, and the resulting 6 Global Initiatives which, if led and coordinated effectively, should result in meaningful progress. It is currently unclear who is leading/coordinating on 5 of these and the UK encourages UNESCO to step into that gap.

This is the final annual review for this programme – the programme completion review will take place in 9 months’ time which the programme formally ends. No significant changes to the programme’s design are anticipated during that period. The FCDO will continue to consider appropriate performance indicators for the next iteration of this programme, drawing on the UK’s International Development Strategy, the Integrated Review Refresh, and the new Women and Girls Strategy. Indicators and milestones will be revisited for the next programme cycle, aiming to better evaluate outcome and impact.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The UK pays a mandatory annual assessed contribution to UNESCO. The UK is obligated to pay this as a condition of our membership to the Organisation.

## C. DETAILED OUTPUT SCORING

Output Title	UNESCO develops reporting on results and impact so that it is able to demonstrate the difference it is making, with a greater focus on measuring outcomes rather than outputs and demonstrating that it is engaging with partners in the process.
Output number:		1	Output Score:	A
Impact weighting (%):		30	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
UNESCO adopts a more strategic approach to assessing and defining the impact of programmes and the concrete results they are producing on the ground, with an increased focus on measuring outcomes rather than just outputs.	UNESCO focuses on reporting on outcomes through key documents shared with member states including the SRR.	Met expectations: UNESCO has maintained its focus on reporting on outcomes rather than outputs. The new Medium Term Strategy for 2022-2029, adopted by the General Conference in November 2021, frames UNESCO’s strategic and enabling objectives in the context of their corresponding outcomes. This strategic framework in turn underpins the Programme and Budget for 2022-2025. The new, single annual C5 Implementation Report was published in August 2022.
UNESCO clearly evaluates and reports on results, impact and partnerships, and enhances the use of results in decision making.	UNESCO further develops performance indicators to ensure that evaluation is more precise and consistent across all UNESCO programmes. / UNESCO reporting enables the clear identification of programme performance across the portfolio, and enables informed decision-making, clearly capturing and communicating results and impact to member states.	Met expectations: The inaugural (August 2022) C5 Implementation Report does not provide as clear and intuitive explanation of progress against the performance indicators in the Programme and Budget as might be hoped for. However, the targets set out in the C4 Programme and Budget relate to 2023 so it is to be expected that this level of detail will be provided in subsequent issues of this Report.

Briefly describe the output’s activities and provide supporting narrative for the score.

UNESCO met expectations in both indicators for this output, therefore scoring an A rating. Due to the attenuated period of this review, there has been only one (non-extraordinary) Executive Board since the last Annual Review. The principal deliverable at the October Executive Board was UNESCO’s new, single annual C5 Implementation Report, which replaces the Performance Implementation Report and the Financial Management Report, streamlining reporting and supporting more focussed, strategic discussion at the Executive Board. The next quadrennial Strategic Results Report is not due until 2024.

There remain concerns that while UNESCO’s performance measurement structure is right, there is insufficient funding available to the Institute of Statistics (IOS/UIS) to gather a broad enough sample of data to accurately assess performance across the span of the organisation’s portfolio and geographical network.  The UK encourages UNESCO to fund the IOS/UIS sufficiently to enable effective field evaluation to supplement desk-based analyses.  The organisation’s ability to effectively communicate on impact and potential will remain key to securing additional funding.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There have been no major changes in the past year that would have any implications for the programme or its delivery, and no significant changes at the output level are planned as a result of this review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

This is the third annual review of the current programme cycle (2020-2023). Given the attenuated period of this review, the outputs and indicators that were put in place at the programme’s commencement (capturing key lessons and recommendations from the previous programme cycle), were rolled across for this review period.  On the basis of the progress made by UNESCO in terms of both impact measurement and reporting, the indicators and milestones will be revised for the next programme cycle.

Recommendations for the year ahead:

Seek adequate and more predictable core funding for the Institute of Statistics, enabling sufficiently broad sample evaluations to inform performance reporting.

Ensure that the Spring 2023 C5 Implementation Report effectively beds in the full suite of appropriate performance indicators, and communicates findings clearly (and visually) to member states.

Remain alive to the need to communicate clearly and effectively to publics and partners, not just member states, in order to enhance the organisation’s reputation (and consequent scope for partnerships, funding etc).

Output Title	UNESCO demonstrates its leadership of the education 2030 agenda and sector, effectively convening and coordinating member states and global education actors in education, and influencing governments with its policy analysis, advocacy and capacity building roles.
Output number:		2	Output Score:	B
Impact weighting (%):		30	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
UNESCO progresses work on the SDG4 agenda up to and beyond 2030 with vision, policy and impact results reporting.	UNESCO utilises the Transforming Education Summit effectively to galvanise global action in pursuit of SDG4.	Partially met expectations: Although SDG4 is codified and prioritised as UNESCO’s ‘Strategic Objective 1’ in the Medium Term Strategy, and UNESCO did successfully co-convene the TES (launching 6 global initiatives which will now be tracked by the HLSC), the UK remains concerns that progress towards SDG4 is significantly off track.
UNESCO is able to demonstrate an improved approach to convening and coordinating member states and global education actors in its Education work, and to demonstrate its advocacy, policy setting and capacity-building engagement with member states.	UNESCO to demonstrate coordination with other UN players on the Education agenda through delivery of the Transforming Education Summit.	Met expectations: UNESCO jointly led the Transforming Education Summit with UNICEF. UNESCO’s coordination in advance of the pre-summit, at the pre-summit and then at the TES was good. Focus now needs to shift to providing effective coordination across the 6 global initiatives. / There also remains a need to render the decision-making processes around the HLSC on SDG4 more transparent and to more formally define the donor constituency.
Utilise and demonstrate the value of UNESCO’s specialised education institutes (Category 1 institutes) around the world in advancing work on SDG4.	Increased cooperation between UNESCO Headquarters and UNESCO’s specialised education institutes (Category 1 institutes) around the world on SDG4.	Partially met expectations: Although UNESCO has now published the annual reports of Category 1 institutes on its website, clearer direct communication to Member States (eg through the Executive Board) on cooperation and performance is needed.

Briefly describe the output’s activities, and provide supporting narrative for the score.

UNESCO met expectations in one of the indicators, and partially met expectations in the remaining two, scoring a B rating for this output.

The UN Transforming Education Summit was held in New York in September 2022, intended to elevate education to the top of the global political agenda and to mobilise global action. UNESCO played a pivotal role in organising and delivering the Summit, which delivered 6 global initiatives to be tracked through the HLSC. The UK welcomes this. Indeed, our concerns in the lead up to the TES, reflected in the last annual review – specifically that UNESCO was not focused enough in its approach in order to drive forward meaningful change in specific, prioritised areas – were addressed by the UNESCO Secretariat, which listened to the global education community’s advice and adapted its approach accordingly. The specific, prioritised approach advocated by the global education community is reflected in the 6 global initiatives adopted by the Summit.

Since the TES, UNESCO has remained a committed and valued partner in the Global Coalition, including personally at ADG level, which the UK much appreciates. The UK is driving this forward as one of the global initiatives agreed at the TES. However, we are now at the half-way point for the realisation of the SDGs, and the UK remains concerned that SDG4 is significantly off track. It is unclear how well the TES reached decision-makers outside of the education sector, nor how the other 5 global initiatives are being coordinated and driven forward. There is a key role here for UNESCO to play.

As noted in last year’s report, the UK continues to see great value in the work of the Institute of Statistics (category 1 institute) and the Global Education Monitoring report, but would like to see greater emphasis on the disaggregation of data (and analysis and communication thereof) combined with a mainstreaming of gender expertise within the UNESCO education sector and reporting.  Furthermore, there are currently significant gaps in the data we need to track progress against SDG4.  In poorer countries, reliable information on what children are learning, especially in primary school, is not collected frequently or at all.  There is therefore no ‘feedback loop’ to national education policy and planning.  The Covid pandemic has deepened the learning crisis and understanding students’ learning levels – as they return post school closures – has never been more urgent.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There have been no major changes in the past year that would have any implications for the programme or its delivery, and no significant changes at the output level are planned as a result of this review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

This is the third annual review of the current programme cycle (2020-2023). Given the attenuated period of this review, the outputs and indicators that were put in place at the programme’s commencement (capturing key lessons and recommendations from the previous programme cycle), were rolled across for this review period.  Indicators and milestones will be revised for the next programme cycle.

As noted above, UNESCO did take on board the recommendation in the last annual review to: pursue a narrower, more targeted approach to realising SDG4, recognising the importance of foundational skills, focussing minds through international events and communications on making meaningful, measurable progress on the global learning crisis.

Recommendations for the year ahead:

To continue being an active partner in the Global Coalition (getting foundational learning right is critical to getting SDG4 back on track).

To grip the coordination of the 5 other global initiatives agreed by the TES and bring all 6 together.

Use its position to ensure that education is a key theme at the UN Summit of the Future.

Ensure sufficient expertise in the Secretariat and the Institute of Statistics to mainstream gender equality as a core element of UNESCO’s approach and reporting.

Seek greater disaggregation of education data, to enable a more insightful, reliable and effective data-driven policy response.

Output Title	Organisational effectiveness and risk management - reform, transparency, accountability and efficiency
Output number:		3	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
UNESCO shows commitment to, and demonstrates, improving transparency.	UNESCO provides thorough updates to member states on progress made towards greater transparency and accountability, both through detailed and well-structured presentations and during the administrative sessions of the Executive Boards.	Met expectations: The requirement for a culture of transparency and accountability to be embedded across the organisation is encoded in the new Medium Term Strategy. The Secretariat plans to achieve this through internal audits (providing assurance on adequacy and effectiveness of internal controls, risk management and governance processes), investigations (promoting accountability), and evaluations (informing decision-making to improve relevance, coherence, efficiency, effectiveness, impact and sustainability of UNESCO’s actions). At the 214th Executive Board (October 2022), the Secretariat brought forward a concept paper through which to consult member states on prospective revisions to the Financial Regulations and Rules of the organisation. It also presented the annual reports of the Internal Oversight Service and the Ethics Office.
UNESCO has robust systems in place to prevent and respond to fraud	UNESCO has robust procedures in place for effectively preventing, detecting, investigating and sanctioning cases of fraud, corruption and other financial irregularities, effectively training staff and taking a position of maximum transparency with member states on any fraud or corruption issues.	Partially met expectations: As noted in the last two reviews, UNESCO has the appropriate policies in place, but currently still lacks sufficient resources to fully manage financial risk. UNESCO is aware of this risk and is strengthening the Secretariat’s capacity to do so. A dedicated team is in now place, but as far as we have been able to ascertain is not yet fully staffed up.
UNESCO works to streamline services and reduce costs	Operational effectiveness is improved through further reduction of administration costs, reform of UNESCO’s network of field offices, improved resource mobilisation capabilities and improved approach to prioritisation when looking at programme areas.	Met expectations: Over recent years, much progress has been made to improve the operational effectiveness of the Secretariat. Significant initiatives are also underway to exploit opportunities for efficiencies through collaboration with other UN bodies within the field network. Agreement was reached during the October Executive Board to begin the reform of the field network, taking a phased approach with no initial impact on the regular budget; the DG will report to the October 2023 Executive Board with an estimate of the global cost of the reform programme.
UNESCO to demonstrate further progress on its reform programme.	UNESCO to regularly report to and consult member states on implementation of its reform plan and demonstrate progress on implementing UN wide reforms	Met expectation: The UK welcomes UNESCO’s continued focus on organisational reform, particularly Secretariat’s attempts to progress field network reform. UNESCO reports annually on ‘the repositioning of the United Nations development system’ – the next such report will be provided in advance of the May Executive Board.

Briefly describe the output’s activities, and provide supporting narrative for the score.

UNESCO met expectations across 3 of the 4 indicators for this output, partially meeting expectations on the remaining 1, therefore scoring an A rating.

UNESCO has improved significantly in recent years in terms of organisational effectiveness and risk management, with further gains made in this review period.  Under the current DG, the Secretariat is performing strongly on commitment to, and demonstration of, transparency and reform.  The Secretariat’s commitment to further reporting on field network reform is particularly welcome, although we note that progress is likely to be restricted due to the strongly held views of Member States in affected regions.

As noted in the last review, there remain two key issues to address on the financial front.  While UNESCO has clear policies and procedures to prevent, detect, investigate and sanction fraud and other financial irregularities, operational and financial risk management capacity continues to be overstretched, risking the effectiveness of those policies and procedures. There also remains a sense that UNESCO is institutionally reticent to close projects even where performance cannot be clearly evidenced.  More detailed reporting to Member States on when this does occur would be helpful.

Describe any changes to this output during the past year, and any planned changes as a result of this review

There have been no major changes in the past year that would have any implications for the programme or its delivery, and no significant changes at the output level are planned as a result of this review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

This is the third annual review of the current programme cycle (2020-2023). Given the attenuated period of this review, the outputs and indicators that were put in place at the programme’s commencement (capturing key lessons and recommendations from the previous programme cycle), were rolled across for this review period. Indicators and milestones will be revised for the next programme cycle.

Recommendations for the year ahead:

More detailed communication to Member States on initiatives undertaken to close underperforming projects.  This will give Member States greater confidence in the continued efficacy of UNESCO’s institutional reform.

Ensure the financial risk management function is adequately staffed.

Output Title	Partnerships and effective coordination
Output number:		4	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
UNESCO has a clear strategy regarding its interaction with other international organisations that overlap with/ complement areas of its mandate.	UNESCO strengthens, continues and creates partnerships and synergies, demonstrating to donors the organisation’s impact and comparative advantages compared to other United Nations agencies.	Met expectations: UNESCO has a Comprehensive Partnership Strategy and maintains an extensive list of partners on a dedicated webpage designed to demonstrate the value of partnering with UNESCO. The new C5 Implementation Report notes that new partnerships established so far under the Medium Term Strategy 2022-29 have resulted in a 6% increase in the volume of resources mobilised this biennium.
UNESCO demonstrates full engagement and coordination with UNSG’s UN reform efforts.	UNESCO engages with and implements UNSG reform plans concerning the Resident Coordinator system.	Met expectations: UNESCO participates in the UNSDG Task Force on Resident Coordinator Talent Management and is also engaged in a multi-year development process for a new coordination instrument to support the work of UN Development and Resident Coordinators. UNESCO actively advocates for deeper integration of UNESCO work within Cooperation Frameworks across the regions, and incentivizes Regional Coordinators to advance a normative agenda including through proposing changes to their results framework. UNESCO co-hosted the first round table with United Nations Resident Coordinators on indigenous knowledge systems and their role in delivering the Sustainable Development Goals.
UNESCO further improves collaboration between headquarters, institutes, regional and country offices to translate the emerging priorities into coherent action.	UNESCO reports to member states on progress made towards improving partnerships and better internal and external coordination, both through detailed and well-structured presentations and during the sessions of the Executive Boards.	Partially met expectations: UNESCO continues to report to member states on progress and plans for improving partnerships and for better streamlining and inter-sectoral working during Executive Board sessions. While ambition on better internal coordination is high, UNESCO still needs to demonstrate better coordination between Headquarters, field offices and its Category 1 institutes.

Briefly describe the output’s activities, and provide supporting narrative for the score.

UNESCO met expectations across 2 of the 3 indicators for this output, partially meeting expectations on the remaining 1, therefore scoring an A rating.

UNESCO’s network is one of its key strengths – its network of 193 member states, 199 national commissions, its own network of field offices, and its wider network of implementation partners.  As a normative body it is reliant on policy implementation partners for action and delivery.  In recognition of this, reporting on partnerships is now embedded in key papers presented to the Executive Board by the Secretariat to a greater degree than was previously the case – including through the new C5 Implementation Report. The 6% increase of partner funding in this biennium speaks to UNESCO’s efforts to create and strengthen partnerships, and to the trust of partners in UNESCO’s expertise and capability.

UNESCO’s efforts in recent years to improve its engagement with other UN bodies at HQ and network level bore fruit at the Transforming Education Summit (co-convened with UNICEF).

Describe any changes to this output during the past year, and any planned changes as a result of this review

There have been no major changes in the past year that would have any implications for the programme or its delivery, and no significant changes at the output level are planned as a result of this review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

This is the third annual review of the current programme cycle (2020-2023). Given the attenuated period of this review, the outputs and indicators that were put in place at the programme’s commencement (capturing key lessons and recommendations from the previous programme cycle), were rolled across for this review period.  The indicators and milestones for this output will be revised for the next programme cycle to better reflect progress to date.

Recommendations for the year ahead:

Reporting should include an assessment of the effectiveness of initiatives undertaken (across UN reform, internal cooperation, and implementation partnerships), not just listing what has been done, but the impact, reach and VfM of those activities.

## D: VALUE FOR MONEY

The UK’s contribution via this programme is an assessed contribution which is an obligation of membership. The funding is provided in accordance with the pre-agreed schedules and spent as per the budget agreed by the organisation’s governing bodies.

Multilateral organisations generally perform a wide range of functions, and many operate across multiple sectors.  This gives rise to conceptual difficulties in assessing their value for money, often compounded by practical problems of gaps in the data on both outcomes and costs.   However, UNESCO has taken significant steps to improve its internal operations and delivery, and offers better value than it did at the time of the last Multilateral Development Review in 2016. The efforts of the current Director General, the completion of the Strategic Transformation plan (which addressed the optimisation of administrative and management issues), and the embedding of transformation recommendations into the new and improved Medium-Term Strategy, remain UNESCO’s best route for maximising progress on effectiveness and organisational capability.   Assessing the results of UNESCO’s new Medium-Term Strategy and ongoing transformation efforts will provide for a good measure of the organisation’s effectiveness and organisational capability and will inform the value for money question in coming years.

E: RISK

The overall risk of the programme remains moderate, reflecting UNESCO’s ongoing efforts to strengthen internal risk management policies and processes while recognising there are still some areas in need of improvement.

The FCDO has assessed that risks related to this programme exist in the following areas: financial and fiduciary, safeguarding, delivery, operational and reputational. Major risks are recognised in the following areas:

Policy and Programme Delivery: So far UNESCO is managing to deliver across its mandate, and it has strengthened its own financial reporting over the last (2021-22) biennium. However, particularly in light of global inflation and rising UN salary costs, UNESCO now needs either increased regular investment (for example through the return of the United States) or for member states to reduce the scope of its mandate if it is to remain a viable and effective organisation. The alternative is an overreliance on voluntary or external funding, which is unpredictable, unsustainable, and in most cases ring-fenced for specific projects, leaving UNESCO’s ability to fulfil its core functions underpowered.

Reputation: the lack of institutional levers with which to challenge the influence of China and Russia within UNESCO leaves the organisation open to severe reputational risk. The FCDO will continue to watch out for malign attacks, drawing on groups of friends and allies at UNESCO to protect international standards and norms.  The SRO will continue to build close working relations with the FCDO China, Russia and multilateral teams, to stay ahead on geopolitical issues and their potential for spill-over into the UNESCO arena.

All risks are continuously monitored, managed and updated by the UNESCO SRO, who keeps Directors and Ministers updated on emerging issues.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

UNESCO has a wide mandate which is not adequately served by its regular budget.  This is not due to financial mismanagement, but global rising costs and the cessation of the United State’s contributions in 2011 (which alone left a 22% hole in the organisation’s budget).  It is also not uncommon for many member states to pay their assessed contributions late in the year (including the UK), or to be in arrears, which further complicates UNESCO’s in-year financial planning.

UNESCO has absorbed these budgetary pressures as far as possible through the streamlining of staff structures and administrative costs, but will struggle to find further efficiencies.  The UNESCO Secretariat seeks increased voluntary contributions to supplement the organisation’s income, and has some (but limited) success in securing external fundraising.  While an increase in voluntary funding in recent years is symptomatic of the trust and confidence of UNESCO’s donors, such donations are often earmarked and so cannot be used to fund central functions.  An overreliance on voluntary contributions is neither stable nor sustainable, and can lead to the political manipulation of UNESCO’s budgetary resources by those member states who invest most in this regard.

So far UNESCO is managing to balance the books, and has strengthened its own financial reporting over the last (2021-22) biennium, but now needs either increased regular investment (for example through the return of the United States) or for member states to reduce the scope of its mandate if it is to remain a viable and effective organisation.

Date of last narrative financial report	31 August 2022	Date of last audited annual statement	31 August 2022