## Annual Review

Title: Programme for Strengthening State Capabilities in India
Programme Value £ (full life): 4,995,000		Review date: 27/02/2021
Programme Code: 300738	AMP start date: 27/02/2019	AMP end date: 01/11/2023

Summary of Programme Performance
Year	2020	2021
Overall Output Score	A	A
Risk Rating	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300738/documents
DevTracker Link to results framework:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300738/documents

List of Abbreviations

Acronym	Full Form
AR	Annual Review
CBIF	Common Back-End ICT Infrastructure Facility
CEIP	Carnegie Endowment for International Peace
CPR	Centre for Policy Research
Discom	Distribution Company
EFO	Externally Financed Outputs
DoPT	Department of Personnel and Training
EPPP	Economic Policy and Prosperity Partnership
FCDO	Foreign, Commonwealth and Development Office
FRAC	Framework of Roles, Activities and Competencies
GoI	Government of India
GPI	Government Partnerships International
IUTF	India Umbrella Multi-Donor Trust Fund
LBSNAA	Lal Bahadur Shastri National Academy of Administration
NGC	National Gender Centre
PBPK	Paani ‘Bachao Paisa Kamao’
MTFF	Medium-Term Fiscal Framework
NPCSCB	National Programme for Civil Service Capacity Building
PSSC	Programme for Strengthening State Capabilities
SARTTAC	IMF South Asia Regional Training and Technical Assistance Centre
TA	Technical Assistance

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme [1-2 paragraphs]

The Programme for Strengthening State Capabilities in India (PSSC) is a £4.99m programme, which aims to strengthen capacity and capabilities of state and sectoral institutions and support the Government of India (GoI) in reforms to bring in greater transparency, accountability and improve delivery of public services commensurate with its development and growth ambitions.

The expected impact of the programme is enhanced state capability for service delivery leading to better performance towards the SDGs. The overall outcome envisaged is improved policies and systems to strengthen states’ capabilities. The PSSC has built strategic partnerships, including three new partnerships in the reporting period, with multilateral organisations, prominent think tanks and UK government departments to deliver on the results outlined in the log frame. These partnerships include:

- World Bank: Two Externally Financed Outputs (EFO) on Energy and Strategic State Engagement have supported States to utilise and implement evidence-based approaches, pilots and knowledge products to reform state level policies, strengthen public institutions and their capacities to deliver services and facilitate knowledge sharing across states.
  [note] ‘State Partnership for Enhancing Commercialisation of the Power Sector’
  [note] ‘Strategic State Engagement for Policy Reforms and Strengthening Capabilities’
- IMF South Asia Regional Training and Technical Assistance Centre (SARTTAC): An ongoing partnership in the state of Odisha to support the state’s capabilities to strengthen its public finance management frameworks and build capacities of government officials on budgetary issues, including on managing fiscal risks, medium term macroeconomic forecasting and cash management.
- Lal Bahadur Shastri National Academy of Administration (LBSNAA): Targeted capacity building of government officials on gender mainstreaming and gender sensitivity in public service delivery.
- Carnegie Endowment for International Peace (CEIP) and Centre for Policy Research (CPR): This new partnership will implement an evidence-based policy approach to improve Indian states’ regulatory design and capacity to make markets work better and strengthen India’s apex institutions.
- Government Partnerships International (GPI): This new partnership aims support the capacity building of India’s civil services by supporting reforms on training and career development. Working with the Department of Personnel and Training (DoPT), the World Bank and others on Mission Karmayogi or the National Programme for Civil Service Capacity Building (NPCSCB), the partnership will support India’s civil service to design, implement and deliver policies and services for its citizens.
- Contribution to the World Bank’s new India Umbrella Trust Fund: This new partnership is set up to pool resources from the PSSC, amongst other programmes, to support its core agenda strengthening Indian states’ systems on themes of climate resilience, social protection, civil service capacity building, economic reforms and jobs and innovation.

Summary supporting narrative for the overall score in this review [1-2 paragraphs]

This Annual Review (AR) covers the second year of implementation of PSSC. Implementation of activities and engagement with state governments under ongoing partnerships was affected by the onset of the COVID-19 pandemic and related lockdowns immediately after the start of the current reporting period.

At an operational level, there were two substantive changes to the programme in the reporting year: 1) A Ministerial reprioritisation exercise resulted in a reduction of the overall budget available for activities in the reporting year. 2) As a result of personnel and other changes, the programme saw changes in SRO and Programme Manager mid-way through the year. Despite these significant challenges, the programme is able to report the following key achievements:

Partnerships: Building on existing partnerships and additional support to new partners enhanced the portfolio of work on strengthening states’ capacities for policy and regulatory design & reforms and strengthen state’s institutional mechanisms & systems to better deliver services to its citizens. Analytical support, technical assistance and capacity building activities cover a broad range of policy issues with a focus on economic and governance systems, including on public procurement, energy, labour markets, improved sustainability of state distribution companies, strengthening capabilities of India’s civil services & its civil services systems, urban governance, data policies, and public finance management.

Four new partnerships – two with think tanks CPR and CEIP, one with a UK government partner (GPI) and one with the World Bank under a new Trust Fund – have been added with the intention of scaling activities and engagement with states to contribute to overall programme objectives.

Addressing challenges created by the COVID-19 pandemic: The onset of the COVID-19 pandemic, lockdown measures and the subsequent economic fallout in India changed the operating context significantly. Whilst there was an initial impact on the pace of delivery against objectives and outputs, where feasible, both the FCDO team and partners have responded effectively and minimised the impact on programme delivery by:
- Adapting to remote delivery and virtual engagement: This has been successful in the delivery of training and capacity building webinars, particularly in the case of the IMF SARTTAC (see below for lessons on delivering virtual training successfully) and in the delivery of peer support activities between senior government officials in India and the UK as facilitated through GPI.
- Adjusting workplans as required: Partners’ engagement on ongoing projects with central and state government was severely disrupted in the first two quarters of 2020-21. While partners managed this by engaging remotely and starting field work as soon as was feasible, some activities have been reprioritised for implementation in the next financial year and completion dates have been extended as required in agreement with the FCDO to meet agreed objectives.
- Contributing to understanding COVID-19 impacts and recovery pathways: Partner activities have focused on informing and supporting governments with evidence and knowledge to support recovery from the impact of the pandemic and the lockdown. Several activities have focused on building macro-fiscal resilience, understanding the impact on livelihoods and strengthening state systems to deliver critical public services. For example:
- The IMF SARTTAC provided support to the Government of Odisha in managing fiscal risks for macro-stability and on budgeting during periods of uncertainty created as a result of revenue shortfalls from a drastic reduction in economic activity through the lockdown.
- CEIP is building a household level, gender disaggregated evidence base on the impact of COVID-19 and the lockdown on labour markets and livelihoods in 4 northern Indian states (Bihar, Jharkhand, Madhya Pradesh and Uttar Pradesh). This work particularly focuses on issues of gender, social change and urbanisation. The study also looks at the medium-term impact of the lockdown on labour market outcomes in Tier 2 urban areas in these states.

The programme has performed well against all milestones scoring an ‘A’ overall despite the substantive challenges to programme delivery.

Major lessons and recommendations for the year ahead [1/2 page]

Major lessons:

- Engagement and programme delivery: All partners have pivoted to using virtual and other remote forms of engagement as a way to implement activities. However, not all activities are suited to virtual delivery; these depend on the type, timing within the project cycle and level of engagement required in successful delivery. For instance, implementation of technical assistance activities provided to Odisha and Punjab governments by the IMF and the World Bank were significantly impeded by the lockdown and the lack of the ability of the staff to travel for meetings and engage in policy dialogue with senior government officials and policy makers. On the other hand, SARTTAC has been very successful in transitioning to the use of virtual platforms to deliver its training activities. In fact, SARTTAC reported that virtual delivery of training activities has enabled an improvement both in the quality of instruction (as a larger pool of experts are available remotely) and expanded participation base, including senior level officials for events. As some of these activities will likely to be delivered using virtual platforms, the SARTTAC team have recommended that more attention must be paid in improving user engagement, designing shorter sessions and more tailored materials and deliberative choice of topics covered when delivering activities virtually. Going forward, lessons from SARTTAC’s experience of delivering virtual training modules should be shared with partners designing bespoke similar training activities. The experience has also demonstrated the limits of delivering technical assistance and engaging successfully on policy dialogue remotely; future programming should factor this into the redesign of workplans if an extended period of disruptions is to be expected.
- Adaptive programming: The pace of change and reprioritisation across the programme’s budget and portfolio to respond to the opportunities and challenges created by the pandemic has put more emphasis on the need for adaptive programming. For instance, where feasible, multilateral and other partners have focused on reprioritising activities to strengthen the evidence base on the impact of the pandemic and the lockdown to inform emerging policy design and to support institutional capacity building for longer term recovery in response to the challenges created by COVID-19. Examples include capacity building activities on managing state finances and fiscal risks under periods of uncertainty, adding research components to a labour market survey to understand the long-term impact of the COVID-19 lockdown on labour markets and women’s labour force participation, and technical assistance and analytical support to state governments to build more efficient and effective public systems such as on direct benefit transfer to vulnerable groups and on state level procurement policy. Adaptive programming has been made possible due to two factors – the ability of partners to pivot or prioritise activities to respond to emerging demands and the flexibility built into the framework partnership agreements to respond to these priorities. On the former, multilateral partners have been able to adapt and respond given the scale and scope of their work and engagement. On the latter, the framework of the partnership agreements with CPR, CEIP and GPI include both a core set of longer-term deliverables as well as responsive components that are agreed based on emerging priorities on a quarterly basis. A key lesson is the need to build in responsive programme elements into the framework of the partnership agreements to facilitate such adaptive, responsive programming.
- Building coherence across partnerships for scale: There are a number of states, policy areas and institutional systems that the programme designed interventions to support through its partnerships. A key learning over the last year of interventions is the need to focus on scale, scope and coherence across programmatic activities and partnerships to scale the likely outcomes and impacts of programme interventions. Where feasible therefore, programme interventions should further prioritise themes covered through its partnerships. An example of this is emerging in the case of strengthening the capabilities of India’s civil services. The bespoke training, peer learning activities and the technical assistance interventions through SARTTAC, the World Bank, GPI and LBSNAA contribute both towards improving the capabilities of India’s civil services on policy reform and delivery of public services as well as in strengthening the underlying systems that support the effective performance of civil services.
Recommendations for the year ahead:

- To consolidate programme partnerships and ensure they all contribute to the overall programme coherence and goals (Action: FCDO – ongoing).
- To redesign the PSSC to align with the FCDO India Country Plan, focusing more strongly on elements of Open Society, Democratic Governance and Institutions. The PSSC will contribute to the development of the Democratic and Institutional Partnership between India and the UK in accordance with the aspiration of the 10-year India-UK Road Map, currently under development (Action: FCDO, September 2021)
- To identify new and build on strategic themes to contribute to the Democratic and Institutional Partnership. New areas currently under consideration include state capacity on governance of data and digital markets, understanding India’s apex institutions, strengthening India’s civil services systems such as on competency frameworks, recruitment, talent management and career development and to support state capacity for better regulation and management of India’s factor markets (Action: FCDO – ongoing each quarter)
- To work closely with the FCDO economics and political teams to prioritise activities within the portfolio, particularly through the responsive programme partnership components (Action: FCDO – ongoing)
- To increase engagement with state and central governments by better leveraging ongoing partnerships with all partners (Action: FCDO – ongoing)

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

The overall theory of change has not changed during this reporting year and there have been no changes to outcome and impact indicators. The overall programme outcome is to strengthen the capacity of institutions in select states and sectors to develop and implement good policies and practices through 1) Engagement with states and sectors to understand drivers and barriers of inclusive growth, fiscal condition, governance readiness; 2) Demand driven research and evaluation to inform policy and institutional and implementation capacity strengthening; and 3) Capacity development trainings and associated activities to states and sector institutions. As recommended in the previous AR, milestones have now been set for the remainder of the programme. These were finalised after the onset of the pandemic and so reflect the changing and challenging operating and delivery context.

Economy: In its second year of implementation, the programme has achieved sufficient economy. The main cost drivers are related to setting up of new partnerships, shaping and delivering knowledge products, technical assistance missions, training seminars and policy support to state governments, ensuring coordination among partners and delivering on planned outputs. For the partnerships with CEIP, CPR and GPI, expenditure on programme expenditure comprises 81% with overhead costs agreed in line with HM Treasury guidance on good value for money when working with partners. As travel has not been possible for much of the year, costs associated with this have been reduced across all partnerships and used to extend the reach of programme activities through virtual delivery.

Efficiency: The programme’s overall budget was reduced during the 2020/21 financial year from £750,000 to £393,333 for until March 2021. This has led to a scaling back of some activities with partners and reprioritisation of activities to the next financial year in some cases. Despite a reduction of the annual budget by 47%, the programme has been able to deliver most of the intended outputs, including new partnerships. The programme has been able to distribute costs across a number of thematic areas and partners to support the production of 16 knowledge products, 3 pilots and 5 capacity development trainings. Programme partnerships have delivered engagement at the highest levels of state and central government as well extensive coverage through training and capacity building activities. Examples include:

- GPI: The peer learning and exchange facilitated with the Department of Personnel and Training (DoPT) to contribute to the process of strengthening the individual and institutional capacity building of India’s civil services, such as the development of the civil service wide framework of roles activities and competencies and on the design principles to develop and deliver e-learning content to civil servants is a good example of activities where returns on policy engagement are feasible through modest financial investment. This has generated further interest in a systematic partnership to learn from the UK’s experience on the capacity building apparatus for civil services for better public services delivery.
- LBSNAA: Training material developed in partnership between the National Gender Centre (NGC) at LBSNAA, the apex training institute for India’s civil services with the FCDO to train senior officers across several government departments on gender analysis and planning in the previous reporting year has been deployed as a core part of the Foundation Course for 430 Officer Trainees. The NGC further plans to join up on these trainings with the Ministry of Women and Child Development and the Ministry of External Affairs.
- IMF SARTTAC: 105 state officials participated in two training webinars on themes of managing fiscal risks for macro-fiscal stability and preparing budgets under uncertainty and 51 state level officials participated in a seminar on public finance management for state finance secretaries.
Effectiveness: Despite the disruptions caused to programme delivery by the COVID-19 pandemic and other changes during the reporting year, a number of knowledge products and technical assistance provided to state governments have contributed to the overall programme outcome (Improved policies and systems to strengthen government capabilities) as follows:

Policy and regulatory reform:
- Energy: A key study on an IT Roadmap for the West Bengal Electricity Distribution Utility to inform the design of ICT systems for better revenue realisation has enabled the state government to leverage a proposed loan of $65 million from multilateral banks to build the ICT infrastructure in the state.
- Agriculture: Knowledge products, including those informing public debates supported under this programme have built understanding of, and are contributing to, public policy engagement on regulatory reforms in India’s agricultural markets with civil society actors, Government of Odisha, multilateral partners and Ministry of Rural Development.

Strengthened Institutional Systems
- Public Finance Management: A key outcome of the fiscal strategy technical assistance provided to the Government of Odisha has been the establishment of a Strategic Fiscal Planning Unit within Odisha’s Finance Department (FD) staffed with a mix of practitioners and academics from the Centre of Excellence in Fiscal Policy and Taxation trained in macro-fiscal concepts and tools. The Unit works under the guidance of the Joint Secretary (Budget), and its activities are subject to review by a committee headed by the State Finance Secretary, which is key to its work being translated into concrete actions.
- Governance and Institutional Reforms: Analytical inputs under the partnership with the World Bank have informed a number of governance reforms undertaken by the Government of Punjab such as on the new Punjab State Data Policy in 2020, the Public Investment Management (PIM) Unit Government Order issued in 2020, and design of rules under the Punjab Transparency in the Public Procurement Act passed in 2020. Similarly, analytical inputs on groundwater management institutions underway in Punjab will support the newly set up Water Resources Regulatory Authority as well as a Groundwater Directorate for sustainable groundwater management and building climate resilience in a state heavily dependent on agrarian activity.

It is too early to report on the impact of the programme’s partnerships on equity. The partnerships under the programme target states in India that have large proportion of vulnerable communities.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

The programme adapted to the ongoing pandemic and budget reductions during this reporting period, but currently is broadly on track to meet the programme outcomes and impact. Partnerships for the next year will be considered based on funding available for the rest of the programme and the outcome of the Integrated Spending Review.

On track:
- All activities under the State Partnership for Enhancing Commercialisation of the Power Sector EFO were delivered during the reporting period as planned.
- Whilst some technical assistance and training activities under the partnership with IMF SARTTAC have been reprofiled to meet the scope of the reduced budgets for the current reporting year, the outputs from this remain on track.
- After initial delays in the signing of new partnerships with CEIP, CPR and GPI due to budgetary reprioritisation related decisions, these partnerships have yielded knowledge products and peer learning workshops to contribute towards programme objectives. In the coming year, it is intended that the partnership with CPR and CEIP on state capacity, apex institutions regulatory reforms and design will focus further on selection of states and sectors in addition to the ongoing research on agriculture and on labour markets in four north Indian states.
Deferred activities:
- Delivery of activities under the Strategic State Engagement EFO have been delayed. These focus on providing technical assistance to the Governments of Punjab and Odisha and as they require close engagement with government partners, the slowdown resulting from the COVID-19 lockdown affected both new and ongoing activities. However, a revised workplan has been agreed; the FCDO team will work closely with the World Bank with a view to ensuring the outputs support the envisaged outcomes over the next year.
- Although the 1st annual review recommended that the programme further develop the partnership with LBSNAA to support capacity building of Indian civil services on other priorities such as private sector development, urban issues and city management and on climate change, this has not been feasible due to the reduction in budgets during the reporting year.
- A planned secondment to the World Bank of a senior adviser to support wider to the civil services strengthening agenda in India, an area of key partnership interest both for the World Bank and the Government of India has been delayed as a result of budget reprofiling and the merger to create the FCDO. This may be considered in the next financial year as a wider part of a coherent set of activities with the World Bank adjusted as necessary to budget constraints.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

Despite the challenges faced in the reporting year, the programme has continued to deliver value for money. Ongoing and new partnerships are contributing to the programme’s core goals around building state capacities for institutional strengthening and policy reform. The progress so far, and current partnerships with think tanks to provide high quality evidence and policy analysis on governance issues, as well as targeted support to the GoI’s civil service capacity strengthening agenda, highlight the impact that can be achieved by the end of the programme.

The ongoing and planned interventions are strategically important for the UK and India and involve engagements with key stakeholders, including at senior levels in selected states on a number of key themes. For example, the partnership with GPI has previously led to direct engagement with Department for Personnel and Training (DoPT) and continues to provide engagement at senior GoI levels to support strengthening of institutional capabilities on key priorities. Furthermore, in the coming year, the PSSC will continue to respond to priorities under the new UK-India strategy and the 10-year UK-India Roadmap, as noted above.

In addition, the COVID-19 crisis has created an urgency for key reforms to build macro-fiscal resilience, protect lives and livelihood and strengthen the state systems to deliver public services which PSSC is well placed to respond to. State governments are now actively engaging with partners to advance implementation of reforms and priority programs to build back better.

With 2 years of the programme remaining there is further scope to identify 1 or 2 more critical areas of work to complement existing work, subject to funding available.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Strategic engagements with states leading to stronger partnerships
Output number:		1	Output Score:	A
Impact weighting (%):		60	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
Number of pilots supported with a pro-poor impact	3	3 / Milestone on track to being achieved / ‘Demonstration Farms’ programme: new approaches for crop diversification and groundwater management/ conservation and technology applications. / TA on Public Financial Management (PFM) in Odisha / Pilot of training material developed on public services and gender issues and tackling gender-based violence for incoming batch of Indian Administrative Service (IAS) officers
% of engagements involving senior government officials	60%	77% / Milestone exceeded

Briefly describe the output’s activities, and provide supporting narrative for the score. [max 1/2 page]

Through the Strategic State Engagement EFO, there has been engagement at the highest-level, including regular interactions with senior state officials with 8 State departments in the Punjab. Technical inputs and good practices from other states shared by the World Bank have informed governance and institutional reforms as described above. In Odisha, discussions have focused on 1) Integrated social protection delivery system 2) Modernising agriculture and allied sectors and 3) Developing human resources management systems for civil services strengthening. These will be progressed further in the coming year. With the Energy EFO concluding in January 2021, and the Strategic State Engagement EFO in its final year of implementation, discussions have been held with the World Bank to further deepen the partnership and consolidate work under the EFOs into an India Umbrella Multi-Donor Trust Fund (IUTF) that will focus on building capability of state institutions, policy reform and enhance institutional and sectoral resilience which PSSC has committed to partly funding.
[note] Finance, Planning, Governance Reforms, Agriculture, Energy, Groundwater Management, Local Government and Women and Child Development departments
[note] Agricultural Produce Markets (APM) Act, 2020, Punjab Transparency in Public Procurement Act; Public Investment Management (PIM) Unit Government Order; Punjab State Data Policy

The programme has seen excellent engagement by the IMF’s South Asia Regional Training and Technical Assistance Centre (SARTTAC) with the Finance Department in Odisha, focusing on improving the budget process which has potential to be replicated in other states. The preparation of credible budgets, embedded in a medium-term framework and reflecting strategic priorities, has allowed resources to be appropriately allocated to poverty reduction and more broadly to achieving the SDGs. Furthermore, work on the early recognition of risks is ongoing, which aims to ensure that the authorities can respond nimbly to adverse developments, the importance of which has been highlighted by the COVID-19 pandemic. The activities described in Output 2 below demonstrate the effectiveness of this pilot programme in Odisha and how the technical assistance and training sessions can be utilised in other states of India.

The programme continued to see the impact of the risks and 9 case studies on tackling violence against women and children developed under the programme have been turned into teaching aids which will be used by training academies for judges, administrators, police, prosecution officers and medical officers across India. In the future, LBSNAA plans to work with the Indian Ministry of External Affairs and the Ministry of Women and Child Development on these issues.

A new partnership with Government Partnerships International (GPI) has been developed during this reporting period. Activities will focus on selected aspects of capacity building of civil services and support the GoI’s National Programme for Civil Service Capacity Building (NPCSCB) through engagement with the Department of Personnel and Training (DoPT). This is an important priority for both the UK and Indian governments with engagement from senior officials on both sides. A roundtable focusing on 4 topics (Capability, Competency Frameworks, Learning and Talent) was held in November 2020 with 26 senior GoI officials participating. Following this event, FCDO-GPI have agreed to support the DoPT in up to 7 key areas, including on the Framework of Roles, Activities and Competencies (FRAC), a tailor-made competency framework for the Indian civil services, content design and development to deliver e-learning to civil services and key institutional mechanisms to support the civil services with working groups for each to be established in early 2021.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

It is inherently difficult to quantify the value for money for this output. The partnerships have enabled the FCDO to deepen engagement, share best practices and lessons between states and bring in peer experiences from the UK to state and central governments in areas mutually agreed between the UK and India. The value for money of the different components varies depending on the kind and scope of partnerships.

The partnership through GPI is a good example of high-value engagement with a nodal government stakeholder on an issue that is viewed as a priority by both the UK and India as it is central to the delivery of public services. In terms of economy, while relatively limited financial resources are deployed in engaging with GoI, the non-financial resources required (e.g. FCDO staff time), remain substantial. However, in terms of effectiveness, the partnership has led to a peer learning based engagement to catalyse institutional change, bringing together the best of the UK’s expertise to respond to the key GoI priority of improving the capabilities of India’s civil services to best design, implement and deliver public services. In terms of efficiency, the World Bank partnership covers a more expansive set of activities and sectors in two Indian states. In terms of effectiveness, this has provided high-level engagement across multiple state departments, providing a more coherent state-wide partnership platform in Punjab on governance issues. For example, this has enabled the FCDO staff to engage with the chief secretary’s office in Punjab on building coordinated state systems for better governance and delivery of public services. In the new financial year, VfM indicators on this output may be impacted due to the impact of cuts in the UK’s ODA on the delivery of planned activities.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

There have been no changes to the output this year. However, as recommended in the previous AR, milestones for the remainder of the programme have been finalised with input from the FCDO Results and Evaluation Advisor. In addition, as noted above, new partner GPI is contributing to this output.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Progress on recommendations from the previous AR
The recommendation last year was for the indicators and milestones to be reviewed and updated; this was completed with milestones from the remainder of the programme finalised. No changes were made to the indicators.

Lessons learned this year
- Substantive engagement with state and central government departments have been made possible through the use of virtual platforms. This modality could be better suited to training activities and continued dialogues where these relationships have already been strongly established. They might be less well suited to others where the activities require in-person engagement or delivery of technical assistance missions that require on-ground presence. In the future, the programme must factor these into the planning of activities with partners.
- Engagement with state and central government partners is key to delivering a coherent set of results on this programme. As the COVID-19 related travel restrictions ease, going forward, it will be important to step-up engagement both directly with government partners and better leveraging the networks and relationships through current programme partners

Recommendations for the year ahead
- The programme should seek more sustained engagement with state and central government partners on policy and regulatory reforms on a consolidated set of thematic areas.
- As the FCDO’s priorities in India evolve, including to support India build recover from the pandemic, the programme should further consolidate the scope of ongoing activities and partnerships. In particular, the programme should leverage current and build new institutional partnerships, including on economic reform and governance issues, based on the priorities identified between the UK and Indian governments, such as in the 10-year UK India roadmap.
- The programme should work more closely with programme partners to better monitor and report on the pro-poor outcomes of interventions implemented - particularly, how the strengthened institutional capacities and policy reform translate into positive impacts for vulnerable communities in these states.

Output Title	Capability building mechanisms to influence key reforms in select states and sectors
Output number:		2	Output Score:	A+
Impact weighting (%):		40	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
Demand led evaluation of government pilot intervention	1 completed and disseminated	1 / Milestone achieved: evaluation of Direct Benefit Transfer of Electricity (DBTE) subsidies in the State of Punjab
Number of knowledge products/exchange programmes facilitated to inform policies - knowledge products, visits, policies informed	4	16 / Milestone exceeded. Knowledge products/exchange programmes facilitated through the World Bank, CEIP and CPR are included in Annex A
Number of capacity development training availed by national and state government (particularly low-income states) on governance, decentralisation, participation, responsiveness, transparency and accountability	5	5 / Milestone achieved: delivery of 2 Technical Assistance (TA) missions, 2 webinars and 1 seminar
[note] ‘Managing Fiscal Risks to Ensure Sound Finances and Achieve Macro-Stability’ in July 2020 and ‘Preparing for 2021/22 Budgets during Uncertainty and Managing Fiscal Risks’ in August 2020.
[note] ‘PFM Seminar for States’ Finance Secretaries’ in August 2020.

Briefly describe the output’s activities, and provide supporting narrative for the score. [max 1/2 page]

Through the State Partnership for Enhancing Commercialisation of the Power Sector EFO with the World Bank, PSSC supported 3 key interventions:

1. An independent impact evaluation to assess the benefits of the Government of Punjab’s Paani ‘Bachao Paisa Kamao’ (PBPK) scheme which covers agricultural consumers of electricity to encourage efficiency in use of electricity and water for irrigation, improve efficiency and transparency in delivery of power subsidy for agriculture, and reduce groundwater extraction as an effective adaptation measure for reducing climate vulnerability of agriculture. Evidence from the impact evaluation of the pilot demonstrated that the scheme incentivised small and medium farmers in Punjab to enroll as they saw a larger potential to save electricity and their cash incentive earnings were not insignificant in comparison with their total earnings. Through adoption of a package of measures and the resulting increase in efficiency, farmers were able to demonstrate a saving of both electricity and water between 12 to 25% without any adverse effect on farm yields.
2. The design of standardised ICT architecture to support distribution companies (Discoms) to adopt the use of Smart Meters to i) improve the inter-operability of the various components of the smart meter value chain ii) ensure a faster roll-out by providing a common service to state Discoms iii) promote efficiencies of scale through centralised procurements and provide iv) provide tools to track the progress of the programme.
3. Preparation of a digitisation roadmap to encourage the adoption of digital technology to support process and governance improvements including i) Gap analysis for West Bengal Discom as a case study ii) Digital readiness report which has been shared with all Discoms.
Further, the World Bank continued to deepen its engagement across 8 State departments with analytical studies produced under the Strategic State Engagement EFO contributing significantly to the policy dialogue and implementation of government programmes. 8 knowledge products developed through PSSC-supported EFOs have informed the following governance reforms: adoption of new procurement law, e-governance reforms in urban areas, and initiating transversal system strengthening actions across planning-finance-data systems.

Over the last year there have been a number of improvements in Odisha’s overall budgeting framework as a result of the capacity development training activities and technical assistance facilitated by SARTTAC with the Government of Odisha. Key results include: the creation of a Medium-Term Fiscal Framework (MTFF) for the FY2020/21 budget to improve the long-term financial credibility of the budget, setting up of a risk management framework that includes drafting a fiscal risk register; identifying, quantifying and analysing the impact of different risks; establishing a fiscal risk committee to evaluate these and to establish mitigation strategies, inclusion of the fiscal risks in the fiscal strategy paper; and a statement of fiscal risk (FRS) to be published in February 2021.

New partners Carnegie Endowment for International Peace (CEIP) and the Centre for Policy Research (CPR) have been brought on board to provide strategic evidence and policy advisory support. The two teams are working together on two discrete but interlinked areas on strengthening state capacity: 1) Strengthening regulatory design and design capacity on agriculture and labour markets, and on 2) Understanding the design of India’s apex institutions to inform the institutional reform processes within India’s cooperative federal framework. For instance, this includes mapping the design of the GST council and the finance commissions to understand the institutional structures within which financial relationships between the central and state governments have been negotiated. Lessons from these could inform the design of other regulatory institutions. Although still in the initial stages of the partnership, 8 knowledge products have been developed (see Annex A for full details); these have informed both the public narrative on specific themes as well as policy making processes. In the coming year, in addition to building on the work already undertaken, the projects intend to further refine the scope of evidence and policy advisory activities in line with emerging UK-India priorities, such as on data governance and digital markets. Activities may also include a focus on developing plans to ensure that outputs and products are made available to key policy makers.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

All partnerships have contributed a mix of knowledge products, pilots and capacity building of individuals on themes of agriculture markets, labour markets, public finance management, procurement and state utility sustainability reforms. The cost of capacity building interventions varies depending on the partner, level of access and reach across GoI partners, spread of activity and type of capacity building interventions undertaken. In terms of economy, over 75% of the budgets for CPR, CEIP and GPI are allocated towards the production of outputs. CPR delivered 6 knowledge products informing public policy and narrative on agriculture reforms in the first quarter of its work plan equating to £2,570 per product. This is different from CEIP, which have delivered 2 outputs (£5,170 per product) with a further 2 in draft – related to a labour market survey on the impact of COVID-19 in 4 Indian states and journal publications, on gender, social change and economic agency in India’s Tier 2 cities and framing some of the forthcoming work on India’s apex institutions. In terms of effectiveness of the training activities and technical assistance missions undertaken by IMF SARTTAC, an ongoing external evaluation of the Centre’s activities in the coming year will provide more evidence on the uptake of training activities on outcomes. However, SARTTAC reports that participants in technical training courses have found these useful and relevant. The technical assistance missions on macro-fiscal frameworks have been context relevant as they have prepared the Odisha state officials to plan for different scenarios amidst a high degree of uncertainty and will enable the state finance department to make evidence-based decisions in the year ahead. In the new financial year, VfM indicators on this output may be impacted due to the impact of cuts in the UK’s ODA on the delivery of planned activities.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

There have been no changes to the output this year. However, as recommended in the previous AR, milestones for the remainder of the programme have been finalised with input from the FCDO Results and Evaluation Advisor. New partners CEIP and CPR are contributing to this output and this is captured in the table above.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Progress on recommendations from the previous AR
In response to the recommendations made last year the programme has:
- Continued to build the partnership with SARTTAC and engage with the new Director SARTTAC who joined in August 2020
- Agreed with SARTTAC to continue the programme focus on the state of Odisha in order to deepen the impact of interventions in the state
- Ensured active engagement of the FCDO’s Power Sector Reform programme in the World Bank Energy EFO
- Finalised partnerships with think tanks (CEIP and CPR) and started the implementation of work to better understand the design of Indian institutions and to provide evidence and policy support on economic and institutional reform in India
Lessons learned this year
- The partnerships have enabled the FCDO to support technical assistance and evidence needs from state governments to respond to the immediate opportunities and challenges created by the pandemic. To achieve impact at scale, it is necessary to build on these interventions. It is critical that this remains a responsive process, i.e., it is balanced with the need to support policy makers with the right type of evidence at the right time.
- Flexibility in framework agreements have enabled the programme’s partnerships to respond to emerging policy and regulatory priorities. Future partnerships should continue to focus on building flexibility into design of bespoke capacity building, technical assistance and evidence building interventions and partnership arrangements.
- Regulatory authorities are a key part of the institutional architecture of governance i.e. upholding transparency and accountability in the delivery of public services. Evidence and training support to regulators will be critical to the delivery of the programme’s impact going forward.
Recommendations for the year ahead
- Gain a greater understanding of how SARTTAC uses the IMF’s Results Based Monitoring (RBM) System and independent evaluations to measure how its capacity development work is translating into improvements in policy making and government administration. The ongoing mid-term evaluation of SARTTAC’s work will inform the team on its effectiveness.
- Explore the feasibility of a secretariat role in bringing together all strands of work under PSSC to support coherence across capacity building, training, knowledge and technical assistance interventions.
- Consider developing a targeted partnership to support hands-on capacity building of Indian civil services on key priorities of UK-India partnership such as on data and digital markets governance, climate change and financial sector regulation.
Re-evaluate the current scope of activities to build institutional new partnerships, including with regulatory authorities and India’s apex institutions to support emerging priorities on open societies and open economies jointly identified between the UK and India and in the light of budget availability.

D: RISK [½ to 1 page]

Overview of risk management [1/2 page]

Currently, the overall risk rating for the programme is moderate. The current, active risks are included below. The key new risk emerging this year has been COVID-19 and its potential impact on FCDO and partners’ ability to deliver. As mentioned earlier in the report, this has been mitigated through ongoing engagement with partners, by reprofiling some spend to the next financial year and delaying some activities accordingly. Going forward, the risks for the programme will be regularly revaluated in light of a number of dynamic changes, including the new priorities set by the creation of the FCDO and the likely impacts of reduction in overall budgets due to the severe adverse effects of COVID-19 on the UK’s economy.

Risks (and residual risk rating post mitigation)	Mitigation measures
Reputational: There is a risk that in partnerships with multilaterals FCDO is not engaged with as an equal partner, adversely impacting the outcome and impact. (Major)	FCDO has set up a clear governance structure for engagement with the World Bank.
Delivery: There is a risk that the programme supports small scale/ad-hoc initiatives that are not subsequently scaled up. (Moderate)	The programme carefully screens activities funded through it, supporting strategic interventions that are in line with to GoI and UK's priorities. / Payments are linked with agreed milestones.
Delivery: Delay in programme implementation due to COVID-19 (Moderate)	In discussion with partners, extending the dates of deliverables where required. Delivery of programme activities remotely where possible, postponing trainings and workshops if necessary.
Delivery: Programme interventions do not lead to envisaged impact due to reduction in ODA budgets (Minor)	By carefully screening sub-projects and through effective governance arrangements, FCDO will increase direct and indirect engagement with government counterparts to enhance the uptake of interventions and recommendations. The FCDO team will prioritise and consolidate activities and interventions to build on priority areas identified between the UK and India on governance, open societies and open economies

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency. [max 1 page]

Performance of Partners: During the review period, the programme worked with the following partners:

- World Bank: This year saw the conclusion of the Energy EFO as planned but experienced some delays in engaging with State governments through the Strategic State Engagement EFO for which a revised workplan has been agreed.
- IMF South Asia Regional Training and Technical Assistance Centre (SARTTAC): Despite the challenges of changing the model through which technical assistance and capacity building training is implemented, SARTTAC has managed to deliver almost 90% of its workplan.
- Lal Bahadur Shastri National Academy of Administration (LBSNAA): Whilst training was completed in the previous reporting period, it had a continued impact this year with 9 case studies on tackling violence against women and children developed under the programme been turned into teaching aids which will be used by training academies across India.
- Carnegie Endowment for International Peace (CEIP) and Centre for Policy Research (CPR) new partners: This new partnership commenced in October 2020 and therefore the focus thus far has been on developing the partnership and governance arrangements, finalising focus areas for the strategic evidence and policy support, and the development of workplans.
- Government Partnerships International (GPI) new partner: Brought on board to provide targeted support to the GoI on the capacity building of India’s civil services, initial engagement with DoPT has been promising with a successful round table in November 2020 where priority areas for support were identified and are being taken forward through the establishment of working groups in the relevant areas.

Financial performance

Overall, the programme is delivering against its financial targets. The total value of the programme is £4,995,000 with £2,530,804.19 spend to date (as of 22 February 2021). The budget for the financial year 2020/21 is £393,333 and is on track to be spent by the end of the year (March 2021).

The FCDO programme team works closely with partners to monitor financial expenditure and ensure disbursements are made according to the terms and conditions of the AG/contract/MoU signed. This includes approval of annual budgets and work plans; review of progress throughout the year through quarterly progress reports, financial statements and forecasts; and convening of regular Steering Committee/coordination meetings.

Monitoring of activities
- This year, due to ongoing restrictions as a result of the pandemic, it has not been possible for the FCDO to meet with programme partners in person.
- However, monitoring activities which would normally have taken place have been conducted virtually such as progress updates, steering committee meetings and engagements with stakeholders.
- Monitoring of overall programme progress has been conducted by the FCDO through the log frame and work plans developed by each partner. Partners in turn, have their internal own monitoring mechanisms. Formal reporting by partners is mandatory through financial and progress reports in line with Accountable Grant/MoU requirements.
- The FCDO team ensures adherence to all requirements, including risk, fraud and safeguarding. Overall responsibility for the management of Accountable Grants/MoUs and other agreements sits with the SRO.

Date of last narrative financial report	January 2021	Date of last audited annual statement	CEIP: October 2019 / CPR: September 2019 / Managed centrally for multilateral organisations

Annex A: Knowledge products/exchange programmes facilitated through the World Bank, CEIP and CPR
Report on the formulation of draft Punjab Transparency in Public Procurement Rules

Technical Note: Preparation of Preference Guidelines for Procurement

Technical Note-Review of PWD Code

Stakeholder Perception Study: Water-Power-Agriculture Nexus

Data Governance and Use for Policy: An Assessment of Punjab's Existing Data Systems

Assessment Report – Institutional and e-governance reforms at Amritsar and Ludhiana Municipal Corporations

Design of Common Back-End ICT Infrastructure Facility (CBIF) for smart meters

Digitisation roadmap for utility sustainability

Article: Farm laws: First principles and the political economy of agricultural market regulation https://www.ideasforindia.in/topics/agriculture/farm-bills-first-principles-and-the-political-economy-of-agricultural-market-regulation.html

Op-Ed: On farm laws, how the Centre faltered https://www.hindustantimes.com/analysis/on-farm-laws-how-the-centre-faltered/story-44IpmLCZ2Pz0PFKnYOJgfJ.html

Op-Ed: Licensing, registration of farm produce buyers needs more reform not removal https://theprint.in/opinion/licensing-registration-of-farm-produce-buyers-needs-more-reform-not-removal/561981/

Multi-media product: Making sense of the New Farm Laws https://www.youtube.com/watch?v=so0qbBvaX2g

Multi-media product: Farm Reforms - in depth conversation with Shekhar Gupta, Editor-in-Chief, The Print https://www.youtube.com/watch?v=1Jvmx5O-z70 78,000 views as of 8 February 2021

Session on Agriculture Reforms at The/Nudge Forum | agri charcha https://www.youtube.com/watch?v=CG0b_Szg4GM&t=7s

Analysis of round 1 survey on labour markets

Essay on ‘Three Faces of the Indian State’ published in the Journal of Democracy