Programme Completion Review

Title: Responding to the Nutrition Crisis in Yemen (R2N)
Final Programme Spend £ (full life): £166,826,317.52	Review Date: June 2023
Programme Code: 300525	Start Date: / 25 September 2018	End Date: / 31 March 2023

Summary of Programme Performance
Year	2019	2020	2021	2022	PCR
Programme Score	B	A	A	A	A
Residual Risk Exposure Rating	Severe	Severe	Severe	Severe	Severe

DevTracker Link to Business Case (and any addendum):	http://iati.FCDO.gov.uk/iati_documents/36022579.odt
DevTracker Links to all logframes used during programme lifetime:	http://iati.fcdo.gov.uk/iati_documents/57385334.xlsx

A. Summary and Overview (1-2 pages)

This Programme Completion Report is a review of the ‘Responding to Nutrition’ (R2N) programme in Yemen, part of a wider HMG and UK National Security Council effort to avert famine in Yemen. R2N was designed as a 3-year programme built around a ‘life-cycle approach’, that aimed to address the immediate and underlying causes of undernutrition, including critical nutrition, health, water, and sanitation needs, and improve the technical analysis and evidence informing the response.

Initially designed as a £96.5m programme starting at the end of 2018, R2N was affected by COVID-19in 2020, the merger of FCO and DFID in 2020/2021; and subsequent cuts to ODA in 2021/2022, which reduced funding and funding predictability for Yemen (including a 4-month funding gap in 2022). Funding levels were inconsistent; with payments of £35m and £34m in the first two years; increased to £47m in the third year (including a response to COVID-19); before a substantial reduction of 59% to £19m. UNICEF received £26m in the final year, which includes a time and cost extension of the programme by an additional year and six months, which served as a pilot stage during the development of the new Women and Children business case,. Overall, UNICEF received a total of £166.8m (72% more than originally budgeted) over the extended life of the programme.

A small additional component was added to prevent, detect, and respond to the threat of COVID-19 during the pandemic; the UK added the World Bank as a partner to R2N under a business case addendum in April 2020. The UK’s funding contributed to the World Bank’s Yemen COVID-19 Response Project (YCRP), a nationwide intervention which covered 333 districts in 22 governorates in Yemen. The UK made a payment of around £5.6m ($7,761,000). The project beneficiaries include Yemeni residents, medical and emergency personnel, and laboratories and testing facilities across the country. This output was considered successful, despite challenges (delays in procurement caused by lack of local suppliers and delays in shipping emergency supplies due to air space restrictions) in working with the World Bank.
[note] Payment of $7,761,000; calculated based on average exchange rate USD to GBP in 2021: 0.7271 GBP.
FCDO investments have been structured across three areas with UNICEF:
Output 1: Immediate Actions – Critical Nutrition, Health, Water, Sanitation and Hygiene service delivery – provide lifesaving, improved quality nutrition, health, and wash services for affected populations, complemented by a focus on protection for the most vulnerable.
Output 2: Remedial Actions – System strengthening and risk management – maintain and strengthen systems delivering nutrition, health and water and sanitation services at a sub-national level. Improve efficiency and effectiveness of health risk management through improved planning and financing.
Output 3: Increase contextual understanding – Knowledge and evidence generation – address the information and data gaps that exist in Yemen by improving the knowledge and evidence base for the context and supporting analytical products to improve decision making.

Since 2018, this programme has contributed to:
- Screening of 5,064,635 children for severe acute malnutrition; 382,502 treated with less than a 7% default rate. (output 1.1)
- 3,139,653 pregnant and lactating women provided counselling on infant and young child feeding practices. (output 1.3)
- 2,678,002 vulnerable women and children provided with health consultations through outreach services and mobile health teams. (output 1.4)
- 113,147 women gave birth with a skilled birth attendant. (output 1.5)
- 13,477,092 children vaccinated for polio and another 788,920 received routine vaccinations. (output 1.6)
- 6,921,761 people provided access to drinking water (output 1.8) with another 11,117,236 provided emergency water, sanitation, and hygiene support. (output 1.9)
- 181,859 children and caregivers provided psycho-social support. (output 1.14)
- The WHO programme vaccinated 1,130,358 people for COVID-19 and trained 4,468 on infection prevention and control.
The programme met or exceeded most output targets. In relation to output 1, “affected populations in Yemen are provided with life-saving nutrition, health, WASH and protection support,” the programme met or exceeded 20 of 25 indicators. In relation to output 2, “nutrition, health and WASH services in Yemen are supported at a local level to be more efficient and effective,” the programme met or exceeded 10 of 12 indicators. In relation to output 3, “evidence is generated by UNICEF to improve understanding of the context and influence the shape of the response in Yemen,” the programme met or exceeded all 6 indicators.
There were similar results at the outcome level. In nutrition and health, the programme met or exceeded targets except for the supply of Ready to Use Therapeutic Foods (RUTF) which remained at 95% of facilities during most of the programme. Severe Acute Malnutrition (SAM) treatments are a notable achievement, especially as UNICEF reports less than 7% default rates. WASH and protection outcome targets were also met.
This report assesses that overall, the programme continued to work effectively, but there was a necessary departure from the proposed ‘life cycle approach’ aimed at protracted crisis context to focus on life-saving service delivery. Whilst the programme was designed around a model that could ‘flex and shift’ approaches in response to changes in the nutrition context, reducing the malnutrition caseload in Yemen by addressing underlying causes and strengthening healthcare became untenable given the change in operating context and reduction in funding. Consequently, in August 2022, FCDO changed the approach with UNICEF, 1) to increase oversight instead of a fully delegated flexible system 2) to adapt their operating model for this project to focus on delivering a more significant level of support to a smaller number of identified health facilities in high vulnerability areas and 3) to increase monitoring to ensure quality standards were met.

Despite the change in approach, the programme achieved commendable outcomes in line with the original aims: the expected impact was for malnutrition caseloads in Yemen to decrease; an improved nutrition status among infants, children, adolescents, adults and pregnant women; and the indicators suggest the programme met or exceeded all targets.  The focus on lifesaving activities has proven effective; for example, the screening and enrolment of children with SAM; default rates were 7% at the end of the programme, well below the target of 15%. This is a notable success and likely attributable to the outreach and general knowledge of healthcare facilities amongst the general population.

While the programme may have been overly ambitious in original design, it did prove effective in providing essential life-saving nutrition, health, and WASH services along with important child protection services. Target achievement levels faced some challenges, but overall the programme was effective. The PCR concludes that the programme scores an A (“met expectations”), in keeping with the average scoring during the lifetime of the programme.

UNICEF have been funded by DFID/FCDO in Yemen since 2011 and the partnership remains productive, although there remain challenges in the quality of UNICEF’s oversight and monitoring of the programmes. Lessons learned have been captured and built into the successor business case, Women + Children (approved in 2023).

Major lessons learned, evidence generated and recommendations

Strategic approach: The original business case notes that the life-cycle approach was ‘ambitious but necessary’: the programme aimed to shift the international humanitarian response model in Yemen to a protracted crisis approach capable of delivering critical lifesaving assistance while attempting to maintain the foundation necessary for future development. The idea was to retain flexibility over the course of programme delivery by focusing on the lifesaving interventions and building on these where possible to maintain and increase the capacity and resilience of the systems involved. The follow-on programme will continue to focus on both lifesaving interventions through service delivery and systems strengthening at the facility level by providing support through UNICEF to support and maintain Primary Health services through the Minimum Service Package (staffing support; operational cost support, and supplies). The selection of the locations of the Primary Health Centres (PHCs) remains critically important to ensure service provision to the most vulnerable communities without duplication of other actors. Under the new business case, there will also be a push for the further decentralization of resources from facility to community level, including outreach.
Flexibility The intention in the original BC was also to ‘shock proof’ the programme, designing interventions able to scale up and down to the situation in Yemen. The global pandemic was unforeseen, and there was no plan in place to ‘shock proof’ the programme from significant internal changes – an organisational merger and global pause and then reduction in ODA derived from the donor. To avoid future disruption on funding, the FCDO is now working on an annual programme basis with UNICEF, communicating funding based on confirmed budget availability, which should also enable a stronger link of payment to performance.

VFM The programme demonstrated VfM across the four ‘Es’, but they tended to lack evidence of a consistent approach to analysing gains in fiscal terms. A VfM framework will be developed at programme inception that can be used to consistently assess VfM in fiscal terms and assessed in each annual review. FCDO can also use the new programme to compare the value for money of the UNICEF operational model as implemented in the 2022-23 programme with the new component of assistance provided through NGOs. The costs and benefits of implementing through single vs multiple delivery channels should also be considered.

Fraud and diversion monitoring needs to be strengthened in Women + Children. UNICEF identified many risks at the outset of R2N but the risk register needed to have been more robustly updated and monitored. Already started in the R2N top-up, the new programme will ensure more stringent monitoring by FCDO of both physical supplies and incentive payments (which are under review by all donors collectively to ensure a common approach), as well as wider operational challenges including restrictions on access, TPMs (Third Party Monitoring Partners), project locations etc.

Partnership UNICEF remain a cooperative partner who deliver technically strong interventions, but the challenge noted in successive annual reviews of their lack of oversight of programmes continued throughout. ‘Bunkerization’ of the UN is not a trait unique to UNICEF (as identified in the 2022 IAHE report), and efforts are under way to improve this across the humanitarian response through collective donor action. This has been discussed with UNICEF, including in country with FCDO; more frequent monitoring visits by the team to Yemen will enable more stringent monitoring of UNICEF.

How this report was conducted

This report was conducted by triangulation of: (i) programme management directly by the FCDO Yemen Humanitarian and Resilience Team (HART) over the life of the programme, which included quarterly meetings with the partner (UNICEF); (ii) reporting directly from UNICEF including quarterly, annual and final reports, and informed by regular monitoring; and (iii) a final review conducted by the contracted third-party monitor, Tahseen. Programme monitoring visits to Yemen since 2022 have allowed the programme team – including SRO and Health Adviser – to complement the formal reporting with in-country visits to our partner UNICEF and direct monitoring of field locations in Aden.

Actions following approval of this report

The programme with UNICEF is being continued through the new (approved) business case, ‘Women and Children’ (W+C). The new programme will draw together multiple former separate programmes, and is intended to be a continuation of core R2N ambitions to deliver an integrated response of health, nutrition, WASH and protection.

Lessons from R2N have already been incorporated into the new business case, including the issue identified in original R2N appraisal case that by only partnering with a single UN agency (UNICEF), FCDO is less closely linked to other organisations including local NGOs who have large capability and technical capacity. There will be a consortium of NGOs under the new business case (already in procurement phase), which will also include Yemeni organisations in line with the FCDO Yemen’s ambitions on localisation. This report will be published on Devtracker
## B: Theory of Change and Outcome Assessment

	Starting point	Result
Budget	Original business case value - £96.5m	Final spend - £166,826,317.52
Timeframe	Original Business Case / 3 years (October 2018 – September 2021)	4.6 years (1.6 year extension) September 2018 March 2023
Outcomes	Business Case: / Girls, boys, and their mothers living in humanitarian conditions have access to critical life-saving interventions through convergent life-saving nutrition, health, water, sanitation, and hygiene services. / Nutrition, health, water, sanitation systems, and hygiene promotion are preserved and strengthened to deliver services and manage risk. / The international and national systems in Yemen are better able to use knowledge and evidence to make decisions and learn lessons.	Final: Affected populations in Yemen have access to critical live-saving humanitarian interventions and services are strengthened (with a focus on provision, maintenance, risk management and learning). / This included seven outcome indicators across nutrition, health, WASH, protection, and evidence. / Lessons on programme delivery were used to inform future business cases.

Overall assessment of programme outcomes, sustainability and VfM.
The programme was designed to decrease nutrition caseloads in Yemen while increasing the nutritional status among infants, children, adolescents, adults and pregnant women. (Impact) This was premised upon the interaction of critical services (nutrition, health, and WASH), health system strengthening at the decentralised, facility level, and the collection and analysis of relevant data to inform decision making and priority actions. This was part of a life cycle approach that posited that improving women’s, children’s, and adolescents’ nutrition requires a mix of interventions, programmes and policies, all at different stages of life. This, it was proposed, would shift the international humanitarian response model in Yemen to a protracted crisis approach (HMG Humanitarian Policy Objective), capable of delivering critical lifesaving assistance while attempting to maintain a foundation for future development.
[note] “Responding to the Nutrition Crisis in Yemen.” FCDO Business Case; September 2018. Page 28.
[note] Branca, Francesco; Piwoz, Ellen; Schultink, Werner; Sullivan; Lucy Martinez; “Nutrition and health in women, children, and adolescent girls”; BMJ 2015;351:h4173: https://doi.org/10.1136/bmj.h4173 (Published 14 September 2015).
Instead, the programme shifted towards essential service delivery to meet the emergency health and nutrition needs of women and children and away from addressing the underlying factors associated with malnutrition and broader system strengthening. This was done primarily because of the consequences of Cholera, COVID-19 (access) and the complicated operating context that prevented coordinated action with health authorities and others involved in overall healthcare in Yemen. Secondarily, the shifts were also driven by funding cuts from FCDO which required a refocusing on immediate service delivery due to both reduction in, and future uncertainty of, funding.
Nonetheless, the revised service-oriented outcome indicators show fair to good progress. In nutrition and health, the programme met or exceeded targets apart from the supply of Ready to Use Therapeutic Foods (RUTF) which remained at 95% of facilities during most of the programme. The percent of SAM coverage treatments against projected needs stayed above targets throughout the programme. However, SMART( Standardized Monitoring and Assessment of Relief and Transitions) surveys were conducted in 2021/2022 but the reports were not formally published, and so the level of need was never fully established during the programme. UNICEF reports that these treatments met the minimum SPHERE standards of 75% cure rate, with less than 7% default rates. In terms of WASH, the indicator was “the number of people accessing a sufficient quantity of safe water for drinking, cooking and personal hygiene.” The target was cumulative and, by June 2021 the target had been exceed by 6% (2,824,610 people reached.) The protection indicator was the “percentage of health facilities supported by UNICEF applying the standard operating procedures for integration of social welfare and psychosocial support into health and nutrition services.” The target for this was 35% which was also achieved by the end of the programme. Finally, in terms of evidence, the indicator was the “number of national policies, strategies or plans amended based on new evidence generated by UNICEF.” This target underachieved with 10 out of a projected 15 such studies being produced, however the indicator was ambitious due to the lack of political cohesion in Yemen. As described in output 3, these also largely failed to establish the links between service delivery and healthcare system strengthening at the facility level.
[note] https://smartmethodology.org/about-smart/
[note] https://spherestandards.org/
While these achievements are notable, it is unclear if they are related to improved caseloads or healthcare services. In late 2021, the World Bank estimated that only 50% of health facilities were fully functional, and over 80% of the population faced significant challenges in reaching food, drinking water and access to health care services. The World Bank cited human resource shortages, lack of equipment, and lack of supplies as major challenges.6 Integrated Phase Classification (IPC) rates of malnutrition have also not improved significantly over the programme period.7
A 2021 survey shows that 70% to 90% of children under the age of 5 years were being fed diets not meeting the minimum acceptable standards and that at least 1 million children under the age of 5 years and 450,000 pregnant and lactating mothers needed urgent food assistance.8 The problematic sources and types of evidence for these outcomes is not helped by evidence, as remarked upon in each annual review, the majority were incomplete and unreliable in some instances. This was combined with a lack of adequate oversight by UNICEF, also pointed out in annual reviews. This includes inadequate coordination between UNICEF, health authorities, and individual facilities. Overall, there are suitable examples of VfM across the four ‘Es’ even if these tend to be anecdotal and lack consistent approaches to analysing gains in financial terms.
 In terms of economy, most costs related to supplies. UNICEF is one of the largest global purchasers of child vaccines, nutrition supplies, and other equipment which gives UNICEF leverage in negotiating the lowest prices with suppliers. This included bulk procurement and transportation of supplies such as vaccines, Ready-to-Use Therapeutic Food (RUTF), and other supplies. UNICEF reports that the RUTF unit cost did not exceed the £37.12 per carton for one child as set out in the business case.
In relation to the World Bank Global Finance Facility grant to WHO for the COVID-19 response, over 50% of each grant was used in support of rolling out the COVID-19 vaccines in Yemen, including contributing to the cost of the COVID-19 mass vaccination campaign in September 2022, conducting integrated outreach, and providing per diem and transport costs for the rollout of the vaccines via fixed sites.
In terms of efficiency, given that over 90% of facilities consistently reported no stock-outs of ready to use therapeutic foods (outcome indicator 1.b), the expected efficiency from this was achieved.
In terms of effectiveness, the programme met or exceeded most output indictors but there was a significant deviation from what was described in the business case. The programme was proposed initially to shift the international humanitarian response model in Yemen to a protracted crisis approach capable of delivering critical lifesaving assistance while attempting to maintain the foundation necessary for future development, but instead ended up providing immediate lifesaving interventions.
In terms of equity, UNICEF’s activities included vulnerable women and children as the primary target. 100% of community health workers (CHW) were women and 50% of the Rapid Response Teams were women.

Summary of technical lessons and recommendations for the new Business Case

- A VfM framework should be developed at programme inception that can be used to consistently assess VfM in financial terms. This should be assessed in each annual review.
- UNICEF could be better at more consistently disaggregating results data to show persons living with disabilities.
- FCDO monitoring identified that some health facilities lacked clear communication between services free of charge under this programme and other services requiring medical fees. This led to confusion among patients paying different amounts and could likely deter the most vulnerable from seeking treatment. FCDO and UNICEF should ensure services and their costs and fees (if applicable) are posted publicly in facilities. FCDO monitoring should continue to track that the minimum service package is delivered free of charge to the user.
- UNICEF should ensure closer monitoring of defaulters from SAM treatment, including tracking and analysing the principal reasons, and feeding this analysis into mitigation measures.
- FCDO health system strengthening support should continue to fund UNICEF to cover gaps in routine immunisations, training of skilled birth attendants, support to authorities on health and nutrition policy development, and operations and maintenance of large-scale water systems. These are the most evidence based and cost-effective means of prevention of disease including acute malnutrition in Yemen.
Following the renewed due diligence of UNICEF Yemen in August 2022, FCDO and UNICEF should work together to address the action plan and recommendations of the assessment. Key areas to focus on are the sufficiency of UNICEF’s field monitoring and exchange rate management. Progress against the action plan should be monitored during the extension period and used to design the UNICEF component in the new Women and Children Business Case.

Clear attribution of FCDO support to particular health centres will make it easier to monitor quality aspects and attribute improvements to FCDO funding. This adapted operating model will be used to inform the design of the UNICEF component of the new Business Case.

UNICEF should design mitigation measures to ensure higher performance around provision of iron supplements among children and adolescents including cultural and social behavioural change.

FCDO and UNICEF should conduct a Nutritional Casual Analysis to better understand the causes of persistently high levels of acute malnutrition in certain areas of Yemen, uncorrelated with acute food insecurity, and research into effective means to promote improved infant and young child feeding practices. This will be funded through the new Business Case.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators.

The programme was designed to decrease nutrition caseloads in Yemen while increasing the nutritional status among infants, children, adolescents, adults and pregnant women. (Impact)
[note] “Responding to the Nutrition Crisis in Yemen.” FCDO Business Case; September 2018. Page 28.
This programme supports the UK Government’s Country Business Plan in Yemen to prevent famine. The right financial and technical inputs were expected to contribute to outputs that address nutrition needs through an integrated approach including health and water and sanitation and hygiene (WASH) interventions. The programme aimed to strengthen Yemeni health systems to ensure that Yemenis have access to life saving interventions leading to an overall improvement in nutrition status among the population. Evidence and learning continued and shared across the interventions to ensure that the most effective approaches are being taken.
These interventions do not happen in isolation, however, and rely on a portfolio approach with other FCDO investments. This programme complemented FCDO programming with other partners including FCDO funded programmes on food security and social protection. This was enhanced in the R2N programme extension as UNICEF prioritised Integrated Famine Risk Reduction districts.
The programme initially targeted 107 high-priority districts considered at heightened risk of famine jointly identified by the WASH, Nutrition, Health, and Food Security and Agriculture clusters and the Ministry of Health. As the situation in Yemen was rapidly evolving and uncertain, the programme scaled up to work in any of the 333 districts for emergency response when the situation arose.

COVID-19 challenged some assumptions within the theory of change. For example, due to previous restrictions on access and movement, vaccination campaigns and other outreach activities were suspended for some periods, resulting in the loss of some planned results. In addition, reduced humanitarian funding for Yemen in 2020 and 2022 led to UNICEF not being able to achieve overall targets for indicators 2.2 and 2.3. As FCDO funding contributes flexibly to UNICEF’s wider country results, this led to some FCDO outputs not meeting expectations.

In August 2022, FCDO asked UNICEF to adapt their operating model for this project to focus on delivering a more significant level of support to a smaller number of identified health facilities in high vulnerability areas and increase monitoring to ensure quality standards were met. Of particular concern was the discovery, through third party monitoring, that some health facilities were charging user fees which risked exclusion the most vulnerable. Limited monitoring and insufficient assurance of quality was also noted. Clear attribution of FCDO support to particular health centres will make it easier to monitor quality aspects and attribute improvements to FCDO funding. This adapted operating model will be used to inform the design of the UNICEF component of the new Business Case.

This programme, it was proposed, would shift the international humanitarian response model in Yemen to a protracted crisis approach (HMG Humanitarian Policy Objective), capable of delivering critical lifesaving assistance while attempting to maintain the foundation necessary for future development. Such life cycle approaches depend on each component being adequately functional while also complementing each other in ways that generate the expected results. Theoretically this makes sense and yet it breaks down in especially volatile conflict situations where health and nutrition infrastructure are degraded, where access to such survives is difficult—especially for the most vulnerable-- and where health authorities are fractious at best.
Given this, the three outcomes related to the integrated approach were changed to a single outcome: “Affected populations in Yemen have access to critical live-saving humanitarian interventions and services are strengthened (with a focus on provision maintenance, risk management and learning).” This included seven indictors that focused on service delivery and supplies. These are described above (output number 1, page 7)

## C: Detailed Output Assessment [aim for max. 1 page per output. Repeat for each output]

Output Number and Title	Affected populations in Yemen are provided with life-saving nutrition, health, WASH and protection support
Output Score	A
Impact weighting (%)	45%	Impact weighting revised since last AR?	No

Output Indicators	Starting Target	Final Target	Final Result Achieved
Nutrition
1.1a (cumulative) / # of children under 5 screened for Severe Acute Malnutrition (SAM)	2,972,000 / (business case) / 3,113,421 (baseline)	8,947,417 / + 22,800 (extension)	16,882,115 (189%) + / 30% FCDO attribution: 5,064,635)
1.1b (cumulative) / # of children under 5 with SAM enrolled in management programmes	70,000 (business case) / 288,928 (baseline)	1,095,518 / + 280,000 (extension)	1,055,957 (96%) / + 19,300 (85%) / 1,318,989 (total) 29% FCDO: 382,507)
1.1c % of under 5 children enrolled in SAM management programmes who default (expressed as an average and range min/max)	<15% / 14.7% / (baseline)	<15%	7.2%
1.2 (cumulative) / # of children at school age (10 - 19 years old) receiving weekly iron supplementation as part of anaemia prevention interventions	500,000 (business case)	900,000	207,057 (23%) / (100% FCDO)
1.3 (cumulative) / # of pregnant and lactating women receiving counselling and education on infant and young child feeding (IYCF)	4,355,869 / 1,530,810 (baseline)	4,355,869	10,728,541 (246%) / (30% FCDO: 3,218,562)
1.3b (extension; August 2022 – March 2023) / # of health facilities where all monthly SAM treatment records meet SPHERE standards (<15% default, <10% deaths)	404		404 (100%) / (100% FCDO)
1.3c (extension; August 2022 – March 2023) / % of abnormal or missing monthly SAM treatment data followed up by UNICEF quarterly.	60%		51% (85%) / (100% FCDO)
Health
1.4 (cumulative) / # of primary health consultations provided to children under 5, caregivers and pregnant and lactating women through health facilities, outreach services, and mobile health teams.	1,090,559 / (baseline)	7,500,000	8,926,674 (119%) / (30% FCDO: 2,678,002)
1.5 (cumulative) / # of women of reproductive age receiving skilled birth attendance (home/facilities)	35,452	933,916	887,649 (95%) / (15% FCDO: 113,147)
1.6a (annual) / % of targeted children who are vaccinated with three doses of DTP/Penta vaccine (Routine vaccination & Integrated Outreach rounds)	82%	77% (average) (3,155,678 total; 25% FCDO: 788,920)
1.6b (annual) / % of children <5yrs vaccinated during each round of Polio Vaccination campaign (Total target=5,535,816)	89%	53% (average) (19,252,989 total; 70% FCDO: 13,477,092)
1.7 (cumulative) / # of healthcare facility staff and community health workers (CHW) trained in Infection Prevention and Control, detection and referral of suspected COVID-19 cases among children, pregnant and breastfeeding women.	12,000	12,000	10,686 (89%) / (13% FCDO: 1,389)
1.7b (extension; August 2022 – March 2023) / Coverage of DTP3 in <1 year old (%)	86% of the annual target for 2022 (510,000 children <1 year) / 22% of the annual target for 2023 (650,000 children <1 year cumulative)		86% 2022 (100%) / (100% FCDO)
1.7c (extension; August 2022 – March 2023) / Number of children (girls and boys) under 5 accessing IMCI in primary health care health facilities, outreach services, and mobile health teams (cumulative)	200,000		193,733 (97%) / (100% FCDO)
WASH
1.8 (annual) / # of people provided with access to drinking water through UNICEF support to operational and maintenance (O&M) and rehabilitation of public water systems.	1,119,791 (baseline) / 2,400,000 / +350,000 (extension)	126% (average) (13,059,927 total; 53% FCDO: 6,921,761)
1.9a (annual) / # of individuals provided with emergency WASH	818,154 (business case) / 668,154 (baseline) / 2,344,691	125% (average) (11,117,236 total; 100% FCDO)
1.9b (annual) / # of Rapid Response Teams responding to cholera and emergencies.	650 / 350	65% average (2,400 total; 60% FCDO: 1,440)
1.10 (annual) / # of household members who have benefitted from UNICEF hygiene promotion activities, observed practicing handwashing with soap at critical times	0	83% average (6,590,525 total; 100% FCDO)
1.11 (cumulative) / # people supported through continuity of WASH service	400,000		1,650,000 (413%) / (100% FCDO)
1.12 (cumulative) / # WASH NFI kit distributed to self-isolated household	25,000 HH/ 200,000 people		64,066 HH (256%) / 448,462 people (224%) / (100% FCDO)
1.12b (extension; August 2022 – March 2023) / # of people in humanitarian situations accessing safe means of excreta disposal	20,000		14,527 (73%) / (100% FCDO)
Health and Nutrition
Indicator 1.13 (cumulative) / # of pregnant women and mothers with new-borns receiving vouchers to cover transportation costs for delivery, postnatal care and medical care in case of complications.	108,000 vulnerable children, women and including 21,600 people with disabilities. (business case) / 3,150 (60%)		3,700 (117%) / (100% FCDO)
Protection
Indicator 1.14a (cumulative) / # of identified children who receive support through case management/referrals.	1,500	1,850	1,801 (97%) / (100% FCDO)
Indicator 1.14b (cumulative) / # of children and caregivers receiving mental health and PSS inside HF and remotely (within HF catchment areas)	125,000 (business case)	138,600	181,859 (131%) / (100% FCDO)
Social and Behaviour Change (SBC)
1.15 (extension; August 2022 – March 2023) / # of functioning Mother to Mother (Jadati) clubs in priority districts promoting lifesaving and positive parenting practices	350		335 (96%) / (100% FCDO)
[note] Includes indicative targets from business case (page 34) along with baseline figures that established either cumulative or annual targets. These were not changed prior to the August 2022 extension. Business case targets also include: “800,000 supported with sexual reproductive health programming including 302,800 family planning, 292,000 antenatal check-ups, 117,200 deliveries, and 88,000 postnatal visits;” and “70,000 provided with early children development support” that were dropped in the first year of programming.
[note] Included in August 2022 – March 2023 extension.
[note] Business case included another indicative indicator “25 million under-five children treated for childhood illnesses” that was dropped in the first year of programme.
[note] Target and milestones are set as 90% of the nutrition caseload and is subject to revision based on caseload.
[note] Included in August 2022 – March 20223 Extension.
[note] This level of overachievement signals a miscalculation in costs and targets.
[note] Implemented from July 2020 to June 2021.
[note] Included in August 2022 – March 2023 extension.
[note] Business case includes: “1,373,400 individuals in urban settings, 186,391 in rural settings and 818,154 internally displaced persons (IDPs) and host communities benefitting from improved water and sanitation services.” This may include indicators 1.8, 1.10 & 1.11, along with relevant indicators from output 2.
[note] Indicator discontinued in August 2021 due to changes in funding related to COVID-19 response.
[note] Implemented from July 2020 to March 2021.
[note] This level of overachievement signals a miscalculation in costs and targets.
[note] Indicator discontinued in August 2021 due to changes in funding related to COVID-19 response.
[note] Implemented from July 2020 to March 2021.
[note] This level of overachievement signals a miscalculation in costs and targets.
[note] Indicator discontinued in August 2021 due to changes in funding related to COVID-19 response.
[note] Implemented from July 2020 to June 2021.
[note] Indicator discontinued in August 2021 due to changes in funding related to COVID-19 response.
[note] Indicator discontinued in August 2021 due to changes in funding related to COVID-19 response.

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.
This output met or exceeded 20 out of 25 indicators, including those related to the UNICEF extension. Overall, this is positive and yet there were significant disruptions due to COVID-19 as well as access. This affected vaccination rates and rapid emergency response teams, amongst other activities. The programme over-achieved in relation to SAM screenings and the provision of drinking water and other emergency WASH services. This output scores an A (“met expectations”).
Nutrition
Approximately 1 in 16 children screened for SAM were enrolled in SAM treatment (output 1.1). SAM default rates were 7% at the end of the programme, well below the target of 15%. This is a notable success and likely attributable to the outreach and general knowledge of healthcare facilities amongst the general population. However, SAM admission rates have not reduced significantly during the programme period.
School age children receiving weekly iron supplementation remained well below target throughout the programme, only achieving 23% of the overall target. (output 1.2) Iron supplementation was suspended in April 2020 as a precaution against COVID-19 and then reinstated at the beginning of 2021. UNICEF was able to reach 207,057 children between January and March 2022, thus reaching this period’s target. While the programme is functional, coverage is limited without the originally planned access to schools due to school closures during COVID-19. Another reason for underperformance is low engagement of adolescents, which UNICEF addressed with broader social and behavioural change activities working with the Ministry of Education to develop strategies that will helped ensuring access and an enabling environment for implementing these activities. UNICEF’s activation of mobile teams met targets across health and nutrition Indicators, with increased coverage on provided integrated nutrition and health services to children under five and pregnant women and new mothers. This includes the management of children under 5 years with SAM, micronutrient powder supplementation to children aged 6 – 59 months, and iron-folate supplementation to pregnant women and new mothers.
Health
Targets related to heath consultations to Pregnant and Lactating Women and children under five (output 1.4) exceeded targets (119%) and likely contributed to the notable SAM default rates, amongst other benefits. The PHC consultations most of the time double-counted due to field level methodology for collecting information. The accurate indictor to measure the impact would be the coverage rates, this will be changed for W+C. The UNICEF extension also included children under five accessing Integrated Management of Childhood Illness in health care facilities, outreach services, and mobile health teams.
Vaccination rates (polio and routine) remained under target for much of the period. This was largely due to access issues associated with COVID-19. Vaccination targets didn’t meet the target due to inability to conduct the campaign in the north of the country due to lack of permission from the authorities. Reported figures fall under target although cumulative for the course of the programme indicates positive performance with coverage of roughly 88%.
WASH
The number of people provided access to drinking water (output 1.8.) was exceeded by 26%. UNICEF also exceeded targets for access to water and hygiene promotion (output 1.10), given the early focus on these as part of the COVID-19 response.
Rapid response teams responding to cholera and emergencies during this period were reduced due to funding challenges, which greatly impacted UNICEF's performance during this period, but subsequently achieved 100% of targets in the last two reporting periods. (Output 1.9b).
Health & Nutrition
The voucher programme for pregnant women and mothers with new-borns to cover transportation costs for delivery, postnatal care, and medical care in case of complications, exceeded final targets (3,700; 117%). This target was greatly reduced from the business case (108,000) given restrictions associated with COVID-19.
Protection
Targets were met or exceeded in this area with a focus on case management/referrals and the number of children and caregivers provided psychosocial Support. The links between this and other aspects of the programme were not determined and could be an area of focus going forward.
Social & Behavioural Change
The extension included the support of Mother to Mother (Jadati) clubs that promoted lifesaving and positive parenting practices. The target for these was slightly under-achieved (335/350).
Lessons learned through this output, and recommendations for future programming
The focus on lifesaving activities has proven effective and there are various areas (SAM default rates; outreach; provision of WASH services) that warrant further investigation to determine what worked, how this relates to longer-term strategies to address malnutrition, and whether key aspects of these can be scaled-up.
Recommendation: 7% SAM default rates, over half the target of 15%, is a notable success and should be further investigated to understand what combination of activities contributed to this.
Recommendation: Ensure that independent baseline, midline, endline surveys are conducted. These should establish the links between expected outputs and outcomes and be used to inform programme adaptations and changes throughout the programme cycle.
Recommendation: for the new programme UNICEF should ensure closer monitoring of defaulters from SAM treatment, including tracking and analysing the principal reasons, and feeding this analysis into mitigation measures.
Recommendation: FCDO and UNICEF should work on increasing monitoring coverage, with particular attention to quality issues and barriers to access. Minimum standards for monitoring type and frequency should be established, with implications for UNICEF support if these are not met, or irregularities are found during monitoring. FDCO should ensure that minimum standards and access to UNICEF TPM findings are an explicit part of any future funding to UNICEF.

Output Number and Title	Nutrition, health and WASH services in Yemen are supported at a local level to be more efficient and effective
Output Score	A
Impact weighting (%)	45%	Impact weighting revised since last AR?	No

Output Indicators	Starting Target	Final Logframe Target	Final Result Achieved
Nutrition
2.1 (annual) / % of functional health facilities supported by UNICEF that provide SAM management programmes	83%	Final: 90%; Average: 87%
2.2 (cumulative) / # of Therapeutic Feeding Centre (TFCs) and Outpatient Therapeutic Programme (OTPs) supported by UNICEF with functional child-friendly spaces (offering Early Childhood Development services)	1,360	1,360	600 (44%) / (50% FCDO: 300)
2.2b (extension; August 2022 – March 2023) / # of health facilities providing Integrated H&N Service Package	444		418 (94%) / (100% FCDO)
2.2c (extension; August 2022 – March 2023) / # CHNVs providing integrated health and nutrition services	3,335		3,524 (106%) / (100% FCDO)
Health
2.3 (cumulative) / % of clinics supported by UNICEF offering minimum initial service package (primary health care, reproductive health, sexual and gender-based violence support) (total=4500)	44%	56%	56% / (20% FCDO)
2.4 (cumulative) / % of estimated pregnant women in Yemen that have received at one ante-natal visit by a community health worker	10%	45%	45% / (25% FCDO)
2.5 (cumulative) / # of Health Facilities provided with medical, preventive and protective supplies (PPE, IPC supplies, ventilators and related equipment, test kits etc) to continue service delivery with optimum safety from COVID-19 transmission (both for health providers and clients)	4,000	4,000	3,643 (91%) / (15% FCDO: 547)
2.5b (extension; August 2022 – March 2023) / # of Primary Health Care facilities providing clinical care to children (girls and boys) under five using the IMCI approach	557		950 (162%) / (100% FCDO)
WASH
2.7a (cumulative) / # of water facilities supported by UNICEF that have a risk management plan for improvement of water services	1	4	4 (100%) / (100% FCDO)
2.7b (cumulative) / # of people provided with improved water services by water facilities with a risk management plan	1,500,000	1,500,000	3,540,383 (236%) / (100% FCDO)
2.7c (extension; August 2022 – March 2023) / # of additional people accessing a sustainable drinking water service as a result of rehabilitation of sustainable water infrastructure	550,000		592,638 (108%) / (100% FCDO)
2.7d (extension; August 2022 – March 2023) / # of additional people with access to and use of basic sanitation	15,000		10,810 (72%) / (100% FCDO)
[note] Indicator discontinued in August 2021 due to changes in funding related to COVID-19 response.
[note] Implemented from July 2020 to March 2021.
[note] This level of overachievement signals a miscalculation in costs and targets.

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.
This output aims to improve the quality of services being offered to children and women of child-bearing age while strengthening healthcare systems. This output scores an A, as most activities met expectations or were overachieved.
Due to limited funding, COVID-19 responses this programme adapted changed initial targets concerning integrated health and nutrition services. As such, it focused on the availability of services (SAM management programmes (2.1); therapeutic feeding centres (2.2); minimum service package delivery (2.3)), medical, preventative, and protective supplies (2.5), and risk management plans for water facilities (2.7). The programme met or exceeded the indicator targets for all of these except therapeutic feeding centres (44% of target). This target was off track prior to the outbreak of COVID-19, due to difficulties encountered in providing incentives for CHWs (Community Health Workers) and lack of space in facilities.
[note] This included primary health care, reproductive health, and sexual and gender-based violence support.
FCDO received anecdotal feedback from Third Party Monitoring exercises reporting issues with overall quality of care at health centres supported by UNICEF, including patients paying for services, overall cleanliness of the facilities and inappropriate design of support packages and the efficiency and effectiveness of distribution approaches. UNICEF’s limited field presence and the fact that implementation is carried out by local authorities (north and south) means that UNICEF often does not have full oversight of services or direct access to data. Furthermore, service and support packages appear to be standardised and not based on essential or baseline assessments.
The results of this output indicates that such investments have been effective. Whilst we don’t have evidence in Yemen there is global evidence that localised system strengthening is critical for saving lives. UNICEF substantially exceeded the number of risk management plans, and we estimate this contributed to overachieving in number of people with access to safe water. (Output indicator 2.7b.) given that this was done with available funding, this represents a cost-effective approach, even if the exact cost of this activity is unavailable.
Lessons learned through this output, and recommendations for future programming
The system strengthening aspect of the programme was more challenging than direct service provision, in a context of weak governance and limited developmental focus at the central level. Ultimately, there continues to be a strong case that investment in maintaining and strengthening local government capacity to deliver services makes sense and will deliver value through more sustainable, resilient health services that are more able to manage shocks. However, this was not established fully in this programme.
UNICEF did not demonstrate an effective approach for working with local government health offices and NGOs to deliver quality services. This affected results for this output and also represents a missed opportunity to build upon what was being learned at the community and facility levels.
Recommendation: Focus on service delivery and healthcare strengthening at the facility level which is the primary hub for both emergency and long-term service provision to vulnerable communities. This can then be broadened iteratively to include health authorities, providing lessons and best practices for policy making and nation-wide development strategies.
Recommendation: Whereas service delivery requires standardised baseline/midline/endline surveys, healthcare system strengthening needs a more qualitative approach that includes regular insights from healthcare providers, healthcare authorities, and local populations. These should establish the constraints and opportunities with both the supply and demand of healthcare services while making links to more sustainable practices.

Output Number and Title	Evidence is generated by UNICEF to improve understanding of the context and influence the shape of the response in Yemen.
Output Score	A+
Impact weighting (%)	5%	Impact weighting revised since last AR?	No

Output Indicators	Starting Target	Final Logframe Target	Final Result Achieved
3.1 (cumulative) / # of surveys and assessments conducted by UNICEF funded by FCDO	2	8	16 (200%)
3.2 (cumulative) / # of analyses conducted on how the response efficiency could be improved (e.g. return on investment analysis)	5	15	14 (93%)
Indicator 3.3 (cumulative) / # of risk analysis and preparedness and contingency plans updated and shared with FCDO	1	2	2 (100%)
3.4 / NIS review action plan endorsed/validated (new in 2021)	1	1	1 (100%)
3.4b (extension; August 2022 – March 2023) / # governorates in which SMART survey is conducted	2		4 (200%)
3.4c (extension; August 2022 – March 2023) / # of water and sanitation assessments	28		28 (100%)
[note] This level of overachievement signals a miscalculation in costs and targets.
[note] Indicator discontinued in August 2021 due to changes in funding related to COVID-19 response.
[note] This level of overachievement signals a miscalculation in costs and targets.

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.
This output scores an A as all indicators were met or exceeded during the programme period.
Activities under this output focus on improving the knowledge and evidence base which underpin the ongoing analysis of malnutrition risks and prevalence in Yemen and strategies to reduce morbidity and mortality. This output was also meant to establish the links between service delivery (output 1) and system strengthening (output 2), thus establishing what works and what doesn’t; what can be brought to scale and what should be curtailed.
UNICEF conducted a Nutrition Information System review that was jointly designed with FCDO and carried out by technical experts contracted by FCDO. It identified factors that affect the collection, analysis, dissemination, and utilisation of timely, accurate and representative nutrition information in Yemen. The final report and findings of the review were validated by stakeholders including Ministry of Public Health and Population in both Sana’a and Aden.
The Standardised Monitoring and Assessment of Relief and Transitions (SMART) surveys funded under this output are critical for understanding the nutrition situation. These were not conducted until 2021, due to delays related to COVID-19 and in obtaining permissions from authorities.
UNICEF conducted three Rapid Assessments in April 2020, July 2020 and March 2021 to assess knowledge, attitudes, risk perception and adoption of COVID-19 prevention practices. A rapid assessment on COVID-19 vaccine hesitancy was also conducted in May 2021, including health workers in the South.
Lessons learned through this output, and recommendations for future programming
While evidence was produced, these lacked important standards (SMART surveys) and evidence that could establish the inks between service delivery and efforts to strengthen healthcare services overall.

Output Title	World Bank Funding: To prevent, detect and respond to the threat posed by the COVID-19 pandemic
Output number:		4	Output Score:	A+
Impact weighting (%):		5%	Weighting revised since last AR?	N/A

Indicator(s)	Baseline	Milestones for this review	Progress	Results Attribution to FCDO
Indicator 4.1: Number of designated laboratories with COVID-19 diagnostic equipment, test kits, and reagents	2	12	18	2
Indicator 4.2: Percentage of vaccination sites which meet site functionality criteria	0	70%	86%	80%

Briefly describe the output’s activities and provide supporting narrative for the score.
The activities for this output were completed in 2022 and covered in the Annual Review. Indicators under this output indicate targets have been surpassed or achieved earning this output a score of A+. With 86 percent of vaccination sites meeting site functionality criteria, measured against the 70 percent target and 18 designated laboratories provided with necessary equipment, test kits and reagents this output has shown significant progress, with laboratories in Aden and Sana’a directly attributed to FCDO’s contribution. 21 health facilities were rehabilitated towards improving service delivery. As per reporting submitted, the country has activated its public health Emergency Operations Centre for COVID-19.

Primary cost centres include the procurement of approximately 86,081 COVID-19 PCR tests and vaccines, with 723,943 people receiving at least one dose and 325,610 people fully vaccinated. In addition to these supplies, 184 ventilators were provided, along with ongoing deliveries to replenish supplies of oxygen, test kits, personal protective equipment, and other needed items to supported IU.
3,143 health workers were trained on infection prevention and control and 1,232 health workers on case management. 670 COVID-19-specific rapid response teams were trained to identify cases, do contact tracing, and contact follow-up.
Despite this output exceeding targets, there was some limitations and challenges to be noted. There was a shortage of vaccines between July and September 2021. Vaccination was not approved in the northern governorates and insecurity is limiting access to vaccination in some governorates, as well as supervision of activities.
Procurement processes were slow due to the lack of local suppliers and delays in shipping emergency supplies due to air space restrictions. In-country, there can be lengthy, multi-layer processes to approve distribution plans, leading to delays in distribution. In this reporting period, $5.25 million worth of supplies and equipment were distributed across NICUs, PHCs, and to RRTs. $1.671 million worth of health commodities were received and $1.77 million remained in the pipeline.
[note] PHC (Primary Health Care facilities), NICU (Neonatal Intensive Care units), RRTs (Rapid response teams)
Increased fuel and therefore transport costs emerged as a significant issue although precise cost calculations for this are not yet available. This may necessitate increased costs for logistics.
As described in relation to the output analysis, these and other delays caused this to be less efficient and cost effective than projected. While it was a viable option at the time to address critical health system strengthening, the overall VfM is questionable going forward.
The World Bank component has been assessed for the first time in 2022 annual review and has demonstrated the ability to deliver the Yemen COVID-19 Response Project successfully. However, the project experienced significant procurement delays (covered in 2021 Annual Review) and inflexibility in budgeting when prices fluctuated. In 2022, the executed funds project ($981,136) also faced significant delays and the World Bank was indecisive in allocating funding to relevant projects. The funds were eventually spent by the programme end date in March 2023. It was used to pay for consultancy to review and revise the financial cost of the new minimum service package for PHCs (a UNICEF/WHO initiative). The partnership between FCDO and the World Bank under the R2N programme has been challenging, due to the World Bank’s lack of responses and action on requests from the programme team.
D: Value for Money

VfM performance compared to the original VfM proposition in the business case
Overall, there are suitable examples of VfM across the four ‘Es’ and yet these tend to be anecdotal and lack consistent approaches to analysing gains in fiscal terms.
Economy
The primary programme cost centre included the bulk procurement and transportation of vaccines and Ready-to-Use Therapeutic Food. UNICEF reports that the RUTF unit cost does not exceed the $26.98 (£21.24) per carton for one child as set out in the business case. In the case of hygiene kits, the cost was US$6 which is judged to be good value for money if compared to US$14 for the cost of similar kits provided under the displaced people’s programme.
UNICEF maintains Long Term Agreements with suppliers of standard items, like RUTF. These agreements are typically in place for a year, securing predictable prices and speeding up procurement.
UNICEF applies the Harmonised Approach to Cash Transfers , which includes partner financial systems, spot checks and scrutiny of use of UNICEF funds.
UNICEF used mobile teams that cost between $4,000 to $6,000 a month, reaching an average of 50 children suffering from SAM. The cost per child is around $100 (which is within the average cost of managing a SAM child without supplies). This cost is offset by using these same teams to provide additional outreach and services for hard-to-reach communities.
UNICEF introduced hybrid solar energy systems into emergency water pumping for more cost-effective and climate-sensitive programming. A 2019 analysis demonstrates that the costs of these in the northern province of Sa’dah broke even against diesel-fed generator costs in less than six months. Projected overall savings will be over $500,000 USD in five years. Over a 10-year period, the return on investment will be 15% when applying FCDO’s 10% discount rate.
In relation to the World Bank Global Finance Facility grant to WHO for the COVID-19 response, over 50% of each grant was used in support of rolling out the COVID-19 vaccines in Yemen, including contributing to the cost of the mass vaccination campaign in September 2022, conducting integrated outreach, and providing per diem and transport costs for the rollout of the vaccines at fixed sites.
Efficiency
UNICEF is one of the largest global purchasers of child vaccines, nutrition supplies, and other equipment. This gives UNICEF leverage in negotiating the lowest prices with suppliers. These are noted above. This mass procurement, in turn, enables UNICEF to position supplies for the speedy delivery to actual facilities. Given that over 90% of facilities consistently reported no stock outs of RUTF (outcome indicator 1.b), the expected efficiency from this was achieved.
There were notable deficiencies in oversight and communication with Local Governorate Health Offices (GHO) and NGOs. This likely affected how activities were coordinated and thus how financial, human, and temporal resources were used.
Effectiveness
The business case projected that effectiveness would be achieved through the following, all of which were based on lessons from previous health and nutrition programming in Yemen.
[note] “Business Case: Responding to Nutrition Crisis in Yemen.” FCDO; September 2018. Page 35.
Investment in preventive services as well as traditional development-context health and nutrition interventions, rather than limiting the support to the emergency/humanitarian response only.	This was not done as the programme shifted toward emergency services.
Integration and multi-sectoral programmes and interventions at both community and health facility levels. This includes the importance of expanding availability of integrated health and nutrition services in the second and third level of coverage through several modalities, including Community Health Volunteers (CHV), Community Health Workers (CHW), mobile teams and integrated outreach services, to reach vulnerable and rural populations that cannot access health facilities due to high transportation costs and social exclusion considerations. This also includes ensuring Internally Displaced People (IDPs) and other conflict-affected populations have access to essential routine health and nutrition services, in addition to humanitarian support.	This was done at the facility level in many cases. However, these integrated approaches were not assessed as such and so the effectiveness (and other) gains from them are not clear. / CHV, CHW, and mobile teams were discontinued after poor performance in the second year of the programme. / Data also did not sufficiently disaggregate by IDPs, PLWD, and other vulnerable cohorts.
Strengthening monitoring and reporting systems at a sub-national level plays an important role in improving quality of services and performance indicators. Centrally led monitoring and reporting are not sufficient, especially as project interventions move to more decentralised levels.	There was an increase in decentralised, facility-level monitoring by both UNICEF and FCDO (Tahseen). However, UNICEF reports were incomplete and included anomalies that were rejected by health authorities. Tahseen monitoring included small samples which led to anecdotal evidence.
All donors supporting Yemen should work better together to support the maintenance and strengthening of the health and nutrition systems in Yemen and prevent their collapse. It is critical to support a combination of public-sector actors, civil society organisations, and local NGOs; and for international NGOs and UN agencies to focus their efforts on building the capacity of those who will remain in Yemen when the crisis ends and international support declines. While there are some risks associated with this approach, many mechanisms have been established to control and mitigate these risks, and there is proof that this approach is feasible within the current context. In the long run this approach will be the most effective towards ensuring sustainability through consistent and continuously maintained national and local systems.	This was not done publicly, however FCDO coordinated with the other key health donors (BHA, ECHO) frequently, about technical and strategic issues, as well as UNICEF performance This will continue under the new business case.

While these deficiencies indicate that the programme may have been overly ambitious, the programme did prove effective in providing essential life-saving nutrition, health, and WASH services along with important child protection services. While target achievement levels had some critical misses, overall, the programme was effective.
As described elsewhere, a concerted focus on service delivery combined with robust facility level monitoring and improvement, could provide a strong foundation for the more complicated and long-term focus on the underlying causes of malnutrition and healthcare system strengthening.
Equity
UNICEF’s activities included vulnerable, marginalised pregnant and lactating women and new-borns, malnourished children with medical and nutrition complications, and those with disabilities primarily through the health voucher scheme. 100% of CHW were women; 99% of CHV (Community Health Volunteers) were women (only 200 out of 18,078 CHVs are men) and 50% of the Rapid Response Teams were women. UNICEF did not consistently disaggregate date related to PLWD or persons over 65 years old.

E: Risk

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.

The 9-year conflict means Yemen has been a challenging place to work; exacerbated pre-existing vulnerabilities resulted in one of the worst humanitarian crises in the world; and a challenging operating environment. Since its start, the conflict has displaced over 4 million people, making Yemen the fourth biggest internal displacement crisis in the world. The risks of working in Yemen are significant; during the first years of the programme Yemen was an active conflict zone, but the risks did not outweigh the high return of providing life-saving support to people in desperate need. In 2020 Yemen experienced macroeconomic deterioration driven by COVID19, increasing costs of key commodity imports, a sharp reduction in humanitarian aid and increased access challenges due to movement restrictions. 2021 saw escalating conflict which civilians at grave risk and challenged the humanitarian situation, including ongoing COVID-19 pandemic, disease outbreaks, torrential rains and flooding, a desert locust plague, economic collapse, a fuel crisis across northern governorates and reduced humanitarian aid. The operating environment was extremely restricted, characterized by extensive access challenges and insecurity that hindered a principled aid operation.

Despite a de-facto truce in place since April 2022, which has reduced the conflict-derived risks, the operating context remains restricted to due significant controls imposed on international organisations by both sets of authorities – more stringent in the Houthi-controlled north. Humanitarian needs remained extremely high, disease outbreaks are re-appearing and food insecurity remains at globally concerning levels. The operating environment continued to be challenging. The Russian invasion of Ukraine and the subsequent increase in humanitarian needs in Europe has had detrimental knock-on effects across the world, including Yemen. Grain exports stalled, supply chains disrupted, and donor funding redirected to the Ukraine response. These risks were captured at the Yemen portfolio level and R2N Programme activities continued to operate, although the UN Humanitarian response is facing severe funding gaps. The response remains underfunded which forces some organisations to scale back their assistance, however billions of dollars have been given to Yemen for nine years, and donors are requesting prioritisation, efficiency and stringent targeting of the most vulnerable.

UNICEF has a risk management system and used this to inform decision making. As part of FCDO’s regular meetings with UNICEF, discussions covered progress against indicators, context, needs and risk.
R2N was originally categorised as a “major” risk but was increased to “severe” from 2019 due to the deteriorating operating environment in Yemen. The programme remains at a severe residual risk and our risk appetite is aligned with the portfolio risk appetite. This programme has risks under the following categories: strategy and context (4), policy and programme delivery (2), safeguarding (1), financial and fiduciary (5), reputational (2) and people (1). There are no risks under the public service delivery and operations category. A full risk register can be found on Aid Management Platform.

Main risks to programming

Fiduciary risks are rife in Yemen. There are ongoing suspicions of fraud, corruption and aid diversion. These were captured at the outset of the programme in UNICEF’s risk register. These include:

Medical supplies: Procurement, transportation and distribution of medical supplies not reaching intended beneficiaries. UNICEF procurement and holding of supplies in decentralised storage was covered by their global insurance (though this is not a mitigation measure). UNICEF managed a centralised security clearance process including mapping of number of trucks, roads and routes. FCDO visited UNICEF warehouses and noted they are managed very systematically, though some warehouses were not managed by UNICEF themselves but by third parties. UNICEF also tried to increase MoH capacity in warehouse management, but more support is needed.

Location of health clinics prior to the top-up in 2022, FCDO and UNICEF were unaware of the specific location of health clinics. It was challenging to secure a list of clinics, eventually a list of names was provided to UNICEF by MoH, but verification of the clinics (assessing their capacity/functionality, or indeed whether they even exist) did not take place until the approach with UNICEF was changed under the top-up.

Mismanagement of funds results in support not reaching intended beneficiaries. This includes:

  - Incentive payment to health workers as cash incentives through Yemeni health systems, and vouchers to beneficiaries, are subject to political, operational and fiduciary risks. UNICEF issue per diems linked to reported performance (# days worked)

  - Use of Cash and extensive use of advances for the project leads to increased risk of fraud and corruption. As mitigation, UNICEF used the UN harmonized approach to cash transfers, which included assessment and strengthen of partners financial systems, though it is unclear if this systematically took place. UNICEF also controlled cash flow through smaller disbursements, advances and reimbursements. UNICEF also said they would increase use of third party monitoring to programme sites, especially in areas not possible for UNICEF to visit themselves. UNICEF ensured their finance and compliance departments are sufficiently staffed with qualified individuals.

A risk identified linked to the World Bank COVID-19 component was the limited capacity of the Third Party Monitors which could have led to misuse of funds and inaccurately reported results.

A continued concern is the administrative restrictions placed on international aid by the authorities, particularly in areas under Houthi control. These administrative restrictions can cause delays to UNICEF’s programming and also affect the ability to conduct assessment and monitoring visits, including their third-party monitoring, audits and spot checks, which are critical for FCDO to assess the impact of the programme. Regular engagement between FCDO and UNICEF helps to ensure that minimum levels of monitoring are being achieved.
Due Diligence Assessment
A full Due Diligence Assessment of UNICEF Yemen was conducted by Tahseen, FCDO Yemen’s Independent Monitor, in August 2022. UNICEF Yemen received a minor risk rating for governance and internal control, a major risk for ability to deliver, moderate risk for financial management and stability, a moderate risk for downstream delivery and safeguarding. Many of these issues were highlighted in previous annual reviews and TPM findings. The assessment identified several areas for progress and subsequent recommendations which are summarised below:
1. Monitoring and evaluation: the desk-based assessment could not provide FCDO with the re-assurance that accurate MEAL ( Monitoring, Evaluation, Accountability, and Learning) was being implemented in the field, and UNICEF required a larger field presence in Yemen. It was recommended that UNICEF continue to establish more presence outside Sana’a and more staff visiting implementation sites. FCDO and UNICEF Yemen have already looked to address this concern in FCDO’s funding to UNICEF Yemen this year, focusing on a specific set of health facilities with enhanced and pre-agreed monitoring activities and reporting, through which FCDO can gain more assurance over delivery and quality control.
2. Exchange rate management: The UN’s current treasury management processes seem strong and appropriate to the context, but the UN including UNICEF has struggled to act in a timely manner during periods of major contextual changes and issues with the YER. There remains a risk that the UN system and UNICEF will again be slow to adapt to future challenges and this could result in poor value for money in the use of FCDO funds. It was recommended that UNICEF Yemen shares the current treasury arrangements in Internationally Recognized Government areas of Yemen and engages closely with FCDO on any further currency issues in Yemen to ensure best value for money to the beneficiaries.
3. Safeguarding and whistle blowing: UNICEF had strong policies and procedures, but FCDO require more information of how UNICEF manage local authorities and ensure whistle blowing, and incident reporting is monitored. It was recommended that UNICEF continue with mandatory PSEA (Protection against sexual exploitation and abuse) assessments and training with CSO partners.
COVID-19
The COVID-19 pandemic affected the overall health service delivery, including delivery of vaccination services through fixed and outreach service delivery points. UNICEF supported the development of a COVID19 risk mitigation matrix to support continuity of immunisation services, ensuring infection prevention control (IPC) measures in place, such a provision of personal protective equipment. The global guidance on IPC was contextualised and translated for use during the training of health workers/ vaccinators in COVID19 context.
The programme added two severe COVID-19 risks during the global pandemic on beneficiaries’ fear of contracting COVID-19 and lack of seeking healthcare and on COVID-19 travel bans and restricting access to humanitarian operations. Now that operating conditions have somewhat reverted back in 2022, these risks have been removed.
People Risks
The programmes “People” risk (P54 on risk matrix) for insufficient resourcing within the FCDO was reworded to include the risk of Programme Operating Framework (PrOF) non-compliance and increased the residual probability to “likely” and residual risk to “major” due to the resourcing constraints in the Yemen Office Network. The resource constraints in Yemen are reflective across the FCDO and recruitment has been difficult due to the changing HR policies across the Civil Service. This risk was added to the portfolio risk register and was escalated by the Development Director up to Director General level.

F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency.

Finance
Year	Spend per year
2018/2019	£35,677,497.75
2019/2020	£34,343,221.67
2020/2021	£52,728,334.10 (*includes £5,643,023 to the World Bank)
2021/2022	£19,077,264.00
2022/2023	£25,000,000
Total funds disbursed to date:	£166,826,317.52
[note] Payment of $7,761,000; calculated based on average exchange rate USD to GBP in 2021: 0.7271 GBP.

There was a funding gap between April and July 2022 whilst the UNICEF extension period was being agreed and the due diligence assessment was conducted. FCDO disbursed £18 million in August 2022 to fund new activities under the extension, reducing implementation to seven months by the end of December 2022 an agreement to add extra 7 million to support UNICEF.

Exchange rate challenges

On UNICEF’s systems, all budgets reflect costs in US dollars and the UN exchange rate for the past 12 months (which is an average of 580 YER/USD), are used at the time of payment. This reasonably accurately reflects the exchange rate in the north of Yemen (around 600 YER/USD). However, the exchange rate in the south of the country has deteriorated markedly and is currently around 1,500 YER/USD. FCDO has raised this issue with UNICEF for around a year, and UNICEF reported finally implementing a new approach in November 2022 that considers local market exchange rates in the South.

Performance of partnership

FCDO appreciates UNICEF’s close engagement and working in partnership. UNICEF’s model of working largely through government entities allows scale but also raises concerns over quality of delivery and reporting, and the sufficiency of monitoring. FCDO must work together with UNICEF to improve monitoring, assurance, and accountability to affected populations. FCDO appreciates closer working with UNICEF recently on areas such as ensuring the transparency and credibility of key SMART surveys, while noting that we expect greater engagement and prioritisation of issues of safeguarding and beneficiary feedback, and greater transparency on UNICEF TPM.

Delivery against planned timeframe

Timeliness of narrative and financial reporting has been adequate and on time. However, in terms of quality and coherency of data there is significant room for improvement. For example, UNICEF’s reporting and presentation of data in relation to the logframe has been incomplete and at times inaccurate.

Monitoring of assets

UNICEF maintains asset registers in a programme called VISION, from which it can trace FCDO funded assets. A physical count is done twice a year (June and December) to ensure asset safeguarding measures are in place and to record functionality conditions.

VfM
FCDO’s contribution included an indirect cost recovery charge of 8% (a standard board approved rate). A further 11.7% in country management cost was applied to cover operations (6.5%), M&E (1.3%), emergency and field operations (0.9%) and security costs (2.5%). Direct staff costs total 6.86% of the total budget.
While there were examples of efficiency gains, these were not measured.
Programme-level approach to monitoring and evaluation
The programme required UNICEF to provide annual monitoring reports. These were reviewed in each annual review. A final monitoring report included a survey of 246 health facilities and 2,630 patient interviews between September 2022 and June 2023. Of these, most were functional although gaps in services existed in nearly all. Six were not functional at all. 41 facilities did not have access to water.
FCDO also provided independent third-party monitoring through Tahseen that conducted 11 field visits to single facilities (light touch reviews) and five visits to multiple facilities and activities (in-depth reviews) in 16 districts in the north and south. These assessed patient feedback, access and/or payment for services, quality of services, quality of facilities, and, during COVID-19, the use of standard COVID-19 protocols. Common findings included:
- High degree of satisfaction from patients with the quality of services.
- Clean and well-maintained facilities with adequate gender sensitivity overall.
- Fair degree of record keeping and use of vaccination cards.
- Inconsistent availability of supplies and medicines.
- Inconsistent staffing levels with key health professionals often absent from facilities.
- Payment for services in most facilities.
- Lack of knowledge/oversight from UNICEF for select facilities.

FCDO recommended ways to improve monitoring and evaluation in the last annual review (2022). These include:
- UNICEF should ensure closer monitoring of defaulters from SAM treatment, including tracking and analysing the principal reasons, and feeding this analysis into mitigation measures.
- FCDO TPM (Third Party Monitor) should review the functionality and sustainability of solar water pumping systems and draw on this learning for future programming.
- FCDO and UNICEF should work on increasing monitoring coverage during the existing programme, with particular attention to quality issues and barriers to access. Minimum standards for monitoring type and frequency should be established, with implications for UNICEF support if these are not met, or irregularities are found during monitoring. FDCO should ensure that minimum standards and access to UNICEF TPM findings are an explicit part of any future funding to UNICEF.
In addition to these, the programme lacked independent baseline/midline/endline surveys and an evaluation that could have better assessed the relationships between outputs and outcomes, the implications of different programme changes, and what could be done to ensure that the programme remained on track towards outcome and impact level results. This is addressed in a proposed recommendation in Section B.

Monitoring

	October 2018-March 2023
Number of programmes monitoring visits	378
Number of micro-assessments	143
Number of audits	76
Number of spot checks	40

The above table notes monitoring conducted by UNICEF throughout the programme. Since COVID-19, UNICEF have advised that some monitoring visits are still being conducted remotely. Monitoring activities UNICEF conducts:

- Programme monitoring visits – undertaken by programme staff or third parties where there are access constraints.
- Project specific TPM – contracted by UNICEF either as a project or donor requirement. FCDO do not fund this type of monitoring, so this type of monitoring is not carried out for this programme.
- Financial monitoring – spot checks and audits (either scheduled or special) which focus only on monitoring cash.
FCDO has contracted its own third-party monitoring service, Tahseen, with two light-touch reviews and one in-depth review conducted in early 2020; one in-depth review in 2021; and 12 light-touch reviews and 10 in-depth reviews in 22/23 period to the programme closure.

Date of last narrative financial report	UNICEF 29 August 2022 / World Bank 15 June 2022	Date of last audited annual statement	UNICEF 27 June 2022 / World Bank 30 June 2021