## Template
Please refer to the Guidance Notes tab for advice on completing the various fields in the logframe.
Please refer to the Results Framework Prof Guide for broader information on the logframe approach
PROJECT TITLE | Support to Establish an International Financing Facility for Education (IFFEd)
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
This programme will contribute to improving learning outcomes in developing countries. This is covered in the IFFEd business case that will be submitted to Ministers in September 2023. This seed funding programme will contribute to the IFFEd learning outcomes by establishing the necessary organisation. |  | Planned
Achieved
Source
| Impact Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Planned
Achieved
Source
OUTCOME | Outcome Indicator 1 |  | Baseline July 2022 | Milestone 1 | Milestone 2 | Target September 2023 | Assumptions
Establish and operationalise IFFEd | IFFEd is established and operationalised | Planned | IFFEd is a project of the Education Commission and IFFEd as an organisation does not exist |  |  | IFFEd is established and fully operationalised | Assumptions for Outcome and all Outputs are: continued UK political support for IFFEd; UK ODA budget for IFFEd's long-term operations is available; continued political support from other donors; continued support from UNSG through the Transforming Education Summit; continued engagement and willingness to participate in IFFEd from MDBs (Asian and African Development Banks); assessment of continued appetite from Lower Middle Income Countries to borrow for education at concessional rates; and seed funding from other sources is secured.
Achieved
Source: Education Commission
| Outcome Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Planned
Achieved
Source
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
750000
INPUTS (HR) | FCDO (FTEs)
1.5 FTE (1 FTE economic adviser + 0.3 FTE policy leader + 0.2 Programme Manager)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline July 2022 | Milestone 1 | Milestone 2 | Target September 2023 | Assumptions
Establish IFFEd as a Swiss Foundation | IFFEd has completed registration as a Swiss Foundation | Planned | IFFEd is a project of the Education Commission |  |  | IFFEd is established as a Swiss Foundation and is operating independently
Achieved
Source: Education Commission
| Output Indicator 1.2 |  | Baseline July 2022 | Milestone 1 | Milestone 2 | Target September 2023
| IFFEd has appointed a founding CEO and initial team members | Planned | The Education Commission has an Executive Director acting as interim CEO and a team from the Education Commission |  |  | IFFEd has appointed a founding CEO and initial team members
Achieved
Source: Education Commission
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline July 2022 | Milestone 1 | Milestone 2 | Target September 2023
| IFFEd's interim governance structure (including interim Board) is operational and the long-term governance structure has been designed and agreed by partners | Planned | The Education Commission does not have an IFFEd governance structure |  |  | A long-term governance structure is agreed by all partners and signed off by the interim IFFEd Board
Achieved
Source: Education Commission
IMPACT WEIGHTING (%) | Output Indicator 1.4 |  | Baseline July 2022 | Milestone 1 | Milestone 2 | Target September 2023
| IFFEd's long-term governance structure is being implemented | Planned | No long-term governance structure |  |  | IFFEd's long-term governance structure is being implemented
Achieved
Source: Education Commission
IMPACT WEIGHTING (%) | Output Indicator 1.5 |  | Baseline July 2022 | Milestone 1 | Milestone 2 | Target September 2023 | INPUTS (£) | FCDO (£) | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
| Application for International Institution Status is submitted and under review | Planned | IFFEd is not yet estabished either as a foundation nor as an international institution |  |  | Application for International Institution Status is submitted and under review | [6 empty] | Assumptions
|  | Achieved |  |  |  |  | INPUTS (HR) | FCDO (FTEs)
Source: Education Commission
OUTPUT 2 | Output Indicator 2.1 |  | Baseline July 2022 | Milestone 1 | Milestone 2 | Target September 2023
Develop critical institutional foundations to operationalise IFFEd | Key parameters of IFFEd's operational and financial model are agreed by partners | Planned | Operational model based on 2018-2019 negotiations. Draft legal and financial documents in place but no detailed discussions with current partners on these drafts |  |  | Key parameters of IFFEd's operational and financial model are agreed by partners through sign-off of the Framework document, legal documents and grant agreement.
Achieved
Source: Education Commission
| Output Indicator 2.2 |  | Baseline July 2022 | Milestone 1 | Milestone 2 | Target September 2023
| IFFEd's legal documents and financial model are agreed by donors and MDB partners | Planned | Draft legal documents and financial documents in place, based on 2018-19 negotiations, but no detailed discussions with partners on these drafts |  |  | IFFEd's legal documents and financial model are agreed by donors and MDB partners. Legal agreements ready to sign and are in accordance with UK law and legal requirements.
Achieved
Source: Education Commission
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline July 2022 | Milestone 1 | Milestone 2 | Target September 2023
| IFFED's financial systems and processes are established to enable the transfer of donor resources | Planned | Draft financial documents in place, based on 2018-19 negotiations. Financial systems used are through RPA acting for the Education Commission. |  |  | IFFED's financial systems and processes are established to enable the transfer of donor resources to IFFEd as an independent entity.
Achieved
Source: Education Commission
OUTPUT 3 | Output Indicator 3.1 |  | Baseline July 2022 | Milestone 1 | Milestone 2 | Target September 2023 | Assumptions
Secure additional donor partners to unlock the UK commitment and proceed to full operationalisation | Approvals are complete and funding agreements are in place for two additional donors across the guarantee and grant windows | Planned | Two additional donors are in place but approvals are not complete and funding agreements are not in place |  |  | Approvals are complete and funding agreements are in place for two additional donors across the guarantee and grant windows
Achieved
Source: Education Commission
| Output Indicator 3.2 |  | Baseline July 2022 | Milestone 1 | Milestone 2 | Target September 2023
| Additional sovereign donors reviewing an IFFEd contribution | Planned | Outreach to other donors in process |  |  | Additional sovereign donors reviewing an IFFEd contribution
Achieved
Source: Education Commission
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline July 2022 | Milestone 1 | Milestone 2 | Target September 2023
| Evidence of outreach to philantropic donors | Planned | Some outreach to philantropic donors |  |  | Evidence of outreach to philantropic donors, with philanthropic seed capital secured.
Achieved
Source: Education Commission
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)

## Change frame
Use this change log to record all changes to the logframe over the life of the project.
ID | LOGFRAME SECTION | DETAILS OF CHANGE | AUTHOR | DATE
E.g. | Output 1, Indictor 2 | Indicator amended from 'No of children enrolled in primary schools' to 'Number of children enrolled in UNICEF supported primary schools (disagregated by sex) | Joe Bloggs | 2022-01-01
1
2
3
4
5
6
7
8
9
10

## Guidance Notes
Logframe Template Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
The name of the programme to which this logframe applies, from the business case
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from FCDO and partners to achieve the impact, ie is your project nested within a broader undertaking? This will often be the Impact indicator from the Theory of Change in the Business Case.
OUTCOME
The outcome should link through to the outcome level in the programme Theory of Change as stated in the Business Case. The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Sustainable Development Goals (SDGs) or Climate Change.
Ongoing monitoring of progress against outcome milestones takes place as an assessment of whether you expect to achieve the Outcome by the end of the programme in the programme Annual Reviews. An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR) based on the target milestone for the programme completion.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear. Outputs should reflect the Theory of Change as set out in the Business Case for the programme.
Progress towards the outputs will be assessed and scored at the Annual Review, using output indicators and milestones. Achievement of the outputs will be assessed at project completion, using output indicators and targets.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
1. Promote a more considered approach to the choice of Outputs at project design stage; and
2. Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by FCDO and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The FCDO share at Outcome Level is a simple, pro rata calculation of FCDO’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual FCDO Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
Specific – what will be measured? And how?
Measurable - data can be collected
Relevant - to the results chain
Useful – for management decision making
Does not include any element of the target
Can be disaggregated if relevant (especially when the indicator relates to number of beneficiaries reached with an intervention)
A mix of qualitative and quantitative
Already defined - if relevant include indicators which towards the FCDO Outcome Delivery Plan / ICF KPIs / SDGs.
Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Theory of Change and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your PRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / Management Information Systems.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually and you should record the expected frequency of data availability.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability. Use the Data Quality Prof Guide to help you consider the quality of your data.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same. If you are carrying out any evidence gathering to check your assumptions then make reference to this as part of this section.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
Equity - Is the intervention meeting the needs of all beneficiaries?
FCDO’s Approach to Value for Money (PrOF Guide) provides further advice on ensuring VfM.

## Sheet1
Mandera | 95 | 23.4
Kwale | 79 | 23.8
Turkana | 64 | 27
Samburu | 84 | 50
Wajir | 54 | 23.2
Nakuru | 64 | 36.4
Lamu | 75 | 48.5
Kilifi | 69 | 45.7
Garissa | 83 | 60
Isiolo | 46 | 26.3
Laikipia | 43 | 25.2
Bungoma | 58 | 45.2
Tana River | 68 | 61.6
Kisumu | 45 | 42.1
West Pokot | 46 | 47.4
Mombasa | 40 | 48.5
Marsabit | 26 | 34.7
Baringo | 25 | 44
All counties | 58 | 38