## Annual Review

Title: Programme for Strengthening State Capabilities in India
Programme Value £ (full life): 4,995,000		Review date: 27/02/2022
Programme Code: 300738	AMP start date: 27/02/2019	AMP end date: 01/11/2023

Summary of Programme Performance
Year	2020	2021	2022
Overall Output Score	A	A	B
Risk Rating	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300738/documents
DevTracker Link to results framework:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300738/documents

List of Abbreviations

Acronym	Full Form
AR	Annual Review
CBP	Country Business Plan
CEIP	Carnegie Endowment for International Peace
CPR	Centre for Policy Research
EFO	Externally Financed Outputs
DoPT	Department of Personnel and Training
FCDO	Foreign, Commonwealth and Development Office
GoI	Government of India
IUTF	India Umbrella Multi-Donor Trust Fund
KYR	Know Your Regulator
LBSNAA	Lal Bahadur Shastri National Academy of Administration
PSSC	Programme for Strengthening State Capabilities
SARTTAC	IMF South Asia Regional Training and Technical Assistance Centre
TA	Technical Assistance

Documents referred to for this annual review:
A. Progress report by the World Bank
B. Mid-year review report by IMF/SARTTAC.
C. Quarterly reports by CEIP/CPR
D. List of articles/studies published.

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

The seismic impact of the pandemic on the UK economy has forced the UK government to take tough but necessary decisions, and as announced in 2020, the UK has now moved to spending 0.5% of GNI as Official Development Assistance (ODA) in 2021.

Following a thorough review, the FCDO’s programme budget has been allocated in accordance with UK strategic priorities against a challenging financial climate of COVID.

Throughout the business planning process, the FCDO has strived to ensure that every penny of ODA spend brings maximum strategic coherence, impact and value for taxpayers’ money.

The move to 0.5% has resulted in changes to this programme, which is being adapted and will continue. This Annual Review reflects that the programme has had to refocus resources and so will deliver against a new plan with new results targets. As a result, the findings of this Annual Review reflect on a programme in transition.

The UK remains a world leader in international development, not only through the impact of these financial allocations but also through the creation of the FCDO, integrating diplomacy and development to deliver greater impact. The Government has set out criteria on returning to spending 0.7 per cent of GNI on official development assistance. Improving economic forecasts shows that HMG may meet its test to return to spending 0.7% of Gross National Income on aid in the final year of the Spending Review.
Description of programme [1-2 paragraphs]
The Programme for Strengthening State Capabilities in India (PSSC) works with select government institutions, sectors, and states (Odisha and Punjab) to improve policies, practices and systems to support India’s governance, economic growth and development ambitions. It does so through research and analysis, hands-on technical assistance, and facilitating learning from the UK experience.

PSSC works with the multilateral partners and think tanks. The three active partnerships during the review period were:

- Carnegie Endowment for International Peace (CEIP) and Centre for Policy Research (CPR): are working together on research and analysis to better understand India’s regulatory and institutional capacity to make markets work better; how to strengthen India’s apex institutions; and how to enhance centre-state cooperation.
- World Bank: (i) test the Bank’s new “strategic state partnership approach” in Punjab and Odisha through policy dialogue, analysis and advise in key areas (urban, social protection, water, data systems); ii) support GoI’s Mission Karamyogi on civil service modernisation and capacity building.
  [note] State Partnership approach: as part of its Country Programme Framework (2018-22), the World Bank introduced a new ‘whole-of-government’ approach and to break the departmental silos. WB will provide multi-year technical support to assist select states in addressing development challenges, support growth and shared prosperity. Several global practice teams in World Bank - Agriculture, Energy, Urban, Water, Governance, Social Protection - support the activities in Odisha and Punjab. This helps the state to strengthen its policies and institutions, gain new knowledge and develop new lending projects to implement reforms and improve service delivery. Bank is supporting Odisha, Punjab, Kerala, Meghalaya and Chennai (city partnership) under this approach. A financial agreement with the World Bank on energy reform ended in Jan 2021.
- IMF South Asia Regional Training and Technical Assistance centre (SARTTAC): Government of Odisha to strengthen its public finance management including fiscal risks, medium term macroeconomic forecasting and cash management.
  [note] Training on Risk Based Audit Techniques, Tax Administration Diagnostic Assessment Tools, Macroeconomic and Fiscal Forecasting (delivered by SARTTAC’s macroeconomic advisor), Fiscal Risk Management and Government Finance Statistics Manual 2014 (GFSM 2014) framework.

The programme directly supports activity 1.4 under the UK India Roadmap (democratic and institutional partnerships between the UK and India). It is the flagship FCDO open societies programme in India, aligned with the UK in India Open Societies strategy and supports objectives under the Connecting our People pillar of the Country Business Plan.

Summary supporting narrative for the overall score in this review [1-2 paragraphs]

The programme delivery was slowed by the continued impact of covid and the ODA cuts that reduced the overall budget. The more intensive COVID second wave had the complete focus of the government, as well as the implementing partners. Consequently, the activity plans were pushed by six to nine months. The World Bank agreement was extended by another year and will now end in March 2023.

Despite the challenging situation, the programme achieved significant results including some new initiatives. These included:

- In focused states: Better fiscal risk controls and management systems in Odisha, a new state data policy and Transparency in Public Procurement Act and Procurement Guidelines adopted in Punjab. Two new World Bank loans for Punjab aggregating US$ 275 million to support urban service delivery reforms and building fiscal and institutional resilience; and a new Odisha state capability and resilience growth project of US$150 million is under.
- Capacity building plans for six departments with the Capacity Building Commission; an assessment framework for Central Training Institutes finalized; and a new World Bank lending project for DOPT and CBC (US$ 50 million) to implement Mission Karamyogi.
- New work streams including on i) regulatory practices and governance with the “Know your Regulator” series, collaboration with national law schools and policy analysis; ii) independent policy and institutional analysis to enhance center -state relations and cooperative federalism; iii) India-UK partnership on court administration.
  [note] with the Forum for Indian Regulators (FOIR) and Indian institute of Corporate Affairs (IICA). IICA is a training institute under the Ministry of Corporate Affairs.
- A series of data-driven articles on gender, social change, and urbanisation in north India.

Major lessons and recommendations for the year ahead [1/2 page]

Major lessons:
- There is genuine interest from Government of India in lessons that can be drawn from the UK experience, particularly regarding civil service learning and training. A few quick joint activities in the initial period helps build trust, understand ways of working and define longer term outcomes.
- COVID put almost all programme activities on hold, particularly with state governments. But it also demonstrated the vital importance of institutions to respond and recover from crisis. We are focusing on the right bodies.
- Access to high quality robust analysis helped the programme team to identify the right entry points such as for court administration and now for internet governance.
- With the Multilateral partners, important to agree results, management and communication arrangements early, to ensure that the UK support is recognised and results clearly attributed.

Recommendations:
- We have agreed an overall approach for our work in India on Open Societies that will have three components - institutions, human rights, and global standards. We will align the programme accordingly - add new activities and update the Theory of Change and the log frame.
- More can be done to i) ensure that the policy briefs land with the right stakeholders; ii) work with the DHCs so that the full benefits of the state level partnerships, learning across states and research on federalism are realised; and iii) continue to build synergies across the India Country Plan including joint visits and learning sessions with the World Bank and other partners.
- The programme focus on understanding government capacity from an economic and market lens continues to meet the requests of support from state governments and is aligned with UK strategy to support open societies and economies.
- Develop the component on rule of law, given the read across to other UK workstreams.
- The Civil Service Reform agenda should be pursued under the World Bank partnership. FCDO should take a light touch approach connecting with the right UK counterparts, unless there are clear requests from GoI.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

The overall theory of change remained valid for this reporting year.

Due to the budget cuts, two programme components - the secondment of a senior adviser to the World Bank; and contribution of £1.5 m to the World Bank Trust Fund – were dropped; and no new states were added under any of the partnerships.
Input	Interventions	Output	Outcome	Impact
Up to £4.96 m TA / FCDO / Resource: / SRO / Sr. Advisers / Programme Manager	Engagement with states and sectors to understand drivers and barriers of inclusive growth, fiscal condition, governance readiness (meetings, diagnostic analysis, research, seminars)	Strategic engagement with states leading to stronger partnerships.	Strengthened institutional systems and capabilities (planning, management, policy making, implementation capacity) in select states and sectors	Strengthened overall governance, enhanced income and livelihood outcomes and inclusive growth
		Identify key areas of governance, institutional and policy strengthening in states and across sectors.
		Evidence driven and informed pipeline development for FCDO India.
	Commission demand driven research and evaluation to inform policy and institutional and implementation capacity strengthening	Enhance DFID's ability to respond to demand driven governance, institutional and policy reforms to influence and enhance state capability. / Enhance FCDO India’s ability to influence key reforms.
	Provide capacity development trainings and associated activities to states and sector institutions	Enhance capacity of state administration based on gaps identified from the diagnostics and research.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

Covid slowed the progress, but the partners are optimistic that the pace will pick up and the programme outcomes and impact will be met. The team will review progress next quarter once the covid restrictions are eased.

The team is finalising the overall approach for Open Society and will review the programme components and log frame against this approach; and also align with the three-year country business plan, which is under preparation.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

The programme should continue. It is FCDO India’s flagship open societies programme delivering against the Country Business Plan, UK-India Roadmap and UK in India Open Societies Strategy. It supports objectives and programmes across the UK network, by:

- Helping us understand India’s political economy and key institutional drivers of reform, particularly labour markets, role of regulators, capacity and politics of apex institutions and changing federalism dynamics in the country.
- Investing in partnerships with India on key UK priorities: civil service modernisation, rules and standards of internet governance, and reform of the justice sector. The latter, if successful, has the potential to support broader justice and home affairs objectives and improve services for UK nationals in India.
- Building relationships with key institutions such as LBSNAA and state governments such as Odisha and Punjab and facilitating new policies, innovative approaches, and improved governance.

The PSSC will be adapted to reflect the UK in India Open Societies strategy paper. The programme is due to end in November 2023. The team will consider if this can be brought forward to end in March 2023, in anticipation of a new Open Societies programme due to begin in the financial year 2023/24.

C. DETAILED OUTPUT SCORING

Output Title	Strategic engagements with states leading to stronger partnerships
Output number:		1	Output Score:	B
Impact weighting (%):		60	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
Number of pilots supported with a pro-poor impact	2	In progress / In Odisha, Knowledge and Learning Hub with CGIAR; ag tech challenge Fund.
% of engagements involving senior government officials (add description)	70%	Achieved: / World Bank interactions are at the senior most levels. / Four IMF missions to Odisha for secretaries/joint secretaries Govt of Odisha;

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

The output is scored B, as many of the activities could not be completed due to Covid despite the best efforts of the partners.

PSSC helped the World Bank implement and test its new “whole of government” partnership approach in Punjab and Odisha including through policy dialogue, analytical studies, good practices.

In Punjab, the support continued in three areas: (i) public management systems and capabilities; (ii) resource efficiency in the water-energy-agriculture nexus; and (iii) urban finances and planning frameworks. Some of the key interventions started in the year were: guidelines and rules for State Data Policy; transparency in procurement; strengthening grievance redressal system and gender budgeting. The technical support has led to two new lending projects of total value of $275 million on municipal reform in two cities and on building fiscal and institutional resilience.
[note] Finance, Planning, Governance Reforms, Agriculture, Energy, Groundwater Management, Local Government and Women and Child Development departments
[note] (i) Punjab Municipal Services Improvement Program, for Amritsar and Ludhiana (US$ 125 million, approved on 31 March 2021) and (ii) Building Fiscal and Institutional Resilience in Punjab (USS $ 150 million, planned for approval in FY22).

In Odisha, the World Bank technical support continued for integrated social protection delivery system, and for modernising agriculture and allied sectors including a Knowledge Sharing and Learning Hub (KSL) on Agriculture was set-up in Odisha. Based on this technical support, the GoO and Bank are preparing a new lending operation around building state capabilities for social protection and disaster resilience for US$ 150 million.
[note] Price dissemination; Value chain analysis; ag tech challenge; district and block level coordination, capacity building strategy; learning sessions

The World Bank proactively shares lessons from Punjab and Odisha with other states and with Niti Aayog. for scale up adoption. The Fiscal Sustainability Analysis tool developed for Punjab, is now being transferred to Orisha, Kerala, Chhattisgarh.
[note] Niti Aayog – Government of India’s Policy think tank.

Building on the first phase of engagement with the Government of Odisha on Public Finance Management (PFM), IMF/SARTTAC developed a new two-year capacity development program with the state. This will strengthen the medium-term fiscal framework, budget preparation, commitment control, and cash forecasting.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

The support to World Bank and IMF delivers good value for money with regard to economy and efficiency. The contribution to the World Bank allows the FCDO to leverage its funds as part of a wider programme of support, and both organisations have trusted and long-standing relationships with Punjab and Odisha state governments. However, we are unable to measure the level of effectiveness of individual capacity building activities. More can be done to test effectiveness and equity before assessing overall VfM of the output.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

There have been no changes to the output this year. The team will review the output to align it better with the India OSHR framework.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Progress on recommendations from the previous AR

The recommendation last year was to have more sustained engagement with the government counterparts; aligned with the HMG priorities for India and a monitoring framework to assess pro-poor impact. All three recommendations are work in progress.
Lessons learned this year

Lessons include:
COVID-19 crisis created an urgency for key reforms – to strengthen macro-fiscal resilience, strengthen the state systems to deliver public services, and protect lives and livelihood.

A sector agnostic core team at the state level in Odisha helped connect different departments. for coordinated action as seen for the covid response.

Virtual trainings and meetings were useful to stay connected and maintain relationships with key stakeholders. But it was often difficult to apply the same rigour.
Recommendations for the year ahead

These include:
Identify connections between state and central work undertaken by PSSC; and opportunities to put learnings on cooperative federalism into practice in Punjab and Odisha.

State-level activities can be better aligned with other programmes and diplomatic engagements in the target states. The PSSC team will work closer with the World Bank and with the DHCs in the upcoming year to ensure this.

Output Title	Capability building mechanisms to influence key reforms in select states and sectors
Output number:		2	Output Score:	B
Impact weighting (%):		40	Weighting revised since last AR?	N

Indicator(s)	Milestone for this review	Progress
Demand led evaluation of government pilot intervention.	0	The evaluation of Direct Benefit Transfer of Electricity (DBTE) subsidies in the State of Punjab was completed for the review period 20-21. / The indicator will be dropped from the log frame for future reporting.
Number of knowledge products/exchange programmes facilitated to inform policies - knowledge products, visits, policies informed.	3	In progress. / Over ten articles published by CPR/CEIP / Knowledge exchange on regulatory mechanisms of India/
Number of capacity development training availed by national and state government (particularly low-income states) on governance, decentralisation, participation, responsiveness, transparency, and accountability.	5	Achieved. / 5 Know Your Regulator events with chairpersons of statutory regulatory authorities, including 1 state-level regulator and 4 national regulators. / Workshops conducted by the Bank and IMF in the states and at the center. (Ref output 1).

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

The output is scored B even as many of the indicators are met because it is not clear how the the training or the knowledge products were used.

Government of India’s Mission Karmayogi aims to build state capabilities and future ready civil servants. It focuses on i) scale-up of training and capacity building with an emphasis on e-learning; (ii) a new Capacity building Commission (CBC) to catalyse, support and monitor various capacity building initiatives; and (iii) strengthen central and state training institutes. During the year 2021 the WB and FCDO teams held several joint discussions with DOPT and Capacity Building Commission in support of Mission Karmayogi.

World Bank is supporting the CBC to a) assess ability and adequacy of central training institutes; b) develop e-learning Module on public finance management and procurement reforms; and c) building capacities for National Infrastructure Pipeline - infrastructure financing strategy and training of central and state government infrastructure ministries /departments. This aligns with FCDO’s ongoing support to DEA on Infrastructure. A new World Bank lending project for DOPT and CBC (US$ 50 million) to implement Mission Karamyogi is under final stage of preparation.

FCDO set up calls between CBC staff on the following topics: Online learning platforms and the UK People Survey with the UK Cabinet Office; results-based management frameworks with IMF SARTACC; and infrastructure project management training with the UK Infrastructure Projects Authority.

We are also scoping a new strand of work with Lal Bahadur Shastri National Academy of Administration (LBSNAA) on i) pedagogy and held an introductory call with the University of Oxford; and ii) integrating gender in the training curriculum and field work.

The Carnegie Endowment for International Peace (CEIP) and Centre for Policy Research (PCR) delivered a few research projects during this period:
- Strengthening regulatory design and design capacity on agriculture and labour markets. Over the last year, CPR launched the Know Your Regulator Series. Regulatory capacity is necessary to ensure that a market economy brings shared prosperity for everyone. Each Know Your Regulator session focuses on a particular regulatory body. Run in collaboration with the Forum of Indian Regulators (FOIR).
- Understanding the design of India’s apex institutions to inform the institutional reform processes within India’s cooperative federal framework. CEIP and CPR will deliver a series of research products over the next year to assess key institutions that mediate centre-state relations on economic and development policy issues.
- CEIP published a series of data driven articles on gender, social change and urbanisation in North India. CEIP also conducted a phone-survey in Patna (Bihar) and Dhanbad (Jharkhand) to examine the labour market challenges due to covid.
- CPR began developing a focus area on regulation of the internet. It undertook research on the regulation of algorithms and followed it up with policy-focused engagements and op-eds. This area will be further developed in the coming year.

Aside from the these, CEIP and CPR also provided real-time political economy analysis on relevant issues of politics and public policy, including on rule of law, institutions, and democracy. CEIP also worked with FCDO colleagues on understanding potential administrative reforms for the India’s judiciary.

Over the last year, FCDO scoped a new workstream under rule of Law for a potential partnership between the UK’s Ministry of Justice and Her Majesty’s Courts and Tribunal Services and Indian counterparts. The project will target judicial administration reforms. A scoping visit from the UK’s Ministry of Justice is expected in 2022.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

The partnership with CEIP and CPR delivered more than the planned activities and the upcoming workstreams are on track. The focus during the upcoming year should be on socialising results and ensuring they translate into government reforms, thereby increasing the effectiveness of the interventions. The State Capacity Initiative within CPR draws on analysis and interventions under PSSC to inform its larger, longer-term programme.

Efforts on civil service modernisation and rule of law have strong economic value, as they require limited financial investment. This has allowed scoping activities to continue despite delivering limited results.
Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

There have been no changes to the output this year. we anticipate changes next year, as the programme is aligned to the country business plan and the overall Open Societies approach in India.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]
Progress on recommendations from the previous AR
In response to the recommendations made last year the programme has worked on developing a UK India partnership on civil service modernisation. We developed working relationships with officials at the Capacity Building Commission and LBSNAA and supported complimentary efforts by the World Bank. We put officials in contact with UK counterparts but haven’t yet agreed on joint activities. We also focused research activities on federalism, apex institutions and regulators.
Lessons learned this year
Government reforms such as Mission Karmayogi, are ambitious agendas which take time to start. The CBC was only established in April 2021 and is focused on defining its own role and mandate. This is part of the reason for a delay in identifying tangible partnership activities.

Regulatory authorities are critical to delivery of public services, and for open, fair, inclusive markets. But they often work in silos, are distant from the citizens and caught up in their long-winded processes. Evidence and training support to regulators is thus important to help them become more responsive; and aligned to the needs of a more digital economy.

Flexibility in framework agreements have enabled the programme’s partnerships to respond to emerging policy and regulatory priorities. Future partnerships should continue to focus on building flexibility into design of bespoke capacity building, technical assistance and evidence building interventions and partnership arrangements.

Primary research and analysis provided a lot of new insights such as on measurement of labour force; or lack of mobility as the biggest factor for low workforce participation of women; but these findings did not perhaps reach the right stakeholders (for e.g., the urban planners in this case).
Recommendations for the year ahead

Translate research into action. Use the findings of the CEIP and CPR workstreams to identify activities to address gaps and support Government of India reform at state and central level. This will begin with a series of interactions, workshops, and roundtables with the right stakeholders to socialise the findings.

Building on the KYR series to develop an analytical framing for regulatory governance in India and focus on two to three sectors/regulators for more intensive work including at the state level.

In line with the work on cooperative federalism, strengthen partnerships with state institutions. Support knowledge dissemination and sharing across states.

Many of the research and analysis, for example the new planned work on internet governance has a bearing on India’s global position. More coordinated efforts to link teams working on domestic and foreign policy.
D: RISK [½ to 1 page]

Overview of risk management [1/2 page]

Currently, the overall risk rating for the programme is moderate. The current, active risks are included below. The key new risk emerging this year has been COVID-19 and its potential impact on FCDO and partners’ ability to deliver. The risks for the programme will be regularly revaluated in light of a number of dynamic changes, including the new priorities set by the creation of the FCDO.

Risk Description	Risk Category	Mitigation Strategy	Residual Risk
There is a risk that the programme supports small scale/ad-hoc initiatives that are not subsequently scaled up	Policy & Programme Delivery	The programme has been carefully screening activities funded through it and is only supporting ones that are crucial to GoI and UK's priorities and are strategic.	Moderate
Delay in programme implementation due to Covid19	Policy & Programme Delivery	In discussion with the partners extend the dates of deliverable. Try to do work on-line by working from home. postpone trainings and workshops.	Moderate
There is a risk that in the partnership with the multilaterals FCDO is not engaged as an equal partner, adversely impacting the goals for outcome and impact	Policy & Programme Delivery	FCDO has set up a clear governance structure for engagement with the World Bank. Working collaboratively across the spread of the partnership is non-negotiable	Minor
Programme interventions do not lead to envisaged impact	Policy & Programme Delivery	By carefully screening sub-projects and through the governance arrangements, FCDO will systematically follow up with government counterparts and implementing partners on progress and uptake of interventions and recommendations. The FCDO team will prioritise and consolidate activities and interventions to build on priority areas identified between the UK and India on governance, open societies, and open economies	Minor

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency. [max 1 page]

Performance of Partners: We worked with the following partners:
Carnegie Endowment for International Peace (CEIP) and Centre for Policy Research (CPR): We have monthly meetings with the team and have worked closely on finalising the work plan for the year. Both the partners have embedded PSSC in their wider institutional mandate and research/practitioner’s network. The overall grant agreement is for 3 years, with the proposed value of £490,210. Budget is approved every year against the annual work plan.

World Bank: Given the impact of covid, the partnership was extended till February 2023 to complete the planned activities. The team has quarterly catch ups with the World Bank and with DHCs and colleagues from other teams. However, we haven’t been able to organise visits or cross learning events.

IMF SARTTAC: SARTTAC switched to virtual training and delivered almost 90% of its workplan. Partnership will end in March 2022. IMF showcased its work on fiscal systems in Odisha at national level training programmes and some states are keen to learn more. FCDO is represented on the overall steering committee for SARTTAC that has senior government officers typically from the Ministry of Finance of member countries and bilateral/multilateral partners.

Financial performance

Overall, the programme is delivering against its financial targets. The total value of the programme is £4,995,000. We are awaiting the spending review settlement, but this is likely to be reduced and will be around £3.2 m.

The total spend under the project so far is £2,773,573.72 (as of 08 February 2022). The budget for the financial year 2021/22 is £284,213 and is on track to be spent by the end of the year (March 2022). The table below gives a snapshot of all the partnerships so far.

Partner	Details	Allocation	Status
World Bank	Diagnostic assessment of state capabilities in 2 states. Punjab and Odisha	£1.526m	Total commitment disbursed to partner. will end in Feb 23.
	World Bank Trust Fund	£100,000	Total commitment disbursed to partner
	Assessment of institutional readiness, impact evaluation of innovative pilots for future scale up – in Energy Sector (Client governments: Punjab, West Bengal, National Ministry)	£450,000	Closed
CEIP and CPR	Implementation of an evidence-based policy approach to improve Indian states’ regulatory design and capacity to make markets work better and strengthen India’s apex institutions.	£230,534 & £259,676	Active / Accountable Grant valid till March 2023
IMF SARTTAC	Strengthening PFM capabilities of Indian States. Provide key public financial, tax and revenue management trainings to government officials in key states as well as offer peer-to-peer learning. / We reduced the commitment by £20,000.	£480,000	Total commitment disbursed to partner, end in March 2022
LBSNAA	Training to batches of entry level and senior officials on issues of governance, gender & inclusion.	£25,000	Closed
GPI	Pilot exchange facility – explored but decided not to move forward with this in 21/22	£7,870	Closed

The FCDO programme team works closely with partners to monitor financial expenditure and ensure disbursements are made according to the terms and conditions of the AG/contract/MoU signed. This includes approval of annual budgets and work plans; monthly updates; review of progress throughout the year through quarterly progress reports, financial statements, and forecasts; and convening of regular Steering Committee/coordination meetings.

Monitoring of activities

This year, due to ongoing restrictions because of the pandemic, FCDO’s travel to states was limited.

FCDO has regular review meetings with the partners against agreed log frame and work plans. through the log frame and work plans developed by each partner. Partners in turn, have their internal own monitoring mechanisms. Formal reporting by partners is mandatory through financial and progress reports in line with Accountable Grant/MoU requirements.

The FCDO team ensures adherence to all requirements, including risk, fraud, and safeguarding. Overall responsibility for the management of Accountable Grants/MoUs and other agreements sits with the SRO.
Date of last narrative financial report	January 2022	Date of last audited annual statement	CEIP: June 2021 / CPR: September 2021 / Managed centrally for multilateral organisations