## Annual Review Template

Title: Global Mine Action Programme 3 (GMAP3)
Programme Value £ (full life): £48.63M		Review date: June 2023
Programme Code: AMP ID 301095	AMP start date: / April 2022	AMP end date: / 31 May 2025 (with option for 12-month extension)

Summary of Programme Performance
Year	2022
Overall Output Score	A+
Risk Rating	Major

DevTracker Link to Business Case:	Not yet uploaded
DevTracker Link to results framework:	Not yet uploaded

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme [1-2 paragraphs]

The Global Mine Action Programme (GMAP) 3 aims to provide life-saving mine action activities in some of the most heavily contaminated countries in the world. This includes clearance of landmines and other explosive remnants of war (ERW), educating local communities on how to stay safe, and building the capacity of national authorities and/or national implementers. The programme expects to save lives and prevent injuries, allow refugees and internally displaced persons to return home safely, enhance access for humanitarian aid, and allow land to be put to productive use, promoting livelihoods and trade.

GMAP3 follows the successful implementation of GMAP 1 (from 2014-2017) and GMAP2 (2017-2022). GMAP3 started in April 2022, and is being rolled out in phases. Three contracts and two grants were active in FY22 (1 April 2022 – 31 March 23), as follows:

Component	Title	Implementation date	Lead delivery partner
301095-103	GMAP3 Enabling contract in Angola, Cambodia, Somalia and Zimbabwe (known as Lot 1)	April 2022	HALO
301095-104	GMAP3 Enabling contract in Laos, Myanmar and South Sudan (known as Lot 2)	April 2022	MAG
301095-111	GMAP3 Ukraine Mine Action Immediate Response Programme – Grant	May 2022	HALO
301095-105	Monitoring and Evaluation of GMAP3 Enabling contracts (contract)	April 2022	Itad
301095-112	Design of a Mine Action and Agricultural Development Impact Bond – Grant	November 2022	Social Finance Ltd.

Table 1: Components of GMAP3 in FY22

The business case stated that the expected impact of GMAP3 is increased human security, and support towards peace and development for people in countries affected by landmines and ERW. The specific impact statements outlined in the theory of change are:
- States’ strategic objectives supported, and relevant treaty obligations met
- Increased community resilience to conflict drivers, contributes to stability and peacebuilding
- Economic development and more resilient communities, contributes to Sustainable Development Goals
- Safer communities and reduced deaths and injuries from mines/ERW
The specific outcomes outlined in the GMAP3 theory of change business case were:
[note] These are the outcome statements in the theory of change that was presented in the GMAP3 business case. The wording of these statements, was amended for the FY22 reporting, and has updated slightly once again since the piloting of the sector-wide TOC and launch of the final version in November 2022.
- Measurable progress towards APMBC and CCM treaty obligations
- Mine Action better managed, regulated and coordinated with increased local implementation
- Mine action integrated with humanitarian and development plans mobilising complementary resources
- Safe and productive land use improves livelihoods and basic services
- Risk of harm reduced through safer behaviour and clearance.
The reduction in ODA has resulted in changes to this programme, which is being adapted. This Annual Review reflects that the programme has had to refocus resources and so will deliver against a new plan with new results targets. As a result, the findings of this Annual Review reflect on a programme in transition. Reflecting the budget uncertainty throughout FY22, GMAP3 is being rolled out incrementally, rather than as one simultaneous, multi-year, multi-country programme as originally envisaged.

Following the successful completion of GMAP2 in March 2022, a series of short-term enabling contracts and grants were issued in FY22. For the Lot 1 and Lot 2 contracts, the existing GMAP2 suppliers were invited to submit proposals for a nine-month contract (April to December 2022), and this was subsequently extended to 31 March 2023. New six month contracts were signed in April 2023 to enable the implementers to continue to operate in the Lot 1 and Lot 2 countries, not covered in this Annual Review. The mine action work in Ukraine was undertaken through a grant, contracted from May 2022 to March 2023 (subsequently extended to June 2023 – extension not covered in this Annual Review). This Annual Review focuses on all FCDO’s mine action work in FY22 (from 1 April 2022 to 31 March 2023), including the above three mine action interventions, the monitoring and evaluation contract, and a grant for the design of a Development Impact Bond. During FY22, a tender process was also undertaken for GMAP3 in Afghanistan, with contract signature in April 2023 (and therefore not covered by this Annual Review). It is envisaged that during FY23, FCDO will issue invitations to tender for further mine action contracts for FY23 and FY24, replacing the current mine action contracts/agreements that are due to complete in FY23.

Summary supporting narrative for the overall score in this review [1-2 paragraphs]

The programme scores A+ as all the programme’s intended targets in FY22 were exceeded. The land released for safe and productive use through clearance and reduction was 17% above final target and 14% above the original target, with implementing partners releasing over a million more square metres of land than planned. In addition to land cleared and reduced, a further 1,901,134 square metres of land was cancelled from the hazardous areas in the national mine action information systems, from non-technical survey conducted by GMAP3 in FY22. 39% more explosive ordnance risk education (EORE) sessions were given than planned, and 42% more women, men, girls and boys were made aware of the risk of explosive ordnance through these EORE sessions. EORE targets were exceeded to a greater degree in Myanmar and Ukraine, both of which are active conflicts where the EO contamination is relatively new and in certain areas increasing and where EORE will have a greater impact on savings lives and limbs. Women and girls benefitted equally from EORE and land release as men and boys.
[note] The number of EORE sessions achieved exceeded the original target from the proposals by 57%
[note] The original target for EORE beneficiaries in the proposals was exceeded by 66%

The programme increased its focus on reporting on outcomes and impact in FY22, with the promotion of the sector-wide theory of change across the sector and the design of a development impact bond. The GMAP3 implementers started to align their data collection with outcomes in the GMAP3 (and sector-wide) theory of change. Data collection and reporting was not fully aligned in FY22, so, for example, it is not yet possible to see to what extent GMAP facilitated return of IDPs and refugees or improved livelihoods but the implementers have put processes in place during FY22 to report this in FY23. The outcomes for which data was collected and reported exceeded the targets, as can be seen in Section B.

The reduction in ODA funding resulted in limited capacity development work being conducted in FY22, as implementers focused more on clearance activities, aiming to retain as many trained clearance teams as funding permitted. Capacity development was limited to very specific activities with the NMAAs in Angola and Somalia, and training for the State Emergency Services in Ukraine. There was no capacity development of other local implementing partners besides MAG training their downstream EORE partners in Myanmar.
Implementers continue to focus on employing people and particularly women from EO impacted communities and in FY22 more female deminers were recruited and trained to try to achieve gender equity. For example, HALO’s percentage of female deminers is 53% in Cambodia, 51% in Laos and 23% in Somalia, where such a percentage of females is really challenging gender norms. MAG’s percentage of female deminers is 36% in Laos, including a female in the most senior operational role, and 39% in Cambodia. The Partnership’s proactive approach to developing an inclusive workforce in such a labour intensive and traditionally male-dominated sector is actively contributing to the UK’s commitment to promoting gender equality through its ODA investments. Significant progress has been made in FY22 on collecting data on the percentage of beneficiaries with disabilities, but this has not yet been reported programme wide and there remain challenges on obtaining realistic percentages and adapting programming to improve disability inclusion.

Major lessons and recommendations for the year ahead [1/2 page]

- GMAP has cross party parliamentary support and is well aligned to UK priorities. It provides an excellent platform for the UK to increase its profile in GMAP countries, facilitating access and dialogue with national governments at the highest levels, benefitting UK strategic interests far beyond mine action. Recommendation 1: GMAP should develop a set of access and influence objectives against which it can capture and report on additional strategic benefits in a systematic way.
- GMAP’s work with Dutch support to pilot the sector-wide theory of change has been well received by implementers and certain donors, but little work has been done to date with the national mine action authorities, beyond the Angola and Lebanon pilots. Recommendation 2: GMAP should work more closely with national mine action authorities to embed the theory of change as part of national systems to collectively achieve the intended outcomes and impact of mine action, as defined by the GMAP host countries, FCDO and other donors.
- The GMAP team managed the uncertainty of funding for mine action well by rolling out GMAP3 incrementally in FY22 as it was not possible to proceed with multi-year contracts. This prevented the abrupt closure of the programme while funding levels for mine action were approved but limited FCDO’s ability to communicate their long-term commitment to mine action. Recommendation 3: The GMAP team should continue close collaboration with implementers but more regularly communicate plans for GMAP3 with Post and national authorities so that they are aware of contract roll-out and the UK’s continued commitment to supporting mine action in GMAP3 countries. This will help maintain FCDO’s position of influence both with national governments in the GMAP3 countries and more broadly in the mine action sector.
- In FY22, GMAP3 funds the employment of over 200 women in mine action, which is a traditionally male-dominated sector. Implementers have made significant progress on challenging gender norms across the range of GMAP countries in line with FCDO’s new strategy on women and girls but reporting on meaningful engagement and the inclusion of women and girls, as well as people with disabilities and other marginalised groups beyond employment is not systematically reported or monitored. Recommendation 4: The GMAP team should proactively communicate to HMG the added value of GMAP3 in terms of gender equality and women’s empowerment and such communication should be assisted by the development of better indicators for measuring meaningful and inclusive community engagement.
- In FY22, FCDO’s drive to be disability inclusive led to GMAP implementers making progress on collecting disability data and measuring the percentage of beneficiaries with disabilities, but there is no system for recording inclusion and engagement beyond people with disabilities and programming is not yet being adapted in response to the disability data collected. Disability collection was introduced during FY22, and formalised during the subsequent enabling contract extensions. Recommendation 5: The GMAP team should work with implementers to see how their mine action programming can be adapted to ensure mine action activities are more inclusive of people with disabilities, as well as people from other marginalised groups.
- In FY22, GMAP shifted emphasis towards outcome level reporting: a household survey was developed and piloted and a development impact bond (DIB) for mine action was designed but there were no external monitoring and evaluation visits to the programme. Recommendation 6: The MEL provider should conduct in-country visits to review implementers’ performance and systems for evidencing outcome and impact level change and roll out the newly developed household survey; and ensure that any learning is programme-wide and linked with lessons emerging from the DIB.
- The GMAP team visited Angola and Zimbabwe, addressing a wide range of issues, including VfM but VfM has not been systematically addressed as part of monitoring by the MEL provider and there were no external evaluation activities in FY22. Recommendation 7: VfM should be more systematically addressed as part of monitoring in future contracts, with a set of simple VfM indicators developed which can be embedded in the implementer’s logframe and collectively reviewed as part of evaluation and learning processes.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

Following the development of a mine action sector-wide theory of change by the MEL provider under GMAP2, in FY22 the Dutch government funded a pilot project to operationalise it in five countries. The sector-wide TOC was refined as a result of the pilots and a broad outreach within the sector and a final version was launched officially at the Meeting of the States Parties to the anti-personnel mine ban convention in Geneva in November 2022. The sector-wide TOC is being adopted by FCDO for GMAP3, by the Dutch government for its future mine action and cluster munitions programme and by a range of other actors including UNDP and several INGOs. Itad are liaising with the UN Inter-agency Coordination Group for Mine Action on how to incorporate the sector-wide TOC into the next UN mine action strategy (from 2024) and it is on the agenda of the International Mine Action Standards (IMAS) Review Board to be incorporated into the revised edition of IMAS 14.10 on the Evaluation of Mine Action Programmes.

As the sector-wide TOC was adapted during FY22, there are some differences between the TOC outcome and impact statements in the GMAP3 business case and the reporting in FY22. Reporting in FY23 will be fully aligned to the sector-wide TOC, not only enabling the aggregation of outcome level data at a programme level but also at country level for sharing with national authorities and other donors to enhance the collective responsibility of mine action outcomes.

The outcomes and indicators used for GMAP in FY22 as compared to those in the GMAP3 business case are shown in Table 2 below. The footnotes show the post-piloting revisions to the sector-wide theory of change, to which reporting in FY23 and 24 will align.

GMAP3 Business case outcome statement and indicators to be monitored	GMAP3 outcome statement and indicators in the GMAP3 logframes & narrative in FY22
Outcome 1: Mine action integrated with humanitarian and development plans mobilising complementary resources / Indicator / Documented evidence on how the mine action aligns with humanitarian and development plans.	Outcome 1: Mine Action is integrated or sequenced with humanitarian development, peace and/ or stabilisation initiatives / Degree of integration with local and regional development plans or with other agencies at programme level. / Degree of integration or sequencing with other humanitarian, development, peace or stabilisation initiatives at task/community level. (reported in narrative report)
Outcome 2: Productive land use improves livelihoods and basic services / Indicators / Area of formerly contaminated land either a) in use, or b) with firm plans in place for use following land release activities for i) residential purposes. Ii) agricultural/pastoral purposes, iii) community development/public services, iv) natural resources, v) infrastructure, vi) roads, bridges, paths and other access routes / Number of direct beneficiaries from land cleared and reduced (SADD) and percentage - with disabilities.	Outcomes 3 & 4: Safe and productive land use improves livelihoods and basic services, improving quality of life. / Area of formerly contaminated land either a) in use, or b) with firm plans in place for use following land release activities for i) residential purposes. Ii) agricultural/pastoral purposes, iii) community development/public services, iv) natural resources, v) infrastructure, vi) roads, bridges, paths and other access routes / Number of direct beneficiaries from land cleared and reduced (SADD) and percentage - with disabilities. / Number of indirect beneficiaries from land cleared and reduced (SADD) and percentage - with disabilities. / (reported in logframe)
[note] This was the outcome statement at the end of GMAP2 and therefore used for FY22. The final sector-wide theory of change outcome statement (which will be in use from FY23) is “Safe and productive land use improves livelihoods and basic services, improving quality of life and the environment.”

Outcome 3: Risk of harm reduced through safer behaviour and clearance / Indicators / % of risk education (RE) beneficiaries surveyed who demonstrate increased knowledge of RE safety messages / % of impacted communities surveyed who report people behaving in a safer manner	Outcome 5: Risk of harm reduced increases safety and normalisation / Area of land cleared and reduced (m2) / % of EORE beneficiaries surveyed who retain EORE knowledge 6 months after EORE session / % of EORE beneficiaries surveyed who report they are behaving more safely 6 months after an EORE session. / Percentage of people surveyed who report increased security and safety as a result of Mine Action activities, SADD / (reported in logframe)
Outcome 4: Mine action better managed, regulated and coordinated increasing transition of sector to national ownership. / Indicators / National authorities are managing and setting the direction of their mine action strategies more effectively / Local mine action organisations have the management capabilities to plan, implement and quality manage their work	Outcome 6: National mine action authorities have the skills & knowledge to regulate, coordinate and manage mine action more effectively with minimal outside technical support / Extent of QM plans, systems, procedures & practices / Extent of information management systems, and extent & accuracy of da / Extent of planning & prioritisation systems, procedures & practices / Extent of strategic planning systems, procedures & practices / Extent of gender equity & mainstreaming / Extent of management skills & knowledge / (reported in the narrative report)
	Outcome 7: Marginalised and/or vulnerable groups are empowered through increased equitable employment opportunities / (reported in the narrative report)
[note] This was the outcome statement at the end of GMAP2 and therefore used for FY22. The final sector-wide theory of change outcome statement (which will be in use from FY23) is “Risk of harm reduced which increases returns and freedom of movement.”
[note] Immediate Outcome 4 indicators will be assessed using the capacity development assessment framework developed under the current programme. This enables a detailed, quantified understanding of capacity development progress.
[note] This was the outcome statement at the end of GMAP2 and therefore used for FY22. The final sector-wide theory of change outcome statement (which will be in use from FY23) is “Responsive and equitable nationally owned mine action through improved governance and with increased local implementation.”
[note] This is a legacy outcome statement at the end of GMAP2 which was used for FY22 but is not included in the final sector-wide theory of change (and therefore no longer in use from FY23).

Table 2 Comparison of outcome statements and indicators between GMAP3 Business case and GMAP3 contracts and grants in FY22.

The sector-wide theory of change developed in GMAP2 was piloted with Dutch funding in Afghanistan, Angola, Lebanon, Libya and Ukraine during FY22 and subject to further consultation with a broad selection of mine action stakeholders. It was finalised and launched by the GMAP team and the Dutch mine action and cluster munitions programme in November 2022 and has formed the basis for all the GMAP3 contracts, though the outcome statements evolved between FY22 and FY23. The evidence from the piloting and the GMAP3 enabling contracts suggests that the new TOC logic is still valid.

In line with the ‘Leave no one behind’ agenda, all GMAP data is disaggregated by age and sex, implementers are proactively employing women and programming is adapted to meet the different needs of women, men, boys and girls but men, who are usually most at risk, remain the most challenging to reach with risk education. There has been a lot of focus on gathering disability disaggregated data during FY22, and implementers have made significant progress in this area. In contexts where it has been historically or culturally challenging to collect disability data (e.g. in Angola, Somalia and Zimbabwe), the implementers have consulted with disability specialists in those countries and are now rolling out use of the Washington Group Short Set questions to identify their land release and EORE beneficiaries who identify as having a disability. All data is recorded in the implementer’s information management systems, which is GIS based, therefore all programme activities are disaggregated by geography.

While data disaggregation of the programme’s beneficiary data is good (for age and sex) and improving (for disability), implementers and the MEL provider could do more to monitor and evaluate the extent of meaningful involvement of women and girls, people with disabilities and people from marginalised groups within the affected communities. This could be done by developing indicators for monitoring how programme activities are sensitive to equality and inclusion as well as for how the programme is directly addressing inequality and improving participation.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

During FY22, the implementers continued to report outcome level data on a six-monthly basis, based on data collection through their pre and post clearance assessments, household surveys and pre- and post EORE surveys. During the year, the implementers also looked at how they can report on more outcomes in the sector-wide theory of change, such as whether mine action has led to improved livelihoods, access to services, and facilitated return. These outcomes were not yet reported in FY22 but will be reported in the second GMAP3 enabling contracts in FY23. Following analysis of GMAP implementers’ existing pre-clearance and post clearance data collection tools, the MEL provider developed a standard household survey questionnaire which is linked to the sector-wide theory of change and piloted it with NPA (a mine action INGO but not a GMAP implementer) in Angola and Zimbabwe. The survey is designed to be used by implementing organisations as a standard tool to gather a wider range of outcome level data at household level of on livelihoods and community resilience and is based on the resilience framework.

The GMAP Programme Manager visited the programme in Angola and Zimbabwe and met with national mine action authorities and people from the communities in GMAP areas of operation. This visit provided an opportunity to see the positive impact that GMAP has bought to the communities affected by mines and ERW. Although there were no external monitoring and evaluation visits in FY22, to verify outcome data, the implementing partners continue to regularly engage with beneficiary communities to understand the number of people using or planning to use the land cleared and what the land will be used for. The Quarterly monitoring of the Lot 1 and 2 GMAP3 enabling contracts shows that the outcomes currently being measured by the implementing partners are being achieved, so the expected impact of the programme should also be on track to be achieved, as the assumptions in the theory of change remain valid. In terms of each specific outcome progress across all countries is as follows:
Measurable progress towards APMBC and CCM treaty obligations
This outcome is not reported in the logframe. It is instead measured by a set of outputs on land released and number of EORE beneficiaries, which are the treaty obligations for all the GMAP countries except Myanmar, which is the only country which is not a States Parties to the APMBC or CCM. The programme achieved this outcome as it exceeded targets for land release and EORE (as noted in section C).
Responsive and equitable nationally owned mine action through improved governance and with increased local implementation
Though the capacity development activities were limited, the planned improvement of capacity in specific parts of the programme were achieved. There was improvement reported for the quality management and information management capacity of SEMA, the national authority in Somalia and for the quality management capacity of ANAM, the national authority in Angola. In addition, the provision of IMAS EOD Level 3 training for six SES staff in Ukraine, including two instructors, should lead to increased national capacity and local implementation of EOD in Ukraine.
Mine action complemented with humanitarian / development / peacebuilding or stabilisation initiatives.
Mine action has complemented humanitarian initiatives in Myanmar, South Sudan and Ukraine, clearing mines and/or providing EORE to IDPs and returnees impacted by the ongoing conflict. It has supported environmental conservation activities in Angola and Somalia (Somaliland) and linked to provincial and national development plans in Angola, Cambodia and Laos. Other than these initiatives there have not been many formal plans or agreements in place for humanitarian, development or peacebuilding/stabilisation initiatives to complement mine action as envisaged in the theory of change and there is room for improvement for this outcome. Implementers do however report organic, unplanned humanitarian and development activities following clearance as the land is made safe and accessible for complementary activities; and the MEL provider and implementers and the GMAP team have been working to agree how to capture this fairly and systematically for GMAP3 going forward.
Safe and productive land use improves livelihoods and basic services, improving quality of life
During FY22, implementing partners and the MEL provider worked together to select additional outcome level data to report in FY23; this includes reporting improved livelihoods and access to basic services because of mine action. For the outcomes that the implementers have reported in FY22, we can see the predominant use (71%) of the land cleared and reduced is for agriculture and pasture, 13% was for natural resources (including forestry, foraging for food, gathering water or natural materials, fishing or extensively grazing animals), 9% for access (including paths, roads, bridges, routes), 5% for residential use and the remainder for community development and infrastructure.
Risk of harm reduced increases returns and freedom of movement.
The risk of harm from EO was reduced for the 45,990 ‘direct beneficiaries’ of the land cleared and reduced, who are the people who use the actual land cleared and their families. This is 2.8 times more or 29,070 more than planned. There were also 104,313 ‘indirect’ beneficiaries, which is the people other than direct beneficiaries who live in the communities where the land was released. This is 35,751 (52%) more than planned.

During FY22, implementing partners and the MEL provider worked together to select additional outcome level data to report in FY23, which includes the number of returnees or whether mine action facilitated return home in countries where this is relevant.

In addition, from the sample of EORE beneficiaries surveyed six months after an EORE session funded by FCDO, an average of 89% retained their knowledge and 74% reported behaving more safely.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

There is sufficient evidence that GMAP3 is continuing to exceed targets for outputs and outcomes, including the number of people benefitting from the programme. The GMAP Programme manager’s monitoring visit to Angola and Zimbabwe demonstrated the positive impact of the programme on mine and ERW affected communities, and the value GMAP brings to both the governments of Angola and Zimbabwe and HMG. The evaluations of GMAP1 and 2 concluded that GMAP offers VfM to HMG. The GMAP1 summative evaluation recorded that “overall, GMAP has demonstrated good value for money. Nevertheless, further economy and efficiency gains can be found.” The GMAP2 summative evaluation recorded that “GMAP, as a Centrally Managed Programme managed by a small team, has made significant contributions to the mine action sector as a whole – including, among other things, by improving the way the sector values and uses evidence for decision making, promoting innovative finance, improving donor coherence and encouraging standardised monitoring, evaluation and learning (MEL) systems – and demonstrates good VfM.” This continues to be the case with GMAP3 and embassy representatives (Post) state that it aligns well with HMG’s broader strategic priorities across the GMAP countries. There is therefore no requirement for restructure of the programme, but the benefits to HMG’s access and influence in GMAP3 countries will be amplified when the multi-year contracts are rolled out in FY23 as planned.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Land has been cleared, reduced & cancelled in accordance with IMAS/NMAS
Output number:		1	Output Score:	A+
Impact weighting (%):		80%	Weighting revised since last AR?	n/a

Output 1 Indicator(s)	Milestone(s) for this review	Progress	Variance
Area of land cleared (m2)	5,479,396 m2	6,168,403 m2	+13%
Area of land reduced (m2)	310,440 m2	573,506 m2	+84%
Area of land cancelled (m2)	(no targets set)	1,901,934	n/a
Number of EOD spot tasks conducted	(no targets set)	2,035	n/a
Items of EO destroyed	(no targets set)	13,041	n/a
[note] Note that the original target for land cleared across GMAP3 is 5,590,155 sqm (the results are 10% above this target)

Country project	Land cleared (sqm)		Land reduced (sqm)
	Target	Results	Target	Results
Angola	535,000	808,908	30,600	162,726
Cambodia	1,092,150	1,285,283	0	101,158
Laos	2,807,200	2,887,905	n/a
Myanmar	n/a
Somalia	510,826	521,657	0	3563
South Sudan	170,000	217,290	n/a
Ukraine	50,000	102,759	0	1,012
Zimbabwe	314,220	393,328	279,840	305,047
Totals	5,479,396	6,168,403	310,440	573,506
Table 3. Land cleared and reduced across the Lot 1 and Lot 2 countries and Ukraine (as at 31 March 2023).
[note] Note that the original target for land cleared in Cambodia (taken from the April to December proposal and the January to March extension proposals combined) is 1,108,400 sqm (the results are 16% above this target)
[note] Note that the original target for land cleared in Somalia (taken from the April to December proposal and the January to March extension proposals combined) is 600,585 sqm (the results are 13% below this target)
[note] Note that the original target for land cleared in Zimbabwe (taken from the April to December proposal and the January to March extension proposals combined) is 332,970 sqm (the results are 18% above this target)
[note] Note that the original target for land cleared across GMAP3 is 5,590,155 sqm (the results are 10% above this target)

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

The activities under this output include non-technical survey, technical survey, clearance and explosive ordnance disposal (EOD) spot tasks. The table above shows that the targets for land cleared and reduced have been exceeded. With the exception of Somalia, all the original targets have been exceeded, and in total GMAP3 has exceed the original clearance targets by 10%.
In total, in FY22, the Lot 1 and 2 Partnership (HALO and MAG) and HALO in Ukraine, have released 6,777,268 sqm of land for productive use through technical survey and clearance (17% above target) and conducted 2,035 EOD spot tasks, destroying 13,041 items of explosive ordnance. This includes cluster munitions, anti-personnel and anti-vehicle mines and unexploded and abandoned ordnance but not the large quantity of small arms ammunition smaller than 20mm, which is also found and destroyed. In addition to this 1,901,934 sqm of land was cancelled from area suspected to be hazardous, because of non-technical survey activities.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

The big change for this output since GMAP2 was the addition of Ukraine. Post invasion, the programme pivoted quickly to provide an emergency response focused initially on tackling the threat posed to human safety and agricultural capacity by contamination in newly liberated areas around Kyiv. The programme operationalised through a direct grant to HALO. HALO was one of the few international NGOs with the necessary accreditations and capacity to deliver (and scale up) demining, EORE and capacity building in Ukraine, and provided an unsolicited proposal that was a good fit with GMAP priorities. Operations in Ukraine faced specific challenges arising from the active conflict, including martial law restrictions on using explosives for EOD, risk of conscription of national deminers employed by HALO, import issues, and restrictions on where HALO could operate. HALO is developing a relationship with the Ukrainian National and Regional authorities and with a key national implementer, State Emergency Services (SESU), for which HALO provid EOD training to build their capacity. HALO, which had previously operated in the Donbass region, used donor funding (including GMAP funding) effectively to re-group in the West and build its capacity from around 300 deminers to over 650 deminers.

The impact of the exceptional drop in the value of the pound sterling during FY22, had a significant impact on GMAP and change requests were approved to reduce capacity and clearance targets for land cleared in Cambodia, Somalia (Somaliland) and Zimbabwe, though in Cambodia this reduction was later not required. For the extension in the final quarter of FY22, implementers’ proposals also reduced capacity and targets to some extent for this output. In total, the GMAP team approved a reduction of clearance targets by 63,000 sqm in Somalia (Somaliland over two change requests), and of 32,500 sqm in Zimbabwe during FY22. Actual results in Zimbabwe exceeded the original clearance targets by 18%, so there was no need for the downwards revision of targets. Somaliland was the only country in which the reduction in targets was required, as they had to cut the number of clearance teams, and they underachieved the original clearance target by 13%. The reason that the drop in the value of the pound against the USD affected Somalia worse than other programmes was partly due to the fact that staff salaries, which are the greatest cost diver, are paid in USD rather than local currency.

Output Title	Men, women, boys & girls are more aware of the risk of harm from mines & ERW
Output number:		2	Output Score:	A++
Impact weighting (%):		15%	Weighting revised since last AR?	n/a

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Explosive ordnance risk education (EORE) aims to raise awareness of the risk of mines and ERW and promote safer behaviour within impacted communities to reduce the risk of injury to women, men, boys and girls. In countries such as Myanmar, where it is not permitted to conduct technical survey, clearance or EOD activities, EORE is critical as it is the only way to reduce the risk of harm from explosive ordnance, which is increasingly prevalent there due to the escalation of conflict following the coup.
The beneficiaries of EORE counted here are those who have received face to face sessions in households, in community sessions, schools or IDP camps. In Myanmar it also includes those who have been trained remotely through telephone or video conferencing. People who have received EORE messaging through any kind of media (mass media, social media, posters etc.) or through training of trainers have not been included in these figures.
The expected targets have been exceeded, which is in part due to the relaxing of restrictions post COVID, when more frequent and larger sessions were permitted.

Country project	EORE sessions		EORE Beneficiaries
	Target	Results	Target	Results
Angola	146	170	2,920	3,608
Cambodia	5,253	5,861	37,449	54,843
Laos	120	120	3,000	3,611
Myanmar	8,379	13,174	75,550	80,341
Somalia	2,700	2,715	23,400	36,263
South Sudan	n/a
Ukraine	675	2,084	6,750	31,096
Zimbabwe	162	170	6,332	10,731
Totals	17,435	24,294	155,401	220,493
Table 4. EORE sessions delivered across the Lot 1 and Lot 2 countries and Ukraine (as at 31 March 2023).

The implementers have made efforts to ensure women and girls are not left behind and as a result women, men, boys and girls have benefitted equally from EORE in FY22, with all targets exceeded. Given that men and boys are statistically more at risk from EO, targets for men and boys could potentially be higher, though typically men are harder to reach, given their work and living patterns. They are also predominantly involved in the conflict in Ukraine and to some extent Myanmar, so there could be an argument for differentiated targets in conflict contexts, though there is a trade-off between the need to reach men with their unavailability. It is also acknowledged that women reach ore indirect beneficiaries.

Indicator(s)	Milestone(s) for this review	Progress	Variance
Number of EORE beneficiaries	33,857 Women / 28,400 Men / 41,583 Girls / 44,712 Boys / 155,302 Total	51,422 Women / 45,067 Men / 60,282 Girls / 63,722 Boys / 220,493 Total	52% / 59% / 45% / 43% / 42%

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

As with output 3, the big change from GMAP2 is the inclusion of Ukraine where EORE is providing immediate life-saving information to reduce the risk of harm from EO contamination. There were challenges at the beginning of the agreement, as HALO had to seek accreditation in the early months of operations to perform EORE in Ukraine. However, over time, HALO managed to attain the relevant certifications and greatly exceeded targets. Towards the end of the FY22/23, HALO began to roll out knowledge retention tests in Ukraine for the first time, a key part of robust EORE, which worked towards achieving the EORE outcomes set out in the Theory of Change, and a part of EORE which was included in other GMAP3 countries.

In FY22 for the Lot 1 and 2 GMAP3 Enabling contracts, a third indicator was introduced for this output, i.e., the percentage of EORE beneficiaries surveyed who increased their EORE knowledge immediately after an EORE session. This information was already collected as the baseline for the knowledge retention survey which is still conducted six months after an EORE session for outcome reporting. However, the immediate knowledge increase which is based on a test comparing scores before and after the session, was not previously recorded. This indicator was introduced in GMAP3 for the implementing partners to understand and demonstrate if adaptation of the messaging or delivery of EORE sessions is required. This was used in five countries and an average of 78% of EORE recipients surveyed had increased their EORE knowledge, ranging from 59% in Ukraine to 90% in Zimbabwe.

The Washington Group Short Set Questions were introduced into the Pre and post EORE questionnaires too, to record the number of beneficiaries with disabilities and adjust the delivery of the EORE session, should some respondents say they have difficulty with one of the areas of functionality (seeing, hearing, walking, etc.). In FY22 WGSS was not used in every programme and in FY23, implementers should ensure its use programme wide for both reporting and adaptation of EORE messaging and delivery.

Output Title	National mine action authorities have the skills & knowledge to regulate, coordinate and manage mine action more effectively with minimal outside technical support.
Output number:		3	Output Score:	A
Impact weighting (%):		5%	Weighting revised since last AR?	Revised downwards from 10% in GMAP2

Indicator(s)	Milestone(s) for this review	Progress
Number of personnel from NMAA trained or supported by CD activities (disaggregated by gender)	There were no targets set for this indicator. This was due to the fact that it was a new indicator and implementers had insufficient time to agree targets with the respective NMAAs for the original nine-month contract.	These outputs were not reported in the logframe and instead addressed in narrative reporting. In FY22 there were only planned capacity development activities in Angola, Somalia and Ukraine. 14 personnel from SEMA, the NMAA in Somalia (SEMA) and 6 personnel from SES in Ukraine were trained in FY22 and one procedure for defining ‘All Reasonable Effort’ (ARE) within land release was agreed and adopted with ANAM in Angola. The procedure adopted by ANAM was a ‘first’ and could be used in other countries to interpret the ARE concept enshrined in international mine action standards.
Number of plans, standards, policies, procedures etc developed.	As above

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Although the implementers met their intended targets for this output in FY22, the expectations for capacity development were reduced from previous GMAP contracts and not as ambitious as the GMAP3 business case due to the reduction in ODA. In FY22, HALO supported the Somali Explosives Management Authority (SEMA), which is the national mine action authority in Somalia, with salary incentives to keep them operational, while they still do not have salaries from the federal Government budget. SEMA was also supported with information management and quality management training to improve their ability to regulate and manage the mine action sector across Somalia (but excluding Somaliland). ANAM, the national mine action authority in Angola was supported to improving their quality management of demining and six personnel form the State Emergency Service (SES) in Ukraine received training in explosive ordnance disposal.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

Capacity development activities in FY22 were reduced from GMAP2 in the Lot 1 and 2 countries due to the reduction in ODA funding and the Lot 1 and 2 contract leads consequently prioritising demining and EORE over capacity development in their proposals. The impact weighting consequently reduced from 10% in GMAP2 to 5% of the overall programme. In Somalia, a planned deliverable for developing a donor relations policy was changed upon SEMA’s request to train SEMA staff in the new informational management system (IMSMA Core).

Output Title	Increased collaboration with humanitarian, peace, stabilisation & development actors.
Output number:		4	Output Score:	B
Impact weighting (%):		0%	Weighting revised since last AR?	n/a

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

This output has no weighting but is in the GMAP3 theory of change and implementers do report it in their narrative reporting. They are good at coordinating within the sector and have made some progress in increasing collaboration with other humanitarian, peace, stabilisation & development actors to maximise outcomes during FY22 as reported below but it has often proved hard to do this in practice and there is scope for improvement during the remainder of GMAP3.

Output 4 Indicator(s)	Milestone(s) for this review	Progress
Number of mine action coordination meetings attended / Number of agreements agreements/MOUs in place with humanitarian, peacebuilding and/or development actors to sequence activities.	There were no targets for this and it was not reported in the logframe.	The implementers are very good at coordinating within the mine action sector and have made some progress in FY22 collaborating with other actors outside the sector. There are some good examples of collaboration on environmental projects (Somalia and Angola) and linking MA with displacement and return (Myanmar and South Sudan) but there is scope for improvement in this area.

Output Title	Community participation in HMA planning & activities
Output number:		5	Output Score:	A++
Impact weighting (%):		0%	Weighting revised since last AR?	n/a

Output 5 Indicator(s)	Milestone(s) for this review	Progress
Number of community liaison visits	669	2,378

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

This output has no weighting but is in the GMAP3 theory of change and implementers do report it in their narrative reporting. Mine and ERW affected communities participate in HMA planning and activities in a number of ways. They are consulted by local authorities and feed into local and national prioritisation and tasking systems in countries, such as Cambodia and Laos where community participation is strongly advocated by the national governments. In other countries, it is mainly the liaison with the implementing partners that ensures their participation. Community liaison (CL) visits comprise of a number of activities carried out by the implementers’ community outreach teams, in addition to EORE.

During FY22 the implementers standardised what is considered as a CL visit. EOD spot tasks and EORE are reported separately for GMAP3E, and do not constitute a CL visit. Community liaison activities for MEL activities, e.g. to survey beneficiaries regarding EORE knowledge retention and safer behaviour are also conducted throughout the programme but do not constitute a CL visit. A CL visit includes the following activities:

- Community Stakeholder meetings, including: Entry meetings, as part of an operator’s visit to a new community, Key Informant Interviews and Focus Group Discussions (if they are not part of Non-technical survey or EORE impact assessment; and follow-on meetings, for example on a training exercise or a training of trainers
- Contamination Baseline Assessment
- Community liaison support to clearance
- Including Handover meetings
- Non-technical survey reports (including resurvey reports)
- Handover meetings post clearance
- Village by Village contamination surveys (HALO Somaliland)
- Community liaison support to EOD tasks.
There is scope to develop better indicators for meaningful community participation and engagement going forward in GMAP3.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

This is the first Annual Review of GMAP3, but as GMAP3 in FY22 is so similar to GMAP2, this AR refers to the seven recommendations from the GMAP2 Programme Completion Review, conducted in June 2022.
Recommendation 1: Future iterations of GMAP should maintain a consortium or partnership approach but look to find ways to bridge multi-lateral and INGO implementers to ensure programme cohesion.
GMAP3 in FY22 maintained the partnership approach with the same INGO implementers in the same countries as at end GMAP2 (minus Vietnam) and brought Ukraine into GMAP, via a direct grant to an existing INGO implementer, to respond to the new contamination resulting from the Russian invasion. GMAP3 did enter discussions with UN agencies in FY22 but did not have sufficient funding certainty to include them. There was no need, therefore, to bridge multi-lateral and INGO implementers to ensure programme cohesion. In FY22 the GMAP team tendered for an INGO to implement demining, risk education and capacity building in Afghanistan, rather than delivering through UNMAS as was done in GMAP2. The contract only starts in FY23, so there is not yet evidence to assess whether this was the right decision (e.g., with reference to value for money).
Recommendation 2: GMAP should keep funding globally, to continue the coherence, coordination and shared learning and maintain FCDO’s position of influence in the sector.
GMAP3 continues to be centrally funded through FCDO’s GMAP team, which in FY22 continued the coherence, coordination and shared learning within the programme and with the sector more broadly through the Wilton Park conference on innovative finance for mine action and the collaboration with the Dutch government on operationalising the sector-wide TOC. The fact that in FY22, the contracts issued under GMAP3 were short term rather than multi-year limited the communications potential for Post towards their national governments and for the GMAP team in terms of its position of influence in the sector. This should be resolved in FY23 once the multi-year contracts are awarded.
Recommendation 3: Close relations with FCDO and IPs is important for shared resolution of challenges, resilience, innovation, etc.
In FY22, the GMAP3E contracts continued close collaboration between FCDO, IPs and the MEL partner to ensure collective responsibility for continual programme improvement. The GMAP team used this collaboration to manage the contracting process in FY22 to ensure that minimum disruption was made to GMAP operations and avoid the need to lay off a large workforce. This was particularly important during FY22 with the uncertainty of GMAP funding, coupled with the impact of the GBP exchange rate and global inflation and without such collaboration the programme would not have been able to meet expectations.
Recommendation 4: Capacity development of national authorities and local implementing organisations needs to be prioritised and ring fenced under a future GMAP to create a sustainable, nationally owned capacity for dealing with residual risk.
This was not conducted in FY22, due to the reduction in ODA funding. Other than in Ukraine and Myanmar (EORE only), there was no capacity development of local implementers, and there was only limited capacity development of national authorities in Angola and Somalia.
Recommendation 5: GMAP should involve Post and national mine action authorities in the design [and delivery] of the programme to align objectives and facilitate sequenced or integrated support to maximise outcomes.
In all the GMAP countries, Posts were kept well-informed of GMAP activities and consider GMAP to be aligned with UK objectives. In some countries Post also attended relevant sector meetings. Outside of Ukraine and Afghanistan, there was less involvement from Post in the programme design and delivery, and there was no evidence of Post’s facilitation of sequenced or integrated support to maximise outcomes but in FY23 with more focus on outcome monitoring and reporting, there should be more opportunity for Post to be involved.
Recommendation 6: GMAP should keep the mix of mine action delivery, MEL and research and focus on evidence advocacy to build on progress made.
In FY22, GMAP has mainly focused on mine action delivery and monitoring that delivery, with no in-country monitoring or evaluation activities. The only research conducted was designing a development impact bond (DIB) as explained in recommendation 7 below. In terms of evidence advocacy, the UK co-hosted two side events with the Dutch in Geneva on the sector-wide theory of change to improve evidence in the sector. The balance of delivery vs innovation was weighted towards delivery in FY22 as funding was tight but going forward with a multi-year programme, there can be more in-country MEL, focused on outcome and impact level change, which can also link the work on the TOC and DIB, and more opportunity to fund new research.
Recommendation 7: GMAP should maintain a focus on outcomes to help diversify the narrative and tap into other funding steams and innovative finance.
GMAP3 has increased the focus on outcomes by starting to use the sector-wide theory of change and toolkit, which has potential to be part of a sector-wide MEL system. implementing partners and the MEL provider have worked together to select additional outcome level data to report in FY23; including data on livelihoods and access to basic services, which were previously only looked at in evaluations. IPs are now using standard indicators so data can be shared with the NMAA and compared both within countries and across the programme.
One advantage of a more outcome focused approach is that it compensates for limitations in output metrics. For example, not achieving land release targets where tasks assigned after proposal stage are for land that is heavily contaminated with scrap metal or includes difficult terrain. Although the land release (output) figure may be lower than anticipated, the outcome (e.g. land released for community access to schools and health centres) may be higher than anticipated.
Also, in FY22 a Mine Action DIB was designed as a model for using innovative finance in the mine action sector. This will be the sector’s first DIB, and as such should be of value to the whole sector, enabling it to attract more development funding by linking payments to achieved outcomes.

## D: VALUE FOR MONEY (1 page)

Key cost drivers and performance

As with all mine action programmes, GMAP3 has significant operating costs in terms of fuel, food, equipment etc. compared to most other development programmes. We will aim to draft a ‘productive recourse maintenance ratio’ indicator and relevant benchmark to ensure these costs are appropriate and deliver economy. This is in line with GICHD’s sector wide recommendation following a review of operational efficiency. The impact of the devaluation of sterling and increase in inflation in FY22 has had a major impact on programme costs in FY22. It is hard to establish whether inflation and exchange rate adjusted efficiency went down, however several change requests were made to adjust their spend between budget lines to try to save money and not reduce demining capacity in most countries. In Somalia and Zimbabwe, a reduction in demining capacity and therefore clearance targets were required, but this reduction only materialised in Somalia. The GMAP team worked closely with the implementers to review and discuss the best ways of maximising economy and efficiency to achieve VfM. VfM indicators will be drafted to ascertain efficiency adjusted to inflation and foreign exchange fluctuations in anticipation of next year's annual review.

VfM performance compared to the original VfM proposition in the business case

Given budget uncertainty, only short-term directly procured enabling contracts and grant agreements were concluded in FY22. This remains in line with option 4 under the business case and exemplifies the advantages of strategic flexibility and operational control that different procurement options provide.

Costs per sqm cleared were substantially higher than outlined in the appraisal case that used GMAP 2 figures as an estimate. This is not necessarily indicative of lower efficiency as it does not account for inflation and differences in geographies demined that could drive up costs. VfM indicators will be produced to factor both inflation and geographic costs for FY23.

Assessment of whether the programme continues to represent value for money
In the Lot 1 and 2 countries (representing seven of the eight countries in which mine action was implemented in FY22), the same operators (MAG and HALO) continued conducting the same activities in the same areas of operation in GMAP3 as they did at end of GMAP2 (with exception of Vietnam, which as of April 2022 is no longer in scope). The Lot 1 and 2 GMAP3 enabling contracts were directly procured through the CSSF framework and were initially for nine months, then extended to the 12 months of FY22. The Ukraine grant started in May 2022 to run to end March 2023. It was subsequently extended to end June 2023, outside the AR reporting. The collaboration between the GMAP team and implementers and their ability to provide continuity of funding while funding levels were finalised for the multi-year GMAP3, has saved the significant time and resources legally required for programme closure [and subsequent start up] across the programme.
The GMAP2 Programme Completion Review noted that, “the Lot 1 and 2 partners have focused on economy and efficiency”, and “have become more outcome focused, informing the prioritisation of their activities and in turn increasing the effectiveness of the programme in achieving its stated outcomes”. This continues in GMAP3. In terms of equity, GMAP works in some of the most marginalised, vulnerable communities and implementers are proactive in recruiting women and men from marginalised groups but indicators on gender, disability and social inclusion and meaningful community engagement could be more robust and more routinely monitored rather than only addressed in the evaluations.
GMAP3 is contributing to HMG’s broader strategic objectives and supporting FCDO’s humanitarian and development objectives in each of the eight countries. Demining and EORE are very visible forms of ODA and the immediate life-saving benefits are easy to understand, articulate and communicate. In FY22 there were several UK ambassadorial visits to GMAP areas of operation, including those in Angola, Cambodia, Laos, and Ukraine. GMAP is particularly important in the countries where there is little or no other development programming funded by the UK, such as Angola, Cambodia, or Laos. In such contexts GMAP is key to allowing the UK ‘a seat at the table’ for wider discussions in country regarding, facilitating access and influence and raising the profile of the UK in those countries. In Zimbabwe GMAP enables the British Embassy in Harare to engage with government security officials including the Minister of Defence and other government Ministers, on subjects and platforms that would not otherwise be possible given the difficult political landscape. Just outside the reporting period, the April 23 Westminster Hall debate on mine action confirmed cross-party commitment to mine action.

The UK has supported humanitarian mine action since its inception in 1989 and during that time has been one of a handful of donors who have influenced the mine action sector globally. The position of the UK as an advocate and thought leader for mine action continued in FY22, particularly through the UK’s timely support for mine action in the liberated areas of Ukraine. However, the fact that in FY22, the GMAP3 enabling contracts were only approved on a short-term basis due to the funding uncertainty, rather than as a multi-year programme detract from the potential impact of this hugely important programme, limiting the potential for the communications impact of contract announcements in Post as well as globally by the GMAP team.

The programme still delivers a positive cost-benefit analysis when considering the net present value of land cleared alongside the value of prevented fatalities (VPF) for each geography, indicating cost efficacy and alignment with the appraisal case. Cost benefit analysis may benefit from other forms of benchmarking as well as capturing wider benefits outside land value and VPF.
The attainment of outputs and outcomes indicates there is certainly sufficient evidence in terms of VfM for the programme to continue. Although VfM has been addressed in the evaluations of GMAP1 and GMAP2, there have not been any indicators developed for monitoring VfM during the programme lifetime and there is potential for the MEL provider to address VfM more systematically for GMAP3 going forwards to enable the GMAP team to better track this during the programme lifetime.

E: RISK [½ to 1 page]

Overview of risk management [1/2 page]

GMAP is a high-risk programme and has been managed accordingly across the first year of implementation in FY22. Risks to the programme included fiduciary risks, aid diversion, safeguarding, fraud, and corruption risks, alongside the risks which are inherent to the dangerous work that mine action actors engage in routinely. Due to the uncertainty around GMAP funding, there were also additional strategic programme risks, which were monitored, mitigated and managed throughout the period. This included “worst case” scenario planning and horizon scanning.

While FCDO’s risk appetite around safeguarding is cautious, it is accepted that, given the nature of the operations undertaken by GMAP3 partners and the complex environments in which they work, GMAP3 safeguarding risk is severe. Both main implementing partners for Lots 1 and 2 have undergone commercial due diligence checks, with a further enhanced due diligence assessments completed by the then GMAP2 Programme Managers. Both scored well during these assessments and clearly evidenced a strong and consistent approach to Safeguarding and implementing robust policies to protect staff and beneficiaries from, for example, sexual exploitation and abuse and sexual harassment (SEAH) and bullying and harassment in the workplace. The GMAP3 Programme manager was content that the robust due diligence process was sufficient not to be refreshed when GMAP3 was implemented.

All allegations are managed in line with FCDO policies for reporting and the programme officer maintains a database of all reports and meets on a monthly basis with implementing partners, (or as required) to review and monitor outstanding cases to ensure compliance with FCDO standards and guidance.

Each quarter country level risk registers are submitted by implementing partners and reviewed by FCDO’s contracted monitoring and evaluation supplier, any changes, increased or decreased risk are highlighted in a quarterly monitoring report submitted to the programme team and discussed with partners at quarterly contract governance meetings. The programme team also attends virtual meetings within country programme teams for countries considered higher risk or more complex on a monthly basis, this is reviewed regularly and adapted to reflect changing country context.

The programme team also follow an internal risk process which requires input and review of the programme risk management tool on a 4-weekly basis, which feeds into departmental and divisional risk registers.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues. [max 1 page]

Delivery partners submitted quarterly reporting to FCDO for all component spend throughout FY22. For Lots 1 and 2, for MAG and HALO led contracts, each organisation provided quarterly reports, updated country logframes, work plans, risk registers and asset registers to the M & E provider, Itad, 10 working days after the reporting period. Itad analysed and summarised these reports for FCDO, focusing on progress against KPIs and outcomes, highlighting key issues or risks and offering recommendations. Quarterly review meetings were then held with FCDO, ITAD and the implementers all participating. Ukraine was outside the MEL provider contract and was monitored by the programme team with additional input from Post, against the same reporting format and quarterly review governance structure.

In the first year of the programme, Lots 1 & 2 and HALO Ukraine submitted good quality, accurate and timely reports. It is noted that there were a number of challenges and obstacles faced, including uncertainty of future funding and of course, an extremely dangerous operating environment in Ukraine, which partners overcame admirably, staying within budget and exceeding output expectations.

Through previous iterations of GMAP, the FCDO and partners have created a strong working relationship to manage and mitigate unforeseen obstacles to operations, creating flexible and innovative working practices which maintained operations at the highest level possible, including agreed change processes, to monitor changes to budget lines and country allocations within contract parameters. This has allowed innovative working while maintaining the integrity of the programme and remaining compliant with the requirements of GMAP3 business case.

Economy has been maintained across the first year of the programme, with Lots 1 & 2, as well as HALO Ukraine, consistently achieving spend to budget at less than 1% variance for the year. Underspend issues were mitigated during the course of the programme, with both partners submitting all financial information quarterly using FCDO’s open book accounting system. Reporting on actual expenditure from previous quarter and forecasted expenditure for full year. FCDO audit checks all expenditure against original commercial proposals, the programme team also audit check each partners’ general ledger, using a spot check method. A good working relationship has been created between FCDO programme team and partner finance teams, with the payment checking methods being streamlined and a stronger understanding between parties of expectations. No issues arose throughout FY22 regarding payment requests and strong evidence of costs was submitted by partners and recorded by FCDO for audit purposes.

Programme-level approach to monitoring and evaluation

The GMAP Programme Manager conducted an in-country visit to Angola and Zimbabwe, meeting with implementing partners and national mine action authorities. In Zimbabwe, this included a visit to the GMAP areas of operations to view operations in progress, speak to implementer staff and meet with beneficiary communities.
The monitoring and evaluation partnership with Itad as the main implementer and FCDO worked extremely well throughout FY22. Itad submitted high quality, informative, and evidence driven reports, and responded positively to ad hoc requests for monitoring advice (e.g. through the change request system that the programme team has established with implementing partners). The M&E contract is delivered through the FCDO Global Evaluation Framework Agreement (GEFA).

Date of last narrative financial report	21/04/2023 (covering the period up until 31/03/2023)	Date of last audited annual statement	MAG: August 2022 / HALO: March 2022