Annual Review – post April 2018

Title: Impact Evaluations on urban transport, transport corridors and road safety across multilateral development banks and bilateral programmes (ieConnect).
Programme Value £ (full life): 12.25m		Review Date: July 2019
Programme Code: / 204931	Start Date: / November 2016	End Date: / November 2021

Summary of Programme Performance
Year	2016	2017	2018
Programme Score	A	A	A+
Risk Rating	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/5627325.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/5578223.xlsx

A. Summary and Overview (1-2 pages)

Description of programme (1/2 page)

The Impact Evaluations (IE) on urban transport, transport corridors and road safety across multilateral development banks and bilateral programmes (ieConnect) is a transport window within the larger £24.7million DFID-funded Fund for Impact Evaluation (DIME). ieConnect and DIME are housed in the World Bank.

Impact evaluations are the instrument used to assess whether a development intervention is effective and achieving intended targets. They are essential in building an evidence base on what works and what doesn’t, as well as what works best ensuring impactful interventions at scale, and returns on investment to drive Value for Money (VfM) decision making.

Transport is normally in the top three sector spends for DFID partner country Governments. It is in the top two largest sector lends for each of the Multi-lateral Development Banks (MDBs). Transport infrastructure construction (capital) and maintenance (recurrent) is expensive. Getting transport right is crucial to poverty elimination, economic development and trade; and to ensure optimum capital and recurrent spend for domestic budgets. Poor transport decisions can be a huge burden on domestic budgets for decades.

Very large investments are made in transport infrastructure - In total the eight MDBs approve about $20 billion in transport investments annually; domestic spend is larger still. One example on rural roads is the Ethiopian Universal Rural Road Access Programme which will construct 70 000km over ten years; the first five years has cost over US$1.4billion. Another example is the Tanzanian Rural and Urban Road Agency’s maintenance budget of US$ 98 million for FY 2019/2020, and road development of about US$ 47 million per annum. There is a lack of rigorous IE evidence which make it difficult to accurately include important factors in prioritisation and decision making.
[note] http://documents.worldbank.org/curated/en/220781554130465463/pdf/Rural-Roads-Poverty-and-Resilience-Evidence-from-Ethiopia.pdf

IEs on transport accounted for less than 1% of IEs globally between 1981 and 2012. Given the very large sums invested in transport projects we want to shift the sector so that decisions are more heavily influenced by evidence on their broader social and economic impact.

The original DFID budget for ieConnect was £7.5million and the project was designed as catalytic in nature and to seed fund transport Impact Evaluations (IEs) at approximately £150k per project. A costed extension of £4.75million was approved in 2018 and signed with WB in 2019, this brings the total funding to the current £12.25million. The additional £4.75million is to seed fund more projects, increase the number of IEs working with non-World Bank project partners, encourage the development of pilot systems for data collection on an ongoing basis (with the ability to scale-up), and have larger investments in some IEs (up to approx. £500k per project) where the non-World Bank project being evaluated is unable to finance the full IE.

The total cost to produce an ieConnect IE for a transport project is in the region of £800k (range £600k - £1m) with the majority of the funding from outside of the ieConnect programme. The average budget for a transport project currently undertaking an ieConnect IE is £195million. The current total value of the existing transport projects undertaking ieConnect IEs is over £5 billion.

DIME has been working within the World Bank for about ten years and has seen a positive culture shift on IEs within the WB. Through DFID funding, ieConnect aims to contribute to starting a similar culture shift outside the WB within the transport sector.

DFID’s investment of £12.25 million over five years aims to achieve significant impact by improving the selection, design, and implementation of transport infrastructure projects in DFID focus countries and beyond. Potentially this could include re-prioritising transport investments to connect remote areas to the global economy, create new trade corridors, ensure women and children are empowered, and to permit the development of bigger, denser, more productive and safer cities.

The Impact Evaluations funded under ieConnect originally focused on three sub-themes of relevance to economic development (i, ii, iii), and in the costed extension an additional sub-theme of Rural Roads (iv) was added:

i)	Urban Mobility
ii)	Transport Corridors
iii)	Road Safety
iv)	Rural Roads

The two cross cutting themes remain constant as fragile, conflict affected states (FCAS) and female economic empowerment (FEE).

DFID is providing funding and guidance to ieConnect to achieve the following aims:

• Technical knowledge - Provide expert technical support to programme teams (including DFID teams) to use impact evaluation in transport programmes;
• Global public good - Build the capacity for evidence-based decision-making on transport investments within governments, MDBs and donors; and
• Knowledge management - Build on existing DIME knowledge platforms and institutional structures to share transport findings.

Examples of IEs funded under ieConnect range from measuring the impact of road access on household income and price dispersion across national markets in Rwanda; to understanding gentrification and displacement related to bus rapid transit investments in Dar es Salaam; to determining the impact on urbanisation and manufacturing production associated with connecting Addis to the port of Mombasa. A full list of ieConnect projects is included in Annex 1.

DFID is supporting the new transport window (ieConnect) through the Development Impact Evaluation (DIME) unit of the World Bank. The Evaluation Unit (EvD) in DFID already supports DIME through the Impact Evaluation to Impact Development (i2i) Multi-Donor Trust Fund, which aims to reduce poverty and scale up development results by improving the availability of impact evaluation (IE) evidence and its use. The next ieConnect AR will be completed earlier than necessary, by March 2020, to align the ieConnect AR cycle with the existing DIME i2i AR cycle.

In a significant advance on existing studies, ieConnect will evaluate the broader impacts of the transport programmes including trade patterns, job creation, urban shape, and female economic empowerment (FEE). This is ambitious and innovative.

Summary supporting narrative for the overall score in this review (1/2 page)

ieConnect scores an A+ in this Annual Review. The programme has performed at pace and, in the majority of cases, met or exceeded milestones. The transport sector is challenging due to the scale of investments, the long lead in and implementation time of transport projects, limited ability for randomised trials and the relatively traditional design of projects. ieConnect is managing a complex portfolio and utilising cutting edge technology and data systems to achieve rigorous IEs across four sub-themes of transport. Overall, ieConnect are congratulated on the progress to date. The areas for further work are highlighted in the recommendations below.

ieConnect has the following outcomes and outputs:

Outcomes:

Improved awareness, demand for and use of transport evidence in decision making

Improved effectiveness and impact of new and existing transport interventions from DFID, MDBs and the wider community

Outputs:

  1. Increased quantity, quality and relevance of transport evidence available to improve policy design and implementation. Scored: A+ (40% weighting)

  1. Increased capacity of transport policymakers, implementers, researchers, and partners to incorporate rigorous evidence/tools into policy making. Scored: A+ (40% weighting)

  1. Increased Communities of Practice and knowledge platforms for sharing of transport evidence and its application for policy making. Scored: A (20% weighting)

IEs are at varying stages but some of the more mature IEs are yielding initial findings such as:

  - In Rwanda, feeder road rehabilitation increases household income by 23.4%. Prior to the road rehabilitation, households living in remote villages had, on average, household incomes that were 23.1% less than households living in more connected villages. This means that the road rehabilitation results in a full catch-up of lagging households.
  - In Dar es Salaam, Tanzania, when comparing households near the Bus Rapid Transit (BRT) (<1km) with those near the planned, but not yet constructed, BRT phase 2 (<1km), there is a statistically significant decrease in travel time to work, no change in the travel cost, an increase in commute satisfaction, and a modal switch out of informal transport and private vehicles.  These are early indications of the benefits of new public transit access on households and the environment. In Ethiopia, within 5km of the expressway, there is a 5% increase in night light luminosity, a proxy for GDP, and a 3% increase in land classified as urban vis-à-vis a 1% baseline, indicating that economic activity increases around a newly constructed highway and spills over to other areas.

For this Annual Review covering 2018 progress, there were 11 IEs that have completed concept note review (Phases 2 or 3), which means these projects have high quality research designs that are approved and beginning implementation of the proposed IE methodologies and data collection. Of these IEs, 45% include multi-arm evaluation designs which allows for different innovations to be tested and show policy makers and government counterparts what works before going to scale. Additionally, 64% of these IEs report having influenced the transport project during design or implementation. In these cases, project teams either improved the project design based on a clear understanding of the underlying theory of change due to the IE or used the baseline results of the IE to stimulate policy dialogue and identify problems and solutions early in the lifecycle of the project. Specific examples of policy impact reported by ieConnect teams include:

- In Tanzania “The IE's midline survey found increases in rents and transport costs along the BRT corridor. In response, Dar Rapid Transit Agency agreed to pilot two Access to Transport programmes, providing fare and location based conditional cash transfers to the urban poor”.
- In Nicaragua, “The IE helped the project to (i) increase attention to its road safety component, which has the potential to significantly reduce road injuries - one of the leading causes of death in Nicaragua, and the availability of road safety strategies that go beyond infrastructure improvements. (ii) It created strong appetite for digitalising the road safety routine data collection process. As such, the project is currently exploring ways of introducing a tablet-based case reporting mechanism in Nicaragua”.
- In Senegal, “The IE brought up the issue that depending on the type of transit fare charged (distance-based or flat rate) it could influence the use by different groups such as women who may have different ridership patterns from men. Based on this, the project is considering initial analysis and experimentation to determine which type of fare would be most equitable.”
- In Ethiopia, “The IE focused on road safety, which has helped develop the rationale for intersection design that gives priority to vulnerable users”

Recommendations for the year ahead (1/2 page)
There are two recommendations from AR2017 that are ‘ongoing’ and two that are marked as ‘progress made and continuing’. The DFID Senior Responsible Owner (SRO) will soon change and all recommendations from this AR and those still of relevance from AR2017 are included here for ease of reference.

Additionality of costed extension:

Quarterly meetings will report on costed extension progress. The agreed deliverables are:

add at least eight more transport IEs (explicitly including DFID-Country Office transport programmes) on non-World Bank financed projects (note: approved addendum states 40% of total funds. This target will be reviewed as per recommendation below), and four MDBs and five bilaterals involved at the operational level of the IE;
- push for a step change in the transport sector’s ability to undertake IEs through engaging beyond the World Bank, specifically with RDBs, bilaterals, Governments, NGOs, and other actors;
- add at least two more data infrastructure deliverables, which pilot data collection techniques that capture outcomes on an ongoing basis and have the ability to scale-up to other projects;
- explore the potential for improving approaches, consistency and co-ordination across the MDBs in their IEs, indicators (e.g. testing a road safety and an urban access indicator), and data collection particularly those relevant to the SDGs;
- add Low Volume Rural Transport as a theme that DFID funds within ieConnect

Action: All additional IEs funded under the extension will be on non-World Bank funded transport projects. The increased non-WB IEs has been reflected in the logframe milestone 2.4 as an increase from 20% to 25% (by 2021) and the number of pilot data systems to 3. DFID will need to review and agree with ieConnect appropriateness of the existing metric and assure that the targets for non-World Bank funded transport projects are challenging.

Profile of DFID funding, burden share and attracting other donors:
Burden share for DFID is a significant issue. Prior to the costed extension, the burden share of DFID’s ieConnect £7.5M contribution was 34% of total contributions. The costed extension provides a higher level of funding per project, and it will therefore affect the ability to meet the DFID <40% target in the short-term until additional, non-DFID funding is secured. DFID approves an increase in burden share to <45% in 2019; the target of <40% will remain for years 2020 and 2021. DIME’s experience from i2i is that in the first two years, most of the staff capacity is spent securing stakeholder and government engagement and getting projects up and running in the field. During this time fundraising primarily occurs at the project level through client contributions for data collection or external research grants. ieConnect has secured over $13M in funds at the project level, including $7.4M through client contributions primarily for data collection on IEs, $2.1M from other WB trust funds, and $3.0M from other allocations to the IE including external research grants and in-kind resources. ieConnect will need to work to attract core donors to fund overheads and staff costs as well as the specific IEs. An update from ieConnect on donor engagement will be submitted in the next quarterly meeting.

Culture shift in partners and in WB:
DFID has pushed hard to ensure that ieConnect is working at pace outside as well as inside the World Bank. There have already been successes for ieConnect within the WB. The more challenging but potentially more impactful aspect of ieConnect is working with partner Governments, Regional Development Banks (RDBs), Bilaterals and Researchers to raise its profile and increase IE work throughout the global transport sector. ieConnect have discussed working with the German Development Agency BMZ (and technical agency, GIZ) but to date no IEs have been agreed; Asia Development Bank (ADB) engagement is under development. Work with DFID, ADB and BMZ should be prioritised. Next steps on these will be proposed by ieConnect and agreed with DFID by October 2019.

ieConnect is active in looking for partners outside of the World Bank. However, there is more to be done to ensure ieConnect makes the most effective impact through engagement with non-WB led fora such as the World Road Congress and ADB transport week. These are the types of international events that must be prioritised over WB-led events. Overall the ieConnect team are less informed than expected about key strategic transport events (within and outside of the WB). The WB’s Global Practice is a partner in ieConnect and should play a stronger role in informing ieConnect team of relevant transport conferences and events.

Framework papers, e.g. the Road Safety Framework, need to ensure they are informed by the wider international agenda and particularly that of RDBs. The final draft of the Road Safety Framework was relatively narrowly informed by WB views and expertise. The Road Safety Framework had not adequately taken into account the WHO development of country approved indicators (feeding in to the Sustainable Development Goal (SDG) indicators) nor the Bloomberg and GRSF 2017 work on Economic Costs of Road Crashes.

Ongoing from AR2017: Following the 2017 AR, ieConnect, in agreement with DFID, has been working to form an advisory committee that would include an MDB representative. The ADB has committed, but there has been little appetite from other organisations approached. Updated action: ieConnect will suggest a different mechanism to ensure the ADB representative is able to engage in the strategic direction of ieConnect. This will be discussed with DFID at the next quarterly meeting and agreed by October 2019.

IeConnect presented at the MDB Transport Working Group meeting in January 2018 (once highlighted as an opportunity by DFID). The MDB Working Group is important for setting the strategic agenda for the transport sector. A presence at the MDB Working Group meetings is one way to move the IE agenda forward. ieConnect should present at least annually at the MDB Working Group.

Indicators and milestones:
ieConnect has performed impressively and at pace. DFID and ieConnect agreed stretching targets (as recommended in the 2017 AR) in early 2019, these will be used in the next AR.

Output 1: There is a need to think through how DFID ensures the Logframe remains relevant and stretching given the impressive progress to date and many of the indicators under Output 1 being related to geographical or thematic focus as opposed to working at pace and specific deliverables. Stretching targets were incorporated into the revised logframe (approved March 2019). However, some of these targets have been met in 2018. Additional stretching targets will be suggested by DFID and agreed with ieConnect by October 2019.

Output 2: milestones for future years must ensure ieConnect is being as impactful outside of the WB as it is being within the WB. DIME’s model is to work directly with implementing partners, and the Independent Evaluation Group (IEG) of the WB have confirmed that policy impact is most likely when IEs are initiated by partner Governments.

Output 3: 3.2 and 3.3 have been substantially increased to stretch the ieConnect team. The 2021 milestone has been achieved for Output 3.1 in 2018, so a revised 3.1 milestone will be agreed by October 2019.

Progress made and continuing from AR2017: ieConnect to make recommendations of practical ways to work in the medium term with the Sustainable Mobility for All (SuM4ALL) initiative on indicators and measurement frameworks. ieConnect will suggest ways to integrate the goals of SuM4All with project-level indicators associated with transport interventions from the World Bank. DFID and ieConnect will discuss opportunities to encourage MDB alignment of key transport indicators with the global objectives and targets. DFID is the founding donor to SuM4ALL and sits on the Steering Committee (SC). Progress: ieConnect and SuM4All have worked together in 2018 on a proposal to address how ieConnect can inform global measurement frameworks. To account for the work on indicators, the logframe was stretched with one more new technical note deliverable. At the project level, SuM4All and ieConnect have prepared a menu of indicators by WB policy goal, which is now available as an input for Task Team Leads (TTLs) during project preparation. Updated action: ieConnect to update DFID by October 2019.

Innovative technology and use of big data:
Transport IEs are typically on a larger scale, have more intensive data requirements, and present unique methodological challenges compared with IEs in other sectors. ieConnect has prioritised the development and expansion of data systems using new technologies to harvest large amounts of data at higher frequency or with greater geographic coverage and spatial resolution than traditional survey methods allow. This includes geospatial, crowdsourced, or sensor data, coupled with new and existing datasets. ieConnect and DFID will by October 2019 agree ways to most effectively disseminate these impressive advances in data systems and use of technology within DFID, RDBs and other International Organisations.

Evidence building across the portfolio:

Progress made and continuing from AR2017: In order to achieve the longer term expected benefits of informing the design of a wide range of transport projects it is important that the findings of the impact evaluations are transferable between contexts and interventions. This is only likely to be the case if ieConnect is successful in conducting a sufficient number and – importantly - range of evaluations to build a body of evidence of how results vary across projects. Achieving a high degree of external validity is dependent on running similar interventions in multiple contexts; the scale of current DFID support is unlikely to be sufficient to achieve this, but strategic coordination of IEs that are conducted is expected to go some way to addressing this. ieConnect has made some progress in this area. There are two areas where ieConnect is already working on evaluating similar interventions in multiple contexts (i.e. i) trauma registry data collection in Tanzania, Malawi and Kenya; ii) BRT baseline and data in Dar is Salaam, Dakar and possibly Abidjan) and two areas where ieConnect are developing proposals (crowdsourcing data collection in Kenya; data systems in Rwanda) Updated action: ieConnect will report back to DFID by October 2019 on how they aim to achieve this in the medium term.

Ongoing from AR2017: The 2017 AR highlighted the utility of ieConnect engaging in dialogue on possible medium term changes across MDBs to move towards a more consistent collection of data across MDB financed projects. This could allow comparison and utilisation of larger data sets for the benefit of the global transport sector. ieConnect are clear that delivery of this is outside of the scope of ieConnect. However, through presentations at the MDB Sustainable Transport WG and engagement with RDBs ieConnect will raise awareness of this issue. Updated action: ieConnect and DFID to agree next steps and realistic objectives by October 2019.

Exploration of other themes and time extension:

Over the past year DFID has substantially increased our work and thinking on climate adaptation and mitigation. Transport and energy are key parts of this agenda. Over the next four months DFID and ieConnect will work together to explore possibilities for an energy and / or climate change theme within ieConnect. Action: DFID and ieConnect to explore the possible development of an energy and / or climate change theme within ieConnect; agreement on way forwards by December 2019.

Transport projects are large scale and lengthy. To ensure the most effective engagement of ieConnect within this sector it is important to explore the possibility of a time extension to the existing programme of work. Action: DFID and ieConnect to explore the possibility of a time extension to the current programme; agreement on way forwards by December 2019.

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Increased quantity, quality and relevance of transport evidence available to improve policy design and implementation
Output number per LF		1.	Output Score	A+
Impact weighting (%):		40%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
1.1Number of Impact Evaluations (IEs) across key sub-sectors (total): urban mobility, transport corridors, and road safety.	Total: 16 / Urban Mobility: 25% / Transport Corridors: 30% / Road safety: 25%	26 IEs / 27% / 54% / 38% / NB: projects can fit within more than one theme
1.2 Thematic knowledge reviews for policymaking	First target 2019	A road safety framework paper is under development.
1.3 Number of cross cutting reviews in FEE and FCAS	First target 2020	First target 2020
1.4 Developed data infrastructure (with ability for scale up)	1	3 / Impact Evaluation of Rwanda Rural Feeder Roads; Health Impacts of Emergency Response and Post-Crash Medical Care in Malawi; smarTTrans: Road Safety in Kenya
1.5 Developed and validated measurement framework that is able to disaggregate impact (male/female or rural/urban).	First target 2019	In Kenya, progress is being made on developing an algorithm to measure road traffic crashes across Nairobi and to categorise hot spots for crashes.
1.6 DFID burden share of ieConnect	First target 2019	Prior to the costed extension, the burden share of DFID’s ieConnect £7.5M contribution was 34% of total contributions. Because the costed extension provides a higher level of funding per project, the programme appears on target for <45% DFID burden share for 2019 and 40% by 2020.
1.7 Thematic distribution: Gender (cross-cutting)	30%	31%
1.8 Geographic distribution:	Africa: 75% / South and SE Asia: 10% / FCAS: 50%	77% / 12% / 69%
1.9 Income level distribution:	Low income, lower-middle income, or high fragility: 100% / DFID focus countries 60%	100% / 81%
1.10 Female Economic Empowerment (FEE):	Proportion of IEs with FEE specific intervention: 30% / Proportion of IEs disaggregated by sex and age: 30%	35% / 50%

Provide supporting narrative for the score

The Output 1: Increased quantity, quality and relevance of transport evidence available to improve policy design and implementation. Output indicators 1.2, 1.3, 1.5 and 1.6 have first milestones in 2019 or 2020.

All the indicator targets measured in the period for this output have been exceeded with some progress on indicators where targets are set for future years. The output targets 1.1 and 1.4 have met or exceeded respective milestones for 2019 and 2021.

The indicator 1.1 has been exceeded. The IEs currently underway are listed in Annex 1. A few of the highlights are:
- Senegal Impacts of the Bus Rapid Transit (BRT) system and Regional Express Train (TER) in Dakar, includes two evaluations: one during the construction phase and one upon initial launch of service. Direct job creation is cited as a benefit of large infrastructure projects. There is little evidence of the impact of these kinds of construction jobs on the well-being of workers and their households. A second IE aims to support a pilot data system in Dakar that will allow a systematic analysis of the impact of these two large transport infrastructures on land value, relocation of households and access to services, jobs and markets. The pilot data system would include data on other variables such as air quality, congestion and road safety.
- Addis Ababa Impact Evaluation of the Transport Sector Improvement Project, Ethiopia: The rapid expansion of transport infrastructures in the city has represented an additional potential threat to safety for pedestrians. Pedestrians represent 80% of the total fatalities. Using new technologies to analyse data from video footage, this IE helps to: (i) Understand the causes of road safety risks at key intersections and five selected transit corridors; (ii) Understand the most effective interventions that reduce road safety risks; and (iii) improve police traffic management through the application of data diagnostics and technology.
Hawassa Industrial Park Community Impact Evaluation, Ethiopia focuses on the emergent impacts on Ethiopia’s industrial parks (IPs) on the local economy in the labor catchment areas. ieConnect studies the impact of the expansion of hiring for the government’s flagship Hawassa Industrial Park (HIP) on the economic, physical, and social well-being of workers, and the broader impact of hiring on the largely rural, agricultural communities from which these workers are recruited.

In 2018 the programme included 26 impact evaluations (IEs) focusing on urban mobility, transport corridors, road safety, and gender and is set to expand to at least 30 IEs and add Rural Roads as an additional sub-theme with the DFID cost extension. ieConnect has added projects beyond the 2018 target of 16 to account for possible attrition and project risks and to bring on projects earlier to ensure they can deliver in a timely manner. Historically, there has been a 20-30% failure rate in the i2i portfolio for reasons outside of DIME’s control, such as a change of administrations, failed projects, and political instability. Transport may experience higher failure rates because of the complexity and scale of projects, lack of available data, and by working with a larger percent of non-World Bank projects. Projects with other MDBs and bilateral organisations introduce additional types of risk into the research portfolio, since they are dependent on projects outside of the World Bank’s control. To address failure rates, ieConnect prepares and approves a larger number of total IEs, including in higher risk investment areas such as corridors.

The indicator 1.4 has been exceeded and development of 3 pilot data systems is underway. To tackle the challenge of working on transport IEs, which are typically on a larger scale, have more intensive data requirements, and present unique methodological challenges compared with IEs in other sectors, ieConnect has begun the development and expansion of data systems using new technologies to harvest large amounts of data at higher frequency or with greater geographic coverage and spatial resolution than traditional survey methods allow. This includes geospatial, crowdsourced, or sensor data, coupled with new and existing datasets. The data systems being developed allow research teams to mitigate methodological challenges—such as the fact that selection of project sites is not random and is often integral to project design—using rigorous IE methods. This, in turn, can build local capacity and strengthen government agencies’ basis for evidence-based decision making in the long-term. One clear example of ieConnect’s work in this area is the use of Artificial Intelligence (AI) for road safety in Kenya. The team has developed machine learning algorithms that scrape tweets on road traffic crashes in Nairobi from Twitter and in real-time geolocate them to build on a comprehensive crash map that can be used to identify and prioritise crash hotspots. In Ethiopia, the team has been using night time light data and other satellite imagery to study the impact of large-scale corridors, enabling them to measure impact in a context where household surveys are infeasible to conduct across such a large area of the country. Similarly in Iraq, use of night time light and satellite imagery make it possible to measure impact in a highly fragile context.

The 3 data systems currently under development are:

1. Rwanda: Impact Evaluation of Rwanda Rural Feeder Roads: has been developing a price survey dashboard.  This website shows the price per unit of different products across the country each quarter.  Teams have been surveying market prices since the end of 2016 and are using this data to understand how the road rehabilitation is impacting the availability and price of goods across markets.
2. Malawi: Health Impacts of Emergency Response and Post-Crash Medical Care: the trauma registries for this impact evaluation have been launched.  This system is collecting baseline data in 10 facilities on an ongoing basis. ieConnect have developed a monitoring tool through Dropbox Paper that not only to helps track data collection but also feeds the data back to the health facilities, sending them key data every week to improve data collection as well as track trauma care needs. As of January 2019, data had been collected on about 14,000 trauma cases across the 10 facilities since August 2018.
3. Kenya: smarTTrans: Road Safety: a pilot of the Nairobi crash map is being developed.  The team is currently testing data collection and verification methods that feed in to populate the map in real-time including collecting data through Twitter and through direct crowdsourcing from delivery drivers. The team has also worked to digitise 10,000 police records on crashes in Nairobi from 2012 to 2018 that will be included in the map and is working with the police to pilot digital data collection methods.

Indicator 1.6 on DFID burden share at <40% is aligned with the DFID EvD logframe and target. The burden share prior to the costed extension was 34%. The costed extension contributes more per IE than the original Business Case. The first milestone for this indicator is 2019. Due to the costed extension DFID agree that the milestone in 2019 will be increased to <45%, in 2020 this will revert to <40%. ieConnect has sourced increased core funding over the last year. The EU Delegation in Rwanda contributes to the trust fund to support agriculture and transport IEs totaling about $3.45M. In addition, the EU Delegation in Mozambique contributes to the trust fund to support agriculture and transport IEs, a portion of which will be used for transport related activities including data collection stratified by planned roads (~$1.96M).

DIME’s experience from i2i is that during the first two years, most of the capacity is spent securing stakeholder and government engagement and getting projects up and running in the field. During this time, fundraising primarily occurs at the project level through client contributions for data collection or external research grants. ieConnect has secured over $13M in funds at the project level, including $7.4M through client contributions primarily for data collection on IEs, $2.1M from other WB trust funds, and $3.0M from other allocations to the IE including external research grants and in-kind resources. Additional programme allocations totaling $1.5M have come from AfDB, IADB, IsDB, the Transport GP, and other sources of Bank Budget to support IEs products, workshops and programme activities. External grant funding comes from MIT’s Abdul Latif Jameel Poverty Action Lab (J-PAL), the International Growth Centre (IGC), Centre for Economic Policy Research’s Private Enterprise Development in Low-Income Countries (PEDL) grant, the Global Road Safety Facility (GRSF) and 3ie, as well as through financial and in-kind support from partner research universities. Three of the external grant funding (IGC, PEDL and GRSF) are DFID funded and ieConnect will need to ensure there is non-DFID financing in addition to these as the programme matures. At this time, the IGC, PEDL, and GRSF grants are relatively small amounts, but are worth noting because they have a competitive grant application processes which are highly competitive with a high proportion of projects from PEDL and IGC being published in top tier economic journals. A much larger percentage of funding to ieConnect comes from client contributions and other WB transport project funding. ieConnect continues to seek other core donors which would reduce the DFID burden share.

Lessons identified this year, and recommendations for the year ahead linked to this output

Output 1: ieConnect has performed impressively and at pace. There will be a need to think through how DFID ensures the Logframe remains relevant and stretching given the progress to date and many of the indicators under Output 1 being related to geographical or thematic focus as opposed to working at pace and specific deliverables. Stretching targets will be suggested by DFID and agreed with ieConnect by October 2019.

Burden share for DFID is a significant issue, particularly as the costed extension is providing a higher proportion of funding on a per IE basis, and ieConnect will need to work to attract core donors to fund overhead and staff costs as well as the specific IEs. Update from ieConnect on ongoing donor engagements during the October 2019 quarterly call.

Framework papers, e.g. the Road Safety Framework, need to ensure they look at the wider international agenda and particularly that of RDBs. The Road Safety Framework had not adequately taken into account the WHO development of country approved indicators (feeding in to the SDG indicators) nor the Bloomberg and GRSF 2017 work on Economic Costs of Road Crashes.

Output Title	Increased capacity of transport policymakers, implementers, researchers, and partners to incorporate rigorous evidence/tools into policy making
Output number per LF		2.	Output Score	A+
Impact weighting (%):		40%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of MDBs involved at the operational level	4	ieConnect is working with Africa Development Bank (AfDB), Islamic Development Bank (IsDB), Asia Development Bank (ADB), the EU and Inter-America Development Bank (IADB) in the transport IE portfolio.
2.2 Number of bilateral donor institutions involved at the operational level	3	4 ieConnect is working with DFID-Country Offices (Pakistan and Ethiopia), EXIM Bank of China, Dutch Development Bank (FMO), and Japanese Development (JICA)
2.3 Proportion of co-financed transport programmes	90%	100% / Improvement in % IEs that are part of a co-financed transport programme from 67% (2016) to 88% (2017) to 100% (2018).
2.4 Spend on non-WB IEs or co-funded IEs where WB contribution <=25%	20%	23% / Increased IEs on non-WB projects or co-funded projects from 17% (2016) to 21% (2017) to 23% (2018).
2.5 Proportion of people participating in workshops that come from low or lower-middle income countries	75%	87%
2.6 Proportion of people participating in workshops that come from FCASs	50%	50%
2.7 Number of people trained in workshops and / or by ieConnect supported teams/ researchers	250	292
2.8 Number of workshops	2	6 / ieConnect for Impact, Lisbon, July 2017; Hawassa Industrial Park Research Workshop, Addis Ababa, March 2017; Road Safety and Emergency Response Impact Evaluation Workshop, Lilongwe, January 2017; Impact Evaluation for Transport Workshop, Nairobi, April 2018; Evidence for Policy in Transport, Nairobi, May 2018; Road Safety and Emergency Response Impact Evaluation Workshop, Dar es Salaam, November 2018; Utilisation de données innovantes pour éclairer les politiques de transport et de mobilité à Dakar, Senegal, December 2018.

Briefly describe the output and provide supporting narrative for the score

Output 2 focuses on the capacity of transport policymakers, implementers, researchers and partners to incorporate rigorous evidence and tools into policy making. This is crucial to the impact of ieConnect. ieConnect has achieved or exceeded all the milestones for this year.

DFID has pushed hard to ensure that ieConnect is working at pace outside as well as inside the World Bank. There have already been successes for ieConnect and DIME (latter as a larger and broader IE programme) within the WB. The more challenging but potentially more impactful aspect of this output is working with partner Governments, RDBs, Bilaterals and Researchers to raise the profile and IE work throughout the global transport sector. Current ongoing work with the Africa Development Bank (AfDB) and Islamic Development Bank (IsDB) in Senegal on urban transport and Ethiopia on Road Safety are good examples of ieConnect working outside of the WB. So far there is only one IE example of ieConnect partnering with a DFID country office (DFID-Ethiopia) in the work on gender within the Hawassa Industrial Parks. DFID-Pakistan and ieConnect are continuing to engage but have so far not agreed an IE. ieConnect have discussed working with the German Development Agency BMZ (and technical agency, GIZ) but to date no IE has been agreed. Working with DFID, ADB and BMZ should be prioritised. Full list of projects is included in Annex 1.

Outputs 2.5 and 2.6 are focused on the people that attend the workshops (% from LICs / LMICS and % from FCAS respectively). Both milestones have been met and 2.5 exceeded. ieConnect report the breakdown of target participants as 82% from Africa and 4% from Asia. Examples of the participants at the workshop include the Director of the Kenya National Highways Authority, Mayor and Deputy Mayor of Hawassa, Doctor from the Mzuzu Central Hospital Malawi, Epidemiologist from the Kenya Ministry of Health and Senior Researcher from the Korean Embassy. The low participation of Asia again highlights the need to continue and increase engagement with the Asia Development Bank (ADB). ADB’s transport annual lend in Asia and the Pacific is of the same scale as WB lend globally.

Lessons identified this year, and recommendations for the year ahead linked to this output

ieConnect is active in looking for partners outside of the World Bank. However, there is more to be done in ensuring ieConnect makes the most effective impact with the evidence through engagement with non-WB led fora such as the World Road Congress and ADB transport week. These are the types of international events that must be prioritised over WB led events. It is surprising that the Transport Global Practice is not more active in profiling ieConnect at international transport events.

Again, the Output 2 milestones should be stretching and there may be a case for reviewing the milestones for future years to ensure ieConnect is set targets for being as impactful outside of the WB as it his being within the WB. The Independent Evaluation Group (IEG) of the WB state that policy impact is most likely when IEs are initiated by partner Governments. DFID and ieConnect to discuss an additional indicator to further measure Government engagement in the IEs and in ieConnect. DFID and ieConnect to agree an additional indicator by October 2019.

Output Title	Increased Communities of Practice and knowledge platforms for sharing of transport evidence and its application for policy making
Output number per LF		3.	Output Score	A
Impact weighting (%):		20%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of organisations participating in ieConnect workshops	60	138, examples in the narrative
3.2 Number of organisations, universities, research centres, and government agencies participating in ieConnect networks	30	34, listed in the narrative
3.3 Number of non-WB hosted dissemination events	4	19, listed in the narrative
3.4 Active MDB participation on DIME Steering Committee	1	0

Provide supporting narrative for the score

Output 3 is focused on Communities of Practice and knowledge platforms for sharing of transport evidence and its application for policy. The Output achieves an A as although the milestones for 3.1, 3.2 and 3.3 have been exceeded these were not stretching and milestone 3.4 is of significant importance and has not been met. In addition ieConnect have two ongoing recommendations from AR2017 and this is reflected in this scoring of an A as opposed to an A+.

A few examples of the 138 organisations participating in ieConnect workshop under 3.1 are listed below:

- Addis Ababa City Roads Authority
- Conseil Exécutif des Transports Urbains de Dakar
- Centre Universitaire de Recherche et d'Étude de la Mobilité
- Dar Rapid Transit (DART) Agency
- Department of Roads, Government of Nepal
- Directorate of Road Traffic Services, Malawi
- East Africa Research Hub
- EDRI
- Eiffage Rail Senegal
- Enterprise Partners, Ethiopia
- European Bank of Reconstruction and Development
- Federal Transport Authority of Ethiopia
- Fondo de Mantenimiento Vial, Nicaragua
- Hawassa Mayor's Office
- Innovations for Poverty Action
- Japanese Development (JICA) Research Institute
- Kenya National Highways Authority
- Kilolo District Hospital
- London School of Economics
- Ministerio de Transporte e Infraestructura, Nicaragua
- Ministry of Agriculture and Animal Resources, Rwanda
- Ministry of Public Works, Liberia
- Ministry of Transport, Infrastructure, Housing and Urban Development, Kenya
- Ministry of Works Transport and Communication, Tanzania
- Ministry of Health, Malawi
- Rwanda Transport Development Agency (RTDA)
- SONATEL
- UN Habitat
- University of North Carolina at Chapel Hill
- Trinity College Dublin

Listings for the organisations and events counted under 3.2 and 3.3 are:

3.2 organisations, universities, research centres, and government agencies participating in ieConnect networks
- Africa Development Bank
- Barcelona Graduate School of Economics
- Beit CURE International Hospital, Malawi
- College of Medicine, Malawi
- College of William and Mary
- DFID
- European Bank Reconstruction and Development
- EC/EU
- European University Institute
- Swedish Development Bank (FMO)
- Harambee
- Harvard School of Public Health
- Harvard University
- Information Technology University
- Islamic Dev Bank
- Japanese Development (JICA)
- John Hopkins University
- London School of Economics (LSE)
- Lahore University of Management Sciences
- Massachusetts Institute of Technology
- New York University Abu Dhabi
- Oxford University
- Sciences Po
- Stanford University
- Stockholm School of Economics
- Trinity College Dublin
- Tufts University
- University of California, Berkeley
- University of Cape Town
- University of Chicago
- University of North Carolina
- University of Southern California (USC)
- University of Toronto
- World Bank Group

3.3 Number of non-WB hosted dissemination events
Date	Event	Host
2017	Presentation on Pakistan to Asian Development Bank	ADB
2017	Mozambique EU Ag Meeting, slides w/ Rwanda Rural Roads	EU
2017	DIME Presentation to SECO	Swiss
Oct-17	GIZ Transport	GIZ
Dec-17	PEDL/IGC PhD Conference	PEDL/IGC PhD Conference
Jan-18	DFID Evaluation Unit presentation	DFID
Jan-18	MDB Sustainable Transport Working Group Meeting	IADB
Apr-18	Brussel, DIME European Union Meeting	EU Parliament, DEVCO, DERegio, others
Apr-18	TUMI/ieConnect Knowledge-Sharing	BMZ
May-18	National Feeder Roads Program High Level Conference	National Feeder Roads Program High Level Conference
May-18	Informing Transport Investments	Nairobi DFID
Jun-18	Entrepreneurship and Private Enterprise Development in Emerging Economies Workshop	McGill University
Sep-18	EUDevCo Mozambique Presentation	EUDevCo
Oct-18	IDRC presentation on GBV IEs	IDRC
Oct-18	Rio GBV Impact Evaluation Presentation	EIB
Oct-18	World Data Forum, Dubai	UN Data 2X
Nov-18	Rwanda IEs presentation	Duke University
Dec-18	PEDL/IGC PhD Conference	CEPR/PEDL
Dec-18	IZA/DFID Growth and Labour Markets in Low-Income Countries Programme	DFID/IZA

Output indicator 3.4 was not achieved. ieConnect have made some progress however the importance of strategic and project level engagement with the RDBs as has been highlighted in earlier sections. The ADB has committed to being a member of a Strategic Committee, but there has been little appetite from other organisations approached. ieConnect will suggest a different mechanism to ensure the ADB representative is able to engage in the strategic direction of ieConnect. The ADB annual transport lend in Asia and Pacific is of a similar scale to the WB globally (circa $6billion and $7billion respectively). Arguably ieConnect progress in ADB on transport IEs is of potentially of greater impact than progress in the WB. This will be discussed with DFID at the next quarterly meeting and agreed by October 2019.

In terms of increasing communities of practice, ieConnect has had multiple sessions with ADB about transport IEs, shared workshop materials and provided input to developing ADB’s IE programme. ADB’s first impact evaluation programme launch will now be on transport instead of health or gender as originally proposed. This is a demonstration of ieConnect engagement.

Lessons identified this year, and recommendations for the year ahead linked to this output

DFID and ieConnect agreement on the logframe targets (as recommended in the 2017 AR) were finalised in early 2019 and so will be used in the next AR. Outputs 3.2 and 3.3 have been substantially increased to stretch the ieConnect team. The milestone for indicator 3.1 is still not stretching enough for 2019 as the 2021 milestone has been achieved in 2018.

Following the 2017 AR, ieConnect, in agreement with DFID, has been working to form an advisory committee that would include an MDB representative. The ADB has committed, however there has been little appetite from other organisations approached. ieConnect will suggest a different mechanism to ensure the ADB representative is able to engage in the strategic direction of ieConnect, this will be discussed with DFID at the next quarterly meeting and agreed by October 2019.

IeConnect presented at the MDB Transport Working Group meeting in January 2018 (once highlighted as an opportunity by DFID). The MDB Working Group is important for setting the strategic agenda for the transport sector. A presence at the MDB Working Group meetings is one way to move the IE agenda forward. ieConnect should present at least annually at the MDB Working Group

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year (1/2 page)

No change in the past year other than an increased focus on data systems and working outside of the World Bank. The ToC remains valid.

ieConnect represents a scaling up of a specific component of an existing programme. The theory of change for additional DFID funding for infrastructure impact evaluation through DIME (ieConnect) is consistent with the theory of change for DFID’s existing investment through DIME (outlined above).

Conducting rigorous impact evaluations on how large-scale transport projects contribute to economic development and poverty reduction is novel and challenging. Therefore a key assumption in delivering the expected outputs is ieConnect successfully developing new and better methods for transport impact evaluation. ieConnect’s proposed approach involves undertaking evaluations based on a structured framework and will need to involve observing intermediate processes that might be assessed over a relatively short time period. This is expected to allow analysis to move beyond traditional transport project outcomes along a range of indicators that have preliminarily been clustered around 4 categories: land, job opportunities, output and trade markets and road safety.

There is some evidence that the World Bank’s impact evaluations specifically do affect policy dialogue and development intervention decisions; a 2012 IEG study of all World Bank impact evaluations concluded that they had: influenced policy dialogue in 55% of cases; influenced the design of new projects in 23-40% of cases; informed scale up/down directly in 22-33% of cases; and increased capacity for impact evaluation with counterparts, such as partner governments in 33% of cases. DIME continuously measures policy influence across the cycle of implementation of its programmes and products. IEG also found that limited active engagement of client government counterparts in the initiation, design, analysis and review of impact evaluations can undermine the influence of evidence in decision making and dialogue. For example, 83% of completed impact evaluations initiated by the client influenced policy dialogue with the government, compared to 46% of completed impact evaluations not initiated by private or government clients. In terms of DIME-specific impacts, 100% of government and implementing agency partners on DIME IEs report that the IE has improved M&E, 89% report that the IE has improved program design, 68% report that the IE has led to the adoption of a new delivery mechanism, and 58% report that the IE led the project to scale up or scale down. DIME IEs involve a hands on approach to government engagement and collaboration, working directly with the implementing partner from design through implementation. This approach is likely to be a reason for such effective engagements on DIME IEs, even beyond the impacts seen in the IEG study.
[note] Independent Evaluation Group (2012) “World Bank Group Impact Evaluations: Relevance and Effectiveness”

The resulting impact is expected to be improved development effectiveness of investments in transport infrastructure, contributing to faster, fairer and more inclusive economic development, and poverty reduction. Under the most ambitious scenarios for the programme, this could be through connecting remote areas to the global economy, creating new trade corridors, or permitting the development of bigger, denser, more productive, safer and cleaner cities.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)

The outcomes and outcome indicators for ieConnect are:

Improved awareness, demand for and use of transport evidence in decision making
  1. Proportion of transport project teams participating in ieConnect workshops that improve their knowledge of impact evaluation techniques.
  2. Proportion of transport impact evaluations with multi-arm evaluation designs to test project innovations.
  3. Proportion of impact evaluations that influence transport project during design or implementation.
  4. Proportion of completed transport impact evaluations that generate evidence used to support project adoption, scale-up, scale-down, continuation or cancelation decisions.

1. Improved effectiveness and impact of new and existing transport interventions from DFID, MDBs and the wider community
  1. Proportion of transport impact evaluations that have influenced the design or implementation of other transport projects outside of the IE itself
  2. Proportion of completed and published transport impact evaluations that are cited in the academic literature
  3. Downloads of ieConnect research working papers

ieConnect is undertaking impact evaluations on large transport projects across multilateral development banks (MDBs), DFID and other bilaterals. The ieConnect for Impact programme is helping to shape and improve over £5 billion in transport investments.

It is early to assess at outcome level, however there is some progress as detailed below. Initial indications are that the programme is on track to contribute to the expected outcomes and impact.

There is demand from non-WB partners for engagement in the ieConnect programme. However, there are constraints on access to M+E funding, particularly non-WB funded projects. The majority of transport projects have an M+E budget, however for projects already under implementation many have already allocated their M+E budget which then precludes engagement with ieConnect due to lack of available project budget for the data collection.

DFID Country Offices have responded positively to the opportunities within ieConnect. However, budgets for funding the planned IE have been problematic to identify. This has meant that DFID-ieConnect collaborations had in some cases not been able to move forward even in the case of mutual eagerness to collaborate on a project IE. The £4.75million costed extension approved in 2018, and signed with the WB in 2019, has increased the proportion of DFID and non-WB transport projects, examples include:
- Constructing Africa’s Cities: Measuring and Enhancing Construction Worker Welfare in Dakar with AfDB, IsDB, French Treasury, AFD, European Investment Bank, and Senegalese Government
- Measuring and Enhancing Mobility in Dakar with AfDB, IsDB, French Treasury, AFD, European Investment Bank, and Senegalese Government
- Hawassa Industrial Park Community Impact Evaluation with DFID Ethiopia
- Understanding the Impacts of Central Asia Regional Economic Co-operation (CAREC) Corridor Investments in Pakistan with DFID Pakistan and ADB
- Matching Youth to Jobs: A Randomized Controlled Experiment in South Africa with the NGO Harambee
- Street Police Patrols and Violence Against Women in Public Spaces: Experimental Evidence from India with the Hyderabad City Police
- smarTTrans: Road Safety in Kenya with the Kenya National Transport and Safety Authority

Without the additional funding these projects were either at risk of dropping due to lack of committed funds or would not have been able to join the programme. Ongoing in 2019, further engagements are under development including with the DFID-Nepal office and GIZ in Liberia. ieConnect is deepening some existing engagements by exploring additional impact evaluations.

Action: the increased non-WB IEs has been reflected in the logframe milestone 2.4 as an increase from 20% to 25% (by 2021) Spend on non-WB IEs or co-funded IEs where WB contribution <=25%) and the number of pilot data systems to 3. Given that all additional IEs funded under the costed extension will be on non-World Bank funded transport projects and those IEs may have up to £500k per IE, on reflection DFID questions whether 25% is a stretching target. DFID will review and agree with ieConnect a stretching target for non-World Bank funded transport projects.

Over the past year DFID has substantially increased our work and thinking on climate adaptation and mitigation. Transport and energy are key parts of this agenda. Over the next six months DFID and ieConnect will work together to explore possibilities for an energy and / or climate change theme within ieConnect.

Action : develop thinking on a possible additional theme of energy and / or climate change within ieConnect.

Explain major changes to the logframe in the past year (1/2 page)

The logframe has been recently updated and the revised logframe is effective from March 2019 so will be used in the next Annual Review. It does not have an impact on this Annual Review period.

Describe any planned changes to the logframe as a result of this review (1/2 page)

The changes to the logframe are effective from the beginning of the next Annual Review. They take into account the costed extension (e.g. addition of the theme on rural roads) and the focus from DFID’s Evidence Department on DFID’s burden share of DIME’s costs. We have worked with EvD to ensure we have the same definition of burden share and are consistent in our messaging.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year (1 page)

The main drivers of direct cost for this project are related to the staff costs of the core research team and those carrying out the impact evaluations. Approximately one third of the direct costs relate to the Core research team at the World Bank and one third for the specific staff recruited to undertake the impact evaluations. The staffing is managed by the World Bank using their internal systems, as per the standard agreement between DFID and the World Bank.

The ieConnect original budget does not pay for the total IE costs, it pays for about $175 000 per IE. For example, the data collection budget is typically sourced from partner or transport project costs. The ieConnect budget runs the ieConnect team, identifies and designs each of the IEs, manages and leads the IE project teams and the IE project implementation from start to finish, assures quality of the IEs, leverages project financing for data collection, and brings together learning across the themes so that the sum of all the transport IEs adds up to more than their parts.

That said the costed extension may fund up to £500 000 per non-World Bank funded IE in an effort to increase IEs outside of the WB and may contribute to the data collection or other associated costs of the IE. An IE can vary significantly in cost, on large transport programmes an IE could cost in the region of $1.5 million. Whether the IE is on a WB or non-WB funded project the funding for the IE data collection, in the majority of cases, comes from the project or partner funds. This constitutes a substantial portion of the budget for an IE.

The £7.5million ieConnect funding from DFID is evaluating transport projects cumulatively totaling about £5 billion, and it is set to increase with the costed extension. The budget allocation, cross-cutting themes and milestones with in ieConnect ensure DFID funding is focused on equity through targets on girls and women and LICs / LMICs.

The design of the ieConnect project provides a more efficient project to undertake IE in the sector as ieConnect draw on the evaluation skills of the larger DIME project, staff and learning to feed into the ieConnect project.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)

The business case outlined the difficulties in producing a fully detailed cost benefit analysis for the intervention and therefore the main benefits were based on the strong evidence that we would be able to identify the correct decisions, reach clear conclusions, and that the findings would have traction with decision makers and the results from logframe target 2 suggest the project is on track to meet deliver this objective.

In a financial sense we believe that the project represents value for money. The investment is enabling evaluation of at least £5 billion in transport investments to date. The evidence generated by the programme could lead to the recovery of the £12.25million invested by DFID through improvements in the rate of return of these large investments. Additionally, ieConnect are working hard to raise counterparts’ funds and ensure that DFID’s contribution has attracted significant additional resources for impact evaluations in transport. More broadly, we expect these innovative evaluations to expand the small existing evidence base on the broader impact of transport programmes, potentially leading to large gains from better prioritisation and design of future transport investments.

E: RISK (½ to 1 page)

Overview of programme risk (noting the rating from p.1) and mitigation

Overall risk rating: Moderate
The risk rating is unchanged from the Business Case.

Overview of programme risk
Risks for the main i2i or DIME project funded by DFID are set out in the detailed risks appraisal in the original Business Case produced by Evaluation Department. These are monitored annually and the risks appraisal updated in the Department’s delivery plan for i2i. Those risks apply generally to the ieConnect project.

The ieConnect project has remained at an overall risk rating of moderate since approval of the business case, when 10 risk areas were identified. All residual risks are judged to be minor-moderate likelihood and impact following mitigation.

The main risk areas of concern (moderate after mitigation) remain as identified at the time of the last annual review. These are:

D2 (Type Delivery) Activities are not approved in time
D3 (Type Delivery) DIME and DFID actively manage the pipeline activities and meet regularly to identify issues quickly
O1 (Type Operational) Security issues in partner countries limits access and delay deliverables Operational
O2 (Type Operational) Rigorous approaches to transport impact evaluation are not identified Operational

The overall risk rating remains appropriate as moderate.

The risk register is a working document and this has been reviewed regularly over the course of the year. It is reviewed at the quarterly DFID-ieConnect management meetings. The risks, mitigation strategies and risk owners are clearly articulated in the risk register.

DIME is committed to follow World Bank safety and security protocols, which puts the team in the position to meet the international standards for research ethic protocols. Nevertheless, two new risk areas should be added to the register.

Type – Safeguards.	“Research providers associating with national partners do not implement appropriate and fair labour standards” is rated as possible with a major impact. The mitigation ensures that ieConnect teams verify that downstream partners apply fair labour standards enforced via contracts issued. The initial residual risk rating is moderate.

Type – Safeguards. “ieConnect consultants and research suppliers are not aware of how to report any concerns regarding policy violations and these go unreported” is rated as possible with a major impact. Mitigation will ensure that all reporting and whistleblowing procedures are available in downstream contracts. The initial residual risk rating is moderate.

Additionally, risks to the IeConnect project fall under the Intellectual/Innovation themes and although none of these were identified as likely to occur their impact is deemed as potentially major. These include intellectual property rights. ieConnect do, when necessary, sign MoUs with Government partners with regard to sharing and publishing data. Due to the nature of these risks the mitigating steps are only able to lessen the impact slightly and we will continue to closely monitor these and escalate any major issues to be resolved through the wider i2i governance mechanisms.

Another risk is the identification and securing of non-DFID funding in order to keep the DFID burden share to <40%. Prior to the costed extension, DFID’s burden share was estimated as 34%. The costed extension provides a higher level of funding per project, the ieConnect programme appears on target for <45% DFID burden share in 2019 reducing to <40% in 2020 and 2021. The WB is actively seeking other core funding and we expect this to become easier as worked-up concept notes are finalised. This will continue to be monitored in quarterly meetings and is consistent with the push and agreement from EvU on i2i / DIME. DFID will continue to introduce ieConnect to possible other funders or donors.

Historically, there has been a 20-30% failure rate in the i2i portfolio for reasons outside of the programme’s control, such as a change of administrations, failed projects and political instability. Failure rates are higher on transport IEs because of the complexity and scale of projects, lack of available data, and having a large percent of non-Bank projects. Furthermore, projects with other MDBs and bilateral organisations introduce different types of risk into the research portfolio, since they are dependent on projects outside of the World Bank’s control. To address failure rates, the programme is preparing and approving a larger number of total IEs, especially in higher risk investments areas such as corridors.

Delays in implementation on transport investments may cause delays on the IEs as well. If this is the case, a time extension for the programme may be required.

Finally, an additional risk to note is the exchange rate fluctuations between GBP and USD. The programme will continue to monitor this.

Outstanding actions from risk assessment
None.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial, and financial issues (1-2 pages)

Overall the progress against the logframe indicators is above the expectations as noted in the earlier sections of this report.

The World Bank has clear financial management and procurement policies in place and the programme follows all relevant policies. These policies have been agreed centrally with DFID.

The World Bank programme team sends DFID bi-annual financial reports as agreed upon at the start of the programme. They also respond promptly to the additional requests for information from DFID. To this point the funding disbursements to the programme from DFID have been made on schedule which we would expect as the programme is delivering on track.

Overall timescales are long for large IEs and uptake of evidence. This is why the project was designed as five year programme of research and the timeframes will continue to be monitored over the coming year to ensure accuracy in the initial planning and also maximum value for money.

The World Bank programme team meet DFID staff on a quarterly basis to discuss progress against the programme timeline, review finances and discuss any issues or concerns. There is also the flexibility to have additional meetings if required to discuss any urgent issues. Both parties have found the meetings to be useful in contributing to a strong working relationship.

As a World Bank Trust Fund this programme is included in the Single Audit of all World Bank trust funds. No issues regarding this programme were highlighted in the last Single Audit.

Date of last narrative financial report(s)	April 2019
Date of last audited annual statement (s)	September 2019

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring (1/2 page)

As mentioned above the project is within the DIME unit which is supported by the DFID Evaluation Unit through the Impact Evaluation to Impact Development (i2i) project. There has been close working between the DFID staff on these projects to ensure consistency of approach and to monitor progress.

The governance structure of this project aligns with that of the Impact Evaluation to Impact Development (i2i) project and there is a clearly defined route to raise and manage issues should they arise. The Growth Research Team (GRT) has quarterly meetings with the ieConnect team and meets at least annually face to face in Washington or London.

Evidence (1/2 page)

The project is an exciting one. It is ambitious and innovative. If successful it will have significant impact in the evaluated projects but more importantly across the transport sector globally. This is with the assumption that the IEs are undertaken with a wide range of collaborating organisations, that the results are broadly disseminated, that tools are made open and available, and that data collected is comparable across projects.

Examples of evidence and findings from ieConnect IEs:

1. In Rwanda, feeder road rehabilitation increases household income by 23.4%. Prior to the road rehabilitation, households living in remote villages have, on average, household incomes that are 23.1% less than households living in more connected villages. This means that the road rehabilitation results in a full catch-up of lagging households.
2. In Dar es Salaam, Tanzania, when comparing households near the BRT (<1km) with those near the planned, but not yet constructed, BRT phase 2 (<1km), there is a statistically significant decrease in travel time to work, no change in the travel cost, an increase in commuter satisfaction, and a modal switch out of informal transport and out of private vehicles.  These are early indications of the benefits of new public transit access on households and the environment.
3. In Ethiopia, within 5km of the expressway, there’s a 5% increase in night light luminosity, a proxy for GDP, and a 3% increase in land classified as urban vis-à-vis a 1% baseline. These are early indications of the changing spatial development patterns, such as how economic activity increases around a newly constructed highway and how it spills over to other areas.

Learning (1/2 page)

ieConnect can have substantial impact at project level and this in itself is impressive with a cumulative transport project portfolio of over £5 billion.

However, the greatest impact of ieConnect will be if:

1. ieConnect can broaden its reach and focus from World Bank dominated IEs to RDBs, partner Governments and Bilaterals. This will start the shift in culture within other organisations. One part of this is for ieConnect to prioritise non-World Bank international events e.g. ADB transport week, UN 3rd Ministerial Conference on Road Safety and World Road Congress (latter 16 000+ participants and over 40 Ministers)
2. ieConnect can also increase its reach through pilot data systems that have the potential to scale across projects, countries and donors. This could have a transformational impact in the field.
3. ieConnect continues to build a strong and rigorous body of evidence on questions about transport, highlighting these in policy and academic fora, and specifically designing IEs that enable large data sets and evidence to be collected across IEs on a select number of indicators and measures of relevance to the international debate and SDGs.

Progress on recommendations from previous reviews (1/2 page)

Recommendations for 2017 AR. Three are complete, two ‘progress made and continuing’ and two ongoing. Those not complete are repeated in the summary section for ease of refence:

COMPLETE: DFID is keen to see ieConnect expand its non-WB work. There are a number of barriers to this. Specifically on a few non-WB planned IEs there have been delays due to:
-	significant sensitivities over perceptions of the WB evaluating another organisation’s project
-	lack of budget within the respective projects
-	lack of an IE culture within some organisations
This AR recommends the development of a BC Addendum to submit a costed extension for approval in the coming months. The main focus of this Addendum would be to ensure a catalytic budget was available for financing the project data collection within non-WB IE.

COMPLETE: The WB’s Internal Evaluation Group (IEG) found that limited active engagement of client or partner government counterparts in the initiation, design, analysis and review of impact evaluations undermines the influence of evidence in decision making and dialogue. For example, 83% of completed impact evaluations initiated by the client influenced policy dialogue with the government, compared to 46% of completed impact evaluations not initiated by private or government clients. The ieConnect programme works with client or partner governments from the start of each impact evaluation project. The IEG results lend additional evidence to what is already the foundation of the way that DIME and the ieConnect program operate. Additionally, in DIME’s own policy influence survey they found that that projects take at least four decisions based on the data and evidence generated by the IE. ieConnect
will report back to DFID at the next quarterly meeting on the number of client or partner initiated IEs and we will agree whether this should be formally measured within the logframe as a target. Note: agreed we would not require an additional indicator for this given this is the overall model used by ieConnect.

COMPLETE (and continuing): EvD and GRT have quarterly meetings with DIME. A short progress report (covering ieConnect and i2i) is to be prepared as an update prior to these quarterly meetings. The programme also prepares two budget updates per year as part of payment requests, including recent activities and planned activities for the next 6 months.

PROGRESS MADE AND CONTINUING: ieConnect to make recommendations of practical ways to work in the medium term with the Sustainable Mobility for All (SuM4ALL) initiative on indicators and measurement frameworks. ieConnect will suggest ways to integrate the goals of SuM4All with project-level indicators associated with transport interventions from the World Bank. DFID and ieConnect will discuss opportunities to encourage MDB alignment of key transport indicators with the global objectives and targets. DFID is the founding donor to SuM4ALL and sits on the Steering Committee (SC). Action: ieConnect to report back at next quarterly meeting

PROGRESS MADE AND CONTINUING: In order to achieve the longer term expected benefits of informing the design of a wide range of transport projects it is important that the findings of the impact evaluations are transferable between contexts and interventions. This is only likely to be the case if ieConnect is successful in conducting a sufficient number and – importantly - range of evaluations to build a body of evidence of how results vary across projects. Achieving a high degree of external validity is dependent on running similar interventions in multiple contexts; the scale of current DFID support is unlikely to be sufficient to achieve this, but strategic coordination of IEs that are conducted is expected to go some way to addressing this.

ONGOING: ieConnect and DFID will discuss possibilities for how ieConnect might engage in dialogue on possible medium term changes across MDBs to move towards a more consistent collection of data across MDB financed projects in order to allow comparison and utilisation of larger data sets for the benefit of the global transport sector. This may also feed into SDG indicator and DAC OECD coding discussions. DFID and ieConnect will agree a way forwards on this issue.

ONGOING: One of the ways to ensure increased engagement of MDBs (particularly Regional Development Banks (RDBs)) is to invite a representative onto the DIME Steering Committee. ieConnect, in agreement with DFID, will discuss MDB representation on the DIME Steering Committee with ieConnect inviting an appropriately senior representative. One possibility could be a specific MDB that works in geographical areas of interest to DFID (e.g. AfDB or ADB). Action: discussion at next quarterly meeting with agreement on next steps and appointment by end August 2019

Annex 1