Gavi 5.0 Annual Review 2022 (conducted October 2023)

Title: UK Investment in Gavi, the Vaccine Alliance (2021-2025)
Programme Value £ (full life): £1.06 billion		Review date: October 2023 (covering 2022)
Programme Code: 300871	AMP start date: 1 April 2021	AMP end date: 31 March 2026
[note] FCDO also contribute to Gavi through commitments to the International Finance Facility for Immunisation (IFFIm). Gavi will receive approximately £590m in proceeds from these commitments 2021-25, bringing the total contribution to £1.65bn (2021-25).

Summary of Programme Performance
Year	2021	2022	2023	2024	2025
Overall Output Score	A	A
Risk Rating	Major	Major

DevTracker Link to Business Case:	Link
DevTracker Link to results framework:	[to be completed by FCDO once uploaded]

A. SUMMARY AND OVERVIEW

Description of programme

Gavi, the Vaccine Alliance, is a global health partnership that brings together national governments, vaccine manufacturers, non-governmental organisations, multilaterals, the Bill and Melinda Gates Foundation and the private sector. Its purpose is to increase access to immunisation in lower income countries and introduce new and underused vaccines in these settings. Since 2000, the Gavi Alliance has contributed to the routine immunisation of over 1 billion children, delivered over 1.8 billion vaccinations through preventative campaigns, and helped to prevent more than 17.3 million future deaths from illnesses such as hepatitis, pneumonia, measles, meningitis, rubella, and yellow fever. In purchasing vaccines for over 50% of the world’s birth cohort, Gavi has a unique ability to influence the vaccine market and achieve access to vaccines at scale in lower income countries.

Gavi’s operating model is designed to support countries to scale up their financing of routine immunisation programmes over time, until a country is fully self-financing, through an eligibility, co-financing and transition policy. Once countries achieve a defined Gross national income (GNI) per capita threshold, they begin a process of transition away from Gavi support until they become fully self-financing. Gavi also provides targeted and time-limited support to transitioned countries to help them sustain high levels of immunisation coverage.

This Annual Review covers Gavi’s second year (2022) of its fifth strategic period, 2021-2025, of the core mission known as “Gavi 5.1”. In 2020 and 2021, routine immunisation was significantly impacted by the pandemic and countries experienced backsliding after two decades of progress. Operationalisation of the Vaccine Investment Strategy (VIS) 2018 new vaccine programmes was also put on pause. Given the effects of the pandemic, in December 2022, the Gavi Board approved an evolution of the 5.0 programme strategy to Gavi 5.1, which renews focus on routine immunisation and reaching zero-dose children, new vaccine introductions, a strengthened Alliance role in outbreak and pandemic preparedness and response, alongside continued COVID-19 vaccinations in countries supported by the COVAX Advance Market Commitment (COVAX AMC). This review does not cover the COVAX AMC performance, which is covered in a separate FCDO annual review. It is expected that reporting on COVID-19 immunisation will be incorporated into the core Annual Review for 2023.

The UK is one of six original donors to Gavi and has been a leading donor since Gavi’s inception in 2000, investing in core and innovative financing instruments to progress Gavi’s mission. The UK is an active participant at the Gavi Board, sharing a constituency with Canada and Qatar. The UK/Canada/Qatar constituency also sits on the Audit and Finance Committee (AFC) the Policy and Programme Committee (PPC), and the Market Sensitive Decisions Committee (MSDC). The UK also supports and advises on technical working groups including the Alliance Partnerships and Performance Team (APPT) and the Gavi CEO Search Committee. In June 2020, the UK Government hosted Gavi’s successful replenishment conference, the Global Vaccine Summit, raising over US$8.8 billion of funding for Gavi 5.0. The UK is also a major donor to the COVAX AMC as part of Gavi’s response to the COVID-19 pandemic.

Summary supporting narrative for the overall score in this review

This is the second annual review of Gavi’s fifth strategic period. The overall score for the 2022 review period is A. This is derived from the following output scores:

Output	Score	Definition	Description
1	A	Met expectation	Introduce and scale-up vaccines
2	A	Met expectation	Strengthen health systems to increase equity in immunisation
3	A	Met expectation	Improve sustainability of immunisation programmes
4	A+	Exceeded expectation	Ensure healthy markets for vaccines and related products
5	A	Met expectation	Organisational effectiveness
6	A	Met expectation	Delivery effectiveness

In addition to the above outputs, Gavi exceeded three of its four outcome indicators and narrowly missed a fourth. Vaccinating 133 million (cumulative) unique children through routine immunisation, reducing the number of zero-dose children to 10.2 million in 2022 and unlocking more than US$35.8 billion in (cumulative) economic benefits were all ahead of their annual milestones. Averting more than 2.4 million (cumulative) future deaths was slightly behind the milestone for 2022 of 2.5 million, which was set assuming faster recovery from Covid-19 would occur in 2021. Based on current forecasts, Gavi is on track to meet its commitments for future deaths averted by 2025 and therefore overall, these targets remain on track for the period.

Some key headlines and highlights of Gavi successes in the past year include:

- 68 million more unique children vaccinated, meaning that Gavi has helped immunise more than 1 billion children in 78 countries since being established in 2000 – preventing more than 17.3 million future deaths;
- Routine coverage rebounded in Gavi-supported countries in 2022 after two years of decline, with coverage for the third dose of diphtheria, tetanus and pertussis-containing vaccine (DTP3) in the 57 Gavi-supported countries increasing from 78% in 2021 to 81% in 2022, though still below the pre-pandemic level of 83%. Recovery in a handful of countries drove the overall rebound in routine coverage, although a total of 23 Gavi-supported countries increased routine coverage in 2022;
- The number of zero dose children in Gavi-supported countries decreased to 10.2 million in 2022, representing a 17% decrease from 12.3 million in 2021;
- Breadth of protection (BoP), a measure of the average vaccine coverage, increased from 51% in 2021 to 56% in 2022, an increase which means that BoP with vaccines in the Gavi portfolio is now higher in Gavi-supported countries compared to the rest of the world (53%).
- Gavi supported the national response to the Sudan ebolavirus (SUDV) outbreak in Uganda, assisting with the Ministry of Health’s outbreak response efforts to control SUDV including by supporting a randomised clinical trial to evaluate candidate vaccines as part of these response efforts;
- 3 countries transitioned to fully self-financing in 2022 (India, Nicaragua and Uzbekistan), bringing the total number of countries that have transitioned from Gavi support to 19 by 2022 and reducing the number of countries eligible to receive Gavi co-financing support to 54;
  [note] India benefits from tailored support until 2026 under a specific partnership approved by the Board.
- Countries contributed US$ 162 million through vaccine co-financing in 2022, bringing the cumulative total to US $1.5 billion since the introduction of the co-financing policy in 2008;
- Gavi was recognised as a top performer in the global aid transparency index, the fourth time that Gavi has been placed in the highest-ranking category of Publish What You Fund’s 2022 Aid Transparency index

Overall, 2022 was a pivotal year for Gavi as both the organisation and countries began to emerge from the emergency mode of pandemic response in 2020 and 2021. Routine immunisation coverage in 2022 began to show positive evidence of rebounding in many countries after the disruptions experienced during pandemic, although not yet back to 2019 levels.
Progress has been however characterised by significant variability across countries, with the increase in coverage in 2022 being driven by a few countries including India, Myanmar, Pakistan and Tanzania amongst others. Many low-income countries in particular face continued challenges and have not yet successfully turned the tide on declining routine immunisation coverage levels. More than half of Gavi-supported countries did not experience an increase in routine immunisation coverage in 2022.
Alongside this, there has also been an increase in outbreak-prone diseases such as measles and cholera, with Gavi and Alliance partners supporting 40 vaccination campaigns in response to outbreaks in 2022. The incidence of these outbreaks has also been worsened by climate-related events such as the catastrophic floods in Pakistan and droughts in the Horn of Africa. Restoring routine immunisation services remains a top priority including catching up missed children and reaching missed communities with immunisation.
Major lessons and recommendations for the year ahead

At the time of writing this review, Gavi continues to be in a critical transition period – both as it continues essential immediate work to support country trajectories on recovery from the pandemic, and as efforts intensify towards developing Gavi's next strategy ‘6.0’ for 2026-2030. Tackling these parallel priorities against a backdrop of continued fiscal pressures for both countries and donors, will require careful consideration of trade-offs and prioritisation over the coming months. In reflecting on programme performance in 2022, this review also seeks to draw important lessons as Gavi and its partners consider their future strategic direction.
Gavi must consider transparently for 6.0 the various trade-offs involved with different priorities, from its expansion to other cohorts/target groups in VIS and the impact that will have on its current vaccine coverage, strengthening its contribution to HSS, a revision of the eligibility, co-financing and transition model, and its potential role in regional manufacturing.
- New Recommendation 1: Gavi Alliance to strengthen Technical Assistance to support comprehensive disease control to help countries strengthen RI, to plan, implement and measure timely, quality preventive campaigns, and to support outbreak responses as needed. Gavi along with the Alliance partners should also consider opportunities for more regular and transparent updates for board members on the status of critical outbreak response, for example through ad hoc board update calls. Gavi needs to maintain a sharp focus on catch up of Routine Immunisation including strengthening planning and operations.
- New Recommendation 2: Gavi will need to make decisions on new vaccines in the context of developing its 6.0 strategy. Gavi should work to ensure that introducing any new vaccines at later touch points (age-related) supports long-term sustainability and resilient health systems, whilst minimising the risk of negative impacts on current vaccine coverage including MCV and YF coverage which are already under strain. Following the 2023 un-pausing of 2018 VIS vaccines (MMCV, DTP boosters, HepB birth dose, Rabies & RSV once appropriate product licensed) and the upcoming PPC and Board decisions on VIS 2024 vaccines (HepE, Dengue, Mpox, TB, GBS, Chikungunya, Shigella), the Gavi portfolio could expand both in volume and complexity by 6.0, including through further targeting populations not reached by routine childhood platforms. The opportunity costs of such expansion must be considered transparently. Gavi should ensure that decisions on VIS 2024 are sequenced effectively with Gavi’s 6.0 wider strategy development to leverage opportunities and synergies and mitigate risks associated with a growing vaccine portfolio on Gavi’s overall strategic direction. Gavi should seek to minimise impact on core EPI functions, and ensure trade-offs/opportunities are properly analysed, particularly regarding transition. Gavi should continue to support countries to effectively prioritise, possibly by vaccine, by region or by schedule if there are insufficient resources.
New Recommendation 3: Gavi should focus efforts on ensuring opportunities for greater collaboration on HSS with other GHIs at country level are identified and utilised (such as consolidated approach to health management information system (HMIS) and Public Financial management (PFM) capacity building support, aligning behind a single budget and common HSS metrics) and building on the findings and recommendations of the Future of Global Health Initiatives (FGHI) process in shaping Gavi’s HSS strategy as part of the 6.0 strategy development process.
- New recommendation 4: Gavi should ensure that learnings form the recent experience on country pressures with regards to co-financing requirements are a central part of considerations for the strategy development process for 6.0 and transition approach coordinated with other GHIs/WB. This should include building analysis to inform a long-term strategic view for Gavi’s role on financing routine immunisation for the future.
- New Recommendation 5: Gavi must continue to work in lockstep with the AU and other partners as much as possible in the development of a new African Vaccine Manufacturing Accelerator, recognising the complex landscape and multi-factorial approach that will be needed to support sustainable, increased manufacturing capacity in Africa. Gavi must conduct a robust risk and legal assessment of AVMA and to regularly update the Board through its committees as the design of AVMA progresses.
- New Recommendation 6: As Gavi integrates COVAX operations and staff fully into its core business, Gavi should maximise opportunities to streamline operations and avoid further fragmentation and complexity. Part of this should include efforts to simplify ongoing oversight mechanisms for the COVAX AMC as donor decisions progress on use of unallocated PVP funds.
- New Recommendation 7: Gavi should ensure that the upcoming Protection from Sexual Exploitation, Abuse and Harassment (PSEAH) framework sets out a robust and comprehensive future approach to safeguarding against SEAH. Gavi will respond to the findings of the PSEAH audits with a robust workplan, to be implemented by Q2 2025. The FCDO programme team, with the support of the FCDO safeguarding unit, should continue to support Gavi in these efforts, and to share information on PSEAH language for funding agreements, with a view to being as consistent as possible in our respective expectations and asks of shared partners.
- New Recommendation 8: That Gavi uses the EVOLVE project to establish a new operating model for its 6.0 strategy which minimises the transaction burden for day-to-day grant management processes and simplifies country and partner engagement with Gavi processes. This should include consideration of the opportunities to streamline Gavi funding windows and of a more streamlined overall structure.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

Gavi’s original theory of change is that increased equitable and sustainable use of vaccines will reduce mortality and morbidity from vaccine-preventable diseases. The levers for achieving this are through: introducing and scaling up vaccines; strengthening health systems to increase equity in immunisation coverage; improving the sustainability of immunisation programmes; and ensuring healthy markets for vaccines and related products.

The theory of change is reliant on assumptions that all countries continue to prioritise and maintain immunisation levels, and that transitioned countries can maintain effective levels of routine immunisation. The COVID-19 pandemic created significant economic, health and immunisation disruptions in 2020 and 2021 and had a direct impact on Gavi’s work. Health resources were diverted away from routine immunisation to respond to the pandemic. Fiscal space and political commitment for immunisation declined due to pandemic-related economic downturns. In 2022, there was recovery of routine immunisation coverage in many Gavi-supported countries, suggesting that the original theory of change remains valid, but with dependencies continuing to be impacted by economic constraints.

Impact indicator	Milestone	Progress
Under 5 mortality rate in Gavi eligible countries	2% decrease on baseline	6% decrease on baseline (2021)
Outcome indicator(s)	Milestone	Progress
Future/Additional deaths averted (cumulative number in new strategy period)	2.5 million	>2.4 million
Reduction in number of zero-dose children	10.5 million (17% increase relative to baseline)	10.2 million (13% increase relative to baseline)
Unique children immunised (cumulative number in new strategy period)	122 million	>133 million
Economic benefits unlocked (cumulative amount in new strategy period)	US$ 34 billion	>US$ 35.8 billion

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

In 2021, under-five deaths in Gavi-eligible countries were estimated to have continued to decline to 55.7 deaths per 1,000 live births compared to 59.2 in 2019. (Estimates for 2022 will be available later this year). The 2022 milestone for the number of unique children immunised was exceeded by more than 11 million, putting Gavi well on track for the 2025 target of 300 million children immunised with Gavi support, and the number of zero-dose children was reduced by more than 2 million in one year. On health impact, Gavi was very close to reaching its milestone of 2.5m future deaths averted in 2021-2022 (excluding COVID-19 vaccinations) and is on track towards its commitment to averting 7-8 million future deaths between 2021-2025. Gavi also continues to deliver on economic benefits, with more than US$ 35.8 billion unlocked in economic benefits so far in the 5.0 strategic period, ahead of the 2022 milestone, pointing to the breadth of benefits achieved through immunisation which goes beyond health alone and supports economic development.

Gavi’s performance in 2022 met the target reduction for zero-dose children, showing recovery from pandemic-related disruptions to routine immunisation in 2020 and 2021. High impact countries, which account for 56% of zero-dose children in Gavi-supported countries, saw an increase in DTP3 coverage of 5 percentage points and a reduction in the number of zero-dose children by 23% between 2021 and 2022. This was driven by impressive recovery in India after two years of disruption, and continued improvement in Pakistan, with both countries now reporting coverage above pre-pandemic levels. Coverage in DR Congo, Ethiopia, and Nigeria remained stable in 2022, with WHO/UNICEF Estimates of National Immunization Coverage (WUENIC) noting uncertainty in these estimates due to data quality concerns.
[note] Democratic Republic of the Congo, Ethiopia, India, Nigeria and Pakistan

However, there was a lower recovery trend in the 26 lowest-income countries where DTP3 coverage fell by 1 percentage point in 2022, driven by the Democratic People's Republic of Korea's reduction in coverage from 41% to 0% due to nationwide stockouts.

Activities to address gender-related barriers to immunisation, as described in the business case, remain in focus with countries increasingly identifying key gender-related barriers to address as part of their proposals for health system strengthening (HSS) and equity accelerator funding (EAF). However, the quality of gender-responsive programming remains variable and Gavi is planning to intensify technical support to countries on gender to help address this. Gavi is doubling down in the remainder of the strategic period to continue recovery of routine immunisation.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Gavi’s mandate to restore immunisation, save lives and protect against future outbreaks and pandemics is more important than ever as the world continues rebounding from Covid-19 and building more resilient health systems. As we remain globally offtrack on meeting the SDGs by 2030, Gavi’s contribution remains vital in in providing support to countries’ health systems, healthcare workers and children who have missed out on life-saving vaccinations.

The UK contribution to Gavi is an essential element of our global health and development offer. Gavi’s core mission remains one of the highest impact investments in the FCDO’s global health portfolio and a key pillar of the UK government’s strategy for international development. It is fundamental to the Government’s manifesto commitment to end the preventable deaths of mothers, babies and children. Childhood vaccination in low and middle income countries yield a high rate of economic returns. It remains a global health “best buy” and a key component of long-term social stability.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Milestones and baselines

Outputs 1-4 of the FCDO logframe closely match Gavi’s own measurement framework for the 5.0 period, and 2025 targets for these indicators were set by the Gavi Board in June and December 2021. The Board agreed to set the baseline year for the 5.0 (2021-25) strategy period as 2019, rather than 2020. This was due to the considerable uncertainty around immunisation coverage in 2020, the then-anticipated impact of the pandemic on coverage in 2020, and the expectation that the WHO/UNICEF estimates of immunisation coverage (WUENIC) for 2020 would be revised over subsequent years due to further survey data availability. This meant that 2019 data was a more stable reference point for tracking progress to 2025. The WHO Immunization Agenda 2030 (IA2030) also took this approach. The FCDO logframe has therefore mirrored this approach, and almost all baselines discussed in this annual review were set based on 2019 values.
When vaccine coverage baselines and targets were set in June 2021, it was assumed that vaccine coverage was disrupted in 2020 due to the pandemic (which was confirmed by the WUENIC estimates published in July 2021), and then would return to 2019 levels by 2021 in most Gavi countries, apart from India which was expected to return to 2019 levels by 2022. It is now clear that these early assumptions were an overestimation and global coverage continued to decline in 2021 before starting to rebound in 2022.
Milestones for 2022 take into account the ongoing impacts of the pandemic and therefore do not represent a linear trajectory from 2019 baselines to 2025. Some milestones are lower (i.e. further away from the target) than the baseline figure.

Output Title	Output 1: Introduce and scale-up vaccines
Output number:		1	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
1.1 Breadth of protection: average across all Gavi supported vaccines	+5pp (53%)	Exceeded: 56%
1.2 Reach of routine immunisations: DTP3, MCV2, PCV3 and HPV2 coverage	DTP3: -3pp (80%) / PCV3: +10pp (66%) / MCV2: +9pp (67%) / HPVC: +0pp (7%)	Met on average: / DTP3: 81% [exceeded] / PCV3: 70% [exceeded] / MCV2: 64% [not met] / HPVC: 10% [exceeded]
1.3 Rate of scale-up of new vaccines	PCV3: 90% / Rotac: 90% / MCV2: 90% / YFV: 90%	Met on average: / PCV3: 98% [exceeded] / Rotac: 90% [met] / MCV2: 86% [not met] / YFV: 88% [not met]
1.4 Introductions of Gavi-supported vaccines into routine immunisation	15	Exceeded: 16
1.5 Preventative campaign reach (measles)	50% of previously unvaccinated children vaccinated	Exceeded: 70.2%
1.6 Timely outbreak detection and response	+2.5pp (30%)	Not met: 18%

Briefly describe the output’s activities and provide supporting narrative for the score.

Gavi met or exceeded most of its global milestones on routine immunisation coverage, reach, scale-up, introductions, and equity, meaning that Gavi is largely on target to meet its 5.1 objectives in these core areas. The second dose of measles-containing vaccine (MCV2) and yellow fever vaccine (YFV) were the exceptions to this – although MCV2 performance increased 4 percentage points (pp) for indicator 1.2, for indicator 1.3 performance reduced by -3 pp since last year. Both MCV2 and YFV are vaccines delivered on later delivery schedules, implying that a greater focus is needed to strengthen later delivery touchpoints, especially those that have suffered setbacks during the pandemic. Timely outbreak response (indicator 1.6) was not achieved across the board, the exception being the timely response to the Ebola outbreak. It is clear continued gaps in early detection, prevention, and response require enhanced Alliance support.

Output 1.1: Exceeded. There was notable progress with a steep increase in Breadth of Protection (BoP) during 2022 rising from 51% to 56% in Gavi countries among children vaccinated with Gavi-supported vaccines. This compares to 53% BoP in the rest of the world. The increase was driven by greater coverage of the second dose of inactivated polio vaccine (IPV2), pneumococcal conjugate vaccine (PCV3), second dose of measles-containing vaccine (MCV2), first dose of rubella-containing vaccine (RCV1), last dose in the schedule for rotavirus vaccine (RotaC) and last dose in the schedule for human papillomavirus vaccine (HPV). This builds on better-than-expected BoP results in 2021 and is a positive signal towards the overall target of +16pp by end of 2025 to reach 64%.

Output 1.2: Met on average. Routine coverage showed signs of recovery in Gavi-supported countries in 2022 after two years of decline, with coverage for the third dose of diphtheria, tetanus, and pertussis containing vaccine (DTP3) across 57 Gavi-supported countries increasing on average by 3pp between 2021 and 2022, reaching 81% in 2022. There was however significant variability in recovery rates with the average increase driven in large part by recovery in India, Myanmar, Tanzania, and Pakistan which had suffered some of the greatest backsliding during the pandemic. In total 23 Gavi-supported countries increased routine coverage in 2022. Many countries, particularly low-income countries, are yet to see a recovery in DTP3 coverage levels. Coverage of PCV3 (70%) continued to increase in Gavi-supported countries due to scale-up in India and HPVC (10%) also continued to increase in 2022. The increase in HPVC coverage is primarily due to new introductions, with several countries where HPV had already been introduced showing falling coverage levels. MCV2 coverage fell short of the 2022 milestone of 67% although it has increased 4pp from 60% in 2021 to 64% in 2022, showing year-on-year improvement.

Output 1.3: Met on average. Whilst this indicator acknowledges the greater complexities with scaling and maintaining immunisation at later touchpoints (9 months and second year of life), the outperformance of PCV3 and Rota compared to MCV2 and YFV indicates further focus on later delivery schedules is required going forward. It is hoped that malaria introductions at the same touchpoint could catalyse renewed focus in this area, with knock-on benefits for MCV2 and YFV. While many countries saw recovery of rotavirus vaccine coverage and the indicator meets the milestone overall, due to severe rotavirus vaccine supply disruptions in seven countries (Cameroon, Kenya, Senegal, Sudan, Tanzania, Zambia, and Zimbabwe) the performance of RotaC in this indicator declined by 7pp in 2022 compared to 2021.
[note] Noting that historical time series are updated annually with WUENIC data (including retrospective revisions). Output 1.3 was reported as 97% in 2021 and reduced down to 96% in line with WUENIC 2022 release.

Output 1.4: Exceeded. In 2022 16 new routine vaccine introductions occurred across 7 vaccines: Yellow Fever (Uganda), TCV (Nepal), Rota (Nigeria), PCV (Tajikistan), MR (Pakistan and Uganda), MCV2 (Chad, Guinea-Bissau, Guinea, and DR Congo), MenA (Benin), and HPV (Lesotho, Burkina Faso, Sierra Leone, Kyrgyzstan, and Eritrea). This reflects an increase in introductions from last year’s 13 introductions indicating progress towards the total target of 82 introductions during Gavi 5.1 strategic period. The successful introduction of HPV in five countries – despite the pandemic – is encouraging however there is work to do on supporting countries to maintain HPV coverage levels and sustainability towards the global cervical cancer elimination agenda.

Output 1.5: Exceeded. 14 countries conducted M/MR preventative campaigns in 2022, a significant increase on the 7 campaigns conducted in 2021. To date however only 7 of the 14 countries have conducted Post Campaign Coverage Surveys (PCCS) with a subset of 3 of those including reporting against this indicator (Niger – 92%, Madagascar – 29% and Syria DAM – 67%) leading to the weighted average of 70.2% estimated campaign coverage among measles zero-dose children. An RFP to outsource PCCSs in several pilot countries is underway which is hoped will help support greater and more timely visibility into the impact of campaigns. Campaigns in 2022 have also highlighted important lessons learned including in Afghanistan where an integrated measles/OPV campaign was launched in November 2022 through a fast-track application achieving 84% coverage with measles vaccines.

Output 1.6: Not met. 2022 saw an increased number of outbreaks requiring implementation of outbreak response vaccination campaigns in Gavi-supported countries with a total of 40 outbreaks in 2022 compared to 12 in 2021, driven by cholera. Timely outbreak response performance declined from 28% to 18% highlighting continued gaps. In 2022, outbreak detection and response for yellow fever and cholera was complicated by the fact that outbreaks occurred in countries and areas where the diseases had not been detected for years, if ever, and detection and response to unfamiliar diseases can be additionally challenging. Diagnostic support approved by the Board aims to provide countries with innovative tools to enable faster, evidence-based outbreak detection.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
Gavi continues to deliver value for money in challenging circumstances, meeting or exceeding its milestones for most of this output. This is demonstrated by performance on routine vaccine coverage which, despite the pandemic, increased 3pp in Gavi-supported countries in 2022, with nearly half of countries reporting coverage at or above pre-pandemic levels. By supporting countries to introduce, maintain, and recover delivery of cost-effective core and novel vaccines, Gavi enables wider economic and social benefits. For example, a study covering the 73 Gavi-supported countries shows that, for every US$ 1 spent on immunisation in the 2021–2030 period, US$ 21 are saved in health care costs, lost wages and lost productivity due to illness and death. Gavi’s work to support 16 new routine introductions in 2022, including 5 introductions of HPV, have the potential to prevent further morbidity and mortality in the coming years.
[note] Sim S.Y., Watts E., Constenla D., Brenzel L., Patenaude B.N. Return On Investment From Immunization Against 10 Pathogens In 94 Low- And Middle-Income Countries, 2011–30. Health Affairs, 2020

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes in the past year, though noting that COVAX integration is on-going and future reporting could include progress on Covid-19 indicator(s).

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
- New Recommendation 1: Gavi Alliance to strengthen Technical Assistance to support comprehensive disease control to help countries strengthen RI, to plan, implement and measure timely, quality preventive campaigns, and to support outbreak responses as needed. Gavi along with the Alliance partners should also consider opportunities for more regular and transparent updates for board members on the status of critical outbreak response, for example through ad hoc board update calls. Gavi needs to maintain a sharp focus on catch up of Routine Immunisation including strengthening planning and operations.
- New Recommendation 2: Gavi will need to make decisions on new vaccines in the context of developing its 6.0 strategy. Gavi should work to ensure that introducing any new vaccines at later touch points (age-related) supports long-term sustainability and resilient health systems, whilst minimising the risk of negative impacts on current vaccine coverage including MCV and YF coverage which are already under strain. Following the 2023 un-pausing of 2018 VIS vaccines (MMCV, DTP boosters, HepB birth dose, Rabies & RSV once appropriate product licensed) and the upcoming PPC and Board decisions on VIS 2024 vaccines (HepE, Dengue, Mpox, TB, GBS, Chikungunya, Shigella), the Gavi portfolio could expand both in volume and complexity by 6.0, including through further targeting populations not reached by routine childhood platforms. The opportunity costs of such expansion must be considered transparently. Gavi should ensure that decisions on VIS 2024 are sequenced effectively with Gavi’s 6.0 wider strategy development to leverage opportunities and synergies and mitigate risks associated with a growing vaccine portfolio on Gavi’s overall strategic direction. Gavi should seek to minimise impact on core EPI functions, and ensure trade-offs/opportunities are properly analysed, particularly regarding transition. Gavi should continue to support countries to effectively prioritise, possibly by vaccine, by region or by schedule if there are insufficient resources.

Output Title	Output 2: Strengthen health systems to increase equity in immunisation
Output number:		2	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
2.1 Geographic equity	-2pp (65%)	Not met: 62%
2.2 DTP drop-out in Gavi57	+1pp (7%)	Exceeded: 6%
2.3 Coverage of first dose of DTP vaccine (DTP1)	-2pp (86%)	Met: 86%
2.4 MCV1 coverage in Gavi57	-2pp (79%)	Met: 79%
2.5 Composite EVM score	+0.5pp (73%)	Exceeded: +0.8pp (73.3%)
2.6 % of HSS and Equity Accelerator Fund (EAF) grant applications including interventions to address gender-related barriers to immunisation	40%	Exceeded: 67%

Briefly describe the output’s activities, and provide supporting narrative for the score.
Although DTP1 coverage continues to lag below pre-pandemic levels due to population growth, particularly in Africa, more children received DTP1 immunisation in Gavi-supported countries in 2022 than ever before and there has been considerable recovery following backsliding due to the pandemic. To achieve higher levels of coverage and introduce and scale new vaccines, country health systems need to increase their delivery capacity year after year, furthermore, to improve higher levels of coverage Gavi should consider the evidence produced from the vaccine confidence project to increase uptake of vaccines and EPI programmes. Accelerated efforts in 2022 following a slowed rate of applications during the pandemic means that 2023 is now on track to be a record year for approved HSS and EAF applications. While the outlook for output 2 is positive and performance has improved over 2021 levels, there remain areas for continued focus and attention including on routine immunisation coverage and routine coverage of measles which is still not at sufficient levels to achieve herd immunity and prevent outbreaks (95% coverage required with two doses).
[note] Between 2019 and 2022, the birth cohort of Gavi-supported countries in Africa grew by more than 1.7m (5% increase).
Output 2.1: Not Met. On average DTP3 coverage in the lowest performing districts in Gavi-supported countries stagnated in 2022 at 62%. While DTP3 coverage among Gavi-supported countries increased on average at a national level in 2022 (as described in Output 1.2), data at the subnational level (which tends to have more variable data quality) suggest that the most marginalised communities in some countries continue to feel sustained impact from the pandemic.
Output 2.2: Exceeded. The DTP drop-out rate from the first dose to the third dose of DTP-containing vaccine in Gavi57 exceeded the milestone and decreased by 1pp to reach 6% in 2022. This reduction in the drop-out rate brings the rate back to 2019 levels. The reduction is a promising sign of country efforts to improve capacity of health systems to deliver a full course of vaccines to children.
Output 2.3: Met. Coverage of the first dose of diphtheria, tetanus, and pertussis containing vaccine (DTP1) in Gavi-supported countries increased by 2pp (84% to 86%) between 2021 and 2022. The number of zero-dose children in Gavi-supported countries has decreased to 10.2m in 2022, down 17% from 12.3m in 2021. Despite this strong progress the number of zero-dose children is still higher than the estimated value of 9.0m in 2019. Performance was variable across Gavi’s country segments with high impact and fragile/conflict countries improving more than countries within Gavi’s core segment.
Output 2.4: Met. Coverage of the first dose of measles-containing vaccine (MCV1) in Gavi-supported countries increased by 2pp (77% to 79%) between 2021 and 2022. While 25 Gavi-supported countries increased MCV1 coverage from 2021 to 2022, immunity gaps and growing outbreaks remain a concern. In 2022, 15.8 million children in Gavi-supported countries were missing the first dose of measles vaccine.
Output 2.5: Exceeded. This indicator measures improvements in supply chain and vaccine delivery chain performance across countries. The Composite Effective Vaccine Management (EVM) score reflects the efforts of the Gavi Secretariat and Alliance partners within the Immunisation Supply Chain Steering Committee (iSC2) to support countries to improve the performance of their immunisation supply chains and ensure that equity and efficiency goals are met. 2021 was the baseline year for Output 2.5 with the composite EVM score for countries that have conducted an EVM assessment (using the EVM1.0 or EVM2.0 framework) at 72.5%. In 2022, the composite EVM score for countries having conducted an EVM assessment was 73.3%, above the milestone of 73%.
[note] Note baseline updated from 72.4% for 2021 based on updated data.
Output 2.6: Exceeded. In 2022, 9 countries applied for HSS and/or EAF grants (Afghanistan, India, Pakistan, South Sudan, Djibouti, Cambodia, Burkina Faso, Comoros, Solomon Islands). Of these 9, 6 countries (67%) included in their applications interventions to address gender-related barriers to immunisation. These interventions include hiring and training of women vaccinators in Pakistan which will both socially and financially empower women, but also ensure that female caregivers are comfortable to attend vaccination sessions.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
VfM compared to the business case proposition remains largely unchanged, though VfM performance on this output must be considered in context of the COVID-19 pandemic (which the business case preceded). The recovery in routine immunisation in 2022 demonstrates the value for money in investing in health systems, with many countries showing rapid recovery from pandemic disruption. At the same time, the number of children susceptible to vaccine-preventable diseases gives a glimpse of the future dangers of vaccine-preventable disease outbreaks which result in higher costs to individuals, households and societies as well as higher rates of disease and death. While the 2022 review shows a picture of health systems recovering, there are still considerable challenges due to population growth and competing demands on limited human and financial resources.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
There are no changes to this output; and none envisioned at this time.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Recommendation 2021	Progress in 2022
Recommendation 1: Gavi should prioritise $400m funding for EAF grants and urgently address bottlenecks in grant delays and country capacity to deliver. Gavi should consider what approaches are needed to help countries complete high-quality grant submissions and timely disbursement with the aim of beginning disbursement for at least half of applications.	In 2022, Gavi continued to socialise and scale-up the zero-dose agenda and access to the Equity Accelerator Fund. In 2022 nine countries applied for EAF support, of which seven were recommended for approval by the Independent Review Committee. Disbursement of EAF support has started for two countries with approvals earlier in 2022, with an average time to disbursement of 6.4 months. To support countries in developing their EAF applications and designing tailored and state of the art interventions to identify and reach zero-dose children, the Secretariat coordinated and deployed technical assistance to more than 20 countries in 2022. Gavi has also initiated a number of learning activities including the launch of zero-dose learning hubs, mapping of pro-equity interventions funded by Gavi. Gavi has also developed 13 evidence briefs on critical zero-dose interventions and 9 case studies to support country learning.
Recommendation 2: For Gavi to make any tangible marked progress on reducing zero-dose, a wider range of delivery partners are urgently required. Gavi should further shift their operational model toward one which is fundamentally based on equity and reach. This includes shifting at least 10% of funding in all new HSS, EAF and TCA grants to CSO organisations as per the Board-approved CSCE approach.	Gavi has centralised the CSO function as a separate country-facing support team to drive the CSO agenda forward. The CSO team is responsible for operationalising the CSCE approach and delivering on the Board mandate relating to CSO allocations. In the past year, Gavi have put in place a streamlined and tailored grant process to enable effective and adapted direct engagement of CSOs, and work is underway to establish a complementary outsourced fund management mechanism to reduce the administrative and grant/contract management burden for Gavi teams as they engage an increased number of CSOs, particularly local CSOs. / In 2022, five countries with applications which were approved by the IRC through the full portfolio planning (FPP) process, adhered to the Board decision of 10% fund allocation to CSOs. Based on the approved funding applications, a total of 29% of combined amounts requested by countries has been allocated to CSOs.

New Recommendation 3: Gavi should focus efforts on ensuring opportunities for greater collaboration on HSS with other GHIs at country level are identified and utilised (such as consolidated approach to health management information system (HMIS) and Public Financial management (PFM) capacity building support, aligning behind a single budget and common HSS metrics) and building on the findings and recommendations of the Future of Global Health Initiatives (FGHI) process in shaping Gavi’s HSS strategy as part of the 6.0 strategy development process.
Output Title	Output 3: Improve sustainability of immunisation programmes
Output number:		3	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
3.1 Percentage of Gavi57 countries meeting their co-financing obligations	100%	Met: 100%
3.2 Number of former-Gavi countries that maintain or increase DTP3 coverage relative to transition year	No decline (8 countries)	Met: 8 countries
3.3 Countries on track for successful transition	70%	Partially met: 50%

Briefly describe the output’s activities, and provide supporting narrative for the score.
While results on the whole are encouraging and illustrate countries’ commitment to prioritising vaccine co-financing in challenging times, deteriorating macro-economic conditions are threatening the capacity of countries to invest in strengthening their immunisation programmes and the COVID-19 pandemic has contributed to a deterioration of vaccine coverage, including in some transitioning countries. World Bank projections suggest that government health spending per capita is expected to stagnate or decline in 65% of Gavi-supported countries compared to pre-pandemic levels. Gavi is actively engaging with countries to mitigate risks of unsuccessful transition, including by supporting the design and implementation of accountability frameworks and transition roadmaps.

Despite the disruption to public finances and health systems caused by the pandemic, most Gavi implementing countries have continued in 2022 to maintain or increase domestic resources for vaccine co-financing. However, it is also important to note that the output does not consider the countries that have their co-financing obligations extended or waivered. In order to get a realistic view of country progress, it is important to look at the full picture which includes countries that have had their co-financing obligations waived.

Output 3.1: Met. Despite difficult macro-economic and fiscal conditions in 2022, including increased debt burden, increased interest rates, and high inflation, only two countries were granted a full waiver (Somalia and Syria) and one a partial waiver (South Sudan, which for the first time in history partially paid for co-financing). The number of waivers was down from nine countries in 2020 and six countries in 2021. Excluding those three countries whose co-financing obligation was waived, 100% of countries fully met their obligation. Overall, 96.5% of 2022 co-financing payments were paid through domestic budgets including domestically generated funds (90.1%) and World Bank borrowing (6.4%).

Output 3.2: Met. The baseline for Output 3.2 was set at eight countries in 2021. Of the 17 former Gavi-eligible countries included in this indicator that can receive support under the Middle-Income Countries (MICs) approach to prevent and mitigate immunisation coverage backsliding, 8 maintained or increased DTP3 coverage in 2022 and 2021 compared to 2019, while 9 did not. Whilst this is the same number as last year, the country composition has adjusted with Ukraine being replaced by Indonesia in the set of countries who maintained or increased DTP3 coverage.
[note] Based on the 17 MICs-eligible countries when this indicator was approved by the Gavi Board in December 2020.

Output 3.3: Partially met. This indicator measures countries’ sustainable transition by measuring the a) co-financing performance, and b) ability to reach and maintain high immunisation coverage. All countries met their co-financing obligations on time. However, of the 10 countries in Accelerated Transition in 2022, only five were able to maintain DTP1 and DTP3 coverage as per the second criterion (b) above. It is important to note though that amongst the other five countries that did not meet the second criterion (Côte d’Ivoire, Djibouti, Lao PDR, Papua New Guinea and Nigeria), all maintained or increased both DTP1 and DTP3 coverage between 2021 and 2022.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

Gavi’s model to ensure country commitment to health and immunisation through co-financing continues to be a key strength. Overall, countries contributed US$ 163 million in 2022, prioritising vaccines co-financing in challenging times, and bringing total co-financing since the introduction of the co-financing policy in 2008 to US$ 1.5 billion. The amount paid increased slightly from US$ 161 million in 2021 and is projected to increase significantly over the coming years as countries progress through their transition pathways. Evidence of this performance is supported by projections that indicate former and current Gavi-supported countries are expected to contribute 39% of the costs of their vaccination programmes over the course of Gavi 5.0, doubling the levels mobilised in Gavi 4.0.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
In June 2022, the Gavi Board approved the implementation of flexibilities for countries in humanitarian crises or severe fiscal distress. This was applied in 2022 to three countries (Somalia, South Sudan and Syria). Subsequently in December 2022, the Gavi Board decided to extend the duration of accelerated transition from five to eight years and to introduce a 35% co-financing threshold for countries moving from preparatory to accelerated transition. This is expected to increase financial sustainability by smoothing yearly co-financing increases faced by countries in accelerated transition.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendation 2021	Progress in 2022
Recommendation 3: In 2022, Gavi should provide an overview and analysis of how co-financing, transition and the MICs objectives apply synergistically across teams, budgets and agendas. This includes addressing the MICs budget underspend, and a root cause analysis of what activities within the extended accelerated transition period (from 5 to 8 years) will be instrumental in sustaining equitable immunisation coverage.	Gavi have begun work on a review responding to this recommendation which is being led by the IF&S and HSIS teams which is due to be published later this year. This is expected to provide a review of experience in previously transitioned countries and develop specific actions to increase the likelihood of successful transition in countries currently in or about to enter accelerated transition. Gavi will also clarify the ‘coherent journey’ for countries as they transition out of Gavi eligibility and into the targeted support provided by the MICs Approach and provide an update on MICs allocations. / Targeted support to address backsliding under the MICs approach has been accelerated with support already been approved for Angola, Bolivia, Honduras and Indonesia. These countries have been prioritized due to the large number of zero-dose children. An application for support from Vietnam is currently scheduled for IRC review as it has continued to experience procurement issues. Ukraine, which has continued to backslide given the humanitarian situation, has been classified as a fragile MIC and is eligible to receive more comprehensive support. Efforts are now being made to support other countries such as Georgia and Azerbaijan that have not yet recovered. / In addition, 3 new vaccine introductions have been supported in MICs, with an additional 3 vaccine introductions in progress before the end of 2023.

New recommendation 4: Gavi should ensure that learnings form the recent experience on country pressures with regards to co-financing requirements are a central part of considerations for the strategy development process for 6.0 and transition approach coordinated with other GHIs/WB. This should include building analysis to inform a long-term strategic view for Gavi’s role on financing routine immunisation for the future.

Output Title	Output 4: Ensure healthy markets for vaccines and related products
Output number:		4	Output Score:	A+
Impact weighting (%):		20	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
4.1 Number of markets exhibiting acceptable supply dynamics	10	Met: 10
4.2 Number of innovative products within the pipeline with commercial-scale manufacturers	Progressive trend towards 2025 target of 8	Exceeded: 9
4.3 Number of vaccine and immunisation-related products with improved characteristics	Progressive trend towards 2025 target of 9	Exceeded: 2

Output 4.1: Met. In 2022, the number of markets exhibiting acceptable levels of healthy market dynamics for vaccines and immunisation products decreased from 11 to ten, still meeting the target for the year. The four vaccines with unacceptable levels of healthy market dynamics are Rotavirus (RV), Human Papillomavirus (HPV), Malaria, and Oral Cholera Vaccine (OCV):
- The Rotavirus market health was downgraded due to production issues impacting all suppliers which resulted in seven countries experiencing severe supply disruption and vaccination interruptions in 2022. Supplier production planning is being closely monitored and Alliance partners are working on supporting countries in optimising their vaccine portfolios.
- The HPV market constraints are driven by a mix of factors resulting in an inability to meet demand including: meeting countries’ product preferences; uncertainties surrounding country adoption of the one-dose schedule; and risk of dose expiry in some countries due to delays in implementation due to COVID-19 pandemic.
- Malaria supply constraints persist with the 18 million doses available in 2023-25 falling short of anticipated country demand. The Alliance has been working on multiple fronts to improve the outlook for the malaria market, including plans for supporting R21 malaria vaccine subject to WHO pre-qualification.
- A rise in Cholera outbreaks created a surge in demand for OCV doses creating a gap in supply for planned preventive campaigns in 2022, resulting in a shortfall of ~18m doses for approved preventive campaigns in 2022, which have been delayed to 2023.

Output 4.2: Exceeded. The number of innovative products within the pipeline of commercial-scale manufacturers increased by 7 in 2022, meeting the 2025 target well in advance of schedule. This was driven by vaccine-microarray patch (MAPs) clinical trials for Measles-Rubella, COVID-19, influenza, and Hepatitis B, as well as the Controlled Temperature Chain (CTC) qualifications of one TCV and one HPV vaccine.
Output 4.3: Exceeded. Innovation-related market shaping indicators are above target for 2022. As part of efforts to scale up innovations, two products with improved characteristics were newly procured for Gavi programmes in 2022: (1) a liquid Rotavirus vaccine, improving ease of delivery for healthcare workers, and (2) a new presentation for Yellow Fever vaccine, upgrading from ampoule to vial presentation, optimising the cold chain footprint.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

This output continues to deliver high value for money. Recent lessons learned from Gavi 5.0 and COVID-19 have led to consideration of continued adjustments to Gavi’s market shaping work, with the Healthy Markets Framework (HMF) and Market Shaping Strategy potentially better reflecting the need for prioritisation of new regional products aligned with Gavi’s regional manufacturing approach. It is envisaged that this approach will continue to support an enabling environment that fosters long-term market health for LMIC markets and will be important in protecting Gavi’s past investments in vaccine programmes through sufficient and uninterrupted supply of appropriate products and prices sustainable for both countries and suppliers.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
To support pillar 2 of the regional manufacturing framework, Alliance partners are reassessing the HMF, used to determine Output 4.1 progress. The HMF was last updated in 2021 to reflect the new strategic priorities of the 2021-2025 Market Shaping Strategy. The update incorporated demand side dynamics into the framework and strengthened the framework’s capacity to assess supply side dynamics and product innovations. As noted above, through the COVID-19 pandemic, Alliance partners recognised the importance of regional diversity of suppliers as a component of healthy markets, and to strengthen Pandemic Prevention, Preparedness and Response (PPPR). The HMF will be further updated to incorporate this healthy market indicator and to inform market strategies accordingly.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
In December 2022, the Gavi Board approved a four pillar strategy to support the African Union (AU) vision of sustainably expanding regional vaccine manufacturing capacity and set the region towards PPPR. The four pillar strategy focuses on 1) sharing market intelligence, 2) inclusion of new African vaccine manufacturing (AVM) into Gavi product menu, 3) demand solidarity from member states under the leadership of the AU and 4) the African Vaccine Manufacturing Accelerator (AVMA) – a financial instrument being designed by Gavi to support new African Vaccine Manufacturers enter the Gavi market and ensure sustainability through providing a top-up that covers their higher production cost, with two major outcomes of supporting a sustainable and substantial production capacity on the continent, and improved pandemic response capacity. The design elements and scenarios for implementation of AVMA are being reviewed, to ensure that the incentive levels are sustainable and relevant to each market, while minimising undesired outcome on the overall health and affordability of the Gavi global market.

New Recommendation 5: Gavi must continue to work in lockstep with the AU and other partners as much as possible in the development of a new African Vaccine Manufacturing Accelerator, recognising the complex landscape and multi-factorial approach that will be needed to support sustainable, increased manufacturing capacity in Africa. Gavi must conduct a robust risk and legal assessment of AVMA and to regularly update the Board through its committees as the design of AVMA progresses.
Output Title	Output 5: Organisational effectiveness (internal)
Output number:		5	Output Score:	A
Impact weighting (%):		10	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
5.1 Operating expense ratio: Operating expenses (total Secretariat costs, evaluations & assessments and AMC fees) as a percentage of total expenditures / Overhead ratio: Overheads (Management, general & fundraising and IFFIm & Gavi campaign) as a percentage of total expenditures	7.5% / 3%	Not met: 7.6% opex (exceeded on a cumulative strategic period basis) / Exceeded: 2.9% overheads (exceeded on a cumulative strategic period basis) / Actual operating expenditure and overhead included within the audited financial statements.
5.2 Resources disbursed as planned according to Board-approved forecasts	19.2%	Not met: 16.2%
5.3 Gavi's centralised evaluations on track as per approved work plan	On track	Met: / Four centralised evaluations were underway in 2022 with a planned delay to the ‘Strat Ops’ evaluation approved by the EAC
5.4 Staff attrition	<19%	Exceeded: 5%
5.5 Average time to hire	<4.5 months (approx. 99 working days)	Exceeded: 84.7 days.

Briefly describe the output’s activities, and provide supporting narrative for the score.

Gavi continued to maintain organisational effectiveness in 2022, delivering core programmes alongside COVAX activities. Overall, the indicators for this output have been met, slightly missing the Operating Expenditure (Opex) indicator although this is still within limits across the overall strategic period. Ongoing efforts on Operational Excellence initiatives, such as Project EVOLVE to achieve grant management transformation, continue to be important steps towards greater organisational effectiveness.

Output 5.1: Not met (opex) and Exceeded (overheads). Absolute Opex was lower than the Board approved budget in 2022 with $128m being spent against a Board approved budget of $166m. The Opex percentage ratio was however over target due to lower denominator, resulting from lower core Programme Disbursements in 2022 as countries continued to recover from the pandemic and efforts focused on minimising excess cash balances held in-country. The overhead ratio exceeded the 2022 target. Over the course of the strategic period, the Opex and Overhead ratio remain within the ratio supported by the board.

While remaining within the limits of the Board approved budgets, Gavi expects to make further investment in Opex during the remainder of the strategic period as it continues to take steps to transform organisational effectiveness. This will include investment in an Operational Excellence Framework with aspirational Opex and strategic workforce goals, ending 2025, that were reviewed and endorsed at the June 2023 Board meeting.

Output 5.2: Not Met. Disbursements to new cash programmes (Equity Accelerator Funding, Middle Income Countries, Strategic Focus Areas) were lower as the pandemic response impacted the operationalisation of new programmes. In 2022, countries prioritised response to COVID-19 and therefore, utilised COVID-19 Delivery Support (CDS), more than HSIS. As countries emerge from the pandemic, there has now been an increased focus on routine programmes and an acceleration in HSIS expenditure in 2023.

Output 5.3: Met. Progress on 4 planned evaluations in 2022 was largely on track.
1. Evaluation of Gavi’s initial response to COVID-19: Progress on track. The final report was submitted in December 2022 and has now been published.
2. Evaluation of the operationalisation of Gavi’s strategy through Gavi’s policies, programmatic guidance and use of funding levers: Progress with planned delay. A delay to the start of the evaluation was approved by the EAC due to the review of Gavi’s funding policies being paused in April 2020, given the newly emerging COVID-19 pandemic. The Funding Policy Review restarted in 2022 and was taken to the Board for decision in June 2022. To ensure utility of the evaluation the start date was postponed to Q4 2023
3. Evaluation of Gavi’s contribution to reaching zero-dose children and missed communities: Progress on track despite some unplanned delays due to an extended inception phase required to enable a new supplier to get up to speed on Gavi and the zero-dose agenda.
4. Mid-term Evaluation of Gavi 5.0 (MTE): Progress on track. The commissioning process was completed in 2022 and the inception phase was completed in Q4 2022.
Output 5.4: Exceeded. Gavi has surpassed its attrition goal of <19%, which is calculated by the ratio of terminations to the average headcount, achieving a rate of 5%. This achievement is a substantial improvement over the previous year figure of 10.8% which is already well within industry benchmarks of 18-19% in the not-for-profit sector. Efforts to strengthen a motivated culture within Gavi which began 2022 have continued into 2023, including the establishment of a culture and wellbeing committee that takes input from ‘affinity group leaders’ to bring together views across the organisation. Gavi have also focused on supporting COVAX staff to find high quality new roles outside of the organisation as COVAX operations have reduced.
Output 5.5: Exceeded. Gavi’s established Hiring Manager Guide continues to be used to equip hiring managers with comprehensive knowledge of Gavi's recruitment policy to be able to strategically plan their recruitment activities. Gavi remains committed to efforts that actively prioritise diversity, fostering a robust gender balance and a concerted focus on attracting and retaining talent from the Global South. Gavi are also now looking to increase their due diligence on new candidates which includes SEAH background checks depending on roles, which will help maintain and ensure a safe working environment.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
Although milestones for outputs 5.1 and 5.2 were not met, these should be interpreted in the context of delivery of the COVAX Facility, which entailed significant disbursements to countries not considered within this annual review. Gavi’s Opex and overhead ratios remain lean with absolute expenditure lower than the Board approved budgets. Expenditure on overheads (output 5.1) remains below 3.0%. Gavi’s lean organisational model ensures good value for donors’ money, with 97% of resources spent on programmatic activities.

At the same time, it is important that Gavi does not prioritise this lean model at the expense of sufficient resourcing to deliver and, under the framework of Operational Excellence, transforms to remain efficient, effective and fit for purpose. The pandemic, which gave rise to the COVAX Facility, and the change required to deliver the Gavi 5.1 strategic objectives (segmented approach, focus at sub-national level) has put pressure on both Gavi staff and partners, and in order for Gavi to continue as an effective organisation, they must be sufficiently staffed, with efficient processes and robust systems to ensure staff wellbeing and capacity to deliver sustainably and cost-effectively for the long term.

It is also important to note that COVAX operating expenditures are counted separately and Gavi has separate financial indicators for COVAX.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Recommendation 2021	Progress in 2022
Recommendation 4: That Gavi consider carrying out first-level supply chain opex mapping to understand downstream spend.	Gavi has internal guidelines on the maximum rate of indirect costs that can be charged on all its downstream contracts (as it does for its cash-based grants to countries). While these guidelines are enforced to ensure a lean operating model, Gavi assesses that it does not currently have the capacity within its existing information systems to consolidate delivery chain opex expenditure downstream. Compiling this data manually would require extensive manual work over a long period of time. / Gavi will therefore explore the possibility of incorporating this as a feature into a new grant management system as part of the development of the target operating model within EVOLVE, Gavi’s grant management transformation project. This is expected to take place mid-2024. As such, the outcome of this consideration and any associated further action will be reported in August/September 2024. At this stage Gavi anticipates that any downstream mapping would likely need to be to be highly differentiated, for example, only on the highest value contracts, rather than consolidating the data comprehensively.
Recommendation 5: That Gavi implement a comprehensive action tracker for evaluations and other reviews across the organisation, with evaluation progress reporting to the EAC	Gavi have taken steps to improve evaluation action tracking over the past year including: / An Evaluation Management Response (EMR) tracker (EMR iTracker), which covers any evaluations completed in the last 5 years with active/open actions, has been implemented / An Annual Evaluation Report which reports consolidated data from this tracker along with other key information on the evaluation function at Gavi has been developed / A thorough desk review/KIIs analysis was undertaken to explore how other organisations approach EMR follow-up and tracking of recommendations/actions. / The results from the review will inform discussions underway with other key Gavi teams to explore options for a comprehensive action tracker to cover other reviews etc beyond Gavi’s centralised evaluations. Gavi’s Balanced Scorecard also includes an indicator to report on implementation of recommendations for both internal and programme audits.

New Recommendation 6: As Gavi integrates COVAX operations and staff fully into its core business, Gavi should maximise opportunities to streamline operations and avoid further fragmentation and complexity. Part of this should include efforts to simplify ongoing oversight mechanisms for the COVAX AMC as donor decisions progress on use of unallocated PVP funds.

Output Title	Output 6: Programmatic delivery effectiveness
Output number:		6	Output Score:	A
Impact weighting (%):		10	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
6.1 Audits on track against AFC-approved plans (both internal and programme) at 80% overall target delivery.	80% target delivery of approved plan: / Internal: 6 / Programme: 12	Met: / Internal: 5 / Programme: 12
6.2 % top risks in the Board-approved Risk & Assurance Report that are within risk appetite	80%	Exceeded: 94%
6.3 % of implementing partner agreement templates that include PSEAH clauses	75%	Met:75%
6.4 Average time between approval and disbursement of programme support	9 months	Met: 8.9 months
6.5 Proportion of funds going through government systems	Progressive trend towards cumulative 55% by 2025	Met: 41%

Output 6.1: Met. Gavi Audit and Investigations team have achieved significant progress in catching up audits from prior years which had been delayed, largely due to the pandemic. As well as completing this backlog alongside internal and programme audit activity, Gavi completed all but one of the audits (PSEAH audit) in the AFC-approved 2022 workplan now having been executed. This indicator is also regularly updated and reported to the Audit and Finance Committee, and in recognition that audits frequently straddle year ends, represents completed audits from the 2022 annual workplan at the time of reporting. Gavi is on track to achieve this end-of-programme target. Focus on recommendation follow-up is showing results, and the corporate Balanced Scorecard presents high level indicators for both secretariat and country recommendation implementation.
Secretariat (Internal) audit have a well-established process with regular reporting to the AFC, at the last report in May 2023 the number of overdue actions had dropped since the last report, and, more significantly, only two high risk actions were overdue, down from 11 at the previous report. Programmatic recommendations present more of a challenge as the responsibilities for implementation lie with country health ministries. However, a renewed focus on following up, which is the responsibility of country support teams, has resulted in the ability to bring metrics on the status of these recommendations to the AFC, which was done for the first time in May 2023, and which is expected to continue on a regular basis. While noting the data need improvement, nearly 70% of the recommendations were at some stage of progress to improve country systems and controls. Gavi Audit and Investigations is working with country support teams to improve the data. Follow-up information is becoming available from audits as the programme audit team revisits countries, which will enrich the status updates. Additional insights and analyses will be presented for the AFC’s consideration as the follow-up process for country-focused recommendations matures.

Output 6.2: Exceeded. This indicator is on track, with 94% of board-approved risks within appetite. In 2022, Gavi’s overall risk profile has changed, with seven top risks increasing and three top risks, mainly related to COVAX, decreasing. Only one top strategic risk related to country management capacity is deemed to be outside of Gavi’s risk appetite. While interventions seem to have contributed to help advance Expanded Programme on Immunisation (EPI) capacities during the pandemic along with support from the Alliance on the ground, countries continue to face challenges. Weak EPI capacity in areas such as leadership, management, coordination, financial management and programme implementation are barriers to programme delivery especially in fragile countries. This is the impact of multi-faceted issues including insufficient human resources, retention challenges and external programme disruptions caused by instability, shocks or political change (such as devolution), natural disasters and more recently – the COVID-19 pandemic and the roll-out of COVID-19 vaccines. The risk that this will affect the Alliance’s ability to reach zero-dose communities is therefore very high and is assessed as outside of Gavi’s risk appetite. To bring this risk within risk appetite, the Secretariat is actively streamlining processes and adapting funding policies to facilitate access to funding and restructuring and simplifying grant management processes through EVOLVE.
In 2022, the Risk function’s capacity was stretched by a vacant temporary position on the COVAX budget which made it difficult to respond to increased demands from the business. Since then, a newly elevated Chief Ethics, Risk and Compliance Officer (CERCO) position has been created, with the new CERCO being onboarded mid-May 2023. The CERCO is accountable for increasing transparency around key risks across the Alliance and the Secretariat, enabling cross-enterprise collaboration to mitigate risks and prioritising resources effectively, and to support management in mitigating strategic, financial, operational and programme risks.

Output 6.3: Met. During the 2022 Review Period, Gavi maintained the inclusion of PSEAH terms in 75% of its templates with implementing partners, meeting the target milestone. Starting in 2023, WHO and Gavi have begun to include new PSEAH terms in their implementing grant agreements, with the goal of updating the Gavi-WHO grant agreement templates to incorporate the changes that have been made on a grant-by-grant basis in 2023.
A new PSEAH Framework is under development and due to be finalised and approved during Q1 2024. It is expected that the framework will introduce Gavi’s approach to protecting children and adults from sexual exploitation, abuse, and harassment and describe how Gavi will transform these commitments into operational practices (prevention, protection, and response). Gavi are also continuing to engage in the FCDO-convened cross-sector safeguarding steering group (CSSG).
Gavi is demonstrating a zero tolerance to inaction on SEAH. The appointment of a new Chief Ethics, Risk and Compliance Officer (CERCO) is also important to the PSEAH agenda. As a member of the Senior Leadership Team and with support of the CEO, the CERCO is leading efforts to drive organisational change and improve Gavi’s policies, training, and communication with partners to protect against SEAH. Gavi is also working on a response to the country and secretariat level PSEAH audits and expects to share an update on key actions and next steps via the AFC.

Output 6.4: Met. This is a new indicator introduced in Gavi 5.0 as part of Gavi’s new programmatic Monitoring and Performance Management (MPM) framework. It includes all applicable funding envelopes: HSS, Equity Accelerator Funds, Vaccine Introduction Grants, Operational Cost grants, and Vaccine Switch grants; and excludes COVID-19 vaccine-related and Targeted Country Assistance funding envelopes. Gavi has met the milestone of 9 months for the average time between approval and disbursement of programme support in 2022, achieving 8.9 months and improving upon the 9.9 months baseline set in 2021. The drivers of this improvement from a monitoring, country data engagement and technology perspective, are the result of improved visibility and routine monitoring of each country application in the MPM dashboard, the CPD country team meetings, as well as CPD and Gavi leadership engagements.
Further improvement in Gavi’s speed of disbursement is anticipated though the EVOLVE project which aims to modernise, simplify and strengthen the core of Gavi’s operations, with streamlined processes, centralised data and an integrated suite of digital solutions. On this basis the target for this indicator (currently set at 9 months) may be revised down to 8 months by the end of the Strategic Period.
Output 6.5: Met. Gavi’s Financial Management and Risk Assurance (FMRA) approach was developed to support government systems while still managing fiduciary risk. Gavi have set a target of reversing the ratio between partner versus direct government disbursement from 71%/29% under Gavi 4.0 to 45%/55% under Gavi 5.0 and to build country ownership. The 2022 actual was slightly lower than expected resulting in a ratio of 59/41 at December 2022, representing a reduction of disbursements to partners by 8% compared to 2021. The reason for the slight reduction is attributed to the rescheduling of planned disbursements due to high cash balances in the transitioned countries.
Gavi is taking a phased approach working with individual countries where there is appetite and ability to progress. The roadmap to reaching the overall targets by 2025 focuses on 14 additional countries divided into 3 cohorts between 2021 and 2024. Of the 14 countries, Cote D’Ivoire, Tanzania, Guinea, Gambia, Benin, Cameroon, Angola and Nigeria have received Capacity Building Support and successfully transitioned to use its country systems. Kenya, Comoros, Lesotho & Congo are also receiving capacity building support and are on track by the end of 2023. In total, 35 countries are partially or fully transitioned countries. To sustain gains, Gavi continues to provide support through continuous investments which supports improvements in financial management as a whole and goes beyond supporting Gavi grants. As part of the roadmap to achieve successful and sustainable transition to use of country systems, various initiatives have been put in place such as:
- Rollout of assurance providers to provide end to end financial management support and assist in the transfer of knowledge to support countries to take on responsibilities in all eligible countries up to the end of the strategic period.
- Increase the number of supreme audit institutions auditing Gavi grants from a current average of 10 to above 33 by the end of the strategic period. This has been achieved through a strategic partnership with Supreme Audit Institution Umbrella bodies i.e. AFROSAI-e and CREFIAF.
- Increase the number of professional accountants trained by professional accounting organisations to support PMUs and improve quality of financial management by the end of the strategic period. This has been achieved through a strategic partnership with International Federation of Accountants with pilots in Ghana & Burkina Faso.
Gavi’s support to countries in this area has depended on increased advocacy and the availability of the Financial Management & Risk Assurance (FMRA) envelope ensuring that countries that are approaching transition have sustainable financial management systems to support their immunisation programmes.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
Gavi’s programme delivery remains effective and efficient, with overall good processes for tracking and monitoring spend and ensuring effective audit response. The EVOLVE project continues to be an important opportunity for continued streamlining and simplification of Gavi’s programme delivery functions. The recovery of the long-standing audit backlog is also a positive step.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

In February 2023, the Gavi Audit and Finance Committee amended the indicator for internal and programme audit plan execution, to simplify it and remove overlaps. The KPI, which has been adjusted for the purposes of this report too, now measures the number of audits for which fieldwork is complete, measured by the date of the exit meeting, as a percentage of the number of audits for which fieldwork was planned to be completed as per the AFC-approved annual plan. The target remains at 80%, as the amendment to the KPI compensates for the previous lag of one quarter.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendation 2021	Progress in 2022
Recommendation 6: That Gavi revisit their template agreement language to include a clause on zero tolerance to instances of PSEAH, and we recommend a timely response to the findings of the PSEAH audit currently underway.	Gavi is conducting a timely response to the PSEAH audit. In response to the FCDO recommendation as well as to the recommendations made in the Gavi audit, the audit is in the final stage of management review and will be released soon. Gavi Legal has updated the Code of Conduct annexed to its template Procurement agreements, including those used with implementing partners, to impose on the contracting party Gavi’s “zero-tolerance” policy with respect to SEAH. Gavi is in the process of negotiating inclusion of zero tolerance language in templates with UN partners.

- New Recommendation 7: Gavi should ensure that the upcoming Protection from Sexual Exploitation, Abuse and Harassment (PSEAH) framework sets out a robust and comprehensive future approach to safeguarding against SEAH. Gavi will respond to the findings of the PSEAH audits with a robust workplan, to be implemented by Q2 2025. The FCDO programme team, with the support of the FCDO safeguarding unit, should continue to support Gavi in these efforts, and to share information on PSEAH language for funding agreements, with a view to being as consistent as possible in our respective expectations and asks of shared partners.
- New Recommendation 8: That Gavi uses the EVOLVE project to establish a new operating model for its 6.0 strategy which minimises the transaction burden for day-to-day grant management processes and simplifies country and partner engagement with Gavi processes. This should include consideration of the opportunities to streamline Gavi funding windows and of a more streamlined overall structure.

D: RISK

Overview of risk management

Gavi has implemented and institutionalised a comprehensive approach to risk management covering strategic, operational, programmatic, and corporate risks, and has a Board-approved risk policy and risk appetite statement. Gavi’s 2022 annual Risk & Assurance Report assessed the most critical risks that could potentially have an impact on the ability of the Gavi Alliance to achieve its mission and strategic goals. As outlined in output 6, in 2022, Gavi’s overall risk profile remained highly dynamic, with three strategic risks related to country management capacity, sustainable transition and insufficient demand rated as very high and 15 strategic risks rated as high. Only one risk exposure related to country management capacity was deemed to be outside of Gavi’s updated risk appetite with intensive mitigation ongoing.

Gavi has structured its risk management and assurance functions around a best practice "three lines of defence" model. A dedicated "risk function" coordinates, facilitates and monitors the implementation of effective risk management practices across the Alliance. The Secretariat’s Risk Committee, chaired by the CEO with senior leadership from across the organisation, systematically reviews the top risks allocated to risk owners in the organisation. Risk is a standing item on the agenda of all Gavi Board meetings, and the Audit and Finance Committee (AFC) of the Board oversees the effectiveness of risk management systems and processes. Gavi’s risk management and assurance model has matured substantially in the previous years, and it is now strongly embedded within its overall strategy.

The small risk team of three people works to embed risk management into overall team performance measures and objectives and to address growing demands from business. Increased uncertainty, complexity, funding and change in Gavi require increasingly robust risk management. To this end, a newly elevated Chief Ethics, Risk and Compliance Officer (CERCO) position was created – with the new CERCO being onboarded mid-May 2023, and two new full-time positions are being recruited in addition to the hiring of a temporary position on the COVAX budget in early 2023.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency.

Gavi have continued to performed well across delivery, commercial and financial aspects including on economy and efficiency. An updated MOPAN review of Gavi is currently underway and expected to complete in early 2024, and FCDO has been engaged in the consultation process.

Commercial: Gavi’s market shaping priorities have focused on improved market sustainability and long-term market competition. Stronger competitive dynamics in markets have led to a decrease in weighted average price (WAP) per dose of Gavi’s top five vaccines by value by approximately 6% from 2021 to 2022, translating into improved VfM. Greater cost savings can be achieved if Gavi implementing countries choose to adopt a greater number of products from some of the newer market entrants with the lowest prices. Gavi have launched a workstream on healthy demand to better understand how countries optimise product choices and prioritise antigen programmes, and how these processes impact long-term market health, supplier sustainability, and resulting financial implications for countries and donors.

Co-financing: Another critical area of delivery is Gavi’s co-financing and transition policy. Countries contribute a proportion of vaccine costs regardless of economic status and this increases as countries’ economies grow. Gavi has maintained co-financing despite the challenging global economic period, with countries contributing US$162m in 2022. On transition, 19 countries have successfully transitioned from Gavi support. Co-financing and transition policies were driven in part by Gavi’s strong focus on country ownership, advocacy, and resourcing. The global context has changed significantly from the period in which the original co-financing and transition policies were designed over a decade ago. Gavi must now consider intra and inter-country equitability and consider longer-term sustainable transition. The original policies and principles remain relevant; however, Gavi presented adjustments to its Funding Policy to the Board in December 2022 to ensure greater predictability in co-financing and stability in transition.

Organisational VfM: Gavi’s total expenditure for 2022 was US$ 1,683 million, of which overheads were US$ 48 million (2.9%) and programme expenditure was US$ 1,635 million. From an economy perspective, this demonstrates that its Secretariat continues to deliver programmes with low overheads. Gavi’s cost drivers include expenditure on new and underused vaccines (60%); health systems strengthening grants (10%); partners engagement framework (12%); other programmes costs (11%), and operating costs (8%). Efficiency in delivering its outputs is demonstrated by Gavi meeting or exceeding most logframe milestones, as outlined earlier in this review.

Financial Management: Gavi’s financial reporting procedures are in line with internationally recognised best practices, with its financial statements fully complying to the United States generally accepted accounting principles (US GAAP). Annual external audits of Gavi’s financial statements have consistently returned an unqualified opinion. Financial performance is reported through both the Gavi Board, on which we are represented, and the AFC. The Board will review Gavi’s budget and forecast for 2023 based on recommendations from the AFC.

Gavi Finance team maintains a Risk and Control Matrix (RCM) which identifies key finance risks. Mitigation controls are identified and monitored quarterly. This RCM serves as a key tool for managing risk and ensuring compliance to policy and procedures.

In addition, Gavi has strengthened its internal financial management reporting with improved performance-based reporting produced monthly, reviewed by the Senior Management Team on a quarterly basis, including actions required to mitigate any performance gaps or emerging issues. Further, at the request of the AFC, from the 2022 Financial Year, enhanced financial management reporting will be presented to the AFC.

Monitoring: The effectiveness of Gavi programmes is regularly monitored via the Gavi 5.0 Measurement Framework. Most indicators in the log frame are based on the 5.0 Mission and Strategy indicators approved by the Gavi Board, which are reported to the Board biannually. For Gavi 5.0, several of these same indicators are cascaded down into the country-level monitoring of Gavi’s grants, thus ensuring coherence from country to portfolio level. Performance monitoring of country progress occurs through the High-Level Review Panel (HLRP) and Gavi programmatic teams regularly review operational and strategic progress. We monitor Gavi’s performance through active participation in Gavi’s formal governance structures. This includes membership of the Gavi Board and participation in several committees including the PPC, AFC, Market Sensitive Decisions Committee and the Partnerships Team. In 2023 the HLRP and the Partnerships Team will be merged into the new Alliance Partnerships and Performance Team.

Date of last narrative financial report	28 June 2023 (link)	Date of last audited annual statement	27 June 2023